## Annual Review Template

Title: Supporting Moldova’s Resilience (Moldova – Growth, Resilience and Opportunities for Well-being (M-GROW) Program)
Programme Value £ (full life): £ 9 million		Review date: 19/01/2026
Programme Code: [AMP ID#] 400027	AMP start date: 19/10/2023	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Overall programme risk rating	Minor	Minor

DevTracker Link to Business Case:	D0004521.odt
DevTracker Link to results framework:	D0005442.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The programme supports Moldova’s energy security, economic and governance reform, as part of wider efforts to boost the resilience of the Moldovan economy and society to malign influence and external crisis, in particular Russia’s war in Ukraine. The programme aims to develop opportunities for formal employment, improved human capital and increased resilience to crisis and climate change, supporting Moldova on its path towards European integration. It is delivered by partnering with the World Bank (WB) through the country-focused Umbrella Multi-Donor Trust Fund (MDTF) Programme “Moldova – Growth, Resilience and Opportunities for Well-Being” (M-GROW). The World Bank MDTF M-GROW programme is designed as a flexible instrument to provide grant support for Moldova’s reform and competitiveness agenda and critical investments over the next 5 years.

The review period for this annual review was marked by significant uncertainty in terms of Moldovan parliamentary elections, pauses and reductions in FCDO development assistance, changing UK strategic prioritisation, and significant changes in the international funding environment. Moldova continues to be a priority for HMG as a key partner in tackling Russian malign influence on the world stage. M-Grow is a key component of efforts to tackle fragility and support long-term resilience within this context.

Summary supporting narrative for the overall score in this review

The M-GROW programme has met the expected outputs for FY 2024–25. All UK-supported projects under M-GROW recorded progress compared to the previous year, though success levels varied across workstreams, as a result of some delays in grant and loan agreements between GoM and WB. M-Grow demonstrates a high level of value of money, especially the activities that directly contribute to Moldova’s EU integration effort, and it benefits from a high level of government buy-in.

Major lessons and recommendations for the year ahead

The Annual Review highlights the following key lessons:
1. The participatory approach, while requiring more time and effort, fosters ownership and sustainability. Effective communication between the WB and recipient institutions, and coordination amongst institutions, remain critical for timely and effective delivery. Regular and ad hoc technical meetings help refine methodologies, improve coordination, and enhance data sharing.
2. Flexible sequencing and strong coordination have been crucial in adapting work plans to evolving institutional priorities, ensuring timely and relevant support.
3. Close donor coordination is essential to avoid duplication, deliver effectively and maximise impact, given the breadth of the EU reform agenda and the absorption capacity of recipient institutions.
4. Institutional restructuring has created gaps in expertise and operational readiness. Limited and still-developing capacity may slow programme delivery and necessitate more targeted, sustained capacity-building support.
5. FCDO’s active engagement has accelerated programme delivery and decision-making, welcomed by stakeholders across WB and recipient institutions. Careful MEL, clear target-setting, and monitoring have proven strong incentives.

Based on the review findings and lessons learned, the following recommendations are directed to the FCDO and M-GROW management teams:
1. Given its strategic relevance in bolstering Moldova’s economic resilience, advancing the reform agenda and EU accession plan, the review recommends continuing UK funding for the M-GROW Programme in close coordination with other donors and government stakeholders.
2. Ensure well-coordinated oversight amongst donors and M-GROW stakeholders to foster effective delivery and maximise programme impact.
3. Maintain active monitoring and engagement with the WB and government counterparts to ensure timely and high-quality delivery. This should include careful consideration of the modalities for bank-executed and recipient-executed programming.
4. Prioritise enhancing the M-GROW Results Framework rather than maintaining two separate results frameworks. The Programme would benefit from defining contextual and causal assumptions that explain its operational and strategic logic (the COM-B Model may be useful).
5. Encourage WB to improve internal and external communication of programme performance in a consistent and coherent manner. Raising public awareness of the importance and achievements of the programme can contribute to broader societal and institutional resilience objectives.
6. Ensure cybersecurity considerations are integrated into relevant programme interventions and coordinated across respective state institutions.
7. Maximise impact by fostering collaboration and synergy with other relevant interventions across the programme, particularly the STEEM project.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme’s high-level theory of change (ToC) is underpinned by M-GROW Umbrella Trust Fund theory of change. The overall intended impact is a “Moldovan economy and society that is more resilient to economic shocks and malign economic influence”[1]. This is to be achieved through increased opportunities for formal employment, improved human capital and increased resilience to climate change and crises. Programme ToC groups programme outcomes under two broad pillars of support: critical project investment (pillar 1) and institutional strengthening (pillar 2).
[1] 1 This aligns to the intended impact and three high-level outcomes of the World Bank Moldova Country Partnership Framework (FY2023-FY2027), the UK country business plan objectives in Moldova and the intended impact of the Good Governance Fund in Moldova, which is also contributing to the above-mentioned impact through a range of interventions.

Under pillar 1, M-GROW will help Moldova to make critical new investments or expand existing projects to boost competitiveness and advance green, resilient and inclusive development, aided by efforts to enhance technical and operational capacity. This pillar will also be supported through the provision of analytics, implementation support and targeted technical assistance and capacity building to enhance delivery capacity. The following three outcomes feed into Pillar 1 and define key areas the programme intends to contribute to:
- Outcome 1.1. Increased competitiveness of Moldova’s enterprises
- Outcome 1.2. Increased quality and accessibility of public services
- Outcome 1.3. Expansion of green and resilient infrastructure and investments
Under pillar 2, M-GROW will support development policy financing and deeper technical assistance (TA) and capacity building. It will support the Moldova’s policy and institutional reform agenda, toward implementing well-funded, coherent, and coordinated advances in the country’s competitive, green, resilient, and inclusive development. This will focus on relevant data and analytics, and capacity to strengthen institutions and policy framework for EU accession readiness, including broader reform efforts. Activities under the two pillars aim to support Moldova to navigate short-term shock, while keeping a clear focus on pursuing the country’s longer-term reform and growth objectives. With this purpose, the programme intends to achieve the following outcomes:
- Outcome 2.1. Decreased regulatory burden of Moldovan enterprises
- Outcome 2.2. Enhanced institutional capacity for service delivery and management
- Outcome 2.3. Increased institutional capacity for infrastructure and sustainable development
The M-GROW Umbrella Trust Fund currently delivers six projects contributing to the overall programme ToC and logical framework, with the UK fund supporting four of them, namely:
1. Support to Sustainable Transition Through Energy Efficiency and Security in Moldova (STEEM)
2. Moldova Small and Medium-Sized Enterprise (MSME) Competitiveness project
3. Enhancing the Competitiveness and Transparency of the Financial Sector in Moldova (Financial Sector)
4. Supporting Public Procurement Efficiency and VfM project (Procurement).
The M-GROW ToC and logical framework have not changed since the inception of the programme. It will benefit from periodic review and update of key elements in line with work planning and reporting, thus allowing the programme to adapt to changing conditions and align with the government’s programmes and priorities.

The FCDO employs its ToC and Results Framework to monitor and assess programme performance against the HMG priorities in the country. The impact and outcome statements in the FCDO ToC are largely aligned with the M-GROW ToC but require a minor update to reflect the current strategic logic of the UK’s contribution. This Annual Review applies the FCDO ToC as its guiding framework.

The ToC logic remains valid. The outcome of the September 2025 election has meant a recommitment to Moldova’s EU integration, anchoring Moldova firmly on its pro-democracy path. In order to join the EU, Moldova must harmonise its legislation in line with the EU acquis. Many of the activities under M-Grow directly support the adoption and implementation of EU standards.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The M-GROW programme has met the expected outputs for FY 2024–25. All UK-supported projects under M-GROW recorded progress compared to the previous year, though success levels varied. The Enhancing Competitiveness and Transparency of the Financial Sector in Moldova project achieved the most significant results, while the Public Procurement Efficiency and VfM project experienced substantial delays, resulting in the least tangible outcomes amongst all projects under review.

There were some delays at the start of the FY in terms of agreeing financing conditions with the Ministry of Finance, in terms of loans to Termoelectrica and grant support on the procurement work. There were also some delays in putting together evaluation committees for the STEEM project. These set both projects back by a few months, with potential knock-on impacts for the year ahead. The STEEM project in particular is limited seasonally, so delays in this workstream can have significant impacts. The recipient-executed nature of this work necessitates a high level of consultation and negotiation, and we are aware that the World Bank has taken some actions to make up lost time. However, upcoming crunch points where additional delays may be possible include the tendering and awarding process for the procurement centralisation contract – we should monitor progress closely here with the World Bank.

## C. DETAILED OUTPUT SCORING

Output Title	World Bank MDTF delivers on HMG and Government of Moldova priorities towards growth and resilience.
Output number:		1	Output Score:	A
Impact weighting (%):		90	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Annual work plan reflecting HMG and Government of Moldova priorities endorsed and reviewed by PC.	Milestone is not set	A – met expectations
1.2 Number of projects/grants under implementation that are meeting agreed results framework indicators.	Milestone is not set	A – met expectations for all four UK co-funded projects

Briefly describe the output’s activities and provide supporting narrative for the score.

The M-GROW programme has met the expected outputs for FY 2024–25. All UK-supported projects under M-GROW recorded progress compared to the previous year, though success levels varied. The Enhancing Competitiveness and Transparency of the Financial Sector in Moldova project achieved the most significant results, while the Public Procurement Efficiency and VfM project experienced substantial delays, resulting in the least tangible outcomes amongst all projects under review.

The programme assessment using the RAG (Red, Amber, Green) rating system, along with a detailed account of output results for each project, is provided below.

Table 1: M-GROW Project Progress Assessment RAG Rating
#	M-GROW Project	RAG
1	Support to Sustainable Transition Through Energy Efficiency and Security in Moldova (STEEM)	Amber
2	Moldova Small and Medium-Sized Enterprise (MSME) Competitiveness project	Green
3	Enhancing the Competitiveness and Transparency of the Financial Sector in Moldova	Green
4	Supporting Public Procurement Efficiency and VfM project	Amber

The project Support to Sustainable Transition Through Energy Efficiency and Security in Moldova (STEEM) intends to enhance energy efficiency (EE) in existing public buildings and district heating sector in Moldova and provide immediate and effective response to an eligible crisis or emergency. The project is currently in its early delivery stage and has been assessed as Amber. This rating reflects significant delays in implementation, limited understanding of the local context (including national audit standards, availability and capacity of certified auditors, and procurement processes), as well as delayed coordination with related interventions such as the “model schools” initiative. These factors have collectively impacted the pace, quality and VfM of project delivery.

During the review period, the following progress has been achieved:
Component 1: Energy Efficiency (EE) Upgrade in Public Buildings
- Energy Audits: Phase 1 audits for 10 schools are nearly complete, with M-GROW submitting a two-page report. To compensate for early delays, the Ministry of Energy’s Project Implementation Unit (MEPIU) and the Ministry of Education added detailed audits for six donor-financed model schools. Phase 2 will cover 12 more schools, aiming for audits of 46 schools in total, selected by the Ministry of Education.
- District Heating Modernisation: M-GROW supported early outputs for the Options Assessment, including Termoelectrica’s (TE) financial model, market projections, and draft assessments. The tender for 203 Individual Heat Substations (IHS) is nearly finalised, with installation planned for summer 2026.
- Internship Programme: The first six-month cohort to promote female participation in energy has begun, with three interns placed (one dropped out from the initial four). Partner companies are expected to hire them after completing the programme. The second cohort with a larger group is expected to start in spring 2026.

Component 2: TA, Capacity Building, and Implementation Support
- NISEEB Procurement: M-GROW is financing the procurement of the National Information System for Energy Efficiency in Buildings (NISEEB), a key EE decision-making tool. Procurement is expected by December 2025, with implementation by end-2026. An environmental impact assessment is underway to inform NISEEB.
- Institutional Capacity Building: M-GROW is strengthening the National Center for Sustainable Energy (NCSE) through targeted support. In April 2025, NCSE staff attended the IEA’s 20th Energy Efficiency Policy Training Week. In November, NCSE, MEPIU, and Ministry of Energy staff joined a multi-day programme on EE and resilience in Vienna. Moldova also participates in an EE knowledge exchange forum to enhance institutional learning.
- TE Capacity Building: Drafts of a financial analysis, financial model, combined heating options, and a management restructuring plan have been submitted to the Steering Committee chaired by the Ministry of Energy. TE supplies electricity to 0.5 million people in Chisinau, underscoring its social impact.

The Moldova Small and Medium-Sized Enterprise (MSME) Competitiveness project aims to boost competitiveness by strengthening the competition framework, improving investment policies and streamlining inspections and permits for MSMEs. Key progress achieved under this project is as follows:
Component 1: Digitalisation and Regulatory Reform - Scaling up Government to Business (G2B) Services
- The GoM and WB teams developed tools, guidelines, and training to advance digitalisation. M-GROW adapted activities to meet institutional needs, providing technical assistance for ToR development and highlighting potential risks. The digital system is designed to remain flexible for legislative changes.
- A concept for an Integrated Catalogue of Investment and Business Procedures was endorsed by the Ministry of Economic Development and Digitalisation (MoEDD) and the e-Governance Agency (eGA), laying the groundwork for a streamlined user experience.
- M-GROW supported agile policymaking guidelines, the Investment Facilitation for Development Agreement (IFDA) assessments, and capacity-building for MoEDD and eGA on IFDA and WTO tools. Pilot assessments of priority IFDA articles were completed. Professional development tools were delivered to the State Chancellery and regulators, covering risk-based inspections, complaints management, checklists, and training frameworks.
- The e-permit system managed by eGA exceeded targets: 65% of businesses updated online. Currently, 103 online services are available, surpassing the initial G2B target of 100 services.

Component 2: Investment Policy - Advancing Investment Legal Framework and Strengthening Investment Agency
- A comprehensive capacity-building programme for Invest Moldova Agency (IMA) was developed, informed by a rapid institutional assessment with actionable recommendations. An onboarding/offboarding guide was introduced to address staff turnover and ensure continuity. Support expanded to investor aftercare and lead generation. Enforcing institutionalisation remains a priority.
- M-GROW assisted the GoM in strengthening the legal framework for investor screening. The WB clarified the importance of screening mechanisms for investor security while addressing country-specific legal uncertainties.
- Building on a prior legal review, the team supported MoEDD in aligning investment-related laws, such as the Law on Examining Investments of Importance for State Security, with EU standards.

Component 3: Competition Policy
- New regulations on state aid and merger control are being developed, introducing simplified notifications for low-risk cases to streamline decisions and reduce administrative burden. M-GROW provides substantial expert support for drafting a new State Aid Law and regulatory framework.
- An enhanced state aid registry and Product Market Regulation (PMR) indicators were developed in partnership with OECD, informing an ongoing comprehensive competition assessment. The goal is full compliance with EU standards.
- M-GROW delivered targeted capacity building for the Moldova Competition Council (MCC) and partnered with the EU Twinning Project to support EU integration. MCC staff received case-based training in merger control, cartel investigations, and state aid. Following the training, MCC applied new approaches to market tests, tailored activities for smaller companies that might be affected by the merger and improved unannounced inspection practices. Positive feedback highlighted M-GROW’s expert pool, including UK specialists.
- MCC completed a complex screening review process, marking a significant milestone.

The project Enhancing the Competitiveness and Transparency of the Financial Sector in Moldova contributes to legal updates, capacity building, software upgrades and development of the National Financial Inclusion Strategy (NFIS). Key progress during the review period across the three components of this project is summarised as follows:

Component 1: Resilience of financial sector by strengthening the Deposit Guarantee Scheme (DGS)
- M-GROW provided technical assistance to the Financial Group for Development and Stability Board (FGDSB) to strengthen its Deposit Guarantee Scheme (DGS), resulting in improved regulatory and operational frameworks, including approved internal audit and target fund ratio regulations.
- FGDSB advanced negotiations on liquidity and fiscal backstops with the National Bank of Moldova (NBM) and Ministry of Finance, though policy challenges have delayed finalisation. FGDSB continues applying NBM risk categories.
- The Management Information System (MIS) is well progressed, with procurement nearly complete and implementation planned for October 2026.
- M-GROW has enhanced financial sector resilience through capacity-building on fiscal arrangements, MIS, stress testing, coverage analysis, internal audit, and risk frameworks.

Component 2: Financial Inclusion and Access to Finance
- Significant progress has been made on the National Financial Inclusion Strategy (NFIS) since the diagnostic note in April 2025. M-GROW supported the inter-ministerial working group led by NBM and organised capacity-building workshops, resulting in approval of the NFIS Concept in August 2025. The strategy reflects a clear vision and objectives based on data mapping and stakeholder analysis. M-GROW also assisted NBM in drafting the action plan, which aligns with Moldova’s EU reform agenda.
- Developed through a consultative process, NFIS engaged over 80 stakeholders, including state agencies, banks, non-banking institutions, savings associations, CSOs, and experts. This participatory approach identified new actors, such as the diaspora, and uncovered vulnerabilities that strengthened planning and risk assessment. Public presentations are planned before Parliamentary approval (expected July), supported by a communication plan to raise awareness and promote engagement.
- Under Financial Consumer Protection, key regulatory and supervisory gaps were identified, with recommendations for improved coordination between NBM and NCFM.
- Oversight of Savings and Credit Associations (SCAs) transferred to NBM, accompanied by a draft roadmap and legislative amendments pending internal decisions. Given the large number of SCAs (1,400), NBM plans consolidation, with M-GROW providing diagnostics and policy options to guide the strategy. Capacity-building and technical assistance have been critical in this new area for NBM.

“The development of Moldova’s first National Financial Inclusion Strategy 2030 has been profoundly strengthened by the World Bank Group’s guidance, provided under the projects supported by the M-Grow Trust Fund. Their structured expertise helped us transform a complex reform agenda into a coherent, realistic and impactful strategy – one that advances financial inclusion, supports sustainable economic development, and delivers tangible benefits to citizens across the Republic of Moldova.”
- Anca Dragu, Governor of the National Bank of Moldova

Component 3: Financial Infrastructure
- M-GROW worked with the MoEDD to draft amendments to the Insolvency Law, which were approved by Parliament in December 2024. A diagnostic identifying gaps with the EU Directive was delivered in March 2025. The WB also supported MoEDD in assessing alignment with the EU Restructuring Directive, a key component of Moldova’s EU accession agenda. Despite leadership changes within MoEDD, implementation is now on track.
- M-GROW has also supported the MoJ in addressing gaps in secure transactions and modernising collateral and insolvency registries. The ToR, Concept Note, and a draft Collateral Registry Law are currently under MoJ review.

The Supporting Public Procurement Efficiency and VfM project aims to improve public procurement reform through development of an e-procurement system to enhance transparency and efficiency implementation of a centralised procurement model for frequently purchased goods. Progress has been slowed by delays in approvals on the recipient side, thus the project is in its early stage of delivery (effective since May 2025) and has been assessed as Amber. The project is closely aligned with Moldova’s Reform Agenda under the EU Growth Plan, where the creation of a new e-procurement system and the establishment of central purchasing bodies are critical milestones. During the review period, the following progress has been achieved across its two components:

Component 1: Redevelopment of electronic procurement system
Moldova’s current e-procurement system offers limited functionality, requiring manual processing of around 40,000 documents - a time-consuming process that also hampers efforts to detect conflicts of interest or corruption. To address these gaps, a new Modular System, supported by M-GROW, is being developed to cover the entire procurement cycle, from planning to contract signing, offering capabilities beyond those in many EU countries. The system will integrate approx. 50 functionalities (e.g., fiscal, payment modules) and allow phased implementation as each module is completed. Consolidating all procurement functions will strengthen the detection and prevention of corruption schemes.

M-GROW has provided extensive technical assistance in drafting the ToR through a participatory process involving the MoF, e-Gov Agency, Public Procurement Agency, STISC, and national experts in over 15 stakeholder meetings. Cybersecurity requirements have been embedded in the ToR, and STISC will maintain the system. The contract for business process mapping and technical specifications was signed in July, with bidding launched in November 2025. The developer contract is expected in January 2026, with 18 months allocated for development. The system is planned to be fully operational by 2027. However, due to the significant delays throughout the project implementation and the time required to develop the e-procurement system, M-GROW may need to revisit and adjust the project deadlines.

Component 2: Promoting a unitary policy and conducting procurement for economic and social efficiency
- With M-GROW’s technical assistance, an in-depth analysis identified 11 categories suitable for centralised procurement, supported by a comparative review of European models. Stakeholder consultations in June informed implementation scenarios. In September, a list of interested pilot institutions was submitted to the MoF and the Public Procurement Agency. MoF will determine the most appropriate centralised procurement model for Moldova.
- MoF has decided to establish three regional procurement offices alongside the centralised unit as part of the decentralisation strategy.
- Several training sessions were held for local and central authorities, focusing on shifting from compliance-based monitoring to a strategic, VfM approach in public procurement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes in programming were observed during the review period, apart from revising the timeframes of the project deliverables, primarily due to the slow start in 2024. The Parliamentary elections in September 2025 and changes within recipient institutions were major factors influencing programme delivery. Adjustments to deadlines and risks should have been communicated more effectively to the donor community and documented in the change log. Most targets and milestones are set in the M-GROW Results Framework, and the review recommends finalising all remaining milestones. Recommendations for the FCDO Results Framework are covered in the MEL section.

Output Title	World Bank MDTF activities support gender equality and social inclusion.
Output number:		2	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of projects informed by GESI analysis.	Not set	A – met expectations
2.2 Number of projects monitoring gender and social inclusion.	Not set	A – met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

The M-GROW programme is assessed against gender and social inclusion (GESI) dimensions across all activities. The design of both the overall programme and individual M-GROW-supported projects draws upon the Moldova Country Gender Assessment conducted in 2022 by the Bank and UN Women, as well as sector-specific gender analysis. All four UK-funded projects commit to monitoring gender impacts, and most prioritise citizen engagement. M-GROW employs several indicators to monitor GESI related progress (see Table 2) and reports annually (e.g., AR 2023–24, AR 2024–25).

By design, two projects (STEEM and MSME) apply more comprehensive GESI lenses (Table 2). For example, STEEM project supports an internship programme for female engineers in participating energy sector institutions. During the reporting period, three interns were placed in private companies, which are expected to hire them upon completion. A second, larger cohort is planned for spring 2026. The programme could be strengthened by embedding additional capacity-building support to improve onboarding and increase employment prospects of female engineers with host companies.

GESI considerations have been incorporated into the National Financial Inclusion Strategy (NFIS). The participatory design process of the Strategy focused on the specific needs of women, persons with disabilities (PwD), different age groups, and rural communities. Consultations included the Ministry of Labour and Social Protection, as well as organisations representing diverse groups, including UN Women. These inputs shaped the definition of financial inclusion and key pillars of the Strategy. However, all consultations were held in Chisinau, which limited geographic inclusivity. The M-GROW Annual Work Plan 2025 and Annual Report 2024–25 provide a detailed account of GESI commitments and progress.

Table 2: M-GROW Cross-Cutting Indicator Review, Annual Report 2024-25
GESI Questions	STEEM	MSME	Procurement	Financial Sector
Will this grant undertake or draw upon existing gender analysis?	Yes	Yes	No	No
Will the grant activities include specific gender actions?	Yes	Yes	No	No
Will the grant activities monitor gender impacts?	Yes	Yes	Yes	Yes
Will the grant activities include specific actions related to refugees and forcibly displaced persons?	Yes	Yes	No	No
Will this grant include citizen engagement?	Yes	Yes	Yes	No

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes were recorded during the review period. Additional capacity-building support is recommended to improve women's onboarding into the host companies as part of the internship programme. The internship programme remains the primary activity aimed at promoting gender equality in the male-dominated energy sector. However, it can be better embedded into the programme strategic logic. A review of the M-GROW logical framework is advised to further systematise and streamline GESI monitoring and reporting.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The programme team has not previously had a tracker or action plan for monitoring progress against recommendations. However, some progress can be observed on recommendations from the previous AR: e.g. the securing of support from FCDO Economic and MEL Advisers (although no Climate and Energy Adviser support has been secured). There were a number of recommendations around MEL that are still relevant; see MEL section recommendation on simplifying results frameworks. In January 2026 programme team will meet to assess programme’s viability and sustainability for further HMG funding, based on its progress, periodic deliverables and achievements, (previous AR scheduled this by November 2025). The outputs of this AR will inform that decision. This year’s recommendations are set out in Section A. The programme team should track progress against these.

D: VALUE FOR MONEY

Key cost drivers and performance

M-Grow delivers projects and technical assistance activities that strengthen institutions, promote sustainable growth and support Moldova’s regional integration. M-Grow’s activities address 20 out of the 155 reform activities required as part of EU accession. Through its projects and TA support, a relatively small contribution to M-Grow has the potential to unlock significant growth for Moldova, boosting living standards and its economic resilience to external threats. It is estimated that with EU accession Moldova could double the size of its economy in 10 years, a potential increase of around $18 billion. It’s difficult to isolate the impact of M-Grow on Moldova’s EU accession chagces, but for illustrative purposes, if the activities under M-Grow contribute just 1% towards these potential benefits of Moldova’s EU accession, return on the UK’s initial £9m investment is around 19%.

Economy: The UK has been a founding contributor to M-Grow, and our early commitment and steering of M-Grow has been effective in crowding in additional funding, which was apparent this financial year as Austria and Ireland joined as donors. An even more important aspect of M-Grow’s VfM is how donor contributions can leverage additional private capital. For example, the $5m contributed from M-Grow to the Sustainable Energy Efficiency in Moldova project (STEEM) was augmented by a $50 m contribution from the World Bank’s IBRD, which issues bonds in global capital markets. Similarly, M-Grow has contributed $1million (around £750,000) to the MSME competitiveness project, a very small fraction of the total $156 million secured for the project. This suggests a very high level of VfM in terms of economy, as the project was able to crowd in a significant amount of additional funding.

Efficiency: The results of the annual report give some indications of efficiency within M-Grow’s activities, under the “capacity building for increased competitiveness of Moldova’s enterprises” output, 9 trainings were delivered for 8 institutions, whereas the end target indicator for 2029 was for 5 trainings to be delivered for 6 institutions. The M-Grow business case included an example indicator of include unit cost of outputs and timeliness of output delivery: the MSME competitiveness delivered around 11 analytical tools and 10 trainings at a cost of around £30,000 per activity.

Effectiveness: In terms of the type of activity conducted as part of M-Grow, FCDO’s Best Buys evidence suggests that National level policy advice and technical assistance to promote pro-growth policies can have very high returns when effective. This evidence suggests that it is only effective when there are local champions for change and capacity to implement. Much of M-Grow fits in this category given the high level of buy-in from the government and recipient-executed nature of the funding, combined with deep technical knowledge and access afforded by the World Bank. An important risk factor is capacity for implementation (the Best Buys research warns against funding reports that ‘just sit on shelves’).

From the annual reporting, there is already some good progress against outcome indicators outcomes 1.1, 1.2 and 2.1. This largely reflects good progress across the SME competitiveness, financial sector, and public procurement lines of activity. Some areas have exceeded their intended outputs including in the public procurement pillar, e.g. number of G2B services digitalised target was for 105, but is now at 133. There has been less progress across other indicators, representing poorer value for money in disbursing funds this FY, e.g. Outcomes 1.3, 2.1.1 and 2.2. For some of these, it is realistic to expect these benefits to materialise over the medium term as regulatory and competition changes are implemented. However, there have been some delays affecting the project’s effectiveness, especially in the STEEM component, where there were delays around the signing and internal processing of the grant agreement between the World Bank and Ministry of Finance. Reporting against the Growth and Resilience DPO is not yet available (Implementation Completion and Results report due in June 2026).

Equity: As noted in Results section under Output 2, the M-GROW programme is assessed against gender and social inclusion (GESI) dimensions across all activities.

Assessment of whether the programme continues to represent value for money

M-Grow demonstrates a high level of value of money, especially the activities that directly contribute to Moldova’s EU integration effort. Despite this still being a relatively early stage of the project, the results framework already shows some progress across many indicators. The MSME competitiveness and financial inclusion projects in particular demonstrate a very high level of value for money. There are, however, some areas where delays and bureaucratic holdups have limited progress as expected, in particular for the STEEM component.

E: RISK

Overview of risk management

Risk rating
The most significant risk to programme delivery in the past year has been around delays in agreeing grant and loan conditions with the government of Moldova. There were also risks in the political and operational context around the September 2025 election. Potential risks for the next year include:

- Strategy and context risk: Regional dynamics, particularly Moldova’s vulnerability to the ongoing war in Ukraine and domestic energy crises, pose significant risks. In addition, there are governance risks related to the political environment: frequent leadership changes within recipient institutions (e.g., three ministers in the past year) have the potential to create uncertainty, slowing the pace of reform.
- Policy and programme delivery risk: Potential delays in tendering and system design for procurement project may require an extension of the project timeline. The final contract value could exceed the allocated budget. Another risk in this category is around capacity: High reform pace under EU accession commitments is commendable, but effective operationalisation requires stronger institutional capacity, including around staffing and budget. Limited and still-developing capacity may slow programme delivery and necessitate more targeted, sustained capacity-building support.
Despite these, we consider that the overall risk rating for the upcoming year is less than or equal to that of the previous year as there is a higher level of political certainty, and the inception grant and loan agreements are now already in place. This is reflected in the World Bank’s own assessment, where Overall Risk is assessed as Moderate down from Substantial. This is driven by Strategic Risk being reduced from Substantial to Moderate. Stakeholder risk remains as Substantial and Financial risk remains as Moderate.

Monitoring risk
Risks are managed primarily by the World Bank. The World Bank has an institution-wide Risk Framework at country, portfolio and project level to manage and mitigate risks in its operations. It Bank screens the risk ratings at several stages in operation preparation and continues to closely monitor and adjust them during implementation which form the basis for management reviews and corrective decisions, where appropriate.

The World Bank’s approach to monitoring, managing and communicating risk could be strengthened. Donors are not provided with regularly updated risk registers and WB was reticent in sharing details of the delays in finalising loan and grant agreements. According to previous ARs, BE Chisinau has had the opportunity to feed in and review the programme risk register at least quarterly – this doesn’t always happen in practice.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The M-GROW programme delivery and governance is dictated by the Administration Arrangement signed between FCDO and IBRD/IDA concerning the Moldova Growth, Resilience and Opportunities for Well-Being (M-GROW) Programme Multi-Donor Trust Fund (Trust Fund No. TF074062), including its Annex 1.

According to WB, its role in M-Grow Management is to:
- Organise annual progress meeting by preparing the M-Grow annual report in collaboration with individual project teams on the GoM and Bank side
- Implement the M-Grow information strategy by holding additional progress and update meetings and other information events, maintaining the dedicated M-Grow page
- Keeping stakeholders regularly informed on key decisions remotely
- Managing the finances and updating key financial data monthly
- Ensuring a smooth communication flow between all the stakeholders on the Government, Bank and development partner side.
The Annual Report 2025 was reasonably detailed, highlighting programme results and benefits quantitatively and qualitatively, including showcasing the results through beneficiary voices. Programme communication with donors in general tends to focus largely on official press releases, high-level communications to donors from the Bank’s senior management on programme-related events. Following donor calls for additional reporting, the WB provides a monthly newsletter, which includes headline updates including announcement about additional donor funding, events and workshops held. WB colleagues are visible and accessible to donors and meetings are fairly frequent.

Given the centrality of many aspects of M-Grow to Moldova’s growth and reform agenda, however, in order to raise its visibility and impact, we would like to see the WB further improve internal and external communication of programme performance in a consistent and coherent manner (as per recommendation 5). Raising public awareness of the importance and achievements of the programme can contribute to broader societal and institutional resilience objectives. We would also like to see more frequent quantitative reporting against benchmarks.

On the FCDO side, the programme oversight has been impacted by management changes in SRO and PRO. Programme teams should clarify roles and responsibilities internally.

G: MONITORING, EVIDENCE AND LEARNING

The M-GROW programme employs a standard Monitoring, Evaluation and Learning (MEL) system, guided by a ToC and operated through a logical/results framework. The ToC effectively reflects the strategic logic and key objectives of the programme; however, it would benefit from a clearer articulation of the causal pathway, showing how anticipated changes progress from outputs to outcomes.
The Logical Framework is well-established, comprising mainly quantitative indicators that are relevant and measurable within this context. Qualitative measurement systems could be further developed to capture changes in the capacities and capabilities of recipient institutions. Milestones and targets have been set for most indicators and are actively used by both the WB and recipient institutions as checkpoints to support timely programme delivery. While the high-level assumptions underpinning the ToC are useful, they could be strengthened by defining causal assumptions that explain the operational and strategic logic in greater detail.

The reporting system is aligned with the M-GROW logical framework, enabling effective tracking and monitoring of programme performance against outputs and outcomes. Programme implementation is guided by an annual work plan, discussed and agreed at the annual Partnership Council meetings, co-chaired by the Government of Moldova and the WB, with participation from the donor community. The WB submits an Annual Review report to the Partnership Council (AR 2023-24, AR 2024-25), complemented by bi-annual progress updates and quarterly informal updates, which together provide a robust monitoring structure. In addition, the FCDO commissions an Annual Review as an internal monitoring mechanism to assess progress and inform decision-making.

A final evaluation of the M-GROW programme is planned upon closure. In the meantime, an independent mid-term evaluation is recommended to provide a rigorous assessment of outcomes and key achievements, and to support ongoing learning and adaptation.

The FCDO applies its ToC and Results Framework to monitor and assess programme performance against HMG priorities in the country. The impact and outcome statements within the FCDO ToC are broadly aligned with the M-GROW ToC. They require a minor update to reflect the current strategic logic of the UK’s contribution. Respectively, the Results Framework could be further developed to better capture the complexity of the programme at the output level. Baseline data, milestones and targets can be established retrospectively to enable more robust monitoring of progress achieved. A key caveat is that, due to the nature of a multi-donor trust fund, it is challenging to assess the effectiveness of the UK’s contribution.

While these suggestions may strengthen the FCDO Results Framework, the review found limited added value in maintaining a separate results framework for this programme. Instead, we recommend prioritising collaboration with other donors and the M-GROW team to enhance the Programme Results Framework. Key considerations for this recommendation are as follows:
1. The M-GROW Results Framework more accurately reflects the complexity of the programme.
2. Programme reporting is already aligned with the M-GROW Results Framework.
3. Using a single framework will enable FCDO to collaborate more effectively with other donors and the M-GROW team to improve the MEL system to support effective programme delivery.
4. This approach avoids duplication of effort for the FCDO management team and allows for more efficient oversight of programme implementation.

Date of last narrative financial report	November 2025	Date of last audited annual statement	N/A

Reference List
1. Business Case- Moldova Resilience Programme (MRP)_October 2023
2. M-GROW Administration Agreement_TF074062
3. M-GROW Logframe (FCDO) - June 2024
4. M-GROW RiskLog
5. M-GROW Annual Report (2023-24)
6. M-GROW Progress Update Meeting - May 2025
7. M-GROW 2024 Work Plan updated - June
8. M-GROW 2025 Work Plan updated - March
9. M-GROW Annual Report 2024-25
10. M-GROW Annual Review_FCDO - January 2025