## Annual Review Template

Title: ASEAN-UK Women, Peace, and Security (WPS) Programme
Programme Value £ (full life): £3.43m		Review date: August 2025
Programme Code: 400029	AMP start date: 11 July 2023	AMP end date: 14 June 2026

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A+	A+
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	D0004175.odt (live.com)
DevTracker Link to results framework:	D0004175.odt (live.com)

## A: SUMMARY AND OVERVIEW

Description of programme

The ASEAN-UK Women, Peace and Security (WPS) Programme is part of a new suite of ASEAN-UK programmes designed to support ASEAN-UK Plan of Action (PoA) 2022-2026 implementation and delivery of the UK’s commitments as an ASEAN Dialogue Partner since August 2021. In February 2023, the UK Government launched the National Action Plan (NAP) on Women, Peace and Security for the period 2023-2027. The ASEAN-UK WPS Programme is designed to contribute to the delivery to the UK’s commitments as an ASEAN Dialogue Partner as well as to support achievement of the strategic objectives stipulated in the UK’s NAP on WPS.

The WPS programme aims to strengthen policies that consider the impact of conflict on women and enable greater female participation in conflict prevention, resolution, and recovery. As an ASEAN programme, this programme involves all ten ASEAN Member States (AMS). Two ASEAN states, Singapore and Brunei Darussalam, are not ODA-eligible and activities involving those two countries are supported through non-ODA funds. In addition, this programme also involves Timor-Leste, as an ASEAN Observer State that is on the pathway to accede to ASEAN.

The programme represents the UK’s contribution to the UN Women regional project, “Empowering Women for Sustainable Peace: Preventing Violence and Promoting Social Cohesion in ASEAN (Advancing WPS in ASEAN)”, which has been implemented since 2021. The project is co-funded by the Government of Canada and Republic of Korea and was expanded in August 2023 with UK support. This expansion allows for additional activities of the initial project, including capacity building for ASEAN Secretariat (ASEC) and its relevant sectoral bodies and institutions, technical assistance to targeted AMS to implement WPS agenda in national and local level, support to non-state actors, and the inclusion of activities in Timor-Leste. In September 2024, after the business case addendum, the project is expanding to Cambodia, Lao, Malaysia and further enhancement to Timor-Leste activities.

In addition to contributing to the UN Women regional project, the programme also enabled the ASEAN Institute for Peace and Reconciliation (ASEAN-IPR), as the main ASEAN institution working in peace and reconciliation and the WPS agenda, to deliver WPS training programme for AMS and Observer State officials to enhance their knowledge and capacity in mainstreaming WPS agenda in policymaking. The Accountable Grant agreement was signed in early June 2024. During the review period, two sessions of training has been delivered: Module 0, 1, and 2 for junior to mid-level officials in September 2024, and Module 3 for senior-level officials in June 2025.

This is the second annual review of the ASEAN-UK WPS programme. Data was obtained through desk study of reports from UN Women and ASEAN-IPR. For UN Women activities, given the co-funding nature of the programme, this report will review only the activities funded by the UK within UN Women’s project from August 2024 to June 2025, based on data provided by UN Women. Data was also obtained through interviews with multiple stakeholders, including UN Women programme team, ASEAN-IPR programme team, focal points in relevant UK diplomatic posts, and sample of beneficiaries from government officials and Civil Society Organisations (CSOs) who have participated in the programme activities.

Summary supporting narrative for the overall score in this review

The programme has demonstrated exceptional performance over the past year, meriting an overall score of A+. This reflects not only the successful delivery of outputs but also the programme’s ability to moderately exceed expectations and expand its strategic reach. Training activities received overwhelmingly positive feedback, with the majority of participants reporting improved knowledge, and based on interviews and six-month follow-up surveys, a strong intention to apply what they learned within their institutions.

Importantly, the programme made tangible progress towards its intended outcomes. Evidence from participant feedback and institutional engagement suggests increased capacity and commitment to advancing the WPS agenda across the region. Early signs of behavioural change and policy uptake are visible, particularly in the integration of WPS principles into institutional practices and frameworks.

The programme also successfully expanded its support to Cambodia, Lao PDR, and Malaysia, countries not initially targeted. Notably, in Malaysia, the programme played a key role in strengthening government commitment, culminating in the development of a NAP WPS, which is set to be launched at the ASEAN WPS Summit this year. In addition, the programme supported the establishment of a Community of Practice (CoP), providing a platform for regional actors to exchange knowledge and experiences. Multiple frameworks and strategies aimed at strengthening WPS at both regional and national levels were also developed with programme support, further reinforcing its contribution to long-term impact and sustainability.

Major lessons from the second year of WPS programme:
1. Knowledge exchange between ASEAN Member States and Observer State is beneficial for a successful implementation and advancement of the WPS agenda in ASEAN. This year, more work has been done to localise the regional policies to national and subnational WPS policy frameworks. By providing a platform for knowledge exchange, state and non-state actors were able to learn from each other on success stories and room for improvements, adapting to each of their local context and security landscapes of individual Member States. Interviews with beneficiaries confirmed that regional knowledge exchange is particularly valuable, with many strongly emphasising its usefulness in enhancing their understanding and capacity to implement the WPS agenda effectively within their institutions.
2. Closer coordination with UK diplomatic posts allows more streamlined FCDO efforts. Learning from last review’s recommendation, a more direct engagement between UK diplomatic posts and regional programme team, alongside between UK diplomatic posts and UN Women country offices where possible, has been beneficial in providing more impactful support. UK diplomatic posts have provided additional support in recommending stakeholders prior to the programme activities, taken follow-up contacts with beneficiaries, and ensuring UK support visibility throughout the in-country activities, which amplifies the overall UK support to the WPS agenda in the region. In some cases where UK diplomatic posts have a parallel project on WPS, closer coordination have taken place to ensure minimum duplication and more to amplify the existing support.
3. Differing definitions of WPS between countries and stakeholders present a challenge, but also an opportunity. Some countries understand WPS in the context of traditional, armed, intra or inter-state conflicts whereas others are interested in non-traditional security threats (such as cyber and digital) or much narrower understandings, such as women in peacekeeping missions. While this can add complexity to the delivery of training, the broad spectrum of ways to apply WPS can help to secure political interest and buy-in.
4. Continuous close consultation with stakeholders in regional and national level is beneficial to deliver technical assistance and capacity building that are responsive to their needs. This is also done in the process of annual workplan development, technical assistance in delivering policy frameworks, and development of policy research.
Wider reflections on the wider programme context gained through this year’s annual review process, and which can be used for Programme Completion Review (PCR), are available in the Annex. These reflections will be further elaborated in the PCR, where insights from the first Annual Review and results from the UN Women’s evaluation will be triangulated to validate and strengthen these reflections.

Recommendations for the year ahead:
1. Recommendation 1: To enhance the ASEAN-IPR WPS training programme, it is recommended to engage further with participants as a follow-up to the two training sessions delivered. Participant feedback and strong turnout suggest that there is strong interest and momentum to sustain and deepen the learning outcomes, and with available time and resources, the programme is well-positioned to build on this foundation. It would also be useful to embed relevant UK’s expertise in the training enhancement activities.
2. Recommendation 2: As the programme approaches its final year of implementation, ensuring sustainability of the WPS agenda in the region should be a key consideration in planning next year’s activities, including in the final evaluation planned by UN Women. One potential pathway to sustainability is through the ASEAN WPS Community of Practice (CoP), as the CoP is planned to be a useful platform for knowledge sharing between state and non-state actors in AMS and Observer State. Another potential pathway is to align efforts with ODA-funded WPS activities as a way to foster sustainability, for example with FCDO supports to Philippine’s WPS Centre of Excellence (CoE), as the Philippines is set to assume ASEAN chairmanship next year.
3. Recommendation 3: Continue to monitor the regional/ASEAN-level and national-level interest and commitment to the WPS agenda and to other gender-related political-security issues that might be related to WPS (e.g., women’s political participation and leadership). In parallel, it is equally important to capture and analyse lessons learned from the UN Women’s evaluation which will be concluded in the end of this year. Leveraging these findings can significantly inform future programming, policy development, and strategic support for WPS in the region, ensuring that interventions are evidence-based, contextually relevant, and responsive to emerging needs.
Progress of follow-up actions based on previous year’s recommendations is available in the Annex.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case
The overall theory of change for the WPS programme was adopted from the UN Women regional project, “Empowering Women for Sustainable Peace: Preventing Violence and Promoting Social Cohesion in ASEAN (Advancing WPS in ASEAN)”. Given the significant implementation role of UN Women and the nature of the UK’s contribution to this project, a decision was taken to adopt the UN Women’s ToC and integrating ASEAN-IPR’s change pathway into the ToC for FCDO reporting. This adopted ToC aligns with the WPS programme’s objectives of promoting gender equality and social cohesion in ASEAN. Any necessary contextual adjustments have been made to ensure the ToC accurately reflects our expected outcomes.

The outcome of the WPS programme is that ASEAN institutions, Member States, and non-state actors promote WPS successfully, including preventing violence against women and girls at the regional and national level. This is achieved through delivering the following outputs:
ASEAN Secretariat, sectoral bodies and institutions have increased gender and WPS expertise to develop regional policies on WPS and related frameworks;
1. ASEAN sectoral bodies and institutions and non-state actors have strengthened capacity to implement the WPS agenda;
2. A regional platform for cooperation and advocacy among ASEAN Member States, sectoral bodies, and institutions as well as civil society and women organizations is strengthened to promote good practices and evidence on WPS; and
3. ASEAN Member States and non-state actors have increased knowledge and capacity to develop, implement and monitoring WPS policy frameworks and test and upscale innovative approaches to implementing WPS agenda and conflict prevention at the national level.
There are no changes to outcome and impact indicators from the business case. A minor and non-material adjustment was made from the original UN Women’s result framework for this programme to incorporate ASEAN-IPR’ result chain.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The outcome of the WPS programme is ASEAN institutions, Member States, and non-state actors promote WPS successfully at the regional and national level, as indicated by: (i) Number of regional WPS policy frameworks completed with implementation and accountability mechanisms adopted; (ii) Number of national policy frameworks to advance WPS complete with accountability mechanisms adopted; and (iii) Perceptions of stakeholders on the authority of the frameworks to effect change.

During this review period, the programme has made notable progress toward the outcome. As the result technical assistance, capacity-building initiatives, and peer learning platforms, AMS have advanced their national WPS frameworks with clear accountability mechanisms. For example, in the Philippines, the government has published a Handbook for the Monitoring, Evaluation, Accountability, and Learning (MEAL) Plan and Framework to support the implementation of its NAP WPS. In Indonesia, the government released its second report on the implementation of its NAP, demonstrating ongoing commitment and transparency in tracking progress. Timor-Leste’s NAP and the Gender Strategy of the National Police both have included monitoring frameworks, reinforcing institutional accountability and gender-responsive security sector reform. Although Malaysia was not originally a target country for the programme, it has requested support to develop its own NAP WPS and plans to launch it at the ASEAN WPS Summit this year. Meanwhile, Cambodia is actively working to integrate WPS into its upcoming Women's Development Plan for 2026–2030, signalling a strategic and forward-looking approach to gender equality and peacebuilding.

While on the regional level, ASEAN adopted the Plan of Action on Enhancing Women’s Political Participation and Leadership, along with its Implementation Matrix in 2024. This strategic framework emerged from a series of regional workshops and dialogues held throughout the implementation of the programme. The framework outlines concrete actions to increase the number and influence of women parliamentarians, dismantle systemic barriers to political participation, and foster gender-responsive parliaments. It emphasises inclusive governance, the active engagement of male allies, and the importance of inter-generational collaboration and recognition of the care economy. The Implementation Matrix provides a detailed roadmap for member parliaments, including timelines, indicators, and mechanisms for monitoring progress. This initiative aligns with broader ASEAN commitments to international frameworks such as Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW), The International Covenant on Civil and Political Rights (ICCPR), and the ASEAN Community Vision 2025, and reflects a regional consensus on the need to build a resilient, connected, and inclusive ASEAN through gender-balanced leadership.

These developments indicate that the programme is on track to contribute to the expected outcome. The presence of accountability mechanisms in both national and regional frameworks reflects growing institutional commitment and capacity to implement WPS principles meaningfully.

The programme’s progress toward the outcome has been underpinned by several key assumptions that held true during this period. One of the key underlying assumptions is that a sustained engagement and dialogue can catalyse policy adoption. For example, the momentum generated through the first and second Women Parliamentarian of AIPA (WAIPA) workshops in 2023 and 2024 created a strong foundation for regional consensus-building, ultimately contributing to the adoption of the Plan of Action on Enhancing Women’s Political Participation and Leadership and its Implementation Matrix by the 45th AIPA General Assembly in October 2024. At the national level, political will among key government stakeholders proved instrumental, as it enabled the finalisation and adoption of WPS-related policies that had previously been in draft form. It is demonstrating that leadership commitment remains a critical driver of progress.

Strong partnerships with regional and national counterparts also validated the assumption that collaboration enhances responsiveness and ownership. For example, UN Women and ASEAN-IPR’s partnerships led to a higher-than-expected number of requests for technical support, which the programme was able to accommodate by re-prioritising resources, highlighting the importance of flexibility in programme delivery. Additionally, the agreement with GNWP and UN Women’s structured approach to engaging CSOs working on WPS across ASEAN significantly expanded access to women’s groups, surpassing initial outreach targets.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The UK’s own WPS NAP prioritises alliances with multilaterals, including ASEAN, on WPS implementation and leadership. This programme is the delivery mechanism for this commitment. It is also the FCDO’s only dedicated WPS programme; at a time when threats to this international agenda are at an unprecedented high, the leadership of the UK is critical.

In the context of the ASEAN-UK relationships, the programme is contributing to the Plan of Action to Implement the ASEAN-UK Dialogue Partnership (2022-2026). Advancing the WPS agenda is a clear priority under 1.2.1 (Enhance cooperation to support ASEAN’s efforts in peace and reconciliation in the region including the implementation of the WPS agenda, through relevant mechanisms, and support ASEAN Member States in the implementation of their respective WPS national action plans). It is also aligned with 1.2.2 and 1.2.3, which focuses on support to ASEAN Women for Peace Registry (AWPR) and ASEAN-IPR, respectively, 1.2.4 to promote linkages between the WPS and YPS, and 1.2.5 to promote best practices and experiences among AMS and UK on gender sensitive peace building, conflict resolution and reconciliation.

During the review period, the publication of the ASEAN Community Vision 2045 marked a significant milestone, explicitly referencing the active participation of AMS in the WPS agenda, including through the implementation of the RPA WPS. This recognition reinforces the legitimacy and relevance of the RPA and provides a strong foundation for its sustained implementation. It also signals a growing regional commitment that should be matched with continued support, particularly to assist AMS in developing robust accountability mechanisms and ensuring the long-term sustainability of their NAP.

Given its strategic relevance, demonstrated results, and continued demand from AMS, the programme has strong merit for continuation. It has contributed meaningfully to advancing the WPS agenda in ASEAN, with tangible progress in both regional and national policy frameworks, supported by validated assumptions such as political will, strong partnerships, and inclusive engagement with civil society.

As the programme enters its final phase, with remaining activities focused on convening and capacity-building, there is a clear opportunity to consolidate gains and ensure sustainability. In the context of the wider portfolio and the UK’s commitment to gender equality and peacebuilding, continued support, in a more strategic and focused form, would be well justified. This could include backing existing platforms such as the CoP, country-level knowledge exchange platforms, and supporting AMS in strengthening the accountability and sustainability of their NAP. Such targeted actions would not only preserve the momentum built but also align with anticipated ODA rationalisation by ensuring value for money and long-term impact.

## C: DETAILED OUTPUT SCORING

Output Title	Technical assistance (TA) on the implementation of regional policy frameworks on WPS and related gender equality frameworks in ASEAN as well as evidence-based policy research are delivered.
Output number:		1	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of regional policy frameworks on WPS and related gender equality frameworks on which TA is provided for implementation.	TA for one regional policy framework are delivered	Successfully delivered TA for two regional policy frameworks: / The Plan of Action and Implementation Framework on Promoting Women’s Political Participation and Leadership in ASEAN 2024-2030 / Baseline study and monitoring framework of the ASEAN Regional Plan of Action on WPS
Number of regional WPS evidence-based policy research produced and disseminated.	One evidence-based policy research produced and disseminated	Two (2) evidence policy research were produced and disseminated: / Advancing Gender Responsive Conflict and Crisis prevention in ASEAN / Regional Study on Youth, Peace and Security (YPS)

Briefly describe the output’s activities and provide supporting narrative for the score.

The output focuses on delivering technical assistance for the ASEAN Secretariat, sectoral bodies, and institutions to build regional expertise and capacity in developing and implementing the RPA on WPS and WPS agenda in humanitarian action through adoption of regional frameworks. It also supports the development of regional evidence-based policy research and data related to WPS in the region.

The programme’s technical assistance led to the development of several regional policy frameworks and evidence-based research products during this review period, as detailed below:
1. The Plan of Action and Implementation Framework on Promoting Women’s Political Participation and Leadership (WPPL) 2024-2030. The Plan of Action serves as a strategic framework to advance gender equality and strengthen the role of women in parliamentary processes across the region. It outlines key priorities, initiatives, and collaborative efforts to foster inclusive governance, promote women’s leadership, and address systemic barriers to political participation. Through capacity-building programmes, policy advocacy, and cross-sector partnerships, it aims to drive sustainable progress towards an inclusive ASEAN. It was adopted at the forty-fifth General Assembly of the AIPA, held in Vientiane, Lao PDR.
2. The baseline study and monitoring framework of the RPA WPS aim to define status, establish measurable indicators, and track progress on priority actions across ASEAN. It enables evidence-based implementation, regular reporting, and review of regional WPS commitments. The baseline study and monitoring framework was endorsed by the WPS Advisory Group and ACW.
3. Policy research on Advancing Gender-Responsive Conflict and Crisis Prevention in ASEAN. The research aims to strengthen ASEAN’s capacity to prevent conflict and crises through a gender-responsive approach. It examines how women’s participation, leadership, and perspectives can be systematically integrated into peacebuilding and prevention efforts. By analysing gaps, best practices, and case studies from AMS, the research provides evidence-based recommendations to operationalise WPS agenda. The research is publicly accessible through ASEAN WPS and ASEAN IPR website.
4. UN Women and ASEAN-IPR, in partnership with the UNDPPA, developed and finalised the draft Regional Study on Youth, Peace and Security (YPS): Mapping of Existing Conflict and Crisis Prevention Mechanisms in ASEAN. The study is expected to inform inclusive policy dialogues with youth and enhance regional cooperation on youth engagement in peacebuilding, with the UN Women adding value of the interlinkages between WPS and YPS in the region. It has been endorsed by the ASEAN-IPR Governing Council and will be launched in late August 2025.

Overall, the output scores an A+, indicating that the major component of the output has exceeded its annual targets.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes or planned changes were made during this review period. The only activities delayed from last year was the Regional Study on Youth, Peace and Security, which was successfully completed during this review period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There is no recommendation from the previous AR for this output. Major lessons learned and recommendations is listed in Section A.

Output Title	Technical assistance to build capacity of ASEAN sectoral bodies, institutions, and CSOs on the WPS agenda are delivered.
Output number:		2	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of training sessions delivered for ASEAN sectoral bodies, institutions, and CSOs.	10 training sessions/workshops are delivered for ASEAN sectoral bodies, institutions, and CSOs.	There are 27 regional training sessions/workshops delivered to ASEAN sectoral bodies, AMS and CSOs on the WPS agenda.
Number of participants (sex-disaggregated) participating in capacity-building activities.	200 participants are attending the events	Overall, a total of 923 stakeholders (602 female, 119 male, 1 other, and 201 unidentified) from ASEAN, AMS and CSOs attended the regional sessions/workshops supported by UN Women and 50 participants attended training sessions provided by ASEAN-IPR.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme has demonstrated commendable performance, moderately exceeding its set targets across key indicators. The A+ rating reflects not only the successful achievement of planned outputs but also the added value generated strategic partnerships. Stakeholder engagement remained strong throughout, with a high level of willingness among partners and beneficiaries to actively participate and support its implementation.

This output focuses on delivering institutional capacity building for ASEAN to implement policies and programmes to promote women’s leadership and participation in inclusive governance and conflict prevention, resolution and recovery, supporting networks of women organisations and civil society to promote WPS localization, and technical support to strengthen the connection between policymakers, women’s representatives in the parliament, and CSOs to promote meaningful leadership, representation and participation of women in peace and security decision making.

The key results are highlighted as follows:
- Over the past year, there are 27 regional training sessions/workshops delivered to ASEAN sectoral bodies, institutions, and CSOs. Notably, this year marked the start of implementation by the ASEAN-IPR under the programme framework, with ASEAN-IPR independently delivering four capacity-building trainings designed for AMS officials. These trainings, structured across four modules (Module Zero to Module Three), aimed to strengthen participants’ understanding of peacebuilding, conflict dynamics, violence prevention, gender, and human security. on WPS-related topics, conducted with UN Women’s technical assistance. These sessions covered global, regional and national WPS frameworks and their alignment with other agendas, including the youth, peace and security agenda, the 2030 Agenda and ‘Leaving No One Behind’, and the ASEAN Community Vision 2045. Additional topics included integrating WPS in human rights and peace education, promoting gender-responsive parliaments, increasing women’s participation in United Nations peacekeeping operations, and strengthening partnerships and resource mobilization.
- More than 900 stakeholders from AMS and CSOs participated in regional sessions and workshops supported by UN Women and ASEAN-IPR. These capacity-building initiatives have strengthened collaboration between regional and national efforts to implement the WPS agenda regionally and inspiring concrete actions at the country level. Participants reported enhanced understanding and confidence in applying WPS-related policies and practices. From the delivery partners, participants expressed a renewed motivation to promote and advance the WPS agenda in their professional roles, demonstrating the programme’s effectiveness in fostering individual empowerment and institutional engagement.
- Through capacity-building support provided by UN Women and the Global Network of Women Peacebuilders (GNWP), women’s organizations, journalists, and academics successfully applied their enhanced skills and knowledge to produce an advocacy paper submitted to ASEAN in 2024. This paper proposed the establishment of a WPS Community of Practice (CoP), as envisioned in the Regional Plan of Action on WPS. The CoP is expected to strengthen collaboration among stakeholders, foster meaningful dialogue between ASEAN government representatives and civil society, and promote mutual learning and trust. It will serve as a platform for sharing knowledge and best practices, building stakeholder capacities through targeted training, and raising awareness of the WPS agenda across the region.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There are no changes to this output during the past year, however we are taking into account the ASEAN IPR training sessions delivered in the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There is no recommendation for this output from the previous AR. Illustrative examples from this output that demonstrate progress made in addressing the recommendation from the previous AR is provided in the Annex.

Lessons learned from this output are:
- The ASEAN-IPR training used a nomination-based invitation process, aiming to reach stakeholders who are either new to WPS issues or have not participated in previous trainings. This approach helped engage the right participants but also presented some challenges. These included lower participant turnout due to delays in receiving nominations, and a lack of continuity between training sessions, as nominations were managed through multiple institutions. If this approach is used again in the future, these challenges should be anticipated and addressed.
- Building on feedback from the first NAP Academy, the second NAP Academy successfully engaged more CSOs in regional capacity-building efforts. This broader participation created opportunities for meaningful collaboration with government officials, particularly in the development and implementation of NAP WPS. For example, the workshop facilitated peer learning and multi-stakeholder coordination, allowing CSOs to share grassroots perspectives while government representatives explored ways to integrate these insights into national policies. Such interactions helped bridge gaps between policy and practice, thus strengthening joint efforts to localise the WPS agenda across AMS.

Output Title	Technical assistance to strengthen cooperation and advocacy of good practices and evidence on WPS in ASEAN are delivered.
Output number:		3	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of cross-sectoral dialogues held to advance WPS within ASEAN by the end of the project.	4 cross-sectoral dialogues or knowledge exchange sharing are held	14 cross sectoral dialogues and knowledge exchange sharing through meetings, workshops, and roundtable dialogues were held regionally
Number of media literacy training/workshops provided to media workers, influencers, including youth, CSOs, and key opinion leaders on raising awareness and advocating for WPS agenda in the ASEAN region.	2 media literacy training/workshops to raise awareness for WPS agenda in ASEAN	3 training sessions/workshops to media workers and CSOs were held to raise awareness for WPS agenda in ASEAN
Evidence of customized advocacy and awareness raising content produced including but not limited to media briefs, advocacy notes, social media posts on WPS.	Tailored advocacy and awareness-raising content produced	Multiple advocacy and awareness-raising media content produced, including stories, press releases, social media posts in various platforms, and newsletter were produced

Briefly describe the output’s activities and provide supporting narrative for the score.

The output’s A+ rating reflects its ability to not only meet but moderately exceed its intended targets. This is evidenced by the growing demand for WPS-related content in regional convenings, driven by stakeholders’ high willingness to engage with and support the agenda. This enthusiasm has translated into concrete requests for dedicated WPS sessions, reflecting the agenda’s increasing relevance across diverse regional contexts.

This output focuses establishing/supporting a regional platform to convene multiple actors and stakeholders, particularly to promote cross-sectoral and inter-pillar dialogue/exchange across ASEAN community pillars to advance the WPS agenda. UN Women’s deliverables were reflected in several high-level platforms and initiatives, including the Third ASEAN Women Leaders’ Summit, where UN Women provided technical support to the Lao People’s Democratic Republic as ASEAN Chair and delivered a presentation on the RPA WPS in the context of care, resilience and the localization toolkit and guidelines, in collaboration with the United Kingdom Mission to ASEAN. At the Forty-fifth General Assembly of the ASEAN Inter-Parliamentary Assembly (AIPA) and the Women Political Leaders Forum, UN Women contributed to the adoption of the Plan of Action on Enhancing Women’s Political Participation and Leadership in ASEAN (2024–2030). Additionally, UN Women supported a side event on inclusion and intersectionality at the International Conference on WPS in the Philippines, emphasizing the importance of addressing intersecting forms of discrimination to ensure no one is left behind. UN Women also facilitated the participation of government representatives from Cambodia, Indonesia, Thailand, Vietnam, the Philippines, and Timor-Leste in the WPS Focal Points Network meeting in Tokyo. In addition, UN Women also supported the establishment of WPS CoP in ASEAN, in collaboration with ASEAN-IPR.

The output also emphasised innovative campaigns and advocacy to promote gender equality, peace, and inclusion across ASEAN, particularly through digital platforms and social media. UN Women supported the development of several communication products that advanced counter-narratives and engaged women and youth in the WPS agenda. These products, available on the ASEAN WPS website, included stories, articles, media coverage in Vietnam on the launch of the National Action Plan on WPS, and publications such as a brief on gender-responsive budgeting. Social media engagement through Facebook, Twitter, Instagram, and LinkedIn was a key component of the outreach strategy with hundreds of posts under hashtags like #ASEANRPAWPS and #WPSASEAN generating thousands of engagements and reaching well over a million users across the region. These figures reflect the programme’s success in amplifying WPS messaging and encouraging broader public engagement and awareness.

The programme also delivered targeted support to CSOs, media professionals, and journalists to strengthen advocacy and storytelling around WPS in ASEAN. UN Women launched the CSOs PEACE Award, a regional competition designed to recognize innovative, impactful, and replicable WPS initiatives led by CSOs across ASEAN and Timor-Leste. This initiative aimed to elevate grassroots efforts, promote women’s participation in peace and security, and foster collaboration and learning through the sharing of good practices. In parallel, an Editor’s Roundtable held in Jakarta brought together media professionals to enhance their understanding of gender-sensitive reporting and amplify women’s voices in peacebuilding narratives. Despite these efforts, WPS coverage in mainstream media remains limited, underscoring the need for greater visibility of women’s leadership and contributions. To address this gap, the ASEAN WPS Media Award was introduced as part of a broader strategy to engage media actors within the WPS CoP. Journalists were invited to submit news pitches on WPS topics, with 30 selected for a capacity-building workshop focused on journalism and WPS. Following the workshop, participants are expected to publish their stories, and three outstanding journalists will be awarded a cash prize and a fully funded opportunity to attend and cover the ASEAN WPS Summit in Malaysia. These initiatives aim to build media capacity, foster sustained engagement with the WPS agenda, and amplify public awareness through impactful storytelling and strategic media partnerships.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes or planned changes were made during this review period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There is no recommendation for this output from the previous AR. Illustrative examples from this output that demonstrate progress made in addressing the recommendation from the previous AR is provided in the Annex.

Lessons learned related to this output are:
- Given the range of dialogues, workshops, and knowledge exchanges delivered, it is important to build on the momentum by taking concrete follow-up actions, such as maintaining contact with participants to support ongoing influence and engagement. Several UK diplomatic posts have contributed to this effort by staying connected with beneficiaries of these activities and encouraging their continued involvement in national-level WPS initiatives. This kind of follow-up helps sustain interest and foster long-term collaboration.
- There is a streamlined effort on CSOs and media involvement, from CSOs PEACE Award and WPS Media Award building towards their participation in the ASEAN WPS Summit and the launch of ASEAN WPS CoP. It is a good momentum to promote non-state actors’ participation and recognition into a more meaningful participation in the regional level.

Output Title	Technical assistance for targeted AMS and non-state actors to implement the WPS agenda at the national and local level are delivered.
Output number:		4	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of policy/programme products resulting from consultative processes to assist state actors in the development, implementation and/or coordination of national WPS relevant policies.	2 national policies/strategic frameworks	Supported 3 policies/strategic framework development at the national level: / Civic Education for Peace programme in partnership with the Ministry of Interior of Timor-Leste. / National Action Plan to Combat Trafficking led by the Ministry of Justice and the National Commission to Combat Trafficking in Persons of Timor-Leste. / Second National Police of Timor-Leste Gender Policy.
Number of trainings and workshops related to implementation of WPS agenda at the local level provided to women’s and youth groups/networks and other CSOs (in Indonesia, Philippines, Thailand, Vietnam).	Multiple trainings with variety of topics on implementation of WPS agenda at the local level based on capacity needs	There are 50 workshops/events related to WPS delivered to non-state actors in Cambodia (1), Indonesia (7), Malaysia (1), the Philippines (5), Thailand (10), Vietnam (6), and Timor-Leste (20) with total participants reached 1,399 individuals from state and non-state actors.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output has been awarded an A+, indicating that it has successfully exceeded its milestones within the planned timeframe. The activities carried out were well-implemented and aligned with the initial objectives, resulting in the desired progress. Notably, growing interest in the WPS agenda, sparked by active participation in various regional events, has led to additional support being provided to Cambodia, Lao PDR, and Malaysia, which were not among the programme’s initially targeted countries.

The output focuses on the support to AMS in enhancing their ability to implement the WPS including the localisation of the RPA WPS and developing national policy or action plan on WPS. It will promote synergies and complementary efforts to ensure that the commitment at the regional level is translated into policy/programme actions at national and local levels tailored to the diverse and specific local contexts within the ASEAN region.

Key results are highlighted as follows:
- Indonesia: Technical assistance was provided to support the formulation of the third generation of NAP, reinforcing national-level commitment to the WPS agenda. Additionally, the 2024 progress report on NAP WPS was published, offering valuable insights into implementation achievements, challenges, and opportunities.
- Cambodia: Support was delivered to raise awareness and mobilise political support for the WPS through an event with the Ministry of Women’s Affair and ten-line ministries at the level of Secretary of State/Under Secretary of State.
- Lao PDR: Support was delivered to integrate WPS into the Women’s Development Plan 2026-2030.
- Malaysia: Technical assistance was provided to develop the first NAP with the launch to be planned during the ASEAN WPS Summit in Malaysia in September 2025.
- Philippines: As a result of technical assistance provided by UN Women, the Government of Philippines developed and launched the Indicator Handbook for the MEAL Plan and Framework for the NAP WPS, facilitating the tracking and assessment of WPS implementation. These efforts were led by the National Steering Committee on Women, Peace and Security and the Office of the Presidential Adviser on Peace, Reconciliation and Unity (OPAPRU) in partnership with UN Women.
- Thailand: The programme supported the launch of Women Empowerment Centres in the North and Northeast region. Th draft NAP to be submitted to the National Committee on the Policy and Strategy for the Advancement of Women and then National Economic and Social Development Board for adoption this year.
- Vietnam: The first-ever NAP was adopted, with technical support for NAP planning and training targeted government ministries. This led to increased engagement from key ministries, including foreign affairs, public safety, defence and home affairs. Continued technical support to the Ministry of Public Security, including co-organization of an international forum to enhance women's participation in peace operations. Ongoing support to support the delivery plan of the NAP was also delivered.
- Timor-Leste: The programmes supported the development of Timor-Leste’s Civic Education for Peace programme in partnership with the Ministry of Interior. Support was delivered in developing the concept and conducted two rounds of consultations with line ministries and CSOs and piloting a curriculum. Technical assistance was also delivered to develop a National Action Plan to Combat Trafficking, led by the Ministry of Justice and the National Commission to Combat Trafficking in Persons of Timor-Leste.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes or planned changes were made during this past year, however in this review we are taking into account the expansion to Cambodia, Lao PDR, Malaysia, and enhancement of activities in Timor-Leste started in September 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

 There is no recommendation for this output from the previous AR. Illustrative examples from this output that demonstrate progress made in addressing the recommendation from the previous AR is provided in the Annex.

Lessons learned related to this output is:
It is important to acknowledge the changing political will and priorities on the national level to adjust and adapt the efforts of developing national WPS policy framework, including through integrating WPS agenda into existing gender-related plans instead of developing a separate NAP for WPS.

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

Economy
The ASEAN-UK WPS Programme demonstrates strong economic performance, with both implementing partners—UN Women and ASEAN-IPR—adopting cost-conscious approaches that align with FCDO procurement standards. Additionally, the programme is co-funded by Government of Canada and Republic of Korea, enabling the UK’s contribution to achieve broader regional impact.

UN Women primarily delivers activities through in-house staff or UN’s pool of experts and national offices, reducing reliance on external consultants. This approach supports quality control and cost containment. Procurement is conducted transparently and competitively, with regional and national teams leveraging existing networks and expertise. The use of local teams in each ASEAN country ensures that costings are contextually appropriate.

ASEAN-IPR employs a three-quote system for logistics—including hotels, airfare, and venues—selecting vendors based on cost, service quality, and accessibility. Facilitators were drawn from the pool of experts who developed the WPS training modules in 2021; these individuals later transitioned into roles as trainers and facilitators, ensuring both subject-matter expertise and continuity in programme delivery, and avoids additional recruitment costs. Workshops held in Bangkok were also economically sound, as the city’s central location within Southeast Asia made it a strategic and cost-effective choice. With participants travelling from across all AMS, Bangkok offered optimal regional accessibility and competitive flight costs, ensuring value for money without compromising inclusivity or convenience. Importantly, ASEAN-IPR benchmarks its costings against those of ASEAN’s dialogue partners, ensuring that budget allocations are not only regionally appropriate but also aligned with established standards. This approach strengthens the justification for expenditures and promotes consistency across ASEAN-affiliated initiatives. However, the programme reported underspending in the first half of the year, largely attributable to delays in implementation and insufficient staffing to carry out planned activities, and lower turnout of in-person participants from approved budget. This suggests that increasing human resource capacity is essential to ensure timely delivery and full utilisation of allocated funds.

Lastly, mobilising resources through the FCDO posts further enhances the visibility of UK support. Having a representative on the ground to attend WPS implementation activities by delivery partners strengthens the UK's presence and engagement. This not only improves coordination and oversight but also reinforces the UK's commitment to the WPS agenda in the region.

Efficiency
The programme demonstrates strong efficiency in converting inputs into outputs, particularly through UN Women’s delivery. The programme has exceeded most of its output targets, indicating effective project management and resource utilisation. UN Women significantly exceeded its 2024 targets. They delivered 82 workshops and training sessions (vs. a target of 30). The programme reached 3,342 stakeholders (1,898 women, 926 men, 7 non-binary, 511 unidentified) and supported 14 cross-sectoral dialogues and 21 CSO-led events. Furthermore, UN Women has facilitated the adoption of two new NAPs (Vietnam and Timor-Leste) and the launch of Indonesia’s first NAP WPS implementation report. The programme’s ability to deliver high volumes of activity reflects efficient use of resources, including its ability to quickly mobilise appropriate speakers and resources for both government and academic audiences in workshops, demonstrating operational agility in notable events targeting different beneficiaries.

ASEAN-IPR successfully delivered four training modules—Module Zero online, followed by Modules One and Two in person in 2024, and then Module Three in person for senior-level officials in 2025—to a total of 50 participants from AMS, Observer State, and ASEAN Sectoral Bodies. The sessions were conducted on schedule and generally well-received. Many participants found the training relevant to their work, with a noticeable boost in confidence, especially among women participants, in applying conflict resolution techniques. However, some logistical challenges emerged during the in-person sessions. Trainers struggled to keep to the planned schedule, which led to certain lessons being skipped. This feedback highlights the need for improved time management and session planning in future modules to ensure participants can benefit fully from the content.

Effectiveness
The programme has made notable strides in advancing its core objectives of strengthening institutional capacity, supporting national policy development, and fostering regional cooperation. UN Women has played a central role in enabling key policy milestones, including the adoption of NAP in Vietnam and Timor-Leste, as well as the launch of Indonesia’s second NAP implementation report. In the Philippines, it supported the development of monitoring and evaluation tools and helped establish a regional CoP to sustain collaboration across ASEAN. Nearly a thousand stakeholders across seven countries have reported improved knowledge and skills in WPS-related areas, with country-level feedback confirming that the programme has facilitated strategic engagement with key institutions such as the Ministry of Foreign Affairs and the Ho Chi Minh Political Academy in Vietnam, and OPAPRU in the Philippines. The programme has also contributed to elevating the UK’s visibility in the WPS space.

In Indonesia, the programme supported provincial-level action planning, although uptake remains limited. Stakeholders have highlighted the need to broaden the definition of conflict and to strengthen civil society participation in policymaking processes. While regional coordination is strong, communication at the country level could be improved. Posts in Vietnam and the Philippines noted that updates from UN Women’s national offices are infrequent, leading to missed opportunities for visibility and donor coordination. In the Philippines, there have also been concerns regarding the accessibility of UN Women to local CSOs. Reports indicate a preference for funding international flights over local transport, which has limited the participation of local CSOs in key events.

The ASEAN-IPR has added value through its training programme, which engaged participants across AMS and Observer State, and delivered foundational WPS content. Participants reported increased confidence and found the training relevant to their work. They also noted that the knowledge gained was not only useful for their own roles but also transferable to colleagues and broader networks. The networking opportunities provided by the workshops were seen as particularly valuable, given the collaborative nature of WPS work. However, several limitations affected the overall effectiveness of the training. The case studies presented during the workshops lacked diversity, with most examples drawn from one country only. This limited relatability for participants from other countries and posed challenges in translating input into meaningful outcomes.

Participant selection for ASEAN-IPR workshops has presented opportunities for refinement. The current approach—primarily guided by recommendations from ASEAN Member States via the Governing Council—has occasionally led to variations in stakeholder representation. This variability, while reflective of diverse national perspectives, may limit the continuity and institutional memory needed to implement the knowledge gained into a concrete action. Introducing greater flexibility and robustness in participant selection to enhance the relevance and impact of the training, as well as to strengthen the networks that are essential for advancing WPS objectives.

Lastly, delivering the programme through ASEAN significantly enhances its legitimacy and receptivity among AMS. The ASEAN association to the programme activities provides a sense of regional ownership and neutrality, which encourages more open and candid participation from stakeholders. Participants are more comfortable engaging in sensitive discussions under the ASEAN umbrella, as it reflects a collective regional initiative rather than a unilateral foreign agenda. This strategic alignment fosters trust, reduces perceived external influence, and ensures that the programme is viewed as a collaborative effort rooted in regional priorities. By embedding the UK’s support within ASEAN’s framework, the FCDO effectively amplifies its impact while respecting local dynamics and sensitivities in the field of peace and security.

Overall, the programme is delivering on its intended outcomes, with clear signs of policy influence, institutional strengthening, and regional momentum. However, to sustain and deepen its effectiveness, continued attention must be paid to localisation, stakeholder alignment, and communication. Addressing the challenges in participant selection, improving the diversity of training content, and ensuring greater accessibility for local civil society actors will be key to unlocking the full potential of the programme.

Equity
The ASEAN-UK WPS Programme demonstrates a strong commitment to equity by embedding gender inclusion and striving to reach underrepresented groups across its activities. Both UN Women and ASEAN-IPR have taken deliberate steps to promote inclusive participation, though structural and operational barriers continue to affect equitable access and impact.

UN Women has integrated equity principles across its programming, with women comprising the majority of participants in capacity-building activities. Dedicated sessions on inclusion and “Leaving No One Behind”—such as those at the WPS International Conference in the Philippines—reflect growing attention to intersectionality. These efforts mark progress in acknowledging the diverse experiences of women affected by conflict. However, equity considerations are not yet systematically embedded at the local level. Monitoring and implementation frameworks could more explicitly address the needs of ethnic minorities, rural women, women with disabilities, and other marginalised groups to ensure that programme benefits are equitably distributed.

ASEAN-IPR also achieved strong female participation in its training programme, with women representing 72% of the cohort. Post-training feedback indicated increased confidence among women in applying conflict resolution skills, suggesting a positive empowerment effect. However, gaps in representation remain. Several ASEAN Member States and key regional bodies were not engaged in the training; there were no representation from Lao PDR and Singapore in the first training, and ASEAN Secretariat representative in both training sessions. This lowered the programme’s inclusiveness and reach. Additionally, the participant selection process, as noted in earlier sections, can be improved to prioritise the most relevant and/or underrepresented stakeholders. This will then improve the strategic equity impact of the training and opportunities for broader network-building.

To strengthen equity outcomes, the programme should adopt more inclusive and transparent selection mechanisms, ensure geographic and institutional diversity, and tailor training content to the differentiated needs of youth, persons with disabilities, and ethnic minority communities. Doing so will help ensure that the programme’s benefits are not only widespread but also equitably shared.

Assessment of whether the programme continues to represent value for money
The programme demonstrates strong value for money and merits continuation to its final year. Economically, both UN Women and ASEAN-IPR have adopted cost-conscious strategies that align with procurement standards, leveraging local expertise and co-funding mechanism to maximise regional impact. In terms of efficiency and effectiveness, the programme has exceeded expectations, particularly through UN Women’s delivery. With over 80 workshops conducted and thousands of stakeholders engaged, the programme has not only met but surpassed its output targets. It has contributed to significant policy milestones, including the adoption of National Action Plans in Viet Nam and Timor-Leste and developments of NAP in Thailand and Malaysia this year, and has strengthened institutional capacities across the region. Equity is a central pillar of the programme, with a strong emphasis on gender inclusion and efforts to reach underrepresented groups. Both implementing partners have achieved high female participation and have begun to address intersectionality in their programming. However, gaps remain in engaging certain institutions and marginalised communities. As the programme moves into its final year, modest adaptations—such as more inclusive participant selection mechanisms and content tailored to the diverse needs of civil society actors—could further enhance its equity outcomes and broaden its strategic impact. Overall, the programme delivers tangible results and represents a sound investment, with clear opportunities for refinement to deepen its impact and inclusivity.

## E: RISK

Overview of risk management
The WPS programme has a moderate risk based on the assessment made during the Business Case stage. After that, a detailed risk register is maintained and updated, in line with FCDO risk management policy and appetite levels are set for all risk categories. FCDO programme team has set out mitigation strategies from the first year which were continued being applied and adapted, alongside both implementing partners. UN Women has set out a risk management strategy for mitigating potential political risks to programme delivery and a detailed risk matrix. ASEAN-IPR’s approach to risk management focuses primarily on managing financial risks, including an annual audit of accounts and external audits to verify the compliance with ASEAN-IPR Secretariat Financial and Administrative, Rules and Procedures (FRP) and ASEAN-IPR Secretariat Staff Regulations (ASR).

The current risk of the programme is moderate. Based on the latest risk register (August 2025), residual risks left are mainly moderate (62%) with one major risk and few minor risks (31%).. The programme falls within the FCDO risk appetite across the seven risk categories.

Key updates on risks based on categories and mitigation measures are summarised below:
Strategy and Context: there is a lower risk of low buy-in of AMS prioritisation of the WPS agenda, which partly brought by the expansion of the programme activities to cover Cambodia, Malaysia, and Lao PDR, focusing on awareness raising to develop WPS policy framework. Under this annual review timeline, there has been promising progress of more countries intending to develop NAP or integrate WPS into their national policies, and some countries is in final stages of adopting their WPS NAP (i.e., Malaysia, Thailand). AMS buy-in are also indicated to be higher due to mention of WPS in the ASEAN Community Vision 2045 that promotes implementation of ASEAN WPS RPA in country level. Nevertheless, this risk is being managed by ensuring close consultation between implementing partners and ASEAN Secretariat and ASEAN bodies through the team’s involvement in the Project Steering Committee (PSC) for the UN Women project; and additionally, by engaging with AMS representatives including through UK diplomatic posts and other Dialogue Partners (DPs) working on the WPS agenda to identify and strengthen collaboration to support the sustainability of the WPS agenda in ASEAN.

Policy and Programme Delivery: the risk of implementation delays as a result of implementing partners’ performance, political and crisis events affecting programme delivery, and ASEAN accreditation are being closely managed by the programme management team. This is done by working with FCDO posts to monitor in-country political changes to ensure UN Women adapt their approaches for in-country activities. Closer monitoring is also being done to track the cause of underspend to avoid similar cases in the future, and further planning to utilise underspend from ASEAN-IPR trainings. In the bigger context, the team is also monitoring how the UN80 reform will likely impact UN Women, although UN Women have provided assurances that the changes will not affect the current programme delivery. Risks remain with engagement with Myanmar through the programme, given the ongoing situation there. This has been properly managed through close engagement with partners and colleagues at FCDO Posts to ensure alignment with UK policy. Under this programme, there are no in-country activities in Myanmar.

People: capacity gaps or staff turnover that may results in the team’s ability to deliver the programme has been properly managed through recruitment of a programme manager and continuous learning and development in relevant areas for staff (e.g., WPS, programme management).

Safeguarding: the risk of Sexual Exploitation, Abuse and Harassment (SEAH) has been managed by conducting safeguarding training for implementing partners. The training happened in May 2025, where both UN Women and ASEAN-IPR participated. Standard FCDO policies on safeguarding have been included in signed agreements with both partners, including the available FCDO channels to report any allegations of SEAH, and the programme team will continue to encourage partners to use the channel and extend support where appropriate.

Financial and Fiduciary: focusing on fraud and aid diversion risk and currency exchange fluctuation risk, since both UN Women and ASEAN-IPR are managing funds in USD as per their policies. These risks are managed by conducting training agreeing on consistent currency exchange rate with implementing partners, scrutinising budget proposals and payment schedule to be compliant with Programme Operating Framework (PrOF) rules, regular and timely engagements to monitor state of expenditures and spending forecast and ensuring both implementing partners are compliant with FCDO’s audit and financial reporting requirements.

Climate and Environment: Risks due to climate change are present in ASEAN countries, which could increase the risk of conflict, fragility, and threats to women. Within the programme, both UN Women and ASEAN-IPR project activities pose no environment risk in the countries. Through NAP Academy under UN Women project and in collaboration with ASEAN-IPR, climate and environment crisis into the WPS topic as part of non-traditional security has been introduced.

Most of the programme activities have been delivered during this review period. Nevertheless, until the end of the programme, close monitoring of UN Women and ASEAN-IPR activities will be continued to ensure timely support in order to achieve all programme outcomes and contribute to impact achievement.

## F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery
Since last year’s annual review in early September 2024, notable progress has been made within the programme. An amendment to the Contribution Arrangement with UN Women to their project of “Empowering Women for Sustainable Peace: Preventing Violence and Promoting Social Cohesion in ASEAN (Advancing WPS in ASEAN)” was signed in mid-September 2024 for an uplift of £355k to allow expansion of the programme activities in Malaysia, Cambodia, and Lao, along with enhancement of activities in Timor-Leste. On ASEAN-IPR side, all main trainings have been delivered in September 2024 and June 2025.

Delivery of UN Women activities
In delivering their project, UN Women is consulting directly to deliver capacity building and technical assistance activities to the ASEAN Secretariat and institutions including ASEAN Sectoral Bodies. The project’s workplan is approved annually through the Project Steering Committee (PSC), which is organised fully by UN Women with the Poverty Eradication and Gender Division (PEGD) and chaired by senior representatives of ASEAN. The UKMis ASEAN programme team attended the 5th PSC in February 2025 as the UK representatives. This annual process of workplan approval has provided flexibility to adapt the programme in responding to a short to medium term needs of ASEAN and AMS, while maintaining achievement of the long-term outcomes.

Activities in Indonesia, Philippines, Thailand, Viet Nam, and Timor-Leste are mostly conducted by UN Women country offices. Expansion to Cambodia, Lao, and Malaysia was made based on consideration of AMS interests during regional events including NAP Academy, and activities in these three countries were delivered with the support of existing presence of actors, with focus on awareness raising activities for WPS policy development. For example, in Cambodia the UN Women country office is also working with The Asia Foundation (TAF) who were already present in WPS field. There is no UN Women country office in Lao and Malaysia, so a wider network of resources was involved. In Lao, activities were delivered by UN Volunteer through the UN Resident Coordinator (UNRC) office and Lao Women’s Union as a continuation of UN Women support in ASEAN Lao chairmanship in the previous year. In Malaysia, activities were delivered by local CSOs and by consultative advisory from UN Women Regional office. With this setting, progress has been made, indicated with Malaysia’s progressing NAP development to date, Lao’s plan to integrate WPS in their Women’s Development Plan, and Cambodia’s increasing interest to develop NAP in future years.

This year’s involvement with CSOs were more apparent in UN Women’s main activities, namely in the 2nd NAP Academy and establishment of an ASEAN WPS Community of Practice, in collaboration with ASEAN-IPR. At the national level, CSOs were also involved in different forms, such as through capacity buildings and establishment of Women Empowerment centres. This is correlated with last year’s recommendation on multi-layered engagements and knowledge exchange between AMS. CSOs involvement is found to be useful to advance the WPS agenda, but there is still room for improvement to ensure inclusivity and sustainability of their involvement.

Delivery of ASEAN-IPR activities
The ASEAN-IPR WPS Training Programme has been delivered as planned, with Module 0, 1, and 2 for junior- to mid-level officials having taken place in late September 2024, and Module 3 targeting senior officials have taken place in June 2025. The modules applied in the training was built upon from earlier version of pilot modules developed in 2022-2023, previously supported by FCDO through IP funds in BE Hanoi. Experts who developed the modules were also a priority to be engaged as trainers for training sessions in this 2024-2025 programme, although adjustments and replacements were made due to limited availability of the experts.

In both training sessions, the invitation was issued through ASEAN-IPR’s Governing Council, consisted of AMS’ Permanent Missions to ASEAN, to nominate participants from respective governments. As the intention is to mainstream the WPS agenda into policymaking, this nomination procedure was taken as the training is aimed at officials who have not previously engaged with WPS trainings from ASEAN-IPR or seldom familiarised themselves with WPS but will have relevant work in advancing the agenda through policymaking. This presented a challenge in the delivery since the invitation need to go through some steps and procedures and led to a lesser turn-out of participants than expected, as some AMS sent fewer number of participants than allocated, and some did not send representatives in the first training in September 2024. To mitigate this, invitations were also issued to participants from ASEAN Secretariat and several ASEAN institutions and sectoral bodies, but due to similar challenge of procedures and low association of their work with WPS, there was a low turnout in the first training. Learning from this, on Module 3 training in June 2025, invitations were sent out with enough time, resulting in a better turn-out and diversity of participants from 9 AMS, Observer State, and two ASEAN sectoral bodies participated (ADSOM and ACWC).

In all trainings, ASEAN-IPR tried to encourage gender-balanced participants, however with the nominations scheme, there were more female participants than male with some countries nominated all female participants, limiting discussions around male allyship and role of men in promoting gender equality and eliminating gender inequality.

All training sessions were conducted interactively, with group sessions, case studies, and interactive discussion. Participants found it especially useful to freely exchange knowledge with their peers from AMS governments. In the September 2024 training for Module 0, 1, and 2, several participants gave feedback that the schedule was too tight, and the duration was too long for 5 days, which was then taken as a lesson learned by ASEAN-IPR team to improve the delivery for Module 3 session in June 2025.

Based on the challenges and lessons learned from the delivery, the main recommendation for next year for delivery is to have an additional activity to enhance achievement of the outcome and its sustainability. This can be in the form of an additional refresher course, additional training session for more targeted participants (e.g., parliamentarians, Training of Trainers (ToT), all male participants to boost male allyship for WPS) or embedding the tested module into an online platform to be accessible for more government officials in ASEAN, along with embedding UK expertise where relevant.

Reporting
Both UN Women and ASEAN-IPR have provided their reporting in a timely manner as per the agreement, with UN Women providing a formal annual report and ASEAN-IPR providing their 6-monthly reporting. With UN Women, since May 2025 it was agreed to have a closer monitoring by having monthly catchups instead of quarterly, as the project is ramping up the delivery of activities. With ASEAN-IPR monthly regular catch-up has been scheduled and with increased frequency during preparation of training sessions.

Comms
Both UN Women and ASEAN-IPR comms have provided clear visibility of UK’s support, aligned with FCDO branding guidelines.

Engagement with UK diplomatic posts
The regional programme team ensures that UK diplomatic posts are engaged and updated, especially those with in-country activities. Taking up a recommendation from last year, a better streamlining has been apparent, indicated with more joined up coordination to ensure no duplication of effort provided by different source of funding to WPS agenda in countries. On UN Women, several UK diplomatic posts have been directly in touch with UN Women’s respective country offices. Apparent benefits were noted as a result of this direct engagement, for example where UK diplomatic posts had closer engagement to relevant stakeholders in government and CSO network and able to recommend their involvement to the programme activities, thus advancing the engagement and further contribute to the achievement of outcomes. Representation of UK diplomatic posts during in-country activities had found to be beneficial, not only to maintain visibility of UK’s support to the agenda in the region, but also to the achievement of outcomes. There is still room for improvement in coordination especially for Posts without UN Women country offices and Posts with limited resources, and to pick up interest in creating coordination channel between UK diplomatic posts, UN Women, and co-donor diplomatic posts, where possible and of high interest.

On ASEAN-IPR trainings, the regional programme team has updated UK diplomatic posts on the participants from respective countries nominated by the government officials. This was found to be useful for a follow-up agenda by UK diplomatic posts to advance UK support to WPS agenda.

Financial Performance
This year, challenges in financial performance in working with both UN Women and ASEAN-IPR were mainly maintaining accurate forecasting. Both organisations operate in different financial years (i.e., calendar year vs UK’s financial year) thus some spending occur across UK financial years, and both partners manage their accounts in USD. These challenges are addressed by closely engaging with both partners to maintain up-to-date record of forecast and spending regularly on top of FCDO financial systems and agree on a stable exchange rate with UN Women and ASEAN-IPR. As per FCDO PrOF rules the programme team also ensured both partners had evidently utilised at least 80% of previous disbursement before subsequent tranche is disbursed.

Within the review period, there were two disbursements made to UN Women as per the agreed Contribution Arrangement, in September 2024 and June 2025. Through regular check-ins, UN Women had a good track record of hitting their spending based on their regularly updated forecast. From the total contribution agreed of £3.05m, by end of May 2025, they have used 92% from the total contribution disbursed (£2.74m), before requesting release of the final tranche. Most of their programme activities were delivered until July 2025, and by July 2025 they have used 89% of the total FCDO contribution (£3.05m), indicating on track spending of full utilisation from committed contribution. UN Women has also provided the annual certified financial statement for their 2024 financial year in June 2025.

ASEAN-IPR received the first disbursement in late June 2024 for both ODA and non-ODA, a total of £188k as agreed in their Activity Based Budget (ABB). However, budget adjustments were made due to challenges of invitation lower turnout of participants, and thus actual spending was much lower than early forecast. By July 2025, 32% non-ODA funds and 84% ODA funds of the first tranche were utilised. On this, the FCDO programme team is doing close monitoring with the ASEAN-IPR team on updating the forecast and allocation for FY25/26, discussing the possibility to absorb the remaining balance, and ensure the subsequent disbursement is only made aligned with FCDO principles, to ensure minimum underspend. On audited financial statements, ASEAN-IPR will provide their 2024 certified financial statement in September 2025.

## G: MONITORING, EVIDENCE AND LEARNING

The programme’s M&E mechanisms are underpinned by a comprehensive results framework, developed and adapted from UN Women’s global results framework. This approach offers significant advantages, including efficiency and time savings, by bypassing the time-consuming process of creating a new framework from scratch. UN Women brings extensive sector-specific expertise, ensuring the framework remains relevant and effective. Notably, the work with ASEAN-IPR, particularly its training initiatives, has been integrated into the framework, given the alignment of its objectives with the broader goals of UN Women’s programme. Furthermore, the adoption of an established framework reduces risks associated with unforeseen challenges and benefits from UN Women’s adaptive capacities.

To ensure accountability and continuous learning, UN Women has established a quarterly reporting mechanism with the FCDO team to share progress updates and inform upcoming activities. In parallel, UN Women is commissioning an independent evaluation aimed at assessing the project’s results and examining its contributions to impact, sustainability, and capacity development. The evidence from this evaluation will inform the programme’s PCR and guide future strategic support for the WPS agenda in ASEAN. Additionally, ASEAN-IPR has demonstrated strong monitoring practices for its activities, including the use of post-training assessments, six-month follow-up surveys, and qualitative data collection through participants’ stories, providing valuable insights into the effectiveness and relevance of its interventions.

This annual review was developed through a combination of desk-based analysis and stakeholder consultations. It draws on reports from implementing partners and insights gathered through interviews with key stakeholders, including the UN Women team, ASEAN-IPR, the FCDO focal point at the UK diplomatic post in ASEAN, CSOs from Indonesia, the Philippines, and Vietnam, as well as government officials from the Philippines, Thailand, and Timor-Leste. These interviews were conducted through both in-person and virtual meetings, ensuring a comprehensive and inclusive perspective on the programme’s progress and impact.

While there is no formal learning strategy or plan developed for this programme, learning has been actively pursued through ad-hoc opportunities such as calls and meetings with delivery partners. These engagements, along with insights captured in partners’ reports, have helped document key lessons learned and inform timely adaptations to implementation. FCDO maintain close communication with delivery partners to ensure responsiveness to emerging needs and challenges.

Date of last narrative financial report	June 2025 (UN Women) / July 2025 (ASEAN-IPR)	Date of last audited annual statement	June 2025 (UN Women)

## Annexes

### Annex 1. Abbreviation

ACW	ASEAN Committee on Women
AMS	ASEAN Member States
AR	Annual Review
ASEAN	Association of Southeast Asia Nations
ASEAN-IPR	ASEAN Institute of Peace and Reconciliation
AWPR	ASEAN Women Peace Registry
CoE	Centre of Excellence
CoP	Community of Practice
CSO	Civil Society Organisation
GNWP	Global Network of Women Peacebuilders
MEL	Monitoring, Evaluation, and Learning
NAP	National Action Plans
ODA	Official Development Assistance
PCR	Programme Completion Review
PoA	Plan of Action
PrOF	Programme Operating Framework
RPA	Regional Plan of Action
TA	Technical Assistance
ToC	Theory of Change
ToR	Terms of Reference
WPPL	Women’s Political Participation and Leadership
WPS	Women, Peace and Security
YPS	Youth, Peace and Security

### Annex 2. Progress of Action from Previous Year’s Recommendations

Recommendations	Progress
Recommendation 1: Ensure multi-layer engagement is delivered within the programme activities, as this is essential to ensure political will in implementing the WPS agenda and its sustainability. This strategy is currently included in the plan for UN Women activities and ASEAN-IPR training course for the second year.	Progress made by enhancing activities under Output 2. Multi-layer engagement has been delivered in the ASEAN-IPR trainings, with the increasing seniority of participants by having junior- to mid-level officials on Module 1 and 2, and senior-level officials on Module 3. Diverse ministerial background was also ensured in the ASEAN-IPR trainings by involving participants not only from women’s ministries, but reaching to defence sector and other line ministries related to WPS. From UN Women activities, selected CSOs have been involved in NAP Academy training alongside government officials, and in all in-country activities more awareness raising to broader line ministries in implementing WPS NAP have been delivered to sustain greater political will.
Recommendation 2: Continue ensuring active knowledge exchange on national WPS policy framework development and implementation is embedded in relevant programme activities. Several AMS have successfully developed and launched their NAP WPS, in which other countries can learn further from their experience. The UK’s 5th NAP WPS can also be leveraged to share UK’s experience in NAP development and implementation, with regards to relevant regional, national and local contexts.	Progress made by enhancing activities under Output 2, with more knowledge exchange between AMS have been embedded within the regional programme activities. For example, in NAP Academy 2, Philippines and Timor-Leste were present as guest speakers for other AMS to learn from their experience in developing NAP, particularly on multi-stakeholder collaboration and non-traditional security issues. This knowledge exchange has also been one of the main added values from ASEAN-IPR trainings, as noted from participants’ feedback.
Recommendation 3: Follow up strong interest from several AMS in advancing their national WPS agenda. Through UN Women’s regional activities, an increasing interest to implement the WPS agenda at the national level has been discovered from AMS who are not currently involved in in-country activities. There is a plan to deliver additional activities in these countries and expanding the current activities in Timor-Leste with additional contributions from FCDO.	Progress made by enhancing activities under Output 4. Expansion of programme activities to Cambodia, Malaysia, Lao, and enhancement of activities in Timor-Leste has been delivered since October 2024, following agreement with UN Women in September 2024.
Recommendation 4: Regional UKMis ASEAN programme team to enhance engagement with UK diplomatic posts in relevant countries, as it is beneficial to help monitor and advise on national-level activities. This includes connecting UK diplomatic posts with implementing partners where needed, as their direct and closer engagement can provide additional support to implementing partners in identifying and engaging with stakeholders, as well as amplifying in-country activities to enhance participation and visibility for UK investments. Several posts that have been connected directly to UN Women have provided beneficial support in ensuring participation of targeted participants and follow-up after activities.	This progress is related to activities under Output 2, 3, and 4. UKMis team took a more proactive approach on providing list of contacts to Posts, which was found useful by UK diplomatic Posts for a follow-up. More frequent catch-up was set up after last annual review, with main channel for updates are through regular DL email and through ASEAN programme monthly update. More Posts were connected with implementing partner in-country (i.e., UN Women country offices), making it possible for several UK diplomatic posts to provide valuable inputs directly on CSOs and stakeholders to be engaged nationally and regionally, or taken follow up actions from participants, leading towards a more effective and cohesive implementation.
Recommendation 5: Regional UKMis ASEAN programme team to revamp engagement with ASEAN Secretariat and relevant sectoral bodies, to identify bottlenecks on ASEAN accreditation and align WPS efforts and priorities.	Engagement with ASEAN Secretariat and relevant sectoral bodies was strengthened, through contribution of UKMis to the ASEAN WPS Advisory Group Consultation Meeting and through progressing accreditation. A close engagement with a dedicated WPS officer sitting in ASEAN Secretariat who recently joined under the UN Women project, although not directly through UK and Canada support, was beneficial in strengthening the relationship.

### Annex 3. Reflection for Wider Programme Context and Programme Completion Review

- Close consultation with stakeholders in and flexibility of the workplan allowed the programme to adapt and response to changing needs and context on the ground, while contribute to longer-term outcomes. For instance, in Cambodia and Thailand there was interest to create national level WPS policy framework, but during the consultation in the delivery it was apparent that more political will across line ministries and senior officials is needed to secure the commitment. Thus, resources were quickly directed to gain more political will. The work WPS network across Thailand in responding to recent Thailand-Cambodia conflict through the WE Centre is also an example of a result in capacity-building enabling quick response of the situation.
- Regional-level activities helped to set ambition of the WPS agenda, to guide to localisation through knowledge exchange between ASEAN countries, while more impactful work of translating the agenda into local context and ecosystem is done on the national and sub-national level.
- The issue of sustainability within this programme should be assessed against the evidence base on how change on WPS implementation has been achieved, globally. The critical components are policy adoption and institutionalisation, resources (financial, human, political), accountability (including MEL frameworks) and cooperation. In many countries and contexts, policies and skills building are commonplace, yet institutionalisation and appropriate resource allocation lags behind. This programme has made good efforts across these core components of WPS implementation, with greater emphasis on policy development and internal government capacity building, but a final review should consider its efforts on sustainability in terms of whether these initiatives have led to enduring institutional change, consistent resource allocation, and mechanisms for accountability and cooperation that can be maintained beyond the programme’s lifecycle.
- From programme management standpoint, regional programme with in-country activities is a resource-effective scheme to deliver impact on the ground, with less extensive resource of programme management needed to be at every UK diplomatic posts. However, extensive coordination needs to be maintained in regional and national level, and in designing the programme the regional programme management team should consider the capacity of resources at related UK diplomatic post to be engaged with the programme activities.
- The co-donor setting within UN Women’s regional WPS project is a good practice to work with likeminded partners with ASEAN. This allows FCDO to deliver greater impact with resource-effective contribution, and to ensure no duplication of efforts with other ASEAN development partners. In the other hand, if future programmes want to do similar co-donor project, the team needs to be aware of the MEL challenges, especially if entering the co-donor project in the middle of the project’s timeline. It required significant effort to isolate UK-funded activities and their impact based on the source of funding and timeline. Completely isolating UK-funded activities and their contribution to the outcomes and impacts is challenging because activities funded by different donors are interlinked and collectively support the project’s overall achievements. This does not mean the UK should avoid such contributions in the future due to MEL challenges, but it highlights the need to be aware of these challenges in similarly structured programmes. To address this, early communications with UN Women and clear expectations regarding reporting and MEL needs from the UK, along with close monitoring, have proven beneficial and will continue to be important for the WPS programme.
- CSOs have been more engaged in this second year of FCDO contribution to the UN Women’s regional project. However, it should not stop there; a more meaningful participation of CSOs need to be embedded in future similar programme. NAP and RPA development processes should also be participatory and engaging CSOs meaningfully as in most cases they have greater oversight to the WPS agenda on the ground. Based on interviews with a couple of CSOs, concerns were raised about the depth and quality of their engagement in the NAP process. This suggests a potential area where the UK, in its role as a development partner and strategic convenor, could consider providing targeted support to both governments and CSOs to strengthen collaboration. Future programming should ensure there is a clear, strategic objective for CSO participation in the programme. CSOs involved in the programme to date have varied mandates; it will be critical to enable them to fulfil their objectives whether they be frontline service delivery, policy and advocacy, and holding their government officials accountable for WPS implementation.
- It is beneficial to continue monitor other regional policies relevant to the implementation of WPS agenda in ASEAN, i.e., ASEAN Community Vision 2045 and its Strategic Plans, which signals the interest of ASEAN in WPS agenda.
- WPS agenda was originated from UN Security Council Resolution 1235. In this context, as a UN body, UN Women is in a good position to implement and drive the advancement of UN agenda in the region. However, given UN Women are not present in all AMS equally and worked with other organisations to deliver programming activity, there is scope to consider a more suitable delivery model. For instance, this programme could be delivered by a consortium with UN Women as the prime contractor, or UN Women establishing a strategic partnership with one or more CSOs in each AMS with whom they jointly deliver activities. Consideration would need to be given to impact on the VfM, especially effectiveness and efficiency.
- The positioning of ASEAN-IPR as an ASEAN-related institution is also beneficial in working as an ASEAN-regional programme. In the early stages working with ASEAN-IPR, the team’s understanding of ASEAN ways of working has been accelerated, which was beneficial to drive the project success to achieve the output and outcome. If future programmes want to continue working with ASEAN-IPR, assessment of capacity and resources need to be undertaken, e.g., ensure there is sufficient human resources available within the project.
- The UK Mission to ASEAN has committed substantial financial, human, and political resources to this programme, working collaboratively with other regional missions, technical advisers, and engaging the WPS policy team in the UK. Given the constraints on resources for international programming, the Mission would benefit from more consistent and in-depth engagement from policy leads responsible for WPS and multilateral institutions. This programme represents a significant achievement for both thematic areas. To sustain the political momentum and goodwill established at the regional level, centrally managed programmes and/or leadership will be increasingly essential.
- In the future, aligning with ODA rationalisation, the UK can continue to explore ways to politically support ASEAN on the development of WPS agenda. Several suggestions that can be considered are:
  - The UK can continue to offer technical support to the WPS Community of Practice, by utilising gender experts within government and within civil society partners that have years of experience collaborating on WPS implementation. They could offer tangible advice to CoP members on a range of topics including policy development, securing funding, and monitoring and evaluation.
  - The UK has a WPS Helpdesk with a public repository of research reports, analyses and evidence syntheses. These are available for AMS and CoP members to use. We also have training material which we can make available to AMS for capacity building and network building.
  - The UK Mission to ASEAN could continue a political dialogue on WPS with ASEAN, for instance by taking part at a senior/expert level in ASEAN-led events or on an annual basis to maintain political momentum and discuss shared challenges and opportunities.
  - Ensuring high level statements of support for the promotion of the WPS agenda in ASEAN-UK agreed documents/statements, such as the next five-year ASEAN-UK Plan of Action.