# Amendment Letter to the Contribution Arrangement

Project Name: Empowering Women for Sustainable Peace: Preventing Violence and Promoting Social Cohesion in ASEAN - Advancing Women Peace and Security (WPS) in ASEAN
Project Number: 400029-401 (ODA) and 400029-403 (Non-ODA)

I refer to the Contribution Arrangement between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) and UN Women signed on 10 August 2023.

Further to recent correspondence, the FCDO proposes that paragraph 1 point (b) of the original Contribution Arrangement be amended by deleting the end date “31 December 2025” and substituting it with “31 March 2026”.

Following recent correspondence, FCDO proposes to increase the amount made available to UN Women by £70,000.

I propose that the figures and words “UK £3,051,784” in paragraph 1 point (e) of the original Contribution Arrangement be deleted and replaced with the figures and words “UK £3,121,784”.

Following recent correspondence, FCDO proposes to delete the Contribution Disbursement Schedule table in paragraph 1 point (g) of the original Contribution Arrangement and replace it with:
	Payment due date	UK£/Amount
1.	August 2023	£1,202,793
2.	September 2024	£1,544,182
3.	June 2025	£304,809
4.	December 2025	£70,000

The amount made available in point 3 above will be used for activities stated in Annex 1: Narrative for the additional funds below.

In addition, FCDO proposes to delete the Payment Request Form in Annex 2 of the original Contribution Arrangement and replace them with Annex 3: Partner Payment Request Form in this Amendment Letter.

This letter of amendment will place on record our common understanding of the above change(s) and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 2 / 2025.

Please sign both copies of this letter; return one to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:
Position:	Deputy Head of Mission and Political-Security Counsellor / UK Mission to ASEAN
Address/Contact Details:	UK Mission to ASEAN / Jl. Patra Kuningan Raya Blok L5-6 / Jakarta 12950 / Indonesia
Date:	11 December 2025

Signed on behalf of the Partner:
Name:
Position:	Officer-in-Charge / UN Women Regional Officer for Asia and the Pacific
Address/Contact Details:	UN Building, Rajdamnen Nok Avenue / Bangkok 10200, Thailand
Date:	9 December 2025

ANNEX 1 – Narrative for the Cost Extension

Empowering Women for Sustainable Peace: Preventing Violence and Promoting Social Cohesion in ASEAN.

This Annex provides a summary of the revisions incorporated into the updated Project Document (Annex 2), which reflects the three-month cost extension requested under Amendment No. 2 (January–March 2026). The updated Project Document consolidates all related programmatic and financial adjustments and supersedes all prior versions.

Executive Summary

This document requests a three-month cost extension for the regional programme Empowering Women for Sustainable Peace: Preventing Violence and Promoting Social Cohesion in ASEAN, supported by the Governments of the United Kingdom, Canada, and the Republic of Korea. Implemented by the UN Women Indonesia Country Office in its liaison role to ASEAN, the programme has contributed significantly to advancing the Women, Peace and Security (WPS) agenda in ASEAN, including the adoption of the ASEAN Regional Plan of Action on WPS (RPA-WPS) in November 2022 and the successful organization of the ASEAN WPS Summits.

The programme has fully delivered its expected results and generated strong, formal demand from ASEAN sectoral bodies for continued technical assistance. Institutions including ACW, ACWC, AICHR and the ASEAN Institute for Peace and Reconciliation have requested sustained coordination, policy advice, capacity development support, and regional knowledge functions as they move into the first full implementation cycle of the RPA-WPS.

This cost extension will consolidate results achieved to date and ensure continuity of core coordination and advisory functions during ongoing ASEAN consultations on the proposed Phase II of the programme (2026–2030). It will also support sustained donor visibility and UK leadership at a moment of strong political momentum.

Background

The programme aims to strengthen the capacities of ASEAN institutions and Member States to develop, coordinate and implement WPS frameworks at regional and national levels. It promotes knowledge exchange, multi-stakeholder collaboration, and peer learning among Member States, civil society, and youth networks.

The project is currently undergoing a final independent evaluation. Preliminary findings confirm that the programme is highly relevant and effective, with strong appreciation from ASEAN and Member State partners for the catalytic role played by UK support. The evaluation also highlights that continuity of technical assistance is essential to avoid slowing progress, given that several Member States are now moving from awareness-raising to policy formulation and implementation of WPS.

ASEAN is simultaneously undertaking internal consultations on the draft concept note for Phase II of the programme, led by the ASEAN Secretariat and the Advisory Group on WPS. This process is ongoing and will continue into early 2026.

Justification

The proposed amendment responds to a clear demand from ASEAN institutions to sustain the momentum of the Women, Peace and Security (WPS) agenda at a critical juncture for the region. Over the past two years, the project has fully delivered on its agreed results, achieving 100% of outputs and generating strong recognition from ASEAN, its Member States, and development partners. It has positioned the United Kingdom, alongside Canada and the Republic of Korea, as a leading partner in embedding WPS in ASEAN’s regional frameworks and national action plans. The success of the ASEAN WPS Summit in Kuala Lumpur in September 2025 further demonstrated the catalytic role of this initiative in mobilizing political will and multi-stakeholder partnerships across the region.

Three interrelated factors make this amendment both necessary and strategic.

First, ASEAN demand is high and formal. Multiple ASEAN sectoral bodies have requested UN Women continued technical assistance to sustain the Regional Plan of Action on WPS (RPA-WPS) implementation.

Second, consolidation of institutional achievements is required. The programme has established coordination mechanisms, advisory capacity, and a regional knowledge platform that are now relied upon by ASEAN institutions and Member States. The preliminary findings of the project’s independent evaluation (September 2025) confirmed that the initiative has been highly relevant, effective, and catalytic in mobilizing resources and political support. However, it also cautioned that any interruption in technical assistance would risk slowing progress.

Third, this amendment is a proactive risk management and sustainability measure. Extending the timeframe to March 2026 will enable the consolidation of achievements, sustain institutional mechanisms such as the ASEAN WPS Advisory Group and the regional knowledge hub. It also provides the space to leverage emerging synergies with related agendas, including Women’s Economic Empowerment (WEE), Ending Violence Against Women (EVAW), climate action, disaster risk reduction, and gender data systems—areas raised in dialogues with ASEAN leaders and partners during the Kuala Lumpur Summit.

At the broader regional level, the ASEAN context underscores the sustained engagement. Southeast Asia continues to face complex peace and security challenges, ranging from political transitions and protracted conflicts, to climate-related risks and transnational threats such as trafficking. At the same time, ASEAN has made gender equality and women’s leadership a priority in its Vision 2045 and gender mainstreaming frameworks. The WPS agenda is therefore not only a normative commitment but also a strategic lever for inclusive governance, social cohesion, and resilience in the region.

The proposed activities are designed to be self-contained and to deliver value regardless of the timeline or outcome of Phase II discussions. They focus on consolidating and sustaining ASEAN-led coordination and knowledge platforms rather than assuming immediate transition to a new programme phase.

In sum, the proposed amendment will:

- Directly respond to formal ASEAN and Member State requests for continued support.
- Consolidate the institutional mechanisms and knowledge platforms established under Phase I to enable sustained, ASEAN-led implementation of the RPA-WPS.
- Reinforce donor visibility and UK leadership at a time of heightened political momentum following the ASEAN WPS Summit.
This cost extension is modest in scope but high in impact. It represents a strategic investment to protect results, maintain ASEAN’s confidence, and position the United Kingdom as a champion of sustainable peace and inclusive governance in the region at a decisive moment.
ASEAN-Regional level requests
- ASEAN WPS Advisory Group: Requested resources to sustain the ASEAN WPS website
- ACW Cambodia: Requested technical support to chair the Advisory Group, including support for planning and monitoring of ASEAN RPA-WPS implementation
- AICHR: Requested continuation of workshops on developing a gender-responsive regional conflict prevention and resolution mechanism.
- ASEAN Institute of Peace and Reconciliation: Knowledge and communication products highlighting WPS–Youth Peace and Security (YPS) linkages for regional advocacy

Proposed New Activities and Alignment with the Logframe of the Project

The additional funding of £70,000 will be used to reinforce the sustainability of the results achieved in the final year of implementation and ensure continuity of core coordination and knowledge functions during the transition to the next phase of the programme.

Immediate Outcome 1: ASEAN Secretariat, sectoral bodies and institutions have increased access to gender and WPS expertise to develop regional policies on WPS and related frameworks.

Output 1.1: Technical assistance provided on the development and implementation of regional policy frameworks on WPS and related gender equality frameworks.

Indicative activities include:

Provide technical assistance to the ASEAN WPS Advisory Group to oversee, plan and report on the implementation of the ASEAN RPA-WPS
  - Facilitate the planning and convening of the 9th ASEAN WPS Advisory Group Meeting, including support to Cambodia as Chair,
  - Support a planning workshop involving representatives from the three ASEAN Community pillars to agree on strategic priorities and coordination arrangements for the next five years of RPA-WPS implementation; and
  - Support coordination and follow-up processes to ensure continuity of monitoring and reporting on RPA-WPS implementation across ASEAN sectoral bodies.

This support will involve working with ASEC PEGD and the ACW Chair to co-facilitate the application of the ASEAN RPA-WPS monitoring template and reporting process, including through a planning workshop, thereby supporting Member States to implement a clear and practical mechanism for tracking progress.

Immediate Outcome 2: ASEAN sectoral bodies and institutions and non-state actors have strengthened capacity to implement the WPS agenda.

Output 2.1: Technical assistance provided to build capacity of ASEAN sectoral bodies and government stakeholders on WPS.

Indicative activities include:

- Provide technical assistance to the ASEAN Intergovernmental Commission on Human Rights (AICHR) to advance the development of a gender-responsive regional conflict prevention and resolution mechanism.
  - Convene a regional expert consultation (10 in-person participants, depending on cost-sharing opportunities identified by AICHR) to review the current draft framework, gather feedback and refine recommendations.
  - Provide streamlined follow-up technical and advisory inputs to ensure that WPS considerations are integrated within the emerging framework, in line with AICHR’s minimum feasible commitments.

Immediate Outcome 3: A regional platform for cooperation and advocacy among ASEAN Member States, observer State, sectoral bodies, civil society organizations, youth networks and women’s organizations is strengthened, promoting good practices and evidence on WPS.

Output 3.2: Technical assistance to support the development and sustainability of ASEAN’s knowledge hub on WPS.

Indicative activities include:
- Ensure the continued maintenance and sustainability of the ASEAN WPS website as the regional knowledge hub for Member States, CSOs, and youth.
- Document and disseminate lessons learned from programme implementation to support regional learning and inform continued roll-out of the RPA-WPS.
- Organize a visibility and knowledge-sharing event highlighting regional achievements and progress in the implementation of the RPA-WPS.
- Produce advocacy, communications and awareness-raising knowledge products highlighting linkages between the Women, Peace and Security (WPS) and Youth, Peace and Security (YPS) agendas to support inter-generational engagement and regional advocacy. The focus here is on knowledge dissemination, rather than new research.

Timeline
The cost extension will cover the period from January to March 2026.

Indicative activities	2026
	January	February	March
Provide technical assistance to the ASEAN WPS Advisory Group to oversee, plan and report on the implementation of the ASEAN RPA-WPS
Provide technical assistance to the ASEAN Intergovernmental Commission on Human Rights (AICHR) to advance the development of a gender-responsive regional conflict prevention and resolution mechanism.
Ensure the continued maintenance and sustainability of the ASEAN WPS website as the regional knowledge hub for Member States, CSOs, and youth.
Document and disseminate lessons learned from programme implementation to support regional learning and inform continued roll-out of the RPA-WPS
Organize a visibility and knowledge-sharing event highlighting regional achievements and progress in the implementation of the RPA-WPS.
Produce advocacy, communications and awareness-raising knowledge products highlighting linkages between the Women, Peace and Security (WPS) and Youth, Peace and Security (YPS) agendas to support inter-generational engagement and regional advocacy.
Salaries
Support costs