## Annual Review Template

Light-Touch Annual Review: 2023/2024 EPICS Programme

Title: Empowering Palestinian Institutions and Civil Society (EPICS)
Programme Value £ (full life):		Review date: 1st Review (Sept 2023 – March 2024)
Programme Code: 400030	AMP start date: September 2023	AMP end date: 31 March 2031

Summary of Programme Performance
Year	2023/2024
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400030
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400030 Documents

A. SUMMARY AND OVERVIEW

Empowering Palestinian Institutions and Civil Society (EPICS) is a British Consulate General Jerusalem (BCGJ) programme designed to support viability, legitimacy and inclusion of governance and service delivery in the Occupied Palestinian Territories (OPTs). EPICS implementation began in September 2023. This review, which is the first annual review of EPICS, covers the first six months of implementation (September 2023 – March 2024). Two of the five components of the programme were initiated and started to be delivered during this period. The early phase of implementation was focused on team mobilisation, mapping and building relationships with stakeholders, and agreeing EPICS interventions with counterparts, particularly those from the Palestinian Authority (PA). This has been a challenging period given the October 7th attacks, subsequent war in Gaza and deteriorating situation in the West Bank, which has shifted the landscape in which EPICS is delivered and delayed the start of some programme activities or required adaptations to be made. Subsequent reviews will incorporate other components of the programme as they get underway.

Description of programme
EPICS aims to improve the viability, legitimacy and inclusion of governance and service delivery and to protect and support civic space and empower women in the OPTs. Effective Palestinian institutions are essential to maintain stability and delivery of basic services to 5 million Palestinians across the West Bank and Gaza. They are also essential to realise progress towards a Two State Solution (2SS). The UK has a strong interest in strengthening the PA and Palestinian civil society, maintaining stability in the OPTs and Israel and sustaining prospects for a resolution to the conflict.
The EPICS programme will provide technical assistance across a range of governance sectors, including:
- Supporting the Palestinian Authority in areas such as public financial management and tax, transparency and accountability, centre of government processes, anti-corruption, rule of law, elections and political participation.
- Supporting Civil Society Organisations (CSOs) to hold the Palestinian Authority (PA) and other local duty bearers to account for governance and service delivery.
- Working to strengthen women’s empowerment, primarily through supporting local and grassroots organisations to advocate and build capacity for women and other marginalised groups.
EPICS will be delivered through the following components:
- a contract with a supplier to provide monitoring, evaluation, research and learning (MERL). BCGJ is in the process of appointing a central MERL partner (via the OPTIMEL programme) for all ODA programmes in the OPTs, which will take on this function for EPICS.
- contracts with suppliers to provide technical assistance to PA institutions.
- a contribution agreement (CA) with UNDP for its Transparency, Evidence, Efficiency, Effectiveness and Accountability (TEA) programme.
- an accountable grant agreement (AGA) with one or more international NGOs and/or Palestinian Civil Society Organisations.
One of these components, the TEA3 Programme being implemented by UNDP, is fully operational. The TEA3 programme is jointly funded by the UK and Sweden to support institutional development in two thematic areas – 1) transparent and accountable management of public resources and 2) improved integrity for effectiveness in priority sectors that provide services and utilities to citizens.
The civil society component is partially operational. The Coalition for Accountability and Integrity (AMAN) is implementing activities designed to strengthen civic space by empowering CSOs, women and other minorities. Work is also ongoing to commence implementation of a project with the Palestinian Independent Commission for Human Rights (ICHR).
The set-up of the MERL work and technical assistance to the PA will take place during the next review period. When operational, the MERL supplier, appointed via the OPTIMEL programme, will monitor progress and evaluate the performance of the entirety of EPICS, as well as gathering lessons from implementation. MERL will be undertaken concurrently with other strands of EPICS delivery, so that programme activities can adapt and take on board lessons learned in real time. The technical assistance to PA institutions will comprise of support to Public Financial Management (PFM) and Centre of Government processes, focused on Public Administration Reform (PAR). During this review period the design and set-up of these components was underway. Progress on these interventions will be captured during the next reporting period.
EPICS’s impact is the ‘improved viability, legitimacy and inclusion of governance and service delivery in the OPTs’. EPICS has four outcomes:
  1. Outcome 1: Improved PA finances, better directed towards the equitable provision of quality public services.
  2. Outcome 2: Improved accountability for governance and service delivery in the OPTs.
  3. Outcome 3: Better protected and more vibrant civic space; and
  4. Outcome 4: Greater empowerment and inclusion of women.
However, in light of the challenging operating environment during the review period – with the October 7th attacks and subsequent war in Gaza – and the fact that not all the components of EPICS started during the programme inception period, this review is not assessed against the programme’s impact or outcomes. It was assessed against the outputs captured in the provisional logframe of EPICS as summarised below:
Output 1: Improved capabilities of government institutions for effective and efficient management of public resources in an inclusive and accountable manner. ​
- Output indicator 1: Progress on establishing a structured dialogue mechanism between the government and civil society, measured by per milestone achieved.
- Output indicator 2: Number of governmental units displaying improved transparent practices disaggregated by type of government unit.
Output 2: Improved capabilities of civil society and private service providers for more accountable, inclusive, effective and efficient service provision. ​
- Output indicator 1: Number of assessments/indices produced examining gaps in civic space providing recommendations for closing them.
- Output indicator 2: Number of CSOs - including media outlets and public utilities - actively engaged to increase transparent, inclusive, accountable, effective and efficient service delivery.

Annual outputs assessment:

No.	Output	Score	Weighting %
1	Improved capabilities of government institutions for effective and efficient management of public resources in an inclusive and accountable manner.	A	50%
2	Improved capabilities of civil society and private service providers for more accountable, inclusive, effective and efficient service provision.	A	50%

The overall score of A was given because delivery against the two outputs assessed met expectations. The socio-political context in the OPTs since October 2023 made it challenging to assess progress towards the programme’s impact and outcome for this review period. This informed the development of a provisional logframe which guided the two programme components currently being implemented.

## Major lessons and recommendations for the year ahead

Despite making progress, the programme team has identified some key challenges and lessons learned and proposed a number of recommendations, as set out below.

### Challenges:

- The attacks of October 7 and subsequent war in Gaza had an impact on the implementation of EPICS. The October 7 attacks took place a number of weeks after EPICS was launched. The uncertainty of the time, as well as the insecurity and overall instability in the OPTs made programme implementation difficult, if not impossible in certain contexts. This led to the rollback or pause of some planned activities. All activities planned to take place in Gaza under both AMAN and UNDP were halted. This included internal assessment of downstream partners, index assessments, and activities related to prompting civic space and gender empowerment. Offices were also damaged, resulting in re-directing implementation of activities to the West Bank only. Despite these challenges, we currently assess that the overall objectives of EPICS and the Theory of Change (ToC) remain relevant, although this will be reviewed in further detail during the next reporting period.
- Political sensitivities around state institutions need to be carefully navigated in implementing some components of EPICS. Issues such as public financial management, transparency, accountability, and institutional reforms are often politically sensitive and naturally attracts political interest and from within Palestinian society. As such, it is important to take time to foster buy-in of all relevant stakeholders before proceeding.
- The inability to operationalise all the components of EPICS at once due to their different dynamics and resource requirements has made programme coordination sometimes challenging. Capacity within the team is stretched, and the fact that the EPICS team in BCGJ needed to work on the crisis response during the reporting period limited the team’s ability to set-up all EPICS components concurrently. Priority was given to operationalising components which could deliver immediately (such as UNDP TEA, which was previously delivered through the SSRP programme), freeing up time to undertake the scoping and design needed for the Centre of Government and PFM support, which require more active management. Delivery of only some EPICS interventions has made the development of a holistic logframe for the programme difficult.
### Lessons learned

- The EPICS programme is inherently politically sensitive as it aims to enhance the accountability and transparency of the PA’s institutions, protect civic space, and promote women and other marginalised people’s rights. Doing this will challenge existing power dynamics and societal norms. As such, to achieve these goals, EPICS will have to be agile and flexible in approach and develop the capacity to adapt to the changing political context, obstacles and opportunities that might emerge during implementation. Programme interventions are most effective when delivered alongside wider policy interventions, such as advocacy and support on key areas of reform.
- The programme will need to be flexible and adaptive, reflecting that the ongoing crisis might have an impact on the programme’s implementation, altering the context in which EPICS is operating and some of the assumptions on which its design was based. There is a need to develop an adaptive approach and identify ways to mitigate the risks of further delays to implementation. It is important to continue to seek the close involvement of Palestinian stakeholders in the design and implementation of EPICS activities, including ensuring broad and systematic consultation with PA counterparts to tackle barriers to implementation.
- EPICS requires active management by BCGJ meaning that resource requirements are high relative to the level of spend. This has meant that not all elements of EPICS could be set-up at the same time, given the time each of these projects needs to be designed and tested.
- The logframe should be updated and unified, to ensure that once all components are operational, we can assess and evaluate progress against the overall impact and outcomes. The ToC should also be reviewed to accurately assess whether EPICS interventions are improving the viability, legitimacy and inclusion of governance and service delivery in the OPTs.
- Coordination between EPICS components is needed to ensure that EPICS works as a holistic programme and is not being delivered as piecemeal projects. This is needed to ensure that interventions are mutually reinforcing (i.e. identifying shared recommendations to improve accountability, for example) and not duplicative. It could be achieved by establishing a programme steering committee, and by ensuring consistent processes to manage programme delivery, reporting, results collection and risk management are adopted for each delivery partner.
### Recommendations
Recommendations	Responsible	Timeline
Operationalise other components of EPICS in order of priority, impact and resource availability within the next reporting period	SRO / PROs	March 2025
Assess capacity within team to deliver EPICS and take steps to increase resources and expertise if deemed necessary	SRO	July 2024
Review EPICS business case to ensure the respective components remain relevant	PROs / SRO	December 2024
Reassess the political context using PEA and refine priority areas for interventions	Implementing Partners and SRO	Ongoing
Develop a unified logframe for all programme components once operational, to ensure there is a single set of objectives which sets out clear and realistic expectations over the remainder of the programme, ensuring there are SMART milestone targets.	SRO/PRO/ / Implementing Partners	December 2024
Ensure all components of the programme governance architecture are constituted – they include lead technical advisors for each intervention, a technical steering committee, and Programme Board.	SRO	March 2025
Continue to develop a comprehensive risk register and mitigation strategy in light of the evolving context, and as new EPICS components come online, in line with the business case.	SRO/PROs/ Implementing Partners	March 2025
Ensure that EPICS is delivered in conjunction with wider FCDO policy and advocacy efforts to improve the accountability, legitimacy and inclusion of governance in the OPTs. Develop an advocacy strategy with the BCGJ Political Team.	SRO/PROs/BCGJ colleagues	Ongoing, with strategy developed by March 2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

The programme's Theory of Change (ToC) is centred on the premise that by supporting Palestinian institutions, strengthening civil society engagement, promoting transparency, and empowering women, the integrity of governance and service delivery in the OPTs will improve. The ToC assumes that achieving these outcomes will lead to greater public trust, reduced corruption, and more inclusive decision-making processes.

The ToC is based on the assumptions that certain elements of social stability remain the same. These assumptions are that:
- The PA does not collapse during EPICS implementation.
- The UK is willing and able to work with and support the PA.
- The Government of Israel (GoI) does not undertake drastic actions that impede governance and stability in the OPTs.
- The PA is ready and willing to engage with CSOs and vice versa, including on the promotion of women’s empowerment and other minority rights.
- PA institutions are receptive to technical assistance and the space for reform exists at the technical and political level and within critical thematic scope.
- Neither the GoI nor PA take drastic steps that will affect stability including the closure of the civic space.
So far, despite the war in Gaza and its subsequent impacts, the operating environment in the West Bank has remained sufficiently stable to deliver EPICS activities. This enabled progress to be made on two outputs and their indicators were assessed during the review period. There is however a need to revisit the ToC once the remaining components of EPICS are operational to ensure the programme’s outcomes and outputs together with their indicators are well aligned to the objectives of these components. This should inform the development of a unified logframe upon which future reviews will be based.
## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Improved capabilities of government institutions for effective and efficient management of public resources in an inclusive and accountable manner.
Output number:		1	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	Not Applicable

Indicator(s)	Milestone(s) for this review – March 2024	Progress
1.1 Progress on establishing a structured dialogue mechanism between the government and civil society.	1 Dialogue mechanism initiated between CSOs (UNDP)	Met: Dialogue mechanism with PA been achieved / 21 community consultation workshops across West Bank, 7 seven reports were developed and disseminated to the line ministries. (UNDP) / One high-level meeting with civil society to discuss the National Policy Agenda. The National Priorities report is being finalised and disseminated to the Prime Minister’s Office. (UNDP) / 1 social accountability initiative was developed and implemented by the downstream partner Miftah. (AMAN)
1.2 Number of governmental units displaying improved transparent practices disaggregated by type of government unit.	2 government units disaggregated by type of / government units. / Two e-services solutions are introduced, developed for local citizens. / National / Local / 2 capacity building programmes targeted the Women Against Corruption Network (NED) members. (AMAN)	Met: 2 government units targeted / Ministry of Health: / Patient Care Evaluation System (PCES) implemented: 15 public health facilities/departments/hospitals. / Local Hospitals Boards (LHBs): formation of 11 LHBs in 11 public hospitals. / Ministry of Finance: / Digital Citizen Budget (DCB): Created 10 DCB for ministries/public institutions. / Two digital solutions achieved: / Property tax e-services: for local citizens utilization: www.palestine.ps/account/login, embedded within Hokumati platform / For expatriates living in the diaspora through www.pt.pmof.ps. / 2 capacity building programmes targeted NED members on ITA (Integrity, Accountability, Transparency), social accountability and gender-corruption were conducted in the West Bank.

Output 1: Positive progress was made by the UNDP towards this output as the two milestones set for the review period were achieved. Despite the challenges in the policy landscape, UNDP built momentum to progress the establishment of a structured dialogue mechanism between government and civil society. Consultations were undertaken with major stakeholders including PA officials, the private sector, and civil society organisations including those representing girls, women, and other minority and vulnerable demographics. These two milestones were achieved including:

Stakeholder Consultation: UNDP supported consultation workshops across the West Bank focusing on seven basic services sectors, which led to improved outcomes across PA institutions including health, interior, local government, refugee affairs, youth and sports, consumer protection, and public procurement. They include:
      - Agreement with the Higher Council for Youths and Sports (HCYS) to focus on a few entry points including revising and amending by-laws related to the structure of youth clubs to enhance their transparency and capacity to better serve the youth population, and the development of a digital evaluation platform for these clubs.
      - Addressing the accountability deficit and development of dialogue mechanisms to support the Government Planning Process and strategies at the Prime Minister’s (PMO). UNDP is in the process of signing an agreement with the PMO to provide support to the Government National Planning Process.
      - Agreement signed with Human Rights and Democracy Media Center (SHAMS) to conduct 21 sector workshops with CSOs and community-based organizations throughout the West Bank. All 21 workshops have been held and 6 of the 7 draft reports have been forwarded to UNDP for review. The reports provide recommendations to be incorporated into the government strategies.

Organized high-level meetings and provided reports on national priorities to the PM’s Office. They include:
      - Several meetings with officials of the Ministry of Health (MoH) to finalize the National E-Health Strategy and to identify other areas of intervention. Areas identified include the digitalization of the licensing and accreditation unit at MoH including in Gaza; the picture archiving and communication system (PACS) for Primary Health Care centers in Gaza; and digitizing the inventory for medical equipment.
      - Discussions with the Department of Refugee Affairs (DORA) on creating an interactive digital platform to be used by DORA and Refugee Popular Affairs Committee (PSC) to strengthen their information gathering capacity including complaints from residents of camps. Discussions were also held on how the legal review of the PSC’s by-laws will be conducted in addition to a policy paper on any agreed modifications.
      - Discussion with the High Council for Public Procurement Policies (HCPPP) on promoting affirmative action in public procurement.
      - Discussion with the Consumer Protection Association (CPA), Palestine Economic Policy Research Institute (MAS) on the status of consumer protection in the OPTs. UNDP also worked with MAS on a perception survey which will provide a roadmap for future engagement. This includes a study on the oversight mechanisms of public utilities (water, electricity, and communications (landline, mobile and internet).
      - Engagement with the Association of Palestinian Local Authorities (APLA) on how best to support local governance in the OPTs. So far, a local governance political economy analysis has been drafted and finalised, and several visits to local authorities have been conducted in preparation for a strategic discussion with relevant stakeholders around the future of local governance including laws, systems, structure, decentralisation and elections.

Patient Care Evaluation Systems (PCES): Work was finalised on the PCES that resulted in improved service delivery in 15 public health facilities/departments and hospitals under the Ministry of Health. Data collection was also concluded for all Public Hospital in-patient wards. This was used as baseline data for drafting updated guidelines for the PCES on the utilisation of the system in the in-patient wards. Other achievements recorded include:
      - Completion of satisfaction surveys and associated programming Terms of Reference for scaling up the Patient Care Evaluation System in Emergency rooms, Outpatient Clinics, and District Health Directorates in the West Bank.
      - Concluded plans to roll out PCES in all government hospitals in Gaza as well as at three hospitals in East Jerusalem (St. John, Maqassad and PRCS) as well as in one NGO hospital in Hebron (Al Ahli).
      - Finalising the process of procuring an initial 150 heavy duty tablets (including stands) that will be distributed between 34 hospitals and 15 directorates.

Digital Citizen Budget (DCB): Achievements recorded during the review period include:
      - An agreement signed with MIFTAH to introduce digital budget in 10 public institutions in addition to the five previously rolled out under TEA. MIFTAH and the Ministry of Finance are identifying beneficiaries of the rollout. MIFTAH will work with relevant stakeholders to prepare a policy paper about the institutionalisation of digital citizen budgets and share with the Government cabinet.
      - A system where citizens can register online and receive a username and password introduced in the Property Tax Department. Once they register and are approved, citizens will be able to see their property tax records, issue receipts, and make payment online. Currently, the system is being tested.
      - UNDP has insured that the issuance of clearance certificates is integrated as part of the E-Government Platform.

Output Title	Improved capabilities of civil society and private service providers for more accountable, inclusive, effective and efficient service provision.
Output number:		2	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	Not Applicable

Indicator(s)	Milestone(s) for this review March 2024	Progress
# of assessments\indices produced examining gaps in civic space providing recommendations for closing them.	No. of gaps in transparency, participation, and integrity in access to power identified (AMAN) / 2 pre-post training evaluation questionnaire assessment identifying gaps in civic participation conducted. / 2 think tanks formed to develop sets of indicators for civic space protection and participation.	Met: / 10 existing gaps were identified (AMAN): Crucial gaps were identified in existing public policies, through AMAN’s study, which highlighted the inadequacies in these indicators and the absence of the political will to address them as challenging to civic engagement as well as the ability of CSOs to function effectively. / 2 pre-assessments for the West Bank conducted. Interventions planned in Gaza were shifted into 4 fact sheet studies. / 1 think tank and 2 sets of indicators for West Bank achieved – Gaza Strip work postponed due to the war.
# of CSOs - including media outlets and public utilities - actively engaged to increase transparent, inclusive, accountable, effective and efficient service delivery.	3 CSOs including media outlets are actively engaged to increase transparent, inclusive, accountable, effective, and efficient service delivery (UNDP).	Met: / 2 media outlets (MAAN & WATTAN) engaged in strengthening public awareness of solutions, services, and mechanisms and in promoting transparency and accountability. / 1 CSO (MIFTAH) engaged to simplify, digitise, and publish the annual budgets of 15 PA ministries and government entities during 2023, as follows: 5 social sector PA ministries (Social Development, Labour, Economy, Health & Finance).

Output 2: AMAN, the implementing partner of EPICS civil society component, achieved significant progress in their milestones. The following achievements were recorded in the review period.

Stakeholders’ engagement: AMAN was able to set up a foundation to engage with the new PA government. This was in line with their previous approach in ensuring a firm and objective relationship with state officials. AMAN coalition was the only civil society organization that was proactively approached by the new government to jointly shape national policy.

Civic space and challenges to good governance: a deep dive was carried out to map out the persistent challenges to civil society and effective governance structures using 44 indicators such as access to information, robustness of legal frameworks and effectiveness of institutional structures. Crucial gaps were identified in existing public policies, and the study highlighted the inadequacies in these indicators and the absence of the political will to address them. These gaps post challenges to civic engagement as well as the ability of CSOs to function effectively. AMAN's efforts in this regard are crucial as they will contribute to future advocacy and policy interventions aimed at addressing these gaps and fostering a more conducive environment for CSOs to participate effectively in governance processes.

Factsheets on the Gaza war: AMAN produced four separate factsheets on the Gaza war which provided insights into a probable post-war scenario including the role of the PA government in the West Bank. These documents analysed post-war scenarios, evaluating their potential impact on governance integrity and compliance with legal frameworks. Furthermore, AMAN delved into the roles of key ministries in the West Bank, assessing their effectiveness in critical areas such as consumer protection, humanitarian aid distribution, and medical referrals. These findings will inform future advocacy efforts and policy recommendations to enhance governance and address societal challenges. The factsheets are testament to EPICS agile nature, as well as its ability to adapt to the challenging and changing context.

Establishing strategic partnership with Miftah: AMAN established a new relationship with the Palestinian Initiative for Deepening Global Dialogue and Democracy Foundation (MIFTAH) as its downstream partner on supporting community engagement and empowering women at the local governance level. AMAN carried out due diligence on four CSOs before selecting MIFTAH to ensure compatibility and effectiveness. An internal committee established selection criteria based on expertise in civil rights, governance capacity, financial stability, and alignment with programme objectives. This partnership led to a joint initiative aimed at enhancing community engagement in policymaking and improving accountability. Comprehensive training programmes on emergency response planning were conducted for 123 women across 7 governorates as a result of the partnership.

Women Against Corruption Network (NED): AMAN successfully reactivated NED, a coalition of CSOs focused on combating corruption and gender-based inequality. Significant progress was made in strengthening NED and building the capacity of its members during the reporting period. Steps taken included developing internal bylaws, membership frameworks, and strategic objectives. Two meetings were held to establish the founding committee and formulate an annual plan. AMAN also conducted a comprehensive three-day capacity-building training for 32 women from the NED, enhancing their understanding of integrity, transparency, accountability, combating corruption, and corruption related to gender. Participants showed significant improvement in knowledge and skills related to these topics, empowering them to prevent acts of corruption and gendered corruption within their institutions. These initiatives collectively aimed to empower women in anti-corruption efforts, reduce corruption, and promote gender equality within Palestinian institutions.

## D: VALUE FOR MONEY (1 page)

      EPICS is a seven-year programme, running from April 2023 until March 2031, with a total budget of £35 million (£5m annually). Given the programme is still in early implementation, it is not possible to undertake a full value for money (VFM) assessment at this stage. A VFM assessment will be carried out in the next review period.
Certain assumptions based on previous programme experience reflected in the EPICS business case have proven to be true in this review period. Previous experiences have shown that implementing governance programmes can offer good value for money despite the challenging implementation context. This has held true given the results achieved in the review period with comparatively low funding; AMAN (£110k) and UNDP (£1m) in the review period and the result delivered. In subsequent reviews, we will assess specific performance indicators against the 4Es (Economy, Efficiency and Effectiveness and Equity) to ascertain if the programme has delivered appropriate value for money.

E: RISK [½ to 1 page]

The overall programme risk at the start of EPICS was Major. This is still the case for all the risks identified in the business case including reputational, value for money, contextual, and fiduciary. The protracted war on Gaza, which could threaten stability in the West Bank and the PA’s ability to continue to govern, along with continued regional uncertainty continues to pose a major risk.

There is however a need to continue to develop the overarching risk register for the programme, particularly as new components become operational, which will include risks identified by BCGJ and EPICS implementing partners. These risks should be aligned and consolidated across components to avoid duplication and enhance effective risk management. The register should inform the development of a mitigation strategy and plan which, together, will help the SRO to oversee and manage risks effectively.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

The MERL component of the programme will be launched and fully operational before the next review. However, during the period under review, the team monitored progress in line with FCDO Programme Operating Framework rules, through the following:

- Regular meetings: This is on a bi-weekly basis with UNDP, AMAN and relevant PA counterparts. The meetings were used to discuss progress, as well as any issues and challenges that needed to be addressed to ensure smooth implementation.
- Monthly and quarterly progress and financial reports submitted by EPICS implementing partners were reviewed on an ongoing basis by the EPICS project team.
- Quarterly review meetings were also held with delivery partners, to discuss progress, address any challenges, and review anticipated deliverables for the next quarter.
- Field visits were carried out by AMAN and UNDP to activity locations for on-the-spot assessments. The results of these assessments were analysed and are regularly discussed with FCDO team.

Date of last narrative financial report	n/a	Date of last audited annual statement	n/a