## Annual Review Template

Title: Empowering Palestinian Institutions and Civil Society in Palestine (EPICS)
Programme Value £ (full life): £35,000,000		Review date: Apr-March 2025
Programme Code : [AMP 400030]	AMP start date: July 2023	AMP end date: March 2031

Summary of Programme Performance

Year	2023-24	2024-25	2025-26
Overall Output Score	A	A
Overall programme risk rating	Major	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400030 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400030 Documents

## A: SUMMARY & OVERVIEW

Description of programme [1-2 paragraphs]

UK governance support in Palestine helps to realise the UK’s policy objective to preserve the viability of a unified Palestinian State, which is governed and secured by the Palestinian Authority (PA), in support of a negotiated settlement delivering a two-state solution. The British Consulate General’s (BCGJ) Empowering Palestinian Institutions and Civil Society (EPICS) programme aims to improve the viability, legitimacy and inclusion of governance and service delivery in Palestine, with a particular focus on protecting the fiscal viability and legitimacy of the PA in a declining political and socioeconomic context and building the effectiveness, accountability and transparency of PA institutions to support stability and deliver basic services equitably. EPICS also aims to protect and support civic space and empower women in Palestine, helping to hold the PA and other local duty bearers to account. Through improving PA viability and legitimacy, it can help to reduce the drivers of instability and extremism. EPICS is designed to be a flexible programme responding to changes in context over the implementation period. EPICS complements the work of the UK Envoy to the Palestinian Authority on Governance.

EPICS is multi-component programme delivered through the following active components. Two are under development.
1. Commercial contract with Adam Smith International subcontracting Tetra Tech, via an arrangement with the Public Finance Resource Centre (PFRC) Programme, to provide technical assistance and support to the PA on Public Finance Management (PFM) and revenue mobilization systems (Active since November 2024). The project is known locally as Isnad.
2. Contribution Arrangement with UNDP, to deliver the joint-funded Transparency, Evidence, and Accountability (TEA) programme. TEA works with both PA institutions (supply-side) and civil society (demand-side) to help them to be more transparent and more accountable to the Palestinian population (Active: July 2023).
3. Accountable Grant with AMAN Coalition for Accountability, to protect civic space, promote external accountability, build trust with citizens, and empower women’s political rights (Active Sept 2023).
4. MoU Agreement with the Independent Commission for Human Rights (ICHR), to undertake activities to defends human rights, support accountability of authorities, and provides capacity-building support to state and non-state actors (Active: Sept 2024).
5. Planned procurement, to provide technical assistance to strengthen the PA’s centre of government processes (under development).
6. MoU Agreement with UK GCSI, to conduct a short-term field visit to assess PA’s communication capacity and capabilities and produce key technical recommendations for future support (March 2025). This project is likely to continue into the next financial year (under development).

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This is the second annual review and focuses on assessing progress made under EPICS’ live projects between April 2024 to March 2025. The overall score has been assessed as an A. The achievements and progress made at the output level, including establishing a strong foundation with the PA government, and a more engaged civil society, remain highly relevant to the programme theory of change (ToC) and the outcome statement, both of which are assessed to remain valid in the current context. EPICS is well positioned to respond to emerging political opportunities, supporting the viability, legitimacy, stability and accountability of the PA.

Despite the challenging political context and the ongoing war in Gaza ongoing during the reporting period, EPICS has continued to perform and mobilise well, delivering timely and relevant interventions and responding to an increasingly challenging context across Palestine. In this reporting period, EPICS has continued to be in its mobilisation phase with some planned components yet to be initiated. Support via the UNDP TEA project has been instrumental in enabling the PA to implement its reform agenda and boost engagement and communication with civil society and the public. It has done this through a range of initiatives which have promoted digitisation, strengthened mechanisms for accountability, and facilitated dialogue between the PA and its people. This is delivered alongside activities implemented by CSO EPICS partners, including the AMAN Coalition for Accountability (AMAN) and the Palestinian Independent Commission for Human Rights (ICHR), both of which have undertaken work to rebuild public confidence and trust in the PA and its service delivery, such as through supporting citizen’s engagement with the new budget law 2025. The PFM components (Isnad) was procured and mobilised during the reporting period. Implementing the full suite of planned EPICS activities in full during the next reporting period will more comprehensively establish EPICS in line with its ToC.

Major lessons and recommendations for the year ahead [1/2 page]

Lesson: Working across the PA, civil society and international community is proving to be a valuable strategy for EPICS but stronger coordination across EPICS partners engaging those actors is needed. This PA government’s more open approach towards civil society has enabled progress on reform priorities, such as adopting a more consultative process to develop the 2025 General Budget and the cross-sectorial anti-corruption strategy.

Recommendation: BCGJ should establish an EPICS Steering Committee to strengthen coordination amongst delivery partners, to ensure that interventions supporting the PA, as well as those working with CSOs, are well aligned and capitalise on the current political economy environment. Owner: PROs. Timeline: March 2026.

Lesson: To adequately assess and address the needs/opportunities prompted by the ongoing conflict in Gaza, including the mounting instability, fiscal and legitimacy crisis in the West Bank, EPICS must remain flexible, politically informed, and adaptive so that it is able to respond to emerging political opportunities.

Recommendation. The EPICS programme team will continue to utilise Political Economy Analysis to inform decision making and programme activities, complemented through proactive engagement with delivery partners, and regular review and management of the programme’ risk register and mitigation strategy. Owner: PROs. Timeline: ongoing.

Lesson: We have been unable to operationalise all the components of EPICS according to the planned timeline and the development of a holistic logframe due to workload pressures to implement several initial components and other priority workstreams alongside continued resourcing gaps within the programme team.

Recommendation: BCGJ should prioritise finalising the mobilisation of remaining core EPICS components and a finalised unified programme logframe, with updated indicators and milestones. The Theory of Change should be reviewed as part of this. The process should include joint discussions with delivery partners to ensure all workstreams are being delivered consistently. Owner: PROs. Timeline: March 2026.

Lesson: Political sensitivities around state institutions need to be carefully navigated in implementing some components of EPICS. Issues such as public financial management, transparency, accountability, and institutional reforms are often politically sensitive, and there are limits to what technical assistance interventions can achieve alone.

Recommendation. EPICS should (a) continue to review and take stock of where it can add value and influence change within the Palestinian governance landscape, being realistic about what is achievable by using rolling political economy and conflict analysis; (b) work to foster the buy-in and trust of key stakeholders; and (c) be joined up with policy and advocacy efforts to strengthen governance. Owner: Programme partners & EPICS SRO. Timeline: ongoing.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The programme's Theory of Change (ToC) is centred on the premise that by supporting Palestinian institutions, strengthening civil society engagement, promoting transparency, and empowering women, the integrity of governance and service delivery in Palestine will improve. The ToC assumes that achieving these outcomes will lead to greater public trust, reduced corruption, improved financial stability, and more inclusive decision-making processes.

The ToC is based on the assumptions that certain elements of social stability remain the same. These assumptions are that:
- The PA does not collapse during EPICS implementation.
- The PA is ready and willing to engage with CSOs and vice versa, including on the promotion of women’s empowerment and other minority rights.
- PA institutions are receptive to technical assistance and the space for reform exists at both the technical and political levels and within critical thematic scope.
- Neither the Goil nor PA take drastic steps that will affect stability including the closure of the civic space.
During the reporting period, despite the war in Gaza and its subsequent impacts, the operating environment in the West Bank has remained sufficiently stable to deliver EPICS activities. This has enabled progress on two outputs, and their indicators were assessed during the review period. There is a need to revisit the ToC in the coming reporting period, particularly once the remaining components are operational. This should inform the development of a unified logframe upon which future reviews will be based.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The live EPICS components have continued to perform well, delivering positive progress against the programme’s outcome. For example, support through UNDP has facilitated progress on the PA’s reform and development agenda, including the development of the National Planning Process 2024–2029 led by the PMO, promoted digitisation, and strengthened mechanisms for accountability. Technical experts embedded across the PA under EPICS have provided targeted support in fiscal and administrative reform, health advisory services, institutional development, and policy formation. Efforts by the AMAN coalition have improved engagement between the PA and Civil Society. Civil society engagement was strengthened through support to the Palestinian NGOs Network (PNGO), improving representation and dialogue between CSOs and government institutions. State-society trust was reinforced when the AMAN Coalition’s policy recommendations on rationalising public spending were fully adopted, and AMAN was appointed to oversee implementation. Anti-corruption efforts advanced through piloting the Sectoral Corruption Risk Management (SCRM) tool with the Ministries of Finance and Health, with follow-up actions planned for next year. Transparency and accountability were institutionalised through four monitoring reports published by AMAN, assessing reform progress and informing government decision-making.

Critical though remains the full mobilisation of all core EPICS components under its ToC – the priority for the coming reporting period. This will contribute to a more comprehensive and cohesive delivery of EPICS. However, the overall context, particularly the PA’s worsening fiscal crisis, limits the PA’s ability to affect transformative change. EPICS is responding with political sensitivity to ensure its support is strategically designed within this context.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

EPICS continues to present good value for money, is relevant to the context in Palestine, and delivers broader policy priorities for the UK in Palestine. It does this by enabling the PA to govern and deliver services, and does so in an accountable and transparent way, particularly in the absence of an effective Parliament and lack of national elections. EPICS continues to operate effectively within a challenging political context, demonstrating an effective ability to respond to emerging priorities and adapt politically. Based on such performance and alignment with BCGJ’s wider portfolio and UK priorities, alongside planned mobilisation of the final core components of the programme, EPICS is justified to continue.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Improved capabilities of government institutions for effective and efficient management of public resources in an inclusive and accountable manner.
Output number:		1	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Progress on establishing a structured dialogue mechanism between the government and civil society.	Priorities and actions identified and agreed upon through the dialogue mechanism incorporated in governmental plans. / (UNDP/AMAN)	Indicator moderately did not meet expectations: / Through UNDP, an informal dialogue mechanism with the PA has been achieved. The government adopted a policy of governing closer to people as stated in the Reform & Development Plan and increased openness towards civil society. However, a more formal, structured policy has been submitted but remained under review for approval by the end of the reporting period.
1.2 Number of governmental units displaying improved transparent practices disaggregated by type of government unit.	12 government units disaggregated by type of government unit: / - National (8) / - Local (4) / (UNDP)	Indicator moderately exceeded expectation: 19 governmental units and LGUs display improved transparent practices. National (13): / TEA supported the Palestinian Land Authority (PLA) in developing e-services through the HUKUMATI Platform. / TEA supported the Palestinian Anti-Corruption Commission (PaCC) in developing and adopting a Sectoral Corruption Risk Management (SCRM) process in two Ministries (Ministry of Health and Ministry of Finance). / TEA provided technical support to the State Audit and Administrative Control Bureau (SAACB). / TEA developed a Digital Citizen Budget (DCB) for 6 ministries (Ministry of Women Affairs, Ministry of Industry, Ministry of Foreign Affairs, Ministry of Culture, Ministry of Tourism and Ministry of Awqaf). / TEA supported the establishment of Local Hospital Boards (LHBs) in two public hospitals (Al Mohtaseb Hospital and Palestine Medical Complex). / Local (7): / TEA supported 5 municipalities (Dura, Beta, Beit Jala, Sabastia and Salfit) in West Bank to develop monitoring tools. Two other municipalities (Salfit and Zababdeh) were also targeted to conduct public hearing sessions with citizens.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The overall scoring has been assessed at A level. This takes into consideration the fact that Indicator 1.1 moderately did not meet expectations, but 1.2 moderately exceeded expectations.

Achievements in this reporting period demonstrate systemic progress toward inclusive governance, fiscal transparency, and institutional accountability. Examples include: five high-level policy meetings, 66% CSO satisfaction, $150,000 in property tax revenues, seven operational e-services, 115 staff trained in IT audits, 17 LHBs established, and PCES satisfaction rates exceeding 80%. The integration of technical expertise, policy reform, digital innovation, and participatory mechanisms reflects a holistic approach that addresses structural and operational challenges.

Output progress:

Ad hoc meetings between the Reform Unit and civil society have become more frequent, resulting in greater national participation in policy discussions. During the reporting period, five high-level meetings were convened, one facilitated by UNDP and four by AMAN, bringing together government and civil society actors. Evidence of achieving milestone targets is reflected in the fact that 66% of civil society representatives reported improvements in joint public policy processes. However, while engagement has increased, a formal mechanism for structured participation is still pending agreement.

Through UNDP’s TEA project, a high-level dialogue session was held between the PA’s Reform Office, CSOs, and the international community, focusing on progress in the government reform agenda. This was widely regarded as a milestone for promoting inclusivity, accountability, and transparency within the PA. Complementing these efforts, a senior policy advisor was deployed to the Prime Minister’s Reform Office, playing a pivotal role in engaging civil society and shaping reform proposals, including the Budget Law, Presidential Decrees Law, and the Anti-Corruption Strategy.

Fiscal transparency has advanced significantly through innovative tools and digital platforms. For the first time in over a decade, the Budget Law 2025 was opened for public consultation with civil society and citizens, following sustained lobbying and technical advice from AMAN. UNDP TEA also developed Digital Citizen Budgets (DCBs) for six ministries, including the Women Affairs, Industry, Foreign Affairs, Culture, Tourism, and Awqaf - simplifying budget information and making it accessible to the public.

On the digital governance front, UNDP TEA supported the Palestinian Land Authority (PLA) in creating 13 e-services under the HUKUMATI platform, with seven services fully operational, including property ownership records and asset registration. The remaining services are undergoing testing. Additionally, the General Directorate Property Tax e-platform was launched under e-HUKUMATI, generating approximately $150,000 in revenues during its initial rollout, demonstrating both uptake and fiscal impact.

The TEA project supported institutional capacity for accountability through targeted technical assistance. The Palestinian Anti-Corruption Commission (PaCC) adopted Sectoral Corruption Risk Management (SCRM) tools in two key ministries, the Ministry of Health and the Ministry of Finance, enhancing central oversight and compliance with anti-corruption standards. Similarly, the State Audit and Administrative Control Bureau (SAACB) received technical support to develop IT audit capabilities, including specialized training for 115 staff members (59% female). An IT Audit System is currently being piloted across two ministries, with plans for mainstreaming if proven effective

In parallel, AMAN convened a high-level meeting between civil society, the Anti-Corruption Commission, and the State Audit Bureau to build consensus on a collaborative oversight model. A recommendation for a government-adopted policy to institutionalise this cooperation has been submitted to the Prime Minister’s Office and is under review.

The health sector has seen notable improvements in participatory governance and service quality. UNDP TEA supported the establishment of Local Hospital Boards (LHBs) in two additional public hospitals, Al Mohtaseb and Palestine Medical Complex, bringing the total to 17 LHBs by the end of 2024. These boards include hospital staff, community leaders, academics, and sector representatives, ensuring inclusive oversight of healthcare services.

To complement these structures, the Patient Care Evaluation System (PCES) was institutionalised within the Ministry of Health, enabling systematic collection of patient and staff feedback. By December 2024, 7,823 patient surveys were completed, showing an 80.7% satisfaction rate, alongside 1,344 staff surveys with a 70.3% satisfaction rate. PCES has since been expanded to 15 central health directorates, reinforcing data-driven decision-making and accountability in healthcare delivery.

Civil society engagement and local governance accountability have been strengthened through multiple initiatives. UNDP TEA supported the expansion of the Palestinian NGOs Network (PNGO), with 45 new CSOs joining the agricultural sector and 31 joining women’s sectors. Six Representation Sectoral Committees (RSCs) were formed to articulate sector priorities and engage with the government’s Reform Office.

At the local level, five municipalities, Dura, Beta, Beit Jala, Sabastia, and Salfit, adopted the Baladiyah Meter, a tool enabling citizens to monitor municipal performance and hold local authorities accountable. Additionally, public hearing sessions were conducted in Salfit and Zababdeh, providing safe spaces for citizens to discuss the impact of new projects and propose solutions, thereby improving trust between communities and local government units.

AMAN’s advocacy efforts have yielded tangible results. The government adopted or at least committed to six policy drafts supporting accountability and civil society engagement, including:
1. Criteria for selecting deputy ministers
2. Recommendations on reforms and national dialogue
3. Commitment to a structured approach for engaging civil society
4. Policy support for the Access to Information Law
5. Two social accountability initiatives implemented to improve responsiveness of line ministries

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There were no major changes to this output during the past year. However, the TEA project’s workplan was expanded to include additional activities targeting civil society in Gaza, supporting the government communication centre, and the national reform agenda. The upscale in activities have allowed the PA’ goverement to deliver its reform priorities, including support setting up the government communication centre. The additional activities also supported civil communities to operate and provided services to citizens in Gaza. The unified EPICS logframe will capture these activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Lessons learned:
Technical assistance to oversight bodies, such as the Anti-Corruption Commission and State Audit Bureau, has strengthened accountability through tools like Sectoral Corruption Risk Management (SCRM) and IT audit systems. However, these improvements remain limited to pilot phases, and without institutionalisation, their impact will be short-lived.
Recommendation:
Institutionalise anti-corruption tools by mainstreaming SCRM and IT audit systems across all ministries, supported by a structured capacity-building program and clear compliance guidelines. This will ensure sustainability and reinforce government accountability frameworks.

Output Title	Improved capabilities of civil society and private service providers for more accountable, inclusive, effective and efficient service provision’.
Output number:		2	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of assessments\indices produced examining gaps in civic space with policy recommendations/actions to push for policy change.	Gaps in transparency, participation, and integrity in access to power identified (AMAN) / 4 pre-post assessments identifying gaps in civic participation conducted. / Percentage of ICHR complaint handling management documented by ICHR.	Indicator met expectation: 10 existing gaps in public policies, supporting civic space and human rights were identified. Policy recommendations were produced and submitted to the government. / (AMAN). ICHR’s 2024 report showed a 22.4% rise in complaints on rule of law and human rights violations, largely linked to the PA’s handling of opponents after Jenin events and heightened West Bank security tensions.
2.2 Number of CSOs actively engaged to increase awareness, and transparent, inclusive, accountable, effective and efficient service delivery.	4 CSOs including media outlets are actively engaged to increase transparent, inclusive, accountable, effective, and efficient service delivery.	Indicator met expectation: 4 civil society organisations, media outlets, and syndicates have become more engaged to promote transparency in government’ performance and service delivery. (UNDP/AMAN/ICHR)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The overall scoring has been assessed at A level. EPICS has made good progress in strengthening Palestinian civic space and fostering constructive relationships between civil society organisations (CSOs) and the PA government during the review period.

Output progress:

Civil society interventions complemented governance reforms by safeguarding civic space and promoting transparency. AMAN engaged two major media outlets (MAAN and WATTAN) to deliver a widescale public awareness campaign on PA mechanisms for transparency and accountability. This included campaigns on the Right of Access to Information Law and on merit-based criteria for appointing senior positions such as deputy ministers. These campaigns hosted senior officials to answer public questions and exerted pressure on the PA to adopt transparent processes in leadership appointments.

Further, AMAN played a central role in advancing governance reform. It identified 10 gaps in public policies and produced one comprehensive study on key reform priorities, focusing on integrity and anti-corruption. This study was jointly discussed at a national conference, and policy recommendations were submitted to the Prime Minister’s Office. In addition, AMAN published four monitoring reports on PA reform performance, three periodic and one annual, assessing compliance with announced agendas and workplans. Two further studies with recommendations on financial and administrative reform were submitted to the government, and three joint advocacy actions were undertaken with civil society to push for reform commitments. AMAN also facilitated at least four high-level meetings on reform and more than ten thematic meetings on finance, health, social development, and accountability. These engagements involved 20 CSOs, and 66% of civil society representatives reported improved engagement with government. A major milestone was achieved when the Budget Law 2025 was opened for public consultation for the first time in over a decade, following sustained advocacy and technical support.

AMAN’s downstream partner MIFTAH (The Palestinian Initiative for the Promotion of Dialogue and Democracy) simplified, digitised, and published the annual budgets of 21 ministries and government entities during 2024, making fiscal information more accessible to citizens and reinforcing public oversight. At the local level, the “Baladiyah Meter” online tool established linkages between Local Governance Units (LGUs) and CSOs, enabling citizens to monitor municipal performance and hold councils accountable. This innovation strengthened participatory governance at the grassroots level.

Gender-responsive accountability was deepened through AMAN’s Women Against Corruption Network, which expanded to include additional grassroots women’s organisations with a focus on gendered corruption. Members designed and delivered social accountability initiatives in their communities, encouraging women to report corruption in the public sphere, particularly in areas with weak PA presence, to help rebuild trust. Four women’s rights organisations (WROs) integrated gender-focused anti-corruption strategies into their core programming, strengthening the intersection of gender equality and public integrity. AMAN also promoted women’s leadership at local and municipal levels, reinforcing women’s voices in budget oversight and service delivery reform.

Amid the war in Gaza, EPICS demonstrated agility and inclusivity. UNDP conducted studies on the conflict’s implications and the capacities of municipalities and civil society in Gaza, using the findings to launch two targeted interventions. First, two CSO Workstations were established (Deir al-Balah and Gaza City) to provide safe, functional spaces for displaced organisations to resume operations, communicate with stakeholders, and contribute to the humanitarian response, hosting 2,200+ visits and 313 activities (e.g., WHO polio vaccination training, humanitarian coordination meetings, sectoral consultations). Second, two One‑Stop Community Service Centres (Deir al‑Balah and Khan Younis) delivered 112,781 services to 77,000+ individuals by December 2024, supporting 19 CSOs across eight service categories with an emphasis on accessibility for persons with disabilities.

In the health sector, UNDP TEA’s medical liability workstream created strong linkages between the Ministry of Health and key actors, including the Health Syndicates, Independent Commission for Human Rights, Palestine Capital Market Authority, and the Health Insurance Union. These partnerships improved coordination between public, private, and civil society actors, ensuring that reforms in medical liability and patient rights are inclusive and well-governed.

On outreach and anti-corruption, AMAN conducted 21 outreach visits (three in the West Bank and 18 in Gaza) in partnership with grassroots organisations, reaching 391 participants (208 male, 183 female). Of these, 63% expressed strong willingness to engage in anti-corruption efforts, and 17% actively submitted complaints related to suspected corruption in aid distribution. AMAN’s Legal Aid Centre provided 740 legal consultations (490 male, 233 female) and pursued 62 suspected corruption cases, all followed up with the Palestinian Anti-Corruption Commission (PaCC) under its new cross-sectoral strategy. AMAN also delivered three capacity-building sessions for 57 journalists (15 male, 42 female) on investigative reporting and financial transparency. As a result, eight investigative reports were published, exposing governance gaps and corruption cases, including gender-related issues.

The Independent Commission for Human Rights (ICHR) published the 2024 Complaint Handling Management (CHM) report, which showed a 22.4% increase in complaints related to rule of law and rights violations. 24% of complaints originated in the West Bank (83.4% male, 7.6% female, 6.2% children, 2.8% persons with disabilities), reflecting heightened tensions following Jenin events. ICHR also reviewed five laws/by-laws and issued 57 policy recommendations (31 advisory pieces, five legal memos, and 20 fact sheets). Notably, 87.5% of law enforcement officials reported satisfaction with ICHR’s review and complaints handling processes.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There were no major changes to this output during the past year. However, The TEA project’ workplan was expanded to include additional activities targeting civil society in Gaza, supporting the government communication centre, and national reform agenda. The unified EPICS logframe will capture these activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Lessons learned:

Structured engagement is essential for effectiveness. Ad hoc meetings between the Reform Office and civil society improved participation, with 66% of CSOs reporting better joint policy processes. However, the lack of a formal engagement mechanism limits institutionalisation. This demonstrates that while informal dialogue can deliver short-term gains, structured frameworks are critical for embedding participatory governance.

Advocacy coupled with technical support accelerates reform. AMAN’s success in opening the Budget Law 2025 for public consultation and influencing six policy drafts illustrates that policy advocacy is most effective when paired with technical expertise. This synergy ensures reforms are not only adopted but also operationalized.
Recommendations:

Work with delivery partners to finalize and adopt a formal CSO engagement mechanism under the Reform Office and support the Prime Minister’s Office to approve and institutionalise the collaborative oversight policy proposed by AMAN.

Continue supporting delivery partners with technical expertise to advance reforms (e.g., Access to Information Law implementation). Prioritize legal drafting and capacity-building for ministries to operationalize adopted policies.
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

The largest cost drivers during the reporting period were consultancy fees and grants to downstream partners. The programme worked to ensure efficiency in the use of these funds by balancing the cost of inputs with the appropriate level of technical advice. A hybrid delivery model, combining in-house, international, and national expertise, enabled delivery partners to build strong relationships with beneficiaries and undertake essential in-person engagement, while maintaining a strong focus on value for money. This approach ensured specialist support to the PA and civil society on reform, transparency, and accountability, despite an increasingly challenging context marked by instability in the West Bank, the war in Gaza, the PA’s fiscal crisis, and movement and access restrictions across Palestine.

Delivery partners have developed a robust Value for Money (VfM) framework, which has been used to assess whether the programme continues to deliver good VfM across implementation. Overall, the programme performed well against the 4Es - Economy, Efficiency, Effectiveness, and Equity - and presented strong financial management and control, as confirmed by audits and financial reports showing only slight variances in the forecast.

Equity: Delivery partners (UNDP, AMAN, ICHR) designed gender-sensitive interventions guided by a gender mainstreaming strategy. An organisation-wide gender policy was adopted, prioritizing gender equality and women’s empowerment through targeted capacity-building, structured awareness campaigns, and strategic advocacy. ICHR conducted an extensive gender review to integrate gender perspectives across its operations. UNDP introduced a dedicated gender component focused on women’s empowerment, including mobilizing public support for the Families Protection Bill. AMAN adopted a gender-responsive strategy that advanced inclusive policy frameworks and localized reforms through the Women Against Corruption Network.

Efficiency and Effectiveness: The programme demonstrated cost-effectiveness in responding to emergencies associated with the Gaza war. Existing resources and civil society partnerships were leveraged to conduct rapid assessments of the war’s impact, avoiding the need for external consultants. This reduced costs and provided timely evidence to inform programme directions, including increased support to CSOs in Gaza.

Economy: Delivery partners capitalized on cost-saving opportunities by applying international best practice and working in consortium to address complex issues. Examples include:
- UNDP collaborated with its regional anti-corruption team to support the Ministry of Health in introducing hospital boards and training the Palestinian Anti-Corruption Commission, reducing consultant costs and applying lessons learned from other contexts.
- UNDP consolidated multiple activities (income taxes, business classification, affirmative actions) into a single agreement with the Palestine Economic Policy Research Institute (MAS), reducing transaction costs.
- Strong relationships between BCGJ, delivery partners, and the Prime Minister’s Office maximized alignment and delivery efficiency, complemented by expert advice from the UK Envoy on PA Governance.
- UNDP saved nearly USD 21,000 in accommodation and travel costs by conducting Local Hospital Board formation workshops online for 10 hospitals instead of in Amman.
- AMAN implemented most awareness-raising activities at minimal additional cost by using existing programme teams and repurposing advocacy infographics.
- Close engagement with PA officials allowed delivery partners to provide timely advice to senior officials and ministers, exemplified by AMAN’s input on the Budget Law.

VfM performance compared to the original VfM proposition in the business case

The programme remains in its overall mobilisation phase and is delivering VfM in line with the original programme design. VfM principles are embedded in programme and activity design. Economy is achieved through cost-conscious delivery and prioritizing local expertise, such as the Palestinian Public Finance Institute, to reduce reliance on costly international inputs. Efficiency is promoted by integrating technical and strategic advisory workstreams, joint workshops, and adaptive planning to minimize duplication. Effectiveness is ensured by aligning interventions with politically feasible priorities identified through PECA and Gap Analysis, focusing on high-impact reforms like VAT law implementation, RMS upgrades, and emergency budgeting. Equity is addressed through gender-responsive budgeting, GESI frameworks for VAT procedures, and Gender Impact Assessments, alongside social value initiatives such as graduate internships to foster inclusive participation in PFM reforms.

Assessment of whether the programme continues to represent value for money

EPICS is overall still in its mobilisation phase with some components mobilized and delivering. Despite this, it continues to represent good value for money. Despite the challenging context and the inherent complexity of delivering governance programmes in politically sensitive and conflict affected environments, EPICS met most planned output milestones during this reporting period. Interventions built effective partnerships across the PA and civil society, advanced transparency and accountability, and supported steps toward better citizen engagement and service delivery.

High administrative and technical input was required by BCGJ staff during the reporting year to advance EPICS priorities. Significant time was invested in building partner capacity for reporting and project management, which remains a concern given disproportionate effort on lower-cost initiatives. A programme-funded BCGJ in-house governance adviser will be recruited to strengthen BCGJ’s delivery of the programme.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

Programme risks are managed by designated risk owners within the programme team and tracked on a quarterly basis. Risk management occurs both formally, through regular at least quarterly reviews, and informally on an ongoing basis. Delivery partners report risks quarterly within their reports and against EPICS’s overarching Risk Matrix, as well as bi-weekly or monthly meetings with BCGJ who escalate risks takes as needed.

The programme’s risk appetite remains at Major. Key risks included deterioration of the internal political and security environment in the West Bank, challenges to the PA’s legitimacy, and PA fiscal instability. The ability of civil society to engage constructively with the PA was tested during the reporting period but improved through new citizen-facing policies and greater openness adopted by the 19th PA Government.

The protracted war in Gaza and its spillover effects in the West Bank negatively impacted on programme delivery. Partners had to re-plan interventions and, in some cases, halt activities due to movement restrictions, settler activities and attacks, and challenges to operate in Gaza. Delivery partners demonstrated flexibility by adapting workplans, increasing focus on political economy analysis, and designing new activities to respond to the Gaza crisis.

Prominent risks and mitigations include:
Risk 1: Severe – Security and political instability prompted by the Gaza war, with spillover effects in the West Bank, impact EPICS’ delivery.

Mitigation: Active monitoring and reporting of these impacts to inform and adapt EPICS programme activities’ design to remain relevant. The UK engaged with other donors to support efforts to stabilize the situation. and ensure.

Risk 2: Severe – The PA fiscal crisis undermines the PA’s performance and credibility, and EPICS’ ability to influence change.

Mitigation: Ongoing engagement with the PA and civil society to understand fiscal dynamics. EPICS provided technical support through ISNAD to advise the PA and strengthen fiscal sustainability.

Risk 3: Moderate – Shrinking civic space and restrictions on freedom of expression in Palestine.

Mitigation: Continuous monitoring of civic space and human rights to inform EPICS activities, in coordination with other donors, alongside proactive engagement with partners when regressive policies or actions arise.

Risk 4: Moderate – The PA lack political and/or technical appetite to reform, undermining the value of EPICS.

Mitigation: Maintain proactive engagement with the Prime Minister’s Office and line ministries to secure buy-in, ensure interventions are need-based and informed by political economy analysis, and align with PA reform priorities.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

EPICS operates through a mixed delivery modality, including contracts with commercial partners, Memoranda of Understanding (MoUs) with civil society organisations, and a UN contribution agreement. Current delivery partners include UNDP, AMAN, ICHR, and PFRC/Tetra Tech for ISNAD initiated at the end of the reporting period. EPICS plans to expand to additional commercial partners in the next financial year. Effective coordination remains critical to ensure proper delivery, avoid duplication, reduce costs, and maximize benefits across outputs.
- UNDP is the lead UN agency on governance. Its TEA programme began as an FCDO-funded initiative and is now co-funded by Sweden and Australia.
- AMAN Coalition for Accountability is a leading Palestinian civil society organisation with 25 years of experience in governance and anti-corruption. AMAN serves as the national chapter of Transparency International in Palestine and receives core funding from a consortium of European donors.
- ICHR is Palestine’s national human rights institution, functioning as an Ombudsman, and is core-funded by six European donors.

Commercial Performance: contracts, including negotiations and terms of reference, were managed in-house with support from local and regional FCDO programme teams. Delivery partners demonstrated strong ownership of activities, applying due diligence and utilizing available resources efficiently. Cooperation with the EPICS programme team ensured timely implementation. For example, UNDP’s regional anti-corruption team and Transparency International’s country office provided interventions that were both efficient and value for money. All deliverables, including operational and financial reporting and audits, were submitted on time.

Financial Performance: each project developed a Value for Money (VfM) strategy in collaboration with the EPICS programme team. Indicators were reported and jointly reviewed quarterly. Performance reviews confirm that EPICS continues to deliver good VfM, supported by strong financial controls and procedures. All partners signed up to FCDO Fraud Guidance and submitted clear financial reports and unqualified annual audits.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

EPICS comes under the Economic Development & Institutions Team (EDIT) and is overseen by the G7 Team Leader (SRO) and managed by two CBS HEOs: a Senior Policy & Programme Officer, and an Associate Governance Advisor. A programme-funded G7 Governance Adviser supports programme delivery, although this position was vacant for more than half of the reporting period.

All active EPICS components have their own monitoring and evaluation processes. Delivery partners have established clear output and outcome indicators, which are used to feed into the overall programme logical framework (noting a unified logframe will be completed in the coming reporting period). Partners report on their workplan and indicators regularly (at least quarterly); payments are released based on the satisfactory review of these reports. Reports include disaggregated M&E information, particularly for women and those with disabilities.

To complement partners’ monitoring efforts, the EPICS programme team conducted the following activities during the reporting period, however for security reasons FCDO could not visit projects and activities delivered in Gaza:

- Regular meetings: undertaken on a monthly, bi-weekly or weekly basis with delivery partners and relevant PA counterparts. The meetings were used to discuss progress, as well as any issues and challenges that needed to be addressed to ensure smooth implementation.
- Monthly and quarterly progress and financial reports submitted by EPICS implementing partners were reviewed on an ongoing basis by the EPICS project team.
- Quarterly review meetings were also held with delivery partners, to discuss progress, address any challenges, and review anticipated deliverables for the next quarter.
- Field visits were carried out to activity locations for on-the-spot assessments. The results of these assessments were analysed and are regularly discussed with FCDO team.

A UK-based result advisor supported partners to design and strengthen their results matrix and logframe indicators for both outcome and output levels. Lessons learned from previous implementation processes and programming were considered in design and implementation.

Evidence

Monitoring data and partner reports provide strong evidence of progress, including timely delivery of outputs, robust financial controls, and gender-sensitive interventions. For example, AMAN’s campaigns reached diverse audiences, while MIFTAH digitised budgets for 21 ministries, improving transparency. Evidence quality is high, with quarterly VfM reviews and unqualified audits confirming compliance.

Gender sensitivity

EPICS delivery partners integrated gender equality across all components through targeted strategies and policies. UNDP introduced a dedicated gender component focused on women’s empowerment, including advocacy for the Families Protection Bill. AMAN adopted a gender-responsive approach, advancing inclusive policy frameworks and supporting the Women Against Corruption Network. ICHR conducted a comprehensive gender review to embed gender perspectives in its operations. These interventions combined capacity-building, awareness campaigns, and advocacy to ensure women’s voices are represented in governance reforms and accountability processes.

Learning:

To strengthen EPICS’ ability to capture and embed learning, it is critical to ensure that adaptive management principles are systematically applied. This requires robust feedback loops and evidence-based decision-making so that lessons from the different stages of implementation inform longer-term strategic choices and policy engagement. Embedding learning in this way will enable EPICS to remain relevant and responsive in a highly dynamic political context.

Increase focus on Gender and Social Inclusion. While the EPICS Programme has made progress in reaching marginalised groups across sectors, further work is needed to mainstream inclusion at policy level. Future interventions should be designed to address structural barriers and ensure that gender and social inclusion objectives are reflected in governance reforms.

In-built flexibility. The EPICS Programme should continue to apply problem-driven iterative adaptation (PDIA) principles, enabling rapid response to emerging opportunities and risks. This is particularly important given the political and socio-economic volatility in Palestine, where windows for reform can be short-lived and require agile engagement.

Longer duration. The EPICS components should align with the overall business case timeframe (March 2031) to maintain continuity of delivery and stakeholder buy-in. Governance change is inherently long-term, and sustained engagement is essential to consolidate relationships and achieve durable outcomes.

Date of last narrative financial report	April/May 2025	Date of last audited annual statement	UNDP: June 2025 / AMAN: May 2025 / ICHR: April 2025