## Annual Review: Amazon Catalyst for Forest Communities (AMCAT)

Title: The Amazon Catalyst for Forest Communities (AMCAT)
Programme Value £ (full life): £94m		Review date: October 2025
Programme Code: 400042	AMP start date: 18/11/2024	AMP end date: 31/03/2031

Summary of Programme Performance
Year	2025	2026	2027	2028	2029	2030
Overall Output Score	A+
Risk Rating	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400042 Documents
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400042

Table 1 - List of Acronyms
Acronym	Definition
ACTO	Amazon Cooperation Treaty Organisation
AIDESEP	Asociación Interétnica de Desarrollo de la Selva Peruana (Interethnic Association for the Development of the Peruvian Rainforest)
AMCAT	Amazon Catalyst for Forest Communities
APA	Amerindian Peoples Association
APCI	Agencia Peruana de Cooperación Internacional (Peruvian Agency for International Cooperation)
APIB	Articulação dos Povos Indígenas do Brasil (Articulation of Indigenous Peoples of Brazil)
CBD	Convention on Biological Diversity
CNAMIB	Confederación Nacional de Mujeres Indígenas de Bolivia (National Confederation of Indigenous Women of Bolivia)
CNTI	Consejo Nacional de Tierras Indígenas (National Indigenous Lands Council)
COIAB	Coordenação das Organizações Indígenas da Amazônia Brasileira (Coordination of Indigenous Organisations of the Brazilian Amazon)
COICA	Coordinadora de las Organizaciones Indígenas de la Cuenca Amazónica (Coordinator of Indigenous Organisations of the Amazon Basin)
CONAIE	Confederación de Nacionalidades Indígenas del Ecuador (Confederation of Indigenous Nationalities of Ecuador)
CONAQ	Coordenação Nacional de Articulação das Comunidades Negras Rurais Quilombolas (National Coordination of Articulation of Rural Black Quilombola Communities)
CONFENIAIE	Confederación de Nacionalidades Indígenas de la Amazonía Ecuatoriana (Confederation of Indigenous Nationalities of the Ecuadorian Amazon)
COP	Conference of the Parties
FENAMAD	Federación Nativa del Río Madre de Dios y Afluentes (Native Federation of the Madre de Dios River and Tributaries)
FPIC	Free, Prior, and Informed Consent
GATC	Global Alliance of Territorial Communities
GEDSI	Gender Equality, Disability, and Social Inclusion
GIS	Geographic Information System
GTAA	El Gobierno Territorial Autónomo Awajún (The Awajún Autonomous Territorial Government)
GTANW	El Gobierno Territorial Autónomo de la Nación Wampis-GTANW (Autonomous Territorial Government of the Wampís Nation)
HMG	His Majesty’s Government (UK)
ICF	International Climate Finance
ILC	International Land Coalition
INCRA	The Instituto Nacional de Colonização e Reforma Agrária (National Institute for Colonization and Agrarian Reform)
IPLC	Indigenous Peoples and local communities
KPI	Key Performance Indicator
MEL	Monitoring, Evaluation, and Learning
MIQCB	Movimento Interestadual de Quebradeiras de Coco Babaçu (Interstate Movement of Babassu Coconut Breakers)
MoU	Memorandum of Understanding
NDC	Nationally Determined Contribution
NORAD	Norwegian Agency for Development Cooperation
ODA	Official Development Assistance
OPIAC	Organización Nacional de los Pueblos Indígenas de la Amazonía Colombiana (National Organisation of Indigenous Peoples of the Colombian Amazon)
ORAU	Organización Regional AIDESEP Ucayali (Regional Organisation of AIDESEP Ucayali)
PRO	Programme Responsible Officer
REDD+	Reducing Emissions from Deforestation and Forest Degradation (plus conservation, sustainable management, and enhancement of forest carbon stocks)
SEAH	Sexual Exploitation, Abuse, and Harassment
SRO	Senior Responsible Officer
UNFCCC	United Nations Framework Convention for Climate Change
USAID	United States Agency for International Development
VfM	Value for Money
VIDS	Vereniging van Inheemse Dorpshoofden in Suriname (Association of Indigenous Village Leaders in Suriname)
VSG	Vereniging van Saamaka Gezagsdragers (Association of Saamaka Authorities)

A. SUMMARY AND OVERVIEW

Description of programme

The Amazon Catalyst for Forest Communities (AMCAT) is a six-year, £94 million regional forest programme running from 2025 to 2030. It aims to strengthen forest governance and tenure security for Indigenous Peoples, Afro descendant Peoples, and local communities (IPLC) across the Amazon Basin. AMCAT seeks to accelerate progress in tenure security, knowledge creation, financial mobilisation, and policy influence. Through grants and technical assistance to IPLC organisations in up to eight countries, alongside support for regional coalition-building, organisational development, and evidence generation,

The programme is designed to scale up proven approaches and mobilise coordinated action and funding to address escalating threats to the Amazon, reduce poverty, protect biodiversity, and contribute to global climate goals. It focuses on securing formal tenure rights, strengthening governance systems, and generating evidence on the role of community-led forest stewardship in sustaining biodiversity and ecosystem services. Investments in territorial planning, environmental monitoring, and capacity building aim to enhance the managerial and advocacy capabilities of IPLC organisations. While UK funding provides the foundation, AMCAT’s catalytic impact lies in its ability to leverage policy influence and attract additional financial support, offering a scalable, regionally coordinated platform for strategic investment in IPLC-led initiatives.

The programme targets improvements in tenure security and territorial governance across at least 24 million hectares, with a further 25 million hectares expected to benefit if additional donor funding is secured. Combined with strengthened evidence, visibility, negotiation capacity, and administrative capability of IPLC organisations, these elements underpin AMCAT’s catalytic effect.

AMCAT is delivered in partnership with The Tenure Facility and structured around three interlinked components, supported by an independent evaluation service. These components work in synergy to advance IPLC forest governance and tenure security across the region.
- Component A focuses on strengthening forest tenure and governance through scalable, transferable approaches and cross-country learning.
- Component B establishes a Regional Coordination Facility to enhance IPLC capacity for regional engagement, influence policy narratives, and promote strategic communication and evidence-sharing.
- Component C delivers a participatory, real-time monitoring and learning system to assess activities and impacts, guide strategic adjustments, and generate evidence on outcomes related to forests, livelihoods, and ecosystems.
An independent evaluation service will assess the programme’s overall effectiveness, value for money, and its ability to catalyse broader systemic change at two intervals during the programme: a mid-term review, and an end-of impact evaluation.
Figure 1 - AMCAT's Components

Summary supporting narrative for the overall score in this review.

Following the finalisation of the business case, AMCAT was rapidly mobilised through a strategic partnership with the Tenure Facility, enabling immediate implementation by embedding the programme within existing systems and minimising administrative burden. A shared commitment to a bottom-up, locally driven approach ensures that IPLC organisations guide the work based on territorial priorities, while mechanisms such as the IPLC Advisory Body and regional coordination structures will strengthen long-term capacity. From January 2025, the focus has been on funding already operational projects, developing new management tools and country and regional strategies, and supporting IPLC engagement in the 30th meeting of the Conference of the Parties (COP 30) - all underpinned by a flexible, collaborative model that prioritises sustainability and alignment with Tenure Facility’s mandate.

AMCAT moved swiftly from setup to implementation by leveraging The Tenure Facility’s existing systems, partnerships, and an active project portfolio, enabling immediate results with lean administration. In its first ten months, the programme supported 17 direct grants across seven countries, contributing to land rights recognition and/or improved governance over nearly nine million hectares, policy reforms, and gender equality. A direct grant in this case refers to funding provided by the Tenure Facility straight to IPLC organisation, rather than it being routed through intermediaries – these grants are designed to empower IPLCs to lead and implement activities based on their own priorities, with minimal administrative burden and maximum autonomy. In some cases, IPLC organisations may have fiscal sponsors who support with financial administration or compliance – these are chosen by IPLC organisations themselves. Even where a fiscal sponsor is involved, the primary partner and main interlocutor remains the IPLC organisation itself.

The programme has delivered noteworthy results, strengthening tenure security across almost 9 million hectares, supporting IPLC actors to secure meaningful inclusion in national climate processes and catalysing regional momentum ahead of COP30. With the Amazon nearing critical ecological tipping points, the urgency of this work cannot be overstated. Indigenous Peoples, Afro-descendant and local communities, with our support, are uniquely positioned to halt forest loss and safeguard biodiversity. The programme also delivers across multiple UK priorities - development, adaptation, mitigation, nature protection, and climate justice - making it a high-impact, cross-cutting investment at a time when global funding is contracting. Continued support is not only justified; it is essential.

Major lessons and recommendations for the year ahead:

- Leveraging existing portfolios for a quick start: By integrating AMCAT into the Tenure Facility’s existing structures and networks, the programme was able to begin implementation rapidly avoiding the slow start common with the set-up of new delivery instruments. While the new elements introduced through AMCAT, such as regional coordination, learning systems, and the IPLC advisory body, are still being established, this approach allowed us to hit the ground running and has laid the groundwork for lasting structures and capacity that are expected to continue beyond FCDO’s funding.
- Flexibility Through Small Grants: The Small Grants approach has enabled AMCAT to respond quickly and effectively to emerging needs, particularly in the fast-evolving context of COP30 preparations. This flexibility has proven essential in adapting to the dynamic realities faced by IPLC organisations across the Amazon.
- Value of Regional Encounters: By ensuring IPLC organisations have a seat at the table in regional and national spaces, as well as more opportunities to coordinate internally, AMCAT has helped catalyse significant shifts in influence and visibility. These include the inclusion of IPLC priorities in Nationally Determined Contributions (NDCs) in Brazil and Colombia, the launch of the Amazon Indigenous Peoples’ Mechanism under the Amazon Cooperation Treaty Organisation (ACTO), and new mechanisms for IPLC participation in a UNFCCC COP, marking a major step forward in regional coordination and advocacy.
- Potential to enhance HMG synergies in the Amazon: AMCAT’s impact is strengthened through collaboration with embassy colleagues who bring a high-level view and connections across other HMG programmes. This has helped reduce duplication, improve efficiency, and increase synergies across initiatives with interrelated goals, leveraging all available tools to support IPLC-led and climate efforts more strategically.
- FCDO internal governance providing no-objection: AMCAT’s bottom-up approach - places IPLC organisations at the centre of decision-making, ensuring that programme priorities and actions are shaped by those most directly connected to forest governance and protection. This includes partnering with the Tenure Facility, not simply as a delivery contractor, but as a strategic partner with its own mandate and expertise. This model has introduced new ways of working, prompting valuable learning for programme teams and embassies. Engagement at post level has proven more time-intensive than initially anticipated, as teams adapt to a more participatory and locally driven approach that centres IPLC leadership in decision-making.
Key recommendations:
- Develop a clear and forward-looking strategy for Component B, shifting from its initial reactive focus on COP30-related small grants to a more structured approach that guides AMCAT’s regional engagement and catalytic work. This should include initiating the new regional assessment to identify priorities, partners, and opportunities for long-term impact.
- Revise and update programme outcomes to better reflect progress towards AMCAT’s regional and catalytic ambitions.
- In light of anticipated spending review budget cuts, work together with the Tenure Facility to prioritise core actions for next financial year while at the same time increasing efforts to mobilise additional donor finance to enable the programme to sustain its planned action, drawing from the political momentum generated by the United Nations Framework Convention on Climate Change (UNFCCC) COP30 and the upcoming Conference for Biological Diversity (CBD) COP17.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

AMCAT addresses the urgent challenge of deforestation and forest degradation in the Amazon by strengthening forest land tenure and governance of IPLC, widely recognised as the forest’s most effective stewards. AMCAT builds the experience and evidence needed to shape future policies and programmes, amplify IPLC voices in national and regional decision-making, and foster coalitions that influence legal frameworks and funding mechanisms. By strengthening and elevating proven approaches to tenure security, and regional collaboration, AMCAT helps IPLC attract finance and government action to better protect their territories. These efforts help preserve standing forests, reduce deforestation, and shape regional and global policy. Ultimately, this leads to more resilient communities, protects biodiversity and carbon sinks, and contributes to safeguarding the Amazon biome from an irreversible climate tipping point.

Figure 2 - AMCAT's Theory of Change

While the Theory of Change remains valid and relevant, the global funding landscape has shifted significantly, with major cuts to official development assistance (ODA) from key donors, including the dismantlement of The United States Agency for International Development (USAID) and reductions from the UK, the Netherlands, and others. As part of the programme’s original design - and now with increased urgency- we are working to scale up political, financial, and institutional support for IPLC tenure security by seeking collaboration with other donors and exploring pooled funding to sustain and expand impact. For the next review, it will be important to revisit our assumptions about the overall funding landscape - across donors, multilaterals, and philanthropies - and adjust our mobilisation strategy accordingly.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on-track with respect to expected outcomes. Mobilisation has progressed rapidly, with swift agreement on the Memorandum of Understanding (MoU) with The Tenure Facility, which set out our shared commitment to minimise bureaucracy and align as closely as possible with their existing structures and systems - such as synchronising reporting periods. AMCAT is designed as a truly collaborative and bottom-up programme, where IPLC organisations guide the work based on their territorial priorities, rather than having regional strategies developed externally. The strategic partnership with the Tenure Facility respects its mandate and technical expertise, with all project proposals undergoing rigorous review and due diligence through its internal processes. FCDO supports this approach by issuing no-objection to proposals that are co-developed by IPLC organisations and the Tenure Facility. This ensures FCDO maintains strategic oversight and alignment with UK priorities, while also recognising and relying on the Tenure Facility’s thorough due diligence and technical assessments, rather than duplicating review processes. This ensures that the structures and capabilities developed through AMCAT remain in place and will continue to deliver impact beyond the programme’s funding period.
Inception Phase
1. 2025 Annual Work Plan: Tenure Facility shared its 2024/25 strategy and updated COP30 Action Plan with FCDO, outlining projects expected to receive AMCAT funding. Together, these form AMCAT’s 2025 Annual Work Plan.
2. Project Grants and Opportunities: By January 2025, through AMCAT, the Tenure Facility was funding 14 active in-country grants across seven countries, with three additional projects in development. Between January and June, 16 small grants were submitted for no-objection. These support Indigenous and Afro-descendant organisations, mapping entities, media platforms, and regional exchanges. Four more were proposed in June. A regional assessment was launched to identify gaps, with a second learning/regional assessment expected in 2026.
3. Talent Recruitment: Tenure Facility hired two Indigenous leaders as Regional Programme and Learning Officers, plus financial officers in Colombia and Peru, and a staff member relocated to Brasilia, bolstering presence in the region. Recruitment of five entry-level IPLC professionals was paused due to UK aid budget uncertainty.
4. COP30 Strategy: An Action Plan was submitted to FCDO, focusing on five objectives: advancing the COP26 IPLC Pledge, influencing policy, amplifying IPLC voices, supporting regional platforms, and strengthening Tenure Facility’s visibility. Eleven small grants and related activities are underway through November 2025.
5. IPLC Consultative Body (Yutzu Group): Tenure Facility established the Yutzu Group, named after a deep-rooted Amazonian plant, that commonly grows along riverbanks in the Amazon and helps stabilise soil and prevent erosion, hence making it a symbol of resilience. The group was given this name because it is firmly rooted in Amazonian realities and aims to strengthen nature’s resilience through inclusive, IPLC-led strategies. It is a consultative body of 15 diverse members from eight Amazon Basin countries. The first meeting took place in September 2025 in Brazil to build shared understanding and provide strategic recommendations.
6. International Climate Finance (ICF), Key Performance Indicators (KPI) Methodology: FCDO and The Tenure Facility agreed on methodologies for reporting against ICF KPIs, including transformational change (KPI 15), technical assistance (TA KPI 2), and mobilisation of public and private climate finance (KPIs 11 and 12).
7. Programme Launch: AMCAT was officially launched on 4 June 2025 at a regional Indigenous Pre-COP30 meeting, attended by 60–70 leaders and NGOs from all nine Amazon Basin countries.
After working together with The Tenure Facility, AMCAT’s logframe has been updated to align with The Tenure Facility monitoring framework – AMCAT’s outcome structure is set out below. The logframe milestones are not cumulative; they are set and measured on a year-by-year basis. AMCAT contributes to these milestones by partially funding the portfolio of Tenure Facility’ projects in the Amazon Basin. However, because FCDO is not the sole funder of these initiatives, the results achieved cannot be attributed exclusively to FCDO. Instead, they reflect the combined efforts of multiple partners and funding sources.

Table 2 - AMCAT's Outcome and Intermediate Outcome Indicators
Outcomes		Tenure Facility Indicators
Outcomes	Outcome 1 - Strengthen IPLC forest tenure security and empower the community-based organisations responsible for forest and territorial governance across the Amazon Basin.	Outcome 1.1 – (TF Outcome indicator 1.1) - Number of hectares of IP, ADP and LC land and forests formally recognised by the government during the year, in the Amazon. / Outcome 1.2 – (TF Outcome indicator 1.2) - Number of hectares of land and forest where IPs, ADPs, and LCs have made identifiable progress in their de jure or de facto rights and/or governance during the year, in the Amazon. / Outcome 1.3 – (TF Outcome indicator 1.3) - Number of communities with land and forest rights formally recognised by the government during the year, in the Amazon. / Outcome 1.4 – (TF Outcome indicator 1.4) - Number of communities where IPs, ADPs, and LCs have made identifiable progress in their de jure or de facto rights and/or governance during the year, in the Amazon.
	Outcome 2 - IPLC organisations leverage additional forest climate finance and regulatory policy decisions and influence policy narratives in favour of their forest tenure security agenda.	Outcome 2.1 - ICF KPI 11 – Volume of public finance mobilised for climate change purposes as a result of ICF. / Outcome 2.2 - ICF KPI 12 – Volume of private finance mobilised for climate change purposes as a result of ICF. / Outcome 2.3 – (TF Outcome Indicator 4.2) - Documented examples of funders investing more in IP, ADPs, and LC land and forest rights and governance and adopting better funding practices influenced by Tenure Facility, in the Amazon. / Outcome 2.4 – (TF Outcome Indicator 3.1) - Number of Tenure Facility-funded projects that have contributed to changes in policies, laws, and regulations to advance IP, ADP, and LC land and forest rights, in the Amazon.
Intermediate outcomes	Intermediate Outcome 1 - Successful approaches are scaled up and adopted	Intermediate Outcome 1.1 - TF Outcome Indicator 1.5 - Successful approaches scaled up and adopted across the Amazon (New).
	Intermediate Outcome 2 - Capacity of IPLC organisations strengthened.	Intermediate Outcome 2.1 -ICF TA KPI2 – Number of individuals and organisations informed by ICF technical assistance. / Intermediate Outcome 2.2 – (TF Outcome Indicator 2.6) - Number of Tenure Facility-funded projects that have improved the governance and strengthened the capacity of partner organisations in non-financial aspects, in the Amazon. / Intermediate Outcome 2.3 – (TF Outcome Indicator 2.7) - Number of Tenure Facility-funded projects that have strengthened the capacity of partners to mobilise resources and manage funds, in the Amazon.
	Intermediate Outcome 3 - IPLC organisations include women, girls, and minorities in decision-making and forest governance.	Intermediate Outcome 3.1 – (TF Outcome Indicator 2.1) - Number of Tenure Facility-funded projects that have strengthened gender equality in communal land and forest rights and governance and/or IP and LC organisations, in the Amazon.

Outcome 1: Strengthen IPLC forest tenure security and empower the community-based organisations responsible for forest and territorial governance across the Amazon Basin.

AMCAT supported meaningful progress on land rights and territorial governance across nearly nine million hectares, with approximately two-thirds of this area advancing toward formal land title recognition, primarily in Brazil and Colombia. Notably, nearly 250,000 hectares were formally recognised by governments, representing a meaningful step forward in securing IPLC territorial rights and reinforcing their role in forest stewardship. In Peru, the Harakbut Peoples approved a territorial plan for 2.7 million hectares through a participatory process.

Outcome 2: IPLC organisations leverage additional forest climate finance and regulatory policy decisions and influence policy narratives in favour of their forest tenure security agenda.

The above gains were reinforced by major policy reforms, including a decree in Colombia enabling Indigenous reserves to become autonomous local governments, and by the National Land Agency issuing four resolutions delimiting the territories of four Indigenous Councils, providing legal protection for nearly five million hectares. Brazil and Colombia also committed to integrating Indigenous and Afro-descendant priorities into their COP30 NDC submissions. In Pará, a “Free Babassu Law” provided symbolic and practical protection for women’s land rights, safeguarding babassu palms across more than half a million hectares. Brazil’s Quilombola movement influenced the launch of a national titling agenda and secured symbolic and legal recognition of traditional practices. Both governments committed to integrating Indigenous and Afro-descendant priorities into their COP30 submissions. Meanwhile, innovative funding mechanisms, such as the Cali Fund and Podaali’s Indigenous Sciences Award, are beginning to channel resources directly to IPLC communities, supporting forest protection and autonomy. These developments mark a shift toward greater IPLC influence in policy, finance, and territorial governance.

Intermediate Outcome 1: Successful approaches are scaled up and adopted.
This intermediate outcome will require further refinement, as the indicator it contains is newly introduced within the Tenure Facility’s Monitoring, Evaluation and Learning (MEL) framework. Nonetheless, the programme’s catalytic potential is already evident in the adoption of innovative mechanisms such as the Cali Fund and Podaali’s Indigenous Sciences Award. These models are gaining momentum and present scalable approaches to IPLC-led finance and governance.
Intermediate Outcome 2: Capacity of IPLC organisations strengthened.

Capacity building was evident across strategic planning, communications, legal support, and alliance-building, with several organisations gaining visibility and influence in national and international policy spaces. Notably, Brazil’s territorial funds improved financial management systems and autonomy, contributing to a growing network of community-led funding mechanisms. These developments reflect a shift towards more empowered, self-determined IPLC leadership in land governance and advocacy.

Intermediate Outcome 3: IPLC organisations include women, girls, and minorities in decision-making and forest governance.

Progress on gender equality was evident across several projects, including the Free Babassu Law in Brazil, which protects the rights of women harvesters. Many grants also supported women-led organisations and promoted inclusive decision-making and governance structures – more info in the equity part of section D below.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The programme has demonstrated exceptional efficiency and strategic relevance within the wider forest and land portfolio. Thanks to the Tenure Facility’s established base of projects, AMCAT funds have been deployed from day one, achieving significant operational gains - minimising setup time and maximising early results.

## C. DETAILED OUTPUT SCORING

Table 3 - AMCAT's Output 1 Indicators
Output Title	IPLC organisations implement increasingly effective approaches for forest governance and tenure security at local, national, and regional levels across the Amazon
Output number:		1	Output Score:	A+
Impact weighting (%):		50%	Weighting revised since last AR.	N/A

Indicator(s)	Milestone(s) for this review (December 2025)	Progress
Determining indicator structure for this output and agreeing it with the delivery partner	Logframe indicators agreed	Achieved: structure of indicators and associate MEL for this output set out below.
Output 1.1 – (TF Output indicator 2.3)- Number of TF projects that have improved the governance of IP & LC territories by strengthening local institutions, agreeing on norms, and/or preparing territorial plans in the Amazon.	11	On track: Six projects reported results on territorial planning, village governance mechanisms (e.g. elections, assemblies, statutes), village-level training, and cultural heritage and revitalisation.
Output 1.2 – (TF Output indicator 2.4) - Number of TF projects that have strengthened IP&LC community mapping and monitoring in the Amazon.	10	Achieved: Ten projects reported results on strengthening mapping and monitoring.
Output 1.3 – (TF Output indicator 2.5) - Number of TF projects that have facilitated IP & LC use of courts and police to ensure rights to land and forest are respected in the Amazon.	4	Surpassed: Eleven projects reported results related to the use of courts and police.
Output 1.4 – (TF Outcome Indicator 2.2) - Number of Tenure Facility-funded projects that have assisted IPs, ADPs, and LCs to resolve conflicts related to land or forest, in the Amazon.	10	On track: five projects reported conflict resolution results.

Briefly describe the output’s activities and provide supporting narrative for the score.

Working closely with the Tenure Facility’s Amazon team, we have revised our indicators to align with the Tenure Facility’s reporting structure. Further details are outlined in Section G (MEL) below. The updated logframe will guide future reporting.

This output has made strong progress across all three indicators, with one milestone achieved, one surpassed, and two ongoing for completion by the December 2025 deadline. The activities reflect increasingly effective approaches to forest governance and tenure security by IPLC, particularly in strengthening local institutions, territorial monitoring, legal engagement, and conflict resolution.

Output 1.1 – Notable progress in strengthening local norms, institutions, and planning processes has reinforced governance, cultural identity, and traditional knowledge - key foundations for sustaining low deforestation and emissions across IPLC territories. Several successful initiatives illustrate this progress. Four projects in Bolivia (National Confederation of Indigenous Women of Bolivia - CNAMIB), Guyana (Amerindian Peoples Association - APA), and Peru (Native Federation of the Madre de Dios River and Tributaries (FENAMAD), Awajún Autonomous Territorial Government (GTAA), and Wampis Autonomous Territorial Government (GTANW)) reported holding recent territorial elections, and developing statutes, territorial plans, maps, and data collection systems. These Indigenous territorial governments play a critical role in forest protection.

Another notable example includes ten Samaaka villages in Suriname, which documented and reintroduced customary agreements, rules, and supervisory structures. In addition, across the region, training was provided for village leaders and facilitators on topics such as local governance, Indigenous agroforestry, project formulation, legal frameworks, customary governance, mapping, and monitoring.

Output 1.2 – Significant progress on territorial mapping and monitoring has empowered IPLC communities to defend their lands, strengthen legal claims, and respond to environmental threats with locally generated data and tools. AMCAT supported territorial mapping and the formation of monitoring teams, providing them with training and equipment, and facilitating collaboration with government agencies and technical experts. Projects in Colombia, Ecuador, Guyana, and Peru stood out for their robust use of Geographic Information Systems (GIS), while initiatives in Brazil relied more heavily on partnerships with local universities. IPLC organisations used mapping to establish land claims, resolve boundary disputes, develop land use plans, collect data on social and environmental condition, and promote community knowledge and appreciation of their territories.

For example, local mappers in the Kapyra-Kanakury Territory in Brazil mapped the boundaries and occupation of their 542,000-hectare territory as part of a self-demarcation process to support legal claims. In Guyana, APA and Indigenous District Councils conducted mapping to develop Village Sustainability Plans and document cultural heritage.

Another standout initiative was Podaali in Brazil, which strengthened monitoring across nearly three million hectares of rainforest in three territories. This was achieved by funding local Indigenous organisations to develop monitoring plans; train Indigenous monitors in mapping, drone use, first aid, and territorial rights; provide boats and communications equipment and contract aerial surveillance flights.

These efforts are among the most effective ways in which IPLC organisations combat environmental destruction in their territories. Much of the monitoring focused on illegal and legal mining, especially mining conducted without community consent and associated with mercury contamination. Activities ranged from drone, satellite, and aerial surveillance, to intercepting illegal miners and equipment, documenting village rights, monitoring mercury levels in people and fish, and filing complaints and coordinating with government agencies.

Output 1.3 – Meaningful progress was recorded in the use of courts and police to protect rights, helping to strengthen legal recognition and enforcement of IPLC land and territorial claims and reinforcing accountability for violations. In Colombia for example, the court system sought guidance from The National Commission of Indigenous Territories’ (CNTI) legal team on Indigenous territorial rights. Judges, magistrates, and law professors attended a workshop organised by CNTI on interpreting national and international jurisprudence related to Indigenous territories. CNTI also secured multiple judicial and administrative victories, resulting in court orders protecting individual communities.

In Bolivia and Peru, IPLC organisations coordinated with courts and law enforcement agencies to resolve land conflicts and address illegal activities. In Peru, two Indigenous autonomous governments (GTAA and GTANW) engaged with the High Commissioner for Combatting Illegal Mining, national police, environmental prosecutors, and the Ministry of Interior to halt illegal mining. The Superior Court of Amazonas collaborated with GTAA to implement the Awajún Justice Code and GTAA ordinances within Awajún territory.

At the international level, The Confederation of Indigenous Nationalities of Ecuador (CONAIE) (Ecuador), The Association of Indigenous Village Leaders in Suriname (VIDS), and The Association of Saamaka Traditional Authorities (VSG) (Suriname) were involved in two landmark victories at the Inter-American Court of Human Rights. Additionally, two District Councils in Guyana launched the country’s first rural paralegal program, aimed at helping local communities understand and defend their legal rights and address other pressing issues.

Output 1.4 – The reporting period saw meaningful progress in strengthening IPLC governance and conflict resolution. At the policy level, organisations in Colombia, Ecuador, and Brazil collaborated with national agencies to develop guidelines and agreements addressing land and interethnic conflicts. For example, CNTI and Colombia’s National Land Agency worked on Indigenous land titling disputes, while CONAIE and The Confederation of Indigenous Nationalities of the Ecuadorian Amazon (CONFENIAE) (Ecuador) studied conflict resolution in protected areas. In Brazil, The Interstate Movement of Babassu Coconut Breakers (MIQCB) and The National Institute for Colonisation and Agrarian Reform (INCRA) agreed to pursue public funding for a joint initiative to resolve land conflicts. At the field level, mapping teams and Indigenous organisations helped settle disputes over land boundaries and resource ownership in Guyana, Bolivia, and Peru. However, fewer projects reported conflict resolution outcomes than anticipated, and the Tenure Facility will assess whether this reflects the actual situation or a gap in reporting.

Given the scale and results of activities, and the early achievement of key milestones, this output merits an A+ score.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made, and no changes are planned as a result of this review.

Lessons learned this year and recommendations for the year ahead.

This year’s progress highlights the importance of strengthening IPLC rights and territorial governance through locally driven planning, monitoring, and legal action. Territorial governments and village-level institutions in Bolivia, Guyana, Peru, and Suriname made significant strides in formalising governance structures, revitalising customary norms, and developing territorial plans. These efforts not only reinforce cultural identity and traditional knowledge but also contribute directly to forest protection and climate resilience. The widespread use of mapping and monitoring - covering millions of hectares - demonstrates how combining Indigenous knowledge with modern tools like GIS and drones can effectively defend territories against illegal activities and environmental degradation. Legal empowerment emerged as a particularly strong area, with nearly triple the expected number of projects reporting results. Victories in national and international courts, partnerships with judicial institutions, and the launch of rural paralegal programmes show that IPLC organisations are increasingly using legal systems to assert and protect their rights.

Table 4 - AMCAT's Output 2 Indicators

Output Title	Dissemination, exchange, and engagement on diverse IPLC forest governance and tenure security projects across IPLC organisations, governments, and a range of development actors.
Output number:		2	Output Score:	A+
Impact weighting (%):		50%	Weighting revised since last AR.	N/A

Indicator(s)	Milestone(s) for this review (December 2025)	Progress
Determining indicator structure for this output and agreeing it with the implementing partner	Logframe indicators agreed	Achieved: structure of indicators for this output set out below.
Output 2.1 – (TF Output Indicator 3.2) - Number of Tenure Facility-funded projects where government or companies have partnered with IP, ADP, and LC organisations on issues related to land forest rights and territorial governance in the Amazon.	10	Surpassed: Eleven projects fostered partnerships with government, exceeding the annual milestone.
Output 2.2 – (TF Output Indicator 3.3) - Number of Tenure Facility projects that have contributed to (FPIC) in the Amazon.	5	Surpassed: Six projects advanced action on FPIC processes (see more info below).
Output 2.3 – (TF Output indicator 4.2) - Documented examples pointing to a vibrant community of practice focusing on IP, ADP, and LC land and forest rights and governance and uptake of emerging narratives influenced by Tenure Facility in the Amazon.	8	Surpassed: With at least eight major events, this has already met or exceeded the annual milestone

Briefly describe the output’s activities and provide supporting narrative for the score.

Working closely with the Tenure Facility’s Amazon team, we have revised our indicators to align with the Tenure Facility’s reporting structure. Further details are outlined in Section G (MEL) below. The updated logframe will guide future reporting.

This output has made strong progress with all milestones already surpassed. The activities reflect increasing dissemination, exchange, and engagement on diverse IPLC forest governance and tenure security projects across IPLC organisations, governments, and a range of development actors. This surge in dissemination, exchange, and engagement has significantly strengthened IPLC visibility, influence, and coordination - laying the groundwork for more inclusive, impactful participation in global climate and biodiversity processes, particularly at COP30.

Output 2.1 – IPLC organisations have significantly deepened collaboration with governments and other actors, resulting in unprecedented opportunities for IPLC voices to shape COP30. Their joint efforts have secured formal roles in negotiations, expanded representation - including over 1,000 Indigenous delegates accredited for COP30 and placed IPLC priorities at the heart of COP30 planning and dialogue.

These developments contributed to the approval of a work plan for the newly established CBD subsidiary body on Indigenous Peoples and local communities, tasked with implementing Article 8(j). Additionally, an agreement was reached to allocate half of the funds raised by the new Cali Fund to Indigenous Peoples.

The Colombian Government and the International Land Coalition (ILC), a Tenure Facility partner, co-sponsored a major global conference on Indigenous and Afro-descendant land rights - where Indigenous partners, together with foreign ministries of the eight Amazon countries, established a permanent Amazon Indigenous Peoples Mechanism within the Amazon Cooperation Treaty Organisation (ACTO). This mechanism is intended to provide a formal framework for dialogue and negotiation between governments and Indigenous Peoples across the Amazon region.

Output 2.2 – Strengthened consultations and free, prior, and informed consent (FPIC) have ensured that IPLC communities are meaningfully involved in decisions affecting their territories, helping safeguard and strengthen their rights and influence in national climate and development planning. Brazil’s national Quilombola organisation, The National Coordination of Articulation of Quilombola Rural Black Communities (CONAQ), launched a significant campaign to ensure that Petrobras, the state oil company, properly consulted Quilombola communities living along a 2,200-kilometre stretch of coastline from Amapá to Rio Grande do Norte, where oil exploration is planned. In Pará, CONAQ’s state-level affiliate Malungu collaborated with the state government to organise consultations with Quilombola communities regarding a proposed jurisdictional REDD+ programme, which led to changes in the programme design and greater ownership by the Quilombola communities. In Guyana, the government-backed National Toshaos Council began drafting national guidelines for FPIC, with formal input and support from the APA, despite ongoing tensions between the two organisations. In Peru and Suriname, The Regional Organisation of AIDESEP-Uyacali (ORAU) and VSG respectively conducted FPIC consultations with communities involved in Tenure Facility-funded projects. VSG’s second round of consultations focused on planned activities in each community, engaging 177 villagers - half of them women - across ten communities, and resulting in the formal approval of village plans by traditional authorities.
[note] Reducing Emissions from Deforestation and Forest Degradation (REDD)
[note] Interethnic Association for the Development of the Peruvian Rainforest (AIDESEP)
Output 2.3 - Strategic communications and learning exchanges were significantly strengthened, fostering greater visibility and cohesion across regional networks and contributing to a vibrant community of practice and uptake of narratives. AMCAT-supported initiatives helped to convene pre-COP gatherings, launch strategic communications campaigns, strengthen regional platforms, and facilitate high-profile events – all helping to amplify IPLC voices and influence in global climate and land governance. By bringing together diverse regional actors in one place, one of the pre-COP gatherings inadvertently created an opportunity for dialogue that helped ease existing conflicts and facilitated the reunification of The Coordinating Body of Indigenous Organisations of the Amazon Basin (COICA) – the Amazon’s main Indigenous regional organisation. Collectively, these efforts have laid a strong foundation for strengthening the negotiation capacity, visibility, and meaningful participation of Indigenous Peoples and local communities at COP30, helping advance climate justice and territorial rights through locally led, strategically aligned initiatives.
Other events also received support, for example the annual week-long Indigenous Free Land Camp in Brasilia, with over 7,000 attendees, and organised by the Articulation of Indigenous Peoples of Brazil (APIB) and Coordination of the Indigenous Organisations of Brazil (COIAB). The event saw an unprecedented number of international participants and featured a wide range of activities, including panel discussions, learning exchanges, launches of new initiatives and publications, meetings with government officials, marches, and cultural events.
The Global Land Forum also stood out for its strong emphasis on Indigenous and Afro-descendant land rights, helping to elevate the visibility of these issues among decision-makers and opinion leaders working in the land sector. One high-profile event of the forum focused specifically on Afro-descendant Peoples, while another centred on Indigenous Peoples, the forum itself featured multiple related panels and field visits.
The Indigenous Free Land Camp, the Global Land Forum, and to a lesser extent the pre-COPs, received widespread coverage in Brazilian, Colombian, and international media and social media. This significantly raised public awareness of Indigenous and Afro-descendant issues and contributed to shaping policy narratives around them. A key element of this communications effort was the launch of APIB’s and the Global Alliance of Territorial Communities (GATC)’s global campaign, “The Answer is us,” which was unveiled during the Indigenous Free Land Camp.
Given the scale and results of activities, and the early achievement of key milestones, this output merits an A+ score.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made, as this is the first review. A proposed change for the future is to capture and measure the growing number of convenings (e.g. Pre-COPs) that AMCAT is supporting more effectively. While this is partially captured under Output 2.3, it could be more explicitly referenced, including the outcomes of these convenings and how they are contributing to tangible change. Regional-level learning, exchange, and facilitation are proving essential in building shared understanding, strengthening networks, and inspiring action, key ingredients for AMCAT’s catalytic effect. More reflection over the coming year will be needed to better understand and track these catalytic results.

Lessons learned this year and recommendations for the year ahead.

This year saw excellent progress in advancing IPLC forest governance and tenure security. Key lessons include the value of inclusive, multi-stakeholder collaboration, particularly with governments, which led to unprecedented representation of Indigenous leaders at COP30 and the establishment of formal mechanisms for ongoing dialogue, such as the Amazon Indigenous Peoples Mechanism. Strategic partnerships and coordinated pre-COP events have helped shape recommendations and fostered trust and visibility for IPLC priorities.

Efforts promoting free, prior, and informed consent (FPIC) in practice has demonstrated the importance of community-led processes and government engagement, with successful campaigns and consultations in Brazil, Guyana, Peru, and Suriname. Communications and learning exchanges, especially through high-profile events, significantly raised public awareness and influenced policy. For the year ahead, continued investment in regional platforms, strategic communications, and inclusive policymaking, especially around COP30, will be essential to sustain momentum and deepen climate justice and territorial rights outcomes.
## D: VALUE FOR MONEY (VfM)

Summary of VfM

It is too early to assess whether the UK’s contribution to AMCAT meets the value-for-money expectations outlined in the Business Case. The programme has shown strong initial performance, particularly in delivering output indicators. AMCAT’s clear prioritisation of equity has been evident throughout its first year of implementation. To ensure continued cost-effectiveness, the next review period should focus on assessing AMCAT’s catalytic impact, particularly its ability to mobilise additional public and private funding.

Economy

Economy looks at VfM by assessing whether cost drivers are at the right price and of the appropriate quality for the programme and its specific projects. Tenure Facility operates as an international not-for-profit NGO and therefore does not include profit margins in its cost structure. Prior to the MoU signing, a comprehensive analysis of fees, salaries, and other expenses was conducted. As a result, Tenure Facility has adopted streamlined oversight and quality assurance processes to minimise organisational-level costs. Overhead costs are maintained at 10% of direct project costs (total programme budget) - this rate falls within the acceptable range specified in the Business Case, typically between 3-16%. This is a good outcome given the high costs of working regionally across the Amazon.

Regarding AMCAT’s processes and costs, Tenure Facility projects are managed at the local level, with all expenditure, procurement, and negotiations conducted where the projects are implemented. Products and services are also sourced locally, which significantly reduces spend associated with procurement, personnel, and transport, and simultaneously strengthens local economies.

The AMCAT Memorandum of Understanding (MoU) outlines a funding arrangement with an upper limit of £90 million, rather than a guaranteed or fixed allocation. The actual funding disbursed will be subject to ongoing review and is contingent upon the fulfilment of the MoU’s provisions, including revisions to budgets, actual expenditure, and the continued availability of resources within FCDO. The MoU includes provisions that allow for termination, suspension, or amendment in response to concerns about delivery, changes in priorities, or resource availability. Any new contracts and agreements (e.g. External Evaluation Partner) will incorporate review points to ensure alignment with future Spending Review outcomes and evolving strategic needs.

Efficiency

Efficiency looks at VfM by assessing how well the programme converts inputs into outputs. AMCAT’s efficiency has been optimised by selecting Tenure Facility as its delivery partner. Since its inception, Tenure Facility has specialised in doing one thing very well and at scale: partnering with IP, ADP, and LC organisations to develop projects that secure and sustain their rights and enable sustainable land and forest management. This positions AMCAT to successfully convert inputs into outputs, with all logframe outputs currently on track to meeting their 2025 annual milestones.

Importantly, IPLC organisations themselves tend to operate with high efficiency. Their structures are lean, often relying on community-based governance and minimal overheads. Administrative layers are limited, and resources are directed primarily toward on-the-ground activities rather than centralised management. This approach keeps costs low while enabling substantial impact in their territories. As a result, IPLCs represent strong value-for-money partners and reinforce the rationale for an IPLC-led approach.

Programme efficiency is demonstrated by AMCAT’s rapid mobilisation and flexible decision-making. Leveraging The Tenure Facility’s existing systems, relationships, and locally managed operations enabled immediate results without the delays of setting up a new programme. The no-objection process and swift deployment of small grants further accelerated delivery. Strategic partnerships, such as with The Invisible Thread (an NGO specialising in culturally appropriate logistics, translation, and facilitation that strengthen the efforts of IPLCs), also enhance scalability and support regional learning.

As a result, AMCAT has achieved notable economies of scale, reducing transaction costs and rapidly channelling funding to partners. Tenure Facility has increased partner disbursements by 580% since 2021, whilst overhead costs have risen by only 175%. This acts as a strong indicator of Tenure Facility’s performance.

The use of Small Grants has given AMCAT the ability to respond and adapt against an ever-changing Amazonian IPLC context, demonstrating efficiency (with rapid disbursements and flexible prioritisation. The Tenure Facility applies rigorous risk management through country assessments and comprehensive financial due diligence for medium and large grants. Small grants (up to USD 300,000) use a streamlines process, relying mainly on external audits and targeted checks proportionate to risk. The lighter approach enables fast disbursement and flexibility, making it easier to support organisations with established systems and low-risk profiles while still maintaining accountability.

Effectiveness

Effectiveness reflects the programme’s ability to translate outputs into outcomes, and to achieve impact proportionate to the resources invested. The programme has shown strong progress across its three core outcome areas.

It is too early to robustly assess cost-effectiveness. However, there is no evidence at this stage to suggest that the assumptions underpinning the positive cost-effectiveness analysis in the business case are inaccurate.

Equity

Equity is a core principle of AMCAT, embedded throughout both its design and delivery. The Tenure Facility is committed to supporting the self-determination of Indigenous Peoples, Afro-descendant, and local communities, who have not only faced historical exclusion but have also frequently been the subjects of top-down development initiatives where they have had little or no role in decision-making. AMCAT seeks to do things differently, ensuring that projects are genuinely bottom-up and community-led and that IPLCs have equitable access to resources, decision-making power, and the ability to shape how forests are protected and used.

The majority of AMCAT funding is channelled directly by Tenure Facility to IPLC organisations with democratically elected leaderships, ensuring that resources reach those best placed to lead forest governance and conservation efforts. Directly financing IPLC organisations and enabling them to self-design projects is a tangible measure of equity, as it shifts decision-making power to rights-holders, respects Indigenous knowledge systems, and supports self-determination. This approach promotes fair access to resources and strengthens institutional capacity, ensuring that interventions are locally led and contextually relevant. Where fiscal sponsors are used to manage funds on behalf of IPLC organisations, they are selected by the organisations themselves and act solely as financial intermediaries. In some cases, the organisations do not want to manage funds themselves, so that they can focus their efforts on advocacy and other related work. All substantive decision-making authority remains with the IPLC organisations.

IPLC organisations retain full ownership over project design, while the Tenure Facility focuses on assessing value for money and ensuring alignment with country-level strategies. All projects are required to secure free, prior, and informed consent (FPIC) from communities before implementation.

To promote gender equality, project budgets include dedicated funding lines, and partners are encouraged to adopt inclusive and gender-responsive approaches. In 2025, women led six of the 14 main partner organisations (43%), with CNAMIB (Bolivia) and MIQCB (Brazil) formally recognised as women’s organisations. IPLC organisations advanced gender equality through a range of strategies, including leadership development, policy reform, and direct support to women’s organisations. Notable achievements included:

- The launch of an interactive map by the National Organisation of Indigenous Peoples of the Colombian Amazon (OPIAC), showcasing 23 Indigenous women’s organisations across the Colombian Amazon.
- Suriname’s first national Indigenous women’s conference, bringing together women leaders from across the country.
- The largest-ever gathering of Wapichan women in Guyana, with 170 participants from 19 communities.
- Quilombola women in Brazil established the Mokambo Territorial Fund with support from the National Coordination of Articulation of Black Rural Quilombola Communities (CONAQ).
- The National Coordinator of Indigenous Women of Bolivia (CNAMIB) and its member organisations made progress towards securing formal legal status.
- Regional platforms in Ecuador, including the Confederation of Indigenous Nationalities of Ecuador (CONAIE) and the Confederation of Indigenous Nationalities of the Ecuadorian Amazon (CONFENIAE), held meetings to strengthen women’s participation in decision-making spaces.
- The South Rupununi District Council in Guyana formally adopted policies on gender equality and sexual harassment.
These achievements reflect AMCAT’s commitment to inclusive governance and the empowerment of women and marginalised groups.

E: RISK

Overview of risk management

The programme is assessed to have an overall risk profile of moderate. Programme level risks are captured using the AMCAT risk register – summarised below. The risk register is updated quarterly or as needed and we discuss any changes to existing risks or emergence of new ones during our monthly programme management discussions with Tenure Facility, as well as feedback from specialist teams (i.e., security and political teams) in the Embassies. All risks have set escalation processes and agreed thresholds for escalation.

AMCAT’s risk management strategy is tailored to the realities of operating in the Amazon region. It combines rigorous due diligence, adaptive delivery mechanisms, and strong safeguarding and reputational risk controls. These systems are essential to ensuring that AMCAT can deliver transformative impact while navigating the complex and often volatile contexts in which it operates.

Table 5 - AMCAT's summarised risk register
Category	Risk
Financial and Fiduciary	Risks include financial misconduct such as fraud, bribery, and corruption among grantees; misuse of advance payments; programme underspend due to delays in partner delivery; overreliance on a single delivery partner; and a concentration of funding around a single expert organisation, which can limit diversity in approaches and perspectives. There is also a risk of insufficient funding beyond the current spending review period. Mitigation strategies include financial due diligence, break and clawback clauses, regular monitoring, diversified partnerships, and strategic support for local organisational capacity.
People	Risks involve the programme inadvertently increasing intercommunity land disputes due to overlapping claims, and failing to address gender inequality and social inclusion, particularly the dominance of male and elder voices in decision-making. Mitigation includes requiring Free Prior Informed Consent (FPIC), conflict-sensitive project design, and mandatory gender and inclusion components in all grants, with partners reporting on progress.
Policy & Programme Delivery	Risks include vested interests blocking tenure reforms, misalignment between IPLC organisational capacity and programme support, failure to capture catalytic effects, lack of transferability of successful approaches, and activities not optimising conservation outcomes. Mitigation involves regional engagement, capacity building, targeted project selection, and robust monitoring, evaluation, and learning (MEL) systems to assess impact and scalability.
Reputational	Risks stem from the programme being associated with politically sensitive IPLC demands or reforms, and disinformation campaigns, such as recent ones targeting NGOs in Peru, undermining trust, and increasing scrutiny. Mitigation includes maintaining a regional identity, consulting government champions, flexible programme design, and public statements refuting false claims, alongside close monitoring, and stakeholder engagement.
Safeguarding	Risks include Sexual Exploitation, Abuse and Harassment (SEAH), particularly in remote and marginalised communities, and threats to civil society partners from armed groups or resource-related conflict. Mitigation includes adherence to safeguarding policies, grievance and whistleblowing mechanisms, conflict-sensitivity training, and safety protocols for staff and partners.
Strategy & Context	Risks relate to political and security instability in the Amazon region, including civil unrest and targeted attacks on IPLCs, and broader shifts in political economy that may hinder programme delivery. Mitigation includes adaptive management, early warning systems, flexible regional approaches, and prioritisation based on organisational strengths and emerging opportunities.

AMCAT operates in a highly complex and sensitive environment across the Amazon biome, where weak governance, extractive pressures, and increasing threats to Indigenous and environmental defenders pose significant challenges. The programme’s risk management systems are designed to proactively identify and mitigate these risks to maintain stakeholder trust and ensure effective delivery.
The most notable developments in risk have occurred in the strategy and context category, particularly due to rising political instability. Peru and Ecuador are currently experiencing significant turmoil with both countries having declared states of emergency. In Ecuador, the removal of a diesel subsidy has triggered widespread protests, disproportionately affecting Indigenous communities and straining relationships with the government. In Peru, political unrest continues with the election of the eighth president in ten years, alongside disinformation campaigns targeting AMCAT partners and the passage of The Peruvian Agency for International Cooperation (APCI) law, widely referred to as the “Anti-NGO law.” This law significantly expands government control over NGOs receiving international cooperation funding, requiring prior approval for all activities, and classifying legal support to communities challenging the state as a serious offence. It is viewed by NGOs and IPLC as a threat to their autonomy, their access to justice, and undermining democratic principles and their Indigenous rights.
There have also been shifts in political and legal frameworks across the region. In Brazil, the passage of the General Environmental Licensing Act appears to weaken environmental and social safeguards in particular for consultations with Indigenous groups. In Ecuador, the merger of the Ministry of Environment with the Ministry of Energy and Mines has raised concerns whether this signals a rollback in environmental governance. Additionally, the freezing of IPLC organisations’ bank accounts in Ecuador introduces more operational constraints. In contrast, Suriname presents a more positive outlook, with the new administration expressing interest in inclusive governance and land tenure reform.
These developments highlight the importance of AMCAT’s regional and adaptive approach, which allows the programme to respond flexibly to shifting political conditions, mitigate risks, and engage where opportunities for tenure reform are most viable.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Following a comprehensive assessment of potential delivery partners, The Tenure Facility (TF) was identified as the organisation best placed to deliver AMCAT efficiently and effectively. The Tenure Facility has broad geographic reach across the Amazon, trusted relationships with diverse IPLC organisations (including Afro-descendant communities), a proven grants mechanism, robust results reporting, regional presence, and the ability to influence wider forest and climate finance initiatives. Its strong track record of direct and semi-direct grant-making to IPLC organisations, combined with its culturally sensitive and community-led approach, make it uniquely suited to deliver AMCAT’s outcomes.

AMCAT is primarily delivered through a Memorandum of Understanding with the Tenure Facility, which started on 1 January 2025. The budget for this MoU is up to £90 million, of which a large majority of funding (~80%) is allocated for direct grants to downstream IPLC organisations. In addition, AMCAT spending reported in this AR includes support for the design of the programme through a contract with DAI Global UK Ltd (£348k, March-September 2023) and for FCDO engagement during the multi-country scoping mission.

Table 6 - AMCAT spend to date (as of 30 September 2025)
	Financial Year
Budget Line	23/24	24/25	25/26	Total
Design:
Stakeholder Engagement	£7,449	£0	£0	£7,449
Programme Design (DAI)	£348,194	£0	£0	£348,194
Implementation
Tenure Facility
Project Activities (e.g., Grants)	£0	£2,219,783	£3,354,941	£5,574,724
Staff Costs	£0	£53,436	£471,951	£525,387
Travel and Subsistence	£0	£0	£164,792	£164,792
MEL	£0	£0	£92,293	£92,293
NPAC	£0	£227,322	£408,398	£635,720
Total	£355,643	£2,500,541	£4,492,375	£7,348,559
			Total Spend	£7,348,559

Since the start of our collaboration with the Tenure Facility, the FCDO AMCAT programme team has worked closely with them to ensure that both narrative and financial reporting align with FCDO requirements. This includes monthly meetings involving the FCDO’s Senior Responsible Owner (SRO), Project Responsible Owner (PRO), Programme Manager, and regional coordinator, alongside The Tenure Facility’s Programme Lead and Finance Lead, to review progress against financial forecasts, deliverables, and risks. It also included visits to Tenure Facility’s headquarters for negotiations on alignment and to allow FCDO to gain insight into their practices and systems, as well as joint field missions to the region to better understand the work on the ground, engage with stakeholders, and review objectives and progress.

Initial challenges arose in Q1 of FY25/26 due to delays in disbursing grant payments to downstream partners, resulting in actual expenditure reaching only 20% of the forecasted amount. However, the Tenure Facility has since provided regular updates to reassure FCDO that spending is on track. Notably, some of the Q1 underspend was recovered in Q2, with actual spend exceeding forecasts by 30%. The programme team will continue working with The Tenure Facility to further improve the accuracy of financial forecasting.

We engage regularly with embassies across the Amazon region to ensure alignment and transparency around AMCAT activities. Recently, we completed a series of in-depth “deep dives” to connect Tenure Facility country leads with the IPLC focal points in each embassy. These sessions also helped Posts gain a detailed understanding of the projects being funded on the ground. As a result, many Tenure Facility country leads have developed working relationships with embassy staff, fostering synergies with other programmes and collaboration on shared goals beyond AMCAT. In addition to these targeted engagements, we hold regular bilateral and regional meetings with embassies - both ad hoc and as required. Embassy staff are consulted in decisions over new project proposals in their respective countries. To stay informed of political and regulatory developments, we convene monthly regional meetings, with every fourth session dedicated specifically to AMCAT. These meetings also serve to update teams on programme progress and strategic priorities.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
During programme design, FCDO agreed to adopt Tenure Facility’s existing indicators and milestones to shape AMCAT’s logframe. This will streamline monitoring and reporting processes and minimise administrative burden, particularly for IPLC organisations, who often cite excessive reporting requirements as a barrier to effective collaboration.

AMCAT has one impact indicator (measured via ICF KPI 15 on transformational change), two principal outcomes and three intermediate ones. The first outcome, linked to Component A, focuses on strengthening tenure security and governance, measured by land formally recognised and improvements in rights and governance. The second outcome, aligned with Component B, assesses IPLC capacity to mobilise forest finance and influence policy, tracked through climate finance mobilised (ICF KPIs 11 and 12), increased donor investment, and policy change contributions.

The intermediate outcomes include:
1. Scaling successful approaches, with new indicators under development.
2. Strengthening IPLC organisational capacity, including in fund management and governance.
3. Advancing gender equality through inclusive decision-making and equitable access to land and forest rights.

The programme has two outputs which track progress against the principal outcomes. These outputs measure: i) land and governance improvements, including the formal recognition of land, strengthened tenure systems and increased capacity to resolve conflicts; and ii) IPLC capacity and influence, assessed through mobilisation of climate finance, increased donor investment, and contributions to policy change.

During the inception phase, FCDO and The Tenure Facility also agreed to implement a dynamic and adaptive monitoring, evaluation and learning (MEL) approach designed to support real-time learning and evidence-based decision-making. Central to this approach is a participatory Monitoring for Learning component, in which IPLC stakeholders play a key role in tracking and reporting on activities using culturally appropriate methods. For example, this may include video or audio storytelling for communities with oral traditions, community mapping sessions, or visual diaries that reflect local knowledge systems. These approaches ensure that monitoring is not only inclusive but also resonates with the ways communities traditionally share and validate information. Monitoring occurs at both local and regional levels, ensuring quality assurance and capturing lessons learned. Tenure Facility provides strategic oversight, leads evaluations, facilitates cross-component learning, and identifies scalable approaches to forest governance and tenure security. The MEL system also monitors contextual risks with a strong emphasis on conflict sensitivity and safeguarding. In the spirit of listening to IPLCs and responding to the barriers they have identified in working with donors, FCDO is adapting its reporting requirements to align with what the Tenure Facility already collects. Information may be submitted in different formats, such as video recordings, particularly where communities rely on oral traditions. The Tenure Facility then compiles and translates these inputs into a digestible format suitable for donor reporting, helping to ensure accountability while avoiding unnecessary bureaucratic pressure.

Additionally, to ensure accountability and long-term impact, external evaluations (due to take place at mid-term and end-of-programme) will assess effectiveness, value for money, and the programme’s catalytic influence on policy and financial systems supporting IPLC-led forest governance. FCDO (and The Norwegian Agency for Development Cooperation - NORAD) will contribute to an independent evaluation of The Tenure Facility, planned for early 2026, and with a special emphasis on the Amazon Basin. This evaluation, covering the period 2022–2025, will help establish a baseline understanding of Tenure Facility’s work in the region, providing a foundation for measuring AMCAT’s impact more accurately. These evaluations will also examine the integration of gender equality, diversity and social inclusion (GEDSI), and the sustainability of IPLC networks across the Amazon. The expected content and plan to deliver these external evaluations should be completed over the next coming year.
Tenure Facility Results Reporting
The Tenure Facility monitors project outcomes by systematically collecting, verifying, and analysing data on how initiatives support Indigenous Peoples’, Afro-descendant Peoples’, and local communities’ land and forest rights, as well as territorial governance. Partners submit activity and results reports twice a year (or at project completion for small grants). Programme Officers review these reports, triangulating information from social media, news, and other sources to draft results aligned with the Tenure Facility’s 2023–2027 Results Framework, which AMCAT also follows with minor adaptations.
These results are entered into the Tenure Facility’s project management system, ROOTS, and undergo a two-stage review. First, the MEL team checks for quality and clarity in collaboration with Programme Officers and partners. Then, for AMCAT-related projects, the Amazon Basin Coordinator conducts a second review, resolving any outstanding issues before marking results as complete. Final copyediting is done by the Development Unit, after which results are approved and ready for donor reporting. This iterative process ensures that reported outcomes are accurate, consistent, and reflect real progress on the ground.
Reporting
This first Annual Review is being completed in November because of when the Business Case was approved and uploaded to the system (the formal annual report date is locked in as 18 November). However, as we are working with The Tenure Facility’s calendar year reporting cycle, this report reflects on actions from the Business case approval through to September 2025.
Going forward, we plan to align our Annual Reviews to The Tenure Facility’s reporting calendar. Future Annual Reviews will be drafted in May, based on Tenure Facility’s annual report which are due in April - covering the full previous calendar year. The Tenure Facility Annual report will serve as the primary source of information for reporting against International Climate Finance (ICF) Key Performance Indicators (KPIs).
Each year, the Tenure Facility will submit two narrative reports: one in November, covering progress from January to July, and another in April, covering January to December. FCDO’s monitoring will consist of a single Annual Review drafted each May, alongside contributions to ICF KPI reporting. The next Annual Review will therefore be produced in May 2026, covering the full 2025 calendar year.
Monitoring visits
Over the past ten months, the FCDO programme team has actively engaged with UK Posts and IPLC stakeholders across the Amazon region, strengthening trust, alignment with UK priorities, and collaboration with local partners. Field visits and regional events have reinforced the Tenure Facility’s strong reputation among IPLC organisations as a responsive and trusted partner. These engagements have informed programming decisions, surfaced risks and synergies, and enhanced the UK’s credibility in advancing land tenure security.
Evidence
We have just begun receiving data from the first year of implementation, and so far, no changes in evidence or implications for the programme are visible. Wherever possible, all data is disaggregated in line with the Inclusive Data Charter, including by sex, age, geography, and other relevant variables.

Learning
During the inception phase of AMCAT, the programme team prioritised continuous learning through regular and responsive communication with Tenure Facility, both online and in person, including organising deep dives with each Post in the region. These exchanges have been used to pilot processes, gather feedback, and adapt implementation strategies in real time. Strategic meetings are documented and stored in the programme’s SharePoint to ensure a clear record of decisions and evolving conversations, and to ensure continuity of knowledge in the case of staff turnover.
Key lessons from the first ten months include:
- Cross-HMG synergies: AMCAT’s impact on land tenure can be significantly enhanced through stronger coordination with other His Majesty’s Government (HMG) programmes addressing related challenges such as Indigenous livelihoods, bioeconomy, environmental crime, and financial innovation. While AMCAT focuses on securing IPLC land rights and strengthening governance, long-term territorial governance also depends on broader economic and security conditions. Recent engagement has revealed promising opportunities for collaboration with initiatives like the Biodiverse Landscapes Fund, the Forest Governance, Markets and Climate programme, the Land Facility, and Aim4Forests. To avoid siloed interventions and maximise impact, the programme team should actively pursue deeper coordination across HMG efforts in the region.
- Engagement with UK Posts has been instrumental in aligning AMCAT with in-country IPLC agendas. Early coordination helped establish shared understanding, but political sensitivities and national contexts have required more frequent and nuanced dialogue, particularly where reputational risks may arise. AMCAT’s co-creation model, which places IPLC organisations at the centre of programme design and decision-making, differs from traditional HMG initiatives that are typically shaped through government-to-government engagement. This has required both programme teams and embassies to adjust our ways of working. The initial months of implementation have allowed the programme team to test the governance model, build communication channels, and align expectations around decision-making and resource allocation. Partnering with The Tenure Facility not as a delivery contractor, but as a strategic partner with its own mandate and expertise, has further challenged our conventional ways of working and introduced valuable learning for the FCDO teams.
- Aligning MEL Systems for Efficiency and Coherence: A key learning has been the importance of aligning the programme’s Monitoring, Evaluation and Learning (MEL) framework with The Tenure Facility’s existing MEL and reporting cycles. Rather than establishing a parallel, project-specific MEL structure, integrating additional variables into the existing system has proven more efficient and sustainable. This approach has supported coherence across reporting, reduced duplication, and strengthened the programme’s ability to track progress in a way that complements institutional processes.
- Monitoring Catalytic Impact Remains Complex: Tracking the programme’s catalytic effects, such as influence on regional mechanisms, policy uptake, and replication of innovative models, presents challenges. These results will unfold over longer timeframes and through indirect pathways, making them difficult to quantify within standard reporting cycles. This highlights the need for flexible indicators and qualitative methods to better capture the programme’s broader strategic contributions.
Recommendations:
- Agree with the Tenure Facility on practical ways to measure their newly introduced Outcome Indicator 1.5: “Successful approaches scaled up and adopted across the Amazon.”
- Revisit and, if necessary, update programme assumptions and indicators to reflect shifts in the global funding landscape.
- More explicitly track and assess the impact of AMCAT-supported convenings, which play an important role in strengthening negotiation capacity and unlocking further financing – both important elements of AMCAT’s catalytic ambition.
- FCDO programme team to begin planning for external Evaluation, including how this will complement Component C and align with existing Tenure Facility MEL systems.
Date of last narrative financial report	01/09/2025	Date of last audited annual statement	01/09/2025