BUSINESS CASE ADDENDUM

PROGRAMME TITLE	Water Adaptation and Desalination Infrastructure (WADI)
Directorate/ Post	MENAD/Jordan	Contact name	Yolanda Chakava
Original programme budget	£5,000,000	Country or region targeted	Jordan
Cost extension value (if applicable)	£15,000,000	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	HoM
New increased or reduced programme budget (if applicable)	£20,000,000	Original programme start and end dates	08/12/2024 - 31/03/2030
Latest AR programme score	N/A	New programme end date (if applicable)	N/A
		Programme ID	400043

Detailed Information
Programme Summary / Jordan faces existential water scarcity. Without large scale water supply, more efficient usage and improved management, Jordan will be unable to provide its population with a decent standard of living, climate risks will be exacerbated, and economic growth will remain stagnant (or decline), adding to Jordan’s debt burden and potentially leading to instability. / The approved £5 million WADI Business Case was designed to provide flexible, demand-driven Technical Assistance (TA) over five years (FY24/25 to FY29/30) to support the Government of Jordan (GoJ): / Enhance water supply at scale via the ~$61 billion Aqaba Amman Water Desalination and Conveyance Project (AAWDCP), also known as the National Conveyor Project (NCP), Jordan’s largest freshwater scheme in history. / Manage demand for water at scale to improve water efficiency in the agricultural sector, which is responsible for over half of the country’s usage. / Reduce inefficiencies and encourage innovation, through targeted smaller scale interventions (supply and demand) to strengthen water management and governance. / Through WADI, FCDO has commissioned flexible TA in the form of a dedicated Risk Management Facility (RMF) to proactively work with the GoJ to identify, advise, manage, coordinate across stakeholders and propose actions to mitigate inherent and residual risks over the construction phase[1]of the NCP, working within the Project Management Unit (PMU).
Changes
What is the purpose of making this change? / The WADI Business Case (BC) has not been amended previously. Despite the (original) Concept Note approved for £20 million for both TA (RDEL) and grant funding (CDEL) support for the NCP, the £5 million WADI BC was developed and approved to provide TA only. This was due to lack of information regarding the status / progress of the NCP and FCDO ODA budget uncertainties. The approved WADI BC clearly stated that an addendum to incorporate the grant funding would be submitted when key information on the NCP funding, design aspects, costs and timeframes was made available. / The purpose of this change is to increase the cost and extend the time of the WADI Business Case, to match the approved Concept Note value and align with the NCP construction phase. The cost increase will provide an additional £15 million Capital Expenditure (CDEL) grant funding for the NCP, with a minimum of £5 million to be disbursed within this financial year. The time extension will add 21 months to the Concept Note and Business Case (non-material change), extending from March 2029 to end on 31 December 2030. / The £15 million CDEL cost extension will support the GoJ to fill a critical gap in mobilising grant funding needed to reach financial close and mobilise NCP construction by March 2026. The 21-month time extension to end 31st December 2030 will align implementation of the RMF and grant funding, with the planned construction phase timeframe of the NCP. / This change is fully aligned with the (original) £20 million WADI Concept Note approved by the Minister of State for the MENA region on 4 August 2023 and the £5 million WADI BC approved by HMA to Jordan on 30 September 2024. This change also fits with the objectives outlined in FCDO’s Jordan Country Plan 25/26 Goal 2: Resilience - “increase economic stability and economic opportunities" - of the British Embassy Amman’s Country Business Plan. / Why now? / Over the past 10 months, funding from development partners and multilaterals has been pledged; preliminary designs completed with the contract value increased (up to ~US$6 billion from US$3.5 billion in the BC); early works contracts were signed in April 2025; detailed design is near completion (December 2025); and the financial close deadline target with the Investor set for March 2026, subject to the GoJ meeting the minimum grant contribution requirement. The planned NCP construction timeframe is from 2026 – 2030. / The UK is currently the only major bilateral partner not providing grant funding for the NCP. An FCDO funded climate scoping study undertaken over 4 months (December 2024 – February 2025) concluded that the NCP is critical to achieving even a minimum level of water security and climate resilience for Jordan, and needs as much support as possible (including from the UK). Without the NCP, political and social unrest become acute risks, threatening Jordan’s stability. / There is now significant momentum behind the NCP. There are credible private sector companies leading the construction (Meridiam- SUEZ), with strong political commitment from the GoJ and substantial financial backing from the US. Our grant contribution, alongside other partners, will help the GoJ progress a major climate adaptation infrastructure project aligning with its NDC targets and socio-economic goals, for Jordan’s water security and stability.
Implementation
This BC amendment to incorporate UK grant funding for the NCP will require a change in the implementation modality. Options involve leveraging sources of private finance using UK instruments, establishing a formal partnership with the GoJ for the NCP and /or working with like-minded partners to mobilise additional financing through an appropriate funding arrangement. The three implementation options are assessed below: / Option 1 – Complementing public funding: UK grant funding directly supports the GoJ via the Ministry of Water and Irrigation (MWI). As per conditions set out in the government’s Joint Funding Agreement (JFA), our donor grant funding is deposited into a ‘Collection Account,’ which will then fund an account dedicated to the NCP implementation referred to as the ‘Escrow Account’ (may include sub-accounts). The Escrow Account will be used exclusively by the GoJ to make direct contractual payments for the NCP construction. / Option 2 – Leveraging private finance: UK grant funding implemented via the two Private Infrastructure Development Group (PIDG)[2] companies Emerging Africa & Asia Infrastructure Fund (EIAAF)[3] and GuarantCo,[4] could be used in two ways: 1) As blended finance (via EIAFF) to lower the cost of borrowing (e.g. from 3.5% down to 2 -3%), which would unlock $75 million in concessional financing for the NCP; and 2) As equity alongside a debt guarantee to mobilise up to 3 times private financing for the NCP (e.g. $5 million can leverage and additional $15 million in guarantees). Both options utilise UK expertise, provide innovative capital at more favourable rates for the Investor (Meridiam-SUEZ), deliver good value for money and maximise UK development impact. / Option 3 – Partnerships with International Finance Institutions (IFIs): UK grant funding is channelled through an IFI (such as EBRD or EIB) to increase concessionally in lending to the GoJ for specific components of the NCP construction or NCP Readiness project (which is equally urgent). EBRD has currently pledged €150m (€100 million EBRD loan / €50 million grant funding) and are seeking partners to blend financing to increase concessionality. / Options Appraisal / Option 1 [Complementing public funding] involves signing a Memorandum of Understanding with GoJ and making a direct minimum grant contribution of ~£5 million (~$6.67 million) to the NCP Escrow Account, which is managed by the GoJ and co-financed by other donors. This contribution would represent approximately 7% of the initial mobilisation payment required to reach financial close (estimated at ~$104 million). This is the most favourable option for the GoJ in terms of direct financial support and is likely to generate significant political capital for the UK. In terms of VfM, this option optimises economy as all inputs into the Escrow Account directly fund the NCP construction; and is effective given the critical importance of reaching financial close at this stage. However, efficiency and attribution of equity outcomes and impact and will be difficult to isolate, due to the scale of the project, government management of the account and wide range of stakeholders involved in construction. / Option 2 [Leveraging private finance] involves blending financing through making a one-off grant contribution to EAAIF via PIDG Technical Assistance Fund (TAF). A minimum contribution of $10 million would unlock $75 million in concessional financing for Meridiam ($15 million for required concessionally). Assuming a linear relationship and depending on the concession structure over time. This Option gives the UK is likely to deliver political capital for the UK. In terms of VfM, economy and cost-effectiveness are strong in leveraging significant additional financing at favourable terms; efficiency is high in delivering through trusted UK instruments; and is equitable in directly contributing to tariff reduction. / Option 3 [Partnerships with IFIs] involves blending financing with partner IFIs (e.g. EBRD) through making a grant contribution for the NCP Readiness project. At the time of writing details on the financing packages were not available, and the GoJ appetite to commit to further lending is unclear. Although this remains a credible option, the timing is unlikely to work within this FY 25/26. / While Option 2 – leveraging private finance through EAAIF/ PIDG – offers the highest value for money with a 1:7 leverage ratio, potential reductions in borrowing costs of at least $23 million, and measurable impacts on water tariffs that could save up to $450 million over 25 years. However, despite its strong economic case, this option is constrained by external dependencies, including central decisions on UK posts engaging with PIDG and Meridiam’s willingness to proceed. Lack of central support, coupled with low confidence in securing commitments in time to disburse funding within this financial year, mean Option 2 is not viable. / Option 1 – a direct UK grant to the GoJ via the Ministry of Water and Irrigation – while not offering the highest value for money, is the most practical and deliverable option within the required timeframe. It contributes to the NCP’s financial close, enables the UK to visibly support GoJ priorities and will deliver political capital. Given the urgency to commit funds this financial year and critical importance of the NCP reaching financial close by March 2026, we recommend proceeding with Option 1. / Value for Money / Notwithstanding the above, Option 1 offers value for money across three out of the four E’s: economy, efficiency, effectiveness and equity. / Economy: A minimum UK contribution of ~£5 million representing approximately 7% of the initial mobilisation payment, is a financially affordable and strategically targeted investment. By channelling funds through the existing Escrow Account, managed by the Government of Jordan and co-financed by other donors, the UK avoids the administrative and operational costs of setting up new delivery mechanisms. This approach minimises overhead costs and management time, enabling the UK to directly support the NCP construction. Economy will be measured by the Outcome - timely disbursement of UK funds into the Escrow Account (before financial close). / Efficiency: Contributing through the Escrow Account enables streamlined fund deployment via a government-managed mechanism. It reduces our internal administrative burden, supports coordinated implementation with other donors, and allows for timely disbursement aligned with GoJ milestones. This approach maximises operational efficiency and minimises transaction costs, ensuring that our funds are utilised effectively without duplication or delay. Efficiency will be measured through GoJ reporting to donors confirming the Outcome - UK funds in the Escrow Account have been disbursed to the Project Company (Meridiam-Suez), with evidence that agreed payment milestones have been met. / Effectiveness: The contribution directly supports the GoJ in reaching financial close for the NCP— a critical milestone for project delivery. It aligns with GoJ priorities and timelines and is backed by a robust financial oversight mechanism. An independent and reputable audit firm will be appointed by the Ministry of Water and Irrigation to conduct annual financial and compliance audits of the Program, including the Escrow Account and related transfers. This strengthens accountability and ensures that funds are used as intended. Effectiveness will be measured through the Outcome -audit report with details of the disbursement issued to donors. / Equity: While equity impacts are difficult to isolate within a pooled funding mechanism, the UK’s contribution indirectly supports improved access to water infrastructure, which is expected to benefit underserved populations. However, due to the scale of the project and the range of stakeholders involved, direct attribution of equity outcomes remains challenging. / Management Arrangements / The Economy and Prosperity team at the British Embassy Amman will continue to manage WADI, with a designated Senior Responsible Owner, Programme Responsible Owner, Programme Manager and multi-disciplinary Advisers to ensure compliance with FCDO’s Programme Operating Framework, and development impact.
Budget
This FY 25/26, 16% of Jordan’s ODA allocation will be spent on economic development, with the majority (61%) minimum ~£5 million CDEL spend allocated to WADI for the NCP. WADI is part of the office ambition to prioritise UK bilateral spend on economic resilience and stability in Jordan and 100% of this funding contributes to UK ICF targets. See funding breakdown below: / approved Concept Note budget – £20,000,000 / total amount already spent - £67,220 / planned RMF budget - £4,932,780 / cost extension amount - £15,000,000 / This cost extension is financially affordable within the Post/Directorate allocation.
Impact
Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition
Risk
The WADI programme’s overall risk is rated ‘moderate’, aligned with BE Amman’s risk appetite. The team will manage risks via a quarterly-updated risk register. Key new risks and mitigations due to the additional grant funding are summarised below and will be refined during mobilisation and inception. / Table Risk Management / Risk Description Residual (Post-Mitigation) Rating Comments / Policy and Programme Delivery / GoJ does not finalise (currently ongoing) NCP negotiations and procurement, resulting in severe delays in uptake. Major The UK has limited influence; funds may be redirected to other impactful projects. / Strategy & Context Risk / Global and regional conflicts significantly affect cost and pricing of materials, resulting in delays to NCP construction. Moderate WADI TA includes the RMF to proactively track this risk and propose mitigation measures. / Financial and Fiduciary Risk / Risk of funds channelled through GoJ systems being used in a fiduciary or a fraudulent manner. Moderate FCDO conducted a Fiduciary Risk Assessment (FRA) through independent consultants that was completed in September 2025, including the water sector. The main mitigation recommendation for the Water/NCP that we will take forward is to advocate for enhanced transparency of the NCP Escrow Account by strengthening reporting requirements and progressively integrating donor oversight into national PFM systems, ensuring alignment with TSA principles (High)." / Safeguarding Risk / Risk of exploitation or abuse of beneficiaries, stakeholders and downstream delivery partners through WADI implementation Minor Covered by contracts and Enhanced Due Diligence minimal public interaction. / Reputational Risk / The UK will not be supporting Jordan to manage existential threats from climate change. Minor Protecting plans to make a grant contribution to the NCP this Financial Year.
Results/Monitoring and Evaluation
This addendum supports the WADI Theory of Change (ToC) outcome and impact related to improving water access to enable a decent standard of living for Jordanians and Refugees; ensuring the economy is no longer constrained by water shortages; and promoting climate sensitive growth. Subject to approval of this addendum, the ToC and programme logframe inputs, outputs and outcomes will need to be updated to reflect the grant funding (CDEL). The additional impact from the grant funding will be a seat at the table alongside other partners on Jordan’s largest infrastructure investment, with increased political capital to influence decisions. / SRO and PRO will be conducting Monitoring and Evaluation on a quarterly basis, and this will be revied by BE Amman M&E Adviser on an annual basis, during annual reviews.
[1] Inherent risk refers to the level of risk associated with the NCP before any mitigation measures are applied and residual risks refers to the level of risk after all efforts have been made to reduce the inherent risk.
[2] PIDG is an innovative infrastructure development and finance organisation funded by six governments (UK as largest donor, Netherlands, Switzerland, Australia, Sweden and Canada).
[3] EIAAF raises and deploys public and private debt capital to deliver infrastructure projects
[4] GuarantCo provides local currency credit solutions to help infrastructure projects overcome financial, technical and environmental challenges, for development impact.