Business Case – September 2024

Summary Sheet

Portfolio/ Business/Country Plan Summary: The UK is pursuing a strategic partnership for prosperity, security and sustainability with Jordan. Jordan’s domestic stability remains crucial for wider security in the Middle East. This programme supports Country Plan delivery against the Economic and Prosperity Campaign Goal 3: to increase growth and stability in alignment with Jordan’s Economic Modernisation Vision, through strengthening sustainable and inclusive economic growth (Outcome 2); and enhancing Jordan’s climate adaptation efforts and ability to mitigate the environmental impacts of increased population (Outcome 4).

Title: Water Adaptation and Desalination Infrastructure (WADI) Programme
Programme summary (100 words maximum): / The WADI programme will provide up to £5 million worth of Technical Assistance (TA) over five years (FY24/25 to FY29/30) to support Jordan in enhancing water supply, managing demand for water and reducing inefficiencies. The programme will provide flexible, demand-driven assistance which could include supporting: / Supply at scale via the Aqaba Amman Water Desalination and Conveyance Project (AAWDCP), the Government of Jordan’s (GoJ) top priority to increase water supply. / Demand at scale to improve water efficiency in the agricultural sector, which is responsible for over half of the country’s water usage. / Targeted smaller scale interventions (supply and demand) to strengthen water management and governance. / * The approved concept note for the programme sets out FCDO’s intention to provide both a flexible TA element and grant financing to the AAWDCP. FCDO will carry out a business case addendum for our grant contribution to the AAWDCP when the necessary information on key design aspects, costs, and timeframes is made available.
What is the rationale for UK Aid spending? (200 words maximum): / Jordan is one of the most water scarce countries in the world. Jordanians have less than 100m³ of water per person, compared to the UN water scarcity threshold of 500m³ per person. Current projections estimate that municipal water supply per capita will half by 2040. Climate change and population pressures are exacerbating the chronic water shortage. / UK Aid spending on WADI would help deliver the UK government’s ambition to create a liveable planet and restore strong global leadership by working with countries at the forefront of the climate crisis and support long term stability. / A contribution of up to £5 million to fund flexible, demand driven technical assistance will allow the UK to fill critical gaps and support supply and demand side interventions to improve water efficiency, management and governance in Jordan. / (1) The AAWDCP is the GoJ top priority to increase supply at scale, critical to tackling water scarcity that constrains climate sensitive economic growth and enable a decent standard of living for Jordan’s growing population (including refugees). A high level of risk is a common, almost universal, feature of megaprojects. The UK will add value by enabling residual risk and associated cost, to be reduced through a dedicated specialist Risk Management Facility. (2) Through TA focused on demand at scale, the UK can support evidence-based policy and decision making to promote water efficiencies in the agricultural sector, and support more equitable distribution of water resources. (3) Flexible TA with possible pilot interventions will leverage UK expertise to meet demand for targeted smaller scale interventions to strengthen water management and governance (particularly for vulnerable communities).
Programme Value: £5 million		Country/ Region or Sector: Jordan
Department/Country Office confirmation of review processes		Director/HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact name:		Contact may be the BC author or another lead.
Threshold for final approval of Business Case: / Country Board - HMA
Date of Approval of Concept Note:	04/08/2023	Name and role of Approver / Lord (Tariq) Ahmad of Wimbledon, Minister of State for MENA, AfPak, India, the UN, Commonwealth and the PM’s Special Representative for PSVI
Date of Approval of Business Case:	30/09/2024	Name and role of Approver / Philip Hall, OBE / HMA Jordan
Programme Code: 400043	AMP Start Date:	AMP End Date:
Overall programme risk rating:	Moderate
[note] This is the most extreme definition of water scarcity described as “absolute scarcity” by the UN.

AAWDCP	Aqaba Amman Water Desalination and Conveyancing Project
ASEZA	Aqaba Special Economic Zone Area
COVID	Coronavirus Disease
EIA	Environmental Impact Assessment
EMV	Economic Modernisation Vision
FCDO	Foreign Commonwealth and Development Office
GDP	Gross Domestic Product
GoJ	Government of Jordan
HM	His Majesty
ICF	International Climate Finance
IFI	International Financial Institution
IGC	International Growth Centre
JFA	Joint Funding Agreement
IMF	international Monetary Fund
MCM	Million Cubic Meter
MDPI	Multi-Dimensional Poverty Index
MEMR	Ministry of Energy and Mineral Resources
MoPIC / MoENV	Ministry of Planning and International Cooperation / Ministry of Environment
MoF	Ministry of Finance
MoWI	Ministry of Water and Irrigation
NAP	National Adaptation Plan
NDC	Nationally Determined Contribution
NRW	Non - Revenue Water
RED	Research and Evidence Division
RMF	Risk Management Facility
TA	Technical Assistance
UNHCR	United Nations High Commissioner for Refugees
USAID	United States Agency for International Development
VfM	Value for Money

## Strategic Case
# Why UK intervention is needed

Jordan plays a critical role as a beacon of stability in a volatile region, but underlying vulnerabilities make it a brittle kind of stability.

Multiple and successive shocks have rippled across the Middle East in the last decade, including the war in Iraq in 2003, the 2011 Arab Spring, and the Syrian conflict and the waves of migration that ensued. This has been combined with exposure to global shocks such as the 2008 Global Financial Crisis, Covid, and the Russia-Ukraine war. The current Gaza conflict and Houthi-led attacks on shipping in the Red Sea have introduced further gyrations into an already volatile region. Whilst Jordan is often touted as a beacon of macroeconomic and political stability compared to its regional peers, it is nevertheless a brittle kind of stability. Jordan’s economy is beset with structural weaknesses such as stagnant low growth (2.5% over the past decade), high debt/GDP (89% net of Social Security Investment Fund holdings), high unemployment (21% overall for Jordanians), particularly among youth (46%), and women (31%). Over the past two decades, Jordan’s population grew from 5 to 11 million. Jordan hosts 1.3 million Syrian refugees (around 650,000 registered with UNHCR) and 2.3 million Palestinian refugees. Population pressure has placed immense strain on living space and water resources.
[note] Jordan Humanitarian Fund Annual Report 2021 | OCHA (unocha.org)
[note] Country Climate and Development Report- World Bank Group. November 2022

Water scarcity is an existential issue for Jordan, posing a major constraint to climate sensitive economic growth and its ability to provide a decent standard of living for the growing population.

Jordan has the second most water deprived population in the world, with less than 100m³ of water per person, compared to the UN water scarcity threshold of 500m³ per person. Jordan depends on agreements with other countries for at least 20% of its water - approximately 10% is from Israel (which is extremely unstable and subject to renewal every 6 months) and another 10% is extracted from a non-renewable aquifer on the border with Saudi Arabia. On current projections, it is estimated that municipal water supply per capita will half by 2040. A household and business survey-based analysis by USAID, Jordan River Foundation and Mercy Corps showed that whilst majority of the surveyed households are connected to the municipal networks, most of suffer from short periods of supply (the vast majority are only supplied for 24 hours per week). As a result, many households purchase water from private suppliers (water tanks) at higher costs with unknown water quality and safety. Poorer and more vulnerable households disproportionately need to purchase water which impacts on their already stretched incomes and exacerbates inequalities. Women and girls are disproportionately affected by inadequate water access due to their role in domestic activities and the importance of sanitation in dealing with menstruation and pregnancy. The paucity of women in the labour market underscores their domestic role: female labour market participation is below 15%.
[note] UNICEF: https://www.unicef.org/jordan/water-sanitation-and-hygiene
[note] This is the most extreme definition of water scarcity described as “absolute scarcity” by the UN.
[note] Aqaba Amman Water Desalination and Conveyance Project Feasibility Study. CDM Smith. March 2022
[note] Water Innovations Technologies Project. Market Mapping: Analysis and Capacity Assessment for Water Conservation Attributes in Five Governorates of Jordan. Final Report- 26 January 2020. USAID, Jordan River Foundation and Mercy Corps.
[note] Palmioli et al, “The gendered impacts of climate change: The Jordan River Basin region and water scarcity”. http://www.ra-un.org/ uploads/4/7/5/4/47544571/13_osce_the_gendered_impacts_of_climate_change.pdf
[note] WeForum, ‘Global Gender Gap Report’, (2021). https://www3.weforum.org/docs/WEF_GGGR_2021.pdf

Climate change and population pressures are exacerbating the chronic water shortage in Jordan. Three of the largest industries (tourism, textiles, and mining) will be adversely impacted whilst the consequences for agriculture are likely to be extreme unless systemic and drastic changes are made in relatively short order. The World Bank estimates that a 20% shortfall in water availability (a plausible scenario reflecting a majority scientific view) could result in a fall in GDP of up to 6.8%.
[note] USAID- Background scope paper. Unpublished.

The Aqaba Amman Water Desalination and Conveyance Project (AAWDCP) is the GoJs top priority to address the existential water scarcity.

Extensive work commissioned by USAID to address Jordan’s water supply at scale shows that even after implementing other interventions, including measures to mitigate non-revenue water, increased groundwater abstraction where it is tenable, increased water purchase agreements from neighbouring countries and re-allocation of water usage (e.g. use of reclaimed water in industry and agriculture), Jordan would still face a water deficit of more than 300 MCM/yr by 2030 and more than 400 MCM/yr by 2040.
[note] AAWDCP Procurement Support Contract (APSC) Statement of Work. Undated. CDM International. Aqaba-Amman Water Desalination and Conveyance Project. Feasibility Study. 2022

The only water resource within Jordan with sufficient capacity to reliably meet the rising demand is the Red Sea. The AAWDCP is the only viable option for providing drinking water at scale. It will be the largest freshwater scheme in the country’s history, producing 300 million cubic meters (25CM per person) of desalinated water and delivering it 420km (uphill) across the country (see Figure 1). The megaproject will be funded by the GoJ, key development partners (including USA, EU, France, and the Netherlands), concessional financing, and private investment.

Figure 1: The AAWDCP Project Description
The project includes the following components: / Marine works in Aqaba (3 intake towers at 750 MCM/yr, intake pump station, brine outfall and energy recovery system at 450 MCM/yr brine, intake and outfall pipes). / Desalination facility in Aqaba (300 MCM/yr drinking water), comprising of pretreatment, reverse osmosis, post treatment and solids handling. / Freshwater Conveyance System (300 MCM/yr in Aqaba and 250 MCM/yr between Aqaba and Amman), 450 km conveyance system with 6 pump station and 10 reservoirs. / Renewable Energy system (300 MW solar, wind or hydropower generation co-located with water systems), 500 km transmission line, transformers, substations, and power lines.

According to the World Bank, the cost of generating potable water through desalination is estimated to be over US$3 per cubic meter, by comparison the equivalent average cost of municipal water provision was US$2 per cubic meter in 2020. However, given the absence of viable alternatives and the acute nature of need, the GoJ has recognised the AAWDCP as a top priority (Economic Modernization Vision, 2023). HMK King Abdullah II stressed the importance of the project to the government regardless of challenges and is personally committed to seeing it progress.
[note] World Bank. Beyond Scarcity: Water Security in the Middle East and North Africa. 2018.
[note] (Jordan's National Water Conveyor and economic transformation | Jordan Times

The interconnected risks of the AAWDCP need to be attenuated to mitigate impact on Jordan’s debt, viability of the megaproject and cost transfer to the population.

Why is the AAWDCP risky?
A Mckinsey paper from 2013 cites that a 10% increase in infrastructure assets increases GDP by 1%. The critical role of public infrastructure and productivity is relatively uncontentious in economic growth theory. By definition, such projects are very big in scale and as a result they carry equivalently large price tags. Governments are almost by default central actors in envisaging and overseeing these projects from inception all the way to delivery, operation, and maintenance.
[note] McKinsey Working Papers on Risk, Number 52. A risk-management approach to a successful infrastructure project Initiation, financing, and execution. November 2013.
[note] César Calderón, Enrique Moral-Benito, and Luis Servén, “Is infrastructure capital productive? A dynamic heterogeneous approach,” World Bank policy research working paper number 5682, 2009

The work of Bent Flyvbjerg and Dan Gardner, alongside collaborations with organisations such as McKinsey, has revealed just how shockingly megaprojects perform. By carefully documenting more than 16,000 projects across a span of 20 plus sectors and 136 countries, their work shows that a staggering 99.5% of projects are over budget, over schedule, under deliver on benefits or some combination of these three criteria. Put another way, just 0.5% of projects are “successful” in that they meet the original design brief and satisfy, cost, time and benefit benchmarks.
[note] How Big Projects Get Done. B. Flyvbjerg and D. Gardner. MacMillan Business. 2023

Table 1 below taken from the Flyvbjerg database shows that for water sector projects the mean average cost overrun is 20% with a 13% likelihood that projects will exceed 50% of the original estimate. Of these projects, the average cost overrun is 124%. In other words, roughly every one in seven water sector projects has a budget that exceeds 50% of the original forecast and on average the costs incurred increased by a factor of 1.24 times the starting budget, so a £100m project in this scenario would have cost £124m.

By virtue of the huge costs and long-time frames to deliver megaprojects, the scope for risks to transpire rises exponentially. According to Flyvbjerg, megaproject risk is not normally distributed. Instead, megaprojects have “fat tails” – that is the cost overruns can be several times the average and the incidence of these extreme cases is higher than for normal distributions. The AAWDCP is an exceptionally complex megaproject, incorporating a conveyancing and energy component alongside the desalination. Each of these three components will carry its own set of risks and merging them under one project increases the number of risks it is exposed to. This heightened likelihood of risk carry-over across the three components almost creates a contagion affect. Relatively minor mishaps and accidents have the potential to have major knock on affects across the project as a whole because of built in interdependency across the three major elements.

Table 1: Base rates for cost escalation by sector type
Project Type	Mean cost overrun (%)	(B) / % of Projects in Tail / (> 50% overrun)	(C) / Mean overrun of Projects in Tail (%)
Nuclear Storage	238	48	427
Olympic Games	157	76	200
Nuclear Power	120	55	204
Hydroelectric Dams	75	37	186
IT	73	18	447
Nonhydroelectric Dams	71	33	202
Buildings	62	39	206
Aerospace	60	42	119
Defence	53	21	253
Bus rapid transit	40	43	69
Rail	39	28	116
Airports	39	43	88
Tunnels	37	28	103
Oil and Gas	34	19	121
Ports	32	17	183
Hospital, health	29	13	167
Mining	27	17	129
Bridges	26	21	107
Water	20	13	124
Fossil thermal power	16	14	109
Roads	16	11	102
Pipelines	14	9	110
Wind power	13	7	97
Energy transmission	8	4	166
Solar power	1	2	50

Source: Flyvbjerg database

Typically, when risks for megaprojects are not comprehensively identified and mitigated from the outset, at the design stage, the costs when these risks materialise end up being absorbed by the government and/or passed down to the end user. The limited scope to take on more debt constrains the GoJ room for manoeuvre. Similarly, additional costs would be undesirable to consumers in a country where 21% of Jordanians are unemployed. At the same time, donor funds to support the AAWDCP are limited. In the context of challenging fiscal commitments to lower debt levels by 2028 agreed with the IMF and rising debt service costs crowding out capital investments, undertaking an ambitious national desalination project of this scale poses considerable risks for the GoJ.
[note] As part of its US$1.2bn 4-year programme with the IMF, the GoJ has committed to reduce debt to GDP levels from current levels- 89% to less than 80% by 2028. This is considered a very stretching target, especially given the adverse impacts on Jordan’s economy due to the war in Gaza.

The implementer will have a risk management approach to identify and monitor risk within their remit, as will GoJ. They will likely follow a compliance-based risk approach that is built around transparency and avoidance of misconduct, the prevailing norm in public sector projects. As above, even with the standard risk mitigation measures in place, only 0.05% of megaprojects meet the original design brief and deliver within the agreed cost and timeframe. There is a strong Value for Money (VfM) case for assisting the GoJ through the provision of a dedicated Risk Management Facility, that takes a dynamic approach to creatively and collaboratively look at residual risks (the risk post mitigation by the implementer and the otherwise unidentified risk) that need to be identified and mitigated. These could include:

- GOJ interministerial coordination. Interconnected risks may not be identified or appropriately mitigated due to a lack of ownership. For example, the impact of energy pricing on large scale water projects and debt, and vicar versa, require ownership across multiple stakeholders (Ministry of Energy and Mineral Resources, Ministry Water and Irrigation, and Ministry of Finance) which would benefit from a central facility to support effective risk management.
- Black Swan events. Delivery of megaprojects is a high risk, stochastic activity, with overexposure to extreme events with hugely negative outcomes (black swans). Risk won’t be appropriately mitigated if managers treat the project as if it existed largely in a world of cause, effect and control (Flyvbjerg, 2017).
  [note] Introduction: The Iron Law of Megaproject Management (2017). Flyvberg, B.
- Land and displacement. Significant demand for land for the project causing adverse effects on populations in its path and potential displacement.
- Distributional impacts. Adverse impacts on specific groups of people, e.g. the most vulnerable.
- Unintended impact on the marine environment. Inexperience in managing the impacts of the desalination process especially brine disposal and the level of complexity could lead to residual risk to the marine environment.
- Lack of focus on inclusion. Project resource constraints (both financial and human) in could lead to inclusion not being mainstreamed throughout implementation.
- Exacerbated pressure on Jordans finances. Unmitigated risks leading to increased costs of the project, including for example interest rate pressures, putting further pressure on Jordan’s already very tight fiscal space. For example, the ongoing impact of the Gaza conflict on Jordan’s economy is an unknown.
- Increased debt burden for Jordan’s National Electric Power Company (NEPCO). Setting low or inefficient tariffs to make the NCP financially viable will generate additional long-term losses to NEPCO, which compromises the energy sector’s financial viability and puts pressure on Jordan’s overall debt management

There are significant inefficiencies in the water sector in Jordan. Even with the additional 25 cubic meters per capita the AAWDCP will produce, water management needs to improve significantly to meet future demand.

Even with the additional 300MCM of potable water the AAWDCP will provide annually, once operational demand for water will still outstrip supply by 2040 (see Figure 2). The additional 25 cubic meters will mean that Jordan has just under than 125 m³ of water per person, which is still substantially under the UN water scarcity threshold of 500m³ per person. With Jordan’s growing population, additional interventions are necessary to address water supply and demand side constraints.
[note] UNICEF: https://www.unicef.org/jordan/water-sanitation-and-hygiene
[note] This is the most extreme definition of water scarcity described as “absolute scarcity” by the UN.
Figure 2: Water supply and demand in Jordan

Source: MoWI
To address demand side pressures on Jordan’s water resource at scale, focus needs to be on Jordan’s highly water intensive and inefficient agriculture sector.

Figure 3 below shows that irrigation water forms 61% of the total water demand in Jordan whereas municipal and industrial demands form 31% and 6% respectively.
[note] Water shortage in Jordan – Sustainable Solutions (2010). Nidal Hadadin et al. Desalination Vol 250 Issue 1, p 197-202.

Figure 3: Water use in Jordan

The Ministry of Water and Irrigation (MoWI) in its latest national strategy, recognises the inefficiencies in agriculture and the significant ramifications this has for Jordan’s overall water demand as well as its long-term food security. Climate change will further increase the demand for water in the agricultural sector and reduce yields of Jordan’s rainfed crops. According to MoWI the ‘economic value of irrigation water’ is 50% higher in the Jordan Valley compared to the highlands based on the kinds of crops grown and agricultural technologies (or lack thereof), which suggests there is significant scope for developing a strategy to change practices.
[note] Jawad Taleb Al-Bakri et al., “Impact of Climate and Land Use Changes on Water and Food Security in Jordan: Implications for Transcending ‘The Tragedy of the Commons,’” Sustainability 5, no. 2 (February 2013): 724–48, https://doi.org/10.3390/su5020724; Rodomiro Ortiz, “Crop Genetic Engineering Under Global Climate Change,” Annals of Arid Zone 47 (September 1, 2008): 343–54

There is scant evidence of a concerted policy to establish a solid evidence base around the water efficiency of different crops and agricultural technologies. The World Bank have done some analysis that compares intensity of water use for a range of crops between Jordan with Israel and OPTs as part of its work on climate adaptation. Consistent crop mapping, alongside the regions they are grown, who is farming them, technology used, and scale has not been carried out in Jordan. The World Bank estimates that shifting towards less water-intensive crops, scaling-up evaporation proof vegetable production coupled with irrigation technology could in total help Jordan to achieve its US$ 1 billion agricultural export potential. Thus, there is a substantial evidence gap to optimise the water efficiency of agriculture, and also significant commercial opportunities to be gained.
[note] Country Climate and Development Report- World Bank Group. November 2022

There is a unique opportunity for UK expertise to support Jordan in addressing overall supply and demand side constraints to water management and governance.

Water management is a complex and multi-faceted area that requires interdisciplinary analysis. Beyond the big-ticket items (large scale supply increase through the AAWDCP and promoting efficiencies in the largest consumer of water, agriculture), this ranges from water infrastructure resilience, water tariffs, urbanisation and other human-induced disruptions impacting water resources, water recycling and re-use, water quality, the impacts of climate change (including drought and flood risk management), the water-energy-food nexus, water conservation and water-use efficiency.

The UK already funds world-class research through the International Growth Centre (IGC) as part of our Jordan Investment and Economic Reform Advisory programme (JIERAP). IGC have a significant existing portfolio and pipeline of research on the water sector in Jordan, covering areas such as pricing, water-saving technologies, behavioural change and the water-agricultural nexus. The UK also has a wealth of resource and expertise to draw on in FCDOs central Research and Evidence Department (RED) and shown global leadership on how to incorporate evidence into policy decisions through the from the What Works initiative. Drawing on well-established expertise, the UK can add unique value by focusing on research, evidence, and technical assistance to support Jordan in promoting efficiencies in water management.

The WADI programme will provide up to £5 million worth of TA over five years to support the Government of Jordan in implementing high priority interventions to enhance water production, manage demand for water, and reduce inefficiencies. The programme will provide flexible, demand-driven assistance which could include supporting:
1. Supply at scale via the AAWDCP, the GoJs top priority to increase water supply.
2. Demand at scale to improve water efficiency in the agricultural sector, which is responsible for over half of the country’s water usage.
3. Targeted smaller scale interventions (supply and demand) to strengthen water management and governance.

# STRATEGIC FIT AND RATIONALE FOR UK INTERVENTION

The UKs Integrated Review states that tackling climate change and biodiversity loss is the UK’s number one international priority. The White Paper on International Development recognises that growing water insecurity, accelerated by climate change, is rapidly undermining the achievements of the global goals for ending poverty and food security and that the human and economic consequences are profound. It makes helping developing countries adapt to the impacts of climate change a priority. The UK Government’s Mission statement emphasises the ambition ‘to create a world free from poverty on a liveable planet’ to increase our climate ambition and restore strong global leadership by working with countries at the forefront of the climate crisis.

The AAWDCP is a national priority identified in Jordan’s Economic Modernisation Vision (EMV). As such, the WADI programme supports the British Embassy Amman’s Business Country Plan to support Jordan’s EMV to increase growth and stability (Campaign Goal 3), by enhancing Jordan’s climate adaptation efforts, and ability to mitigate the environmental impact of increased population in particular (Outcome 4).

Over the past six years, UK ODA spend on economic growth in Jordan has significantly declined. This FY 24/25, spend on economic development represents 4% of the overall bilateral ODA budget allocation for Jordan of £53 million. This programme is part of the office ambition to increase spend on economic growth in Jordan to 10-15% of the total ODA allocation for FY 25/26 and beyond, pending spending review decisions. The direct trade-off will be a minimal reduced spend on humanitarian response cash transfers, to focus on supporting inclusive economic growth and job creation, build resilience and reduce dependency on aid. This approach aligns with UK Government priorities, British Embassy Amman Country Business Plan and the Government of Jordan's EMV.

# Assurance of Compliance with UK Law

Climate and environment
The technical assistance provided through this programme will contribute to climate and nature protection and management. Jordan has included water as a key climate adaptation sector in its national climate change policy (2022-2050) with several policies and actions aiming to reduce vulnerability and increase resilience to the impacts of climate change and climate variability in a proactive manner. The policy mentions desalination as one of several actions to promote the development and use of non-conventional water and refers to the AAWDCP as an example. Investment in desalination plants and inland seawater use is set as a policy indicator.
[note] National Climate Change Policy for the Hashemite Kingdom of Jordan 2022 – 2050, 2023, Ministry of Environment.

The updated Nationally Determined Contribution (NDC) highlights the water sector as an important climate adaptation contributor, and the AAWDCP as part of the country’s efforts to address the challenges associated with the on-going water scarcity with a planned 185 MW solar PV component to cover 50% of the project’s power demand.
[note] Updated Submission of Jordan’s 1s t Nationally Determined Contribution (NDC), 2021, Ministry of Environment.

In its strategy for the water sector, the MoWI stresses the urgency of implementing large desalination projects and states that the AAWDCP will bridge the demand-supply deficit by 2035 and allow for groundwater recovery by reducing or stopping extraction.

Jordan emphasises the importance of the water sector – among six green growth sectors – in greening the economy, attracting green investments and creating green jobs for Jordanians. The Water Sector Green Growth National Action Plan (2021 – 2025) indicates the potential for renewable energy powered desalination plants to serve as an enabler for green growth.

Jordan’s National Adaptation Plan (NAP) includes important measures under the programme “improving adaptive capacity of water utilities” to protect water utilities (including desalination plants) and enhance their adaptative capacity. Such measures include: conducting climate-proofing studies for planned utilities including Environmental Impact Assessment (EIA), climate resilient water safety plan and other legally binding assessments. The NAP stresses on the importance of Climate Resilience Water Safety and Security Planning to identify adaptation measures at the utility level.

Gender and Public Sector Equality Act (2010)
This programme will be compliant with both the UK Gender Equality Act and Public Sector Equality Act. Equity and inclusion of women and girls is an important theme in Jordan’s Business Country Plan.

There is still a lack of female representation in water-related policy making. In a study by the Women Studies Unit at the Ministry of Water and Irrigation of Jordan, interviews and surveys were conducted with women and men working in three water entities and three companies undertaking the governance and operation of water and sanitation services. The results of the study reveal the weak representation of women in the sector, with female employees constituting only 11% of the total workforce. Gender disparity is also observed with regard to leadership and supervisory positions, of which only 17.5% are held by women in the Jordanian water sector.
[note] E Andrew, L Pamioli & C Borges, “The gendered impacts of climate change: The Jordan River Basin region and water scarcity”, (2020). https://www. researchgate.net/publication/348550735_The_gendered_impacts_of_climate_change_The_Jordan_River_Basin_region_and_water_scarcity
[note] USAID, Water Management Initiative, “The Status of Women in Jordan’s Water Sector”, (2019).

WADI will ensure equality in opportunity throughout all levels of its delivery. This business case noted that the poorest and most marginalised households are disproportionately affected by water scarcity. Stronger evidence on distributional impacts could be developed through the technical assistance provided by the programme. At the impact level, WADI aims to improve water management in Jordan to help address a key barrier to growth, unlocking job led growth, which can create opportunities for women and girls (if complementary policy and programming addresses the disproportionately low female labour market participation rate in Jordan).

Disability
The programme will contribute to the implementation of the FCDO Disability Inclusion Strategy. This include ensuring persons with disability are not excluded from programmes. Performance against disability and ensuring no harm will be monitored through the annual reporting process.

Safeguarding
The programme will adhere to HMGs safeguarding policies, referenced under Contract Condition 50 in FCDOs standard terms and conditions for supplier and within the Code of Conduct Annex. The FCDO Jordan programme team will monitor that all implementing partners are compliant with the safeguarding rules. Application and monitoring of these policies will be reviewed and tested throughout the programme cycle.

Counter-terrorism financing
Our assessment is that the risk of programme resources being used to fund terrorism is low and acceptable. We will ensure that all implementation partners are aware of HMG policy and funding rules on counter terrorist financing. All contractual agreements and payments processing will be done in accordance with relevant laws and regulations. Management review and decision will be sought in cases where there is any concern or doubt.

Peace, Security and Stability
Given that the scarcity of water and water management that favours those in power and those economically better off causes (sometimes fatal) water disputes in communities and can act as a threat multiplier when it comes to societal stability in Jordan, the programme should be accompanied by a conflict sensitivity analysis. This should examine:
- where and how water disputes happen;
- how good water management and equitable distribution can reduce conflict potential;
- and how potential security threats to the long pipeline can be mitigated.

A conflict and gender sensitivity analysis could also usefully link to equity VfM indicators by considering what equitable water management would need to look like, taking into account dimensions such as gender, power relationships, vulnerability and exclusion etc.

## Appraisal Case
# Theory of Change

Problem statement: Jordan faces existential water scarcity. Without large scale supply, more efficient usage and improved management, Jordan will be unable to provide its population with a decent standard of living, climate risks will be exacerbated, and economic growth will remain stagnant (or decline), unsustainably adding to Jordan’s debt burden and potential leading to instability.

High level Context		High debt/GDP / High unemployment		Chronic and worsening water scarcity / Rapid population growth
		High risk from undertaking a megaproject		Climate change and rising temperatures

Specific Context		Lack of dedicated support around risk of design and build of megaprojects		Inefficient water usage, management and governance

		Lack of context specific evidence on what works in promoting efficiencies in water supply and demand / (both at large and smaller scale)

Inputs		Dedicated Risk Management Facility embedded alongside the AAWDCP Project Management Unit		Research specialists identify critical gaps. High-quality TA drawn down to improve efficiencies in the agricultural sector and inform smaller-scale interventions to strengthen water management

Outputs		Risk management incorporated into all stages of the AAWDCP lifecycle. / Robust risk management plan informs construction phase.		High quality research and analysis products inform GoJ policies and decision making. / Smaller scale pilot interventions demonstrate more efficient supply and demand practices.

Complementary Outputs		More effective GoJ risk management capacity and expertise around megaprojects.		Improved efficiency and water usage in the agricultural sector for more equitable distribution of water resources. / Improved water management and governance (particularly for vulnerable communities).

Outcome		AAWDCP lifecycle risks are attenuated: costs contained, impact on GoJ debt and fiscal liabilities mitigated. / Water savings are realised. Reforms and interventions in agriculture drive efficiencies and increase crop cultivation. Stronger governance, more sustainable and efficient practices in managing supply and demand.

Impact		People of Jordan have better access to water to enable a decent standard of living, the economy is no longer constrained by water shortages promoting climate sensitive growth, agricultural sector becomes more competitive. Overall support to stability

# OPTIONS APPRAISAL

Option 1 - Do Nothing (Business as Usual) [£0 million]

This is the low ambition scenario. This option means we adopt the status quo and do not deploy any additional resource, whether staff or official development assistance (ODA) to support the AAWDCP or other water-related interventions.

Pros: The benefits are financial and human resource savings (no additional costs to FCDO), reduced administrative burden at the organisational level, and availing staff time to support other Business Country Plan priorities such as sustainable and inclusive growth and mutual trade and prosperity which could have a positive benefit cost ratio.

Cons: This option would mean that we do not meet our International Climate Finance targets in Jordan. UK government departments, research centres and private sector have a strong track record on supporting water resilience and climate adaptation projects through infrastructure, community-based interventions, evidence and technical assistance [1]. While Jordan has not been a recipient of major UK support in the water sector, lessons learned from Africa and Asia would be useful to the Jordanian context.[[2]] With this option, the UK would be foregoing a strategic opportunity to positively influence the AAWDCP and leverage UK expertise to shape reforms in other important water-related interventions including major national priorities around climate adaptation, resource efficiency, economic and agricultural productivity and energy transition.
[[2]] UK aid to agriculture in a time of climate change, ICAI review, June 2023.

Conclusion: While the “do nothing” option may appear as an initial cost saving, economic and reputational risks are high, and lack of UK engagement could negatively affect our relationships with key stakeholders and other areas of macroeconomic stability, resulting in poor VfM in the longer term.

Option 2 – Fixed fiscal advisory support and residual risk management TA for the AAWDCP (water supply at scale) [£5 million]
The complex AAWDCP megaproject is expected to double annual fiscal losses in the water sector from 0.4% on average to nearly 0.9% of GDP. Thus, there would be merit in supporting the GoJ to reduce the possible negative fiscal implications of this megaproject. Option 2 comprises of two distinct approaches involving TA to the Ministry of Finance (MoF), MoWI, Ministry of Planning and International Cooperation
[note] In-house FCDO estimates based on additional water supply quantity of 300MCM/year.
 (MoPIC) in managing the AAWDCP:

Fixed fiscal advisory support: Supporting the MoF with oversight of AAWDCP over its lifecycle, as well as the water sector operators, looking at fiscal liabilities and budget implications. This would involve enhancing cost-impact assessments and compliance with IMF targets, complementing existing work by the Fiscal Commitments and Contingent Liabilities Unit at MoF (supported by the UK through the Jordan Growth Multi-Donor Trust Fund).

Dedicated Risk Management Facility (RMF): Supporting the existing Project Management Unit (PMU) at MoWI to manage actions for the AAWDCP across its lifecycle; coordinate across stakeholders (GoJ agencies, the international community and the private sector); and lead on project communications and reporting with stakeholders. The AAWDCP carries high residual risk, as set out in the risk section of the Strategic Case. Typically, when risks for megaprojects are not comprehensively identified and mitigated from the outset, at the design stage, the costs when these risks materialise end up being absorbed by the government and/or passed down to the end user. The limited scope to take on more debt constrains the GoJ room for manoeuvre and donor funds to support the AAWDCP are limited. This underscores the importance of providing support to help manage risk as effectively as possible. Under this option, the basic premise would be to provide a high-quality RMF to mitigate unidentified risks as far as possible to minimise additional costs being passed to GoJ, donors, and above all else, to consumers. It is recognised that ideally such support should have been integrated into the design phase to maximise impact. Early risk management has the greatest potential to mitigate risk as it is not afflicted by sunk costs and existing investments/commitments. The further down the project cycle risks are dealt with, the less scope there is to attenuate magnitude of loss/exposure. There is substantial scope to provide constructive support to GoJ and add value, as design and planning details are still being finalised. The RMF would be embedded at the centre of the AAWDCP PMU. This approach requires buy-in from all parties, as risks need to be universally understood, so they can be appropriately identified, costed and owned and managed. This is quite distinct from a compliance-based risk approach that is built around transparency and avoidance of misconduct – the prevailing norm in most public sector projects. A gold standard risk management approach requires a creative and collaborative approach amongst stakeholders so that risks are managed dynamically, and this thinking is hardwired into all aspects of the project from beginning to end. The RMF could also be used to improve Jordan’s experience in managing the impacts of the desalination process, especially brine disposal. We envisage this to be an area where we could offer niche TA (including innovative solutions from UK businesses) to the GoJ and/or Aqaba Special Economic Zone Authority (ASEZA) in monitoring and managing impacts on marine environment.

Pros: The two distinct TA options will support/ advise the GoJ on improving financial and fiscal performance (great buy) which is considered good VfM. Given the GoJs commitment to macroeconomic reforms and debt management, this option it likely to attract strong GoJ buy-in and ownership from the MoF. Moreover, this option aligns with the UK’s Business Country Plan Economy and Prosperity outcome of promoting macroeconomic stability, and with GoJ priority pillars under the EME.
[note] FCDO economic development best buys.

Cons: In this option FCDO would be manoeuvring through an extremely challenging context given the difficulty in actualising revenue gains and reducing losses. Addressing short-term needs (including firefighting) can often take a priority over long-term planning. This option carries reputational risks, as the UK could be exposed to negative perceptions if our support fails to meet its intended outcomes, and/or adds (real or perceived) to the existing macroeconomic challenges.

To be effective, delivery of this option would need to be through partners with an extensive and niche track record in fiscal reforms, IMF requirements and managing megaprojects. Complementary expertise in the water-energy nexus would also be required. Finding a single or consortium of delivery partners with the required niche skillsets will be challenging. Management of this option would require direct oversight and heavy engagement from British Embassy Amman to ensure GoJ buy-in and commitment is sustained throughout the lifecycle of the interventions. This would be challenging, and beyond the remit and capacity of the UK and its delivery partner(s) to ensuring effective communication and alignment among the various ministries (MoF, MoPIC, MoWI, MoEnv, MEMR etc), water sector operators and the utilities companies. It will be difficult to directly link the benefits of fixed TA in contributing towards more equitable outcomes for vulnerable groups (including refugees) in promoting stability.

Conclusion: Option 2 would aim to improve the financial and fiscal management of the AAWDCP at both project and macro level to deliver good VfM and is likely to have strong buy-in from the MoF (linked to our ongoing support). However, delivery is likely to be challenging via a limited number of partners and will be entirely dependent on others. The context will be difficult to navigate, and the scope limits our ambition in this space to fiscal and operational management. Operating at macro level, it will be more difficult to achieve equitable outcomes. Given the range and complexity of institutional stakeholders involved, this option carries high reputational risks and will require intensive FCDO programme management.

Option 3 – Fixed TA to managing demand at scale for water [£5 million]

As stated in the Strategic Case, the agriculture sector utilises the most quantities of water. The FCDO could look at propping new water saving techniques, commission research related to the agriculture sector water usage, or work with others who have a longer track-record in the agricultural sector. Additionally, the aforementioned work commissioned by USAID in 2020 in collaboration with Mercy Corps and Jordan River Foundation used a market mapping approach to gauge the level of usage of water saving devices (WSD) across five governorates at the level of households and firms. The study highlighted several areas for potential investigation that could help reduce the cost outlays of households and businesses buying WSD and their maintenance, such as reforms that enable the importation of high-quality devices, training of plumbers so that preventable leakages are fixed to a high quality and in a timely manner and more targeted awareness campaigns about WSD. Building on this evidence base, FCDO could focus on specific interventions that could yield the highest impact in a particularly water-distressed governorate such as Jerash, in order to test what works and is scalable.

Pros: This option builds on existing evidence, thus saving the need for additional commissioning of research (except when there is a specific need) which tends to be timely and can be expensive. Delivery would be at pace, by utilising the USAID-funded research as a starting point and piloting the recommended interventions. If done well, we would expect the pilots to provide implementable examples of interventions that could be scaled up by local authorities. Furthermore, tangible progress on agricultural reforms would constitute a big ‘win’ for the UK as a newcomer to this sector. Reducing water usage in agriculture would enhance the overall supply of water to other more needed sectors.

Cons: We know that this area already has several donors including USAID, Germany and Japan Despite these donors already having programmes covering several areas (apprenticeship schemes for plumbers, sanitation related reforms etc) benefits have largely been localised. It is unclear how much water saving can be achieved at scale, even in the most successful cases. The capabilities of local authorities are inevitably going to vary, thus lessons from any pilot in one locality or governorate may have limited application for another area. Such interventions at community level produce low levels of evidence in terms of cost effectiveness and sustainability, therefore VfM is likely to be low. Most adaptation benefits are typically overestimated. Additionally, almost all interventions are centred around development options with little direct targeting of climate risks. In addition, enhancing water usage in the agriculture sector might prove less attainable given the dependency of farmers on older methods of irrigation and might prove to be an economically less favoured option. Other than utilising USAID-funded research, GoJ buy-in for TA on demand side reform and interventions has not been tested, which could negatively impact delivery. It will be difficult to directly link the benefits of fixed TA in contributing towards more equitable outcomes for vulnerable groups (including refugees) in promoting stability.
[note] This is according to an assessment (February 2024) by Adam Smith International commissioned by FCDO to inform the design of this present WADI Programme.

Conclusion: Whilst Option 3 delivery could be at pace to help improve how water usage in urban areas and agriculture sector, benefits are largely localised and highly variable which would be difficult to measure and scale up. Finally, it is not clear how much of a priority this is for the GoJ, to obtain buy-in. Without strong government ownership at both national and local levels, it is questionable how far any benefits are likely to be realised or sustained, therefore VfM is likely to be low.

Option 4 – Flexible, demand-driven TA for water supply and demand [£5 million]

Option 4 provides a more strategic yet flexible approach in providing streamlined demand-driven TA in niche areas that would enable the UK to demonstrate its leadership and expertise in mega project management, water, climate and the overall sustainable development framework. This option comprises of the two distinct approaches:

Dedicated RMF for the AAWDCP: As stated in Option 2, but with a caveat that this is a flexible facility to directly respond to GoJ demand
[note] TA should be responsive to partner demand rather than directional – FCDO K4D help desk report: Lessons from donor support to technical assistance programmes.

Research and pilot interventions to improve water efficiency, management and governance: While the AAWDCP is the only viable option to scale up water supply in Jordan by 300 million CM per year, even after the project Jordan will still be a water scarce country. Under this option, research specialists will be commissioned to undertake a synthesis of what has been commission so far and needs analysis to fill critical gaps. This would then inform evidence-based policy and decision making and make recommendations for pilot interventions. The UK already funds world-class research through the International Growth Centre (IGC) as part of our Jordan Investment and Economic Reform Advisory Programme (JIERAP). IGC have a significant existing portfolio and pipeline of research on the water sector in Jordan, covering areas such as pricing, water-saving technologies, behavioural change, and the water-agricultural nexus – to name a few. Taking advantage of their research would entail no additional funding through the WADI programme. FCDO has a wealth of experience on water-saving agricultural interventions via our central Research and Evidence Department (RED). The WADI programme could build on this research from IGC and RED to explore funding world-class specialists who could, for example, help to oversee the planting of new heat-resistant and drought resistant crops in suitable terrains, or a variety of other water management interventions. Alternatively, the WADI programme could commission other specialised local and international researchers for the same purpose. This is potentially a high impact intervention to deliver VfM, with relatively low reputational risks given our established track record.

Pros: Option 4 would provide niche TA that will help to gradually enhance UK credibility in a sector (water) where the UK is a newcomer in Jordan compared to other donors. The TA will help to facilitate UK policy engagement with GoJ, and the demand-driven nature of this facility should in theory ensure that the advisory and evidence generated is more likely to get buy-in and be owned by the GoJ. Supply side interventions including direct TA or through providing specialist advice using contacted advisory services on such a megaproject is considered a great buy given the ability to shape the government thinking while working with partner governments. R&D is also a great buy, research normally leading to changes in ways of thinking and therefore policy by the accumulation of evidence rather than a single study. The benefits can be very large, delivering high VfM. Marine works on the other side, has a high potential. The benefit cost ratio for this type of intervention varies, but with positive yields. This flexible approach will enable the UK deliver on a critical megaproject with huge potential for costs to overrun, which will showcase the UK value addition of UK expertise, and demonstrate the cost-effectiveness of the intervention.
[note] The OECD’s (2012) evidence synthesis based on 19 “peer reviews” of donor capacity building activities suggests that ownership can be achieved by ensuring partners play the lead role throughout the process.
[note] FCDO nature-based solutions suggests: Investment in research, monitoring and evaluation to learn ‘what works’ should be a key priority.
[note] A global synthesis of 235 studies from costs of restoration projects of marine coastal habitats report a median of US$80,000/ha and average US$1,600,000/ha (2010 values). Community-or volunteer based marine restoration projects usually have lower costs.
[note] Evidence is emerging and not yet definitive but promising. See Best Buys in Economic Development
[note] Average 87:1 for mangroves (mainly flood protection and fish nursery services), 4:1 for coral reefs, 232:1 for saltmarshes and 5:1 for seagrass.) Successful kelp restoration projects are rare, mostly in small, short pilots and costs have been high.

Cons: The UK might operate separately from other donors who are part of the Joint Financing Arrangement designed to provide technical support to the AAWDCP. The UK operating independently would require proactive engagement with GoJ, other donors and stakeholders to identify unmet TA needs and gaps, to enable us to add value. It will be difficult to directly link the benefits of flexible TA in contributing towards more equitable outcomes. Additional UK grant funding will be important to increase the programmes overall contribution towards promoting stability for vulnerable groups (including refugees).

Conclusion: UK support for the AAWDCP, is likely strengthen our partnership with the GoJ. The demand-driven flexible TA facility will both respond to the GoJ demand for buy-in and ownership, as well as creating the opportunity to leverage UK expertise to support overall water supply and demand efficiencies, management and governance, enabling the WADI programme to achieve its objectives in a context full of uncertainty. Additionally, it presents good VfM opportunities, particularly in terms of effectiveness (likelihood of positive development outcomes) by drawing on TA, research and evidence.

Table 2: The Critical Success Criteria
Critical Success Criteria	Description	Rating	Weight
Ownership of assistance	The programme needs to be accountable to the Government of Jordan, the private sector and the Jordanian public, ensure effectiveness, feed into policy decisions, and have impact if it is demand driven. The work should ensure changes are sustained over the long term and that Government systems are equipped once external funding comes to an end.	Key	35%
Reputational	The inability to provide the needed support to GoJ	Key	25%
Delivery	Deliver results as fast and efficiently as possible. Taking into account and addressing the capacity of key players.	Very important	20%
VfM	Potential to achieve VfM, assessed at three levels – economy, efficiency and effectiveness. This assessment considers not only cost saving but also how to maximise outputs and impacts. Equity proxy has been deployed to test against social exclusion and weak participation such as gender inequality and socio-economic status of disadvantaged Jordanians and Syrians, ensuring the interventions are doing no harm and not exacerbating existing inequalities.	Very Important	20%

Table 3: Options Analysis
Critical success criteria	Weight	Option 1 Do nothing		Option 2 Fixed fiscal advisory support and residual risk management TA for the AAWDCP (water supply at scale)		Option 3 Fixed TA to managing demand for water at scale		Option 4 Flexible, demand-driven TA
		Score	W score	Score	W score	Score	W score	Score	W score
Ownership	35%	0.0	0.0	3	1.05	3	1.05	4	1.4
Reputational	25%	0.0	0.0	3	0.75	2	0.5	4	1
Delivery	20%	0.0	0.0	2.5	0.5	1	0.2	3	0.6
VfM	20%	0.0	0.0	3	0.6	2	0.4	3	0.6
Total (1-5)			0.0		2.9		2.15		3.6

# Preferred Option

Option 4 is the preferred option, best addressing the critical success criteria as reflected in its score in the Options Analysis in Table 3. The demand-driven TA facility will provide sufficient flexibility to allow the WADI programme to achieve its objectives despite numerous uncertainties. The UK will be able to support the GoJ in achieving one of its top priorities, addressing the existential water scarcity in Jordan, as well as meeting our climate ambition and strengthening sustainable and inclusive growth.

Commercial Case

# Assessment of delivery route options

The Appraisal Case set out the rationale for recommending a demand-driven flexible technical assistance (TA) facility to support supply and demand side interventions in the water sector in Jordan. The Commercial Case sets out how our support will be prioritised, i.e. which areas the flexible TA will cover and, and outlines the anticipated delivery route options to ensure that the UK intervention is responsive to changing needs.

Needs Assessment to determine TA type: The areas of focus for the TA provided through the flexible facility are yet to be agreed, in collaboration with the Government of Jordan. A Needs Assessment will be conducted by the WADI programme team to:

- Identify TA required, including gaps, synergies between donors to avoid duplication.
- Guarantee that the TA is explicitly requested by the GoJ, to ensure GoJ ownership and effective implementation.
- Identify niche areas where the UK can add unique value with limited funding.

The Needs Assessment will produce a long list of potential interventions which will be scored against an agreed set of criteria to produce a short list of priority interventions that are within scope of the WADI programme. The programme team will then produce a specific Terms of Reference (ToRs) including details of TA support type, focus, timelines and deliverables.

Table 4 Criteria to select priority TA to be delivered through the WADI programme
		Criteria	Weight
(1)	Need	Addresses a critical gap, which is not being addressed by GoJ or other donors
(2)	GoJ buy in	Meets a key priority for GoJ and a committed GoJ counterpart takes ownership
(3)	Value addition	UK is able to add distinct value by bringing in specific expertise
(4)	Budget and VFM	Feasible within the scope of the WADI programme and presents good value for money
(5)	Impact	Potential for specialized, niche, TA to influence policy and deliver tangible impact
(6)	Sustainability	Potential for effective capacity building, impact on policy change

Once ToRs have been developed for a short list of interventions, the appropriate delivery route will be chosen. Potential delivery routes include:
1. FCDO procurement including frameworks to contract a private sector supplier and draw down experts and/or buying into Centres of Expertise COEs and Centrally Managed Programmes CMPs Drawing down experts can also include the possibility of seconding an FCDO expert to a GoJ entity. This route can be utilized to support the AAWDCP and/or TA beyond the project.
2. Contributing to the GoJ Joint Financing Agreement (JFA) on TA for the AAWDCP. The JFA will pool donor’s contributions to provide TA to support the AAWDCP project with GoJ oversight.
3. Accountable Grant Agreement (AGA) with a local or international NGO or a Memorandum of Understanding (MoU) with a multilateral organisation (administratively similar FCDO agreements). This route can be utilized to support the AAWDCP and/or TA beyond the project.

The selection of the most appropriate route will depend on the specific needs identified. The three delivery assumption routes provide sufficient flexibility to identify the best route based on the TA type and value for money.

Delivery Route Selection: The following factors and criteria will inform the selection of the most suitable delivery route for the determine TA type:

Table 5 Delivery Route Selection Criteria
Agility and time sensitivity	How quickly technical assistance is needed.
Ability to influence	To what extent the delivery route creates opportunity for UK influence.
Expertise and capacity	Availability and suitability of expertise within each route.
VfM	Cost effectiveness of the delivery route in implementing the agreed TA.

Figure 4 explains the delivery route process selection, following the Needs Assessment. Starting with the continuous engagement with GoJ, including key ministries overseeing the project (Ministry of Planning and Cooperation, MoPIC; and Ministry of Water and Irrigation, MoWI). Depending on the area of support, the delivery route will be selected per FCDO’s guidance on funding arrangements and VfM, before mobilising the TA via the implementing partner, the GoJ or/and both.

Figure 4 Delivery routes

# Procurement approach

FCDO procurement including frameworks to contract a supplier or experts. This delivery route allows for the rapid mobilisation of qualified specialists with specific sector expertise. The competitive tendering process will ensure VfM and transparency and can also offer further flexibility to scale up or down based on the intervention needs. This route involves the following:
- Procuring TA by contracting experts through mini competitions below the Official Journal of the European Union (OJEU) threshold, which is usually up to £120,000-£130,000.
- Procuring TA through the established FCDO procurement framework beyond the OJEU threshold. Potential frameworks include the Expert Advisory Call Down Services (EACDS2) and Global Development Delivery frameworks (GDD).
- Buying into available Centres of Expertise COEs and Centrally Managed Programmes CMPs. Possible COEs to utilise include Green Infrastructure and Cities, Green and Inclusive Growth and others.
- WADI Programme-funded secondment of an FCDO Adviser.

JFA between the UK and GoJ on TA for the AAWDCP. This route involves contributing to a government-managed trust fund that pools funding from multiple donors to support TA specifically for the AAWDCP (unlike the other delivery routes which can cover water-related TA more broadly). This will allow coordination and alignment with GoJ priorities, building stronger government ownership and sustainability of interventions, in addition to streamlining progress and audit reporting on TA support.

GoJ is currently developing the JFA framework. The JFA will include grant financing for both the CAPEX and TA elements of the AAWDCP. However, this WADI Business Case considers the possibility of funding the TA part only (a business case addendum will be completed when sufficient information is available to enable us to make a grant contribution to the AAWDCP). Contributing to the JFA will require signing an MoU between FCDO and GoJ, will require alignment with the FCDO Partnership Principles, Fiduciary Risk Assessment (FRA) and the Annual Statement of Progress (ASP). The current design of the JFA covers the programme scope and cost, independent audits, performance assessment frameworks, as well as monitoring and evaluation frameworks.
[note] FRAs are conducted to provide assurance over the partner country/region’s public financial management (PFM) arrangements. FRAs focus on reviewing the partner government’s core financial functions and commitment to improving PFM, including fiscal transparency, good governance, fighting corruption and strengthening domestic financial accountability. In the period between carrying out full FRAs, the ASP Annual Statement of Progress is the primary way in which we monitor a partner government’s commitment to strengthening financial management and accountability.

FCDO Jordan carried out a full FRA in 2022 and an ASP in 2023. Both the FRA and ASP concluded that there was no deterioration in the risks identified, and the trajectory of the overall risk level was stable and assessed as moderate, meaning a change in our risk appetite was not required. The 2024 ASP will be conducted during the second and third quarters of calendar year and should inform the WADI programme team and wider FCDO teams of any changes.

FCDO Jordan has long and extensive experience of working with GoJ, including through a similar JFA to support the Jordan Compact Education Programme between 2016- 2023.
[note] Jordan Compact Education Programme

The WADI programme team have a high degree of assurance that utilising the JFA is suitable if this delivery route is considered via the Needs Analysis step, after signing an MoU with the government. It is critical that the JFA reflects strong mechanisms for transparency and accountability, in addition to accounting for potential delays due to government procedures (including procurement) and bureaucracy risks. Funding the JFA will also be in accordance with guidance set out in the FCDO Programme Operating Framework. All funding will follow standard FCDO terms and set out the expected value and timing of planned payment disbursements.  The timeline for reporting and any other agreements between FCDO and GoJ will be reflected in specific clauses within the MoU. Further details on the governance of the JFA are available under the Management Case.

AGA/MoU: This route involves signing an AGA with a reputable local or international NGO; or alternatively, signing an MoU with a Multilateral to deliver water-related TA.

The selection of this delivery route could be in addition to one of the aforementioned alternative delivery routes (i.e. contractor/supplier and/or the JFA). Overall, NGOs often have strong local presence and understanding of the context, and potentially offer lower costs for FCDO compared to commercial suppliers. Nevertheless, local NGOs may have limited capacity to scale up quickly and may require more grant management and operational oversight by FCDO. Similarly, Multilaterals and INGOs can often deploy their TA more quickly than other contractors or local NGOs. However, they typically have higher rates for experts and higher administrative fees.

Cost Drivers
The table below outlines the main cost drivers associated with each delivery route. Costs drivers and costs will be monitored throughout the programme to ensure VfM.

Table 6 Main cost drivers associated with each delivery route
Delivery Route	Key cost drivers
Procurement of supplier/expert(s)	Daily rates and fees of principle-level experts and specialists, especially international consultants. / Fees and administrative costs of framework agreement, and contactors. / Costs associated with delivery including travel.
JFA	Fees and administrative costs associated with the Project Management Unit (PMU) at MoWI. / Fees and administrative costs associated with contractors and consultancy firms undertaking TA. / Fees and administrative costs of independent auditors for the JFA.
AGA/MoU	Salary costs and administrative costs of (I)NGOs or Multilaterals.

Ensuring VFM
The programme will strive to achieve FCDO VfM metrics, including economy, efficiency, effectiveness, and cost effectiveness.

Economy will be achieved by selecting the best delivery route based on the nature of the agreed TA. The procurement option will allow the WADI programme team to tap into a pre-selected list of suppliers and contractors where rates are pre-negotiated and agreed via the FCDO central Commercial Team. The JFA option will deliver economy through the reduced transaction costs of working through a single facility. For the AGA/MoU delivery route, economy will be achieved through negotiating salary and administrative costs, which are the key cost drivers, prior to mobilising the TA, to be within the acceptable market rate range.

Efficiency will be delivered as we work to reduce duplication and enhance co-ordination between development partners and GoJ. Through the procurement delivery option via mini competitions or via an FCDO framework agreement, the WADI programme team will be able to quickly mobilise the needed TA. Additionally, it would be possible to start with the procurement option, to mobilise TA prior to agreeing on joining the JFA or engaging a local/international NGO – both of which can be lengthy processes (especially for the GoJ JFA), taking months for mobilisation. Rapid mobilisation is essential, especially for TA related to the AAWDCP, as this will be more effective the earlier it begins. This is particularly the case for FCDO’s proposed risk management facility, which revolves around early identification and mitigations of risks.
[note] FCDO experience with the Jordan Growth Multi-Donor Trust Fund, is that GoJ procurement processes can take up to 21 months.

Effectiveness in delivery through the identified delivery routes will be achieved through the high degree of co-ordination between donors, IFIs and GoJ and through the effective mechanisms to identify the needs and mobilise accordingly. Effectiveness should also be viewed in terms of the government’s absorptive capacity, buy‐in and implementation of the proposed intervention.

Cost effectiveness: Providing a relatively small-scale, but flexible and highly specialist technical assistance, will be cost effective as long as needs are appropriately identified, and expertise is matched correctly. The proposed risk management facility, for example, would prove cost effective judging by the cost of cubic meter per end user, total project cost, delays to implementation in days, and financing costs.

Key commercial and delivery risks and mitigation actions
The table below summarises the key commercial and delivery risk as well as mitigation strategies for each of the identified possible delivery routes:

Table 7 Key Commercial and delivery risks
Delivery Route	Commercial and Delivery Risks	Mitigation strategy
Procurement of supplier/expert(s)	Delays in mobilisation and delivery impacting intervention timelines.	Regular monitoring and performance reviews, including clear key performance indicators (KPIs) in contracts, contingency planning, and maintaining a pool of pre-qualified service providers.
	Limited Competition leading to limited proposals received, and consequently the possibility of higher cost	Utilising mini competitions in addition to the most relevant framework for procurement activities.
JFA	Agreement on technical priorities: No clear agreement and coordination between GoJ and donors.	Clear governance and coordination mechanism to be reflected in the MoU between the UK and GoJ, to ensure agreement on technical priorities.
	Cost and scope: Risk of cost overruns due to unforeseen technical change to the scope agreed between donors and GoJ.	Focusing on the Needs Analysis with clear ToRs and agreement on project scope; and managing GoJ and donor expectations on scaling up interventions.
	Delays and slow procurement due to GoJ bureaucracy or capacity issues, in addition to difficulty in understanding the delivery chain, and a lack of responsiveness or flexibility in reporting., including relating to information needed for FCDO Annual Reviews.	Seek assurance from GoJ on their capacity to conduct multiple procurement activities and reflect that in clear KPIs in the MoU between the UK and GoJ, which will include clauses around FCDO expectations on transparency and delivery chain risk maps.
AGA/MoU	Slow mobilisation and responsiveness of (I)NGOs: / Local NGOs may understand the context, but lack capacity and be slow to deploy. / International NGOs and Multilaterals may mean higher costs to FCDO.	Careful selection of the (I)NGO or Multilateral with clear parameters for selection including relatively quick deployment, the understanding that FCDO may negotiate costs, and strong understanding of the local context –with a preference of a combination of both local and international expertise.

Management Case
# Management Arrangements

Management of the WADI Programme will be led by the FCDO Jordan Economy and Prosperity team. The WADI Programme team will consist of the Senior Responsible Officer (SRO), the Programme Responsible Officer (PRO), and a Programme Manager who will be supporting operational activities, financial management and compliance with the FCDO Programme Operating Framework (PrOF) rules/guidelines. The WADI team will also have support from other team members and multi-disciplinary advisers (climate, political and governance, humanitarian, monitoring and evaluation, commercial, and economic advisers).

WADI programme management will also be overseen by existing British Embassy Amman governance mechanism. This includes the Country Board, where the Business Case will be submitted for review and approval by the senior leadership team (including the Head of Mission); and the monthly Delivery Board, which is overseen by the Deputy Head of Mission and Development Director. The below diagram summarises the roles, responsibilities and fit into the British Embassy Amman structure:

Figure 5
# Governance
The management and governance arrangements for the selected TA activities will be detailed per the selected delivery route, as explained in the Commercial Case.
- Procurement of supplier/expert(s): Management and governance arrangements will be detailed in the contract between FCDO and the supplier, reflecting what will be agreed in the scope of work and TORs. The PRO and Programme Manager alongside the Delegated Procurement Officer (DPO) and/or Commercial Adviser will be overseeing the management arrangements, starting with the TORs development. This includes selecting the best procurement route or framework agreement and moving to implementation. The TORs will indicate the frequency of engagement required between FCDO, the supplier and GoJ. A clear table of deliverables will also be included in the TORs, including periodic reporting and KPIs to manage performance. All technical activities via the procurement route will follow a phased approach, starting with an inception phase of up to three months, an implementation phase, and finally closure and exit.
- JFA: Management and governance arrangements will be reflected in both the MoU between the UK and GoJ, as well as in the JFA itself. The PMU at MoWI will oversee project progress and compliance. The responsibilities of the PMU include invoice verification, dispute investigation, and approving any change order/amendments to the contract with the supplier. Through the JFA, MoWI will submit an Annual Work Plan covering January to December, 30 days before the year-end, and quarterly performance and financial monitoring reports from MoWI to donors will be submitted within 30 days of each calendar quarter's end.
Regular consultations among JFA signatories will ensure effective engagement and implementation through a Steering Committee (SC), which will serve as the decision-making body of the TA provided to the AAWDCP. The SC will provide overall management direction and oversight of the JFA through periodic meetings and technical discussions, and strategic/policy advisory. The SC will be chaired by a senior representative from MoWI (Minister or Secretary General) in addition to the PMU Director, and is comprised of the following decision-making members:
  - Representative(s) of the GoJ, including MoWI and MoPIC.
  - Representative(s) of the PMU.
  - Representative(s) of each of the contributing donors/signatories, including the FCDO WADI SRO.
AGA with an (I)NGO or MoU with Multilateral: management and governance arrangements will be reflected in the AGA with the (I)NGO and MoU with the selected Multilateral. The SRO and PRO will attend at least a quarterly meeting with the (I)NGO/Multilateral to monitor progress, outline priorities for the upcoming period, review TA progress, and discuss results. The (I)NGO/Multilateral will produce Quarterly Progress Reports which will cover updates, results achieved during the reporting period, risks and lessons learned, potential pipeline updates, in addition to detailed financial information/reporting.

Figure 6
# decision mAKING
To ensure flexibility and responsiveness, decisions for the Technical Assistance type will be made through a consensus-based approach, with all key stakeholders, including the Government of Jordan and donors contributing to discussions on how the technical assistance is deployed. This approach allows for continuous adaptation of the FCDO technical assistance to respond to both immediate technical needs and longer-term policy priorities. By maintaining this flexibility, the assistance can not only address project-specific challenges, such as risk management, but also engage in providing recommendations and influence on the broader policy work, such as water sector reforms or regulatory improvements. This structure ensures that the assistance remains flexible, allowing the FCDO and other donors to shape their support in a way that maximizes impact across both technical and policy domains.
# Results monitoring, measurement and evaluation
Monitoring, Evaluation and Learning: MEL will be central to the achievement of WADI programme objectives. The WADI programme team will work on developing a clear MEL strategy and a framework, with the Theory of Change (ToC) as the cornerstone to set the key indicators for the programme and what success looks like, to allow for continuous measurement.
The WADI logframe will be prepared setting out the impact, outcomes, and output statements. International Climate Finance (ICF) KPIs will be incorporated into WADI logframe to monitor the impact of FCDO’s climate financing and assist with FCDO’s annual ICF results collection and publication. The WADI programme team will ensure that progress reports through the different delivery routes is aligned to the logframe indicators, and that financial reports are provided in a format agreed by FCDO.
The WADI programme team will work with GoJ and the FCDO delivery partners on KPIs (such as quality of deliverables, timeliness, management of risks, cost control) which will also be tracked as part of FCDO’s Annual Review (AR). The AR process will also be the key trigger point for formally assessing progress against the ToC and logframe. The AR will provide recommendations for follow-up action and lessons learned. A break clause will be inserted into the contract/AGA/MoU/ (depending on the selected delivery route). If progress at the AR is found to be unsatisfactory based on the agreed KPIs and logframe, then the programme can either be improved through a Programme Improvement Plan (PIP) or can be terminated.
# Partnership Principles
The FCDO Partnership Principles underpin the aid relationship between the UK and a host country. The four principles are:

1. A commitment to reducing poverty and achieving the Sustainable Development Goals.
2. A commitment to respecting human rights and other international obligations.
3. A commitment to strengthening financial management and accountability and reducing the risk of funds being misused through weak administration or corruption.
4. A commitment to strengthening domestic accountability.
This programme will work in close collaboration with the GoJ (MoWI and MoPIC) as the main beneficiary of the water related technical assistance. FCDO will monitor adherence to our Partnership Principles by reviewing the GoJ’s commitment via the ASP in 2024, a full FRA in 2025, and as part of each WADI Annual Review. We will also work closely with other donors and other stakeholders (e.g. IFIs and the EU) if circumstances change, including the utilisation the EU’s Public Expenditure and Financial Accountability (PEFA) assessment tool, which is designed to identify the strengths and weaknesses of Public Financial Management (PFM) systems at national or subnational level in Jordan.
# Risk Management
The overall risk rating for the WADI programme is assessed to be as ‘moderate’, in line with UK’s risk appetite for Jordan. The WADI programme team, including the PRO and Programme Manager, will manage the ongoing risks to delivery by developing a risk register and updating it on a quarterly basis at minimum.
Some of the key risks to successful delivery of the programme and mitigation measures are summarised in Table 4 below. Risk analysis and the risk register will be refined further during the mobilisation and inception phases.

Table Risk Management
Risk Description	Residual (Post-Mitigation) Rating	Comments
Policy and Programme Delivery
GoJ does not finalise the (currently ongoing) negotiations and procurement around the AAWDCP, resulting in the project being restructured and delayed. This will in turn delay any WADI programme TA targeted at the AAWDCP (though broader water-related TA can commence).	Major	This remains a possible/highly likely risk with major impact. There are limited options for the FCDO for mitigation, as the commercial negotiations are purely between GoJ and the sole bidder, and beyond the remit of UK influence. However, the preferred option mitigates against this risk by broadening the scope to wider TA to inform supply and demand side water management interventions.
Limited GoJ capacity to absorb additional TA for the AAWDCP, as USAID has allocated a $50M TA facility and Germany is embedding human resourcing at MoWI and PMU.	Major	This risk can be managed with regular conversations with GoJ, USAID, Germany and other donors providing TA to the AAWDCP. FCDO has used such consultations to ensure from the outset that the proposed TA in the WADI Appraisal Case is unique and able to add value.
GoJ priorities suddenly change, resulting in a fundamental change of direction regarding the utilisation of UK TA, whether for the AAWDCP or broader water-related areas.	Moderate	FCDO will ensure flexibility in our TA, to enable it to respond to changing priorities.
TA contractor/supplier(s) fails to meet the expectations of GoJ.	Moderate	Ensuring proper and clear ToRs, agreed between FCDO and GoJ for the contractor/supplier(s). The proposed governance structures and contract management will address poor performance
Strategy & Context Risk
Global and regional conflicts affect cost and pricing of materials dramatically, resulting in delays to the implementation of the AAWDCP, and WADI TA elements related to this.	Moderate	The risk represents the high uncertainty of external factors. The Russia-Ukraine war, as well as the Israel-Gaza war resulted in significant costs increases since 2022 during the design and procurement phases of the AAWDCP. One of the key proposed areas of WADI TA is a Risk Management Facility intended to identify, quantify the cost of risks, and mitigate them.
Financial and Fiduciary Risk
Misuse of TA funding available through fraud and corruption.	Minor	This risk will be controlled through the FCDO procurement routes and contract clauses for the procurement delivery route. For other delivery routes, including JFA, Multilaterals and/or (I)NGOs, FCDO will rely on Fiduciary Risk Assessments on PFM for JFA, and Enhanced Due Diligence Assessments for (I)NGOs and Multilaterals
Safeguarding Risk
Risk of exploitation or abuse of beneficiaries and stakeholders through the WADI implementing and downstream delivery partners.	Minor	FCDO contracts cover safeguarding and the Enhanced Due Diligence Assessment that has a particular pillar focusing on safeguarding. The nature of the TA that will be provided will likely have minimal interactions with beneficiaries or the public and is limited to the core team of experts and consultants dealing with the GoJ. The programme team will continuously assess the TA provided and whether interaction with beneficiaries increase any safeguarding risks. The team will revisit the mitigation strategy accordingly.
Reputational Risk
Poor performance of TA reflects badly on the UK as a donor.	Minor	The proposed governance structures and contract management will address poor performance that may cause reputational risk.

Financial Case
The WADI programme is planned as a five-year programme that will run from FY24/25 – FY29/30.  This business case is requesting approval for funding of up to £5 million.
We assume that the Needs Assessment exercise, as outlined in the Commercial Case, will start as soon as the business case is approved. Based on the Needs Assessment, the expenditure profile will be further refined during the design phase when a detailed programme budget will be developed.

Affordability will be consistently reviewed with spend in year one being dependent on 24/25 budget allocation decisions and thereafter future Spending Review decisions. Break clauses and go/no go decisions will be inserted into agreements. The programme will develop in an incremental way, scaling up over time and flexing and adapting depending on the circumstances including need and the financial availability of ODA.

[VAT will be chargeable on the entire WADI programme – as appropriate]

How will it be funded: capital/programme/admin?
The ODA spend (100% of this business case) will come from the FCDO Jordan core budget as per settlement - this funding will mostly come from FCDO’s RDEL budget within MENA Directorate. WADI Programme may use CDEL for R&D, provided that specific Research under WADI as part of the TA meets the eligibility criteria, and it is approved by Research and Evidence Directorate (RED) who hold quality control.

How will funds be paid out?
Procurement and AGA/MOU delivery routes: FCDO payment for the service of operating the WADI programme will only be made against invoices submitted to FCDO quarterly/monthly and in arrears.  Payments will be directly credited through the UK Banker Automated Clearing Systems (BACS), thus requiring that invoices contain details of the bank account to be credited.

JFA: FCDO payment contributions to the JFA will be made based on the Annual Work Plan which will be submitted by GoJ to all contributing donors at the start of the calendar year. All payments to the JFA will follow UK requirements, including avoiding payments in advance of need. These requirements will be detailed to ensure full alignment and compliance with UK guidance and will be added to both the bilateral agreement with the government of Jordan as well as the JFA itself, if the JFA delivery route is considered. More details on financial risks and governance are included in the commercial and management cases. For the JFA, the WADI programme team will ensure proper identification of primary funding sources, including contributions from other donors, government allocations, and potential co-financing from international organizations.

FCDO will only make payments in Sterling (GBP) against invoices once it is satisfied that the delivery against duties, obligations and responsibilities undertaken in any period are consistent with the value of the invoice.  FCDO will reserve the right not to pay any items invoiced for more than 90 days from the first day the payment becomes due.

Cost profiling
The expenditure for design thus far following ministerial concept note approval and the forecasted expenditure envisaged for the current financial year (2024/25) and outer years (2025/26 – 2028/28) are:

Table 9
Year	2023-2024	2024-2025	2025-2026	2026-2027	2027-2028	2028-2029
Forecast- up to	£67,000 / Utilised to support the design of the strategic case.	£1,000,000	£2,000,000	£1,000,000	£933,000	0

Fiduciary Risk Assessment and Due Diligence
The Commercial Case touched upon Due Diligence Assessments on the suppliers selected for the country/regional programmes will be carried out by FCDO’s Procurement and Commercial Department as part of the procurement delivery route as well as the Fiduciary Risk Assessment and Annual Statements of Progress when considering the JFA delivery route. Additionally, for (I)NGOs and Multilaterals, the WADI programme team will carry out Enhanced Due Diligence Assessments as required, with the support of the Due Diligence hub at the centre.

The allocation of funds in WADI as outlined in the Commercial Case will be a mixture of delivery models. Each delivery route will be required to supply a delivery chain map so that funds can be traced to the beneficiaries and risks tracked.

Financial reporting, and accounting for funds
The reporting requirements for the suppliers, government and NGOs/multilaterals will be set out in the contract agreed, JFA and bilaterial agreement with the government as well as in the AGA and MoU. This will specify the need for compliance with FCDO ProF Rules and guidance and set out reporting requirements. The reporting requirements will include quarterly or bi-annual financial monitoring reports detailing expenditures, budget variances, and financial performance. Annual financial statements and audits will also provide a comprehensive overview of financial status and compliance. Continuous improvement based on feedback from financial reports and audits, ensuring efficient use of funds and value for money.

Forward looking budgets, delivery plans, and milestones will be agreed quarterly or bi-annually and will be produced alongside retrospective analysis of performance in the half year. These will be supplemented by quarterly and annual reports.

The arrangements under this Programme will be disbursed in accordance with central FCDO guidance / ProF Rules. Centrally negotiated contracts will be reinforced by ToRs, workplans and budgets.