## Annual Review

Title: Water Adaptation and Desalination Infrastructure
Programme Value £ (full life): 5,000,000		Review date: 26/11//2025
Programme Code: [AMP ID#] / 400043	AMP start date: 08/12/2024	AMP end date: 31/03/2030

Summary of Programme Performance
Year	2024/25	2025/26	2026/27	2027/28	2028/29	2029/30
Overall Output Score	B
Risk Rating	High

DevTracker Link to Business Case:	Link
DevTracker Link to results framework:	Link

List of Acronyms
AAWDCP / AR / ASEZA / BEA / BOT / CN&E / CoE / DDA / EU / FCDO / GCIEP / GEDSI / GEM / GIZ / GoJ / ICF / KPI / MoEnv / MoPIC / MWI / NCP / NCPMU / OGP / PMU / PWC / QA / RCF / RM / RMF / SRO / TA / ToC / USG / VfM / WADI	Aqaba Amman Water Desalination and Conveyancing Project / Annual Review / Aqaba Special Economic Zone Authority / British Embassy Amman / Build-Operate-Transfer / Climate, Nature and Environment / Centres of Expertise / Due Diligence Assessment / European Union / Foreign Commonwealth and Development Office / Green Cities, Infrastructure and Energy Programme / Gender Equality, Disability and Social Inclusion / Gender Equality Marker / German Corporation for International Cooperation (Deutsche Gesellschaft für Internationale Zusammenarbeit) / Government of Jordan / International Climate Finance / Key Performance Indicator / Ministry of Environment / Ministry of Planning and International Cooperation / Ministry of Water and Irrigation / National Conveyor Project / National Conveyance Project Management Unit / Oxford Global Projects / Project Management Unit / Price Waterhouse Cooper / Quality Assurance / Reference Class Forecasting tool / Results Monitoring / Risk Management Facility / Senior Responsible Owner / Technical Assistance / Theory of Change / United States Government / Value for Money / Water Adaptation and Desalination Infrastructure

A. SUMMARY AND OVERVIEW

Description of programme

Jordan is one of the most water scarce countries in the world. Jordanians have less than 100m³ of water per person, compared to the UN water scarcity threshold of 500m³ per person.[1] Without large scale water supply, more efficient usage and improved management, Jordan will be unable to provide its population with the recommended minimum threshold of water per person, climate risks will be exacerbated, and economic growth will remain stagnant or decline, adding to Jordan’s debt burden and potentially leading to domestic instability.
[1] This is the most extreme definition of water scarcity described as “absolute scarcity” by the UN.

The Water Adaptation and Desalination Infrastructure (WADI) Business Case for £5 million over five years (FY24/25 to FY29/30),[2] aims to provide flexible, demand-driven Technical Assistance (TA) to support the Government of Jordan (GoJ):
[2] Note the approved £20 million Concept Note for the WADI programme sets out FCDO’s intention to provide both a flexible TA (around £5 million) and grant financing (£15 million) for the NCP.

- Enhance water supply at scale via the ~$5.6billion Aqaba Amman Water Desalination and Conveyance Project (AAWDCP), also known as the National Conveyor Project (NCP), Jordan’s largest water scheme in history.
- Manage water demand at scale to improve water efficiency in the agricultural sector, which is responsible for over half of the country’s usage.
- Reduce supply and demand inefficiencies and encourage innovation, through targeted small-scale interventions to strengthen water management and governance.

Under the WADI programme, FCDO has contracted flexible TA in the form of a dedicated Risk Management Facility (RMF) via the Centre of Expertise (CoE) Green Cities Infrastructure and Energy Programme (GCIEP). The purpose of the RMF is to identify, advise on, and propose actions to mitigate inherent and residual risks over the NCP lifecycle, in collaboration with the investor and other key stakeholders. The RMF operates within the Ministry of Water and Irrigation (MWI) Project Management Unit (PMU), known as the National Conveyor Project Management Unit (NCPMU).

Over the review period, the WADI programme experienced two significant challenges in the operational context that impacted delivery timelines and strategic alignment. First, the United States Government (USG) foreign development assistance – Jordan’s largest donor in the water sector - was paused for ninety days from January 2025. This was followed by the closure of United States Agency for International Development (USAID) in July 2025, which disrupted technical advisory support to the GoJ on the design and construction of the NCP, including on risk management. Second, reductions in the UK’s Official Development Assistance (ODA) announced in February 2025, resulted in a five-month procurement delay of the RMF Supplier. These developments created uncertainty around the continuation of USG support for the NCP, which in turn affected the scope and strategic alignment of WADI’s complementary RMF support and further compounded procurement delays.

Summary supporting narrative for the overall score in this review

In its first year, the WADI programme focused on RMF mobilisation as the core output. To respond to a challenging operational context, the team adopted a flexible and adaptive approach. This involved engaging regularly with the GoJ Ministry of Planning and International Cooperation (MoPIC), the NCPMU, and external stakeholders (including the USG) to define the RMF scope, ensure strategic alignment and enable proactive scenario planning. To mitigate procurement delays, PwC was secured as the RMF Supplier via the CoE GCIEP programme, leveraging their expertise. RMF mobilisation phase is scheduled for completion by 31 March 2026. However, due to the number of challenges experienced over the review period, overall progress against the set milestones has been slower than anticipated.

On this basis, performance against this output is assessed as ‘B - moderately did not meet expectations.’ Outputs scoring is summarised in Table 1.

Table 1 Output Scoring
Description	Weighting	Score	Performance
Output 1 / Risk Management Facility incorporated onto NCP lifecycle -mobilisation phase concluded by 31 March 2026, with all inception phase milestones achieved, establishing operational readiness for implementation phase. FCDO Jordan initiated strategic partnerships and coordination mechanisms with key water sector stakeholders.	100%	B	RMF incorporated onto NCP lifecycle -mobilisation phase scheduled for completion by 31 March 2026, with 30% of Inception Phase milestones achieved to date. Completion of the RMF Inception Phase ToR met expectations, and the number of coordination meetings attended exceeded expectations. However, other milestones including establishing the core team, developing the final risk advisory report and risk management tools for the RMF did not meet expectations, and are in progress.

Major lessons and recommendations for the year ahead

Key lessons

Procurement. Engage Commercial Advisors early to select the right procurement route, especially for specialist areas. Early involvement better aligns technical needs with the procurement strategy and can reduce procurement timelines.

Flexible and adaptive programming. A flexible and adaptive management approach to developing the scope of works was necessary for stakeholder buy-in, but was time intensive and placed a significant strain on limited staff resources.

Stakeholder coordination. The RMF’s success will depend on sustained GoJ buy-in, including establishing trusted relationships with wider stakeholders to prevent duplication, demonstrate value addition and respond to GoJ needs.

Key recommendations

WADI grant funding. Disburse a minimum contribution of approximately £5 million (CDEL) within this financial year. This follows approval of the WADI Business Case addendum in November 2025, to incorporate an additional £15 million grant funding and extend the programme duration to align with the planned NCP construction phase. [FCDO programme team, by March 2026].

Staff resourcing. Allocate sufficient staff resources to engage closely with the RMF Supplier. This will enable meaningful influence and value addition of the RMF for the GoJ and wider stakeholders. [FCDO programme team, by April 2026].

Stakeholder coordination. Establish a clear coordination mechanism with other technical advisors during the Inception Phase. This will include agreed ways of working, regular meeting schedules, defined reporting lines and integrated risk management processes. This will prevent duplication and conflicting guidance. [PwC team, by April 2026].

Role Consolidation and Integration. Streamline the RMF team structure to ensure greater efficiency, coherence in roles and responsibilities that respond to the needs, and clear reporting mechanisms between London and Jordan operations. This will enable effective use of multidisciplinary expertise. [PwC team, by April 2026].

Transition from Inception to Implementation Phase. Prepare a structured handover plan to transition from Inception to Implementation, including a contingency if GCIEP CoE is not extended beyond March 2026. This will ensure sustainability and support continuous learning and improvement from programme activities. [PwC team, by April 2026].

Results Framework. Revise WADI ToC and logframe through a consultative approach with key stakeholders. This will include the additional grant funding and ensure proportionality and coherence with the current programme structure. [FCDO programme team, by May 2026].

Gender Equality and Social Inclusion. Develop an initial GEDSI risk assessment for the NCP with the NCPMU and wider stakeholders during the Inception Phase. This will include Gender-Specific Indicators for the RMF to be scored as GEM 1 not GEM 0 (gender blind). [PwC team, by April 2026].

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The WADI Theory of Change (ToC) sets out the programme’s overall intended impact for the ‘people of Jordan to have better access to water to enable a decent standard of living, the economy is no longer constrained by water shortages promoting climate sensitive growth and the agricultural sector becomes more competitive, for overall support to stability.’ The ToC outlines that the intended outputs and outcomes will be achieved through two inputs: 1) Establishment of the RMF, and 2) Production of high-quality research, with small-scale pilot interventions to inform GoJ policies and decision making.

Problem statement: Jordan faces existential water scarcity. Without large scale supply, more efficient usage and improved management, Jordan will be unable to provide its population with a decent standard of living, climate risks will be exacerbated, and economic growth will remain stagnant (or decline), unsustainably adding to Jordan’s debt burden and potential leading to instability.

High level Context		High debt/GDP / High unemployment		Chronic and worsening water scarcity / Rapid population growth
		High risk from undertaking a megaproject		Climate change and rising temperatures

Specific Context		Lack of dedicated support around risk of design and build of megaprojects		Inefficient water usage, management and governance

		Lack of context specific evidence on what works in promoting efficiencies in water supply and demand / (both at large and smaller scale)

Inputs		Dedicated Risk Management Facility embedded alongside the AAWDCP Project Management Unit		Research specialists identify critical gaps. High-quality TA drawn down to improve efficiencies in the agricultural sector and inform smaller-scale interventions to strengthen water management

Outputs		Risk management incorporated into all stages of the AAWDCP lifecycle. / Robust risk management plan informs construction phase.		High quality research and analysis products inform GoJ policies and decision making. / Smaller scale pilot interventions demonstrate more efficient supply and demand practices.

Complementary Outputs		More effective GoJ risk management capacity and expertise around megaprojects.		Improved efficiency and water usage in the agricultural sector for more equitable distribution of water resources. / Improved water management and governance (particularly for vulnerable communities).

Outcome		AAWDCP lifecycle risks are attenuated: costs contained, impact on GoJ debt and fiscal liabilities mitigated. / Water savings are realised. Reforms and interventions in agriculture drive efficiencies and increase crop cultivation. Stronger governance, more sustainable and efficient practices in managing supply and demand.

Impact		People of Jordan have better access to water to enable a decent standard of living, the economy is no longer constrained by water shortages promoting climate sensitive growth, agricultural sector becomes more competitive. Overall support to stability

During the review period, the programme team prioritised operationalising the RMF as the core output contributing to the outcomes, given its direct alignment with GoJ priorities. As a direct trade-off, inputs aimed at producing high-quality research and undertaking small-scale pilot interventions were paused. Where feasible, research on water and agriculture will be leveraged through the existing International Growth Centre (IGC) programme in Jordan. The WADI programme ToC will be updated to reflect that this research is no longer a direct input and will not generate corresponding outputs or outcomes.

The approved £20 million Concept Note for WADI envisioned a combination of inputs comprising of flexible TA (£5 million) and grant funding (£15 million) for the NCP, as a substantive contribution to the ToC outputs and outcomes. However, the grant funding input was not included in the Business Case due to limited information regarding the status of the NCP and FCDO ODA budget allocations. Since then, the GoJ has made significant progress on the NCP – i.e. funding from development partners and multilaterals has been secured, early works contracts were signed in April 2025, detailed design is near completion and the financial close deadline with the investor is set for April 2026. On this basis, adequate information is now available to determine disbursement options for the grant funding. A Business Case addendum was approved in November 2025 to incorporate the additional £15 million grant funding as a key input. The ToC outputs and outcomes will be updated to reflect this substantive contribution towards achieving the programmes overall intended impact, which remains unchanged.

The underlying ToC assumptions remain valid. For the RMF and grant funding contribution to achieve the intended outcomes and impact, assumptions relating to regional stability and sustained GoJ momentum to reach financial close on schedule remain critical. Two new RMF assumptions include: 1) establishing strong coordination and trusted relationships with the existing GoJ counterparts, technical advisors, other line Ministries and key stakeholders’ (donor and investors) and 2) timely access to relevant data. These new assumptions will be added to the ToC and logframe.

WADI programme exemplifies FCDO’s modernised approach through its strategic pivot across four key transformations:

1. From Donor to Investor

WADI is transitioning from traditional aid to catalytic investment. A Business Case addendum has been approved to increase financial support by providing a ~£5 million grant (CDEL to the GoJ) this financial year (ending March 2026), complementing the existing £5 million TA for the RMF. This grant, alongside with private investment, will help increase the government’s borrowing concession and support the NCP to reach financial close by April 2026. This approach positions the UK as a strategic partner driving climate-resilient growth and fiscal sustainability, directly responding to GoJ priorities.

2. From Service Delivery to System Support

Rather than delivering water services directly, the WADI programme will strengthen the GoJ institutional systems to manage megaproject risks. Through the RMF, embedded within the MWI, the programme will equip MWI systems with advanced UK technology and robust risk management tools (including AI), to capture, forecast and manage risks on complex infrastructure projects, ensuring climate resilience and sustainability beyond external support.

3. From Grants to Expertise

WADI leverages global expertise through PwC and the CoE, providing specialist advisors to support on risk governance, cost containment, environmental and social safeguards and compliance. This TA model prioritises knowledge transfer, sharing UK expertise and capacity building, aiming to equip multiple GoJ line Ministries with the skills to manage cross-government risks on complex infrastructure projects independently.

4. From International Intervention to Local Leadership

The programme fosters local ownership by embedding national RMF experts within the NCPMU and aligning with GoJ priorities. Inclusive governance and GEDSI integration will ensure that solutions are context-driven and sustainable. WADI complements existing donor efforts rather than duplicating them, reinforcing GoJ leadership in addressing water scarcity.

In its first year, WADI has laid the foundation for a modernised UK development approach—mobilising expertise, catalysing investment, and embedding systemic resilience. By aligning with the Foreign Secretary’s vision, WADI is enabling a transformative shift towards self-reliance, economic stability, and climate resilience.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The RMF contributes to Output 1, which aims to ‘integrate risk management into all stages of the NCP lifecycle’ and ‘strengthen the GoJ capacity to manage risks associated with megaprojects.’ The expected RMF Outcome statement is that ‘NCP lifecycle risks are offset, costs contained and the impact on GoJ debt and fiscal liabilities is mitigated.’ However, supporting Outcome statements referring to ‘water savings, reforms and interventions in agriculture drive efficiencies and increase crop cultivation, stronger governance and more sustainable and efficient practices in managing supply and demand;’ do not relate to the RMF. Therefore, while the RMF is on track to contribute towards its corresponding outcome statement, this output alone cannot achieve the broader intended outcomes and impact of the WADI programme. The ToC will be revised for more proportionality and coherence with the current programme structure. Revisions will reflect the paused research inputs, incorporate the additional £15 million grant funding and update relevant assumptions to align with the current programme context.

Despite the challenging operational context, the RMF Inception Phase is now fully underway. Following confirmation that USG technical advisory support on the NCP will be sustained throughout the construction phase, the RMF is working with key stakeholders to identify the gaps and ensure strategic alignment. The RMF will play an important role in supporting the NCPMU assess and proactively manage cross-government risks to deliver the NCP, including responding to demand for additional expertise on specific thematic areas (e.g. environmental and social risks).

In the year ahead, effective coordination with GoJ counterparts and technical advisors will be essential to deliver intended outcomes. This coordination is being established early during the Inception Phase (November 2025 – March 2026), with clearly defined roles, responsibilities and scope for the RMF in relation to other GoJ technical advisors. During the Implementation Phase (commencing April 2026), the RMF will fully operationalise its TA through embedded expertise within the NCPMU, working alongside other technical advisors to apply risk management methodologies, support mitigation efforts and strengthen institutional capacity for megaprojects. Regular cross-government engagement and the use of integrated risk management tools will be critical to promoting best practices, transparency, consistency, and lessons learning.

Continuity of the WADI programme from the Inception Phase to Implementation Phase is subject to availability of multi-year funding from April 2026. Subject to approval, it is expected that a proportion of the grant funding (~£5 million) will be disbursed before the end of this financial year to contribute to filling the financing gap and reach financial close by April 2026. In addition, the duration of the WADI Business Case has been extended by 21 months - from March 2029 to end 31st December 2030 - to align implementation of the RMF and grant funding with the planned NCP construction timeline. This extension was essential to allow for a meaningful assessment of the programme’s outcomes and overall impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The NCP is a high-risk mega infrastructure project. Even with the standard risk mitigation measures in place, only 0.05% of megaprojects meet the original design brief and deliver within the agreed cost and timeframe. There is a strong Value for Money (VfM) case for assisting the GoJ through the provision of a dedicated RMF. The RMF takes a dynamic approach to look at residual risks (the risk post mitigation by the implementer and the otherwise unidentified risk) that need to be identified and mitigated.

The WADI programme is in its first year of implementation, with the RMF TA at the start of the Inception Phase. While it is too early for the RMF to demonstrate progress towards outcomes, the GoJ has expressed clear demand for this specialist expertise, with buy-in from other key stakeholders. The WADI programme should continue based on its own merits as the RMF represents a modest, yet highly targeted TA offer complemented by grant funding within the broader context of NCP, directly responding to the GoJ’s top priority. By leveraging UK expertise, the RMF has the potential to deliver multiplier effects across the NCP lifecycle, particularly in enhancing risk management, enabling better project governance and fiscal sustainability. The RMF also aligns with the British Embassy Amman’s Country Business Plan 25/26 Goal 2: Resilience - “increase economic stability and economic opportunities”, exemplifies FCDO’s modernised approach and is a substantive contribution to the embassy International Climate Finance (ICF) targets.

## C. DETAILED OUTPUT SCORING

Output Title	Risk Management Facility incorporated onto NCP lifecycle - mobilisation phase
Output number:		1	Output Score:	B
Impact weighting (%):		100%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 RMF Inception Phase TOR designed by Supplier and formally approved by FCDO programme team. and RMF core team mobilised.	Inception Phase ToR created and approved by FCDO programme team (31 October 2025). / RMF core team mobilised (31 March 2026).	Met Expectations. ToR reviewed and accepted by NCPMU and approved by FCDO on 11 November 2025. / Not Met Expectations. Core team mobilisation to be completed by December 2025.
1.2 RMF inception phase deliverables completed	Coordination structure and mechanisms for NCP risk management developed and endorsed by the NCPMU and relevant NCP stakeholders. / Final risk advisory report, including assessment of inherent and residual risks, mitigation strategies, and governance recommendations submitted to NCPMU and FCDO. / Risk management tools for the RMF developed and agreed with NCPMU and FCDO.	Met Expectations. Outline mechanisms for the RMF discussed and agreed with the NCPMU during Design Phase. To be developed further during the Inception Phase. / Not Met Expectations - Will be completed by 31 March 2026. / Not Met Expectations. Will be completed by 31 March 2026.
1.3 Number of coordination meetings, sector events, and stakeholder engagements convened or attended by FCDO Jordan with key water sector stakeholders.	At least 10 coordination meetings/events held or attended with participation from key stakeholders.	Exceeding Expectations. Monthly meetings (10) attended with Water Sector Donor Group and readouts produced. In addition (2) PwC field visits engaging key NCP stakeholders in risk management.

Output 1 is assessed as moderately not meeting expectations. Following a five-month procurement delay and extensive engagement with Commercial Advisors on possible procurement routes, the FCDO programme team reached an agreement for the WADI programme to buy-in to the GCIEP CoE. This buy-in agreement mitigated further delays and secured access to specialist expertise via PwC London working in collaboration with the Jordan Office, to implement the RMF. Given the challenges in the operating context and large number of stakeholders involved in the NCP, PwC adopted a flexible and adaptive two-stage mobilisation approach to ensure coherence and strategic alignment of the RMF. This commenced with an initial Design Phase 1 (5 September – 31 October 2025) before commencing the formal Inception Phase in November 2025.

During the review period, the PwC London team conducted two field visits to Jordan – the first during the Design Phase (6 - 10 October 2025) and the second during the early stages of the Inception Phase (16 – 20 November 2025). These visits facilitated engagement with key stakeholders to support the definition of the Inception Phase scope of works. While adopting a flexible and adaptive management approach proved necessary in an evolving context, it required structured and regular engagement with a wide range of stakeholders which was time-intensive and placed significant pressure on staff resources.

Output Indicator 1.1 RMF Inception Phase TOR designed and formally approved by FCDO programme team. RMF core team mobilised. The Inception Phase ToR was developed between 18 September - 10 November 2025, and was subsequently reviewed and accepted by NCPMU, with final FCDO approval on 11 November 2025. With the approved ToR, the RMF core team is partially mobilised and will be fully mobilised by December 2025. The Inception Phase is scheduled to end on 31 March 2026 with all Inception Phase deliverables completed, to ensure operational readiness for the Implementation Phase.

Output Indicator 1.2 RMF inception phase deliverables completed. At the time of writing this Annual Review, the programme is in early stages of the Inception Phase. During the Design Phase, progress was made in developing an outline coordination structure and mechanism for the RMF, which was further refined at the onset of the Inception Phase in consultation with NCPMU. However, other key Inception Phase deliverables — such as the provision and documentation of risk advisory support, the development of a cost management framework for residual risks, and the development of risk management tools — have not yet commenced. These activities will commence in the latter half of the Inception Phase, to be completed by March 2026. Therefore, it is currently classified as ‘not met,’ despite progress being proportionate to the time elapsed since commencement of the Inception Phase.

A structured plan for risk management processes including gap filling, alignment with the key advisors including CDM Smith, sharing contact details for different stakeholders and creating a dashboard will be agreed during the Inception Phase. The work will also include developing tools, and training materials to ensure a smooth transition into the Implementation Phase and long-term sustainability beyond the programme’s activities. This will be complemented by targeted capacity development for both NCPMU and MWI staff throughout the NCP lifecycle. This approach is designed to embed risk management practices within GoJ systems and ensure long-term ownership and impact.

Output Indicator 1.3 Number of coordination meetings and stakeholder engagements. During the two field visits (Design Phase and Inception Phase), PwC engaged with the FCDO programme team and a wide range of key stakeholders, including the NCPMU, MoPIC, Ministry of Environment (MoE), United States Government (USG), CDM Smith, Water Authority Amman (WAJ), Aqaba Special Economic Zone Authority (ASEZA), German Corporation for International Cooperation (GIZ) and European Union (EU). This stakeholder meetings helped the PwC team clarify the nature of the existing risk advisory support available to the NCPMU, understand the gaps in risk management and provisional institutional capacity needs. This enabled PwC to adapt the Inception Phase ToR and define the evolving boundaries of the RMF scope of works, to be endorsed by wider NCP stakeholders during the Inception Phase. Due to the number of stakeholders engaging on risk management for the NCP, during the Inception Phase, the PwC team will need to establish a coordination mechanism with the NCPMU that clearly defines the RMF scope of works in relation to other technical advisors. This will include agreed ways of working, regular inter-government meeting schedules, defined reporting lines and integration of risk management tools and processes.

In parallel, the FCDO programme team has initiated strategic partnerships with other donors in the water sector to enhance sectoral alignment. Over the review period, WADI Senior Responsible Owner (SRO) and the Technical Advisor have attended over 10 Water Sector Donor Group and NCP coordination meetings (with participation from a range of donors and lenders). Donor Group meetings provided helpful information on partners interventions in the water sector, including the NCP. NCP coordination meetings provided important GoJ updates on the NCP financing structure, commercial contracting and timelines. These meetings are a critical platform for engagement on the NCP, enabling the FCDO programme team to remain well informed and actively engaged. However, participating in all the numerous meetings has been time-intensive for the FCDO programme team, with several competing priorities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output 1 milestones will be updated in the logframe to include the RMF Implementation Phase outputs, scheduled to commence from April 2026.
Progress on recommendations from the previous AR (if completed).

Not Applicable. This is the first annual review for the programme.

Lessons learned this year and recommendations for the year ahead.

Lessons Learned

Procurement. Engage Commercial Advisors early to identify the most appropriate procurement route, especially in specialist areas beyond core expertise. This proactive approach helped align the RMF technical and capability needs with the procurement strategy, reducing risks and procurement timelines.

Flexible and adaptive programming. Adopting a flexible and adaptive approach when defining the scope of works in in a challenging operating context was necessary for stakeholder buy-in, but was time intensive and placed a significant strain on limited staff resources.

Stakeholder coordination. The RMF’s success will depend on sustained GoJ buy-in, including establishing trusted relationships with wider stakeholders to prevent duplication, demonstrate value addition and respond to GoJ needs.

Recommendations

Staff resourcing. Allocate sufficient staff resources to engage closely with the RMF Supplier. This will enable meaningful influence and value addition of the RMF for the GoJ and wider stakeholders. [FCDO programme team, by April 2026].

Stakeholder coordination. Establish a clear coordination mechanism with other technical advisors during the Inception Phase. This will include agreed ways of working, regular meeting schedules, defined reporting lines and integrated risk management processes. This will prevent duplication and conflicting guidance. [PwC team, by April 2026].

Role Consolidation and Integration. Streamline the RMF team structure to ensure greater efficiency, coherence in roles and responsibilities that respond to the needs, and clear reporting mechanisms between London and Jordan operations. This will enable effective use of multidisciplinary expertise. [PwC team, by April 2026].

Transition from Inception to Implementation Phase. Prepare a structured handover plan to transition from Inception to Implementation, including a contingency if GCIEP CoE is not extended beyond March 2026. This will ensure sustainability and support continuous learning and improvement of programme activities. [PwC team, by April 2026].

Gender Equality and Social Inclusion. Develop an initial GEDSI risk assessment for the NCP with the NCPMU and wider stakeholders during the Inception Phase. This will include Gender-Specific Indicators (e.g. proportion of women engaged in NCPMU risk management training) for the RMF to be scored as GEM 1 not GEM 0 (gender blind). [PwC team, by April 2026].
## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost drivers are the average consultant fees and travel and subsistence costs. Such costs are set centrally by the GCIEP.

VfM performance compared to the original VfM proposition in the business case

As the programme is in early stages of the Inception Phase, our value for money focus is on key cost drivers and their impacts on economy, efficiency and equity. We will continue to develop and apply milestones, learning cycles, and monitoring tools effectively to measure RMF value for money and progress towards achieving outcomes and impact.

Economy: Economy is how budgets are transferred into activities. The average daily cost of an international consultant in the GCEIP COE is set at £736 per day (except for the Oxford Global Projects sub-contractor rates which are slightly higher at £828 given the specialist service), while the national (Jordan) rate is set at £573 per day. All rates are set in accordance with the CoE rates. Rates are subject to periodic reviews and will be monitored monthly and billed on time and expenses-based actuals.

While the CoE rates are more costly nationally compared to the alternative FCDO EACDS Framework by 29.5[3]%, it remains the only viable contracting option given the limitations of EACDS for interventions exceeding £1 million and nature of specialist skills required. Moreover, the multi-year nature of this intervention cannot be accommodated within EACDS procurement mechanisms. It is also reasonable to expect higher setup costs during the early stages of programme implementation. Additionally, two full-time positions may be based in the NCPMU premises, which will reduce the overhead costs over the duration of the programme. Additionally, buy-in through the centres of expertise provides the bases of assurances of quality of delivery. The centre given the size of funding it provides guarantees that suppliers will strive to achieve the required level of service the centre demands.
[3] The average cost reflect the average daily rate of international consultant is higher by 13% while the national consultant rate is higher by 46% than of those in EACDS framework. This is not a representation of weighted average.

In terms of efficiency, this relatively low-value intervention has the potential to embed sustainable risk management systems within this megaproject, and potentially in other projects—not necessarily of similar scale but facing comparable challenges. As part of the RMF scope, the presence of full-time PwC staff will help directly transfer risk management knowledge and expertise to other members of the PMU. Furthermore, training programmes will be delivered on active risk management techniques, may involve innovative tools developed by the Oxford Global Projects (OGP) tailored for Jordan, using artificial intelligence to establish benchmarks against cost escalation. These benchmarks could be applied during the lifetime of the project and could be extended to other water projects in Jordan.

Effectiveness. As this is the first-year implementation, we are unable to report on effectiveness. However, the programme’s ToC assumes that FCDO funds will be used in the creation of dedicated RMF, this will limit the overall cost of the project from further increasing. Effectiveness will be measured by cost escalations after exhausting all mitigation measures as proposed by the RMF (the NCPMU will hold full responsibility for any advice).

Equity. Working with the CoE will be key to Gender Equality, Disability and Social Inclusion (GEDSI) success. The RMF has already contracted a team of technical experts (with expertise additional to those already working on the project). These roles will be focused on functions that support GCIEP’s GEDSI, and Climate Nature & Environment CN&E.

Assessment of whether the programme continues to represent value for money

In its first year of implementation focused on mobilisation, the WADI programme has demonstrated clear relevance and elements of effectiveness, with strong performance on economy and efficiency, offering value for money.

Multi-year funding availability, securing continued GoJ buy–in through the CoE and continued GoJ demand over the programme lifecycle, will be critical for the programme to continue to achieve value for money in its current structure.

E: RISK

Overview of risk management

The overall risk of the programme is ‘High.’ The risks have been mostly driven and influenced by external factors, such as regional issues and implications to donor funding.

This year saw significant regional and global events that had direct impact on the NCP: US aid pause of funding, Israeli/Iranian strikes and UK ODA cuts. During this period, the GoJ mitigated the impact by providing full assurance to the continuation of the NCP. The risk of TA not meeting expectations has increased due to limited GoJ capacity to absorb the TA and the high number of stakeholders involved. The programme team are closely monitoring the risks and updating the risk register on quarterly basis.

Below is the list of risks to the programme:

Risk Description	Residual Risk After mitigation	Mitigation
Policy and Programme Delivery
GoJ does not finalise the negotiations and procurement of the NCP, resulting in the project being restructured, delayed or halted. This could be related to affordability and/or water tariff/pricing. This will in turn delay the WADI programme implementation.	Major	FCDO has limited mitigation options, as commercial negotiations are primarily between GoJ and the investor, beyond UK influence. However, the RMF can be developed early to help mitigate delays through consistent GoJ engagement. The FCDO programme team can also keep updated on progress via existing coordination mechanisms (e.g. the Water Sector Donor Group).
TA via WADI flexible facility faces ambiguity on GoJ priorities for either the water sector and/or NCP causing major delays to the WADI programme to mobilise TA during FY24 and FY25. FCDO ODA cuts and pauses may contribute to further in implementing the RMF to align with NCP timelines.	Major	The WADI RMF design follows a structured mechanism to identify GoJ priorities through a risk compliance officer embedded into the NCPMU. SRO/PRO is also heavily engaged alongside the senior management (Development Director and DHM, HMA) with GoJ, and major donors supporting the water sector and NCP, to identify a niche for WADI TA. Subject to confirmation of ODA allocations, the FCDO programme team has planned for multi-year funding for the RMF, including a clear exit handover and exit plan.
Limited GoJ capacity to absorb additional TA for the NCP, as USAID and GIZ are embedding human resourcing at MWI and PMU.	Major	FCDO will continue to have regular conversations with GoJ, USAID, Germany and other donors providing TA to the NCP. FCDO will continue to hold consultations with key stakeholders to ensure value addition from TA provided. As part of the RMF we may provide full-time personnel to be embedded in the NCPMU for capacity building in areas of greatest need.
CoE extend their GCIEP contract with the implementing partner, that will mean we lose the buy-in agreement beyond 31 March 2026	Moderate	Programme Team are in direct contact with the CoE to understand the status of the contract. Programme Team have had the other procurement options aligned to apply if the contract isn't extended.
TA contractor/supplier(s) fails to meet the expectations of GoJ.	Moderate	Ensuring proper and clear ToRs, agreed between FCDO and GoJ for the RMF Inception and Implementation Phases. The proposed governance structures and contract management will address poor performance. Engage NCPMU with ToR drafting and selection of supplier. Design and extended Inception Phase to fully understand GoJ and key stakeholders’ requirements and expectations.
GoJ priorities suddenly change, resulting in a fundamental change of direction regarding the utilisation of the RMF	Minor	FCDO will ensure flexibility in the RMF, for it to respond to changing priorities. A two-stage approach was adopted, to have an initial Design Phase followed by an extended Inception Phase to clearly define the RMF scope and methodology.
Strategy & Context
Global and regional conflicts affect cost and pricing of materials dramatically, resulting in delays to the implementation of the NCP, and the RMF.	Moderate	The risk represents the high uncertainty of external factors. The Russia-Ukraine war, as well as the Israel-Gaza war resulted in significant costs increases since 2022 during the design and procurement phases of the NCP. The RMF will play a key role in supporting the GoJ to identify, quantify the cost of risks, and mitigate them.
Financial & Fiduciary
Misuse of TA funding available through fraud and corruption.	Minor	This risk will be controlled through the FCDO procurement routes and contract clauses for the procurement delivery route. As this is being managed by CoE GCIEP FRA and DDA For other delivery routes, including JFA, Multilaterals and/or (I)NGOs, FCDO will rely on Fiduciary Risk Assessments on PFM for JFA, and Enhanced DDAs for (I)NGOs and Multilaterals
Safeguarding
Risk of exploitation or abuse of beneficiaries and stakeholders through the WADI implementation and downstream delivery partners.	Minor	FCDO contracts cover safeguarding and the Enhanced Due Diligence Assessment that has a particular pillar focusing on safeguarding. The nature of the TA that will be provided will likely have minimal interactions with beneficiaries or the public and is limited to the core team of experts and consultants dealing with the GoJ. The programme team will continuously assess the TA provided and whether interaction with beneficiaries increase any safeguarding risks. The team will revisit the mitigation strategy accordingly.
Reputational
Poor performance of TA reflects badly on the UK as a donor.	Minor	Contracting an RMF Supplier with the relevant expertise. The proposed governance structures and contract management will address poor performance that may cause reputational risk. ToR will have proper selection criteria to ensure proper quality of work. The Supplier performance will be checked against set milestones

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery Performance

The FCDO Programme team has collaborated with the NCPMU, MoPIC and other donors contributing technical advisory to the NCP during the WADI design phase. The RMF Terms of Reference (ToR) were created after extensive coordination with the stakeholders, then incorporated with PwC.

PwC have delivered against the agreed ToR and been responsive to changes in scope. Key deliverables until the time of writing this Annual Review include the Inception Phase TOR, partial mobilisation of the core team and initial stakeholder map— which were submitted and aligned with GCIEP standards. The team mobilised a multidisciplinary group of local and international experts, ensuring contextual relevance and technical depth.

The initial Design Phase was structured into three parts (identifying the RMF, where it fits within the NCPMU and core outputs for the inception phase), each with clear objectives and outputs. The Inception Phase built on this with eight interlinked workstreams – focused on defining the RMF scope, which will culminate in a comprehensive RMF operating model. The implementing partner has demonstrated adaptive management, integrating feedback from FCDO and NCPMU throughout.

However, there were some delays in finalising the Inception Phase TOR, some about the role of the RMF in relation to other technical advisors and the RMF team operates as an integrated, cross-functional unit spanning London and Jordan, ensuring coherence in delivery and accountability across both locations. Roles and responsibilities will be clearly delineated to avoid duplication and streamline decision-making. Strategic oversight remains with the London-based leadership, while operational execution and contextual engagement from Jordan, leveraging local expertise and proximity to stakeholders.

In the year ahead, this could be mitigated by creating a clear and concise coordination plan with the NCPMU and ensuring that the RMF is a supporting mechanism and does not duplicate existing support.

FCDO Jordan has provided consistent support, facilitating stakeholder engagement and timely feedback on deliverables. The FCDO programme team has played a key role in coordinating across government and donor stakeholders.

Commercial and Financial Management

Forecasting and Budgeting

Pre-design	£67,220
RMF Design	£53,275
RMF Inception	£767,426.25

Prior the implementation of the programme the team conducted a preparation study to help design the Business Case. The programme maintained accurate financial forecasting across both phases. The design phase was delivered within its £53,275 budget, while the Inception Phase budget is up to £767,426.25, that has remained within expected variance, originally this was around £900K then reduced as we finalised the ToR. Monthly financial reviews and transparent reporting have supported strong financial governance. Maintaining within FCDO Jordan budget planning.

Open Book Accounting and Transparency

PwC has complied with FCDO’s cost transparency requirements. While profit margins were not explicitly challenged, the use of Open Book Accounting has enabled FCDO to monitor value for money across the 4Es (economy, efficiency, effectiveness, equity).

To maintain clarity and efficiency, resource allocation will be reviewed on a monthly basis, with adjustments made as necessary to reflect evolving priorities and workload. This approach mitigates risks of overlapping functions and ensures that all workstreams remain aligned with programme objectives. Billing will continue to be based on actuals, as agreed, reinforcing transparency and cost-effectiveness

Asset Monitoring

Digital tooling and data governance protocols are to be developed during the Inception Phase, including secure access tiers and audit trails. This could qualify as digital spend, but we will check with relevant FCDO teams to remain compliant with the procedure for such spending.
The RMF dashboarding specialist will begin configuring risk analytics tools, with integration of the Oxford Global Projects Reference Class Forecasting tool to be delivered during the Inception Phase.

Contractual Compliance

Milestones and Terms & Conditions

Delivery against milestones were met, and/or in progress and the RMF team adhered to the agreed scope and timelines. The team also demonstrated flexibility in adapting to stakeholder needs, changes in scope and emerging risks.

Supply Partner Code Compliance

There were no reported breaches of the Supply Partner Code. The implementing partner maintained high standards of conduct, safeguarding, and conflict-of-interest management.

Gender Equality Duty and Equalities Monitoring

The RMF has mainstreamed GEDSI considerations across its Inception Phase workstreams. Inclusive stakeholder engagement protocols were embedded. The initial risk register includes GEDSI risk categories, and training plans have been developed to build NCPMU capacity in this area. The programme aligns with the Public Sector Equality Duty and Jordan’s National Strategy for Women.

Strategic Relationship Management

The Strategic Relationship Management (SRM) scorecard assessment for PwC indicates strong performance in stakeholder coordination, responsiveness, and technical delivery. Areas for improvement include streamlining internal review processes and enhancing local partner capacity building.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Monitoring activities during the review period have been well-integrated into programme delivery. During the RMF Design Phase (September –October 2025), the supplier conducted structured consultations with key stakeholders including the NCPMU, MWI, MoPIC, donor representatives and technical advisors. These engagements ensured that the RMF ToRs were aligned with both WADI and GCIEP ToC, and responsive to GoJ priorities as these all were attended by the programme team, to ensure proper formation of the RMF implementation phase ToR and reflect on modification to the RMF team structure, WADI logframe and possible changes to the WADI ToC. As a result, corrective measures are being discussed with the implementing partners.

The RMF supplier has maintained weekly coordination meetings with the FCDO programme team, enabling real-time feedback and adaptive planning. During the inception phase (November 2025 – March 2026), the plan is to have monthly reporting to FCDO, including updates on progress against deliverables, stakeholder engagement, and risk register development. These reports are to inform programming decisions, such as the prioritisation of GEDSI and CN&E risks and the sequencing of capacity-building activities.

While there is no external M&E supplier contracted for this phase, the RMF team has embedded monitoring functions within its workstreams. The milestones for the inception phase include creating a Results Monitoring (RM) framework aligning with GCIEP logframe indicators and includes quarterly updates to track progress and learning. The FCDO Programme team will also reflect these updates into the WADI logframe.

The Annual Review process has drawn on inputs from FCDO Jordan, GCIEP central teams, and the RMF Supplier (PwC). Feedback from stakeholders—including NCPMU and donors—was incorporated through structured workshops and bilateral meetings.

Evidence

Evidence generation has focused on stakeholder mapping, risk typology development, and institutional capacity assessments. The RMF has produced a draft risk register and risk management plan, informed by consultations and document reviews. These outputs provide a clearer picture of the NCPMU’s current capabilities and gaps, particularly in managing environmental, social, and financial risks.

For the Inception Phase, the evidence base will be strengthened by disaggregating stakeholder data by sector, institutional role, and risk appetite. While full disaggregation is planned for the implementation phase, initial steps have been taken to integrate GEDSI and CN&E indicators into monitoring tools.
The quality of evidence is high, though breadth remains limited by the availability of baseline data from previous suppliers covering the NCP Design Phase. The RMF team has proposed structured handover protocols to mitigate this and ensure continuity.

Learning

Learning has been embedded throughout the Design and Inception Phases via adaptive management cycles, stakeholder workshops, and internal after-action reviews. Key learning targets for the PwC team include:

Establishment of strong and trusted GoJ relationships and inclusive stakeholder engagement from the onset, is critical to align risk management tools with GoJ needs. The RMF’s advisory role must be clearly defined to prevent duplication and ensure value addition.

Embedding GEDSI and CN&E considerations into risk governance frameworks enhances programme relevance and sustainability. The RMF model offers a replicable approach for other infrastructure programmes facing complex risk landscapes.
Learning aims for the coming year include:

Operationalising the RMF’s performance management system, including milestone indicators and learning cycles.

Strengthening GEDSI and CN&E integration into risk identification and mitigation.

Documenting lessons learned through quarterly learning products and contributing to GCIEP’s knowledge hub.
These learning priorities will inform the implementation phase and support continuous improvement across WADI and GCIEP portfolios.

Date of last narrative financial report	N/A	Date of last audited annual statement	N/A