## Annual Review Template

Title: ASEAN-UK Health Security Partnership (ASEAN-UK HSP)
Programme Value £ (full life): £25 million		Review date:
Programme Code: [400044]	AMP start date: / 26 February 2024	AMP end date: / 31 March 2029

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005861.odt
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The ASEAN-UK Health Security Partnership (HSP) is a five-year programme that aims to enhance global health security and reduce the health, social and economic impacts of health emergencies in ASEAN. The programme aims to achieve this goal by building capacity for the prevention, detection and response to health threats in the ASEAN region. The programme strengthens cooperation between UK and ASEAN public health actors, supports mobilisation of a One Health approach and advances equitable access to health by strengthening health systems.

HSP programme interventions contribute to three priority outcomes i.) strengthened preparedness and response to health emergencies; ii.) improved health system resilience and equitable access to care; iii.) better understanding and improved action to address the health impacts of climate change.

HSP is delivered through three components (pillars). Pillars 1 and 2 are managed by a contracted managing agent (FHI 360 UK) in consortium with the Pandemic Institute, Southeast Asia One Health University Network and ITAD, a specialist monitoring, evaluation and learning provider. Pillar 3 is delivered by the Quadripartite through an MoU with WHO South East Asia Regional Office.

Pillar 1: HSP grants facility funding catalytic medium-long term projects that support implementation of relevant national and regional policies and action plans to strengthen health security and preparedness for health emergencies.

Pillar 2: The HSP Peer Exchange Platform serves as a dynamic hub for fostering collaboration and innovation among experts from the UK, ASEAN, and the wider Global South. Through a competitive brokering and funding process, the platform supports short to medium-term peer exchange partnerships that are designed to spark meaningful connections and impactful outcomes. These experts’ partnership enables structured knowledge sharing, the dissemination of best practices, and the transfer of technology across borders. The Peer Exchange Platform also promote collaborative efforts in areas such as cross-border initiatives and One Health approaches, creating an innovative ground for global cooperation and sustainable development.

Pillar 3: A partnership (MoU) with the UN Quadripartite (FAO, WHO, WOAH, UNEP) enabling their combined support for implementation of the ASEAN One Health Joint Plan of Action.

Summary supporting narrative for the overall score in this review

The ASEAN-UK Health Security Partnership (HSP) has encountered a lengthy mobilisation phase that has spanned much of the initial 18-month reporting period. Several factors have contributed to this extended mobilisation, including the complexity of the programme design in seeking to respond to the needs and priorities of 10 diverse ASEAN Member States (AMS), plus Timor-Leste. Additionally, the timeframe required to leverage FCDO’s new Global Development Delivery (GDD) procurement framework has been longer than anticipated. The programme has also had to navigate dual approval processes for its design involving both ASEAN and FCDO; develop and agree upon a separate Memorandum of Understanding (MoU) for pillar 3; and contend with a limited human resource complement within the UK Mission to ASEAN. Furthermore, the limited FCDO development capability in the wider region, particularly in Initiative for ASEAN Integration (IAI) countries, is a limitation. The need to allocate sufficient time for co-designing the programme with ASEAN has also been a factor, given the limited frequency and capacity for external engagement of relevant working groups and networks.

Despite these constraints, the HSP programme design received endorsement from the ASEAN Council of Permanent Representatives on October 3, 2024. An MoU with WHO SEARO, covering pillar 3, was signed in the same month, and a robust delivery consortium, responsible for managing pillars 1 and 2, was contracted in February 2025 following a mini competition delivered through FCDO’s GDD framework. Initial implementation under pillar 3 began in January 2025, while a six-month inception phase for pillars 1 and 2 commenced in February 2025 and is set to conclude in July 2025.

Inception phase activities for pillars 1 and 2 are centred on finalising the co-design of the programme with the ASEAN health sector. This includes consultations with the ASEAN Secretariat (ASEC) and health clusters to determine thematic priorities for grant and peer exchange funding, conducting stakeholder and political economy analyses to inform programme implementation, and developing the programme's monitoring, evaluation, and learning strategy. Additionally, the inception phase is expected to support the launch of 'early-win' activities and see the launch of an initial grant competition. Initial activities under pillar 3 have focused on regional-level initiatives that align closely with established ASEAN priorities and strategies, such as supporting the development of an implementation plan for the ASEAN rabies elimination strategy through the World Organisation for Animal Health (WOAH). The Quadripartite (QPT) is currently working to identify additional country-level inputs in consultation with ASEAN.

This annual review focuses primarily on progress towards implementation because an overarching results framework is still in development and early programme results have not yet been reported. The review assesses whether the programme is on track to deliver expected outputs and contribute to outcomes in future years. Although the mobilisation phase has taken longer than expected, the programme is now well-positioned to advance implementation rapidly in its second year. All three programme components have been mobilised, with technically and programmatically robust delivery partners onboarded across all three pillars. This offers a level of confidence that the programme will deliver expected outputs in its second year. A formal programme launch, marking the end of the inception phase, is anticipated to coincide with the Senior Officials Health and Development Meeting in July 2025.

Despite delays in mobilisation and the subsequent impact on delivery of expected outputs, the programme is assessed as on track to deliver expected outputs and contribute to its intended outcomes, earning an 'A' score for having met expectations in its first year.

Major lessons and recommendations for the year ahead

- To facilitate ASEAN-UK co-ownership of the programme, timely decision making and cross-pillar coordination, the HSP programme should expedite the establishment of planned joint governance and coordination arrangements between ASEAN and HSP programme stakeholders. These include the Joint Programme Steering Committee (JPSC) and Programme Technical Consultation Groups (PTCGs).
- Work to develop an integrated HSP theory of change, covering all 3 pillars, should be prioritised. Ongoing work to establish MEL systems across pillars 1&2 and 3 should seek to deliver an integrated approach to MEL, with the results framework for pillar 3 connecting to the wider HSP results framework.
- UKMis and the HSP delivery consortium (including ITAD as a common MEL partner) should explore opportunities to enable the two-way exchange of learning with other relevant HMG programmes addressing health security and preparedness (including the Tackling Deadly Diseases in Africa Programme and Fleming Fund for AMR surveillance and data).
- UKMis, the HSP delivery consortium and Quadripartite should explicitly identify and pursue synergies between pillars e.g. in building demand for programme interventions, aligning MEL, communications and stakeholder engagement. This should include consideration of how to maximise the benefits of FCDO staffing (health advisers and focal points) across the ASEAN region.
- UKMis should regularly review programme & advisory capacity against programme needs, developing a consolidated assessment to inform future strategic workforce planning.
- UKMis, the HSP delivery consortium and Quadripartite should use ongoing scenario planning to inform a portfolio investment strategy that allows – to the extent possible – the programme to manage significant budgetary uncertainty in future years.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

In its first year of mobilisation, the HSP programme’s theory of change (ToC) remains as outlined in the original programme business case. Programme outcomes, proposed indicators and underlying assumptions remain valid.

The theory of change (figure 1) envisions that by mobilising: targeted grant funding at regional and country level; ASEAN & UK expertise; and enabling technical and multisectoral inputs by the Quadripartite, the programme will contribute to: i.) improved preparedness & response to health emergencies; ii.) more resilient health systems and equitable access to care; and iii.) better understanding and action on the health impacts of climate change.

As the HSP programme progresses through its 6-month inception phase the programme theory of change is being actively refined. Revision of the theory of change is being informed by detailed design consultation with ASEAN, wider stakeholder engagement and political economy analysis. Based on this, proposed revisions to the theory of change include the addition of nearer term ‘intermediate outcomes’, which will enable more granular tracking of progress towards outcomes.

Other proposed changes to the ToC include the addition of ‘mechanisms of change’ e.g. ‘policy dialogue and advocacy’ or ‘community engagement & risk communication’. These define how programme inputs will realise intended outputs. The addition of ‘mechanisms of change’ will strengthen the Theory of Change because, in the context of a demand-led programme that competes grant funding, it is not possible to specify exact programme outputs prior to making grant awards. A refined theory of change and updated results framework will therefore be in place for future annual reviews.

The assumptions underlying the ToC (as outlined in the business case) also remain valid. These include assumptions that there will be sufficient demand from eligible stakeholders for HSP support; an assumption that the contracted delivery consortium and Quadripartite will be able to mobilise a high-quality final design and coordinate effectively across programme components, supporting an adaptive approach; and an assumption that governments will continue to prioritise investment in health systems and integrated capabilities for the prevention, detection and response to health emergencies. Detailed interrogation of ToC assumptions is planned during a May 2025 MEL workshop. As an active tool for programme management and course correction, ToC assumptions will also be regularly re-visited during Quarterly Learning Forums.

A programme midline and endline evaluation is planned with an independent evaluation lead appointed as part of the pillar 1 and 2 delivery consortium. Evaluation questions are subject to revision during the inception phase but are expected to include: a.) to what extent is the HSP portfolio strategically relevant and coherent; b.) how is grant management, delivery and governance working and is HSP delivering VfM; c.) to what extent has the HSP programme contributed to its intended outcomes. The MEL supplier, ITAD, expects to submit the final evaluation design to FCDO’s Evaluation Quality Assurance and Learning Service (EQUALS) at the end of the inception phase.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

We assess that the programme theory of change remains valid and that with key delivery mechanisms being mobilised, the programme is well positioned to deliver expected outputs in future years, contributing to target outcomes and the ASEAN-UK Plan of Action. On this basis we recommend that the programme is continued.

Figure 1: ASEAN-UK Health Security Partnership – programme theory of change:

## C. DETAILED OUTPUT SCORING

Detailed output scoring for the ASEAN-UK Health Security Partnership programme is not possible during this annual review. This is because the programme remains in its inception period, with implementation under pillars 1, 2 and 3 only having commenced in early 2025 and grant activity under pillars 1 and 2 not due to commence until July 2025. This limits the availability of monitoring data and reporting to inform a detailed output scoring.

The current draft logical framework, included in Annex 1, is being actively revised during the inception phase (February – July 2025) and therefore is not being used for the purposes of this annual review. Whilst programme outcomes are set, discussions with ASEAN regarding thematic priorities for grant funding are ongoing as of May 2025. The outcome of these discussions will directly inform expected programme outputs and enable finalisation of the results framework.

This 1st HSP annual review will therefore provide a narrative assessment of progress towards implementation across the three main components of the programme. It will evaluate the likelihood that the programme will effectively deliver the expected inputs and outputs in the coming year, as defined in the theory of change. Additionally, the review will include a high-level assessment of programme readiness for year two of implementation, focusing on the development of a comprehensive approach to monitoring, evaluation, and learning, as well as programme coordination, governance, and resource allocation.

Output Title	Component 1 and 2: HSP grants facility & HSP peer exchange platform
Output number:		1 & 2	Output Score:	A
Impact weighting (%):		66%	Weighting revised since last AR?	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

Pillars 1 (grants facility) and 2 (peer exchange platform) form the core of the HSP programme, with design and implementation overseen by a contracted managing agent (FHI 360 UK) in consortium with the Pandemic Institute, South East Asia One Health University Network and a specialist MEL provider (ITAD).

The HSP grants facility funds catalytic medium-long term projects that support implementation of relevant national and regional policies and action plans to strengthen health security and preparedness for health emergencies, contributing to HSP target outcomes. The grants facility will fund i.) competed grant awards open to relevant ASEAN Member State (AMS) institutions (e.g. National Institutes of Public Health), CSOs and academic institutes, and ii.) non-competed grant funding at the regional level to the ASEAN secretariat and ASEAN institutions.

The HSP peer exchange platform brokers and funds competed, short-medium term peer exchange partnerships between UK, ASEAN and ‘global south’ practitioners, researchers, policy makers and academics to strengthen health security and preparedness for health emergencies across One Health domains. Peer exchange partnerships are intended to support: i.) structured knowledge exchange; ii.) dissemination of best practice; iii.) technology transfer; iv.) cross-border collaboration v.) One Health collaboration. The platform will support partnerships that contribute to HSP outcomes, are aligned with relevant action plans and/or strengthen one or more of the 13 IHR core capacities[1] or capacity building needs identified through the Performance of Veterinary Services (PVS) pathway.
[1] The 13 core capacities are: (1) National legislation, policy and financing; (2) Coordination and National Focal Point communications; (3) Surveillance; (4) Response; (5) Preparedness; (6) Risk communication; (7) Human resources; (8) Laboratory; (9) Points of entry; (10) Zoonotic events; (11) Food safety; (12) Chemical events; (13) Radionuclear emergencies.

The mobilisation of pillars 1 and 2 has been delayed by longer than expected procurement and contracting timelines. On the advice of FCDO’s procurement and commercial directorate, UKMIS ASEAN elected to procure a managing agent for pillars 1 and 2 through FCDO’s refreshed Global Development Delivery (GDD) Framework which was launched in late 2024. The GDD includes multiple thematic lots with a pool of pre-qualified suppliers. Proposals for programme delivery can be solicited through mini competitions open to pre-qualified suppliers.

Whilst the GDD is intended to streamline procurement processes, timelines to conclude the procurement process still exceeded expectations. Delays related to a range of factors including: staff familiarity with the new framework; the time required to prepare a tender for a relatively complex programme; limitations to advancing procurement during the UK electoral period; the need to respond and adjust Terms of Reference in response to supplier feedback following early market engagement and the significant investment of staff time required to complete the technical evaluation of large proposals.

Despite some delays, the tender for pillars 1 and 2 was concluded in December 2024 and a contract was signed with the selected supplier in February 2025. The outcome of the procurement demonstrates the value of the GDD, with the HSP mini competition receiving several strong proposals and ultimately the appointment of a robust delivery consortium that offers both depth and breadth of technical expertise on health security and One health, contextual understanding of the ASEAN region and strong programme capabilities.

Following contracting of the lead supplier (FHI 360 UK) as management agent for pillars 1 and 2 and commencement of a 6-month inception phase (February-July 2025), programme mobilisation has progressed at pace, in line with the inception phase workplan submitted in the selected proposal. Key milestones in the mobilisation of pillars 1 and 2 have included:

- Timely contracting and mobilisation of core staff in February and March 2025
- The organisation and completion of in person kick-off meetings in Jakarta with UKMIS and ASEAN secretariat in March 2025
- The on-time submission of month 2 milestone deliverables including completion of a desk review to inform thematic prioritisation for grant and peer exchange award investment
- Initial consultation and agreement with ASEAN secretariat on an approach to programme governance and co-design
- Planning and agreement with ASEAN for a public launch event on the sidelines of the ASEAN Snr Officials Meeting Health and Development in July 2025
At the time of completing this annual review three months of the inception phase remain. A key focus for this period will be actioning agreed next steps in relation to co-design with the ASEAN health sector and securing sufficient input and consultation with ASEAN health clusters to develop and agree co-owned thematic priorities for grant investment. This critical step must be prioritised to ensure that thematic priorities that will guide programme investments are agreed in a timely manner so that grant and peer exchange competitions reflect ASEAN priorities, achieve strong buy-in from ASEAN stakeholders, and launch on time, enabling best usage of HSP’s allocated budget in FY 24/25.

Uncertainty in relation to budgetary allocation for pillars 1 and 2 in future years requires that programme act early to consider a range of investment scenarios. UKMIS has commissioned scenario planning from FHI360 to accommodate a range of financial scenarios in future years. This work should be continually refined as the fiscal context for UKMIS ODA investments becomes clearer.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

- Build staff familiarity with the GDD - to enhance the efficiency of future procurement processes, FCDO should increase staff familiarity with the Global Development Delivery (GDD) framework.
- Plan and allocate sufficient staff time for technical evaluations - given the complexity and task size of technical evaluations, it is important not to underestimate staff inputs required. This may require temporarily de-prioritising other activities.
- Prioritise and expedite inception phase consultations with ASEAN Health Sector - HSP should focus on expediting consultations with the ASEAN health sector to collaboratively develop thematic priorities.
- Develop and refine a flexible portfolio investment strategy - in light of potential budgetary uncertainties, it is important to develop a flexible portfolio investment strategy. This strategy should enable the HSP to adapt to various financial scenarios in future years while ensuring optimal resource allocation for the 2024/25 financial year.
- Finalise the programme results framework - completing and integrating the results framework into programme planning is essential for future annual reviews and effectively measuring and tracking progress towards the programme's outcomes.
- Strengthen coordination with Pillar 3 - to maximise synergies and ensure cohesive programme implementation, it is important to mobilise planned governance and coordination structures and to strengthen coordination with Pillar 3.

Output Title	Component 3: partnership with the UN Quadripartite (FAO, WHO, WOAH, UNEP) in support of ASEAN One Health Plan of Action
Output number:		3	Output Score:	A
Impact weighting (%):		34%	Weighting revised since last AR?	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

Pillar 3 of the HSP programme ‘partnership with the Quadripartite to support implementation of the ASEAN One Health Joint Plan of Action’ supports implementation of the ASEAN-UK Plan of Action 2022-26 including objectives to ‘promote coordination and collaboration in sectors involved in One Health’. The project contributes to implementation of the global and ASEAN One Health plans of action by enabling the deployment of the Quadripartite’s unique technical expertise, convening power and coordinating role to address those health security threats that arise at the One Health (human, animal, environmental) interface e.g. antimicrobial resistance and emerging disease, including diseases of pandemic potential.

Pillar 3 is implemented through a Contribution Arrangement with WHO South East Asia Regional Office, leveraging the established FCDO-WHO framework agreement. WHO SEARO manages downstream agreements with other Quadripartite members (WHO Western Pacific Regional Office, FAO, World Organisation for Animal Health – WOAH and UNEP). Following HSP business case approval in January 2024, UKMis and the Quadripartite entered discussions to develop an agreement, workplan and budget. An agreement was signed in November 2024 and implementation began in January 2025.

The relatively lengthy process to agree a workplan and contribution agreement reflects the complexity of facilitating a collaboration between the UK, ASEAN and 5 independent agencies (2 WHO regional offices, FAO’s regional office, UNEP’s regional office and WOAH’s sub-regional office). Despite taking 10 months to reach final agreement, the initial design and mobilisation process was greatly facilitated by i.) the presence of an established Asia-Pacific Quadripartite Regional Secretariat ii.) the ability for UKMis to draw on the established FCDO-WHO framework agreement iii.) WHO SEARO’s willingness to manage onwards agreements with other QPT agencies iv.) the constructive feedback and collaboration of the ASEAN Secretariat and health sector in the design of pillar 3.

Pending the publication of the ASEAN One Health Plan of Action (expected in summer 2025), the pillar 3 workplan orientates activities around the 6 ‘action tracks’ of the Global One Health Joint Plan of Action[2] and articulates how these contribute to ASEAN priorities (for example as articulated in the ASEAN One Health Leaders Declaration or relevant strategies e.g. ASEAN Highly Pathogenic Avian Influenza Framework).
[2] Enhancing One Health capacities to strengthen health systems; Reducing the risks from emerging and re-emerging zoonotic epidemics and pandemics; Controlling and eliminating endemic zoonotic, neglected tropical, and vector-borne diseases; Strengthening the assessment, management, and communication of food safety risks; Curbing the silent pandemic of antimicrobial resistance (AMR); Integrating the environment into One Health

Following the start of implementation in January 2025, initial activities supported under pillar 3 have focussed at the regional level (e.g. WOAH’s support in the development of an implementation plan to underpin the ASEAN rabies elimination strategy). In April 2025, UKMis and the Quadripartite agreed with ASEAN’s One Health Coordinating Committee that country level inputs under pillar 3 would be developed based on needs and opportunities identified through a workshop with ASEAN One Health network representatives. The workshop is scheduled for August 2025. Country level inputs will also be defined through wider consultation between Quadripartite agencies and ASEAN member states.

Key progress under pillar 3 to date includes:

- Operationalisation of the ASEAN One Health Joint Plan of Action (OH JPA): QPT partners have contributed to ongoing dialogue being led by Indonesia to finalise the ASEAN OH JPA, enhancing multisectoral collaboration and regional ownership.
- Continuation of the Asia-Pacific Quadripartite Secretariat: HSP is supporting the continuation of the regional secretariat, with responsibility being handed from WHO SEARO to UNEP, with a One Health consultant onboarded to improve coordination among partners.
- Project Management Unit Creation: WHO established a Project Management Unit to oversee project coordination, ensuring timely disbursement of funds and effective communication with stakeholders.
- Engagement with Regional Partners: WOAH engaged key regional partners, contributing to the Monitoring and Evaluation framework for the ASEAN Rabies Elimination Strategy and FAO support preparations for the ASEAN Avian Influenza Group meeting.
- Strengthened Stakeholder Engagement: Significant discussions were held with ASEAN sectoral bodies and UK FCDO representatives to align project objectives and planned activities with ASEAN priorities.

Challenges noted during initial implementation of pillar 3 include the absence of a clear process and timeline for the revision, consultation, and approval of the pillar 3 workplan in response to a dynamic operating context and emerging ASEAN One Health priorities. Additionally, financial reporting is not currently aligned with narrative reports or the FCDO financial year, creating a lag in reporting and availability of financial information. In addition (whilst HSP programme inception is ongoing) cross HSP coordination and governance arrangements are not yet fully established, limiting the effectiveness of coordination across all 3 pillars of the programme. Finally, whilst the work plan continues to evolve in response to ASEAN member state inputs, pillar 3 does not yet have a finalised results framework, limiting the ability to monitor progress towards outcomes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

- Establish a regular process and timeline for the revision, consultation, and approval of the pillar 3 workplan to adapt to the dynamic operating context and emerging ASEAN priorities.
- Harmonise financial reporting requirements and timelines for pillar 3, ensuring alignment with narrative reporting and the FCDO financial year.
- Define and establish cross-pillar coordination structures within HSP to enhance collaboration and realise synergies across its pillars (e.g. the potential for QPT partners to build demand for grant and peer exchange opportunities under pillars 1 and 2 and provide technical assistance to eligible stakeholders in developing grant applications)
- Streamline coordination between HSP pillar 3 and relevant ASEAN health sector bodies and networks engaged in One Health (including the ASEAN One Health coordinating committee, ASEAN OH Network, ASEAN Coordinating Centre for Animal Health and Zoonoses)
- Clarify and navigate the policies and constraints of all HSP stakeholders (including Quadripartite agencies) when working with non-ODA eligible countries and Myanmar.
- Reinforce and clarify FCDO expectations with an updated guidance regarding the branding and visibility of HSP-supported activities.
- Fully incorporate pillar 3 within the recently updated HSP programme theory of change and narrative.
- Develop a results framework for pillar 3 that can be integrated into the wider HSP logical framework currently being developed.
- Share UKMis experience and learning in working with the QPT with relevant FCDO policy teams.

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case and assessment of whether the programme continues to represent value for money

As detailed in the introduction to this annual review, the HSP programme has only completed 3-4 months of implementation during the review period. Therefore, in the absence of detailed results and financial reporting it is not yet possible to determine VfM performance. However, we assess that the VfM proposition in the business case remains valid.

In summary, HSP will seek to deliver value for money through:

- Economy: the programme will leverage local ASEAN expertise and, where feasible, remote working methods to minimise costs associated with travel and subsistence, ensuring efficient use of resources.
- Efficiency: key output indicators will be tracked throughout the programme's lifecycle to identify effective spending, with robust management arrangements in place to ensure that management costs remain within an efficient range.
- Effectiveness: the programme will focus on evidence-based interventions, utilising FCDO’s Best Buys analysis to ensure that investments in health surveillance and public health goods deliver significant benefits at a low cost.
- Equity: programme funds will prioritise countries and communities with the greatest need, particularly targeting vulnerable populations such as women and children, to enhance health security and equitable access to health systems.
- Evidence: robust monitoring, evaluation, and learning (MEL) framework will be implemented to assess the impact of interventions. Where possible, disaggregated data will be collected to evaluate outcomes across gender and disability.
Value for money metrics are being refined during programme inception, but are expected to include:

HSP Indicative Value for Money (VfM) metrics
VfM dimension	Indicators (qualitative and quantitative)
Economy	Fee rates of consultants (regionally sourced vs international) / Cost and effectiveness of programme in-sourced roles (PIR) vs external consultants / Ratio in-person vs. remotely provide time inputs (cutting travel/subsistence) / Number of locally sourced projects. / % of contractors’ costs relative to disbursements.
Efficiency – spending well	Ratio overhead/administration costs vs. intervention/TA input costs / Timeliness of project completion: Average time (months) to identify, agree and approve initial plans and interventions by ASEC, starting from Business Case approval date. / Project completion within budget.
Effectiveness – spending wisely	Percentage change in IHR scores. / Increase in regional domestic resource investment in health security. / Country or regional examples of identifiable influence on events, policy uptake and programmatic decision-making that demonstrate use of global evidence on key themes.
Equity – spending fairly	Beneficiaries of interventions compared by gender. / Extent to which interventions translate into benefits for IAI countries. / Impact of interventions on marginalised groups.

E: RISK

Overview of risk management
The preliminary assessment from the Business Case risk appetite indicated that the HSP programme carries a moderate risk level, with fiduciary risk also categorised as medium. Considering the ongoing challenges and dynamics during the first implementation year, such as delays in contract and MOU mobilisation, along with the recent announcement of the potential budget reduction anticipated in the upcoming years, there is a chance that the programme's risk rating may rise to a high-risk level due to the aforementioned concerns.
At the UKMis level, the seven identified risks category outlined in the Business Case remains relevant, especially in relation to the limited capacity of human resources within the ASEAN Secretariat to facilitate programme delivery and promote co-ownership of grant applications with ASEAN Member States. There are also inclusivity issues remains significant in ensuring the participation of all ASEAN Member States, including Myanmar, in demand-led grants under the HSP Pillars for instance. The inclusion of Myanmar enhances under Pillar 3 delivery discussion, particularly in terms of how to involve Myanmar in a manner that respects Quadripartite rules, ensuring that everyone is included in the HSP programme.
At the programme level, the risks are primarily operational, as highlighted in the Business Case, where delays in securing capable implementing partners are a reality, pushing the start of supplier contracts to February 2025. Additionally, there is growing concern regarding how the programme team will manage potential budget cuts and collaborate with implementing partners to prepare for various budget scenarios in the coming years. Specifically, the Business Case also indicates that a limited budget poses a risk that could lead to reduced impact, which is another concern. Consequently, the mitigation strategies outlined in the Business Case remain relevant, and as HSP team discussed during the MEL Workshop, all pillars will promote innovative approaches to leverage opportunities and maximise impact despite the constrained budget as we brace for anticipated budget reductions in the future.
As the HSP programme is still in its early stages of delivery, the development and incorporation of risk management systems are still ongoing and will regularly update within the programme implementation (FHI for Pillars 1 and 2, and Quadripartite for Pillar 3). Since the outlined risk register in the Business Case continues to be relevant, risk appetite and its mitigation will regularly identify and updated through:
- Development of risk management and fraud mitigation strategies with all implementing partners.
- Requirement for annual assessment. For FHI, this will be highlighted in the inception report and their annual report, while for Quadripartite, this will be updated regularly through the agreed six-monthly/quarterly report.
- Regular financial spot checks, field visits with support from the SE Asia Health Advisers/HSP Focal Points, and quarterly risk register reviews (discussed with implementing partners and updated through AMP quarterly).
- Maintenance of asset inventories by delivery partners, with annual reporting.
- Due diligence assessments for all implementing partners.
- FCDO’s right to conduct forensic audits at any stage of the programme.
To ensure timely and effective risk management, the HSP programme team has proposed establishing the Internal Programme Board (chaired by HSP team) and utilising the UKMis Programme Portfolio Board (chaired by UKMis Development Director) for escalating risks and seeking agreement on risk management as one of the key agenda.
The Internal Programme Board (IPB) will serve as a programme level channel for reviewing progress across all programme pillars and for identifying and addressing key risks. It is being designed to include participation from all implementing partners, allowing for shared updates, collaborative problem-solving, and early escalation of risk issues. The IPB will be conducted every quarterly and play a significant role in identifying and mitigating risks, such as financial fraud, implementation delays, or underspending, and determining appropriate mitigation strategies. It will be the first option for escalating identified operational and delivery-level risks.

The second forum is the UKMis Programme Portfolio Board, which serves as a mission level channel every quarterly for discussing significant programme-wide risks with the UKMis Head of Development and UKMis Development Director. This includes reviewing budget forecasts and delivery plans, tracking overall programme spending, and assessing programme impact. If major risks occur, such as financial concerns or detected fraud, they can be escalated to this forum for further guidance and decision-making, following the FCDO PrOF guidance, related to the risks issues reported.
In summary, the PRO and Health Adviser conduct a quarterly review of the programme risk register, which is then discussed with the SRO. Then, the SRO will approve the risk register during updates to the AMP and when reporting to the IPB and will escalate it to the Portfolio Board if necessary. These two board channels will enable conversations about risk mitigation and the identification of new risks, with baseline information derived from all updates on implementing risks that the HSP team will receive regularly according to the established reporting schedule with implementing partners. Furthermore, these two board channels will ensure a structured and responsive approach to risk management, enabling both operational and strategic oversight throughout the HSP programme lifecycle.
Safeguarding
The brief duration of the HSP programme's mobilisation makes evaluation challenging to assess safeguarding implementation across all pillars. Nevertheless, the pre-identified assumptions regarding safeguarding, as detailed in the business case, still remain prominent. The HSP team has maintained a proactive approach on safeguarding, consistent with the commitments made to the FCDO in the business case. Protecting children and vulnerable adults from sexual exploitation, abuse, harassment, and other types of harm continues to be a key focus in all programme activities and collaborations.
To further mitigate safeguarding risks, the UKMis safeguarding champion conducted regular workshops for all implementing partners across the mission's programmes, including the recent partner's day meeting in Jakarta. The safeguarding session within the partner's day agenda was well-received, with implementing partners participating and providing positive feedback on its clarity and practical value, ensuring consistent reinforcement of safeguarding principles.
Due Diligence Assessment
The DDA was conducted as part of the pre-qualification for selected suppliers under the GDD framework, while the CAA was carried out by the central assessment team for WHO, sourced from the FCDO WHO Hub team.
The FHI DDA did not raise any significant risks from the commercial team during the pre-qualification assessment. However, the WHO CAA indicates a significant/major level of net risk in the overall framework of governance, risk management, and control. In response to the significant level of net risk identified in the WHO CAA, the HSP team is recommended to take a proactive and structured approach to mitigation with the Quadripartite, strengthening the governance, coordination, and oversight mechanisms with WHO as the representative of the Quadripartite in the FCDO's MoU.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The HSP Programme has made significant progress in its first year of implementation. Despite a lengthy commercial and MoU arrangement process, which left only 2-3 months for mobilisation before the end of the 24/25 financial year, the programme has successfully identified and proposed an initial governance structure, particularly for Pillars 1 and 2. As we highlighted, the process of finalising the governance structure is still ongoing and will be completed within the next few months of the inception phase with FHI. Ongoing discussions are also taking place to finalise the results framework and governance with the Quadripartite for Pillar 3. All ongoing engagements are noted to be in close collaboration with ASEAN, ensuring smooth coordination with the Secretariat and sectoral health bodies.

The primary management team for the HSP programme, located in Jakarta and Bangkok, has shown impressive commitment in guiding the programme during its foundational year. The Senior Responsible Owner (SRO) and Programme Responsible Owner (PRO) in Jakarta, along with the Regional Director for Southeast Asia (Health) in Bangkok, have collaborated effectively, although they are operating with minimal resources. From a governance perspective, to effectively manage a large-scale regional initiative with a significant budget, the Health team at UKMis needs more personnel. Despite its limited capacity, this team is working diligently to ensure the UK's contribution to the region and to maximise the programme's impact, which involves coordination with the ASEAN Secretariat and sectoral health bodies representing 10 Member States and Timor Leste.

Pillar 1: Grant Facility and Pillar 2: Peer Exchange Platform

FHI 360 UK, leading a consortium that includes The Pandemic Institute (TPI), SEAOHUN, and ITAD, has taken responsibility for delivering Pillars 1 and 2. According to the latest progress report, FHI has proposed a robust governance structure to UKMis and the ASEAN Secretariat, promoting inclusivity, transparency and accountability through mechanisms such as the Joint Programme Steering Committee and Joint Technical Consultation Groups. Once this structure receives approval from the ASEAN Secretariat, it is recommended to test the proposed structure through a learning-by-doing process, including assessing potential gaps and addressing key identified areas for improvement in the future.

Pillars 1 and 2 have shown promising progress as they are in the inception phase, which inclusively includes consultation with UKMis and ASEAN, such as to identify collaboration areas and thematic priorities for the grant avenue. As agreed in the contract KPI, the first two months of deliverables have met good quality standards with a high degree of professionalism. Of the two deliverables, one KPI was submitted on time, while the other experienced a slight delay. This delay is understandable, as the due date for these first two deliverables coincided with the first kick-off meeting, where the FHI consortium met to discuss the programme strategy with UKMis, leaving only a couple of weeks to work on the targeted KPIs. To address this, the next inception KPI will be assessed in advance with proactive coordination with FHI, assuring that the targeted deliverables are delivered promptly and are of satisfactory quality.

Throughout the last financial year, the HSP team has maintained open and proactive communication with FHI regarding risk management. This has included regular updates on emerging risks and the steps taken to mitigate them during the progress tracker meeting coordination. The FHI approach has been both strategic and adaptive, ensuring that potential challenges are addressed before escalating to UKMis. This ongoing exchange in communication and coordination has strengthened trust and contributed to a shared understanding of the pillar's operating environment, especially during the inception period. Moreover, financial risk management has also been a notable strength. Financial reports and invoices have been submitted in a timely and organised manner, with clear documentation and adherence to financial protocols. On the rare occasions when clarifications were needed, the FHI team responded promptly and effectively, reinforcing a culture of transparency and responsiveness.

Pillar 3: Partnership with Quadripartite (WHO, FAO, WOAH, UNEP) in mobilising the ASEAN One Health Joint Plan of Action

The implementation of HSP Pillar 3 has been marked by a deepening of collaboration among the Quadripartite partners, strengthening its existing close coordination with the ASEAN Secretariat and ASEAN Member States. This partnership has been instrumental in advancing the ASEAN One Health Joint Plan of Action, with a shared vision of improving the health of humans, animals, plants, and the environment through integrated, cross-sectoral approaches.

The quality and timeliness of narrative reporting is a prominent concern, as highlighted by the recent six-monthly report received. Overall, the reports have provided clear information on each action tracks commitment of the global One Health Joint Plan of Action activities that were agreed upon earlier. However, the details available on the implementation progress and completion of each activity implemented by WHO and other Quadripartite members are quite limited. Under the advance payment mechanism with WHO, detail reporting on the agreed activities from the costed workplan is prominent (such as attaching a record of ToR and budget expenses), alongside the six-monthly report or submitted in advance of the event implementation to monitor execution, maximise value for money, and ensure UKMis visibility.

Another review highlighted in the financial report submitted with the six-monthly report is the confidence level in spending and forecasting under Pillar 3. Forecasting has been quite low for the implementation of Pillar 3 in the financial year 25/26, raising questions about how efficiently resources will be allocated under this Pillar. Further coordination, consultation, and monitoring are highly recommended to ensure accountability and increase Quadripartite commitment to the allocated budget resources in achieving Pillar 3 objectives, particularly in mobilising the ASEAN Health objectives, including the implementation of the ASEAN One Health Joint Plan of Action and specific health cluster priorities related to Quadripartite expertise.

As the implementation of HSP Pillar 3 continues to evolve, the role of the UKMis remains critical in ensuring that the Quadripartite can fulfil its ambitious mandate under Pillar 3, mobilising the ASEAN One Health Joint Plan of Action. One key area where UKMis can add value is by helping the Quadripartite fully utilize the allocated budget to accelerate Pillar 3 delivery. With UKMis support in enhancing collaboration with ASEAN Health Clusters and facilitating structured engagement between the Quadripartite and relevant clusters, this can help identify synergies, align priorities, unlock co-financing opportunities, and maximise the impact of Pillar 3, including support for the newly established ASEAN One Health Network.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

Summarise monitoring activities and how these have informed programme decisions

With only 4 months of implementation during the reporting period, monitoring activities to date have been limited. UKMis has prioritised stakeholder engagement with the ASEAN secretariat; ASEAN health sector (including health clusters) and relevant health bodies (e.g. the ASEAN BioSurveillance Threats Centre). Opportunities for stakeholder engagement have been used to socialise and gather feedback on the HSP programme design. In addition, the programme health adviser has undertaken country level visits to Laos and Cambodia, engaging with country governments, building the programme’s understanding of the national context, the challenges facing Initiative for ASEAN Integration (IAI) countries and beginning to scope opportunities for programme investment.

Due to the short duration of programme implementation there has been limited submission of monitoring information to date. Pillar 1 and 2 mobilisation meetings in March 2025 and a Monitoring, Evaluation and Learning (MEL) workshop scheduled in May 2025 provided an opportunity to refine the Pillar 1 and 2 MEL strategy during the inception phase. Pillar 3 (MoU with the Quadripartite in support of the ASEAN One Health) was due to submit their initial 6 monthly narrative report, outlining progress against the pillar 3 workplan, in May 2025.

MEL for pillars 1 and 2 is led by ITAD, a specialist MEL provider, contracted as part of the pillars 1 and 2 delivery consortium led by FHI360. ITAD has led a process, drawing on the expertise of the wider consortium and their support to MEL in other HMG health programmes, to develop a MEL strategy and framework for the HSP programme. The strategy (figure 1) outlines the expected approach to MEL at three levels: i.) grant / award level – with a focus on M&L at the grantee/awardee level implemented by grantees/awardees and quality assured by FHI360; ii.) portfolio level – with a focus on M&L synthesis from the aggregated portfolio of grant/peer exchange awards – with shared responsibility between FHI360 and ITAD; iii.) programme level – with a focus on M&L across the breadth of the programme, assessing progress towards outcomes against the theory of change – led by ITAD. A summary of the proposed approach is outlined in figure.2. During the inception phase, the Quadripartite (leading implementation of pillar 3) are developing a logical framework and nested theory of change which will link to the wider HSP theory of change.

Figure. 2 – HSP pillars 1 and 2 monitoring system

ITAD are also leading design and implementation of an integrated evaluation component. The evaluation includes a mid and endline assessment and focusses on three evaluation questions: i.) to what extent the HSP portfolio is strategically relevant and coherent; ii.) How grant management, delivery and governance is working and whether the programme is delivering VFM; and iii.) to what extent the programme has contributed to its intended outcomes. To assure a level of independence from the wider delivery consortium, and robustness of evaluation findings, ITAD has appointed an independent consultant to lead on the programme evaluation who will work at arm’s length from FHI360 and the wider team supporting the MEL system.

The programme’s approach to learning is being refined during the inception phase. Key learning spaces identified during initial discussions include after action reviews (e.g. following a grant competition); internal quarterly learning forums – providing a separate reflective space for both internal and external stakeholders and dedicated learning events to disseminate results of the programme. An inception phase MEL workshop, scheduled in May 2025, is expected to identify specific learning questions, with a particular focus on optimising learning around an intensive 1st year of implementation (e.g. on the efficiency and effectiveness of grant application and award processes).

In relation the HSP programme’s 1st annual review, the review team has adopted a light touch process, recognising the limited duration of implementation to date and longer than expected procurement and mobilisation phase. A desk-based review of key documents and inception phase meetings including the pillars 1 and 2 kick off meetings; pillar 3 mobilisation meeting; and several meetings with ASEC and ASEAN stakeholders, have fed into the review and its recommendations.

We expect that the next programme annual review will be able to assess the programme’s 1st substantive year of implementation and be able to draw on a range of monitoring and learning information that the MEL system is now positioned to provide.

Date of last narrative financial report	21 March 2025	Date of last audited annual statement	N/A

ANNEX 1 – DRAFT RESULTS FRAMEWORK

Annex 2: HSP – PrOF ODA Compliance:

Compliance Indicator	Details	HSP
SRO and PRO (3.14)
	The programme has a named SRO and PRO	Yes
	SRO and PRO training completed	Yes
RESULTS FRAMEWORK (3.13)
	The programme has a valid results framework in place (i.e. logframe)	Incomplete
PROGRAMME TRANSPARENCY (3.01)
	The following documents are published on DevTracker:
	Business Case	Yes
	Funding agreement(s)	Yes
	Logframe	Incomplete
	Annual Review	N/A
	Evaluation (if relevant)	N/A
	Project Completion Report	N/A
RISK MANAGEMENT (2.07)
	Risk Register is in place (on AMP)	Yes
	The risk appetite is set for every risk category	Yes
	The risk register is updated at least every quarter	Yes
	Any risks outside of appetite have been escalated to the portfolio risk register	Yes
FCDO BRANDING REQUIREMENTS (3.03)
	A signed visibility statement is in place with each implementing partner	Yes
DUE DILIGENCE (3.02)
	For all funding arrangements, an up-to-date DDA is in place (less than 3 years old)	Yes
	All completed DDAs are saved in the DDA library	Yes
FORMAL FUNDING AGREEMENTS (3.08)
	All funding relationships have a signed funding agreement or contract in place	Yes
	A signed funding agreement is in place prior to the commitment or disbursement of funds	Yes
	The funding agreement or contract uses the appropriate template, and any changes to the template have been agreed by the SRO and where appropriate based on advice from the Control and Assurance Team	Yes
	No payment has been made for costs incurred prior to the start date, or after the end date of a funding agreement or contract	Yes
FOREIGN CURRENCY COMMITMENTS (4.05)
	Programmes with foreign currency commitments had the necessary approvals in place prior to signing the formal funding arrangement	N/A
PROGRAMME CONTRACT APPROVAL (5.01)
	For all contracts under £122k, procurement has been carried out by a DPO	N/A
	For all contracts under £122k, the contract has been signed by a DPO	N/A
	For all contracts over £122k, procurement has been led by the Programme Delivery commercial team	Yes
CONTRACT MANAGEMENT (5.03)
	Contract managers are all appropriately trained through the Contract Management Capability Programme (all staff managing bronze contracts must have Foundation level; all staff managing silver contracts must have Practitioner level)	Yes
	If staff are unable to take expert or practitioner course, commercial capability team have been notified	Yes
	All contracts over £5m have at least 3 SMART KPIs to ensure performance management and VfM	Yes
ODA COMPLIANCE (4.06)
	All programme ODA spend is in line with the OECD ODA rules, as per the PROF Guide	Yes
CONCEPT NOTES (CN) & BUSINESS CASES (BC) (3.05 & 3.06)
	A valid, signed off concept note is in place	Yes
	A valid, signed off business case is in place	Yes
	The BC includes a proportionate statement on impact of the programme on gender	Yes
	The BC includes a summary of how the partnership principles will impact the programme	Yes
	The BC includes a summary on how the programme aligns with the Paris Agreement	Yes
ANNUAL REVIEWS (AR) (3.09)
	All ARs due have been signed off at the appropriate level	Yes
	All ARs due have been completed and signed off on time (or any deferrals have been signed off)	Yes
	All ARs due have measured progress against an agreed results framework	N/A
	All ARs due have used the appropriate template	N/A
PROGRAMME COMPLETION REVIEWS (PCR) (3.10)
	Completed programmes have a valid PCR signed off at the appropriate level	N/A
	PCRs due have been completed and signed off on time	N/A
	For PCRs due, progress has been measured against an agreed results framework	N/A
	For PCRs due, the correct template has been used	N/A
PROGRAMME UNDERPERFORMANCE (3.11)
	For ARs that scored a C or second consecutive B a performance improvement plan (PIP) is in place, or an alternative plan of action has been agreed	N/A
	For all PIPs that were live, a decision has been made at the appropriate level regarding the continuation, restructure or closure of a project/programme; or the PIP has a fixed timeframe for such a decision to be made	N/A
PROGRAMME FINANCIAL CLOSURE (3.12)
	All audited accounts and financial statements covering the full duration of the programme have been received	N/A
	Financial reconciliation, including full payment of funds due and recovery of unspent monies, has been completed	N/A
	All liabilities have been extinguished	N/A
	All assets disposed of represents value for money with a clear record of decision making	N/A
FRAUD AND SAFEGUARDING (1.01 & 1.02)
	To the best of our knowledge, all known instances/suspicions/allegations of fraud and/or the misuse of funds have been reported to the Fraud Investigations Team at reportingconcerns@fcdo.gov.uk	Yes
	To the best of our knowledge, all known safeguarding concerns related to our programmes have been promptly reported to the Safeguarding Investigations Team within Internal Audit Department at reportingconcerns@fcdo.gov.uk	Yes
OVERSEAS SECURITY AND JUSTICE ASSESSMENTS (3.07)
	An Overseas Security and Justice Assistance (OSJA) assessment is in place for all programmes in the Justice or Security Sectors	N/A
PUBLIC SECTOR EQUALITY DUTY (PSED) (2.08)
	Programme is covered by a valid Public Sector Equality Duty (PSED) assessment	Yes
PROJECT FUNDED POSTS (3.15)
	All project funded posts are essential for delivery and better VfM than an outsourced alternative	Yes
	All plans to create new project funded posts were notified to CfD and Strategic Finance	Yes
SUPPLIER RECORDS (4.10)
	Approvers have thoroughly reviewed and approved any additions or amendments to supplier records based on their delegated authority and relevant policies	Yes
	Requestors have provided adequate supporting documentation and supplier maintenance forms to validate company information and verify bank details	Yes