Business Case – June 2023
Summary Sheet
Portfolio/ Business/Country Plan Summary: The UK became an ASEAN Dialogue Partner (DP) in August 2021 and agreed an ASEAN-UK Plan of Action (PoA) in August 2022, which sets out priority areas for ASEAN-UK cooperation over the next five years. The PoA responds to ASEAN and UK priorities and strategies, including the UK International Development Strategy (IDS) and the Integrated Review Refresh (IRR). This programme is part of a suite of new ASEAN-UK programmes the FCDO is designing to support PoA implementation and deliver on UK commitments as an ASEAN Dialogue Partner.
ASEAN Economic Integration Programme
Programme summary: / The programme will leverage expertise in UK institutions to support ASEAN member states (AMS) implement ASEAN initiatives that will reduce poverty in the region and in particular support women’s economic empowerment and small businesses. It aims to reduce barriers to development in AMS and the overall ASEAN Economic Community, to increase prosperity and provide the foundation for more inclusive economic development that benefits the poorest. / The programme will support reforms covering regulatory reform, financial services, and trade through technical assistance, capacity building and knowledge-transfer partnerships. It will look to harness the potential of digitalisation in ASEAN.
What is the rationale for UK Aid spending? (200 words maximum): / The Programme is aligned with the Integrated Review Refresh (IRR) and International Development Strategy (IDS). It will support the IRR objective to support an ‘open global economy’ and the IDS priorities to help developing countries “grow secure, open, thriving economies” and “improve economic security for girls and women”. It will take the approach to development set out in the IDS, including using “our world-class British expertise to support partner countries” and “accelerate digital transformation for all”. / The programme will support the commitment in the IRR to make the UK’s increased engagement in the Indo-Pacific into a permanent pillar of the UK’s international policy by demonstrating the UK’s long-term commitment to this region, delivering on our commitments as an ASEAN dialogue partner and providing expert development support to further bolster our bilateral and regional relationships. The UK has world-class expertise to offer across the programme focus areas – financial services, regulation and trade – and there is demand for support and collaboration from ASEAN.
Programme Value: £25m		Country/ Region or Sector: ASEAN
Department/Country Office confirmation of review processes		Development Director UKMis Amanda McLoughlin; UK Ambassador to ASEAN, Sarah Tiffin; SEAPD Director, Joelle Jenny
Contact name		Kenn Especkerman-True
Threshold for final approval of Business Case: DG Jenny Bates
Date of Approval of Concept Note:	21 Oct 2022	Name and role of Approver / Lord Goldsmith, Minister of State
Date of Approval of Business Case:	24 May 2023	Name and role of Approver / Jenny Bates, DG Indo-Pacific
Programme Code:	AMP Start Date: April 2023	AMP End Date: June 2029
Overall programme risk rating:	Moderate

Table of Contents

# A. Strategic Case

## Strategic context

### ASEAN Economies
Since its creation in 1967 and expansion in 1999, the Association of Southeast Asian Nations (ASEAN) has seen rapid economic development among its 10 members. Real GDP per capita in AMS grew by 3.5% on average from 2000-2021, compared to 2% for the world economy. The economy of ASEAN is the fifth largest in the world.
ASEAN countries are at different stages of economic development:
- Singapore and Brunei generally score highly on development indicators and are ineligible for ODA funding.
- Malaysia followed by Thailand, Indonesia, Vietnam and the Philippines are in the middle of their development journey. They are between the first and fourth quartile in most development indicators, share some of the same challenges and are all eligible for ODA funding.
- Cambodia, Lao PDR and Myanmar are the poorest countries in ASEAN, which is reflected in most development indicators. The ongoing conflict in Myanmar means that conditions for development there are worsening still. ASEAN agreed to Timor-Leste joining ASEAN at the ASEAN Leaders’ Summit in Cambodia 2022; Timor-Leste is now observing ASEAN meetings and undergoing an accession process, as set out in the ASEAN Accession Roadmap published after the ASEAN Summit in Labuan Bajo in May. When it officially joins, it will be in this category of the least developed economies.
Despite strong growth in recent decades, ASEAN faces a challenging economic context, including slowing global growth, high food and energy prices, and tightening monetary policy.
The ASEAN Economic Community (AEC) is one of three pillars of the ASEAN Community (alongside the ASEAN Political-Security Community and the ASEAN Socio-Cultural Community). ASEAN has agreed to strive for greater economic integration between member states, as set out in the AEC Blueprint 2025. This blueprint provides strategic direction for the AEC from 2016 to 2025, including a plan to transform ASEAN into a region with free movement of goods, services, investment, skilled labour, and freer flow of capital.
### Poverty in ASEAN Member States
The rapid economic development across ASEAN in the last 20+ years has helped reduce poverty in the region drastically. In Indonesia alone, the number of people living in extreme poverty (less than $2.15 a day) has fallen from 93 million in 2000 (43.6% of population) to under 10 million in 2021 (3.5% of population).
However, there are still 15.5 million people in AMS (plus Timor-Leste) who live on less than $2.15 per day and 99.9 million who live on less than $3.65 per day (World Bank, latest data 2017-2021). Women in the region are still more likely to live in poverty than men.[1]
[1] ASEAN Gender Outlook 2021
The reduction in poverty is fragile and vulnerable to reverse through economic shocks. The Asia Development Bank (ADB)[2] estimated that 4.7 million more people in Southeast Asia were pushed into extreme poverty in 2021 since the pandemic. The International Labour Organization estimates that there were 10.6 million fewer employed workers in the region in 2020 compared to a no-pandemic scenario. Employment losses were particularly hard on women, youth, and workers in micro, small, and medium sized enterprises (MSMEs). The employment gap is projected to remain at 9.3 million and 4.1 million jobs in 2021 and 2022, respectively. The ADB predict that the pandemic’s impact on poverty and unemployment will likely persist as inactive workers become de-skilled and poor people’s access to opportunities further deteriorates.
[2] https://www.adb.org/sites/default/files/publication/779416/southeast-asia-rising-pandemic.pdf
Table 1: Poverty levels vary between South East Asian countries
	Population	World Bank $2.15 measure	World Bank $3.65 measure	National poverty measure	GNI per capita 2021	Human Development Index 2021
Units	millions	millions (% population)	millions (% population)	millions (% population)	2017 PPP $	Value / (rank)
Singapore	5.5	0.0	0.0	0.0	90,919	(12) 0.94
Brunei	0.4	0.0	0.0	0.0	64,490	(51) 0.83
Malaysia	33.6	0.0	0.0	(8%) 2.8	26,658	(62) 0.80
Thailand	71.6	0.0	(1%) 0.5	(7%) 4.9	17,030	(66) 0.80
Indonesia	273.8	(4%) 9.5	(24%) 61.3	(10%) 26.6	11,466	(114) 0.71
Philippines	113.9	(3%) 3.3	(18%) 19.9	(17%) 18.1	8,920	(116) 0.70
Vietnam	97.5	(1%) 1.1	(5%) 5.0	(7%) 6.4	7,867	(115) 0.70
Lao	7.4	(7%) 0.5	(33%) 2.3	(18%) 1.3	7,700	(140) 0.61
Timor-Leste	1.3	(8%) 0.1	(43%) 0.5	N/A	4,461	(140) 0.61
Cambodia	16.6	N/A	N/A	(18%) 2.6	4,079	(146) 0.59
Myanmar	53.8	(2%) 1.1	(20%) 10.2	(25%) 13.0	3,851	(149) 0.59
Total	675.3	(2%) 15.5	(15%) 99.9	(11%) 75.6	-	-

Looking to the future, the factors that drove several decades of poverty reduction will not necessarily continue to contribute in the same way in future years. In most of Southeast Asia, agriculture accounts for proportionally less of the economy year on year and urbanisation will reduce agricultural growth’s influence on poverty. As the middle-income countries in the region move up the value chain, the role of unskilled workers in the economy is likely to change.
### UK – ASEAN Partnership
ASEAN has been an important partner for the UK in delivering the Indo Pacific Tilt. The UK supports ASEAN centrality and the vision for a free and open Indo-Pacific. Its Members States are some the world’s fastest-growing economies; we want to deepen our economic partnerships and work together to tackle global challenges, including climate change. The UK is a major trade, investment and development partner for Southeast Asia.
In August 2021, the UK became a Dialogue Partner (DP) of ASEAN – the only western European nation with this status. In September 2021, the UK and ASEAN issued the Joint Ministerial Declaration on Future Economic Cooperation between ASEAN and the UK. In November 2022, the UK and ASEAN Economic Ministers agreed a Work Plan to track activity in the Economic Pillar. In August 2022, we agreed the ASEAN-UK Plan of Action (PoA), outlining UK and ASEAN shared priorities across political, security, economic and global issues over the next 5 years. Twenty-one UK government departments/agencies are involved in delivering the PoA, coordinated by the FCDO. The Plan of Action and the Joint Ministerial Declaration on Future Economic Cooperation, with the associated Work Plan, are complementary.
### Programme Strategic Fit
The programme is aligned with the Integrated Review Refresh (IRR) and International Development Strategy (IDS). It will support the IRR objective to support an ‘open global economy’ and the IDS priorities to help developing countries “grow secure, open, thriving economies” and “improve economic security for girls and women”. It will take the approach to development as set out in the IDS, including using “our world-class British expertise to support partner countries” and “accelerate digital transformation for all”.
The IRR now commits the UK to go even further and ‘make this increased engagement [in the Indo-Pacific] stronger and enduring, and a permanent pillar of the UK’s international policy’. This programme will support these objectives by demonstrating the UK’s long-term commitment to this region, delivering on our commitments as an ASEAN dialogue partner and providing expert development support to further bolster our bilateral and regional relationships.
The programme will support key elements of the ASEAN Economic Blueprint and strategic goals 2 (Digital Innovation), 3 (Seamless Logistics) and 4 (Regulatory Excellence) in the Masterplan on ASEAN Connectivity. It will deliver on ASEAN policy and sector level strategies, such as the Bandar Seri Begawan Roadmap on Digital Transformation, the ASEAN Standards and Conformance Strategic Plan, the commitments in the ASEAN Trade in Goods Agreement and ASEAN Trade in Services Agreement and the scope of the planned Digital Economy Framework Agreement. It will seek to support the Initiative for ASEAN Integration (IAI) and delivery of IAI Workplan IV, particularly the strategic areas on trade facilitation and MSMEs. It will support Timor-Leste’s pathway to accession as set out in the Roadmap for Timor-Leste’s Full Membership in ASEAN. Where possible, it will also support the development of future ASEAN strategies.
## The Case for UK investment in ASEAN Economic Integration

### Spending Objectives
Intended impact: The programme aims to reduce barriers to development in AMS and for the overall ASEAN Economic Community, to increase prosperity and provide the foundation for more inclusive economic development that benefits the poorest in society.
The programme will leverage UK expertise to support AMS to work towards further integration of the ASEAN Economic Community (AEC), the largest integration effort attempted in the developing world. It will encourage open, free, fair and transparent trading practices, aligning to UK values.
A more prosperous and economically resilient ASEAN will also be better able to resist coercive economic influences in the region. Secondary benefits for the UK include creating a more accessible market for UK businesses, resulting in mutual prosperity, while championing our values in the Rules Based International System.
Intended impacts by pillar:

- Regulatory reform: Improved regulatory and standards system in AMS that are less bureaucratic, provide a more stable environment for business investment, and better protect workers and consumers, particularly the most vulnerable in society.
- Open Trade: lower barriers to trade (goods and services) between AMS and with the rest of the world, particularly for MSMEs
- Financial Services: wider access to financial services in AMS that enables greater financial resilience, particularly for MSMEs, and women.
### Theory of Change Outline
The three pillars will all contribute to the overall intended impact. In general, the pillars will have independent outcomes and so we will split the theory of change into the three pillars. We will look for ways to ensure activity is complementary between pillars. The pillar impacts are necessary conditions for inclusive economic growth, so overall success of the programme depends delivery of all three pillars.
The theory of change for each pillar will have the following structure:
- Activities: Technical advice, research and capacity building on regulatory reform, open trade and financial services
- Outputs: Reports, tools and policy/implementation recommendations about how to improve regulations, increase trade flows and improve access and development of financial services in ASEAN
- Outcomes (1-5 years): AMS adopt and begin to implement policy recommendations and reforms based on programme outputs
- Pillar impacts (3-10 years): Improvements in regulation, trade and financial services supported by the new ASEAN policies
- Overall Impact (10+ years): Inclusive economic growth that reduces poverty in AMS
The appraisal case sets out the theory of change in more detail for each pillar.
### Evidence Base
Regional Development Barriers
The FCDO conducted a Regional Diagnostic (RD) for the ASEAN region, which identifies factors that affect development and growth across AMS, informed by individual FCDO country diagnostics. It identified over 45 barriers that either affect two or more AMS or are cross-border in nature. They cover each of the five aspects of the diagnostic model: governance, inclusive growth, core state capability, social policy, and resilience.
The RD identified ‘five top barriers’ that affect 5 or more AMS and are particularly restrictive for development:  lack of voice and accountability, market access barriers, vulnerability to climate change, low domestic resource mobilisation and low levels of human capital. The RD further identified the five most important tractable barriers that UK can work with ASEAN to support development in the region: infrastructure financing gap, human capital (including education), low female labour force participation, ineffective disaster risk and humanitarian assistance response and preparation, and vulnerability to climate change (more detail in Annex A).
ASEAN Integration
The ASEAN Economic Community (AEC) is the largest integration effort attempted in the developing world. If realised, it will create a single market with the free movement of goods, services, foreign direct investment and skilled labour, and freer movement of capital encompassing over 650 million people. A 2011 study found that the AEC could yield benefits similar to those of the European Union, amounting to 5.3% of the region’s GDP and more than twice that if, as expected, the AEC leads to free trade agreements with key external partners.[3]
[3] https://www.brandeis.edu/economics/RePEc/brd/doc/Brandeis_WP13.pdf

Another paper uses dynamic computable general equilibrium (CGE) mode to make quantitative assessments of the effects on economic welfare, trade flows and sectoral output. When the removal of trade barriers is combined with reductions in administrative and technical barriers and lowering the trade and transport margins, the estimated welfare gains for the year 2015 range from 1.1% in Indonesia to 9.4% in Thailand. The results suggest that reductions in administrative and technical barriers (e.g. streamlining customs procedures and mutual recognition of product standards) and lowering the trade and transport margins (e.g. through increased competition and improvements in infrastructure) are significant in enlarging the benefits of the AEC.[4]
[4] http://www.osipp.osaka-u.ac.jp/archives/DP/2011/DP2011E002.pdf

Programme Focus Areas
The three focus areas of the Programme reflect ASEAN’s priorities in its Economic Community Blueprint and the UK Government’s areas of expertise and experience:
Regulatory Reform: The RD found that bureaucratic regulatory barriers are constraining growth, investment and entrepreneurship in multiple member states. This programme will improve the investment environment and the ease of doing business by increasing transparency, and simplifying, codifying and harmonising regulations, including competition regulations. This will include supporting ASEAN to reach internationally recognised standards. This will create a more stable, reliable environment for businesses to invest and flourish.

On the World Bank Ease of Doing Business Index for 2019 (has now been discontinued);  Myanmar (171) Lao PDR (154) – where it takes 174 days to start a business, Cambodia (138) -  where it costs 47% of income per capita to start a business and the Philippines (124) were the lowest scoring countries in the region.

Open Trade: The RD identified market access barriers as one of the top five barriers to development in ASEAN. The programme will work with AMS to address these and other barriers to trade across sectors to make moving goods and services across borders easier, more transparent and more accessible, especially for MSMEs. The approach will consider how ASEAN should use digital tools to address the challenges, leading to an increase in trade flows across AMS and help make supply chains more resilient.

Financial Services: The RD found that low levels of financial inclusion, shallow capital markets and weak investment frameworks hamper access to financial services and limit investment. The programme will improve accessibility to finance for the poorest in society through FinTech and digital payment systems, improve the processes behind cross border payments and remittance services, including data sharing, and improve financial literacy to increase access and investment leading to growth in the region.

Only a quarter of adults in ASEAN have full access to financial services, yet the region spends more time on mobile internet than any other globally. Across ASEAN, there are gaps in the breadth of services available, including investment products and insurance.  Most ASEAN nations lack deep and liquid capital markets and have a domestic focus. Bank lending is still the dominant form of finance, through equity and bond financing are slowly gaining traction.

FinTech adoption is growing rapidly, though there are many barriers to companies, including governments protecting their incumbent banks and competing with other ASEAN members (though some are linking up their payments systems).  International financial institutions face a number of barriers across the region, particularly 1) restriction on ownership and operation permits, 2) regulations on data, 3) restrictions in the (re) insurance sector, and 4) movement of labour.

The RD found that development of financial services is tractable and a relatively underserved space across dialogue partners. It is also one that ASEAN is keen to partner with the UK on, as it is seen as a leader in this sector. Singapore is very active in developing cross-border financial services across ASEAN, as are the MDBs like the World Bank and ADB.
Digitalisation and inclusion are two themes that will cut across our interventions in three pillars outlined above.
Digitalisation
A lack of digitalisation, differential access to digital services, cyber security deficiencies, and differing approaches to cross-border data exacerbate barriers to development. The programme will focus on introducing technology and innovation in all three pillars, drawing on UK expertise and existing activity like the UK-ASEAN Digital Innovation Partnership.

Inclusivity
For this programme, we will embed inclusivity into programme by targeting intervention to support women’s economic empowerment and MSMEs.
The RD highlighted low female labour force participation as one of five key issues that would be tractable with UK support. We know about persistent inequality within and between AMS where women are concentrated in the lower end of the value chain, in more traditional sectors, and often in more vulnerable work conditions[5]. Women are overburdened with care work and earn much less than men. The deviation in salaries amongst AMS is more than seven times than in the EU.
[5] UNWomen infographic
Several factors are at play here – traditional norms; limited access to skills, finance and markets; and lack of policies/ incentives for private sector to create more opportunities. Disaggregated data is not collected. Limited investments in enabling infrastructure such as safe transport, care work, have a direct bearing on women’s ability to access, pursue and economic options. We will design all activities to help narrow these gaps and ensure that marginalised groups can benefit, particularly women and girls.
The AECs “Equitable Economic Development” pillar highlights that MSMEs are key to narrowing the development gap across AMS.[6] Across AMS, MSMEs make up between 88.8% and 99.9% of total establishments and account for between 51.7% and 97.2% of total employment.[7] ‘Micro’ enterprises constitute a substantial number of enterprises in the AMS. However, definitions of MSMEs vary among AMS.
[6] https://asean.org/wp-content/uploads/2021/01/Final-SAP-SMED-2025-Update-in-2019.pdf
[7] https://asean.org/wp-content/uploads/2021/01/Final-SAP-SMED-2025-Update-in-2019.pdf https://www3.weforum.org/docs/WEF_ASEAN_Digital_Generation_Report_2022.pdf
The AEC brings benefits to MSMEs, through integration and openness to the global economy and opportunities to integrate with regional/global value changes. However, increased competition also presents a challenge and local MSMEs need support to improve productivity to harness the benefits. For example, the RD found that a lack of digital financial services products designed for SMEs, which are linked to barriers in financial technology.[8]
[8] https://www.weforum.org/agenda/2022/01/south-east-asia-sme-digitization-financial-services/; https://www.temasek.com.sg/content/dam/temasek-corporate/news-and-views/resources/reports/future-of-southeast-asia-digital-financial-services.pdf
## Key considerations for programme design

### Exiting Arrangements
This is a new programme but follows on closely from the ASEAN Economic Reform programme (AERP), which will have spent £19.6m over financial years 2018-19 to 2022-23. The AERP focused on business environment regulations and financial markets. It provides established relationships in the region and a strong record to build on.
As part of developing this business case, we conducted a lesson learning exercise with UK posts across the region to inform the design of this programme. We have taken these lessons forward in developing this business case, as well as lessons from the programme annual reviews. The AERP programme completion review is due to take place in June 2023 and we will adapt the programme based on its results.
ASEAN Accreditation
We will aim to accredit this programme with ASEAN so it is formally recognised under our ASEAN-UK Plan of Action. ASEAN have four requirements for accreditation:
1. Address challenges at the regional level and create synergy with other projects that are addressing the same issues;
2. Be of benefit to ASEAN, engage all AMS; adhere to the principles of the ASEAN Charter, including the ASEAN Centrality;
3. Aligns with the ASEAN Community Blueprints and other relevant ASEAN documents; and
4. Be endorsed by either the relevant ASEAN sectoral body/ASEAN body or the CPR, or both.

We are confident we can meet these requirements and will work closely with ASEAN bodies as we refine the programme to secure formal accreditation.
Approval of this business case at DG level will allow us to move into a formal ‘inception phase’ (see appraisal case), in which we will run procurement, do more detailed design work, and build the governance / management structures. The business case allows flexibility to co-design with ASEAN during the inception phase to secure accreditation.
The ASEAN requirement to engage all 10 AMS also creates a constraint on the programme:
- Singapore and Brunei are not ODA-eligible, but we will use non-ODA funding to facilitate their involvement and explore opportunities to collaborate with them on programme delivery.
- Myanmar will be included in the programme, however UK programme funds will not be used to benefit the current military regime. Where possible we will still look for opportunities to support non-state actors and provide assistance directly to the Myanmar people.
- In November 2022, ASEAN agreed in-principle to admit Timor-Leste to ASEAN. As such, it will now be incorporated into the programme, where the barriers to development and their tractability align.

### Gender Equality and Inclusion (G&I)
This programme will be an important vehicle to deliver the UK’s International Women and Girls Strategy in the region. The programme will incorporate a specific G&I strategy to both mainstream women’s economic empowerment across the three pillars and develop specific gender focused projects. We will use the inception phase to review the evidence available and to address any evidence gaps to identify the most effective G&I interventions. We will look to secure consistent FCDO G&I expertise to support the programme, building on the input already provided by social development advisers.
This programme will comply with the requirements of the International Development Act and the International Development (Gender Equality) Act 2014 to ‘have regard to the desirability of providing development assistance that is likely to contribute to reducing poverty in a way which is likely to contribute to reducing inequality between persons of different gender.’
Context: The RD found that low female participation in the workforce in Malaysia, Philippines, Myanmar and Indonesia leads to a reduction in potential output, sometimes due to cultural norms or a lack of education. The female share of the labour force in 2021 was 39% in Malaysia, 39% in the Philippines and Myanmar, and 40% in Indonesia, compared to 47% in the UK (in other AMS, rates are much higher). In Cambodia, women are more than twice as likely as men to have none or only some education and have much lower access to technical and vocational education. The employment rate is higher for men than for women, and women’s employment is more likely than men’s to be unpaid and vulnerable. In the Philippines and Indonesia, although girls perform better than boys at school, fewer women than men participate in the labour market.
In the Global Gender Gap Report 2022 of the World Economic Forum, AMS have an average rank of 77 out of 146 countries. The index captures gender-based disparities across economic, education, health and political criteria; only three AMS make it into the top half of the rankings – Philippines (19), Singapore (49) and Laos (53).
In November 2021, the FCDO ‘Work and Opportunities for Women’ Helpdesk was asked to review AERP to explore how G&I has been integrated into AERP, the challenges that had been faced and successes achieved. There is also some useful learning from the Prosperity Fund (PF) Evaluation and Learning report on the ‘Financial and Economic Reform Sector Summary’ from August 2020. Annex C contains the recommendations from both reports, which we have integrated into the approach set out below, including plans to build a G&I strategy / conceptual framework, source social development expertise to support the programme and commission research to build the WEE evidence base for each pillar.
What can we do: The programme will build in a strong focus on G&I across the three pillars with well-defined activities and results. For example, we will promote non-traditional jobs in non-traditional sectors thus helping break stereotypes; promote access to finance, soft skills and financial and digital literacy to help women grow in their jobs or their businesses; and advocate for more targeted polices / regulation.
We will do this by:
  1. Building evidence: investigating barriers to development in AMS linked to equality; designing interventions based on this evidence; requiring collection and analysis of gender disaggregated data (including quantitative data) where possible in project MREL;

  1. Programming: having ‘inclusion’ as a theme cutting across the three programme pillars, with well-defined results and allocation of finance and expertise; analysis of gender disaggregated data (including quantitative data) where possible in project MREL; considering the impact on gender norms at household, community or wider societal levels that could result from our interventions to assess the potential for any unintended negative consequences; securing access to technical expertise to effectively assess and monitor G&I work.

  1. Procurement: placing stringent requirements on delivery partners to incorporate G&I considerations and results into their plans; look for and act on opportunities to promote systemic change in the organisations that we are working with, either as suppliers or in other capacities; ensuring the programme has at least one programme intervention focussed directly on addressing barriers to women’s economic empowerment.

  1. Listening to women: Incorporating women’s voices throughout the design, delivery and evaluation phases of the programme; Ensuring female participation in consultations and other engagement activities, including individual participation and through community groups and women’s business associations.
This approach ensures the contents of the programme align with evidence on the issues women face in the business environment and financial services. This goes beyond the principle of doing no harm into actively pursuing interventions that address the issues women face. We will commission an in-depth analysis of constraints, opportunities and risks in the first three months of the programme to inform the design of the programme activities and ensure G&I is a focus at programme review points (e.g. programme boards and annual reviews).
### Disability
In all support, implementing partners will be expected to give due consideration to the particular needs and vulnerabilities of persons with disabilities, in accessing required information and support. We will make efforts to ensure that programme implementers engage with the relevant organisations representing persons with disabilities and promote better economic opportunities with them. The EIP will adopt a rights-based understanding of disability that explicitly recognises disabled people as a normal part of all social groups. The design of interventions will adopt a focus on barriers to disabled people, considering environmental, institutional and attitudinal barriers.
As part of AERP, the UNDP commissioned a report titled ‘Fostering Disability Inclusion and Business Integrity in ASEAN’. The report suggested a number of recommendations to support disability inclusion. We will look to incorporate some of these recommendations into this programme[9].
[9] These include raising awareness and capacity building of public and private sector entities in ASEAN countries regarding how to address disability inclusive business integrity in corporate compliance, procurement, employment, design of good and services and digital accessibility; promotion of employment and work experience in the open labour market; and advocating for the reform of national laws and policies in ASEAN countries to support disability inclusive business integrity principles
The programme will consider where it is appropriate to collect data that disaggregates by disability and look for opportunities to improve the knowledge base through commissioned studies that are disability sensitive areas and align well with the economic integration of ASEAN.
### Assurance Statements
Public Sector Equality Duty: The programme’s approach will include a specific focus on inclusion as a cross cutting theme across all interventions. In line with this, the programme will contribute positively to advancing equality of opportunities. Implementing partners will be expected to uphold standards and principles relating to non-discrimination and no harassment or victimisation, as well as international human rights provisions.
Climate and Environment: All countries in the region have a high vulnerability to climate risks, three of the top 10 countries affected by climate in the Global Climate Risk Index[10] were in ASEAN: Myanmar (2), the Philippines (4) and Thailand (9) were most affected. Vietnam and Cambodia were also in the top 15. We will look for opportunities to collaborate with planned ASEAN-UK climate programming, particularly within financial services pillar. There is potential for economic integration and reduction of market barriers in ASEAN to support sustainable economic growth, so we will consider if any activity can be classified as International Climate Finance (ICF).
[10] https://www.germanwatch.org/en/19777
Partnership Principles: The programme will provide bilateral support to AMS governments in the form of technical assistance, but it will not offer any direct budget support or financial aid. It will provide targeted technical assistance and expertise, in areas where we judge the likelihood of engagement and implementation to be high. Therefore, we do not expect the Partnership Principles to be relevant for the management and monitoring of programme activities very often, if at all, but we will continue to monitor this during delivery as we assess the specific activities and delivery mechanisms being proposed.
In Myanmar we judge that the current military regime is not committed to any of the Partnership Principles, and therefore UK programme funds will not be used to benefit the current military regime. Where possible we will still look for opportunities to support non-state actors and provide assistance directly to the Myanmar people.
Conflict and Fragility: Operations in fragile and conflict-affected parts of AMS will be designed in a conflict-sensitive way. This includes their resilience to deliver in the face of security concerns, violence and fragility. Strong central and post-based co-ordination efforts will be made to ensure the programme does not to provide any assistance which could benefit the military regime in Myanmar.
Risk: This project is expected to be moderate risk overall. A detailed risk register is included in the Management Case. The main risks are:
- Impact: interventions could lack impact if spread too thinly across multiple complex policy areas, given limited budget. Mitigation: evidence-based interventions that focus on UK expertise and where we have identified tractable barriers to development.
- Management complexity: the programme could become unmanageable given the challenges of monitoring and control of a regional multi-partner programme. Mitigation: streamline regional interventions where possible; limit the number of lead delivery partners; ensure robust monitoring and results frameworks are in place.
- Reputational: ODA budget changes and / or delays to procurement could undermine delivery and our reputation. Mitigation: work to confirm and maintain multi-year budgets; manage stakeholder expectations; build in contingency options for delays.
Counter Terrorist Financing: The risk of UK aid being diverted to support terrorist groups or activities is low. The programme will mostly use established international organisations or bilateral government channels to provide support. All implementing partners will have passed due diligence or fiduciary risk assessments and have a strong record of delivery. The FCDO programme team will identify, mitigate, and manage risks in accordance with a risk management framework.
Safeguarding: we avoid harm to people and the environment by encouraging partners to move beyond compliance to the minimum standard and commit to adopting comprehensive safeguarding practice and culture. Will monitor and mitigate safeguarding risks, including those related to Sexual Exploitation, Abuse and Harassment (SEAH), child protection, slave labour, trafficking and the environment. The programme will retain a focus on inclusive economic growth and will monitor impact. We will use careful financial control with delivery partners and subcontractors, and work in collaboration with political officers at Posts.
Working with Partners: we have consulted other ASEAN Dialogue Partners on their technical assistance offers to ASEAN and will continue to work with the through the programme to ensure complementary of interventions. We will also look for ways to collaborate on specific projects, although it is unlikely that we will look to joint-fund specific activity due to the complexity of managing such arrangements.

# Appraisal Case

The Appraisal Case includes the following:
1. Theory of Change pathway in which the programme will achieve intended impacts, and the evidence base supporting the channels
2. Option selection using critical success factors to inform a long list and short list identification and preferred way forward.
3. Value for money analysis appraises the preferred option to show Net Present Value for the programme in poverty reduction in AMS (through inclusive economic growth)

## Theory of Change (ToC)

### ToC Overview
We are developing the theory of change iteratively in collaboration with UK posts and departments in the region. Where possible, we will specify intended outputs before the programme formally starts. However, the programme will need to retain flexibility during delivery and so we will leave some outputs open for development after the formal programme start date. We continue to develop these outputs in collaboration with UK posts, delivery partners and the ASEAN Secretariat.
As set out in the strategic case the overall intended impact (over 10+ years) is that the programme reduces barriers to development in AMS to increase prosperity and provide the foundation for more inclusive economic development that benefits the poorest (i.e. poverty reduction).
We have split the theory of change into the three distinct pillars, as summarised below:
Programme impact	Reduce poverty in AMS through inclusive economic growth
Pillar impacts	Improved regulatory and standards system in AMS	Increased trade by AMS	Wider access to financial services in AMS
Outcomes	AMS implement policy recommendations that simplify, codify and harmonise regulations and standards.	AMS implement policy recommendations to lower barriers to trade across AMS	AMS implement policy recommendations to promote financial inclusion
Outputs	Reports, tools and policy/implementation recommendations that support AMS to implement ASEAN wide policies on regulation, trade and financial services.
Activities	Technical advice, events, research and capacity building on ASEAN policies related to regulatory reform, trade and financial services.

The overall logic behind the theory of change is that there are capacity and capability gaps in AMS governments for the implementation of ASEAN reforms and that the UK government can help fill these gaps through the technical specialists and institutional knowledge it has access to. There is good evidence that ASEAN economic integration has the potential to support inclusive economic growth in AMS and that further progress with integration requires wider ranging reforms across regulation, trade and financial services. There is also good evidence of demand for UK technical assistance from ASEAN and AMS from the Plan of Action and previous economic technical assistance programmes in the region.
There is less strong evidence for three assumptions underpinning the theory of change, which we will need monitor carefully. The first is that the programme can identify specific outputs under each pillar that are applicable to each AMS. The second is that the programmes can recruit experts that have the right specialist skill set to support the range of AMS, which have very different levels of capacity and capability. The third is that technical assistance will lead to policy implementation in AMS. See Annex D for more detail on assumptions.
Going forward, we are using three ‘filters’ to narrow down the theory of change and identify specific interventions:
Regional and Bilateral: ASEAN accreditation requirements mean we need to show there is a clear link between our programme and ASEAN initiatives. We also want to work bilaterally with individual member states as part of this programme. Therefore, we have chosen to focus our efforts on finding ASEAN-wide initiatives that will reduce poverty in the region, which we can support individual member states to implement. This provides a harmonious approach to working both regionally and bilaterally.

The ASEAN Economic Community Blueprint 2025 sets the strategic direction for ASEAN-wide economic policies. The ASEAN Trade in Goods Agreement and Trade in Services Agreement set the legal basis that implement the policies at a regional level; implementation or further liberalisation of these will be a measure of success in this programme. Each of the pillars will need to work with the relevant ASEAN working groups, who will each have their own strategic plan with more detailed policies (see detail below).

Inclusivity and Digitalisation: these two themes should cut across the three programme pillars. Therefore, we will only look for interventions that deliver outputs that harness digital technologies and support inclusion, with a focus on Women’s Economic Empowerment and MSMEs. We will use ASEAN’s Digital Masterplan 2025, Committee on Women Work Plan (Chapter 8) and Strategic Plan for SME Development to guide our approach.

Availability of UK expertise: the International Development Strategy set the ambition to harness “world class British expertise” in our development work. Identifying what UK expertise is available to deploy in the region (‘bottom-up approach’) is equally as important as understanding the largest development barriers in the region (‘top-down approach’). See the commercial case for more detail.

Across all pillars, we will look to support Timor-Leste’s accession to ASEAN, including helping them participate in ASEAN committees that we are work with under each pillar. For example, we could support them to gather and report basic data to ASEAN.
### ToC by Pillar
The following sections sets out the theory of change for each pillar, using the approach set out above. A detailed version of each theory change is included in Annex D.
Regulatory Reform
Problem statement: the Regional Diagnostic found that bureaucratic regulatory barriers are constraining growth, investment and entrepreneurship in multiple member states.
Complex and inconsistent regulatory environments are widely considered to be a significant barrier to business and economic growth. In ASEAN’s mid-term economic review, harmonisation of standards and regulation came out as the second biggest barrier facing business, with 36% and 39% of domestic and foreign businesses surveyed highlighting it as an issue. / NB Timorese regulations are poorly aligned with ASEAN’s and the economy is not well prepared for ASEAN integration.
Pillar impact: Improved regulatory and standards system in AMS that are less bureaucratic; provide a more stable environment for business investment; and better protect workers and consumers, particularly the most vulnerable in society.
Several studies have proved a strong correlation between good regulation and economic growth, achieved when programmes of reform change companies’ behaviour to enhance investment and encourage innovation. / Potential metrics: OECD ease of doing business replacement metric, ASEAN working committee metrics
Outcomes: AMS adopt and implement policy reforms, informed by UK expertise and in line with international standards, that simplify, codify and harmonise (or mutually recognise) regulations and standards. These policies will be tailored based on a consideration of their impact on woman and girls and vulnerable members of society.
Regulatory reform has been recognised as a cross-cutting theme that will support economic integration across ASEAN and underpins various high-level ASEAN strategies. The Office of Product Standards and Safety (OPSS) in the Department of Business and Trade (DBT) is working with FCDO posts and ASEAN to identify specific ASEAN initiatives we could support. These will likely cover Better Regulation, Consumer Protection and E-Commerce, and Standards. / Potential metrics: Number of policy reforms introduced by AMS, in line with ASEAN strategies and programme recommendations.
Potential outputs: Technical assistance to AMS government officials and ASEAN bodies, including guidance on good regulatory practice, supporting the development and harmonisation of new laws, policies and standards across ASEAN, improving the delivery (enforcement) of regulation and the development of better government/business/citizen consultation and engagement.
We have started engagement with the ASEAN Committee on Consumer Protection (ACCP) and the ASEAN Consultative Committee on Standards and Quality (ACCSQ) to discuss potential areas for co-operation. We plan to commission research to address knowledge gaps and understand the intersection of gender equality and regulatory reform activities. / There is good evidence from the AERP that technical assistance can fill capacity gaps in AMS and there is a strong demand from stakeholders to continue this work. The AERP regulation project supported partner governments with the implementation of 13 new or revised laws, regulations, rules and administrative practices. / Outputs will align with the Plan of Action 2.1.6 (regulatory improvement) and 2.2.10 (standardisation). / Potential metrics: Number of reports / tools / recommendations; Feedback from beneficiary organisations in AMS

Open Trade
Problem statements: the Regional Diagnostic identified market access barriers as one of the top five barriers to development in ASEAN.

Pillar impact: increased trade between AMS, and between ASEAN and the rest of the world, particularly for MSMEs and in digital trade.
Trade is recognised as an engine for inclusive economic growth and poverty reduction in the 2030 Agenda for Sustainable Development. Best Buys evidence has reducing cost of trade (e.g. anti-competitive behaviour, regulations) as a great buy, given the benefits of increased trade the potential benefits are high, for limited financial cost. / Potential metrics: ASEAN trade flows
Outcomes: AMS adopt and implement policy recommendations and reforms to lower barriers to trade across AMS, targeting barriers related UK specialisms, including intellectual property rights, competition policy and / or digital trade procedures.
Harnessing the benefits of trade is a core part of the AEC project and ASEAN has many initiatives that aim to reduce trade barriers. Outcomes for this pillar are less detailed than the other pillars at this stage, partly because there is less previous programme work to build on. It is also a relatively crowded donor space. Therefore, we are taking time to consult with ASEAN and UK Posts to identify areas of UK comparative advantage where ASEAN wants support. We will also conduct business consultations (including with the UK-ASEAN Business Council) and commission further research during the inception phase to narrow down our proposed offer. / Potential areas of focus include: / - Intellectual Property (IP) enforcement: ASEAN is keen to build up their IP systems to support their businesses, innovators, creators and attract foreign investment. The ASEAN Intellectual Property Rights Action Plan sets out plans to strengthen online IP enforcement in particular, giving the growing importance of e-commerce in the region. / - Competition policy: effective competition policy can help address trade barriers that arise from anti-competitive behaviour and unfair trade practices. ASEAN acknowledges that operational and effective rules on competition are necessary for ASEAN to be a competitive region with well-functioning markets and has an ASEAN Competition Action Plan (ACAP) 2016-2025[11] / - Digital trade: The ASEAN Bandar Sri Bagawan Roadmap sets out their cross cutting a Digital Transformation Agenda to support ASEAN trade. This area aligns well with UK expertise, although it is a crowded donor space, and we are still identifying the barriers to development we could target. / Potential metrics: Number of policy reforms introduced by AMS, in line with ASEAN strategies and programme recommendations.
Potential outputs: Technical assistance to AMS government officials to support implementation of polices that lower barriers to trade in ASEAN.
We are working with the UK IPO and DBT to better define the programme focus areas with ASEAN. In particular, we are working the ASEAN Competition, Consumer Protection and Intellectual Property Rights Division and Digital Economy Division. / The UK IPO are working on a proposal to improve ASEAN’s IP ecommerce environment by strengthening IP enforcement policies and practices and enhancing IP skills of creative businesses. The Competition and Markets Authority is running a series of workshops this year with the ASEAN Experts Group on Competition (AEGC), which we will look to build on if we choose competition policy as a programme focus area. / Detailed outputs are open for development after the formal programme start date. These will align with the Plan of Action: 2.1.2. (open multilateral trading system), 2.1.8. (ASEAN-UK Digital Innovation Partnership), 2.2.4. (trade links), and 2.1.11. (Intellectual Property Rights). / Potential metrics: Number of reports / tools / recommendations; Feedback from beneficiary organisations in AMS

Financial Services
Problem statement: the RD found that low levels of financial inclusion, shallow capital markets and weak investment frameworks hamper access to financial services and limit investment
Financial inclusion is uneven among AMS. For example, the percentage of adults with an account at a financial institution—a key financial inclusion indicator for usage—is much lower among Least Developed Countries in ASEAN
Pillar Impact: wider access and usage of quality financial services in AMS that enables greater financial resilience, particularly for MSMEs, and women and girls
It is widely accepted that financial sector development is important for economic growth. The financial sector plays a key intermediation role in allowing the mobilisation of savings for investment; facilitating and encouraging inflows of foreign capital; and optimising the allocation of capital to the most productive use. FCDO Best Buys identifies financial sector development as a high potential intervention; modest amounts of technical assistance can unlock substantial amounts of finance. / Potential metrics: average financial exclusion (ASEAN aim is to reduce from 44% to 30% by 2025)
Outcomes: AMS adopt and implement policy recommendations and reforms that promote financial inclusion, access, and resilience in the region, particularly for MSMEs and women.
The ASEAN Working Committee on Financial Inclusion (WC-FINC) works to meet ASEAN’s financial inclusion targets, as set out in the ASEAN Economic community blueprint 2025 and 2016-2025 ASEAN Strategic Plan for Financial Integration. This programme will identify financial inclusion initiatives within WC-FINC and other ASEAN working committees that could benefit from support from UK experts. / Potential metrics: Number of policy reforms introduced by AMS, in line with ASEAN strategies and programme recommendations; financial inclusion infrastructure readiness (ASEAN aims to increase from 70% to 85% by 2025)’
Potential outputs: Technical assistance to AMS government officials and ASEAN WC-FINC on policy implementation, including on adoption of ASEAN wide frameworks on FinTech, development on national financial inclusion strategies and implementation of polices in individual AMS.
We have started initial engagement with WC-FINC to discuss potential areas for co-operation. We plan to commission research through UKMIS as part of the wider ‘ASEAN-UK Collaboration on Financial Services’ to address knowledge gaps and better understand barriers for Women and MSMEs. / There is good evidence from the AERP that technical assistance can fill capacity gaps in AMS on financial services and there is a strong demand from stakeholders to continue previous work. / Detailed outputs are open for development after the formal programme start date. Outputs will align with the relevant parts of the Plan of Action 2.3.1. (financial development and integration, including financial inclusion), 2.3.2. (sustainable finance), 2.3.5. (digital economy including FinTech and financial inclusion), 2.3.6. (sustainable financial services) and 2.3.7. (financial services digitalisation). / Potential metrics: Number of reports / tools / recommendations; Feedback from beneficiary organisations in AMS

## Options Selection

### Critical Success Factors
HM Treasury guidance recommends using critical success factors (CSFs) as a tool for programme design. Critical success factors are the attributes essential for successful delivery of a programme, against which the initial assessment of the options for the delivery of the programme will be appraised, alongside the spending objectives. The critical success factors for the programme must be crucial, not merely desirable, and not set at a level that could exclude important options at an early stage of identification and appraisal.
We are using CSFs to design the ASEAN Economic Integration Programme (EIP), first at a whole programme level and then to help select specific projects. The programme is working in a complex environment and is trying to deliver multiple outcomes with limited funds. The CSF will support prioritisation throughout design and delivery.
Below are the six factors that will be critical for successful delivery of EIP. Annex E sets these out in more detail, including how we will use the CSFs for project selection.
The programme (and each project within it) must:
Achieve the primary spending objective of poverty reduction in South East Asia:
  1. Does it fit with outline theory of change for open trade, regulatory reform or financial services and address barriers to economic development?
  1. Is the evidence to support intervention strong enough?
  1. Does it focus interventions on inclusivity and / or digitalisation?

Fit with our wider strategic approach in the region:
  1. Does it meet all of the ASEAN accreditation criteria and/or is it flexible enough to respond to ASEAN steers on strategic direction?
  1. To what extent does it support the ASEAN-UK Plan of Action?
  1. Does it fit with the Integrated Review Refresh, the UK’s International Development Strategy and country plans in the region?

Optimise value for money:
  1. Is it an effective, cost effective, efficient, economical, and equitable way to achieve our theory of change?

Match supplier capability and capacity:
  1. Are there delivery partners with genuine expertise available to work in the region?
  1. Does it harness particular UK specialisms and areas of expertise?

Be affordable within our budget:
  1. Are costs within our ODA and non-ODA allocations, and factor in the need to spend some ODA as CDEL?
  1. Is spend flexible to respond to future allocations?

Be achievable given available programme resource and deadlines:
  1. Is the programme management burden sustainable?
  1. Can projects be started and completed within acceptable timescales?

### Long List Identification and Short List
The HMT Green Book recommends using the ‘Options Framework’, which provides a structured approach to identifying and filtering a broad range of options for delivering programmes and projects. It identifies and filters choices for the operational scope (what), service solutions (how), service delivery vehicles (who), implementation timeframes and funding mechanisms for the programme.

The first stage is identifying a long list of options under a series of programme design areas (see Annex E). The next stage is to use the critical success factors to identify preferred solutions for each design area, which when put together create an overall ‘preferred way forward’. We then created alternative options by iterating the design choices to identify other viable ways of meeting the critical success factors.

We conducted a workshop on 1 March 2023 with the South East Asia Economics Network, supported by programme design experts. The results of that workshop, and subsequent follow up discussions, produced the following delivery options:

Option	Description	Comments
Preferred way forward	The programme will leverage expertise in UK institutions to support AMS implement ASEAN initiatives that will reduce poverty in the region and in particular support women’s economic empowerment, MSMEs and digitalisation. / The focus in year 1 (FY 2023/24) will be on programme inception, with activities generally expected to start from October – April 2024 onwards. / We will work with UK public sector institutions and departments wherever possible, so that the programme is sharing UK experience / expertise and supporting the PoA delivery throughout. The programme will outsource to external delivery partners - including to private sector, multilaterals and NGOs - where departments do not have the capacity to deliver directly. / Each pillar will have a single lead delivery partner. The preferred way forward for each pillar is: / Regulatory Reform: the Office for Product Standards and Safety in DBT (xBEIS), supported by the British Standards Institute and in country contractors. / Financial Services: outsource to external provider, with light touch input from the Financial Conduct Authority and the Bank of England. / Open Trade: outsource to external provider, with support from the Intellectual Property Office (IPO), DBT and other specialist UK public sector institutions where relevant. / UKMIS ASEAN will retain overall programme management to ensure the programme is an integrated part of the UK-ASEAN relationship, in close coordination and consultation with the ASEAN Secretariat. This will also enable us to allocate sufficient programme management to ensure compliance with FCDO policies and programme management rules. We will consider secondments into ASEC as part of this option.	This represents the preferred strategic direction for programme delivery and a series of working assumptions about how it will operate in practice. / It is a balance between the contrasting options set out below; it gives the programme the ASEAN focus that ministers intended while proving a simple mechanism to work through bilateral channels. / While all options assume we adopt best practice in programme management, this option articulates the particular route we think is most likely to meet the critical success factors across a range of design choices (see vfm section). It incorporates the lessons learned from previous regional programmes. / We have selected the delivery model and delivery partners based on the principle that we should work through UK public institutions where possible, while acknowledging the limited delivery capacity of many public bodies for direct international development work. Having three lead delivery partners balances the need for access to niche expertise and the need for simplicity given limited FCDO programme management resource. / We will do further design work during the inception phase to iterate design choices based on more detailed scoping, feedback and evidence. We will look to identify interventions with partners across government, ASEAN partners and delivery partners.
‘Do minimum’	A minimum viable programme would: / Enable UK departments and contractors to work directly with the ASEAN Secretariat (ASEC) only, on specific projects identified in advance as part of the plan of action. We could outsource projects on a case-by-case basis to meet ASEC’s needs. / We would delay the business case until we have identified projects under each pillar in year 1.	This realistic way forward meets the core requirements of the concept note with the minimum amount of FCDO action and spend. / It acts as a comparator to more ambitious options and a benchmark for VfM.
Focus on ASEAN bodies and accreditation	Another option is to focus on meeting ASEAN’s needs: / We could follow some other ASEAN donors and create a demand-led model to support the ASEAN secretariat and bodies directly, with no / limited bilateral work with member states. The FCDO would retain control of the programme funds and source delivery partners to work directly with ASEAN institutions, with no / limited bilateral work with member states.	This approach would narrow the scope of the programme to focus on ASEAN as an organisation, rather than the individual member states. / It provides a viable alternative to the preferred way forward. It has a similar delivery model to ‘do minimum’, but is solely focussed on meeting the demands of ASEC and other ASEAN bodies.
Focus outcomes at country level	An alternative would be to maximise focus on development impact and specific bilateral priorities in each member state individually. / We would outsource each pillar to a provider who can work with each post to shape activity in each member state, with little coordination or alignment between the various bilateral activities.	This option more closely matches the approach of previous economic programmes in the region (e.g. the AERP).

## Value for money analysis

### Review of delivery options
	Critical Success Factor					Total Score
Low = 1 / Medium = 2 / High = 3	Optimise Value for Money	Achieve poverty reduction in South East Asia through ToC	Match supplier capability and capacity	Be achievable and affordable	Fit with strategic approach in the region
Do nothing	Medium (2) / Zero monetary cost so resources could be allocated elsewhere	Low (1) / Will not achieve impact.	Low (1) / Loss of strong relationships built through previous programmes	Medium (2) / Achievable	Low (1) / Missed opportunity to strengthen DP status and support direction and development of economic reforms.	7
Do minimum	Medium (2) / Lack of country level engagement reduces effectiveness. / Slower start to programme activities may miss key opportunities to maintain suppliers, but slower development may pay off in stronger delivery.	Low (1) / ASEAN secretariat only gives regional barriers focus which may be less effective at targeting key populations	High (3) / Outsource projects on a case-by-case basis may mean a more focused fit with suppliers.	Medium (2) / Achievable	Medium (2) / Scores highly on fitting with the ASEAN accreditation criteria, but does less well on meeting IDS and country business plans in the region.	10
Preferred way forward	Medium (2) / Potential to be highly effective. Outsourcing downstream activities through UK government partners may increase administration costs	Medium (2) / FCDO maintaining focus on ToC, working with government partners	Medium (2) / Model uses bespoke mix of HMG expertise and external providers, with strong emphasis on selecting delivery partners that have depth of expertise	Medium (2) / Working with UK government partners offers simplicity, as does limiting the number of lead delivery partners. Time required to issue commercial tender may delay parts of programme.	High (3) / Highly aligned with strategic approach	11
Focus on ease of ASEAN accreditation	Low (1) / Lack of county engagement reduces effectiveness. Increased costs compared to do minimum	Medium (2) / ASEAN secretariat only gives regional barriers focus which may be less targeted to key populations	Medium (2) / Demand led model may prove more difficult to effectively match suppliers and pool of experts to ASEAN needs	Low (1) / Likely to have high resource burden given ad-hoc and demand led projects.	Medium (2) / Scores highly on fitting with the ASEAN accreditation criteria, but does less well on meeting IDS and country business plans in the region.	8
Focus outcomes at country level	Medium (2) / Potential to be highly effective at meeting impacts in country, but has risks on feasibility and increased costs	High (3) / Country-level delivery model allows programme to best influence and reduce poverty	low (1) / May struggle to find supplier with breadth of contacts across countries	Low (1) / Risks around delivery	Low (1) / Inherent risks of not getting accreditation	8

### Quantification of costs and benefits

To estimate programme benefits, we used an appraisal model to quantify economic and poverty reduction benefits for each pillar. We have been able to quantify benefits for the Financial Services and Regulatory Reform pillars. The discounted monetised benefits compared to costs give the following overall Net Present Value (NPV):

 Table 2: Overall value added of EIP over 10 years
	10 Year Primary NPV (£m)
Central estimate	47 / (+Open Trade benefits)

The programme will also support non-monetised secondary benefits in addition to the monetised primary benefits. The most notable of which being increased UK trade from a strengthened more prosperous ASEAN. In addition, EIP supports benefits to the UK ASEAN Dialogue Partner status

Summary of costs: The total programme cost central estimate is £18.3 million (between £6.8 million lowest estimate and £25 million highest estimate.

Summary of benefits: Regulatory Reform: A series of studies have analysed the relationship between the business environment as a whole and macroeconomic performance. Haidar (2012) estimates the size of this relationship with each reform giving 0.182 percentage point increase in economic growth. The project targets 7 reforms across countries over 4 years. When adjusted for GDP forecast data from the IMF, UK’s likely contribution to reforms as part of a multi-donor effort in the countries and success rates for each targeted reform. The resulting benefits focusing on those under the national poverty line gives the overall benefits for each country, with an additional overall ASEAN integration benefit.

Summary of benefits: Financial Services: As outlined in the ToC, financial sector development affects economic growth, which can lead to poverty reduction. To estimate the benefits for those under the national poverty line, remittances are used as a proxy of financial services with empirical evidence suggesting that a 10% increase in remittances are associated with a 0.66% permanent increase in GDP in developing countries. Similar to regulation pillar, the methodology uses GDP forecast data from the IMF, UK’s likely contribution on reforms as part of a multi-donor effort in the countries and success rates for each targeted reform, along with assumptions regarding reduced transactions costs being used to increase remittances (table 3).

Table 3: Financial Services - remittance data for some ASEAN countries
Country	Inward remittance flow as % GDP	Average cost	Average cost as % GDP
Cambodia	4.4%	13%	0.568%
Indonesia	0.8%	6%	0.049%
Lao PDR	1.2%	13%	0.162%
Malaysia	0.4%	6%	0.022%
Philippines	3.2%	5%	0.155%
Thailand	9.5%	8%	0.753%
Vietnam	1.8%	7%	0.128%

Summary of benefits: Open Trade: For assessing impacts in open trade, we will use the OECD Trade Facilitation (TF) Indicators. The OECD Trade Facilitation Indicators allows countries benchmark and improve their border procedures. The OECD TFIs cover the full spectrum of border procedures for more than 160 economies across different income levels, geographical regions, and levels of development. Each TF indicator is composed of several variables related to existing trade-related policies and regulations and their implementation in practice. This programme could focus on TFI areas with the lowest performance at ASEAN level.

The OECD report on the Potential Impact of Trade Facilitation on Developing Countries' Trade presents findings of the indicators for assessing the impact of specific trade facilitation measures on developing countries’ trade. Sixteen Trade Facilitation Indicators (TFIs) correspond to the main policy areas under negotiation at the WTO. These show how TFIs contribute to the variance of bilateral trade costs. Each of the indicators were evaluated to determine the highest impact (estimated potential reductions in trade costs).

Sensitivity Analysis

Sensitivity analysis was conducted on the NPV appraisal. This tests assumptions regarding the size of the impact of reform, number of reforms to successful reforms, remittance cost decreases and UK additionality, these variables were adjusted to test sensitivity in a higher and lower scenario. Adjusting all assumptions +/-10% gives a range of scenarios for the NPV from £20 million to £68 million. Therefore, the programme represents good VfM across a range of outcomes.

Table 4: Sensitivity analysis for NPV (minus Open Trade benefits)
Scenarios	NPV £m
High	68
Central	47
Low	20

Assumptions	High	Central	Low
Additionally factor UK	0.011	0.010	0.009
Impact of reform on GDP growth rate	0.190	0.173	0.156
Conversion of number of reforms to successful reforms	28%	25%	23%
10% remittance increase to GDP	0.73%	0.66%	0.59%
Remittance cost decrease	0.11%	0.10%	0.09%

# C. Commercial Case
The Commercial Case includes the following:
1. Commercial strategy sets out the overall approach to selecting delivery partners.
2. Delivery partner arrangements by pillar explains the preferred commercial structure for each pillar.
3. Value for money proposes metrics to help ensure funds are well spent.

## Commercial Strategy

### Delivering the Preferred Way Forward
The preferred way forward identified in the appraisal case is to use the programme to leverage expertise in UK institutions to support AMS to implement ASEAN initiatives that will reduce poverty in the region. The focus in year 1 (FY 2023/24) will be on programme inception, with technical assistance activities generally expected to start from October to March 2024 onwards.
We are currently scoping the best delivery partner(s) for each programme pillar using the critical success factors identified in the appraisal case. There will need to be flexibility in deployment to adapt to (i) emerging priorities and requirements from ASEAN stakeholders, (ii) potential future changes in budget and (iii) lessons learned through delivery about where impact is highest (both thematically and geographically).
We will work with UK public sector institutions and departments wherever possible, so that the programme is sharing UK experience / expertise and supporting the PoA delivery throughout. The programme will outsource to external delivery partners - including to private sector, multilaterals and NGOs - where departments do not have the capacity to deliver directly.
Each pillar will have a single lead delivery partner. The preferred way forward for each pillar is:
- Regulatory Reform: the Office for Product Standards and Safety in DBT (formally BEIS), supported by the British Standards Institute and in-country contractors.
- Open Trade: outsource to external provider via FCDO procurement framework, with support from the Intellectual Property Office, DBT and other specialist UK public sector institutions.
- Financial Services: outsource to external provider via FCDO procurement framework, with light-touch support from the Financial Conduct Authority and the Bank of England.
Each of the pillars will be largely independent and managed separately. This will help us source the right expertise to deliver specialist projects, rather than requiring a generic delivery partner to sub-contract across multiple broad themes, which could result in complex delivery mechanisms (which proved problematic under AERP and was a key lesson). The programme management team in UKMIS ASEAN will ensure coordination and synergies between delivery partners. We will also consider recruiting for a cross-cutting coordination role to sit within ASEC (see management case).
Summary of the preferred approach:
Component	Budget	Procurement Route	Organisation
Regulatory Reform	£7.8m	MoU (Subject to outcome of Inception Phase)	Office for Product Standards and Safety in DBT (formally BEIS)
Open Trade	£7.8m	Direct Procurement via call-down under Framework/ Open Competition	TBC
Financial Services	£7.8m	Direct Procurement via call-down under Framework/ Open Competition	TBC
Programme Insourced Role in ASEC	£0.5m	FCDO recruitment	TBC
M&E	£1.0m	Direct Procurement via call-down under GEMFA	TBC
TOTAL	£25m

### Selection of Lead Delivery Partners
The majority of services required under the programme will be the provision of expertise through technical assistance. The programme is aiming to build capacity and knowledge for AMS and the ASEAN Secretariat to support them with policy implementation. We will require delivery partners to provide project management, stakeholder management and design functions.
We will use the critical success factors to assess delivery partners and commercial structures. In particular, we are looking to identify a combination of delivery partners that have:
1. In-depth technical skills and expertise to support the programme theory of change.
2. The ability to flexibly surge and deploy UK, international and regional/local TA based on demand and circumstances.
3. Strong, existing ASEAN regional presence with in-house capacity in many AMS and knowledge of ASEAN institutions, ways or working and approaches to engage and influence.
4. Robust delivery capabilities, with an ability to offer strong project and stakeholder management services, mobilise quickly and satisfy FCDO’s supplier requirements around monitoring and evaluation, due diligence, safeguarding, accountability and value for money.
We expect to run procurements to source lead delivery partners for both the Financial Service pillar and Open Trade pillar (see ‘Delivery Partner Arrangements by Pillar’ section below).
### Role of UK institutions
During design workshops, stakeholders agreed that the programme should draw on experts in the UK Government or other UK institutions where possible. This approach scored well across all the critical success factors.
For example, using UK Government experts helps ensure wider strategic fit, reduces programme management burden, helps build sustainable bilateral links with governments of AMS and ensures the UK gets recognition for the support. It also gives subject matter specialists in the partner departments the chance to shape the programme early in design and help the FCDO identify credible external providers to supplement internal efforts. This approach aims to support partners across government to deliver their commitments under the Plan of Action. The AERP demonstrated the high demand for UK expertise from our government stakeholders.
We will offer government departments, agencies and other UK institutions the chance to contribute to the programme through three ‘partnership models’:
Steering function: formal agreement to be part of a panel of UK experts that help shape a programme pillar, with the aim of ensuring consistency with their institutions wider work in the region and increasing effectiveness through provision of expertise.
The role would involve support for theory of change design, delivery partner selection (e.g. during early market engagement and procurement), quality assurance of outputs and occasional direct engagement with their counterparts in the region (e.g. to seek feedback).
Blended delivery: agreement to deliver some activity directly, such as workshops and seminars with counterparts in the region, alongside helping to identify complementary projects that can be delivered by external delivery partners. The FCDO UKMis ASEAN Programme Team will help blend internal and external delivery together to form a coherent pillar under the programme.

Lead delivery partner: agreement to deliver the majority of activity under a programme pillar, potentially in partnership with other UK institutions. Overall programme management and control would remain with UKMis ASEAN and the SRO, but the lead department / institution would lead on engagement with counterparts in the region and delivery of pillar outputs. The programme would provide the lead department / institution with a facility to procure additional delivery capacity if justified.
## Delivery Partner Arrangements by Pillar

### Regulatory Reform: Office of Produce Safety and Standards (OPSS)
The preferred option is that the Office for Product Safety and Standards (OPSS) in the Department for Business and Trade (DBT) delivers this pillar. OPSS is a leader of good regulatory practice in the UK and globally. They provide high-quality technical advice and capacity building support to overseas governments on regulatory reforms that support trade, investment, growth and environmental sustainability. OPSS (previously in BEIS) have a proven record in the region, having delivered the Regulatory Reform Project under the AERP.
We are in discussions with OPSS about a new project proposal for this programme (see Annex F), which builds on the achievements of the previous project under AERP. We have asked them to design a new ASEAN wide regulatory reform project that fits with the critical success factors for this programme. This is a complex task given the differences between the AMS and the very specific regulatory reform needs of each country. However, one of the main advantages of working with other UK Departments is ease of collaborative design. By working directly with OPSS, we are confident we can design a project that will meet the design criteria for this programme.
Previous experience: While the new project will need to differ from OPSS’s work under the AERP, we expect them to adopt a similar core delivery model in EIP. This allows us to build on the success and valuable lessons learned from the AERP project. We have summarised the previous approach below.
The AERP regulation project was delivered from 2019 - 2023, with a value of just over £1 million. The project aimed to improve regulatory environments in Philippines, Vietnam and Indonesia through strengthening approaches to design, implementation and delivery of regulation; and to improve regulatory efficiency, transparency predictability and harmonisation in ASEAN. The project worked bilaterally and supported the OECD-ASEAN Good Regulatory Practices Network. Outputs have supported the delivery of tangible results: the project has supported partner governments with the implementation of 13 new or revised laws, regulations, rules and administrative practices. Engagement with businesses has shown a general increase in optimism about progress on business environment reforms across all 3 partner countries.
The project completion report noted some relevant lessons learned. Government to Government support was noted to be highly valued by overseas counterparts: “OPSS and the UK Government, is recognised for its thought leadership, expertise and experience on regulatory reform and are the only donors who combine knowledge and funding, which is a strong, niche position valued by partner governments” (PCR, para 27). The project was able to draw on recent, relevant UK expertise and experience of reforms. “The ability to share UK experience, both the successes and the lesson learned, means that partner governments can often accelerate their reforms, avoid common mistakes, and in some cases leap-frog stages in the reform process” (PCR para 28). This delivery mechanism also provides the opportunity for mutual learning, which can be fed back into the UK’s regulatory policy and practices.
OPSS delivered the project using a hybrid model. OPSS experts and other delivery partners, supported by locally engaged ‘Regulatory Reform Attachés’, provided technical assistance virtually and in person. This model has proved highly successful, offering the possibility for flexibility and adaption when needed.
Partnership arrangements: the preferred option is to sign a Memorandum of Understanding (MoU) with OPSS, drawn up in compliance with the FCDO’s Programme Operating Framework. There is a dedicated template for use with Other Government Departments (OGDs), which served its purpose for the previous funding arrangement. Once agreed, the full OPSS Terms of Reference (built from their proposal) will be attached to the MoU as part of the agreement and will include all necessary documents such as a detailed activity based budget and logical framework.
The Terms of Reference will document the programme management function of OPSS. OPSS propose to adopt a similar hybrid delivery model for the project, involving local consultants, regulation attaches based in the region, reporting up through a programme office in Jakarta, and over-all oversight provided by the Assistant-Director for International Delivery from OPSS. The programme management function will need to be strengthened, due to the increase in project size and to meet the latest FCDO requirements. It will be necessary to have a senior project manager employed by OPSS to ensure proper oversight and compliance with FCDO requirements, and who will be responsible for reporting to the ASEAN UKMis Senior Programme Manager in charge of EIP.
The MoU will detail the mechanisms by which OPSS will be held accountable for project delivery. The current model has proven successful in this regard and will likely continue:
- Monthly meetings between OPSS and the Senior Programme Manager in charge of EIP for ASEAN UKMis. OPSS will be asked to minute these meetings and provide the record for agreement. These meetings are used to provide regular project updates, assess progress vs. objectives, highlight successes and challenges, assess risks/issues and whether spend is on track.
- Quarterly narrative and financial reports – a submission schedule will be agreed at project inception, and standard FCDO reporting formats will be used to ensure that all the necessary data is captured (including gender and inclusion, compliance with Paris Agreement etc). Checks will be made on whether the project is on track, with reconciliation against the agreed log frame deliverables and targets. If agreed outputs are on track the reports will be approved.
- Submission of invoices once delivery against targets is agreed.
Following the inception phase, FCDO / OPSS may source additional delivery partners for particular strands of work. Ideally, OPSS will retain overall oversight of the pillar and take on the programme management responsibility for any additional suppliers. This represents the ‘lead delivery partner’ (option 3) of partnerships models outlined above.
OPSS is the HMG sponsor of the British Standards Institute (BSI) and United Kingdom Accreditation Service (UKAS); they will work closely with both during the design and delivery of this programme. BSI have a strong existing relationship with ASEAN, having supported the ASEAN Consultative Committee on Standards and Quality (ACCSQ) through a separate programme.
Contingency: In the unlikely scenario that OPSS are unable to be the primary delivery partner for the Regulatory Reform Pillar, there are two further options:
(a) Hybrid delivery: OPSS will design and deliver a project but will not be responsible for delivery across the pillar. Where it is not possible or appropriate for OPSS to deliver on certain activity, then we will revert to a commercial procurement route. The Statement of Requirements for any commercial procurement would be reviewed with OPSS for their technical input and advice, and to ensure complementarity. The procurement process would be undertaken in collaboration with the commercial team to ensure fulfilment of the necessary requirements. In this scenario, careful consideration will be given to the over-all programme management function in terms of where this responsibility will sit and to ensure that it is properly resourced.
(b) Commercial supplier: If following the inception phase it is concluded that OPSS would not be the best option for delivery, we will pursue a commercial procurement for the regulatory reform pillar. The Statement of Requirements will require one supplier to take on sole responsibility for the pillar, and any sub-contracting arrangements should they become necessary. For this model of delivery, we would sign a contract specifying payment by results, with associated key performance indicators and penalties for non-performance. Programme management of a commercial contract should in theory be more straightforward than working through an MoU. However, for the reasons outlined above, a funding arrangement with OPSS remains the preferred option.
### Open Trade and Financial Services Pillars: External Supplier via FCDO framework
The preferred option: is that one external supplier delivers the Open Trade pillar and one external supplier delivers the Financial Services pillar, both likely sourced via a FCDO framework. We have not yet determined the exact route to market but we will comply with HMG Procurement Policy and FCDO best practice. Commercial procurement ensures fairness and transparency, including the publication of tender documents and contracts, reporting on key performance indicators, supporting the engagement and performance of the best suppliers, and driving value for money (PrOF principles, Rule 15).
The benefits of a commercial supplier include the ability to build in a programme management requirement, which in turn reduces the burden on the ASEAN UKMis Programme Management Team. Commercial suppliers contracted through the framework also partner with approved sub-contractors, which facilitates access to a broader range of expertise.
The drawback of commercial supplier is that the private sector can find it harder to build host government buy-in. Governments in the region generally have a high regard for UK Government impartiality and expertise and are open to our advice on regulatory, business and financial matters; this is also true for multilateral organisations. This was a challenge in the ASEAN Economic Reform Programme, with the
Sourcing and competition: The preferred procurement route is to use the FCDO General Economic Development Framework (GEDF). This framework is for economic development Technical Assistance services on call-down contracts above £5 million and up to 4 years. We expect these pillars to cost ~£8m each over 4 years. This route to market is the most efficient, as due diligence has already been completed, and a mini competition can be conducted in a relatively short period. Negotiation time is lower as suppliers have already signed up to the terms of the agreement. The tender process is like to take up to 12 weeks from issue of invitation to tender to selection of preferred bidder.
However, this framework will expire on 30th November 2023 and if we use this route, we must sign the contract before then. FCDO commercial expect a new replacement framework – Global Development Delivery (GDD) - to go live by 1 December 2023; procurement is currently on schedule. We estimate a 50% chance that we can sign the contract before 30 November for the Open Trade Pillar and a 75% chance for the Financial Services pillar, so this does represent a risk of a delay to delivery timescales (see contingency section below).
There is also a risk that none of the 13 lead suppliers on the GEDF have access to the specific expertise we need during this programme (e.g. networks in Southeast Asia). Subcontractor flexibility under this framework partly mitigates this risk - successful suppliers have the option of proposing sub-contractors distinct from those listed in their original tender if necessary, depending on the actual requirements of the future work. This provides SMEs and any future local suppliers the opportunity to participate. However, it is worth noting that in this scenario, more time may be needed to prepare bids if the lead suppliers need to source alternative supply chain members.
We ran an early market engagement (EME) exercise on the 11 May with 84 suppliers, which suggested high commercial interest in the programme. Suppliers were generally supportive of the programme aims and suggested delivery structure. They gave rich and varied feedback, which we will use to inform continued programme design. A few consistent themes emerged in feedback from suppliers: a strong demand for clarity on route to market and the provision of a Statement of Requirements as soon as possible to allow time to prepare bids; the need for specialist suppliers and / or a bespoke consortium to enable targeted interventions; and concerns that the scope of the programme could get too broad given requirement to work with all 10 member states plus Timor-Leste. Overall, the EME confirmed that our preferred approach is viable and gave us valuable recommendations for the inception period. In particular, we plan to facilitate networking between suppliers to support the formation of targeted consortia.
We will develop the Statement of Requirements (SoRs) in collaboration with FCDO commercial advisers to ensure requirements are clear to potential suppliers and to shape delivery model proposals that offer value for money. We will build in requirements based on the programme critical success factors. For example, suppliers will be required to show they can work with UK expertise and deploy across all AMS plus Timor-Leste. We will develop the SoRs and assess supplier proposal in consultation with partners across government and ASEAN bodies.
Contract Structure and Supplier Performance: A GEDF call off terms and conditions document will include (as a minimum): call-off start date, call-off end date, potential extension period, terms of reference, pricing and benefits.
The GEDF uses standard FCDO terms covering policies such as Expenses, Safeguarding and Due Diligence, ceiling fee rate cards from each supplier, and % discount rates for longer pieces of work, as agreed up front by the Framework suppliers as the maximum chargeable rate. The rates are based on maximum day rates based on an eight-hour working day. These rates are fixed for the life of the framework. This may present a barrier to suppliers bidding as they may prefer to wait for the new framework if rates are higher.
Our preferred option is to use payment-by-results contracting, given the programme requires agility and iterative objectives. The AERP has shown that the success of this approach rests with very careful design, noting that the higher up the results chain you choose to pay for results, the closer a programme is likely to be to achieving its outcomes. However, the selection and measurement of outcome level results can be very challenging (see PrOF guide on PbR Contracting). In the case of the large commercial contract under AERP, a hybrid model was adopted, built iteratively. The model, which focused on output level results, led to the creation of hundreds of milestones over the delivery period, which in turn created a heavy administrative burden for programme teams both for the delivery partner and for FCDO. This should be avoided with the new programme. Ultimately, the decision to use PbR will depend on whether there are suitable mechanisms to link payment to performance and delivery in some way (vs. results service levels, milestone or other appropriate performance indicators). This will be determined in close collaboration with our commercial advisers.
Contingency: given the risks and potential drawbacks to using the FCDO GEDF, we have prepared alternative options to retain under consideration during the inception phase.
- Option 1: Delay procurement for the Open Trade pillar until the new GDD is live (expected 1 December 2023). We are strongly considering this option, as it would give us further time to develop this pillar, which is the least developed of the three. To mitigate the delay, we would consider sourcing an NGO or consultant to support design work in June-December. This would enable us to draft a more specific SoRs for the eventual procurements and potentially speed up delivery post procurement. We would also consider running discrete pilot projects during the inception phase.
- Option 2: Delay both the Open Trade pillar and Financial Services pillar (using the same mitigations as option 1 across both pillars).
Option 3: Run a new competition (open or restricted tender). This would reach a wider pool of suppliers and increase the chances of finding a single specialist provider. This model may increase value for money by avoiding additional management costs associated with a consortium. However, a new competition would take 6-12 months from invitation to tender to delivery, thus significantly delaying timescales.
Option 4: Agree a grant agreement with a not-for-profit organisation. A grant agreement could be much faster, but we are yet to identify any suitable not-for-profit partners.
## Monitoring Value for Money
VFM means making the best possible use of all our resources to maximise our impact. This will include:
- Benchmarking of data will consider the use of capped rates, whilst being cognisant of the fact that we are sourcing specialist expertise. Data sources will be carefully considered working with our Commercial Team and would likely include reviewing current AERP governance agreements and mapping donor activity in regions where suppliers are already delivering.
- Reference and use of non-project attributable costs (NPAC) terms, negotiated with FCDO for non-commercial programmes
- Alignment to use of existing fee and management costs of existing, FCDO commercially agreed rates from other programmes, such the proposed new Centre of Expertise for financial services and trade (benchmarking).
- Where possible, to complement UK expertise with the employment of local Southeast Asian based expertise and remote / hybrid ways of working where feasible, to limit more expensive, carbon intensive travel and subsistence costs. The region has few insecurity concerns and a relatively large pool of skilled administrative and medium-high level expertise. This principle also recognises the importance of bringing in local expertise to provide invaluable country/regional expertise and context. Annual breakpoint in MoUs and potential for re-negotiation of fee-rates, to limit risks associated with longer multi-year commitments.

The table below sets out initial metrics across the different dimensions of VfM, to serve as a basis for a detailed VfM framework and monitoring plan to be developed during the programme’s inception phase.

Table 5: Indicative Value for Money (VfM) metrics
VfM dimension	Indicators (qualitative and quantitative)
Economy	Programme and operational costs (through procurement, contracting, programme and contract management, staff costs) / Fee rates of consultants (regionally sourced vs international) / Cost and effectiveness of programme in-sourced roles (PIR) vs external consultants / Ratio in-person vs. remotely provide time inputs (cutting travel/subsistence)
Efficiency – spending well	Ratio overhead/administration costs vs. intervention/TA input costs / Economies of scale with shared learning and planning across pillars. / Disbursement ratio: disbursement of funds divided by total undisbursed funds by the beginning of the fiscal year. / Implementation progress: measured outputs and outcomes in terms of high-value direct procurement – supported by robust contracting terms and KPIs. / Average time (months) to identify, agree and approve initial plans and interventions by ASEC, starting from Business Case approval date / Country or regional examples of identifiable influence on events, policy uptake and programmatic decision-making that demonstrate use of global evidence on key themes: regulatory reform, open trade, financial services.
Effectiveness – spending wisely	Logical framework – to measure progress against relevant indicators. Regular review and adjustment of indicators to take account of change. / Volume of specific initiatives/activities that are (i) completed to time/budget, (ii) rated at Satisfactory or better by key ASEAN partners. / Credible examples of technical assistance and initiatives improving the design and effectiveness of other domestic AMS and multilateral investments
Equity – spending fairly	Collection of disaggregated data mainstreamed into programme monitoring and evaluation strategy. / Development and review of inclusivity indicators across the programme. / Gender ratio improvements in participation in technical assistance and capacity building activities across the programme. / Development and implementation of specific programme activity which is targeting inclusion, in addition to mainstreaming throughout the programme.
Cost-effectiveness	Estimate of additional funding crowded-in as a results of TA and initiatives to demonstrate better, global evidence based approaches. / Estimate of long term cost savings and return on , influenced by TA and support (on specific requested intervention areas)

FCDO’s approach to VFM requires a focus on development effectiveness, to deliver ODA where it is most needed, maximising the value of each pound spent to alleviate poverty, and ensuring the best results accrue to beneficiaries and the UK taxpayer.
# Financial Case
The Financial Case includes the following:
1. Programme budget sets out cost forecast and profiles.
2. Financial management explains how the finances will be managed, including risk and fraud considerations.

## Programme Budget

This programme will be funded from the ASEAN regional programme budget managed by UKMIS ASEAN. We expect the total lifetime budget (ODA + non-ODA) to be up £25m over five years.
Subject to funding allocations, the programme will also include a non-ODA budget each year (c. £0.5-1m). This will enable us to include a substantive offer in Singapore and Brunei, strengthening our bilateral relationships and responding to their priorities as part of the programme. Covering all AMS will also allow us to secure ASEAN accreditation and a non-ODA budget will allow some activity to leverage secondary commercial benefits for the UK.
### Cost Profiles and Forecasting
FCDO will contribute up to £25m over give years (2023/24 - 2027/28). Estimated forecasts by component are set out below and will be reviewed quarterly throughout the life of the programme. Relatively low spend has been proposed for 2023/24 – 2024/25 within the current Spending Review period. This will enable us to complete a comprehensive inception phase in 2023/24, with a focus on forging new relationships with ASEAN counterparts and developing initiatives in a consultative process with AMS.
Given funding uncertainty, we have profiled three scenarios:
- Low: ODA allocations stay at current levels throughout programme
- Medium: ODA allocations increase to £5m per year from next spending review.
- High: ODA allocations allow the programme to spend full £25m initial allocation.
Spending review	Current		Future
	2023/24	2024/25	2025/26	2026/27	2027/28
ODA (£m)	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Low	0.8	1.5	1.5	1.5	1.5	6.8
Medium	0.8	2.5	5.0	5.0	5.0	18.3
High	1.0	3.0	6.2	6.2	6.3	22.7
Non-ODA (£m)	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Low	0.1	0.2	0.2	0.2	0.2	0.9
Medium	0.1	0.3	0.5	0.5	0.5	1.9
High	0.1	0.3	0.6	0.6	0.7	2.3
Total (£m)	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Low	0.9	1.7	1.7	1.7	1.7	7.7
Medium	0.9	2.8	5.5	5.5	5.5	20.2
High	1.1	3.3	6.8	6.8	7	25

We will split the budget between the three pillars on a roughly equal basis (~£8m each) but will be flexible to respond to demand from ASEAN and value for money considerations. We expect that the Regulatory Reform Pillar will reach delivery before the other two pillars so will take up a high proportion of the budget in 2023/24. OPSS have estimated the costs in 2023/24 will be £310,000. Once delivery routes and funding arrangements have been finalised, we ensure that the budget will cover spending commitments. We have allocated £1m for MREL, which will include commission external evaluations at the midpoint and end of the programme. We have estimated up to £100,000 per year for an embedded programme adviser / small team in the ASEAN secretariat.
Internal programme management spend will be covered by the baseline costs of running UKMis ASEAN –separate from the programme budget; UKMis ASEAN will pay for the programme managers. Similarly, UK Embassies/ High Commissions across the region will cover the proportion of the salaries of staff tasked to oversee bilateral programme management activities (see management case).
UKMIS ASEAN, in partnership with the SRO, will hold the budget resources and manage forecasts, as part of total ODA allocations for the UK ASEAN Plan of Action. While there will be considerable delegation of routine and detailed operational budget planning to delivery partners where possible, ASEAN UKMIS will maintain strategic oversight and control over resource allocation. There will be full flexibility to scale up or down or terminate components and activities, based upon performance and AMS demand for strategic UK support. MoUs or contracts for higher cost activities will need to include break clauses at the next spending review, to ensure funds are not committed until there is confidence of budget availability 2025/26 – 2027/28. Technical assistance can be a relatively flexible modality if uncertainty is factored into delivery plans, which should help the programme manage spending within potentially changeable budgets.
We will consider if any of the £500k allocation ring-fenced this financial year by UKMis ASEAN to support the accession of Timor-Leste can be delivered through this programme.
### Funding and Sector Codes
The programme will be funded within the ASEAN regional programme budget allocation for the current and next Spending Review period. The first two years are reflected in our current departmental Business Plan and in line with current allocations. We will seek approval from the Management Accounts Group for the full programme commitment which goes beyond the current SR. We anticipate funds will be mostly Resource Departmental Expenditure Limit (RDEL), but we will be looking for opportunities to spend Capital Departmental Expenditure Limits (CDEL) where spending meets the Frascati criteria. This includes the commissioning of research during the inception phase to build the evidence base for interventions.
Most costs will be ODA eligible; involvement of non-ODA AMS (Singapore and Brunei) in ASEAN-wide knowledge exchanges will be self-financed or through non-ODA allocations. It is not anticipated to seek co-finance for this programme, but opportunities may arise to align or collaborate on initiatives using downstream partners own resources or with other ODA donors, such as US, Japan or Australia who are active in the region.
Funding will contribute 100% to both spend on the ASEAN Plan of Action and to the Women and Girls objective of the International Development Strategy. Input Sector Codes will be confirmed during inception.
## Financial Management
### Expenditure, Financial Reporting and Accounting
Payment schedules will depend on management arrangements agreed for the components of the programme. Implementing partners will provide forecasts of expenditure to FCDO at the beginning of each financial year and these will be revised regularly in accordance with the respective delivery agreements. Payments will normally be made in arrears against actual expenditure on a quarterly basis. There will be potential for limited advance mobilisation payments for trusted partners where due diligence and fiduciary controls allow, providing this is not in advance of need. If programme funds are used to pay FCDO staff taking up programme in-sourced roles (PIR), these will be disbursed through FCDO payroll mechanisms; we are still investigating the exact mechanism needed if we embed someone within ASEC.
All funding arrangements will outline how disbursement of funds will take place. This will be agreed in advance with FCDO, and each disbursement will be conditional on specific delivery milestones being met and demonstration of financial need.
The programme spend is anticipated to be classified predominately as RDEL and will be resource accounted. ASEAN UKMIS will monitor risk throughout the programme cycle in compliance with the PrOF, risk registers, progress reports discussed at steering boards, and formal review points, including annual reviews. We will liaise with FCDO’s Internal Audit and Investigation Section (IAIS) if reports of fraud or safeguarding concerns are received. The funding arrangements for both commercial and not-for-profit delivery partners include provisions on risk management.
Agreements with delivery partners will define responsibilities for managing activities, finances, and reporting. This includes narrative and financial reports on a quarterly basis (with reconciliations of actual expenditure and forecasts). Where possible, payments will be performance based, linked to milestones and compliance criteria, and evidence of need for funding. Suppliers may also be required to use Activity Based Budgeting (ABB) where applicable for direct service delivery and influencing work, to enable VfM analysis in combination with other data sources.
### Financial Risk and Fraud
The overall fiduciary risks around misuse or diversion of ODA financing from this programme is assessed as medium. We will access the financial management capabilities of leading partners and any downstream partners. Some activities will take place in more fragile, corruption-prone AMS. UKMIS ASEAN, in collaboration with FCDO country Posts, will undertake the following measures to mitigate against financial risk and fraud:
- Work with each lead partner to develop a robust risk management system and fraud mitigation strategy which meets FCDO’s ProF requirements. They will also in turn need to develop this with downstream partners and set out how they will monitor their performance and financial management. This includes having in place internal risk management and reporting systems.
- Delivery partners and suppliers will be required to provide external annual audited accounts, certified by auditors that separately identify FCDO funds. UKMIS ASEAN may also finance independent audits of any partner, if required.
- Conduct regular monitoring and evaluation (from UKMIS ASEAN and Posts) by undertaking financial spot checks at least once a year, supervisory field visits and annual reviews. FCDO will also review annual audited accounts from each delivery partner, as part of its continuous due diligence. Recommendations will also be incorporated into the overarching programme risk register, which will be reviewed at least quarterly by the UKMIS ASEAN programme team.
- All assets bought by delivery partners will remain the property of FCDO until the end of the programme. FCDO will then decide whether to hand over or otherwise dispose of these assets. Delivery partners will maintain an asset inventory and report annually on changes or additions.
- UKMIS ASEAN or PCD will undertake due diligence assessments of all suppliers that do not have a valid DDA for an existing programme, prior to signing implementation agreements. Partners will need to notify FCDO of any changes to the delivery chain. Any contract tendering stage will include a thorough consideration of suppliers’ abilities, capacity and systems to perform such assessments to the high standard FCDO expects. Suppliers will also be expected to strengthen the financial capacity of downstream partners where needed and conduct periodic financial checks.
- FCDO will reserve the right to conduct a full forensic audit. This can be actioned at any stage of the programme and will be stipulated in all funding arrangements with suppliers and delivery partners. It is in line with FCDO’s zero tolerance to fraud.
- The FCDO will provide training to lead suppliers on FCDO fraud and aid diversion policies and processes, including how to report any suspicions to reportingconcerns@fcdo.gov.uk.

If fraud is detected, FCDO will require full remedial action including repayment in full of diverted UK funds. Trigger points will be outlined in the funding arrangements with lead delivery partners, including the timeframe by which funds should be returned. Continued disbursement of funds will only be contingent on adequate financial oversight mechanisms being in place. Advice from FCDO’s Finance Department and Fraud Liaison Unit will be sought in such cases.
# Management Case
The Management Case includes the following:
1. Management Structures
2. Monitoring and Risk

## Management structures

As a multi-country regional development programme and part of the UK ASEAN Dialogue Partner Plan of Action, there are a number of specific organisational, management and approval requirements to synthesise, to meet both (ii) FCDO requirements (defined in the PrOF and (ii) be accredited as an ASEAN compliant programme.
To ensure the programme meets ASEAN accreditation conditions, ASEAN institutions will be involved in the programme governance. The Programme Senior Responsible Owner (SRO) and the UKMIS ASEAN Programme Responsible Officer (PRO) will lead routine FCDO programme management and oversight procedures; a Programme Steering Committee (PSC) that includes ASEAN officials, will approve the overall programme, annual work plans and specific projects being proposed.
### FCDO Governance
The SRO for the Programme is the Southeast Asia Regional Director, Economics and Trade Policy based at the British High Commission Singapore. The SRO is responsible for strategic oversight of the programme(s); they are accountable for ensuring the programme team delivers effectively, and providing overall leadership, decisions and direction. The SRO is accountable to both the UK Ambassador to ASEAN as the portfolio-level SRO for all ASEAN-UK programmes and the ASEAN Development Director who has delegated authority for ODA oversight. The SRO will work closely with the Trade and Economic Counsellor and the Head of Development in UKMIS ASEAN to ensure the programme is run as an integrated part of the overarching ASEAN-UK relationship. There will be a full time PRO based in the programme team in UKMIS ASEAN.
The FCDO Programme Board will be responsible for the overall governance and management of the Programme. This will include oversight of progress towards outcomes/impact, spend, and risk management. The Members of the Board will provide advisory support to the SRO and the EIP Programme Team to ensure the alignment of the policies and priorities at the bilateral and regional levels.
 The Programme Board is chaired by the SRO and will be made up of the following:
- Head of Development, UKMIS ASEAN
- Trade and Economic Counsellor, UKMIS ASEAN
- Deputy Trade Commissioner, BHC Singapore
- Development Director, UKMIS ASEAN
- 10 x Heads of Prosperity (or counterparts) from each UK Embassy/ High Commission
- MEL Adviser
- SDA Adviser
- Commercial Adviser
The Board will meet every three months during the lifetime of the programme to review progress and approve quarterly reports, and to help shape strategic priorities and support delivery.
### ASEAN Governance
The Programming Steering Committee (PSC) will be convened annually to review and discuss work plans, progress and new initiatives. The PSC will consist of relevant programme management officers, ASEC Directors and Assistant Directors and UKMIS ASEAN. It may also include Chairs of ASEAN Working Groups and Senior Economic Officials to the ASEAN Economic Community, depending on level of interest and topics of discussion. It will meet annually to review progress and approve annual work plans / activities for the programme. It will also review and approve the programme annual review each year.
Alongside the PSC, we will sight the Senior Economic Officials of relevant documents at the annual UK-ASEAN Senior Economic Officials Meeting. This will ensure oversight remains with Senior Economic Officials whilst ensuring the formal governance checks and balances remain at the appropriate seniority and in line with the other UK programmes for consistency. We will time the PSC to fall after the annual UK-ASEAN Senior Economic Officials Meeting to ensure we can reflect any comments from Senior Economic Officials in final decisions. We will be testing this governance model with ASEAN through the accreditation process.
We will consider the option to locate some programme resource at ASEC, taking advice from other donors who have adopted this model. Employing some roles that ASEC then agree to take over provides an opportunity for both building staff capacity for ASEC and for the UK to gain a better understanding of how ASEAN works in practice. We will undertake detailed scoping during inception to understand the costs and risks of this approach to determine whether it represents value for money.
### Programme Management
Baselined FCDO staff in each bilateral SE Asia Post will be responsible for programme management. The PRO will be supported by one or two further programme managers / officers. The final resource allocation, including what proportion of time each staff member spends on this programme, will be determined during inception phase as more details emerge about the precise programme delivery model, capabilities of implementing partners and complexity of outputs. All UKMIS ASEAN programme managers and officers will be expected to work flexibility to manage the overall portfolio of ASEAN-UK programmes as required.
Each bilateral post will also be required to allocate sufficient staff resource to manage and oversee local programme implementation. This will be managed differently depending on available capacity and likely scale of implementation and activity at each post. Final resourcing will be agreed in consultation with the programme SRO and the programme team in ASEAN UKMIS. We will advocate for a minimum of 0.2FTE per post from a qualified programme manager, with a recommended target of 0.5FTE to provide comprehensive oversight and to work as part of the regional programme team.
This model means we can centralise contract and programme management functions with the ASEAN UKMIS but still give posts control and ownership over the specific interventions in their country, to make sure programme activities are tailored to fit the bilateral context and support bilateral objectives. AERP demonstrated that having dedicated programme resource within each country significantly increases the likelihood of successful delivery, as well as providing valuable feedback to the regional level regarding the local context.
A further lesson learned from AERP is the importance of programme staff capability. All those responsible for programme management will be required to complete PrOF training as a minimum, and ideally to be given sufficient time and resource to complete additional more specialist training as required.
The Commercial Adviser, MREL Adviser and Social Development Adviser (SDA) will support throughout the Programme, to ensure a rigorous approach to commercial delivery, MREL and gender and inclusion.
Title	FTE	Grade and number
SRO/ SE Asia Regional Director, Economics and Trade Policy	0.2	x 1 x Grade 7 UKB
Head of Development, ASEAN	0.1	0.1 x 1 x Grade 7 UKB
PRO/ Head, Economic Integration Programme	1	1 x SEO CBS
Economic Integration Programme Managers	2	2 x HEO CBS
Economic Integration Programme Officer	1	1 x EO CBS
Programme Managers (each UK Post)	2	0.2 x 10 x HEO CBS
Total	6.3	Regional programme team and G7 SRO, supported by network

## Monitoring and Risk

### Monitoring and Evaluation
Monitoring, reporting, evaluation and learning (MREL) will be an important element of programme management given gradual inception phase and flexible delivery model. We will ensure compliance with PrOF requirements and incorporate elements of adaptive programming.

During the inception phase, we will
- Develop a comprehensive MREL plan that ensures the integration of MREL throughout the project cycle
- Build in additional staff management time given the need for intensive engagement with ASEAN and implementing partners during this phase
- Continue to focus on lessons learned from the AERP
- Initiate the programme board to ensure oversight of decisions regarding delivery partner and project selection
- Secure a permanent MREL adviser on the Programme Board.
- Develop a research / CDEL plan and commission initial research to develop the evidence base under each pillar
- Signal expectations for adaptability in ToRs with suppliers.
- Develop a logframe and results framework with delivery partners

During delivery, the FCDO (UKMIS ASEAN and bilateral posts) will monitor programme performance through quarterly reporting compliant with PrOF requirements, regular field visits, annual reviews and an end of project completion review. They will be supported by the Commercial Adviser, MREL Adviser and Social Development Adviser throughout the lifetime of the Programme.
The PRO will ensure that activities and reviews are part of the programme delivery plan. Monitoring will include:
1. Verifying interventions are being delivered to quality, based on standards set for approaches.
2. Verifying results through spot checks and focused interviews with stakeholders and AMS/ASEC officials
3. Checking on fraud, fiduciary risk, and safeguarding through inspections and data verification interviews
4. Assessing data trends and emerging issues needing policy attention
5. Evaluating collective programme and individual initiative performance.
6. Evaluating performance of delivery partners. This will be reviewed and appraised annually with ASEC and SEAMEO counterparts.
FCDO staff will assess quality of implementation during visits, where possible drawing on FCDO country-based staff and central HMG expertise from FCDO, DBT, DSIT where appropriate.
A valuable lesson learned from AERP is the importance of agreeing the theory of change and logframe indicators before delivery begins. Outcomes, outputs and activities should match implementation plans. Indicators and targets should be agreed prior to commencement of delivery, to ensure the buy in and ownership of all stakeholders, and to ensure that the logframes can be effectively used as a monitoring tool. Indicators should be both quantitative and qualitative. It may be useful to plan MREL training for delivery partners to help them understand the FCDO approach and expectations regarding logframes.
As part of the MREL plan, we will commission external evaluations at the midpoint and end of the programme to identify and track short, medium and longer-term impact of interventions and collective impact. These will include quantitative metrics (e.g. domestic AMS or external donor funds assigned to supported initiatives, AMS enrolment and learning profile trajectories) and qualitative measures regarding embedding reforms and initiatives sustainably into government systems, and perceptions on the influence of UK expertise and value of UK institutional partnerships. We have allocated a budget for external MREL support, which could be contracted through the Global Evaluation and Monitoring Framework Agreement (GEMFA). This would most likely be through Lot 3 (ITT 5485).

### Risk Management and Assessment
This Programme is expected to be medium risk overall. A high-level risk register for the programme has been drafted (see Annex G) and a comprehensive risk mitigation strategy will be developed in the inception phase and maintained by the PRO, as part of the overall Delivery Plan and management approach led by the UKMIS ASEAN.
The appointed delivery partners will develop a more detailed risk register to track and monitor implementation, safeguarding, fiduciary and institutional risk with commercial, AMS and ASEAN partner organisations. This will be used to escalate severe risks to the FCDO for guidance and mitigation. FCDO will lead and manage around reputational and geo-political risks, including any programme engagement involving Myanmar.
The main risks are:
- Impact. Interventions are too thinly spread given limited budget and scope of programme. Mitigation: evidence-based interventions which focus on UK expertise and interventions where the potential multiplier effect is largest.
- Complexity: Monitoring and control of a regional multi-partner programme is challenging. Mitigation: streamline regional interventions where possible. Ensure robust monitoring and results frameworks are in place.
- Reputational: budget changes could undermine our delivery, impact and reputation. Mitigation: work to confirm and maintain multi-year budgets.

# Annexes

### Annex A: Regional Diagnostic

### Annex B: Readout from lessons learned workshop 13 January 2023

### Annex C: Lessons learned on gender and inclusion

### Annex D: Theory of change detail
ToC: Regulatory Reform pillar

Problem statement: the Regional Diagnostic found that bureaucratic regulatory barriers are constraining growth, investment and entrepreneurship in multiple member states.
Complex and inconsistent regulatory environments are widely considered to be a significant barrier to business and economic growth. In ASEAN’s mid-term economic review, harmonisation of standards and regulation came out as the second biggest barrier facing business, with 36% and 39% of domestic and foreign businesses surveyed highlighting it as an issue
Pillar impact (programme outcome): Improved regulatory and standards system in AMS that are less bureaucratic; provide a more stable environment for business investment; and better protect workers and consumers, particularly the most vulnerable in society.
Several studies have proved a strong correlation between good regulation and economic growth, achieved when programmes of reform change companies’ behaviour to enhance investment and encourage innovation. An improved business environment contributes to poverty reduction through increasing investment and economic growth, equally a poor business environment hampers investment increases transaction costs and creates a drag on economic growth. A study based on World Bank Doing Business data finds robust evidence of a positive impact of regulatory reforms on economic growth, with each regulatory reform associated, on average, with a 0.182% increase in growth (Haidar, 2012). Best Buys evidence on Regulatory Reform of the business environment is mixed but these interventions can be low cost and effective when targeting implementation of politically supported reforms. / By increasing the degree of regulatory overlap amongst the member states, but without increasing the overall number of non-tariff measures (NTMs), trade costs within ASEAN can be substantially reduced. This is especially pronounced in commodity groups in the primary sector and food products, and in chemicals, plastics and leather, footwear, machinery and electronics, and vehicles. There is substantial potential for trade cost reduction – and therefore potentially greater positive effect on intra-ASEAN trade and on overall economic welfare – from greater regulatory convergence within the region. Such efforts at regulatory convergence are at the heart of regulatory cooperation through mechanisms such as those on standards and conformance in ASEAN.[12] / Potential metrics: OECD ease of doing business replacement metric, ASEAN working committee metrics
Pillar Outcomes: AMS adopt and implement policy reforms, informed by UK expertise and in line with international standards, that simplify, codify and harmonise (or mutually recognise) regulations and standards. These policies will be tailored based on a consideration of their impact on woman and girls and vulnerable members of society.
The Regional Diagnostic found that barriers to doing business in AMS are tractable. ASEAN is already operating in this space via the ASEAN Consultative Committee on Standards and Quality (ACCSQ). Through this committee, guidelines on good regulatory practice have been published and work is underway. As well as the UK’s existing work with this committee, the OECD are also working closely with ASEAN through the ASEAN-OECD Good Regulatory Practice Network. The OECD helped AMS identify some expectations for future regulatory reforms in their respective administrations, including improving the quality and delivery of online services, re-engineering government systems and refining the use of good regulatory practice (GRPs). The AERP has a successful record of supporting the implementation of 13 new laws and policies across ASEAN. / The next step in developing this ToC is to identify specific ASEAN initiatives we could support, with a focus on digital solutions and those that particularly support WEE and SMEs. The Office of Product Standards and Safety (OPSS) in the Department of Business and Trade (DBT) is working with FCDO posts and ASEAN to identify specific ASEAN initiatives we could support. These will likely cover Better Regulation, Consumer Protection and E-Commerce, and Standards. / Regulatory reform has been recognised as a crosscutting theme that will support economic integration across ASEAN and underpins and is driven by various high-level ASEAN strategies. These include the ASEAN Economic Community Blueprint 2025 (“Effective, Efficient, Coherent and Responsive Regulations, and Good Regulatory Practice”, “facilitative standards and conformance” and “Consumer Protection”), the Consolidated Strategy on the Fourth Industrial Revolution, the ASEAN Comprehensive Recovery Framework and The Masterplan for ASEAN Connectivity (Regulatory Excellence). / Initial desk-based research has highlighted various work plans, principles and guidelines that support the implementation of these overarching strategies: / Better regulation: / ASEAN Work Plan on Good Regulatory Practice (2016-2025) / ASEAN Good Regulatory Practices (GRP) Core Principles[13] that aims to support AMS to improve their regulatory practices and foster greater ASEAN-wide regulatory co-operation. / Consumer Protection and E-Commerce: / ASEAN Strategic Action Plan For Consumer Protection (ASAPCP) 2021 - 2025 / Work plan on the Implementation of ASEAN’S E-Commerce Agreement[14] which aims to enhance consumer protection in the online and digital environment to help drive inclusive growth. / Standards: / ASEAN Standards and Conformance Strategic Plan 2016 – 2025[15] / All AMS are currently using digital tools to support regulatory reforms, with 7 AMS including a focus on using digital tools to improve procedures around the design and delivery of regulations in their national digitalisation policies and strategies. The anticipated interventions within this pillar will seek to support AMS to leverage the opportunities of digital transformation but also address the pace of digital innovation, designing “fit-for-purpose” regulatory frameworks, the enforcement challenges and the institutional and cross-jurisdictional issues which digitalisation present. / Potential metrics: Number of policy reforms introduced by AMS, in line with ASEAN strategies and programme recommendations.
Potential outputs: Technical assistance to AMS government officials and ASEAN bodies, including guidance on good regulatory practice, supporting the development and harmonisation of new laws, policies and standards across ASEAN, improving the delivery (enforcement) of regulation and the development of better government/business/citizen consultation and engagement.
We have started initial engagement with the ASEAN Committee on Consumer Protection (ACCP) and the ASEAN Consultative Committee on Standards and Quality (ACCSQ), to discuss potential areas for co-operation. This will take into consideration the current priorities of ASEAN, what has already been achieved, other development partner activity and where OPSS and other delivery partners are best placed to deliver impactful interventions. / The programme’s interventions will focus on developing the capacity of government officials on good regulatory practices, supporting the development and harmonisation of new laws, policies and standards across ASEAN, improving the delivery (enforcement) of regulation and the development of better government/business/citizen consultation and engagement. / The potential areas of co-operation within this pillar offer scope to deliver interventions that will focus on women’s economic empowerment. We plan to commission research to address a critical gap in knowledge and understanding of the intersection of gender equality and regulatory reform activities. This research will examine the links between gender and regulatory reform through an ASEAN lens, to develop a regional evidence base and recommendations on gender specific regulatory reform interventions, which are suited to, and most likely to have greatest impact in an ASEAN context. / There is good evidence from the AERP that technical assistance can fill capacity gaps in AMS and there is a strong demand from stakeholders to continue this work. The AERP regulation project supported partner governments with the implementation of 13 new or revised laws, regulations, rules and administrative practices. / Outputs will align with the Plan of Action: / 2.1.6. Support ASEAN’s efforts on regulatory improvement through technical assistance, economic cooperation, exchange of best practices, information sharing and capacity building and training; / 2.1.10. Promote ASEAN-UK cooperation in standardisation to facilitate the trade and investment between AMS and the UK; / Potential metrics: Potential metrics: Number of reports / tools / recommendations; Feedback from beneficiary organisations in AMS
[12] The ASEAN Economic Community Into 2025 and Beyond (eria.org)
[13] https://asean.org/wp-content/uploads/2020/12/Adopted-ASEAN-Good-Regulatory-Practice-GRP-Core-Principles.pdf
[14] https://asean.org/wp-content/uploads/2022/03/Work-Plan-E-commerce-Agreement_endorsed_logo.pdf
[15] https://asean.org/wp-content/uploads/2021/01/ASEAN-Standards-and-Conformance-Strategic-Plan-2016-2025.pdf

ToC: Open Trade pillar
Problem statements: the RD identified market access barriers as one of the top five barriers to development in ASEAN.

Pillar impact (programme outcome): increased trade between AMS, and between ASEAN and the rest of the world, particularly for MSMEs and in digital trade.
Trade is recognised as an engine for inclusive economic growth and poverty reduction in the 2030 Agenda for Sustainable Development. The 2015 joint WTO-World Bank publication: “The Role of Trade in Ending Poverty” strengthened the evidence that trade has played a critical role in poverty reduction and that the further integration of developing countries into an open global economy will be essential for achieving the goal of ending extreme poverty by 2030. / Research into Trade Facilitation issues suggests that this can be just as important as traditional trade barriers. An OECD report estimated that a 1% reduction in transaction costs would boost world GDP by $43bn, and two-thirds of this would accrue to developing countries. The increased efficiency of border procedures triggered by a full Trade Facilitation Agreement (TFA) implementation could potentially add between 0.04% and 0.41% to countries’ GDP, depending on the level of development. The GDP growth links improved Trade Facilitation through to poverty reduction, with income inequality important in determining how powerful an effect growth has in reducing poverty. / Knebel and Peters (2017) provide results on ‘regulatory distance’ for technical measures amongst AMS. The results show that Non-Tariff Measures (NTMs) are more numerous and the regulatory distance amongst AMS is significantly bigger for agricultural products than for manufacturing. Ad Valorem Equivalents (AVEs) show NTMs costs as a percentage of trade, there are substantially higher in agriculture and food products – such as animals and meat, fats and oils, fruits, vegetables, and grains, and processed food, beverages, and tobacco – than in manufactures, such as metals and metal manufactures, miscellaneous manufactures, and even machinery and electronics. / Best Buys evidence has reducing cost of trade (e.g. anti-competitive behaviour, regulations) as a great buy, given the benefits of increased trade the potential benefits are high, for limited financial cost. Political support likely to be necessary given opportunities for rents from barriers from policy or implementation. / Potential metrics: ASEAN trade flows
Pillar Outcomes: AMS adopt and implement policy recommendations and reforms to lower barriers to trade across AMS, targeting barriers related UK specialisms, including intellectual property rights, competition policy and / or digital trade procedures.
The ASEAN Economic community blueprint 2025 sets out the aim to “continue to reduce or eliminate border and behind-the-border regulatory barriers that impede trade, so as to achieve competitive, efficient, and seamless movement of goods within the region” and “further broaden and deepen services integration within ASEAN, ASEAN’s integration into the global supply chains in both goods and services, and enhance AMS’ competitiveness in services”. The ASEAN Trade in Goods Agreement and Trade in Services Agreement set the legal basis that implement the policies at a regional level; implementation or further liberalisation of these will be a measure of success in this programme. / Outcomes for this pillar are less detailed than the other pillars at this stage, partly because there is less previous programme work to build on. ASEAN has many initiatives that aim to reduce trade barriers and it is a crowded donor space. Therefore, we are taking time to consult with ASEAN and UK Posts to identify areas of UK comparative advantage where ASEAN wants support. / The most promising areas are: / - Intellectual Property (IP) enforcement: ASEAN is keen to build up their IP systems to support their businesses, innovators, creators and attract foreign investment. Ineffective IP enforcement reduces innovation and investment, which lowers economic growth, as companies are reluctant to invest in the research and development of new products if they are uncertain of their ability to protect IP and make a return on their investment. The ASEAN Intellectual Property Rights Action Plan sets out plans to strengthen online IP enforcement in particular, giving the growing importance of e-commerce in the region. / Ecommerce offers MSMEs and entrepreneurs a cost-effective channel to start a business, internationalise, and reach wider markets. Women are also leveraging ecommerce to overcome challenges (e.g. care responsibilities, access to capital) and enter sectors where they have been traditionally underrepresented (e.g. electronics) as anonymity on ecommerce has helped reduced stereotypical gender bias and entry barriers. / - Competition policy: effective competition policy can help address trade barriers that arise from anti-competitive behaviour and unfair trade practices. ASEAN acknowledges that operational and effective rules on competition are necessary for ASEAN to be a competitive region with well-functioning markets. It has therefore developed an ASEAN Competition Action Plan (ACAP) 2016-2025 with several goals and initiatives to cement competition policy as an integral economic policy. Its fundamental goal is to provide a level playing field for all firms regardless of their ownership, to facilitate liberalisation and create a unified market as well as to support the formation of a more competitive and innovative region[16] / - Digital trade: The ASEAN Bandar Sri Bagawan Roadmap sets out their cross cutting a Digital Transformation Agenda to support ASEAN trade. This areas aligns well with UK expertise, although it is a crowded donor space and we are still identifying the barriers to development we could target in this space.
Potential outputs: technical assistance to AMS government officials to support implementation of polices that lower barriers to trade in ASEAN.
We are working with the UK IPO and DBT to better define the programme focus areas with ASEAN. In particular, we are working the ASEAN Competition, Consumer Protection and Intellectual Property Rights Division and Digital Economy Division. / The UK IPO are working on a proposal to improve ASEAN’s IP ecommerce environment by strengthening IP enforcement policies and practices and enhancing IP skills of creative businesses. In particular, it is exploring how it could support promotion of IP ecommerce best practices and codes of conduct through public-private partnerships and industry action, strengthening of ASEAN’s IP Ecommerce policy development and business engagement through capacity building and sharing of expertise. / The Competition and Markets Authority is running a series of workshops this year with the ASEAN Experts Group on Competition (AEGC), which we will look to build on if we choose competition policy as a programme focus area. The UK funded the OECD to run a project on Fostering Competition in ASEAN as part of the AERP, which would give us a strong base to start from. / Outputs will align with the Plan of action: / 2.1.2. Continue cooperation to enhance regional development and prosperity by promoting an open, free, inclusive, non-discriminatory, rules-based, transparent, predictable, and stable multilateral trading system that operates in line with WTO rules and agreements; / 2.1.8. Work cooperatively on the operationalisation of the ASEAN-UK Digital Innovation Partnership to promote greater digital connectivity, cross-border digital trade, and inclusive economic growth by supporting the development, adoption and use of international standards; / 2.2.4. Jointly work to maintain and strengthen trade links through the opening of our markets and facilitating the smooth flow of goods and services, including through the removal of unnecessary trade barriers that are inconsistent with World Trade Organization (WTO) rules; / 2.1.11. Support the ASEAN Intellectual Property (IP) Rights Action Plan 2016-2025 that identifies strategic goals and initiatives that will contribute to the collective transformation of ASEAN into an innovative and competitive region through the use of IP;

ToC: Financial Services pillar

Problem statement: the RD found that low levels of financial inclusion, shallow capital markets and weak investment frameworks hamper access to financial services and limit investment
Financial inclusion is uneven among AMS. For example, the percentage of adults with an account at a financial institution—a key financial inclusion indicator for usage—is much lower among Least Developed / There are many gender-based barriers to financial inclusion in ASEAN. There are linked barriers on the demand side, supply side and regulatory side. For example, on the demand side, a lack of assets and land ownership for collateral are linked to legal barriers to owning and inheriting property.[17]
Pillar Impact (programme Outcome): wider access and usage of quality financial services in ASM that enables greater financial resilience, particularly for MSMEs, and women and girls
It is widely accepted that financial sector development is important for economic growth. The financial sector plays a key intermediation role in allowing the mobilisation of savings for investment; facilitating and encouraging inflows of foreign capital; and optimising the allocation of capital to the most productive use. FCDO Best Buys identifies financial sector development as a high potential intervention; modest amounts of technical assistance can unlock substantial amounts of finance / In particular, expanding the supply of appropriate financial services to low-income households has a direct benefit to those individuals, supports wider financial sector development and can reduce income inequality. Financial inclusion benefit occur through various mechanisms: / Provision of savings facilities: enabling low-income households to accumulate their available funds securely in order to finance relatively large, anticipated future expenditure or investment. / Lower risk exposure: reducing vulnerability of low-income households to shocks in the absence of savings or insurance by allowing borrowing and consumption smoothing when there are unanticipated fluctuations in income. / Increasing the opportunities accumulate assets: enabling low-income individuals to invest in higher returning assets or productivity enhancing technologies, increasing long-term income. / Facilitating remittances and domestic transfers: lower transactions costs allowing easier access to remittances[18] from abroad and domestic transfers, allowing greater job creation, access to credit, formalisation, consumption smoothing and human capital investment. / More broadly, financial inclusion impacts on economic growth by empowering consumers and businesses to make better and well-informed choices, thereby enabling them to make sound financial decisions and raise their standard of living. / The ASEAN Access to Digital Finance Study (2021, CCAF) found that alternative finance channels are a critical component to enable individual consumers and small businesses cope with their financial needs by enhancing their access to credit. Results show that businesses accessing fintech platforms are mainly micro and small enterprises, mostly led by females, that use online finance channels to access funds for working capital. Further, most MSMEs reported improved business performance after receiving finance through these channels, highlighting the key role of alternative finance in small business financing, especially during the pandemic. / Metrics: Reduce average financial exclusion in ASEAN from 44% to 30%
Pillar Outcomes: AMS adopt and implement policy recommendations and reforms that promote financial inclusion, access, and resilience in the region, particularly for MSMEs and women.
The ASEAN Working Committee on Financial Inclusion (WC-FINC) works to meet ASEAN’s financial inclusion targets, as set out in the ASEAN Economic community blueprint 2025 and 2016-2025 ASEAN Strategic Plan for Financial Integration. In particular, it’s key policy focus areas are: / Support national financial inclusion strategy and implementation / Elevate AMS capacity building to enhance financial inclusion ecosystem / Promote financial inclusion innovation via digital platforms / Increase awareness on financial education and consumer protection / This programme will identify financial inclusion initiatives within WC-FINC and other ASEAN working committees that could benefit from support from UK experts. / Potential metrics: The UN Capital For Development Fund (UNCDF) tracks progress on financial inclusion in ASEAN. Their detailed annual report provides good metrics to use during this programme; Enhance financial inclusion infrastructure readiness from 70% to 85%
Potential outputs: We will develop detailed outputs developed during the programme inception period, in collaboration with ASEAN and UK posts. / There is an opportunity to engage and influence WC-FINC (as the body that covers FinTech) to encourage them to adopt frameworks and develop clearer regulations that support the utilisation of FinTech solutions which enhance access to finance, similar to the UK’s approach. / There are opportunities to engage at country level, as financial inclusion in ASEAN will be addressed mainly through the actions of individual governments and regulators (though there will be some knowledge transfer and sharing opportunities through ASEAN).
Outputs will align with the relevant pars of the Plan of Action: / 2.3.1. Support regional financial development and integration, and resilience of the overall financial system, through deepening the understanding of capital market development in AMS including the use of green and transition bonds, and strengthening the capacity of ASEAN financial regulators in the areas of financial inclusion, sustainable finance, digital finance, and cross border payments and remittance services; / 2.3.2. Promote an increased flow of high-quality sustainable finance, including private sector investment, to support green, clean, inclusive growth and resilient infrastructure, including to reduce the vulnerability of low-lying and coastal regions; / 2.3.5. Strengthen the cooperation including through knowledge sharing and capacity building, on aspect of digital economy including FinTech and financial inclusion; / 2.3.6. Provide support to develop capacity in sustainable financial services sectors in ASEAN; / 2.3.7. Exchange information and support capacity building in financial services digitalisation;
[17] https://www.uncdf.org/article/8202/2022-monitoring-progress-financial-inclusion-in-asean
[18] Analysis across countries worldwide shows the significant poverty reduction effects of remittances across a range of studies. One finding from Adams and Page study shows a 10% increase in per capita official remittances leads to a 3.5% decline in the share of people living in poverty.

### Annex E Critical success factors and long list identification questions
Critical success factors​	Programme level​	Project level​
1. Spending objective: poverty reduction​
​	Programme delivers theory of change at impact level (e.g. inclusive economic growth in ASEAN)​	Project fits with theory of change at outcome level (for trade, regulation, financial services pillars). / Projects should have solutions that harness inclusion and /or digitalisation to reduce poverty. Each project will also need to evidence how their outputs will lead to sustainable outcomes.
2. Strategic fit​
ASEAN relationship​	Programme gains ASEAN accreditation and recognition (for whole programme or the majority of projects)​	TBC based on discussions with ASEAN Secretariat, but projects likely to score well if they support UK-ASEAN Plan of Action, work with all member states and/or support an ASEAN led initiative (* see detail on next page)
Wider UK objectives in region ​	Programme supports country business plans… . / …and is consistent with the International Development Strategy and Indo-Pacific tilt (Integrated Review)	Project is wanted by individual member states​, who will recognise project as a UK contribution to bilateral relationship / E.g. “using our world-class British expertise”, championing free trade and rules based international system / “improve economic security for girls and women” / “accelerate digital transformation for all”
3. Value for money (“5 E’s”)​
​	Focus on maximising cost-effectiveness (of impact), efficiency (inputs to outputs) and equity (fairness)​	Focus maximising on effectiveness (outputs to outcomes) and economy (price of inputs)​
4. Supplier capability and capacity​
Expertise​	Programme can access genuine subject matter expertise (so needs to leverage UK specialisms)​	Implementing partners available to deliver the project in the region​
Flexible / adaptable ​	Programme has model that is responsive to changing UK and ASEAN priorities	Project can be mobilised quickly ​(generally within 6 months)
5. Affordability​
Budget​	Up to £5m per year	Project small-scale (e.g. <£1m per year)
Flexible (budgets likely to change)​	Programme has model that makes it easy to control total spend​	Project needs to be scalable and / or pausable​
6. Achievability​
​	Can be delivered on time with available FCDO programme resource​	Low marginal resource costs for each additional project​

Scope – what?	What level of detail should we design before inception? / What do we deliver regionally at an ASEAN level? / What do we deliver bilaterally at a member state level? / What projects should we continue/adapt from the ASEAN Economic Resilience Programme? / What activity should we do with Singapore and Brunei? / What does delivering across three pillars and two themes mean?
Solution – how?	How do we manage three pillars? / How do we make the programme flexible? Should it be an ‘adaptive’ programme? / How do we select projects? / How do we consult member states?
Delivery – who?	Who is better placed to deliver, UK Government / institutions or commercial providers? / Should we do early market engagement? / What should / could we outsource? / Who might be good implementing partners for each pillar? / Preferred procurement structure / commercial model?
Implementation – when?	What will we aim to delivery in Y1? / What is the ideal procurement timetable?
Funding	How much non-ODA does the programme need? / How do we flex programme spend to respond to changing and uncertain ODA budgets?

### Annex F: OPSS proposal for Regulatory Reform Pillar

### Annex G: Risk register