## Annual Review Template

Title: ASEAN – UK Economic Integration Programme (EIP)
Programme Value £ (full life): £25m		Review date: August 2025
Programme Code: 400046	AMP start date: April 2023	AMP end date: June 2029

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400046 (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400046 Documents (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW
Description of programme

The EIP aims to reduce barriers to development in ASEAN Member States (AMS) and the overall ASEAN Economic Community (AEC), to increase prosperity and provide the foundation for more inclusive economic development that benefits the poorest in society. The programme will support reforms covering three pillars: (1) Regulatory Reform, (2) Financial Services, and (3) Open Trade, through technical assistance, capacity building and knowledge-transfer partnerships. It will look to harness the potential of digitalisation in ASEAN and will leverage expertise in United Kingdom (UK) institutions to support AMS to implement ASEAN initiatives that will reduce poverty in the region, particularly supporting women’s economic empowerment and small businesses and working towards further integration of the AEC.

The ASEAN-UK Economic Integration Programme (EIP), accredited by ASEAN in March 2024, was officially launched in April 2024. The EIP programme is progressing across its three pillars at different stages. The Regulatory Reform pillar (RRp) is currently in the implementation phase, the Financial Services pillar (FSp) is in its inception phase, and the Open Trade pillar (OTp) is still on-going of procurement process during this review period.

Summary supporting narrative for the overall score in this review

This Annual Review covers the period from July 2024 to March 2025. FY 24/25 has been a year of transition for the programme as it looks to ramp up delivery, onboarding new delivery partners, engaging key stakeholders at both regional and national level and completing procurement for the Financial Services pillar and progressing procurement for the Open Trade pillar. Over the past year, the programme made good progress against programme objectives and has been awarded an overall score of A.

The programme has overcome two key challenges in its first year, (1) successfully completing procurement of FSp and progressing OTp procurement process due to unforeseen delays, and (2) obtaining buy-in and approval from ASEAN governing bodies and AMS.

Due to procurement delays, the RRp was the only pillar operational for FY 24/25. The FSp completed its inception period, engaging with key ASEAN stakeholders and will move to implementation in the next reporting period. Unforeseen delays to procurement has meant that the OTp will move to inception and then implementation in the FY 25/6. This has slowed EIP delivery but not dampened progress.
All the while, the RRp enhanced its regional presence through strategic appointments, including a regional Senior Regulatory Reform Attaché and a network of attachés based in targeted AMS. This has improved the programme’s ability to coordinate both regional and bilateral workstreams. Other key delivery partners for the RRp – the British Standards Institution (BSI) and the Intellectual Property Office (IPO) – were successfully onboarded and began implementation.

To deliver progress towards programme objectives, the EIP requires buy-in and the approval of workplans from the governing body for each ASEAN sectoral body. The ASEAN Secretariat and sectoral bodies are a key stakeholder for the programme. However, for each output, there are a multitude of often complex approval structures in place. This has proven to be a key challenge to the pace and momentum of programme delivery. Further to this, AMS also require formal agreements to be in place before local delivery can begin, which can require significant time. Nevertheless, the EIP has worked closely with the Office for Product Safety and Standards (OPSS), BSI and IPO to learn from each approval process and implement into the next phase of delivery. This iterative learning process is a key success factor for the programme, which it will take forward in the next phase of inception for FSp and OTp.

Despite challenges to implementation, delivery of the RRp continued to build momentum over the past year. Achievements included a well-attended regional event focused on empowering women entrepreneurs through regulatory reform, expanded engagement with the ASEAN/Organisation for Economic Co-operation and Development (OECD) Good Regulatory Practices Network (GRPN), and the completion of Good Regulatory Practice diagnostics across all Official Development Assistance (ODA)-eligible AMS. Sectoral collaboration also progressed, with the programme agreeing a two-year workplan with the ASEAN Committee on Consumer Protection (ACCP), contributing to the development of ASEAN Product Safety Labelling Guidelines and supporting the assessment of country capacity for the ASEAN Product Injury Portal. BSI supported ASEAN’s standards agenda by completing the End of Term Review of the ASEAN Consultative Committee for Standards and Quality (ACCSQ) Strategic Plan and launching design work in all seven ODA-eligible AMS and Timor-Leste.

Bilateral cooperation on regulatory reform advanced in Indonesia, Vietnam, and the Philippines. In Indonesia, OPSS signed an MoU with the Coordinating Ministry for Economic Affairs and began multiple activities in supporting Regulatory Impact Assessment (RIA) implementation with relevant ministries. In the Philippines, OPSS delivered well-received workshops on product risk assessment and initial knowledge-sharing session on supporting consumer organisations. Following an MoU to support product recall and consumer engagement reforms, OPSS held workshops in Vietnam on consumer policy and incident management. Meanwhile, IPO finalised its delivery model for the intellectual property workstream, signed an MoU with the Government of Vietnam, and began development of an e-commerce code of conduct.

The programme advice and expertise have contributed to substantive changes in ASEAN policy frameworks, such as through support to ACCSQ Strategic Plan and the ASEAN Product Labelling Guidelines. As such, the EIP programme pools its resources to deliver across AMS states, working directly with ASEAN and bi-laterally. This approach is more resource efficient working in partnership with ODA-eligible member states.

In summary, the EIP programme has made good progress it its first year of implementation with ASEAN accreditation and engaged member states to reduce barriers to economic development. This model also aligns well with FCDO’s UK growth agenda, linking UK expertise to key ASEAN and AMS stakeholders to further shared priorities on economic growth. Working in tandem at regional and national level are likely to support outcome and impact level changes in the future. These efforts are expected to improve regulatory framework and business compliance across the region, in line with EIP’s theory of change. Early indications suggesting that its underlying assumptions remain valid as ASEAN and its member states counterparts have been receptive to EIP inputs and translate them into tangible policy change. Thus, demonstrating that the programme will remain relevant and important in building the international foundations for sustainable and inclusive, as the primary economic programme in the regional portfolio.

Lessons and recommendations for the year ahead
The EIP has made good progress towards addressing the recommendations of the last reporting period, which can be found in Annex 1. Looking ahead, this review and period has identified key lessons to address.
Pillar level results frameworks should add more detail of measurable targets. The Regulatory Reform pillar began implementation with a broad set of outputs that reflected programme objectives. However, output indicators require refinement with clear targets set at a regional and national level. Output indicators also should be more detailed and specific, especially when targeting Micro, Small, and Medium Enterprises (MSMEs) and women.

An overarching logframe should be finalised and needs to align with the pillar-level results frameworks to ensure coherence and strategic oversight. While progress has been made in developing the EIP logframe, completion has been delayed due to the staggered mobilisation of the programme’s pillars. As the FSp and OTp move into implementation, the programme will need to consolidate inputs from all pillars to finalise a comprehensive logframe that captures key outcomes at both regional and national levels.

As a new dialogue partner to ASEAN, the programme could do more to amplify its programme delivery and objectives d external stakeholders, as well as internally across UK Government. The EIP should implement a communications strategy that highlights UK expertise, achievements, signals opportunities for growth and investment partnerships, tells the human impact story of the programme and demonstrates ASEAN-UK partnerships. Case-studies or other comms products would be valuable across AMS and xHMG stakeholders.

The programme should formalise its Gender, Equality and Social Inclusion (GESI) approach. While initial steps have been taken—including internal memos and pillar-specific research—these should now translate into targeted activities and measurable outcomes, developed in collaboration with ASEAN and AMS partners.

EIP will need to be agile, scaling or adapting activities in response to potential budget pressures or lessons learned from early delivery. To support this, the programme should develop a clear prioritisation to guide which activities and countries to focus on, in line with portfolio-wide prioritisation being initiated in line with 0.3 ODA reductions. This will help balance broad, light-touch engagement with more targeted, in-depth interventions, depending on strategic value and delivery capacity.

1. Explore the potential areas for collaboration with other dialogue/development partners throughout ASEAN, in order to help maximise our collective impact and prevent duplication.
2. Strengthen cross-pillar coordination to ensure activities are strategically aligned and mutually reinforcing. To maximise the impact, the programme should establish inter-pillar planning sessions to identify overlapping objectives, reduce duplication, and promote synergy across initiatives. By fostering collaboration between pillars, and integrating monitoring mechanisms, we will ensure each pillar contributes to a cohesive and complementary development strategy.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Programme impact	Reduce poverty in AMS through inclusive economic growth
	Regulatory Reform	Financial Services	Open Trade
Pillar impacts	Improved regulatory and standards systems in AMS	Wider access to financial services in AMS	Increased trade by AMS
Outcomes	AMS implement policy recommendations that simplify, codify and harmonise regulations and standards	AMS implement policy recommendations to advance financial inclusion	AMS implement policy recommendations to lower barriers to trade across AMS
Outputs	Reports, tools and policy/implementation recommendations that support AMS to implement ASEAN wide policies on regulation, trade and financial services.
Activities	Technical advice, events, research, and capacity building on ASEAN policies related to regulatory reform, trade and financial services.

The EIP’s theory of change is grounded in a deep understanding of systemic barriers to inclusive economic growth in ASEAN. Key challenges include bureaucratic hurdles and corruption that limit investment and entrepreneurship, market access barriers like non-tariff measures and persistent non-tariff barriers that fragment regional trade and hinder inclusive development, disproportionately affect MSMEs and women-led businesses.

In response, the EIP deploys a three-pronged, mutually reinforcing strategy: strengthening regulatory frameworks, particularly around good regulatory practice, consumer and product safety, quality and standards, and intellectual property rights, expanding access to inclusive and innovative financial services, and supporting open trade and market integration. This is delivered by filling capacity and capability gaps in ASEAN institutions and AMS governments for the implementation of ASEAN reforms. The programme adds value by leveraging UK expertise, technical assistance and government to government knowledge exchange activities. The programme is split into three pillars:
1. Regulatory Reform pillar – this component aims to support AMS in implementing policy recommendations that strengthen regulatory systems and improve standards. This is achieved through in-country capacity building workshops, knowledge transfer, technical assistance and research.
2. Financial Services pillar – aims to improve businesses’ access to finance, particularly MSMEs, to promote inclusive economic development through digitalisation, improving resilience, and increasing financial literacy and inclusion.
3. Open Trade pillar – focused on addressing the overall business environment and trade barriers and policies through technical assistance, capacity building and workshops to facilitate and increase trade between AMS and externally with other countries.
Overall, the Economic Integration Programme is well balanced and targets issues where the UK can make a meaningful contribution and add value through technical assistance. EIP joins up UK-ASEAN objectives and wider FCDO priorities on deepening growth and investment opportunities with targeted markets in ASEAN. Engagement with beneficiaries in Vietnam and Indonesia demonstrate positive and receptive engagement in the programme, which will improve business environments and potentially unlock greater opportunities for UK growth partnership.

The programme continues to deliver against its outcomes and impact indicators from the original business case. However, this could be further developed and considered as the programme looks to set up a new overarching programme results framework. Outcome indicators are required to measure, monitor and track progress towards outcomes and impact of the programme. Whilst the overall results framework encompassing all three pillars is under development, the focus of this annual review will primarily report against the RRp.. The next review period will encompass all three pillars through an overall results framework.

Where possible, data has been disaggregated by sex, geography and the project has meaningfully engaged with in-country stakeholders with high levels of local ownership and engagement. The EIP meaningfully targets and considers UK obligations on gender inclusion and women’s economic empowerment at the outcome level, and it is well considered in the business case; however, this could be strengthened by creating more robust indicators at the delivery level.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is broadly on track to contribute to its intended outcomes, although the ability to measure and verify outcome-level change is currently limited. This is primarily due to the staggered implementation timeline – only one of the three pillars was operational during the review period, with others delayed through the procurement process. The active pillar (RRp) has delivered all planned outputs on time and within budget, demonstrating strong delivery performance.

However, beneficiary feedback from field visits and interviews with key ministries in Indonesia and Vietnam has been consistently positive, offering some evidence of early relevance and influence. Key themes to be drawn from interviews include (1) high level buy in and strong ownership from bilateral countries in Indonesia and Vietnam, (2) regulatory work is driving change in law and implementation projects, and (3) EIP regulatory work aligns well with national trade objectives. The beneficiaries reported that the programme aligns with national and regional priorities, helps tackle policy bottlenecks, and has supported the development of national or regional guidance and frameworks. For example, based on consultation from government stakeholders, outputs from the programme’s support on Good Regulatory Practice (GRP) in Indonesia were considered as inputs for the upcoming amendment process of Law No. 12 of 2011 on the Establishment of Laws and Regulations. The amendment is intended to improve the process on laws and regulations establishment in Indonesia by introducing a regulatory impact assessment approach.

The programme has also supported Indonesia’s efforts to meet key preconditions for OECD accession, particularly in the area of regulatory reform. Indonesia’s accession to OECD would contribute to sustained economic growth by aligning Indonesia’s governance, economic policies and trade standards with international best practice, enhancing investor confidence, improving market efficiency and strengthening trade relations. These insights suggest that the programme is beginning to play a catalytic role, even if outcome-level change is not yet measurable.
[note] Center for Indonesian Policy Studies. Unlocking Indonesia’s Economic Potential Through OECD Accession. Policy Brief: 29. July 2025. https://repository.cips-indonesia.org/media/publications/619206-unlocking-indonesias-economic-potential-a8d0e8ee.pdf

While major assumptions in the theory of change have not yet been explicitly tested, initial feedback indicates that government buy-in remains strong, with active participation and endorsement from relevant institutions. Workshop participants are well-positioned within their roles to apply the learning, and stakeholder feedback indicates improved knowledge to implement policy reforms. While there is emerging evidence that participants are starting to use the tools and approaches introduced, uptake varies across institutions, highlighting the need for continued follow-up to support consistent application and institutional embedding.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme aligns well with ASEAN-UK partnership priorities as set out in our Plan of Action, and the Department’s priorities on building international foundations that support sustainable and inclusive growth for key markets of the future It is broadly on track to contribute to its intended outcomes, despite measurement and verification of outcome-level changes remaining limited at this stage. Perspectives from beneficiary feedback indicate that the programme is progressing well towards outcomes, reflected in its overall A score, indicating delivery is meeting expectations.

## C. DETAILED OUTPUT SCORING

For this annual review, the output scoring focuses on the RRp, as it is the only workstream that has been actively delivering throughout the past year. The delivery partner has also finalised a results framework for this pillar, which is being used to guide and inform the review process.

Output Title 1	Relevant ASEAN and/or AMS stakeholders have improved capability and capacity to implement fundamental and/or emerging good regulatory practices as a result of Regulatory Reform Pillar interventions; with consideration of Women’s Economic Empowerment (WEE)/MSME/GESI concerns where relevant.
Output number:		1	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 1a: Number of regional / bilateral Good Regulatory Practice (GRP) capability and capacity building event(s) held	Planned: / 1 regional, 4 bilateral	Exceeded: 2 regional events: / GRP 101 Workshop to the ASEAN – OECD Good Regulatory Practice Network (GRPN) (Nov 24) / Co-hosted 9th Annual OECD – GRPN Meeeting (Nov 24) / 6 bilateral events: / Indonesia: / GRP Round Table Discussion (Sept 24), Good Regulatory Practices (GRP) 101 (Nov 24), 2x Regulatory Exchange Call with DBT Regulation Directorate (Dec 24, Jan 25), Regulatory Impact Assessment (RIA) 101 Workshop (Feb 25), RIA Guidelines and Threshold Workshop (Feb 25)
Output indicator 1b: Number of participants in regional/ bilateral GRP events	Planned: 25 Regional, 80 bilateral	Exceeded: The RRp engaged with 40 regional and 218 bilateral participants.
Output indicator 1c: Number of regional/ bilateral GRP products [e.g. policy/guidelines/ tools/ recommendations] developed	Planned: 1	Achieved: 1 (the ASEAN – OECD Good Regulatory Practice Network (GRPN) Workplan for 2025)
Output indicator 1d: Number of GRP case studies tracking policy development & implementation	Planned: 0	N/A: 0 – (case study methodology under development by M&E supplier)
Output indicator 1e: Number of GRP events promoting the inclusion of MSMEs and women and/or addressing GESI	Planned: 1	Achieved: 1 (Panel discussion on Effective Regulatory Reform Frameworks to Enhance MSME and WEE Outcomes in ASEAN, held during the OPSS Research Launch Event, with discussion materials published on ASEAN Access Learn)

Briefly describe the output’s activities and provide supporting narrative for the score.
The output is scored A+ as all the indicators have been fully achieved with two indicators exceeded, demonstrating that the programme has largely delivered on its commitments for the year.

Over the past year, OPSS spearheaded efforts to reinvigorate the OECD-ASEAN GRPN at the regional level. This involved engaging non-attending member states into the network and securing agreement to expand the network’s scope to continuous, in-year collaborative efforts. At the 9th OECD-ASEAN GRPN Meetings, OPSS facilitated a pre-meeting workshop on foundational aspects of Good Regulatory Practice – ranging from policy coherence to practical application – which responded directly to member requests and received positive feedback.

Another key regional highlight was the launch and dissemination of OPSS-commissioned research on empowering women entrepreneurs and MSMEs through regulatory reform. The report highlighted evidence-based recommendations and case studies from Indonesia, Malaysia, and Vietnam. The launch event featured panel sessions which facilitated discussions between a wide range of relevant government stakeholders, women entrepreneurs and support organisations. These discussions connected the findings with strategies for designing a regulatory environment that is more enabling for women and MSMEs. As a result, the report and launch event generated actionable ideas. The panel discussion recording and key research findings have been uploaded to the ASEAN Access Learn platform, becoming part of ASEAN’s MSME knowledge ecosystem. This ensures that MSME members can access the materials anytime, extending the impact of the research and the launch event.

In Indonesia, OPSS signed an MoU with the Coordinating Ministry for Economic Affairs and began multiple activities in supporting RIA implementation with relevant ministries, aligned with Indonesia’s OECD accession efforts. The initial plan included delivering in-country support to the Philippines and Vietnam, adding more AMS as implementation matures but the progress was influenced by evolving local context. In the Philippines, OPSS initiated work with the Anti-Red Tape Authority (ARTA) on RIAs and business licensing; however, a realignment of priorities at ARTA led to a brief pause in the work. In Vietnam, delays were due to government restructuring, OPSS is now working with the Ministry of Public Security to revise its approach and continue supporting licensing reforms. A clear path forward has been identified for both countries, and full implementation is expected to begin next reporting period. These efforts will continue to enable the UK to support AMS in implementing the ASEAN Guidelines on Good Regulatory Practices.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

OPSS will continue to provide technical assistance at regional level network meetings to enhance regulatory practices. At the AMS (national) level, OPSS has had mixed results as activities were affected by changing government structures, priorities and mandates in Philippines and Vietnam. To improve delivery towards programme outcomes, this output will include national level output indicators with defined interventions to support capacity building and capability of member states when the MEL framework is finalised.

See recommendation 1 & 2: An overarching results framework will be produced for the EIP, which will include reviewing current results frameworks for individual pillars to ensure they align with the theory of change and target interventions at the regional and national level. By doing so, the programme will benefit from enhanced monitoring, evidence and learning.

Output Title 2	Relevant ASEAN and/ or AMS stakeholders have improved capability and capacity to effectively develop and implement best practice in consumer product safety and e-commerce as a result of Regulatory Reform Pillar interventions; with consideration of WEE /MSME /GESI concerns where relevant.
Output number:		2	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 2a: Number of regional/ bilateral Consumer Product Safety (CPS) capability and capacity building event(s) held	Planned: / 2 regional, 7 bilateral	Achieved: The RRp has held 2 regional events: / ACCP capacity building event on: (i) product risk evaluation and product risk assessment (Aug 2024); and (ii) market surveillance / 7 bilateral: / Indonesia (4 events): / Market surveillance reporting system M&E capacity building (Dec 24), 3x survey and field visits for INAMS evaluation Feb – Mar 24) / Philippines (3 events): / Workshop on the role of consumer organisation in product safety (Nov 24); / Product risk and market surveillance workshops in Manila and Ilo-Ilo (Feb 25)
Output indicator 2b: Number of participants in regional/ bilateral CPS events	Planned: 44 Regional, 126 bilateral	Exceeded: The RRp engaged with 73 regional and 135 bilateral participants.
Output indicator 2c: Number of bilateral/ regional CPS products [e.g. policy/guidelines/ tools/ recommendations] developed	Planned: / 1 bilateral	Achieved: 1 bilateral (Indonesia report on Indonesia Market Surveillance evaluation)
Output indicator 2d: Number of CPS case studies tracking policy development & implementation	Planned: 0	N/A: 0 – (case study methodology under development by Monitoring &Evaluation (M&E) supplier)
Output indicator 2e: Number (#) of CPS events* promoting the inclusion of MSMEs and women and/or addressing GESI	Planned: 1	Achieved: 1 (Panel discussion on Advancing Inclusive Growth: Ensuring Product Safety for Women Entrepreneurs and MSMEs, held during the OPSS Research Launch Event, with discussion materials published on ASEAN Access Learn)
Briefly describe the output’s activities and provide supporting narrative for the score. / The output is scored A, reflecting overall delivery that has exceeded expectations for this review period. / At the regional level, OPSS secured endorsement from the ASEAN Committee on Consumer Protection (ACCP) for a two-year workplan, despite initial lack of buy-in by ASEAN on the bilateral (in-country) delivery plan. Following the agreement on the workplan, OPSS delivered two regional capacity building events: i) product risk evaluation and product safety assessment and ii) market surveillance. workshop and endorsement from ACCP scheduled for the first half of next year. validation workshop and finalisation scheduled in the first semester of next. OPSS is also supporting the development of ASEAN Guidelines on Product Safety Labelling. The inception report has been approved, with a validation workshop and endorsement by ACCP scheduled in the first half of next year. OPSS is also conducting an updated feasibility study on an ASEAN Product Injury Portal and will share the result at the next ACCP meeting in June 2025. / In Indonesia, OPSS supported the Ministry of Trade to strengthen INAMS (Indonesia Market Surveillance), a localised version of the Product Safety Risk Assessment Methodology (PRISM). The first milestone, a review of INAMS, was completed through multiple capacity building sessions and field visits. In the Philippines, OPSS delivered well-received workshops on product risk assessment and initial knowledge-sharing session on supporting consumer organisations. This focus on consumer engagement will continue over the next year and expand to include business engagement. After signing an MoU to support reforms in product recall and consumer engagement, OPSS delivered workshops in Vietnam on consumer policy (including cross-agency cooperation) and incident management focusing on product recall. Additionally, OPSS hosted a major event showcasing research on empowering women entrepreneurs and MSMEs through regulatory reforms, including in consumer product safety. The discussions from the event have been uploaded to the ASEAN Access Learn platform, allowing MSME members to access them anytime. / Describe any changes to this output during the past year, and any planned changes as a result of this review. / OPSS has done well to deliver against the planned outputs over the FY24/25. To build on this progress, this output will require adapting how it incorporates GESI objectives into interventions meaningfully. By combining output 1e and 2e and hosting a single event empowering women and MSMEs to target key stakeholders on consumer protection and regulatory reform. Therefore, the EIP will consider how to capitalise on opportunities for women and MSMEs highlighted in the research. / See recommendation 4: EIP will look to homogenise its approach to gender inclusion with measurable and actionable targets for delivery partners. A gender strategy and its implementation will also allow the programme to move away from hosting single events and target women’s economic empowerment throughout all three delivery pillars.

Output Title 3	Increased capability and capacity of regional stakeholders (ACCSQ, specific Working Group (WG)/Product Working Groups (PWGs) and selected AMS standards and the national quality infrastructure (NQI) institutions) to implement best practice in standards and NQI, ensuring consideration of WEE/MSME/GESI concerns where relevant.
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 3a: Number of engagements to support the Roadmap for Sustainable Development Goals (SDGs) actions	Planned: 2	Achieved: 2 / Webinar on the Roadmap of ASEAN Standards Harmonisation to support SDGs implementation (Feb 25); Webinar on Standards for Climate Action (Feb 25)
Output indicator 3b: Number of stakeholders engaged in Roadmap-related SDG actions	Planned: 40	Exceeded: 80 regional stakeholders under ACCSQ
Output indicator 3c: Number of capacity building events conducted for ACCSQ, WG/PWGs, and NQI institutions	Planned: 1	Achieved: 1 / Webinar on Standards for AI (Feb 25)
Output indicator 3d: Number of materials developed to support standards and NQI	Planned: 1	Achieved: 1 (ACCSQ End-Term Review 2016 – 2025)
Output indicator 3e: Number of SNQI events promoting the inclusion of MSMEs and women and/or addressed GESI	Planned: 1	Achieved: 1 (Panel discussion on Advancing Inclusive Growth: Standards and Quality Compliance for Women Entrepreneurs and MSMEs, held during the OPSS Research Launch Event, with discussion materials published ASEAN Access Learn)

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall performance shows that the programme is on track and delivering against expectations, justifying a score of A.

Despite delays in finalising contractual arrangement, BSI delivered several targeted projects during the review period, building on earlier support. This included the development of the ASEAN Standards Harmonisation Roadmap to support SDG implementation and capacity-building webinars on standards for AI and the circular economy.

BSI also supported the End-of-Term Review of the ACCSQ Sectoral Plan 2016–2025. This was successfully completed through inception, workshops, and multiple drafts, with a public version to be published in Q1 FY 25/26. Following this, the UK was invited to support the development of the ACCSQ Strategic Plan 2026–2030, recognising the UK’s commitment, BSI’s expertise, and the programme’s responsiveness. BSI has led the process through idea generation, workshops, and several drafts, closely following ASEAN guidance, with endorsement expected in July. BSI also shared its expertise on standards and quality compliance during the research panel discussion event, which focused on how these areas can empower women entrepreneurs and MSMEs. The discussion is now available for MSMEs in the region via the ASEAN Access Learn platform.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There are no planned changes to this output.

Output Title 4	Enhanced capability and capacity of regional stakeholders on Intellectual Property (IP) protection and enforcement and the use of IP for business growth, ensuring consideration is given to WEE/MSME/GESI concerns where relevant.
Output number:		4	Output Score:	N/A
Impact weighting (%):		N/A	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 4a: Number of bilateral IP products [e.g. Code of Conduct (CoC), toolkits] developed	Planned: 0	N/A; IPO held initial discussions with Malaysian and Vietnamese government on the e-commerce CoC and ASEAN Secretariat on the IP Toolkits and Webinars for AMS. In February 2025, the MoU between Vietnam and the UK on preventing counterfeiting and IP infringement was signed. IPO has yet to plan any milestones for this FY due to our focus on designing the programme framework and ensuring stakeholder buy-in.
Output indicator 4b: Number of capacity building seminars delivered	Planned: 0	N/A; IPO proposed the IP Toolkits and webinars to ASEC and they demonstrated strong interest in the programme as this is aligned with their new 20-year IP Action Plan. IPO has yet to secure endorsement from ASEC and plan to secure it in the beginning of FY25/26. IPO has yet to plan any milestones for this FY due to our focus on designing the programme framework and ensuring stakeholder buy-in.
Output indicator 4c: Number of IP case studies tracking policy development & implementation	Planned: 0	N/A; the evaluation contractors (CSES) will support IPO in developing IP case studies as agreed by IPO and OPSS. / IPO has yet to plan any milestones for this indicator for this FY due to their focus on designing programme framework and ensuring stakeholders buy-in.

Briefly describe the output’s activities and provide supporting narrative for the score.
IPO has not yet begun formal delivery of its workstream, as it awaits endorsement of its concept note from the ASEAN Working Group on Intellectual Property Cooperation (AWGIPC). In FY 24/25, IPO focused on programme design, securing stakeholder support, recruiting key personnel, and onboarding delivery partner Rouse, laying the groundwork for implementation in FY 25/26. The workstream includes developing two national IP e-commerce Codes of Conduct (CoCs), three ASEAN IP toolkits, and capacity-building webinars for all AMS. IPO also spoke at the research launch event on leveraging IP for business growth in ASEAN, especially for women entrepreneurs. The discussion is now available for MSMEs in the region via the ASEAN Access Learn platform.
Progress has already begun in Vietnam, where IPO signed an MoU with the Ministry of Industry and Trade to strengthen IP enforcement and market surveillance, despite institutional changes within the Vietnamese Government. In Malaysia, initial interest has stalled due to internal restructuring, prompting consideration of a regional model CoC instead. A Model IP e-commerce CoC aims to address both regulatory gaps and practical IP enforcement challenges across the region and will include recommendations for ASEAN on key e-commerce regulations and practical guidelines for implementation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There are no planned changes to this output.

## D: VALUE FOR MONEY

Key cost drivers and performance

The EIP has not yet transitioned into full delivery phase across all three pillars. As such, the primary delivery was through OPSS as the implementing partner for RRp, and the inception phase of the FSp through Cadmus. Value for money has been assessed using the the 5 E’s of FCDO’s value for money framework – economy, efficiency, effectiveness, equity and cost-effectiveness.

Efficiency: OPSS operates on a cost-recovery model and uses a hybrid delivery model, which has proven to be economic, effective and efficient as a delivery partner of the preceding ASEAN Economic Reform Programme (AERP). The network of attachés based in the region, supported by UK experts and local contractors, provides on-the-ground programme resource and represents better VfM as it supports more effective use of UK experts remotely and in-person, reducing travel costs and but also harnessing local expertise and context. The network has also accelerated the delivery of focused support to ASEAN and AMS helping the RRp to meet and exceed all its projected outputs for this year.

Economy: Delivery partners seek to organise events (hybrid and in-person) to coincide with pre-planned in-person ASEAN regional events, to maximise attendance and reduce AMS travel costs. The programme also maximises opportunities to host events at ASEAN or AMS offices to avoid venue hire.

As the FSp and OTp are being delivered by the same commercial partner, the programme anticipates some economies of scale on programme management without impinging on the quality of delivery as each pillar will continue to have distinct team leads. Furthermore, costs are aligned with the rate cards presented in their bids, which provides economic Value for Money (VfM).

Effectiveness: All EIP pillars will continue to be designed with a degree of agility and flexibility to adjust resources and activities in response to evolving priorities and needs to capitalise on new opportunities and challenges, helping to maximise the impact of programme interventions, allowing the programme to replicate and scale impactful interventions and pause less successful activities, and driving better VfM over the course of the programme’s lifetime. This is evidenced in OPSS’ response to changing priorities in the Philippines and Vietnam, whereby it was able pivot quickly to agree new areas of co-operation which will help to ensure resources are directed towards the most relevant and impactful activities for AMS, which will optimise the pillar’s efficiency in achieving its objectives. For the Intellectual Property workstream, the commercial arrangement with Rouse will allow the Intellectual Property Office to scale delivery based on targeted needs and available resources.

Equity: A robust contract arrangement for commercial partners, underpinned by annual work plans, will support the design and delivery of an agile and responsive programme. Further, to ensure equity and VfM, GESI considerations are fully integrated at all stages of delivery and are regularly reported on in the MREL framework.

Cost effectiveness: The programme’s pillars represent good value for money, which will increase as it enters a phase of full delivery across all workstreams and pillars, because fixed costs, such as the costs of the UK core team for Regulatory Reform pillar and expert costs for Financial Services and Open Trade pillar, will be spread over more activities and outputs.  As the programme matures, the programme expects to start to see some progress towards programme outcomes, which will support better measurement of cost-effectiveness. As outlined above, EIP is already seeing early signs that programme outputs have potential to be translated into policy and systems changes, . For example, through interviews undertaken for the annual review, interviewees confirmed that the programme’s interventions under the RRp are already helping to inform legislative reform in one AMS, which will impact the regulatory governance for at least six ministries.

E: RISK

Overview of risk management

The programme risk register contains approximately 16 risks of varying severity of ‘minor and ‘moderate’. These risks are reviewed quarterly by the Programme Responsible Owner (PRO) and the EIP team. Over the past year, the programme has maintained a moderate overall risk rating, with regular risk mitigation measures embedded in the programme design and implementation processes. The risk register has been actively monitored and updated as part of quarterly reviews, ensuring that risks are identified early and managed appropriately.

People and Safeguarding Risks have shown a decreasing trend, reflecting strengthened safeguarding measures, improved staff training, and effective partner due diligence.

Reputational, Strategic, and Contextual Risks have remained stable, with no significant changes in the external environment or stakeholder relationships that would elevate the risk level. Existing communication and engagement strategies have effectively mitigated these risks.

Financial and Fiduciary risks are classified as major risks (before mitigation) due to potential budget changes following the UK decision to reduce the total UK ODA budget to 0.3% of GNI by 2027. This has resulted in EIP temporarily pausing rollout in new ASEAN member states as a precaution whilst budgets are clarified. To mitigate against this risk the EIP programme has focused on priority areas and enhancing efficiency through results-based approaches. This includes developing scenario planning for future years to guide strategic decisions, while maintaining transparent and regular communication with delivery partners. Aligning current-year activities with existing spending plans helps sustain momentum and ensures that limited resources are allocated effectively and strategically. As a result, the residual risk factoring mitigations is recorded as ‘minor’ risk.

A Policy and Programme delivery risk was the protracted procurement of the delivery partner under the OTp, which took significantly longer than anticipated because a bidder raised a number of potential issues with the procurement. This delay created a risk to programme delivery timelines and achievement of outputs within the financial year. Looking ahead, this risk is now resolved as all partners are now onboarded.

In summary, all risks are actively managed through enhanced partner coordination through regular fortnightly catch ups, through planning and monitoring processes, and through increased oversight of delivery timelines and quality assurance. Any new risks (or any changes to existing risks) are forwarded to the Senior Responsible Owner (SRO), who reports it to the EIP Board and updates the Aid Management Platform (AMP) accordingly. The quarterly EIP board meeting provides a mechanism to update board members on programme management updates and risks, as well as to facilitate discussions on risk mitigation and the identification of emerging risks. Continued attention will be given to managing delivery-related risks to ensure timely and high-quality outputs.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Programme Management

The SRO for EIP is the FCDO’s Southeast Asia Regional Director for Economics and Trade Policy. They are supported by EIP Economic Adviser, a PRO, a Programme Manager, and a Programme Officer within the UK Mission to ASEAN. Both SRO and PRO have been completed the ProF training as SRO and PRO including the Contract Management Foundation training.

Ways of working between delivery partners and the EIP Programme Team have improved in the second year of EIP, with a consistent rhythm of biweekly catchups covering delivery, risk, and financial updates. The EIP programme team monitors progress against set milestones and gathers evidence of delivery and performance. This includes monthly, quarterly and annual reporting from delivery partners. But also reporting to internal and external governance structures such as the Quarterly UK Mission to ASEAN Portfolio Board, EIP board meetings and ASEAN-UK Project Management Team Steering Committee (PMT) and the Project Steering Committee (PSC) meetings.

The inaugural PMT meeting was held on 21 August 2024. The PMT acts as a preparatory forum ahead of the PSC session, with the purpose of finalising the EIP review of last year’s activities and the work plan for the year ahead for the PSC’s endorsement and approval. The first PMT was attended by the Country Coordinator for ASEAN–UK Economic Relations, representatives from the UK Mission to ASEAN, and the ASEAN Secretariat representation from ASEAN’s own Programme Cooperation and Project Management Division (PCPMD).

Meanwhile, the PSC, comprising of the ASEAN Secretariat and Economic Officials from AMS, will take place yearly in May, leading to the endorsement of achievements and future work plans.

Reporting and evidence collection have been resource-intensive, requiring significant effort to ensure quality and timeliness. To mitigate these challenges, the EIP Programme team introduced quarterly coordination meetings with delivery partners to improve communication and alignment. The programme also adopted a more flexible approach to work planning, allowing adjustments to timelines while maintaining compliance with governance and financial requirements.

Detailed due diligence reviews were completed for Cadmus as the lead partner on Financial Services pillar. This has provided assurance that Cadmus is able to meet financial, operational, and governance standards therefore reducing risks related to compliance, performance, and value for money.

Additionally, due to evolving circumstances particularly regarding programme-funded roles and commercial obligations within the OTp, the SRO decided to amend the business case, extending the programme’s duration to June 2029. This amendment ensures the programme remains responsive to changing conditions, reduces potential risks, and enhances the overall confidence to deliver programme outcomes.

Delivery

The RRp is currently the only pillar in full delivery mode. Both OPSS and IPO are operating at full capacity, supported by regional and in-country attachés in Indonesia, the Philippines, Vietnam, Laos, and Cambodia. BSI officially joined in May following a delay in signing the grant agreement, although they had already been delivering regional activities under an interim contract. With the full team now mobilised, Regulatory Reform pillar delivery partners have been able to meet or exceed most output milestones.

On the quality of delivery, feedback from the ASEC and in-country counterparts has been positive, highlighting strong alignment of technical assistance with regional and national priorities as well as valuable cross-country learning. Stakeholders appreciated learning from UK experts on global standards, especially when this knowledge was contextualised to local needs. This was evidenced by interviews with beneficiaries in Indonesia and Vietnam and post-event surveys. Workshops were deemed to have improved participants’ technical knowledge, were rated highly relevant, and showed strong potential for practical application, further supported by the presence of attachés that followed up with delegates on application. While feedback from Vietnam suggested improvements in timely distribution of final materials and more country-specific sessions during the group events, like the UK inward mission, these are operational refinements that do not affect the overall success in the pathway toward achieving intended outcomes.

During the review period, Cadmus was appointed as the delivery partner for the FSp. With extensive technical expertise and regional experience, Cadmus is well-positioned to support ASEAN’s financial sector goals and priorities. The four-month inception phase focused on developing implementation strategies through both regional and country-level engagement. This structured approach ensured that the subsequent implementation is well-aligned with local contexts, effectively targeted, providing a strong foundation for effective delivery.

The inception phase of the Financial Services pillar has laid a strong foundation for shaping our strategic direction in the next phase of implementation. During inception, we actively engaged with ASEAN divisions and sectoral bodies, including presenting at the Working Committee on Financial Inclusion on the proposed project pipeline and how these were with regional priorities. This period also saw the launch of the End-Term Review of the AEC Blueprint 2016–2025, which will provide valuable insights to inform future interventions whilst developing a strong relationship with ASEAN.

The EIP programme has progressed at varying stages across its three pillars. Looking ahead, we will prioritise designing ways of working and mechanism that enable stronger collaboration across EIP pillars. The Theory of Change (ToC) will provide foundation for this process, ensuring that synergies are embedded and maximising impact across Regulatory Reform, Financial Services and Open Trade pillars.

Commercial

As a result of the FSp inception phase, Key Performance Indicators (KPIs) for commercial partner, Cadmus, have been developed, providing a clear framework to assess partner performance across the programme lifecycle. These KPIs are aligned with programme objectives and include milestones for the inception, implementation, and closure phases, ensuring delivery accountability at each stage. At the time of writing, the OTp had not concluded the procurement process.

Additionally, the charging rates for the Service Provider Management Team (SPMT) and Service Provider Subject Matter Experts (SPEx) of Financial Services pillar have been formally agreed and are now being applied though the task order as the pillar moves into its first - year of implementation. This approach has enhanced consistency, transparency, and value-for-money. The introduction of these measures has improved the programme’s ability to track partner performance, manage commercial risks, and ensure timely delivery of results. These KPIs was embedded into contract management and partner review processes, ensuring that commercial arrangements continue to support effective and efficient programme delivery.

Financial Performance

There were several challenges faced regarding the financial performance of EIP due to delays in implementation and commercial processes. Financial forecasts were regularly reviewed and adjusted accordingly as mitigation measures. As a result of these measures final spend in FY24/25 achieved 99% of the latest forecast of which 68% was delivered through the RRp, 29% committed to the FSp and the remaining expenditure committed to programme operating expenses (staffing, Monitoring Evaluation and Learning, and communications). The OTp spending was moved to FY25/26 due to procurement delays.

On RRp, at the end of FY24/25 OPSS recorded 100% budget expenditure in late March 2025. This was closely monitored through weekly checks and regular updates to the EIP programme forecast. Most of the spending occurred in quarter four FY24/25, this was because of a protracted reconciliation process of downstream partners, which took some time. As a result, quarters two, three and four invoices were submitted at the end of the year. Therefore, the team will look to improve this process so that the spending can be spread out closer to quarterly basis rather than collated at the last quarter.

On FSp, Cadmus reported a spend of 97% of allocated budget in March 2025. Delay in spending occurred due to the pushback of procurement timelines, with the contract signed in November 2025 and inception phase ending in March 2025. KPIs were developed in inception phase, thus taking effect at the start of the implementation phase from April 2025 onwards.

There is no audited financial statement required and received yet for this period of annual review. OPSS are not obligated to provide audited financial statements under the MoU as another UK government department.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring: Over the review period, the programme undertook regular monitoring and stakeholder engagement across its three pillars. The programme team worked closely with partners to gather annual performance data and contextual insights. For example, the regulatory reform pillar submitted quarterly and annual reports, providing structured updates on activities, achievements, and challenges. In addition, the programme facilitated quarterly Delivery Partners Coordination Meeting, which served as a platform to review progress, surface delivery risks, and discuss adaptive responses.

As part of the Annual Review process, the review team conducted in-country visits to Indonesia and Vietnam. In Indonesia, consultations were held with the Coordinating Ministry of Economic Affairs, Ministry of Trade, Ministry of National Development Planning, and National Law Development Agency – Ministry of Law. In Vietnam, meetings included the Vietnam Competition Commission, Ministry of Industry and Trade, and the Vietnam Women Entrepreneur Council. These engagements helped assess not only technical progress of the programme, but also the extent to which it aligns with partner country priorities. To ensure broader perspectives, the team also interviewed EIP focal points in UK embassies in Indonesia, Vietnam, and the Philippines as well as EIP’s delivery partners. This provided a cross-country lens on implementation and generated useful feedback for internal coordination and adaptive management.

Evaluation: No evaluation was conducted during the current review period. However, the programme has initiated internal discussions on its evaluation approach and is in the process of identifying suitable opportunities for evaluation activities. If commissioned, future evaluations are expected to focus on midline and endline evaluation, with emphasis on evaluating processes, outcomes, and VfM rather than conducting full-scale impact evaluations. The purpose of these evaluations will be to assess how programme activities are being implemented, whether intended changes are starting to materialise, and whether resources are being used effectively to deliver results. The evaluation plan is still under development and will be further refined and agreed internally in the next period, with consideration given to timing, resourcing, and the maturity of programme components.

Learning:
The programme does not currently have a formal learning strategy in place. However, an overarching MEL plan is being developed, which will incorporate a structured approach to learning across the programme’s pillars. To date, learning has been gathered on an ad hoc basis, primarily through delivery partner’s quarterly and annual report, the programme’s annual review, and discussions in quarterly delivery partners meetings which will then inform the EIP’s board. The forthcoming MEL plan is expected to strengthen learning by introducing a more deliberate and strategic approach to learning – one that supports adaptive management, informs decision-making, and helps surface cross-cutting insights across the programme.

Date of last narrative financial report	March 2025	Date of last audited annual statement	N/A

Annex
Annual Review’s Recommendation Tracker

Recommendations from the 1st Annual Review	Progress
Recommendation 1: The overarching results framework for the EIP will be finalised by end January 2025. The results framework is essential for providing a clear and structured approach to monitoring and evaluating the progress, ensuring all activities align with the intended objectives. To achieve this, EIP could organise a MEL workshop with all partners, once they are onboard, with support from the MEL advisers.	The development of the EIP overarching results framework is currently in progress and is expected to be shared with delivery partners by Q3 FY 25/26. The results framework for the Regulatory Reform Pillar has already been developed and agreed, and it will contribute to the overarching framework alongside the frameworks for the Financial Services and Open Trade pillar.
Recommendation 2: Since the EIP encompasses three pillars, each with multiple delivery partners and subcontractors, it is crucial to have a consolidated communications strategy document that all partners can use to ensure unified messaging about the programme. This document is being developed.	Cadmus will be taking the lead on communications for the EIP programme, which encompasses its three pillars, including the RR Pillar. They are currently developing a comprehensive communication strategy that outlines the overall approach and ways of working. Separately, the communications strategy specific to the RR Pillar has been finalised and inclusive of all RR Pillar delivery partners. OPSS is working closely with the UK Mission to ASEAN’s Communications Team to coordinate upcoming communication activities and ensure they align with the broader EIP messaging. Once the overarching strategy is complete, Cadmus and OPSS will collaborate to ensure consistency and alignment across all communications.
Recommendation 3: Finalise agreements with lead implementing partners for each pillar to prevent delays in programme implementation, as currently, only the RRp has a lead implementing partner onboarded. Following this, ensure the completion of key EIP pillar documents, including the implementation plan with pillar governance and communication strategies, the activity-based budget, and the results framework for all partners, should be finalised. This will establish robust implementation plans and monitoring mechanisms for each pillar.	The implementation MoU between OPSS and FCDO was signed in July 2024. All contracts and grants for sub-contractors for the Regulatory Reform pillar, except for the delivery grant agreement with BSI, which took longer than anticipated due to a change in the agreement modality. Delivery partner agreements for the Financial Services pillar have been finalised. EIP has also received approval to proceed with the Open Trade contract signing in Q1 FY25/26.
Recommendation 4: Continue to use the EIP Board to agree and implement recommendations on strategic decisions related to resourcing, risk, in-country delivery and results monitoring. Agreeing these with the EIP board ensure a consensus-based approach to regional delivery with relevant FCDO Posts.	The EIP has been using Board meetings to discuss and agree strategic decisions, supplemented by quarterly delivery partner meetings to coordinate implementation, share progress, and address operational issues.