## Logframe
PROJECT NAME: India UK Economic Cooperation Programme (ECOP) - Milestones are cumulative
IMPACT |  | Impact Indicator 1 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (December 2027) | • Macro-economic climate does not deteriorate significantly • Political commitment to infrastructure development and sustainable growth is maintained at the national and state level, especially against the backdrop of upcoming General Elections • Political will exists to undertake reforms based on evidence/recommendations generated through the programme across States and Centre The NITI SDG Dashboard is the most comprehensive set of inclusive growth indicators available publicly in India. However, NITI is measuring SDG indicators at a state level first and then aggregating nationally. ECOP Programme interventions at State level may be limited
Sustainable and inclusive economic growth in India |  | India's SDG performance rank | Planned |  | Improvement or maintainance | Improvement or maintainance | Improvement
|  |  | Achieved | 109 (score 63.99) | No source data updates
Source
NITI Aayog SDG Index https://dashboards.sdgindex.org/rankings
OUTCOME 1 |  | Outcome Indicator 1 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (December 2027) | Assumptions
Private financial flows support increased financing for sustainable economic development | Demonstrate change narrative NAP, State level, enterprise (business level) | Evidence of contribution to increasing private sector investment/ financing for infrastructure and climate | Planned |  | N/A | Change story | Change story |  | The priorities of overall UK-India bilateral agenda do not change significantly • Government of India (particularly DEA) is supportive of suggested interventions and support attribution of resulting successes to the programme, where possible. • State level commitment to the sector to incentivise development e.g. – clearance for projects, tax incentives, tariff structure for private sector/PPP developers
|  |  | Achieved | 0 |  | 1 projected change story | 2
Source: DPIIT, PPP-VGF, UNDP
PPIAF Investment pipeline Ease of doing business Policy recommendation implemented
OUTCOME 2 |  | Outcome Indicator 2 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (December 2027) | Assumptions
Public financial flows support increased financing for sustainable economic development |  | Evidence of contribution to increased public revenue and incorporation of climate action in public financial management systems at national and/or sub-national levels | Planned |  | N/A | Change story | Change story |  | •Adequate resources (optimal staffing and financing) provided and maintained by concerned government agencies (both HMG and GoI) for implementing and sustaining interventions which will be delivered bilaterally •Work is prioritised in a manner that allows for logical closure of programme within the year in case funds for future years are not made available • Government of India ensures that any member of staff who is trained through the programme is then deployed for actual implementation of suggested reform area.
|  |  | Achieved | 0 |  | 1 projected change story | 2
Source: NIPFP /WB - 1, PPP-VGF, CEEW
Economic survey in the budget State level competitive ranking Policy recommendations implemented
OUTPUT 1 |  | Output Indicator 1.1 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (Jan 2027) | Assumptions
Investable sectors / projects identified/developed in line with international standards, that attract more private sector financial flows. |  | Number of government officials/staff whose knowledge/understanding has been increased through ECOP capacity building initiatives/TA | Planned |  | 0 | 75 | 100 |  | •Reform effectiveness and sustainability is ensured through adequate resource allocation during and post programme implementation period by Government of India. This will allow for Impact assessment to be undertaken in future years • Any gains made from new/improved infrastructure, stronger financial markets and improved public finances are deployed (at least partially) in a way which is inclusive and sustainable
|  |  | Achieved | 0 | 0 | 206 | 0
Source: PPP WS Northern and Southern
| PPP, VGF |  | Programme reporting , Annual perception survey and training feedback
|  | Output Indicator 1.2 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (Jan 2027)
|  | Number of PPP projects supported and or advanced to the next stage of development and implementation | Planned |  | 25 | 20 | 0
|  |  | Achieved | 0 | 26 | 29 | 0
Source: PPP WS
RISK RATING
IMPACT WEIGHTING 25% |  | x
OUTPUT 2 |  | Output Indicator 2.1 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (Jan 2027) | Assumptions
Recommendations and improvements to Public financial frameworks and improved revenue generation and management | WB, ICTD, CEEW | Number of technical assistance/research papers strengthening public finance presented to Central and/or State Governments | Planned |  | 4 | 7 | 13 | 0 | •Government of India ensures that any member of staff who is trained through the programme is then deployed for actual implementation of suggested reform area. •Reform effectiveness and sustainability is ensured through adequate resource allocation during and post programme implementation period by Government of India. This will allow for Impact assessment to be undertaken in future years
|  |  | Achieved | 0 | 6 | 6
Source: WB - 2, ICTD - 1, NIPFP - 2024, CEEW - 2, MH - 1
Programme reporting
|  | Output Indicator 2.2 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (Jan 2027)
|  | Number of individuals supported who report perceived improvement in capacity and ability, attributed to programme interventions for PFM | Planned |  | 0 | 100 | 200
|  |  | Achieved | 0 | 0 | 82
Source: WB Finance Department, CBDT/ ICTD - , CEEW - 40
Annual perception survey and training feedback
|  | Output Indicator 2.3 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (Jan 2027)
|  | Number of states supported in PFM. | Planned |  | 0 | 3 | 5
|  |  | Achieved | 0 | 0 | 3
|  |  | Source WB, CEEW, ICTD | [5 empty] | RISK RATING
IMPACT WEIGHTING 30%
OUTPUT 3 |  | Output Indicator 3.1 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (Jan 2027) | Assumptions
New/Improved Business Environment and climate finance policy/ regulatory frameworks |  | Number of significant analytical products developed and disseminated with senior government engagement | Planned |  | 4 | 14 | 20 |  | •Government of India ensures that any member of staff who is trained through the programme is then deployed for actual implementation of suggested reform area. •Reform effectiveness and sustainability is ensured through adequate resource allocation during and post programme implementation period by Government of India. This will allow for Impact assessment to be undertaken in future years •The priorities of overall UK-India bilateral agenda do not change significantly.
|  |  | Achieved | 0 | 2 | 13
| GGC, DPIIT, UNDP,BIM, ECB, FX, adaptation , IPA, Pensions, BSI, SheTrade, TERI |  | Source: UNDP 1, DPIIT 2, TERI 4, BIM 6, SheTrades - 1, VGF&IIPDF 1, refer col B
Programme reporting
|  | Output Indicator 3.2 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (Jan 2027)
|  | Number of Government officials / staff whose knowledge / understanding has been increased through ECOP capacity building initiatives and TA | Planned |  | 0 | 75 | 100
|  |  | Achieved | 0 | 0 | 142
Source: BIM, ECB/FX, GGC, TERI 100 , IPA 35, Ecorys 7 refer col B
|  |  | Programme reporting |  | 0 | 6 | 7
|  | Output Indicator 3.3 |  | Baseline (2024) | Milestone 1 (December 2024) | Milestone 2 (December 2025) | Milestone 3 (December 2026) | Target (Jan 2027)
|  | Number of business supported , financial regulatory frameworks developed, contributed to or improved by ECOP | Planned |  | 0 | 50 | 0
|  |  | Achieved | 0 |  | 221
|  |  | Source - SheTrade, TERI 91, She Trade, BIM | [5 empty] | RISK RATING
IMPACT WEIGHTING 45% |  |  | Programme reporting
Note on G47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 conference proceedings + 2 analytical reports
Note on G57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MSMEs, businesses and think tanks

## Change Log
Area of change | From | To | Rationale
Weightage for Outputs 1 & 3 Amended
Output 1 | 45% | 25% | change in resource allocation and programme priorities
Output 3 | 25% | 45% | change in resource allocation and programme priorities
Output 2 remains same | 30% | 30%
OUTCOME INDICATORS AMENDED - AR 23-24 did not report against outcome indicators
Outcome indicators 1.1 | Amount of private financial flows that could be mapped to programme interventions | Evidence of contribution to increasing private sector investment/ financing for infrastructure and climate | To align it more to the current refocused interventions
Outcome indicators 2.1 | Amount of public financial flows that could be mapped to programme interventions | Evidence of contribution to increased public revenue and incorporation of climate action in public financial management systems at national and/or sub-national levels | To align it more to the current refocused interventions
OUTPUT AMENDMENTS
OUTPUT 1
Output 1 Statement Amended | Pipeline of investable projects developed in line with international standards, attracting more private sector financial flows | Investable sectors / projects identified developed in line with international standards, that attract more private sector financial flows | Pipeline of investments could not be guaranteed due to the uncertain duration of the intervention
Output Indicator 1.1 discontinued | Number of guidance, policy and knowledge documents developed and presented to DEA leadership, to enable development of pipeline of investable projects in line with international standards | Nil | Pipeline of investments could not be guaranteed due to the uncertain duration of the programme
Output Indicator 1.3 - language amended as indicator 1.1 now | Number of knowledge and capacity development initiatives for potential government sponsors / financial institutions to support development of project pipelines | Number of government officials/staff whose knowledge/understanding has been increased through ECOP capacity building initiatives/TA | the previous 1.2 has been deleted as mentioned above
Changes in Milestones 1.1 1.2
OUTPUT 2
OUTPUT 2 Statement Amended | Recommendations to the Public Finance Frameworks through knowledge exchange and research | Recommendations and improvements to Public financial frameworks and improved revenue generation and management | More reflective of the programme priorities and resultant interventions
Output Indicator 2.2 - original indicator discontinued Amended new indicators 2.2 & 2.3 | Number of knowledge sharing/capacity development initiatives with key public finance departments across Centre and State | 2.2 - Number of individuals supported who report perceived improvement in capacity and ability, attributed to programme interventions for PFM 2.3 - Number of states supported in PFM. | More reflective of the programme priorities and measurable indicators
OUTPUT 3
Output 3 - Statement Amended | New/improved business and financial regulatory frameworks by Centre/State | New/Improved Business Environment and climate finance policy/ regulatory frameworks | language strengthened- Aligning to refocused attention to Climate Finance
Output indicator 3.1 - language amended | Number of guidance, policy and knowledge documents developed and presented to Central and/or State Government/policy-making institutions or Standards Agencies | Number of significant analytical products developed and disseminated with senior government engagement | More reflective of the programme priorities
Output indicator 3.2 - language | Number of knowledge sharing and capacity development initiatives with key policy makers in Government of India on relevant reforms | Number of Government officials / staff whose knowledge / understanding has been increased through ECOP capacity building initiatives and TA | More reflective of the programme priorities
Output indicator 3.3 Added New Indicator | nil | Number of business supported , financial regulatory frameworks developed, contributed to or improved by ECOP | More reflective of the programme priorities