Programme Completion Review
(Template for Smaller Projects Programmes)
[note] A Smaller Project is defined as a funding arrangement with a single implementing partner normally not exceeding £250k. Such projects can be grouped as a Programme for approval and reporting purposes provided the total budget envelope does not exceed £2m. See PrOF Guide.

Summary of Programme Performance
Year	2022-23	2023-24	2024-25
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

Programme title: Mauritius Multi-Sector Development Programme (MMDP)
Programme Value £ (full life):	£1.335 million	Review Date: / 30 June 2025
Programme AMP Code: 400050	Programme Start Date: October 2022	Programme End Date: March 2025

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-400050/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-400050/documents

## SUMMARY AND OVERVIEW (1 page)

Programme description: / The Mauritius Multi-Sector Development Programme (MMDP) aimed to support Mauritius’s own social and economic development aspirations insofar as they are aligned with HMG’s foreign and development policy objectives e.g. climate, trade, democracy and governance, women and girls, and anti-corruption/countering illicit finance. The programme was designed to support delivery of the Government of Mauritius’s Vision 2030 development programme (developed by the predecessor to the current Mauritian government, which won the 2024 general election in Mauritius). Through targeted, low-value projects focused on capacity building in key areas, MMDP provided support to the Government of Mauritius to help create the policies and capabilities needed to strengthen key growth enablers outlined in the Vision 2030 model. / Phases 1 (Oct 22–Mar 23, £600k) and 2 (Apr 23-Mar 24, £650k) of MMDP were intended to pilot innovative approaches and strategic policy development. MMDP was extended into a third phase in the 2024-25 financial year which comprised activities delivered from April 2024 to March 2025, with a final year budget of £84.5k, representing a year-on-year reduction of 87%. Prior to the start of the programme’s final financial year, its definition as a “Smaller Projects Programme” (see footnote 1 below) was formalised by the SRO and Programme Board. All projects delivered by the programme were delivered by a single implementing partner in projects not exceeding £250k, with the total programme envelope not exceeding £2m.
Intended policy objective(s) of projects within this programme. / MMDP supported Mauritius’s own social and economic development aspirations and plans to be an African hub on issues aligned with HMG's objectives e.g. financial services (over 10% of all Foreign Direct Investment to Africa flows through Mauritius), education (the UK has over 40 awarding bodies active in Mauritius) and climate (a role model Small Island Developing States (SIDS) with an ambitious Nationally Determined Contribution (NDC)). Mauritius is a willing partner, seeking technical expertise rather than substantial development finance. Given this willingness and a relatively mature democratic, policy and regulatory framework and strong human capital, a small amount of investment had the potential to be truly catalytic. The programme’s approach also followed HMG’s Africa-wide shift from a threats-based approach to an opportunity-based approach. / It intended to deepen our bilateral relationship and enable us to make progress on country business plan priorities by enhancing cooperation on Security and Defence, Governance and Open Societies and Women and Girls. Mauritius is one of the few functioning democracies in Africa and a key development actor in the Indian Ocean, an increasingly important region to our Indo-Pacific objectives.
Overall Programme Score / Based on the two previous Annual Reviews (ARs), and the programme’s performance in its third and final year, MMDP is scored A overall.
Summary supporting narrative for the overall programme score in this review. / This review should be read in conjunction with the detailed ARs of MMDP completed in October 2023 and October 2024 and published on DevTracker. It should be noted that the 2024 AR was completed mid-way through the programme’s last financial year and examined its final-year projects in significant detail. / Project activities and outputs largely met expectations of beneficiaries, implementing partners, and the funder. Particularly in the final year of the programme, the vast majority of activities exceeded the expectations of the funding partner, and represented a notable increase in the quality and pace of delivery as the BHC programme team built on its experience and skills; as per the PrOF’s programme grading system, for programmes where over-delivery outweighs any under-delivery (which was very rare, especially in the last two financial years), programmes should generally be graded at A+. However, as the most recent Annual Review also notes, a recurring theme across the programme’s life was challenges in developing detailed output monitoring and reporting in the programme logical framework, which resulted in over-achievement of some outputs; under-achievement in others; and general challenges in assessing the quality and impact of outputs. For these reasons, the review team believes a score of A, “met expectations”, is a fair reflection of the programme’s overall performance across its three years.
Major lessons and recommendations / See Table 1 on page 6 of this review.
Actions following the approval of this PCR. / The BHC should consider whether a successor programme to MMDP should be established to support implementation of development priorities. If yes, a business case must be drafted and agreed. The recommendations in Table 1 on page 6 should be implemented for future programme delivery.

## PROGRAMME STRATEGY OR THEORY OF CHANGE (1 page)

Recap from the programme approval document the intended objectives of the programme, and whether the objectives have been changed since approval.

Vision 2030 was developed by the GoM to give a new impetus to the economic and social transformation of Mauritius following the external shock of COVID-19 and wider global economic pressures. The development model aims to jumpstart a new phase of growth with shared prosperity and enhanced quality of life, ultimately transforming Mauritius into a high-income country by 2030 – the “Vision 2030”. This Vision 2030 Development Model has identified sectors that have the potential to accelerate growth. As such, growth enablers have also been identified with accompanying strategies to develop a range of Mauritian industries; to improve the productivity of the growth sectors; and to enhance the capacity to compete on an international scale.
Through the deployment of programme funds and/or UK expertise and knowledge, MMDP provides support to the GoM to analyse and create the necessary policies and build the necessary capacity to strengthen key growth enablers as set out in the Vision 2030 development model. These are principally: (i) Good Governance, (ii) Public Order and Safety Strengthening, (iii) Public Infrastructure Upgrading, and (iv) Human Capital and International Trade.

Summarise from the programme approval documents the criteria by which projects were to be selected for funding and how project selection has operated during the year.

As the 2023 Annual Review of MMDP noted, the British High Commission has continued throughout the life of the programme to put together a complex portfolio of demand-led interventions, designed to respond to priority issues for both the Mauritius and UK governments in the development space. Throughout the programme, the delivery model remained agile, allowing the BHC team to respond flexibly and quickly to the changing context. It was reaffirmed by the SRO and BHC Programme Board before the final year of the programme, in Jan-Feb 2024. Across the programme, projects were assessed by the SRO and Programme Board on the basis of: 1) their relevance to delivery of Vision 2030, in line with MMDP’s original business case and subsequent addendums; 2) value for money to the UK, proportionality to local implementing partner expertise, and likely efficiency and speed of delivery; and 3) proportionality to the BHC’s programme management capacity and experience.

Describe whether the programme-level objectives have been achieved and are likely to be sustained. Summarise what information you have to support this assessment, for example if projects have collected and reported information from stakeholders and beneficiaries.

Data collected by the review team, including in project-level completion reports provided by every implementing partner at the request of the BHC programme team, show that most programme-level objectives were achieved. In some cases, as previous Annual Reviews have noted, it has been difficult for the review team to accurately judge the success of certain programme-level objectives, because of challenges in relation to the clarity of the programme’s theory of change and results framework. While MMDP is now closed, if the BHC delivers further programmes in future, this review repeats the recommendations of its predecessors that formal monitoring & evaluation expertise from within FCDO – which has recently been made more available than in previous financial years for this region – be taken up in the design phase, and at the appropriate review points during delivery.
## DETAILED OUTPUT OR PERFORMANCE AREA SCORING

Delivery of Projects (1 page)
Performance area:	Delivery of projects.
Number:	9	Score:	A
Weighting (%):	100%	Weighting revised since last AR?	n/a

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

The projects delivered across the lifetime of the programme were:

- Good governance: Increased awareness of options to digitise and improve voter registration, delivered by the Westminster Foundation for Democracy;
- Public order and safety: Assessment and training to build institutional capacity of Mauritian law enforcement organisations, delivered by the UK International Police Assistance Service (IPAS);
- Public infrastructure: expert advisory services to support water sector reform and repair in Mauritius, delivered by the Climate Resilient Infrastructure Development Facility (CRIDF) and latterly Interconz;
- Human development: provide entrepreneurs from poor and vulnerable backgrounds with training and services to access export markets and international buyers, delivered by SheTrades;
- Renewable energy: enhancing and promoting engagement by women and youth entrepreneurs in the renewable energy sector in Mauritius, delivered by the UNDP office in Mauritius;
- Anti-corruption: strengthen Mauritius’s response and resilience to corruption and illicit financial flows, including progress towards accession to the OECD Working Group on Bribery, delivered by GovRisk; and Mauritius’s participation in the annual ARINSA conference for Southern Africa, delivered by the UNODC office;
- Institutional support: expert advisory services to enhance the reporting and analytical capabilities of the Mauritius National Audit Office, delivered by the UK National Audit Office;
- Countering SGBV: technical support to the Government of Mauritius to standardise procedures and policies for the effective management of cases for survivors of sexual and gender-based violence in Mauritius, delivered by the UN Population Fund office in Mauritius.

Summarise the projects that have been delivered during the lifetime of the programme. How many projects? What was the range of project budgets? What was the range of activities (e.g. events, research, communications), places or themes?

As outlined above and in the detailed 2023 and 2024 Annual Reviews, MMDP delivered nine projects in total, the vast majority of which lasted only one financial year (for reasons including the timing of ODA allocations by FCDO, and the availability of appropriate implementing partners. The two exceptions were the projects delivered by CRIDF, latterly Interconz, and by GovRisk). Total programme spend was £1.335 million, with a reduced budget of £84.5k in the final year. Activities focused on targeted capacity building support (e.g. technical support to enable Mauritius to develop plans to accede to the OECD Working Group on bribery; technical support to the quality of National Audit Office reporting and analysis) for which Mauritian government ministries and agencies, whose stated intent was to improve outcomes for Mauritian society and the public at large through realisation of the Vision 2030 document, were the proximate beneficiaries. Programme activities remained faithful to MMDP’s original design structure and purpose: prioritising flexibility, adaptability, and value for money, targeting UK development spending where it would have the greatest, unique, and most proportionate impact.

Summarise whether the projects have been delivered according to the planned timescales, budgets and quality. Provide an assurance that risks and finances have been managed in a proportionate manner and in line with PrOF rules.

The vast majority of the projects outlined above were delivered according to the planned timescales, budgets, and quality. The BHC programme management team reported to the review team that implementing partners consistently met or exceeded expectations on delivery timescales, effective project and financial management, monitoring and evaluation, and reporting. Furthermore, beneficiaries of projects consistently reported positive feedback in their interactions with their implementing partners. In several cases, the implementing partner-beneficiary working relationship is expected to continue into future financial years, beyond the life of MMDP, demonstrating the effectiveness of the programme’s targeted approach to matching need with expertise (e.g. the projects delivered by Interconz and the National Audit Office).

However, this is not to say that project delivery was always entirely smooth. The programme team noted to the review team that, often as a result of the timing of ODA allocation notifications to the BHC, the challenges involved in delivering single-year programmes, and the unpredictable nature of implementing partner capacity, a build-up of project outputs scheduled for delivery in Q3 and Q4 was a feature of each financial year of MMDP. This generated risks that project outputs would not be delivered as agreed, and the risks required careful and proactive management. In a small number of cases this risk was realised. (For example, minor elements of the NAO project listed above could not be completed in time before the end of Q4.) The review notes, as the 2023 AR did, that deployment of ODA is most effective in achieving strategic objectives if it is part of a multi-year programme. This review repeats the 2023 AR’s recommendation that the BHC seek approval for multi-year programmes in the event that MMDP has a successor (while recognising that this decision is not wholly within the BHC’s gift).

This review also notes findings by previous ARs regarding occasional misalignment between outputs and outcomes in the programme and project level results frameworks. For this reason, in some cases, it has been difficult for the review team to determine that all results were achieved in the manner and quality that the BHC expected. This review recommends that, in future programmes, the BHC establish a clearer process for agreeing project level outcomes and outputs with implementing partners, and for subsequently ensuring they are directly aligned with programme level results.

The BHC programme team has robust processes and governance arrangements in place for management and oversight of risks and finances. The MMDP has a standalone risk register and financial forecast, which are maintained in two places: in the BHC programme team’s local files, managed week by week by the Head of Programmes and Project Managers as needed; and in AMP and EPM (the central systems for programme risk and financial management). Risks and finance are standing items at the Quarterly Programme Boards, chaired by the SRO. The PRO updates the risk register and financial forecast at least twice per month, and more often if needed. Decisions on risk and financial management are made by the PRO and where required by the PRO delegation letter issued by the SRO, are referred up to the SRO for a decision.

Reflect back to the Business Case. How have the criteria and mechanisms that were put in place to select and manage projects operated in practice? Is there anything that a future programme could do better?

Selection of projects for delivery under the programme is a process governed by the Quarterly Programme Board, chaired by the SRO, at the meetings held before the start of each of MMDP’s financial years. Decisions were made collectively by the Board, reviewing demand-led proposals submitted by ministries of the Government of Mauritius, multilateral organisations represented in Mauritius, and/or by third sector organisations, and assessing through discussion their alignment with core objectives of the Vision2030 policy document. As per the 2023 AR’s recommendations, the Board did consider project proposals against explicit entry and exit criteria, including cost, value for money, and policy alignment. However, future programmes could more closely consider questions including:

- the complexity of the delivery model – are delivery models proposed by implementing partners proportionate to the level of cost and the timeframe? What is Programme Board’s level of confidence in the delivery model to achieve its goals, and for those goals to be monitored accurately and effectively, within the timeframe?
- how well activities map onto a single-year delivery model (which may continue to be the case because multi-year programmes are not entirely a decision for the BHC) – do implementing partners have clarity from the BHC programme team about the status of multi-year funding opportunities? Are their goals calibrated appropriately?
- and the potential for projects to have an impact beyond the strict time limit of the programme – can the BHC programme team focus on activities that will lead to the establishment of institutional relationships, ensuring important work can continue beyond the programme’s life and without direct BHC involvement?

To score delivery of projects at programme-level the reviewer will weigh up whether, on balance, across all projects:
A++	Projects were delivered substantially better than expected (over delivery substantially outweighs any under-delivery).
A+	Projects were delivered better than expected (over-delivery outweighs any under-delivery).
A	Projects have been delivered as expected (any under- or over-delivery is in balance).
B	Projects were delivered below expectations (under-delivery outweighs any over-delivery).
C	Projects were delivered substantially below expectations (under-delivery substantially outweighs any over-delivery).

This review gives a score of A for delivery of projects at the programme level.

Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).

Table 1 below lists the programme-level recommendations that the BHC programme team should strongly consider implementing in the event of a successor (or similar) programme to MMDP.

Table 1 – PCR Recommendations, June 2025
#	Recommendation
1	If the BHC delivers successor programmes to MMDP in future, approval for multi-year programmes should be sought in order to maximise the effective deployment of ODA in achieving strategic objectives.
2	BHC should establish a clearer process for agreeing project level outcomes and outcomes in results frameworks, and for subsequently ensuring they are directly and explicitly aligned with the programme level results framework, bringing in 10% M&E support if/where possible.
3	Build-up of project output/deliverables into the fourth quarter of future financial years should be avoided by early mobilisation, quick and effective decision-making, and early engagement with implementing partners.
4	PRO and project leads to identify more regular and formal ways to discuss and manage risk on a monthly basis, and the PRO to issue more regular and structured commissions to leads to update and manage the risks they own.
5	For future programmes, the Theory of Change should be refreshed on at least an annual basis, and reviewed by Quarterly Programme Board to ensure it matches policy and programme objectives and practice.
6	Additional entry criteria for project approvals should be agreed and implemented for future programmes.
7	Depending on future ODA funding picture, SRO and PRO should consider proportionality of governance arrangements and keep them under review on a rolling basis, ensuring structures and practice are flexible and adaptable to needs.

Table 2 below lists the recommendations from the previous two ARs, with a comment on the extent to which they were progressed or fully implemented. Where recommendations were not implemented and yet remain relevant considerations for future programme, they have been adopted by this review.

Table 2 – AR Recommendations, 2023 and 2024
AR	#	Recommendation	Comment on progress
2023	1	Refresh the theory of change and results framework to focus on the impact of supporting policy analysis/ development.	Implemented - Results framework was refreshed on at least an annual basis. Core theory of change was not substantively refreshed.
2023	2	Consider ring fencing MMDP budget to bring in regular external monitoring and evaluation expertise.	Not implemented - MMDP budget was never sufficient to fund dedicated M&E expertise, particularly in its final year (which saw a reduction from £650k to £84.5k).
2023	3	Ensure consistency between the output and outcome indicators contained in project and programme level results frameworks.	Partially implemented - Quarterly Programme Board did make efforts to more closely link results framework at the programme and project level, but as this review finds, more progress could be made on this.
2023	4	Complete a refresh of the risk register, set risk appetites for each risk category and build in regular updates to risk registers.	Implemented - Risk register was refreshed following this review, and comprehensively on a quarterly basis. The PRO was responsible for overall day-to-day management and escalation of risk.
2023	5	BHC Port Louis increase capacity and capability for MMDP in terms of ODA management and oversight.	Implemented - Capacity was increased by the establishment of a Head of Programmes role at the BHC.
2023	6	BHC Port Louis pitch for a multi-year funding (24-26).	Implemented - BHC did seek approval for a multi-year programme before the start of the 2024-25 year but was unsuccessful due to regional funding constraints.
2023	7	Criteria developed against which new proposals are assessed for inclusion in the MMDP portfolio and either approved, modified or rejected.	Implemented - Quarterly Programme Board did assess projects for entry into the programme against clear criteria. This review has recommended those criteria could be expanded and made more precise in future.
2023	8	Focus of any evaluation strategy should focus on the extent to which the MMDP was able to facilitate and co-create lasting and impactful policy and legislative changes with the GoM.	Implemented - Evidence collected by this and previous reviews strongly indicates that policy impact has been lasting, as evidenced by the fact some implementing partner/beneficiary working relationships will extend beyond the life of MMDP.
2024	1	BHC should aim to align future programming more closely with financial years so reviews can take into consideration the full range of activities, particularly when dealing with any multi-year programming.	Implemented – Shift was made for MMDP and is adopted as a recommendation for future programmes by this review.
2024	2	The programme team should closely monitor the risks to timely completion posed by delays to machinery installation with the Interconz Project, seeking assurances that the GoM’s post-election timetable for the installation is robust.	Implemented - This risk was managed effectively, with appropriate and proactive intervention by the BHC with both the implementing partner and the beneficiary, at senior level. The installation timetable was expedited and enabled by the project to complete on time.
2024	3	PRO and project leads to identify more regular and formal ways to discuss and manage risk on a monthly basis, and the PRO to issue more regular and structured commissions to leads to update and manage the risks they own.	Partially implemented - PRO issued more regular commissions to project managers on risk, but the review did not find evidence of programme level risk meetings outside of the Quarterly Programme Board. This recommendation is adopted by this review.
2024	4	PRO and project leads to consider establishing a monthly, formal opportunity for the programme team to meet outside of quarterly Programme Board, below SRO level.	Partially implemented - As above, this review did not find evidence that a formal monthly opportunity had been instituted – though notes that the BHC is a small mission and the programme team a small group within that mission; consequently much of the relevant discussion happened informally on a day to day and flexible basis.
2024	5	Review the assumptions contained in the logframe and, where appropriate, align these more closely with the risk register.	Implemented - Closer links between the logframe and risk register were established in the final year of the programme.
2024	6	Depending on future ODA funding picture, SRO and PRO should consider proportionality of governance arrangements and keep them under review on a rolling basis, ensuring structures and practice are flexible and adaptable to needs.	Implemented – No longer relevant for MMDP, but this review has adopted this recommendation in the event of future programmes.
2024	7	BHC to prioritise programme management training for staff especially new starters, and to explore opportunities for learning from key development hubs in the local region, e.g. Programme Management Unit at BHC Pretoria.	Implemented - Accepted by Quarterly Programme Board and will be monitored on an ongoing basis, subject to future programmes.
2024	8	BHC should consider how MMDP Programme Board formally reports or feeds into Post’s Country Board.	Implemented - Programme and finance management is a standing item on Post’s Quarterly Management and Security Committee.
2024	9	PRO to continue to explore possibility of procuring 10% advisor cadre M&E support from within the wider Africa network, assuming no- or low-cost can be achieved, with a focus on strengthening the logframe.	Implemented - PRO explored seeking additional 10% M&E advisory support but was largely unsuccessful in securing it for review periods.
2024	10	Timely preparations should be made for the completion of a comprehensive PCR in 2025 that: 1) identifies key lessons from the full lifetime of the programme; 2) permits the development of a plan to sustain the BHC’s access in key sectors in Mauritius even in lieu of future funding; and 3) establishes a firm base for future programme management and practice in the event successor programmes materialise.	Implemented - This review delivers findings and makes recommendations based on the whole life of the programme; will contribute to a foundation that will sustain the BHC’s impact in key sectors after MMDP; and further will contribute to establishing a firm base for effective programme management in the event that successor programmes are established.