BUSINESS CASE ADDENDUM

PROGRAMME TITLE
Directorate/ Post	EECAD	Contact name	Charlie Morris
Original programme budget	£18m	Country or region targeted	Central Asia (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan, Uzbekistan)
Cost extension value (if applicable)	N/A	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Director
New increased or reduced programme budget (if applicable)	N/A	Original programme start and end dates	Start – March 2024, / End – March 2029
Latest AR programme score	A	New programme end date (if applicable)	N/A
		Programme ID	400053

Detailed information
Programme summary	(250 words maximum) / A brief summary of the programme and its purpose, as approved in the Business Case - noting any caveats from Minister/approver at CN or BC approval stages. / Describe what the programme has achieved so far and what lessons have been learned. / Central Asia’s economies are growing steadily on the surface, but just beneath lies a narrow economic base built on commodities and remittances, stagnant rural poverty, and a dependence on Russia’s economic influence. Central Asia desperately needs jobs, driven by a more diversified economy. / GIG will drive Central Asia’s independence, economic resilience, and support inclusion by developing and investing in the region’s small and medium enterprises (SME). To do this, GIG will establish under Component 1: Central Asia’s first SME private equity/venture capital fund (PE/VC), investing in high-potential firms, providing much needed green finance to support Central Asia’s green transition. Component 2 will build the capacity of SMEs (including women-led businesses) through dedicated training, incubation and acceleration, and Component 3 will support improvements in the business enabling environment. / Activity began under Component 2 and 3 of GIG in November 2024, and February 2025 respectively. Though very early, 55 startups have graduated from training programmes so far. Legal and design work has just commenced on Component 1, the focus of this BC Addendum.
Changes	(300 words maximum) / What is the objective or purpose of making this change? What are the drivers of that change (eg. context change, under-performance of programme or partner). / How will the programme deviate from the original business case? How significant is the change (be clear if this is a material change which requires re-approval)? Where there is a material change, describe that change and the overall impact you expect it to have. / What would be the result if the proposed change was not approved? / GIG was originally budgeted as 100% RDEL to maximise flexibility in terms of potential delivery mechanisms. For Component 1, options varied from a dedicated Multilateral Trust Fund, to a bespoke Special Purpose Vehicle that would use programme funds to take equity stakes in chosen beneficiaries. / We have now selected the delivery partner, and clarified their chosen delivery mechanism. FCDO will provide a Development Capital Grant to the Delivery Partner, an NGO (Aga Khan Foundation). The Development Capital Grant will be used to establish a bespoke investment vehicle, as a LLC holding company or Non-Bank Financial Institution structure. This investment vehicle will then use equity and equity-like instruments to invest in SMEs in accordance with GIG’s Business Case. The Fund will be 100% owned by the grant partner, or one of its subsidiaries. FCDO will not be a Limited Partner (i.e. it will not have an equity stake in the Fund) and will therefore not have ownership or control over the investment assets, nor will FCDO have any rights to returns generated from the Fund. / In accordance with GIG’s original business case, the objective is to establish an evergreen fund that will continue to recycle capital and invest in accordance with GIG’s objectives after programme closure. As such, FCDO does not expect the funds to be returned to FCDO. / The Addendum is therefore to request converting a proportion of the envisaged RDEL envelope into Fiscal CDEL to be used for the purposes of capitalising the Fund. / We judge this to be a technical change, rather than material, change.
Implementation	(100 words maximum) / Describe how the change(s) to the programme will be implemented. / Will changes be required to the existing management arrangements as a result of the amendments to the Business Case? / Detailed governance arrangements to ensure appropriate mitigation of financial and commercial risk are being discussed between FCDO and the Delivery Partner as part of the initial scoping work for Component 1. Such discussions involve consultations with relevant colleagues in Commercial and PSCMD team to ensure latest best practice regarding Development Capital Grant projects is being followed. / No changes are required to existing management arrangements.
Budget	(100 words maximum) / For cost extensions, set out the pre/post amendment finance profile over the life of the programme including: / original budget / total amount already spent / amount of cost extension / revised total(s) / Confirm that any cost extension is financially affordable within the Post/Directorate allocation, i.e. where will the Post/Directorate find the funding for any cost extension, and whether the proposed cost extension will take the programme beyond this SR period? (See Section 5 of the PrOF Guide to Programme Approvals for further guidance. / Key budget headlines: / Original Budget: £18m RDEL / Spend to Date (end July): £1.75m RDEL / Revised Budget: £11m RDEL, £7m CDEL / This amendment seeks to reprofile the RDEL/CDEL proportions of the programme, with a shift towards SME private equity/venture capital funding. The below table shows expected allocations over the life of the programme, pending decisions on future year ODA budgets. / FY24/25 FY25/26 FY26/27 FY27/28 FY28/29 / RDEL £0.5m £3.2m £3.8m £1.9m £1.6m / CDEL £1.7m £2m £2.5m £0.8m / The proposed amendment is affordable within existing FY25/26 Post/Directorate allocations, with a FY25/26 CDEL uplift agreed through the Ministerial ODA exemptions process in June. The programme continues to have break clauses built in to flex accordingly to future year allocation decisions and will not take us beyond the SR period. The programme remains 100% ODA.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☐ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☒ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	(100 words maximum) / Describe any new key risks arising as a result of this change. How will they be mitigated? / GIG’s original Business Case outlines the risky nature of the envisaged investments, in particular early-stage Venture Capital in emerging markets. It is for precisely this reason that use of a Development Capital Grant is warranted, to mitigate the risk for private capital in order to catalyse investment. As such, inbuilt in the design process of the Fund are consideration and codified (with FCDO approval) of mechanisms and controls to appropriate judge and mitigate financial risk throughout, whether concerning individual investments or day-to-day spending. / We do not envisage any new risks to the programme because of this addendum.
Results/Monitoring and Evaluation	(100 words maximum) / Describe the new/additional results that you would expect to see from these changes. Outline at what level changes to the results will be seen, e.g. what is expected at outcome or output level? / Review the Theory of Change for the Business Case and outline whether the approach taken is still valid based on the evidence for the BC addendum and whether any updates are needed. / Outline any additional monitoring and evaluation activity that will be needed in the programme as a result of the changes proposed. / We do not envisage changes to the programme Theory of Change to the programme because of this addendum. / We do not envisage additional monitoring and evaluation activities, beyond those outlined in the BC, because of this addendum.

REVISED JANUARY 2025