## Annual Review of UK-CA Green Inclusive Growth Fund (GIG)

Title: UK-CA Green Inclusive Growth Fund (GIG)
Programme Value £ (full life): 18,000,000		Review date: 13/03/2026
Programme Code: 400053	AMP start date: 14/03/2024	AMP end date: 30/05/2029

Summary of Programme Performance
Year	2025	2026
Overall Output Score	A	A
Overall programme risk rating	Major	Major

DevTracker Link to Business Case:	BC https://iati.fcdo.gov.uk/iati_documents/D0005878.odt / addendum to BC https://iati.fcdo.gov.uk/iati_documents/S40005315.odt
DevTracker Link to results framework:	Not available

A. SUMMARY AND OVERVIEW
Description of programme

The UK-Central Asia Green, Inclusive Growth Fund (GIG) is the UK’s private sector development programme for the Central Asia region. It has been created to strengthen Central Asia’s independence and economic resilience by developing and investing in the region’s small and medium enterprises (SMEs), with a focus on women-owned, youth-led and green businesses. The programme comprises three components:

- Component 1 (led by Accelerate Prosperity): The establishment of Central Asia’s first SME-focused private equity/venture capital fund (PE/VC), investing in high-potential firms, including women-led business, and providing green finance to support Central Asia’s green transition.
- Component 2 (led by Accelerate Prosperity): Business Development Services (BDS) to prepare firms for investment, with priority given to green and women-led businesses.
- Component 3 (led by International Finance Corporation - IFC): Technical Advice to reform the legal and regulatory framework in targeted countries to introduce venture capital-relevant legislation.

The programme has been designed carefully to support FCDO priorities, in Central Asia and globally. In Central Asia, GIG supports inclusive growth by contributing to sustainable and broad-based job creation. Through this, it contributes to Central Asia’s wider economic resilience, security, and independence. Internationally, GIG mobilises green finance and supports private sector-led innovation and solutions to the global climate challenge in one of the world’s most intensely polluting regions. In doing so, GIG contributes to UK International Climate Finance (ICF) objectives.

Summary supporting narrative for the overall score in this review

Overall the programme is delivering well against its outputs and has started to achieve some of its intended outcomes on investment and jobs. Establishment of the International Finance Facility under Component 1 is later than expected following delays to FCDO budget setting and a thorough Gateway review process which has provided enhanced assurance on the programme’s riskiest component. Business development services are being delivered in line with expectations in three countries under Component 2 with some beneficiaries already securing investment. Finally, the Alternative Investment Law is drafted and nearing the statute books in Uzbekistan and preliminary steps have been taken in this area in two other countries thanks to the work of IFC under Component 3.

Major lessons and recommendations for the year ahead

The recommendations for the year have been grouped into three broad categories:

1. Inclusion and impact: GIG has set clear targets to drive inclusion (women, youth, disabled) and climate outcomes (green/greening business models). They are not consistent between components and there may be scope to raise the level of their ambition. For example, women-led businesses form 40% of the target for Component 2 and 30% of the target for Component 1, and green business models form 5% of the target for Component 2 and 20% of the target for Component 1. To address this, it is proposed that the GIG team:
  1. Consults once more with the FCDO Eastern Europe and Central Asia Directorate (EECAD) gender lead to explore harmonising the gender target at 40%. Target date: within six months.
  2. Reevaluates the climate targets and definitions of the project, in particular whether the currently loose definition of “greening” businesses under AP’s Green Business Assessment Tool (GBAT) needs to be tightened. Target date: within six months.
  3. Sets up a 6-monthly Impact Review of the disaggregated data on businesses receiving investment and business development support in order to be able to monitor and adjust the ambition and targets of the programme overall. Target date: within 6 months.

1. Delivery: recommendations for improved delivery include that GIG:
  1. Focuses on providing business development services which convert startups/SMEs with a minimum value product into investible deals. This would require a greater focus on supporting acceleration rather than incubation programmes and is in line with AP’s stated direction. Target date before the next annual review.
  2. Develops a more robust and targeted investor influencing strategy and improved investor-focused communication activities in order to deliver the goal of influencing systemic change in investor behaviour. Target date: within 6 months of the annual review.
  3. Pivots to provide enhanced regulatory reform support and resourcing in Kyrgyzstan and Tajikistan, in line with stakeholder requests and following the strong progress in Uzbekistan with the Alternative Investment Law. Target date: within 3 months.

1. Programme management: it is recommended that the team:
  1. Develops an aggregate logframe with common outcomes for the whole programme (not 3 individual logframes) and a clearer link between the logframe outcomes and those in the theory of change. The weighting of the three components should also be changed to reflect level of effort/spend rather than the current 33:33:33. Target date: within 3 months.
  2. Clarifies logframe outputs for Component 3 (IFC) for the lifetime of the project with agreed annual milestone targets for 2027 and 2028.Target date: within 3 months.
  3. AKF/AP to identify and compile a small set of relevant benchmarks from comparable programmes (e.g. cost per graduate, cost per business supported, or investment leveraged per £1 of programme funding) and use these as reference points in future reviews.
  4. IFC should ensure it has a simple but robust VfM framework in place. This does not need to be complex, but it would be useful to track at least one clear indicator for each of the VfM “E’s” (economy, efficiency, effectiveness and equity). For comparison, IFC could draw on data from similar technical assistance programmes implemented by organisations such as the World Bank or other IFIs, where publicly available project documentation often includes comparable cost and output metrics.
  5. Amends the AR timing in order to accommodate IFC and AP reporting cycle which end in April. Target date: within 3 months.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The theory of change sets out how business development services for SMEs combined with early-stage venture capital and regulatory reform can combine to increase investment, boost jobs and reduce poverty. The programme’s explicit focus on businesses led by women and disabled people and those that support green business models and those serving the disabled maximises that inclusive and environmentally sustainable impact that it can have.

The start-up sector has evolved quickly across all three countries since the business case was written, particularly in Uzbekistan. Government-led development of the sector in Uzbekistan has seen the state Venture Capital (VC) fund, UZVC, develop into a fund of funds and top-down, President-directed reform has accelerated adoption of investment reforms and initiated a new Tashkent International Financial Centre to rival that of Astana. In Kyrgyzstan the pace of change is noticeable but has been slower and more bottom-up, driven by the acceleration and development of new startups by programme partner Accelerate Prosperity, High Tech Park and others.

Despite the level of change, the overall theory of change still holds. Even in more developed markets like Uzbekistan, the volume of VC/PE deals remains small: according to the IFC annual deals are $17m compared to $80m in Kazakhstan. There may be scope for adjusting the level of effort and focus of different components within the overall theory of change in response to changing market conditions (e.g. more acceleration/less incubation, tighter focus on inclusive investment criteria and prioritising less developed countries) and these are discussed further below.

The one area where the theory of change is unclear is the link to UK growth and trade impact. If this is a priority for the programme then additional targeting and activities will be required, e.g. support to SMEs addressing UK import needs/demand, trade missions/market engagement activities of successful investees and/or targeting co-investment with UK VC funds like Sturgeon Capital.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Assessing progress against outcomes can only be done at a component by component level as there is no aggregated log frame with common outcome indicators that apply to all (or most) components. This makes tracking overall outcome delivery difficult and does not do justice to the coherence and complementarity between the three components which are well designed to deliver a greater collective outcome.

As regards Component 1, it is too early in the programme to see evidence of the outcomes being delivered. Delays to the launch of the Investment Finance Facility mean that achieving the outcomes related to investment for this component are likely to be later than envisaged – these outcomes include making investments, attracting other investors and growing business revenues. Good progress is being made on delivering business development support (Component 2) and there is evidence that the outcomes on attracting investment, greening business models and increasing business revenues are on track. There are no stated outcome indicators for Component 3.

Recommendation (3a): an aggregate logframe is needed which uses common outcomes as far as possible for the whole programme. Individual components may continue to monitor additional outcomes but key measures such as investment, revenue, jobs, green business support, women beneficiaries etc could be tracked at an aggregate level. The link between the logframe outcomes and those in the theory of change should be clear – this may require updating the outcome statements in the theory of change. Target date: within 3 months.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme is delivering its expected outputs overall and demonstrating good early results in Kyrgyzstan, Tajikistan and Uzbekistan through both its business development services and legislative reform and stakeholder engagement activities.

## C. DETAILED OUTPUT SCORING

Output Title	GIG-IFF Fund established in Central Asia
Output number:		1.1	Output Score:	A
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1 Legal establishment of the new GIG-IFF Fund to operate in Central Asia	Established	Established

A significant amount of work has been undertaken during the year to get the Investment Finance Facility (IFF) ready for launch. This has centred on an innovative Gateway review process which has enabled FCDO to gain assurance on a number of critical areas such as investment policy, Environmental, Social, and Governance (ESG) policy, financial/commercial model of the IFF, fundraising strategy and governance. The process has also ensured that the delivery partner and FCDO have a common understanding about key elements of the fund and its long term operation, both during the lifetime of the project and beyond. Alongside the Gateway review, steps have been undertaken to incorporate the IFF in the Astana International Financial Centre and is expected to be achieved by the end of FY 2025-26.

The existing investment policy proposes that by 2029 there should be a geographic split of roughly 30:30:30:10 (Uzbekistan, Kyrgyzstan, Tajikistan, Kazakhstan). As a starting ambition this appears to strike an appropriate balance between the need to invest where there is demand/pipeline and the desire to reach the regions where the supply of more commercial investment is less available. Given the commercial terms of IFF investments it is appropriate to retain a significant investment of this type of donor support in more developed Uzbekistan/Kazakhstan as well as low income Kyrgyzstan and Tajikistan.

The investment policy proposes that the portfolio should comprise 30% women led businesses, 30% youth-led businesses and 5% disabled led businesses. Furthermore, 20% of investments should be in green enterprises and 80% in “greening” enterprises. These targets provide a good starting position and the early experience of the fund will help to establish the right balance between supporting the most needy SMEs and truly commercial opportunities.

The Fund is at the beginning of its lifecycle and this investment policy should be allowed to be put to the test. However, given the programme’s aspiration to maximise sustainable and inclusive impact, there would appear to be scope to increase the targeting of investments in women led businesses above 30%. Ad hoc reports indicate strong women participation in VC investments (e.g. KPMG report indicating 32% of funded start ups are women in Kyrgyzstan). The programme could consider adopting the 40% women led business target used under Component 2 and having an integrated gender strategy across components. The programme could also reflect on the extent to which it intends to seriously target green investment business models and services – the current 20% of investments in green businesses is only a start in this direction and the green requirements for the remaining 80% “greening businesses” are low.

Recommendation (1a): GIG team should consult once more with the EECAD gender lead to consider introducing a more consistent approach to gender-targeting across Components 1 and 2 and strengthening the target for Component 1 to match the 40% target in Component 2. Target date: before the next annual review.

Recommendation (1b): GIG team should, collectively with AP, reevaluates the climate definitions of the project, in particular whether the currently loose definition of “greening” businesses under AP’s Green Business Assessment Tool (GBAT) needs to be tightened. Target date: within 6 months.

Recommendation (1c): The GIG team/AKF/AP should set up a 6-monthly Impact Review of the disaggregated data on businesses receiving investment and business development support in order to be able to monitor and adjust the ambition of the programme and its targets in this area. Target date: within 6 months.

Output Title	Innovative startups/SGBs supported through tailored training and advisory services in priority sectors
Output number:		2.1	Output Score:	A
Impact weighting (%):		17%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Expected Progress
2.1.1 Number of entrepreneurs reached through awareness/outreach sessions and/or digital communication campaigns for pipeline development	805	Achieved: 964 by Q3
2.1.2 Number of startups/SGBs graduating from GIG-BDS incubation and acceleration programmes	445	Not achieved: 425 projected by AP (192 by Q3)
2.1.3 Number of startups/SGBs supported under GIG-BDS that received training sessions or workshops on disability inclusion	165	Achieved: 125 by Q3 but expect to exceed annual target.

The analysis for all of Component 2’s outputs is based on data provided to the end of quarter three plus narrative feedback from the implementing partner AP. Full reports for the year will be available in March which is too late for the purposes of this review (see recommendation 3 (c) below on changing the annual review date). All of the targets for this output are on track and AP has successfully designed and delivered a number of incubation and acceleration programmes in all three countries:

- Kyrgyzstan: 2 incubation rounds (Women Cup, Prosperity Cup) for pre-seed and seed businesses looking for up to $10,000 in support and 2 acceleration cohorts (UniConer IT and Go Green Cup) looking for an average of $100,000 in investment.
- Tajikistan: 3 acceleration programs (TechRoh, EcoRoh, and TechUp) were implemented and 2 incubation cohorts (Production Power and TexStyle with Khujand and Khorog planned to be completed by end of March 2026).
- Uzbekistan: 2 incubation rounds (USOLVE Hackathon and incubation) have taken place as part of the partnership with UEnter and Virtual Accelerate.
The quality of AP’s business development services is recognised by sector stakeholders such as Swiss State Secretariat for Economic Affairs (SECO) and High Tech Park and Business Association JIA business park in Kyrgyzstan. Interviews with beneficiaries highlighted the benefits which startups receive from AP’s combination of in-person and online learning along with a dedicated expert mentor. Muhalim AI (an education startup on the left below) said the experience helped them understand what investors want and to refine their target client and business model. Fusion AI (a Customer Relationship Management - CRM startup on the right below) has gone from an idea to graduating from a US acceleration scheme at Drapers University in little over a year with support from AP, leap-frogging the incubation stage with the help of an international mentor and exposure to several demo-days.

For the coming year, AP is considering increasing its focus on acceleration programmes and reducing its work with very early-stage businesses and incubation programmes in Kyrgyzstan. Although some stakeholders highlighted the dwindling pipeline of start-ups and the importance of these early forms of support, a focus on acceleration is more aligned with other components (especially the Investment Fund) and is backed by stronger evidence of impact. The transition to a model of acceleration only should be undertaken in a phased way (particularly in Tajikistan where there are fewer providers of this support) in order to ensure that other partners are able to fill the incubation gap left by AP and could be added as a risk to the risk register.

The provision of business development services is targeted to achieve a geographic split of roughly 40:40:20 (Kyrgyzstan, Tajikistan, Uzbekistan). This split should be kept under review as part of the 6 monthly Impact Reviews (recommendation 1(b)) and adjusted in favour of countries where AP support is needed and can convert more businesses to the stage of being investment-ready.

In terms of inclusion and sustainability, this component aims to support 40% women led businesses, 40% youth-led businesses and 10% disabled led businesses. Early results are promising with 98/192 (51%) of graduates being women and 66/192 (35%) youth. Furthermore, 5% of businesses supported should be green enterprises and 70% in “greening” enterprises. These targets provide a strong starting position but may need to be further strengthened depending on market development to ensure that UK support is provided to commercially viable businesses with the most inclusive and sustainable impact. The definition of “greening” enterprises is somewhat opaque and subjective and the target of 5% for green business models might not sufficiently reflect the climate and environment ambitions of the programme.

Recommendation (2a): GIG should focus on providing business development services which convert startups/SMEs with a minimum value product into investible deals. This would require a greater focus on supporting acceleration rather than incubation programmes and is in line with AP’s stated direction. Target date: before the next annual review.

Recommendation (2b): GIG should determine its level of ambition on climate and consider tightening the definition of “greening businesses” or, in time, revising the target of 5% for green businesses as appropriate. It may be possible to adopt the 20% green business target that has been set for the IFF as a starting point to ensure greater consistency between components. Target date: 6 months before the next annual review.

Output Title	Blended digital platform (Virtual Accelerate) upgraded and expanded
Output number:		2.2	Output Score:	A
Impact weighting (%):		7%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Expected Progress
2.2.1 Number of new virtual / blended learning content / courses developed for the Virtual Accelerate (VA) Platform	1	Achieved: 0 by Q3 but expect to launch the greening your business module in March/April
2.2.2 Number of upgrades on the VA Platform (e.g. additional features, investment management solutions, etc.)	1	Achieved: 2
2.2.3 Number of private and / or public sector incubators / accelerators adopting VA solution	1	Achieved: 2 – Idea Central Asia and Agency for Innovative Development
2.2.4 Amount (in GBP) of revenue generated by VA through subscription from incubators / accelerators and entrepreneurs' contribution to cohorts using the fee-based model	GBP 100,000	Not achieved: GBP 17,936 by Q3 and anticipate a further GBP 45k and some further interest from Uzbek firms so 80% of the target will be met
2.2.5 Number of accessibility or assistive features introduced through VA to entrepreneurs with disability	1	Achieved: 0 by Q3 but expect to launch substantive improvements (e.g. magnifying tools) by end of period

Virtual accelerate is the online platform used to deliver virtual courses and digitally register and track participants. It is integrated into AP’s incubation and acceleration programmes and has been updated during the year to reflect objectives on new content (e.g. greening your business module) and greater accessibility (e.g. new features such as magnifying tools). It is a small element of the overall programme and could be more easily managed through 2 indicators on i) content development (e.g. new course content and accessibility features) and ii) uptake (e.g. number of incubators and accelerators adopting VA).

Output Title	Startups/SGBs supported to raise investments, promote market linkages and trade.
Output number:		2.3	Output Score:	B
Impact weighting (%):		7%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Expected Progress
2.3.1 Number of startups/SGBs supported under the GIG-BDS raising investments	37	Not achieved – projected to reach 33 (21 by Q3)
2.3.2 Number of regional events on investment raising, investment networking and B2B linkages organised under the GIG-BDS	1	Achieved: 2
2.3.3 Number of new international market linkages unlocked for supported startups/SGBs trading cross-border under GIG-BDS	69	Unknown

By the end of Q3 the programme had supported investment in 21 businesses with a further 12 going through due diligence meaning that 33 businesses should receive financing during the year, narrowly missing the target of 37. The average investment per business was not provided but in Tajikistan 5 businesses received an average of £20,000 each during Q4. All investments were deployed through local partner financial institutions, including AKDN-affiliated banks such as Kyrgyz Investment and Credit Bank (KICB) and Investment and Credit Bank Tajikistan (ICB, formerly FMFB-TJ). By Q3, 6/16 (38%) of businesses receiving investment in the year were women and 7/16 (44%) were youth. Although the investment target was not met, the number of regional events target was exceeded which has led to an overall A for this output.

The establishment of the Investment Facility under Component 1 will dramatically change the tools and leverage that is available to AP in order to financially support businesses that complete their training programmes. However, the extent to which they and beneficiaries can mobilise other sources of private capital is a crucial factor in amplifying impact (by increasing capital available to beneficiaries) and testing the validity of investment propositions. Therefore, the programme should continue seek to raise investment that is not backed by AP’s revolving fund and that is provided by other financial institutions independent of AP.

Output Title	Increased availability of documented insights and evidence on women-led businesses, businesses led by people with disabilities, and green entrepreneurship and trade.
Output number:		2.4	Output Score:	A
Impact weighting (%):		4%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Expected Progress
2.4.1 Number of evidence-based knowledge and communication products developed focusing on relevant local and international stakeholders	3	Achieved: 2 by end of Q3 and further 3 expected by programme year end (2 videos and a Playbook on designing gender inclusive startup support).

The several evidence and communications products have been produced such as video stories of successful SMEs/startups. Whilst these are important communication outputs, there appears to be scope to increase the impact of these outputs in a way that delivers the programme’s objectives of engaging investors into the SME/startup sector.

Recommendation (2c): In order to deliver the Theory of Change outcome of attracting new investors into the SME investment sector more robust and targeted influencing activities are needed. These could involve: i) producing evidence products which generate and disseminate compelling evidence to investors of the commercial returns and impact in the sector; and ii) working closely with Component 1 to develop and implement a clear investor influencing strategy to maximise the systemic impact of GIG’s investments and work with disability-inclusive, green and women-led businesses. It is still early in the programme but this could be planned now. Target date: Before the next annual review.

Output Title	Policy and regulatory reforms undertaken which support the start-up eco-system in three Central Asian countries
Output number:		3.1	Output Score:	A+
Impact weighting (%):		16%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1.1 Uzbekistan	Draft law on Alternative Investment funds prepared	Achieved: draft law and explanatory note, report on good practices for government Fund of Funds submitted to the GoUZ
3.1.2 Kazakhstan	Review of the draft Investment Law	Achieved: 1st review of the draft law completed shared with the government in May 2025
3.1.3 Kyrgyzstan	Discuss the scope of IFC support with the host government	Achieved: draft law on Alternative Investment Funds prepared (Dec 2025); three reports on regulation, ecosystem, and Fund of Funds completed
3.1.4 Tajikistan	Discuss the scope of IFC support with the host government	Achieved: policy note on the Fund of Funds drafted, consultation with government planned in early March

Component 3 is more advanced in Uzbekistan, where IFC has deeper context knowledge through earlier market and regulatory framework assessment and longer engagement with the government. IFC delivers the work of this component through its “Building Venture Capital and Start-up Ecosystem in Central Asia” project covering Kazakhstan, Kyrgyzstan, Tajikistan, and Uzbekistan.

While IFC neither uses the FCDO logframe template to record and report on the targets nor reports on the GIG Annual Review cycle (April to March), the documents presented to the review team and interviews with the IFC team revealed strong progress on the draft Alternative Investment Funds legislation across Uzbekistan, Kyrgyzstan, and Tajikistan. The work progressed furthest in Uzbekistan, where the government aims to pass the law in April 2026. In Kyrgyzstan, the government established working group on the alternative investment funds held its first meeting in early February 2026, whereas Tajikistan is lagging and stakeholders have made requests for an increased focus from IFC on this work in the country. Kazakhstan stands out as it permits and regulates venture capital funds to operate, primarily through Astana International Financial Centre. In Kazakhstan, the IFC engagement was limited to a review of the draft Investment Law that would upgrade the ability of Funds and investors to operate onshore within its domestic jurisdiction. IFC’s recommendations regarding the law have been accepted by the Government of Kazakhstan, ready for implementation in the coming year. IFC will work with the Kazakhstan regulator to adjust the draft law following any comments from parliament members, as the law is now in parliamentary procedure.

Recommendation (3b): Following the strong progress in Uzbekistan with the Alternative Investment Law, IFC and the team should pivot to provide enhanced support and resourcing in Kyrgyzstan and Tajikistan, in line with stakeholder requests. Target date: within 3 months.

Output Title	Capacity building and engagement activities which support the start-up eco-system in three Central Asian countries
Output number:		3.2	Output Score:	A
Impact weighting (%):		16%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.2.1 Uzbekistan	2 workshops for government officials on venture capital, private equity, and crowdfunding	Achieved: 2 workshops held
3.2.2 Kazakhstan	Consult private sector on the challenges	Achieved: Workshop with ecosystem players in Sep 2025
3.2.3 Kyrgyzstan	Consult private sector on the challenges	Achieved: 1 workshop on alternative investment funds held
3.2.4 Tajikistan	Consult private sector on the challenges	Achieved: 1 roundtable with private sector held; 1 workshop on alternative investment funds schedule pending in Mar 2026

IFC reported taking continuous efforts to explain the benefits of permitting and regulating alternative investment funds in Uzbekistan, Kyrgyzstan, and Tajikistan during the period. The hesitance of the government stakeholders was primarily driven by lack of experience and fear of investors using private equity to construct fraudulent financial schemes, dozens of which have been exposed and shut down in Kazakhstan and Uzbekistan causing billions loss in local currency.

The three countries vary in terms of government/private sector dynamic on alternative investment funds regulation. Uzbekistan has a strong government backed process, whereas in Kyrgyzstan it is more evolutionary with the government responding to the demand from private sector. And in Tajikistan the government has been slower to engage in this area until very recently.

Recommendation (3c): This component requires clearer output targets with agreed annual milestone targets for 2027 and 2028. The targets and results for this annual review have been compiled from an ad hoc report provided by IFC in February 2026. Target date: within 3 months.

Recommendation (3d): GIG team should explore amending the AR timing in order to accommodate IFC and AP reporting cycle which end in April. This could be done by conducting a light-touch annual review in April/May 2026 and then resetting the reporting cycle from then onwards. If this is not possible, the programme team should disaggregate activities and expected results by quarter so that expected results for the period to December are agreed and tracked with IFC. Target date: within 3 months.

## D: VALUE FOR MONEY

Value for money has been assessed for those components under implementation, Components 2 and 3, and to date the programme shows good evidence of cost control, operational efficiencies, successful mobilisation of co-financing, and the reallocation of savings toward higher-impact activities. There is limited data available for Component 3 and this could be addressed by agreeing key indicators with IFC as part of the proposed logframe revision and reporting date change (recommendations 3(b) and 3(c).

1. Economy (Input)
The main cost driver for economy on all components is staff costs plus costs associated with organising events, workshops acceleration and incubation programmes and developing digital platforms such as the Virtual Accelerate platform. Additional professional fee expenses have been significant for Component 1 as it goes through legal and regulatory establishment. Some evidence of action on economy was identified during the review - AP has taken steps to manage costs during the period, including the following:
In Kyrgyzstan staffing was streamlined in response to a temporary funding gap while retaining the core technical capacity needed to deliver programme activities. Office costs were also reduced by rationalising the office footprint, including closing the largest of the four offices.
In Tajikistan accommodation, food and local transport costs for trainings decreased due to better planning, consolidation of field visits, and increased use of hybrid delivery. Competitive procurement, framework agreements with fixed unit prices in Kyrgyzstan, budget ceilings, improved forecasting, and greater use of in-house expertise in Tajikistan helped ensure that inputs were procured at an appropriate quality and cost.

2. Efficiency (process)
Efficiency is measured through the monitoring of unit costs to outputs. During the period AP calculated that the total cost of training per business trained (all costs divided by number of businesses) was £3,883 – this is favourable compared to some regional benchmarks. AP has identified a number of efficiency gains it has achieved including through raising finance from third parties - ticket sales for the Central Asia Start-Up Club raised $2000 and co-funding for networking events raised $4,300. IFC assesses efficiency only after the project end as a funds spend to benefit generated ratio, comparing it to similar projects globally. For all components, the regional delivery model contributes significantly to efficiency with central teams from both AP and IFC providing technical and programme support across a number of countries, avoiding duplication. Cross-country learning further improves intervention design and avoids repeated inefficiencies.

3. Effectiveness (output/outcome) and Cost-Effectiveness (impact)
Given that all components have been operating for a little over a year there is relatively little data to calculate effectiveness and impact. However, AP has calculated that for its business development services work, an additional £1.52 of gross revenue is generated for every £1 spent on the programme and the cost of each new FTE[1] created by the programme is £8,875. IFC assesses effectiveness only after the project end as a ratio of funds spent to benefits generated (e.g. private capital enabled), comparing it to similar projects globally.
[1] Full-Time Equivalent FTE is a unit of measurement equal to the workload of one employee working full-time (usually 30-40 hours/week). It converts part-time or contract hours into a standard metric, allowing employers to calculate total staffing levels regardless of individual employment type.

5. Equity (distribution)
Equity is a critical objective of the programme and remains central to programme delivery. Both Components 1 and 2 have specified inclusive impact targets – for example the proportion of women owned businesses which are targeted is 30% for Component 1 and 40% for Component 2 (see recommendation 1(a)). Other targets include the proportion of businesses run by disabled people and business models targeting the disabled. Results to date show strong equity distribution: 51% of businesses benefitting from business development services are women-led, 34% are youth-led and 3% are led by disabled people. Furthermore, 38% of business models target green solutions and 10% target services for disabled people.

Overall, the programme has begun to deliver good value for money based on efficiency and economy and there are promising signs that the programme will deliver value for money on effectiveness and equity as outcomes are achieved.
Recommendation (3e) AKF/AP to identify and compile a small set of relevant benchmarks from comparable programmes (e.g. cost per graduate, cost per business supported, or investment leveraged per £1 of programme funding) and use these as reference points in future reviews.
Recommendation (3f) IFC should ensure it has a simple but robust VfM framework in place. This does not need to be complex, but it would be useful to track at least one clear indicator for each of the VfM “E’s” (economy, efficiency, effectiveness and equity). For comparison, IFC could draw on data from similar technical assistance programmes implemented by organisations such as the World Bank or other IFIs, where publicly available project documentation often includes comparable cost and output metrics.

E: RISK

The project is considered to be of Major risk overall due to its operation in 4 countries with differing contexts and the innovative nature of its International Finance Fund. During the period, changes in the programme’s Severe and Major risks were as follows:
- Reduction in ODA (Severe): this risk has been realised and revisions have been made to the programme which have reduced the annual budget of Component 2 by 50% going forward. This has led to reduction in the overall scope of work on business development services. Now allocations have been made, this risk can be removed/reduced.
- Loss of investment capital (Major): this risk remains valid and will be relevant when the IFF begins operation
- Decline in the business environment and increase in corruption (Major): this risk remains valid and under review. In Kyrgyzstan this risk was seen in the increased administrative scrutiny and security-related clearance procedures in certain oblasts faced by foreign-funded organisations. The programme responded strengthening internal compliance systems, closer coordination with legal advisors and reinforced documentation procedures.
- Delays in ODA allocations compressing the timeframe for IFF launch (Major): this risk has been realised and has led to a one-year delay in the launch of the IFF. Now the launch is scheduled this risk can be removed/reduced.

The risks register is regularly reviewed by the programme team, including with key partners such as AP. The register reflects the critical risks facing the programme and could be updated to include a new risk relating to the availability of SME/startup pipeline businesses which could arise as AP shifts away from earlier stage, incubation activities.

For Component 1 investment vehicle several key risks were identified during the gateway review including financial sustainability, reputational exposure, resourcing requirements on both the FCDO and implementing partner side, and long-term commitment associated with the vehicle. These risks were discussed and formally signed off by the FCDO Central Asia Strategy Board.
For Component 2, the overall level of risk of the project has increased slightly but remains within existing risk tolerance levels. As noted above, a tightening of government control and supervision was noted in Kyrgyzstan. In Uzbekistan, risks were primarily linked to phased market entry, onboarding of new partners, and limited maturity of the green enterprise ecosystem.

For Component 3, the level of risk remains stable and is centred on delivery risk relating to insufficient one-government approaches to policy and enforcement, and slow or incomplete delivery of the regulatory reforms that are being implemented. Private equity and venture capital regulation (legal, economic, tax) is overseen by different parts of government which have competing interests and stakeholders (particularly relevant to Uzbekistan). Staff expertise in the government ministries constrained the absorption capacity of the advice and follow-on implementation.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The key partners for this programme are Accelerate Prosperity (part of the Agha Khan Development Network) which leads on Components 1 and 2 and the IFC which leads on Component 3.

Accelerate Prosperity has been a reliable and responsive partner for both Components 1 and 2 and has delivered in line with their agreement with FCDO. The delays in delivering Component 1 were largely due to uncertainty on budget allocations for the period from April 2026 onwards. The AP team delivering Component 2 has proved highly responsive and experienced and bring a strong focus on the inclusive and green intended outcomes of the programme. The team has a dedicated programme management, monitoring and learning team which have provided completed quarterly reports and financial reports.

Financial forecasting at programme level has been accurate, with expenditure closely aligned to approved budgets and forecasts over the reporting period – overall there were small underspends on both components (£200,000 for C1 and £150,000 for C2). The underspends on C1 arose largely due to delays caused by FCDO whilst those in C2 related to changes in delivery approach and timings. These underspends were used to increase the overall budget for the year for IFC.

IFC has shown considerable flexibility during the period and has effectively ramped up its activities in response to the small underspend in other components. Whilst there is a need to more tighten their logframe outputs and milestones (see recommendations under Component 3 above) and the level of detail of formal in-year reporting is limited, the delivery team have demonstrated a high degree of flexibility in accommodating FCDO’s requests for additional information and reporting data, for example by reporting results to the end of February (ahead of the usual year end results reporting). Component 3 spend has almost tripled from the forecast of £349k to an expected £962k by end of FY 2025/26. This jump was driven by the recipient government demand for IFC advisory in three countries that started picking up from autumn 2025 and flexibility of the contractual arrangement with the IFC, where the FCDO can make advance payments.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring has been ongoing on a quarterly basis with the implementers of all components. This has been supplemented with field visits by the programme team to Osh in Kyrgyzstan, GBAO and Sughd regions in Tajikistan.

As regards Accelerate Prosperity, there has been intense engagement on Component 1 with FCDO as the design and scope of the International Finance Fund have been agreed. Component 2 is the most complex component under implementation and this has benefitted from AP’ standardised Performance Monitoring Plan, harmonised indicators, and integrated digital systems which have enabled consistent data collection, validation, aggregation, and cross-country comparison across Kyrgyzstan, Tajikistan, and Uzbekistan.

As noted above, IFC’s monitoring data for Component 3 is complicated by a lack of clear and simplified targets and milestones which align with GIG’s reporting calendar. Several recommendations are made above to address this. IFC has demonstrated a willingness to provide additional reporting information outside the usual reporting time period to support this annual review.

Learning on the investment activities of Component 1 is yet to begin but the programme’s “Gateway Review” approach to establishing the fund and providing the necessary clarity of purpose and assurance is an excellent example which the rest of FCDO can learn from. The team should seek to showcase this through the Private Sector cadre.

The lessons learned through Component 2 include:
- Delivery models and timing: The introduction of hybrid delivery formats has increased accessibility and participation, particularly for rural entrepreneurs. Programme schedules are now aligned with the seasonal calendar of agribusinesses, as demonstrated by the Go Green cohort in Kyrgyzstan, ensuring fuller engagement from women managing both farm and household responsibilities.
- Mentorship and incubation: A needs-based, one-on-one mentorship approach has proven highly effective in strengthening participant outcomes across incubation and acceleration programmes.
- Targeted approaches for women work: Targeted approaches, such as Women CUPs, have shown better results in terms of businesses completing programmes, particularly for incubation programmes.
- Disability inclusion: Seeking to include disabled business owners has been challenging with higher drop out rates than for other groups and a hesitancy amongst businesses to disclose disabilities due to personal or social reasons. Future programming will focus on normalizing discussions around disability, building trust through inclusive communication, showcasing success stories based on capability, and deepening partnerships with local disability organizations.
- Outreach and communication: Learning highlighted that one-size-fits-all messaging is ineffective. Platform communication, value propositions, and outreach materials are now contextualized to local ecosystem maturity, digital readiness, and user expectations. Collaboration with local ESOs, universities, and community organizations has expanded regional reach, credibility, and engagement, serving as trusted intermediaries in underserved areas.
For Component 3, the key lessons learned are:
- Expectations alignment: looking at delivery in Uzbekistan, IFC identified the importance of engaging early on with key line ministries and also non-government stakeholders to align expectations and avoid delays.
- Capacity constraints: partner government agencies carry capacity gaps – both, in terms of headcount and expertise to drive the implementation and keep the pace. On-the-job, ongoing and regular support was found to be more effective than periodic advisory missions.

Date of last narrative financial report	04/02/2026	Date of last audited annual statement	11/06/2024