## Annual Review Template

Title: Chevening Scholarships
Programme Value £ (full life): £59,330,000		Review date: 08/07/2025
Programme Code: [AMP ID] 400066	AMP start date: 01/04/2024	AMP end date: N/A

Summary of Programme Performance
Year	2025
Overall Output Score	A+
Risk Rating	Minor

DevTracker Link to Business Case:	D0005179.odt
DevTracker Link to results framework:	D0006604.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Chevening is the FCDO’s international scholarship programme for future global leaders and has been in place since 1983. It supports exceptional scholars from over 140 countries and territories around the world with fully funded master’s degrees at top UK universities. Chevening also offers fellowships to mid-career professionals in positions of influence to increase their knowledge, networks, and potential through tailored short courses, research, or professional placements at UK institutions. Chevening is one of the UK’s most important soft-power instruments. With an established reputation as a world-leading, global scholarships programme, Chevening creates lasting positive relationships with future leaders, influencers and decision-makers across the world. The programme aims to support FCDO’s objectives, achieving long-term diplomatic and strategic impact by equipping international scholars with advanced education in the UK, fostering deep personal and professional links to the UK, and encouraging alumni to apply their learning to promote positive change in their home countries.

The Chevening programme is overseen by FCDO and has been delivered by the British Council since September 2023 following a competitive tender process. The British Council has shown itself to be a reliable and efficient delivery partner, meeting expectations and contributing to the programme’s continued success. The Chevening Secretariat, managed by the British Council as the programme’s delivery partner, is responsible for the operational delivery of the Chevening Programme. This is the first annual review completed on the programme.

Summary supporting narrative for the overall score in this review

This year the Chevening programme has scored A+. The reasons for this assessment are that the programme has demonstrated strong performance overall and recent notable innovations include the successful launch of The Applicant Scholar Alumni Management System (ASAMS), the development of the new Chevening Resource Hub and an online AI-powered chatbot to assist applicants and scholars with queries. These have significantly enhanced user experience and operational efficiency.
The contract took time to bed in with ASAMS presenting particular challenges, partly due to the complexity of the system requirements including the need to develop a single platform for both Chevening and Marshall scholarship programmes, and partly because early development was focused on the security of the system rather than the user experience. Both the Scholarships Unit and British Council responded by dedicating additional support. ASAMS is now delivering well for all stakeholders, saving both time and money by automating many previously manual processes.

Communications have been impressive, with a smooth and strategic approach that has led to increased engagement across platforms, including Instagram and other digital channels. The strong and collaborative partnership between the FCDO and the British Council has been central to the programme's success, enabling innovation, responsiveness, and high-quality delivery across all areas of the programme.

Key outcomes achieved during the Annual Review period:
- Academic achievement: In the 2024/25 academic year, there were 1336 Chevening Masters scholarships awarded in priority areas, and 79 fellowships. Scholars have reported positive feedback on their academic and cultural experiences in the UK, highlighting the programme’s role in fostering personal growth, cross-cultural understanding, and professional development. In terms of academic experience, 97% of current scholars indicate that they are satisfied or very satisfied. This is similar to the high figure from last year’s scholar cohort at 99%. 99% of current scholars (2024/25 academic year) say that they would recommend UK culture.
- Increased partnership funding: For the 2025 academic cohort the partnership funding was £5.2m, this was a 33% increase on the £3.9m received the previous year demonstrating continued confidence in the programme and expanding its reach and sustainability. The FCDO has also increased efforts to attract new partner funding with additional dedicated resource now in place as of January 2025.
- Strengthened UK Perceptions: Scholars consistently report positive attitudes toward the UK, with a deepened understanding of UK communities, values, culture, and HMG priorities. 93% of 2023/24 scholars (most recent data currently available) agree that the UK is a force for good in the world, and 91% of all programme alumni report similarly. This reflects the programme’s success in fostering mutual respect and global awareness, as well as the sustained impact of the programme.
- Influential Global Network: The Chevening network continues to grow in prestige and influence, with alumni serving as world leaders, policymakers, and changemakers. The sense of connection among alumni remains strong, reinforcing Chevening’s global impact. Demand for alumni-led initiatives has increased, as evidenced by the 129 applications received for the Chevening Alumni Programme Fund (CAPF) in the current cycle. These proposals reflect alumni commitment to driving positive change in their countries and regions, while also strengthening ties with the FCDO and the broader Chevening community.
- UK as a Business Destination: Alumni increasingly view the UK as a trusted partner and destination for business, investment, and collaboration, contributing to long-term bilateral relationships. Almost half (47%) of alumni recommend the UK as a good place to do business, and more than one in ten alumni have personally done business with the UK.
- Upskilling the Chevening delivery network: The Chevening Programme has strengthened delivery capability across its global network through targeted learning and collaboration. Two regional Chevening Officer Conferences provided valuable opportunities for shared learning, peer exchange, and strategic alignment, including a focus on improving diversity in scholar applications. These events, alongside ongoing engagement with FCDO posts and the Secretariat, have supported upskilling across the network - enhancing understanding of programme priorities, improving operational performance, and embedding a more user-centred approach to delivery. This investment in learning has helped the programme remain adaptive, inclusive, and aligned with evolving global contexts.
- Improved budget management: A review of budget management processes, in collaboration with the Chevening Secretariat, has produced a more transparent, streamlined, and accurate budgeting process, with greater confidence in budget figures earlier in the financial year. This supports strategic decision-making, including the annual scholarships allocations process.

Major lessons and recommendations for the year ahead
This year has demonstrated the continued strength and relevance of the Chevening Programme. The programme delivered a series of high-impact events for scholars and alumni, fostering meaningful engagement and reinforcing the value of the Chevening network. Ministerial involvement was strong, adding visibility and support to key activities and reinforcing the programme’s strategic importance.
The programme’s popularity continued to grow, with over 90,000 eligible applications received in 2024 for approximately 1,300 places in the 2025/6 academic year - underscoring Chevening’s global appeal and competitiveness. This surge in interest – up over 28% on the previous year - presents both an opportunity and a challenge: while it affirms the programme’s reputation, it also highlights the need for continued review of selection processes, outreach, and capacity to manage scale effectively.
The programme aligns with UK foreign policy objectives, but there is scope to better evidence its contribution to soft power and development goals. Following three internal FCDO Strategic Reviews, there is also an opportunity to better align scholarship allocations to the newly identified geographic and thematic priorities.
Events and engagement activities are highly valued by scholars and alumni, but there is potential to widen alumni involvement in programme delivery and impact measurement.
Together, these lessons point to a programme that is thriving in terms of visibility, engagement, and demand, but which must continue evolving its systems and strategies to sustain quality and demonstrate long-term impact.
Recommendation 1: Enhance the programme’s evidence base
A key lesson is the challenge of evidencing impact at the highest levels of the results framework - particularly in demonstrating return on investment and the programme’s contribution to broader development goals. To address this, we will work closely with the Chevening Secretariat and M&E leads within the FCDO to explore practical ways to enhance the programme’s evidence base. This will likely include investing in further longitudinal tracking mechanisms and leveraging the Chevening alumni network for more robust data collection. We will also mature our approach to measuring impact across the three FCDO scholarships schemes including Chevening to identify the combined benefit and impact of all three scholarships to the UK and in advancing HMG priorities. Strengthening the monitoring and evaluation framework will be critical to ensuring the programme remains accountable, adaptive, and aligned with its long-term strategic objectives. We will drive forward this work in 25/26.
Recommendation 2: Enhance the application process to attract high-quality candidates from a broader range of backgrounds
With over 90,000 eligible applications received in 2024 for the 25/26 academic year, it underscores the need for continued review of the selection processes and outreach to ensure we are attracting and selecting outstanding candidates from diverse communities, and ensuring GenAI is used in an appropriate way by applicants. We are working with the Chevening Secretariat to explore targeted improvements to the application process including:
- Refining outreach and marketing strategies to better reach underrepresented groups and diverse groups, including through our network of posts as well as alumni.
- Reviewing of our approach to AI to ensure that AI tools are used in an appropriate manner;
- Reviewing selection criteria and tools to ensure they are inclusive, transparent, and aligned with the programme’s evolving goals and FCDO priorities.
These steps will help ensure that Chevening remains accessible, competitive, and representative of the UK’s commitment to inclusive global leadership.
Recommendation 3: Increase our funding for scholarship places from corporate and philanthropic partners. We currently have over 60 corporate partners funding 25% of scholar places. Since January 2025 we have undertaken outreach to over 100 corporate and philanthropic partners and have secured new partnerships. We will continue to work closely with colleagues in the Chevening Secretariat to engage with external organisations directly and indirectly via officers at post to increase the proportion of scholarship places which are funded by external partners, recognising that this is a challenge given the reduction in development funding globally and the increased competition to win funding from private and third sector donors.
Recommendation 4: Increased engagement with alumni through implementing the alumni action plan agreed with the Chevening Secretariat to develop and sustain a vibrant global network of alumni e.g. increased communications and promotion of social media networks, learning and development and networking opportunities through the new Chevening Resource Hub. Further enhancing our alumni outreach may be subject to resourcing.
Recommendation 6: Change in Annual Review timeline. FCDO to move the Annual Review timeline to September as this would coincide as best as possible with the annual scholarship cycle and tie up with the end of the contract year reporting to allow for more effective annual reporting and assessment of progress at all levels.
B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
The Chevening Programme’s Theory of Change is grounded in the belief that investing in exceptional individuals through fully funded postgraduate education in the UK will cultivate a global network of future leaders, influencers, and decision-makers. These individuals, equipped with world-class education, cross-cultural experiences, and professional networks, are expected to drive positive change in their home countries and to maintain positive relationships with the UK.

At its foundation, the programme invests in inputs such as funding, institutional partnerships, and the expertise of various stakeholders including the Chevening Secretariat, UK universities, and the FCDO. These resources fuel core activities like scholar recruitment, academic and cultural engagement during study, and structured alumni relations. The intended immediate outputs include the selection of exceptional scholars, delivery of a world-class academic experience, and promotion of positive attitudes toward the UK.

Through these activities and outputs, the programme seeks to produce intermediate outcomes focused on individual empowerment and professional advancement. Chevening alumni are expected to assume influential roles across sectors in their home countries. They will be equipped not only with academic credentials from the UK but also with an understanding of UK values and governance. Alumni engagement and support aims to encourage alumni to continue their connection with the UK as well as other alumni once they have completed their studies.

The theory of change envisions long-term impacts that extend beyond personal development. These include enhanced UK influence worldwide, increased bilateral trade and investment, and greater political and economic stability in countries where alumni operate. By embedding UK values and fostering strategic partnerships, the Chevening Programme contributes to soft power goals -demonstrating that education and diplomacy can work hand-in-hand to shape global development and cooperation.

The Chevening theory of change (Annex 1) was updated and a new logframe put in place in January 2025. The theory of change was updated to ensure the route from funding to impact was accurate. The inputs and impact largely remained the same, but the following changes were made:
- Broadened programme assumptions, including expectations that the selection process attracts high-calibre candidates, scholars actively engage with Chevening opportunities, and alumni in leadership and influential roles maintain strong UK ties;
- Expanded activities to include engagement with current and prospective partners;
- New outputs related to alumni engagement and partnerships;
- Additional outcomes focused on individual empowerment, a strengthened evidence base, and sustained or increased external partnership funding.
These refinements enhance the programme’s ability to demonstrate its value and impact. However, the overall programme design has remained stable since the British Council took on the contract for the Chevening Scholarship Programme.

The Chevening Programme continues to make strong progress toward its expected outcomes and impact. Overall, the programme is on track, with data successfully collected for approximately 85% of the expected outcomes and impact.

Notably, 21 alumni have been or are national leaders (Prime Ministers or Presidents), with many more in influential roles driving priorities including development in their home countries. Our partnerships remain a cornerstone of this success, with over 25% of scholars funded by partner organisations. Rising application numbers reflect the programme’s growing global appeal. While the applicant pool is highly diverse, we recognise the need to further encourage applications from underrepresented groups to ensure equitable access. Increasing alumni engagement also remains a priority, and we are exploring new initiatives to strengthen global alumni connections in the year ahead.

Some areas require targeted attention. Under Impact 2 (“Increased growth and stability in countries where our alumni work”), Impact Indicator 1 remains an area for development due to inconsistent data collection. We have redesigned the CAPF (Chevening Alumni Project Fund) proposal forms to integrate this data, and will provide training to alumni to improve reporting quality.

Under Outcome 2 (“Chevening is a network of connected, influential leaders with enhanced prestige via Chevening association”), we propose rewording Outcome Indicator 1 for clarity:
“% of scholars who strongly agree or agree with the statement ‘I am proud to be associated with Chevening.’”

For Outcome Indicator 3 (% of surveyed alumni who strongly agree or agree that the alumni network is helpful in remaining connected with the UK), the exact reporting data required was not captured in the most recent alumni survey, although a related question was asked. We are considering whether to use this as a proxy or wait for the correct data in the 2026 survey, where the revised question has been included.

Planned actions for the year ahead include:
- Delivering training to alumni on new CAPF reporting requirements;
- Finalising revisions to outcome indicators to improve clarity and data relevance;
- Strengthening survey design and review processes to prevent future data gaps.

These measures will help strengthen the programme’s evidence base and maintain alignment with intended outcomes and impact.

The Chevening Programme continues to demonstrate strong strategic value and should be sustained as a flagship initiative within the UK’s international engagement portfolio. On its own merits, the programme attracts exceptional individuals from around the world, fosters long-term relationships with future leaders, and enhances the UK’s global reputation for educational excellence. With over 90,000 eligible applications received in 2024, Chevening remains one of the most sought-after international scholarship schemes, reflecting its credibility and reach.

The programme also plays a vital role in advancing UK foreign policy objectives by cultivating a diverse, influential alumni network that contributes to development goals, democratic governance, and global cooperation. In the context of the wider FCDO portfolio, Chevening offers a unique and cost-effective soft power tool that complements diplomatic, trade, and development efforts. Our Heads of Mission regularly report that alumni help them deliver their goals. Its continued investment is justified not only by its direct outcomes, but by its long-term contribution to the UK’s global influence and partnerships.

## C. DETAILED OUTPUT SCORING

Output Title	Exceptional future leaders chosen
Output number:			1	Output Score:		A+
Impact weighting (%):			15%	Weighting revised since last AR?		[If Yes, up or down?] N/A

Indicator(s)		Milestone(s) for this review			Progress
% of total applicants advancing to the next phase of the application process following the reading committee review.					10% of application (25-26 cohort) advanced to the next phase of the application process following reading committee review (90,353 applicated sifted by the reading committee resulting in 9,268 Scholarship applications advancing to the next stage of the application process.

This measures the proportion of all applicants who move forward in the application process after their materials have been reviewed by the Chevening reading committee. It is expressed as a percentage of the total number of applicants.

The Chevening selection process is a rigorous, multi-stage procedure that spans approximately nine months. Central to its success is the ability to attract and identify candidates with both the academic excellence and leadership potential required to thrive. Chevening operates an open application system, meaning applicants do not need third-party nominations to apply. Ensuring a diverse and high-quality pool of applicants across all eligible countries is essential to selecting the next generation of global leaders.

For the 2025/26 cycle, the programme received over 90,000 eligible applications. Longlists of qualified candidates were generated for interview consideration by the reading committee provided they met the required criteria, Chevening Scholars had to demonstrate academic excellence, leadership potential, strong networking skills, and a clear vision for how their UK studies will drive positive change in their home countries. Given that 10% of application (25-26 cohort) advanced to the next phase of the application process following reading committee review, this demonstrates the quality of the applications received and provides strong confidence that a high-calibre cohort will once again be selected from across the globe for the 25/26 academic year.

Output Title	Scholars have a world class academic experience
Output number:		2	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	[If Yes, up or down?] N/A

Indicator(s)	Milestone(s) for this review	Progress
% of individuals ( scholars) very satisfied with the academic quality of their higher education experience	Target of 64%	Data from 2024 Scholar T3 survey / 50% of scholars are very satisfied with the academic quality of their higher education experience NB A further 46% are satisfied with the academic quality of their higher education experience, giving a total of 96% satisfied or very satisfied.

This measures the proportion of scholars who report being “very satisfied” with the academic quality of their higher education experience. It is typically expressed as a percentage of the total number of respondents within a given institution, region, or system. Scholars’ perceptions of academic quality encompass access to academic resources, study support services, curriculum relevance and rigor, and the quality of faculty supervision.

For the 2025/26 cohort, 50% of scholars reported being “very satisfied” with the academic quality of their experience—falling short of the 64% target. However, an additional 46% reported being “satisfied”, indicating that overall satisfaction remains high. These figures are consistent with the previous year’s data and align with strong alumni feedback regarding the world-class status of UK universities. Social media posts from scholars frequently reflect a sense of pride and accomplishment in studying at UK institutions and actively participating in academic and campus life.

Insights from the May 2025 Scholar Survey help contextualise the gap between “very satisfied” and “satisfied”. Key themes emerging from scholar feedback include concerns around academic rigor, course structure, and the classroom learning environment—particularly peer engagement and language barriers. These challenges are common among international students in the UK and highlight areas for potential enhancement to better align the scholar experience with programme goals.

Selected Scholar Testimonials:

"My experience is so far great with my University. I am experiencing a high-quality education in a world top University with access to unlimited learning materials, practical opportunities, networking and more."

"The university and my faculty have been amazing. Extremely supportive, forthcoming with resources and networks to positively impact my career."

Output Title	Scholars experience and engage with UK culture and values and interact with other scholars in the UK.
Output number:		3	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	[If Yes, up or down?] N/A

Indicator(s)	Milestone(s) for this review	Progress
% of scholars participating in engagement activities report them as instances of learning about UK society	55%	Data for scholar events 2024-25 cohort is being captured and will be available at the of September 2025
% of scholars participating in engagement activities evaluate the experience as providing opportunities to increase interactions (networks) with other scholars	50%	84% of scholars participants in engagement activities increase interactions(networks) with other Chevening scholars outside their university. / This data is extracted from last scholar survey (May 2025).

This output captures the immediate, measurable experiences that Chevening Scholars are expected to have during their time in the UK. These experiences are designed to immerse scholars in British cultural, social, and institutional life, while also fostering meaningful connections within a diverse global cohort. Scholars participate in a rich and varied engagement programme coordinated by the Secretariat, offering opportunities to explore UK education and culture more broadly and to expand their professional and personal networks.

Two flagship events - Orientation and Farewell - bookend the academic year and are attended by all scholars. During the current academic year, a further 24 in-person activities will have taken place across the UK. These include volunteering opportunities, educational panel discussions, and cultural visits. The engagement programme is further enriched by working with partners who open up dedicated spaces for Chevening scholars at their events. Notable examples include:
- Receptions by Study UK for students in Wales and Scotland,
- BBC World Service internships,
- Access to online Law and International Development courses in run by the University of Cambridge.

A vibrant social media campaign encourages scholars to share their experiences across the UK. Ten Social Media Ambassadors are selected annually to lead this effort,

Engagement data shows that 84% of scholars who participated in engagement activities reported increased interaction with fellow Chevening Scholars outside their own universities—well above the 50% target. This indicates that the programme is successfully fostering cross-institutional networking and building a strong, interconnected scholar community.

Output Title	Alumni maintain connections with the UK (directly, or through ongoing contact with Post) and become future change makers
Output number:		4	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	[If Yes, up or down?] N/A

Indicator(s)	Milestone(s) for this review	Progress
% of engaged alumni (as defined as those who open the Connection alumni newsletter)	22%	46% of engaged alumni open the Connection alumni newsletter) / Data (see below) shows open rates in the last 3 years.
% of engaged alumni (who have registered for and/or attended a Chevening-organized event - in person at Post, in the UK, or online, in the last 12 months. (eg, Welcome Home; other events; online webinars)	22%	30% of engaged alumni attended a Chevening organized event / Data from 2025 alumni survey.

This output is currently on track and has surpassed its targets. Both indicators under this output have exceeded expectations. This positive trend has been supported by the alumni team’s efforts, including the introduction of online development courses. These initiatives have encouraged increased engagement, with more alumni actively reconnecting with Chevening. Notably, the connection alumni newsletter has seen a significant rise in engagement - its open rate has increased from 24% three years ago to 46% this year.

Other indicators of positive engagement with Chevening alumni has been the growth of the two closed social media communities on LinkedIn and Facebook which have expanded their membership over the course of the year to reach 9,600 and 7,900 alumni respectively.

Data from the alumni survey in 2025 continues to support the position that Chevening alumni go on to positions of influence and leadership in their careers. 71% report that they hold such positions.

Quote from an Alumni in the 2025 Alumni Survey
“My Chevening experience was truly life-changing. As part of the 2019/20 cohort, I had the unique experience of spending the first COVID-19 lockdown in the UK, which, in an unexpected way, made me feel even more at home there. Beyond the exceptional academic and life experiences, the most invaluable aspect was the people I met: fellow scholars from the Western Balkans, the UK, and around the world. These connections have grown into lasting friendships, and we continue to support and celebrate each other's academic, professional, and personal achievements. Chevening also had a direct impact on my professional trajectory. As a result of this experience, I transitioned to working for a UK-based NGO that runs programmes in the Western Balkans. Through our projects, we collaborate closely with the UK Government to strengthen the rule of law, advance SDGs, and promote societal development. The British experience and expertise I gained during my time in the UK are widely recognised and valued in my work, shaping my approach to policy, governance, and capacity-building in the region. Chevening was not just a scholarship, it was a transformative journey that continues to influence my professional and personal growth. I am truly grateful once again for this opportunity!”

In addition to alumni events delivered by Posts, a new initiative this year introduced a series of Learning and Development webinars focused on soft skills. These sessions attracted 1,380 registrations and engaged over 600 participants from 66 countries. Building on this initial success, the Secretariat will explore further opportunities to expand such activities to strengthen alumni engagement.

While current levels of engagement are encouraging, there is recognition that more can be done to sustain and deepen alumni involvement over time. Alumni remain one of the programme’s most valuable assets, and continued investment in their development and connection to the UK is essential to achieving long-term impact. Looking ahead to 2025–26, plans include launching an alumni survey. This will help to identify the on-going trajectory of alumni and the specific interests at different stages of their journey.

Output Title	A healthy and diverse partner portfolio that is maintained / expanded
Output number:		5	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	[If Yes, up or down?] N/A

Indicator(s)	Milestone(s) for this review	Progress
No. of partner organisations (corporate, foundation, higher-education institutions) supporting Chevening. (Excludes universities contributing a discounted tuition fee only)	63	97 partner organisations (corporate, foundation, higher-education institutions) supporting Chevening
No. of higher-education institutions supporting Chevening	? Not applicable	51 higher-education institutions supporting Chevening

The partnership portfolio has continued to expand and grow over the year. New central partnerships and local partnerships have been secured to support the costs of scholarships. Recent local partnerships secured include the Trident Group in India and Koji Atelier in Japan. Partnerships are typically agreed for a 3-year period, and over the course of the year 28 corporate partnerships have been renewed. A government round-table event in April resulted in new partnership commitments from 3 companies in the sustainable energy sector: Octopus, Centrica and Prysmian.

Long-standing university partnerships bring in valued income in-kind to Chevening as they waive tuition fees for scholars. Aston University and the University of Greenwich have become new partners for the first time during the year and will support scholars starting in September 2025.

There has been an increased focus in pursuing partnerships with two new members of staff joining the TSU team dedicated to following up on leads for corporate partnerships. The challenging external environment for winning funding is noted. With the reduction of funding globally for development activities, corporates, trusts and foundations are reported to be receiving many more requests and applications for funding. From the UK university perspective, the very difficult financial situation that many now find themselves in appears to be putting pressure on partnerships. For instance, two long-standing partners have reduced the number of partner awards available for the upcoming cohort.

Chevening may have the opportunity to optimise partnership funding from universities more effectively. The current approach presents a gap between awards pledged and those that are finally able to be taken up. This is as a result of the selection process which only considers applicants for partnerships once they have been selected. A modified approach, giving greater priority at the longlisting stage for applicants eligible for partnership awards could help to leverage a greater number of partnerships. This can be explored further for the next application cycle.

Lessons learned this year and recommendations for the year ahead

As this is the first Annual Review under the current programme cycle, there are no prior recommendations to report on. However, the implementation experience over the past year has surfaced several important lessons that will shape our approach going forward.
A key learning has been the challenge of evidencing long-term impact, particularly in demonstrating return on investment and alignment with broader development goals. This has highlighted the need for a more robust and coordinated monitoring and evaluation framework across the FCDO’s scholarship schemes. We also recognised the importance of refining the application process to ensure it remains inclusive and responsive to emerging technologies such as generative AI. Additionally, our experience engaging with corporate and philanthropic partners, as well as alumni, has reinforced the value of sustained, targeted outreach.
The challenging start to the contract also highlighted the importance of open communication and continuity, including the need for the FCDO contract lead to remain in place for 6–9 months post-award to support a smoother transition. These insights underpin our recommendations for the year ahead, which focus on strengthening the programme’s evidence base, enhancing accessibility and diversity in recruitment, expanding external funding, and deepening alumni engagement.

## D: VALUE FOR MONEY

Key cost drivers and performance

Over 90% of programme costs are those which relate directly to the benefits received by Chevening scholars, namely: tuition fees paid to universities, stipend payments made to scholars, flight costs, and visa & immigration health surcharge (IHS) fees paid to the Home Office. These inputs are fundamental to the delivery of the programme, so there is little opportunity to deliver savings without reducing output. Furthermore, the ability of the FCDO to reduce costs of these inputs is limited: tuition fees are set by UK higher education institutions and influenced by market forces; the stipend rate is a basic rate intended to cover scholars’ basic living requirements such as food and rent, and is increased in line with the Consumer Price Index (CPI) rate of inflation annually; flight costs are set by the market; and the visa and IHS rates are mandated by the Home Office.

The Scholarships Unit maximises value for money in relation to direct scholar costs by securing considerable support from partners to leverage FCDO funding. Without this support direct scholar costs as outlined above would exceed 120% of the programme allocation. In-kind contributions, primarily in the form of 20% tuition fee waivers from all UK higher education institutions and further 100% waivers for a smaller number of scholars, represented £10.8m in-kind benefits in FY24/25. Additionally, income from corporate and philanthropic partners produced £5.6m income in FY24/25. The Scholarships Unit has collaborated with Other Government Departments and solicited advice within the FCDO to develop a new partnerships strategy which will secure greater external support for the programme in the form of cash and in-kind contributions in future years.

Another cost driver of the programme is the management fee paid to the commercial supplier for its administration of the programme in its capacity as the Chevening Secretariat. The supplier was awarded the contract having been successful at tender through the Crown Commercial Service’s Dynamic Purchasing System (DPS) route. The supplier was paid in line with the contractually agreed price in FY24/25. This represents value for money given the strong quality of service which the Secretariat has provided in the administration and delivery of Chevening Scholarships programme, in line with the Key Performance Indicators (KPIs) specified in the contract. These services include:
- Managing the implementation of the bespoke Applicant, Scholar and Alumni Management System (ASAMS). Responsive engagement with the ASAMS developer has produced a system capable of more efficiently managing applicant, scholar, and alumni data.
- Leading on monitoring and evaluation to provide greater evaluation of programme effectiveness against outputs and outcomes specified by TSU in a results framework.
- Cohesive and responsive international team which manages the programme’s relationship with a network of over 120 posts worldwide.
- Continuous improvement of financial reporting requirements. Budget profiling and forecasting were delivered with greater confidence than before, and end of year expenditure was more accurate than in previous years. With more accurate, detailed and responsive management information the Scholarships Unit is better able to scrutinise supplier expenditure in support of strategic expenditure decisions, in line with value for money principles.
- Emphasis on financial efficiencies. Financial management by supplier has identified and delivered financial efficiencies such as in reducing administration fee paid to travel supplier and reducing expenditure on merchandise.
A contract variation negotiated during FY24/25 and agreed during FY25/26 will result in an increase in contract price of 3%, all of which will be accounted for in subsequent financial periods. The Scholarships Unit is confident this represents value for money given the new innovations the contract has brought. Even including the cost of the variation, the British Council contract still remains the best value of all the bids received during the tender process.

The Scholarships Unit is also ensuring value for money in Chevening Fellowships, which constitute around 3% of programme costs, by conducting a Fellowships Review. This will assess the value for money case of each of ten fellowship programmes; the outcome of the review will inform the adjustment of the fellowships portfolio. Additionally, although the Chevening business case suggested competitive tenders should be run for fellowships contracts, the Scholarship Unit has decided to preserve the usage of the Memorandum of Understanding mechanism in many cases. This is a strategic decision to ensure that fellowships may be procured and/or adapted quickly, thereby serving as a flexible tool responsive to changing FCDO strategic priorities. A comprehensive switch to tender-led fellowship procurement would reduce the strategic utility of the output and would therefore not represent value for money.

Assessment of whether the programme continues to represent value for money

Based on the above analysis there is clear evidence that the programme continues to represent value for money and that the programme should continue. Scholarships are scalable on an annual basis so that the output may be increased or decreased in line with expenditure appetite. FCDO funding is highly leveraged by means of successful partnerships which generate both cash-based and in-kind benefits, effectively subsidising scholar unit costs to allow FCDO to deliver considerably more scholarships than would otherwise be affordable. Given the intersection of Chevening Scholarships with various FCDO priorities, including growth, soft power, and development, and their utility in bilateral relationships, the programme represents value for money.

E: RISK [½ to 1 page]

Risk management

The FCDO currently assesses the overall risk rating for the Chevening Scholarships Programme as moderate, which aligns with the department’s established risk appetite. The programme continues to operate well within this threshold, as reflected in the accompanying risk matrix. Risk management is embedded in programme delivery, with regular reviews conducted by the Senior Responsible Owner (SRO) and the programme team. Any emerging or escalating risks are promptly escalated to the senior leadership team, ensuring timely oversight and mitigation. The FCDO’s risk register for the Chevening programme is reviewed and updated on a quarterly basis, capturing any changes in the risk landscape and ensuring that mitigation strategies remain robust and responsive.

Risk Appetite vs Residual Risk
Risk Category	FCDO Risk Appetite	Residual Risk Level	Alignment
Strategy & Context	Receptive	Moderate	✅ Within Appetite
Policy & Programme Delivery	Receptive	Moderate to Minor	✅ Within Appetite
Public Service Delivery	Cautious	Moderate	✅ Within Appetite
People	Cautious	Major	At Appetite Limit
Safeguarding	Cautious	Major	At Appetite Limit
Financial & Fiduciary	Cautious	Minor to Moderate	✅ Within Appetite
Reputational	Cautious	Minor to Moderate	✅ Within Appetite

Risk Appetite levels for each of the seven categories
Risk Category	Proposed Appetite	Rationale
Strategy and Context	Receptive	Chevening operates in a dynamic global context and must adapt to geopolitical shifts, ODA eligibility changes, and strategic partnerships. A moderate appetite allows for innovation while managing reputational risk.
Policy and Programme Delivery	Cautious	Delivery must be consistent, equitable, and aligned with FCDO objectives. While some flexibility is needed, risks to delivery quality or fairness must be tightly controlled.
Public Service Delivery and Operations	Cautious	Operational risks (e.g., IT systems, data handling, scholar logistics) must be managed conservatively to ensure continuity and compliance / Digital Security & Data Protection: Risks around personal data (P4) remain high due to cyber threats. Mitigation includes the launch of ASAMS, staff training, and a new Data Protection Impact Assessment. / Operational Delivery: Risks from contract performance (D12) and staff turnover (D7) have been reduced through succession planning and KPI monitoring.
People	Minimal	Given the importance of safeguarding scholars and staff, and the reputational sensitivity of personnel issues, the programme should have a low tolerance for people-related risks.
Safeguarding	Minimal	Zero tolerance for SEAH, child safeguarding breaches, or discrimination. Strong policies and rapid response mechanisms are essential. Risks to individuals with protected characteristics remain significant. Safeguarding policies, critical incident protocols, and targeted support are in place.
Financial and Fiduciary	Cautious	While some financial flexibility is needed (e.g., partnerships), the programme must avoid overspend, fraud, or mismanagement.
Reputational	Minimal	The Chevening brand is a core asset. Any damage could undermine trust, funding, and long-term viability. Risks must be tightly controlled. Concerns about Chevening’s value (R5) and online content (R6) are being addressed through a new Monitoring and evaluation lead MEL strategy and enhanced digital oversight.

Key Risks and Mitigation Measures
Inconsistent Funding Due to ODA Cuts (Risk ID: F0)
Description: ODA budget fluctuations restrict planning and management of the Chevening scheme.
Mitigation: Establishment of a dedicated partnerships team to enhance sustainability and value for money (VFM).
Progress: Risk rating reduced from Major to Moderate.The partnerships team is now operational and contributing to financial resilience however partner funding cannot immediately replace ODA cuts.

Risk of Overdrawn Government Banking Service Account (F3)
Description: Overdrafts could lead to reputational damage, as they are reported daily to HM Treasury.
Mitigation: Strengthened oversight via Chevening Programme Board and Risk and Finance Committees; improved Scholarship Unit’s finance capacity; new contract with Key Performance Indicator (KPI)-based performance.
Progress: Risk reduced from Major to Moderate. Enhanced financial scrutiny and contract management are in place.

Rising Costs (Tuition & Stipends) Impacting Award Numbers (F13)
Description: Cost increases could reduce the number of scholarships awarded.
Mitigation: Proactive budget management, regular FCDO-BC discussions, and a fee cap policy.
Progress: Risk reduced from Moderate to Minor. The team has successfully adjusted award numbers to stay within budget.

Budgetary Control and Financial Reporting (F11)
Description: Inaccurate projections or unreliable data could lead to poor financial decisions.
Mitigation: New reporting templates, regular finance meetings, and a Theory of Change framework.
Progress: Risk reduced from Major to Minor. Improved reporting and governance structures are now embedded.

Post Allocations Under/Overspent (F9)
Description: Variance between forecast and actual spend, especially in Q3.
Mitigation: Reduced allocations for FY25/26, clearer AMP/Hera coding, and enhanced The Scholarship Unit (TSU)-post engagement.
Progress: Risk reduced from Moderate to Minor. Financial tracking and collaboration with posts have improved.

Climate and Environment
The Chevening Programme has assessed climate and environmental risks and considers them low. However, we are exploring opportunities to reduce the programme’s carbon footprint, including promoting virtual engagement, sustainable travel options, and green procurement practices.

Actions taken by the Chevening Secretariat to measure and reduce the Programme’s environmental impact include:

- Requiring the Programme’s travel provider to track and report on CO2 emissions and travel distances.
- Ensuring that marketing materials for Posts comply with the Global Recycled Standard (GRS).
- Planning events with greener catering options.
- Developing Social Value initiatives for Scholars that support sustainability-related objectives (e.g. Carbon Literacy Training).
Due Diligence

- Due diligence assessments are done at post level and they are stored in FCDO Due Diligence Library (DDA) Library. Due diligence assessments conducted by the Chevening Secretariat include:
- A Pre-Appointment Screening (PAS) process for all newly hired Secretariat staff.
- A background check (“desk research”) for applicants to the Chevening Reading Committees.
- Sanctions and financial crime screening for selected suppliers.
Positive Progress

Improved financial governance: Establishment of Chevening programme Board and Risk and Finance Committees and enhanced Scholarships Unit finance capacity.
Proactive cost management: Adjustments to scholarship numbers and fee cap policy to maintain programme scale and quality.
Data-driven decision-making: Introduction of new reporting tools and a Theory of Change to align financial planning with strategic goals.
Partnership development: A dedicated team now supports financial sustainability through diversified funding.

F:
PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Contract: The British Council took over the contract for delivery of the Chevening scholarships programme on 1 September 2023 following a competitive tender process. It is a two-year contract with the option of extending for further year (year 3) and a following further year (year 4). While the early days of the contract experienced some teething problems, the British Council responded by deploying additional staff to support the process. For example, the implementation of ASAMS was more complex and resource-intensive than initially anticipated, but it is now operating effectively. The British Council has proved itself to be a highly effective delivery partner, and we have recently agreed to extend the contract for Year 3. The programme is overseen by a Senior Responsible Owner (SRO) in the FCDO.

Governance: A Chevening Board made up of senior FCDO members meets quarterly to oversee Chevening strategy, decision making and long-term planning of the programme.

Reporting Cycle: The Chevening Secretariat provided the FCDO with a detailed and comprehensive annual progress report at the end Year 1 of the contract enabling the FCDO to maintain strong oversight of the programme. The Secretariat also submits to the FCDO quarterly contract review reports. These provide an update on programme activity over the previous quarter including scholar and alumni engagement, promotion and comms, monitoring and evaluation as well as a risk review and progress against KPIs. Reports are always submitted on time and provide a consistently high-quality review of the programme. Quarterly contract review meetings are held with the FCDO and the Secretariat to discuss quarterly and annual reports to ensure alignment on strategic and operational priorities. In addition, fortnightly working level meetings are held between the Chevening Secretariat and the FCDO on programme activity.

The Secretariat has delivered new innovations to enhance programme delivery, including:

- a new online applicant, scholar and alumni management system (ASAMS) to streamline the process of scholarship management from application through selection and study phase and onto management of alumni;
- the introduction of a new Chevening Resource hub for scholars and alumni providing tailored support and resources for scholars and alumni;
- an online chatbot (“Chevening Charlie”) an AI-powered chatbot to assist applicants and scholars with common queries.
To support operational resilience, the Secretariat reviews and updates its Information Security (InfoSec) Plan and Business Continuity and Disaster Recovery (BCDR) Plan annually, ensuring robust risk mitigation and continuity of service are in place. The BCDR was last updated and approved by FCDO in November 2024, and the most recent InfoSec review was completed in June 2025.

Financial Management: Financial reports have been delivered consistently on time in line with KPIs, with 100% of detailed monthly accounts of both drawdown costs and administration costs submitted to the FCDO Scholarships Unit within 10 days following month end. 0% of reports rejected by FCDO for lack of conformity to agreed reporting format. The Secretariat has iteratively improved the quality of financial reporting in consultation with the Scholarships Unit by redesigning cost categorisation, providing greater transparency by way of granulated information, and by embedding within the monthly financial report separate sub-reports for partnership income and fellowships expenditure.

Risks: Risk management is embedded in programme delivery, with regular reviews conducted by the Senior Responsible Owner (SRO) and the programme team. Any emerging or escalating risks are promptly escalated to the senior leadership team, ensuring timely oversight and mitigation. The FCDO’s risk register for the Chevening programme is reviewed and updated on a quarterly basis, capturing any changes in the risk landscape and ensuring that mitigation strategies remain robust and responsive.

A detailed Delivery Chain Map of the programme is submitted annually by the Secretariat as part of compliance with the FCDO Supplier Code of Conduct (the most recent was submitted in May 2025). In addition, the “Contractor and Supplier Register” is updated regularly and is included as one of the annexes to the Secretariat Exit Plan.

The Secretariat Exit Plan is reviewed and updated regularly and includes annexes that monitor and account for programme assets. These annexes include:
- The Chevening Asset Register, which tracks laptops issued by the FCDO to Secretariat members.
- The Physical Materials and Documents Inventory, which records the storage locations and inventory of historical records, physical programme assets, and merchandise.
The programme data assets are monitored through the ASAMS Handover Plan. The overall approach to the monitoring and management of data is governed by the Data Protection Impact Assessment (DPIA), Information Security (InfoSec) Plan, Legitimate Interest Assessment (LIA), and Record Retention Schedules (RRS).

Delivery against KPIs: the Secretariat is delivering strongly against the KPIs set out in the contract. These include targets for:
- Communications and Promotion: Targets have been exceeded, with a notable increase in engagement across social media platforms. The Chevening Resource Hub has seen a significant rise in user traffic, indicating strong interest and uptake.
- Scholar and Fellow Selection and Support: The selection process has been delivered on schedule and to a high standard, with strong support mechanisms in place for scholars and fellows throughout their time in the UK.
- Alumni Engagement: an alumni action has plan has been agreed to enhance alumni activities further and contribute to a stronger global Chevening network.
- Partnerships: new corporate and university partnerships have been developed, supporting programme sustainability and reach.
- Finance: Financial management has been compliant and transparent, with timely reporting and adherence to budgetary controls.
- Monitoring and Evaluation: A strengthened M&E framework with a revised theory of change and logframe, and we are exploring additional M&E methods with the Secretariat including improved data collection to better evidence Chevening’s impact.

Compliance with the Supply Partner Code:
The Secretariat has demonstrated full compliance with the FCDO’s Supply Partner Code. It is a responsible and accountable partner that acts transparently and with integrity. It demonstrates commitment to wider FCDO priorities and seeks ways to improve value for money. It adheres to ethical standards, environmental sustainability and has robust anticorruption measures and safeguarding policies in place. Regular monitoring of the code by the Secretariat ensures continued alignment with the Code’s principles. For additional compliance with the Code, the Secretariat also provides FCDO with a Delivery Chain Map and a Profit Declaration, and publicly discloses financial information through its submissions to the International Aid Transparency Initiative (IATI).
The Chevening programme is committed to promoting and supporting diversity and inclusion through its programming. It ensures that gender considerations are embedded across programme delivery. Robust processes are in place to attract a diverse range of candidates to the programme, and ensure that the application and selection processes are open, accessible and fair. Whilst scholars are in the UK, Chevening provides welfare support and an events programme which is accessible and celebrates diversity. A pregnancy and maternity policy supports pregnant scholars to pause and complete the studies according to their needs. All scholars and fellows receive training on equality, diversity and consent in the UK.
Additional EDI practices implemented by the Secretariat include:
- Mandatory EDI-related training for Secretariat staff, including completion of the Understanding Equality, Diversity and Inclusion course.
- Ensuring alignment with British Council organisational approach to EDI in programme delivery and planning.
- The inclusion of EDI clauses in supplier contracts. For example: “Equality, Diversity and Inclusion: The Supplier must agree that it does not, whether as an employer or provider of services and/or goods, discriminate within the meaning of the Equality Legislation, and that it shall comply with any equality or diversity policies or guidelines included in the British Council.”

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and evaluation activities have remained central to programme delivery throughout the review period. The Chevening Secretariat leads on data collection from scholars and alumni. Scholars provide feedback at three key points during their one-year award in the UK, while alumni are surveyed post-award through Chevening’s longitudinal evaluation project. This project tracks changes in attitudes toward the Chevening experience, the UK, and UK values. In a recent report, 85% of alumni respondents reported applying the skills and knowledge gained during their award to promote change in their home countries.
Qualitative evidence further supports these findings. Chevening’s Impact Report, published annually, includes case studies that illustrate how alumni are driving meaningful change. FCDO posts regularly submit alumni success stories, which help the Secretariat document and showcase programme impact. The calibre of alumni - 21 of whom are current or previous heads of state or government - also reflects the programme’s long-term influence. Alumni contribute to UK soft power by influencing investment decisions, promoting UK exports, aligning to UK priorities in multilaterals and other fora and maintaining personal and professional ties with the UK.
The Secretariat also surveys FCDO posts to gather feedback on its own performance. Programme adaptations have been informed by ongoing stakeholder consultation. For example, posts were engaged in the development and rollout of the ASAMS system, and consulted on key programme decisions. This consultative approach has ensured delivery remains responsive to local contexts and operational realities.
Additionally, the 2022 Public Bodies Review provided an independent assessment of the FCDO’s three scholarship schemes, including Chevening. It found all three to be highly effective in delivering their strategic objectives and recommended improvements to enhance coordination and efficiency. These findings continue to inform strategic planning. Looking ahead, we will continue to strengthen our M&E systems, including exploring a counterfactual study and improved data collection for Chevening.

Evidence

During the 2024–2025 review period, the programme added to a strong evidence base:
1. Programming documents
New Logframe and KPIs: In January 2025, we developed a logframe to reflect targets and milestones.
2. Quality and Breadth of Evidence
Mixed Methods: Chevening uses both quantitative (e.g., KPIs, survey results) and qualitative (e.g., case studies) approaches, enhancing the robustness of its evidence.

Learning
Over the past year, the Chevening Programme has embedded learning processes across both delivery and strategy. Lessons have been captured through ongoing feedback from the Chevening Secretariat, regular dialogue with Chevening leads at our overseas Embassies and High Commissions, and consultation with the FCDO’s Monitoring and Evaluation team. These insights have been used to inform programme improvements. For example, a key lesson has been the importance of designing with the user in mind. Feedback from FCDO posts during the rollout of the ASAMS system highlighted areas for improvement in user experience, prompting a more user-centred approach to system development and communications.
Learning has also been supported through scholar and alumni surveys, internal reviews, and cross-scheme collaboration with the Commonwealth and Marshall scholarship teams. The Chevening Alumni Programme Fund (CAPF) has reinforced the value of sustained alumni engagement, supporting alumni-led projects and highlighting the importance of maintaining long-term relationships with awardees.
A key area of learning has been the value of investing in the capability and cohesion of the Chevening delivery network. The two Chevening Officer Conferences served as important platforms for shared learning, peer exchange, and strategic alignment. These events, alongside ongoing engagement with FCDO posts, have reinforced the importance of continuous upskilling and collaboration across the network. This learning will inform future efforts to strengthen delivery, enhance inclusivity, and ensure the programme remains responsive to evolving global and operational contexts.
For the wider FCDO, the programme reinforces the importance of investing in long-term, people-centred partnerships and capturing evidence of impact beyond the award year. It also highlights the value of coordinated learning across scholarship schemes to improve strategic alignment and shared impact measurement. Looking ahead, a key learning aim is to strengthen the evidence base on alumni impact - particularly how Chevening alumni contribute to development goals and UK strategic interests globally. This will inform future programming and help ensure that the full value of the scholarship is captured and communicated.

Date of last narrative financial report	3/06/2025	Date of last audited annual statement	N/A

Annex A - Chevening Theory of Change