## Annual Review

Title: Portfolio guarantee to the Innovative Finance Facility for Climate in Asia and the Pacific
Programme Value £ (full life): The contingent liability of the guarantee provided by FCDO is $280,000,000. There will be no spend on the programme unless the guarantee is called. There have been no calls on the guarantee to date.		Review date: July 2025 (Review period covers November 2024 to December 2024)
Programme Code: 400072	AMP start date: 10/07/2024	AMP end date: 31/12/2053
[note] The value of the guarantee is denominated in USD in agreement with the Asian Development Bank as the beneficiary of the guarantee. There has been no payout, and therefore no spend, on the guarantee to date. The value of any payout would be converted from USD to GBP based on the spot exchange rate at the time of payout.

Summary of Programme Performance
Year	2024
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400072 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	Refer to DevTracker link to logframe once uploaded.

A. SUMMARY AND OVERVIEW

Description of programme

This Annual Review is the first annual assessment of the programme for the portfolio guarantee to the Innovative Finance Facility for Climate in Asia and the Pacific (IF-CAP). IF-CAP is a portfolio guarantee platform developed by the Asian Development Bank (ADB) covering a portfolio of ADB sovereign loans to 29 countries. Through IF-CAP, the UK provided a $280m guarantee which will unlock $1.26bn of additional climate finance for countries in Asia and the Pacific. The UK guarantee is provided alongside $2bn of guarantees from five other ADB shareholders, which together will unlock $10.26bn of additional ADB lending. IF-CAP is a key element in enabling ADB to reach its ambitions to provide $100bn in climate finance from 2019 to 2030, and for climate finance to reach 50% of the total committed financing volume by 2030.

As with all Multilateral Development Banks (MDBs), ADB provisions ‘risk capital’ (i.e. shareholder capital plus reserves) to back up the loans that they make. The IF-CAP guarantee works by transferring the default risk of a reference portfolio of existing ADB loans to the governments of 29 countries in Asia and the Pacific from the ADB balance sheet to the UK and the other IF-CAP guarantors. By providing a guarantee, the IF-CAP guarantors commit to paying ADB, up to a limit, what it is owed in the event that a borrower defaults on a loan that the guarantee covers. As ADB now faces less risk of not receiving a repayment, less risk capital is required to support ADB’s existing lending portfolio and it is therefore able to redeploy its resources and expand lending operations as a result of the guarantee. ADB will use the unlocked lending headroom to commit new IF-CAP-enabled projects during the first five years of IF-CAP’s implementation, referred to here as the ‘Investment Period’.

Guarantees to the MDBs are used by the UK to expand MDB lending to provide additional, affordable finance for developing countries. Guarantees offer good value for money by unlocking large volumes of additional MDB financial assistance with no upfront cost to the UK (as no Official Development Assistance is scored when a guarantee to a MDB is issued), and a very low possibility of future ODA costs conditional on sovereign default on MDB lending. The IF-CAP guarantee is a major part of the UK’s portfolio of MDB guarantees as an innovative risk-sharing mechanism involving multiple guarantors, creating a positive demonstration effect for other MDBs and potential guarantors.

Summary supporting narrative for the overall score in this review

This annual review covers milestones and results for calendar year 2024, as reported in ADB’s IF-CAP Annual Report provided to IF-CAP guarantors in April 2025. Given that IF-CAP became operational in November 2024, the reporting period for this first annual review includes in practice only the first two months of operation. The first review period therefore assesses performance against a qualitative milestone of whether IF-CAP has been operationalised and started to deliver unlocked lending through IF-CAP-enabled projects. Future milestones and ARs will assess a full year of IF-CAP’s operation against quantitative expectations, aligning with ADB’s IF-CAP Annual Report provided every April and covering the previous calendar year.
[note] The IF-CAP Business Case was approved in October 2023. The negotiation and finalising of the IF-CAP guarantee structure took place in the period leading up to the UK’s formal signing of the guarantee in November 2024, which is also when IF-CAP became operational.

We make the overall judgement that programme outputs have met expectations for the first two months of IF-CAP becoming operationalised and starting to deliver on expected outcomes and impacts. IF-CAP is shown to be providing credit relief and enabling ADB to commit additional climate finance for new projects as expected (see Box 1). The level of risk (i.e. potential payout costs) taken on by the UK as a result of providing this guarantee also remains in line with expectations. The overall score is therefore an ‘A’, indicating that the programme has met expectations in this review period.

Major lessons and recommendations for the year ahead

Lesson learned	SMART recommendation	Deadline
The successful design and implementation of IF-CAP so far demonstrates its potential to deliver additional and affordable climate finance. Increasing the external awareness and understanding of IF-CAP should help to realise the direct benefits of unlocking finance and development impacts, but also the indirect benefits of IF-CAP’s demonstration effect as an innovative instrument.	FCDO and ADB to identify opportunities for knowledge exchange with borrower countries and ADB shareholders. / FCDO to share experiences from IF-CAP with other MDBs. / The aims of this knowledge-sharing should centre around increasing external awareness of IF-CAP and the opportunities it creates to deliver new climate projects, and IF-CAP’s potential for replication.	July 2026
Project pipeline development at this early stage of IF-CAP’s implementation will determine the success of IF-CAP, in terms of delivering the new lending and projects needed to achieve the outcomes and impacts envisaged in the BC. Increased awareness within FCDO and ADB of the opportunities created by IF-CAP is a key part of promoting IF-CAP utilisation and supporting pipeline development by ADB.	FCDO and ADB to strengthen respective internal communication channels to improve technical understanding of IF-CAP’s financing mechanism, and to increase awareness of the opportunities to deliver new IF-CAP-enabled climate projects.	July 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Figure 1: Theory of Change for the IF-CAP guarantee
Inputs		Outputs		Outcomes		Impacts
UK provides support to ADB’s IF-CAP transaction. / Guarantee on ADB’s existing loan portfolio. / Policy engagement with the ADB, participation on IF-CAP donor committee, and performance monitoring.		A UK guarantee unlocks additional ADB lending capacity and increases ADB’s climate finance lending. / ADB lower their exposure to risk, increasing capacity for new lending operations.		The IF-CAP guarantee platform delivers additional climate finance for Asia and the Pacific. / Additional ADB lending to eligible members for development projects aligned with ADB’s Climate Change Action Plan.		Greater climate change mitigation and disaster resilience in Asia and the Pacific. / Countries in Asia and Pacific reduce greenhouse gas emissions, their negative exposure to the impact of climate change is reduced, and progress towards Climate Action SDG 13 is accelerated.
		Assumptions: / Other donors contribute to IF-CAP alongside the UK. / ADB’s lending capacity is increased. This has been confirmed by credit rating agency Fitch’s assessment that IF-CAP reduces ADB’s exposure to default risk.		Assumptions: / ADB pipeline and capacity increases. ADB must have institutional capacity and a pipeline of projects to utilise additional lending headroom (for mitigation and adaptation activities). / IF-CAP finance is additional and non-fungible. ADB must provide monitoring and evidence to provide all assurances that lending unlocked through IF-CAP is additional to lending plans – including those unlocked by other CAF measures – and not substitutional thereof. / Demand from partner countries for climate-change related investment increases in line with ADB’s lending projections.		Assumptions: / Projects deliver expected results. ADB is capable of sustained impact on the sectors and policies of its programmes. / Effective allocation. We assume that ADB systems are in place to allocate new lending effectively to projects which will have a positive impact. / There is political will and capacity in partner countries to make commitment and reforms to reduce GHG emissions and to ensure that ADB projects have a sustained impact.

The Theory of Change for the IF-CAP guarantee above shows how UK support for the ADB, alongside other IF-CAP guarantors, is used to enable greater climate change mitigation and disaster resilience for countries in Asia and the Pacific. This has been updated to align with the programme’s results framework and ADB’s IF-CAP Annual Report. Specifically, the outputs reflect climate finance mobilised as a direct result of the UK’s guarantee, whilst the outcomes reflect the climate finance mobilised by the IF-CAP guarantee platform as a whole. There is otherwise no change in how the programme is expected to deliver climate and development impacts.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The IF-CAP programme is on track to achieve the expected outcomes and impact of increasing climate finance lending to support greater climate change mitigation and adaptation in the Asia and Pacific region. The time taken from approval of the BC to signing of the guarantee was in line with expectations given the involvement of multiple guarantors, and the innovative nature of IF-CAP. The link between the capital relief provided by IF-CAP and the climate and development impact of additional ADB lending is clear and functioning as envisaged in the business case.

As of end-2024, IF-CAP has reduced the amount of risk capital that ADB needs to provision to back up its loans by $0.9m (see paragraph 2 for how IF-CAP transfers risk). As a result, ADB was able to redeploy this risk capital and use it to approve the first IF-CAP-enabled project to support the construction of a new sustainable aviation fuel facility in Pakistan.

Box 1: Example of expected outcomes and impacts from IF-CAP-enabled projects

ADB is providing $41.2m of climate finance enabled by IF-CAP to support the construction of a sustainable aviation fuel facility in Pakistan. This private-sector led project will increase the adoption of clean production technologies and generate local employment in a gender-inclusive manner. The project is expected to mitigate 168,700 tCO2e of emissions annually, generate at least 155 jobs, and provide at least 20 skilled jobs for women. At this early stage of IF-CAP’s implementation, this project demonstrates the potential for our guarantee to contribute towards tackling climate change through the unlocking of ADB lending headroom for new climate finance.

ADB have also presented an indicative pipeline of new IF-CAP-enabled projects to be committed in the year ahead. The rate at which new lending will be committed based on this project pipeline indicates that ADB expect to develop new projects at the rate required to achieve the finance mobilised outcomes and development impacts envisaged. FCDO will work with ADB to review, and if necessary, update the milestones and indicator targets based on the results achieved from the prior (i.e. this) year’s remaining pipeline of IF-CAP-enabled projects and a finalised project pipeline for the remaining years of the Investment Period. This information will enable us to make a more accurate assessment in the next annual review: (a) whether the link between headroom unlocked by the guarantee is delivering on outcomes and impacts as envisaged in the Theory of Change; and (b) if IF-CAP is on track to deliver the level of outcomes and impacts envisaged in the business case.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme is achieving its intended objectives by delivering on lending and development outcomes as expected. Delivering through the ADB enables the UK to achieve development results that often could not be achieved bilaterally given (a) its wider geographical coverage, and (b) expertise in areas such as managing large scale, cross-country, infrastructure projects. Countries feel a high degree of ownership and trust in ADB.

IF-CAP represents good Value for Money (VfM) and is a highly cost-effective way for the UK to leverage additional MDB finance and mobilise private finance for countries’ climate and development needs (see Section D for further detail on VfM). IF-CAP enables ADB to increase its overall level of financing commitments as a result of transferring risk from ADB to the UK and other IF-CAP guarantors, and within that the level of climate finance it provides – unlocking an additional $10bn by end-2029. This is a key element in enabling ADB to reach its ambition to provide $100bn in climate finance from 2019 to 2030 and for climate finance to reach 50% of the total committed financing volume by 2030.

The programme should therefore continue, with FCDO and ADB taking onboard the lessons learned and recommendations from this annual review to ensure that the programme remains on track in terms of both delivery and reporting.

## C. DETAILED OUTPUT SCORING

Output Title	Climate finance mobilised for Asia and the Pacific by the UK guarantee.
Output number:		1	Output Score:	A
Impact weighting (%):		80	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 – New climate finance committed by ADB for mitigation as a result of the UK guarantee ($m)	IF-CAP operationalised and first IF-CAP-enabled projects approved	IF-CAP operationalised and first IF-CAP-enabled projects approved – $6m committed as a result
1.2 – New climate finance committed by ADB for adaptation as a result of the UK guarantee ($m)	IF-CAP operationalised and first IF-CAP-enabled projects approved	IF-CAP operationalised and first IF-CAP-enabled projects approved – no climate finance for adaptation committed yet

Briefly describe the output’s activities and provide supporting narrative for the score.

As of end-2024, IF-CAP has been operational for two months and so far enabled ADB to commit $41.2m of new climate finance for one climate mitigation project, though no climate adaptation projects have been approved yet. $6m of this climate finance is attributable to the UK as our guarantee made up 14% of the total value of IF-CAP guarantees as of end-2024. By the end of the Investment Period, we expect ADB to have committed $1.26bn of new climate finance as a result of our guarantee, based on the leverage ratio of $4.50 of unlocked lending for every $1 guaranteed (in line with the range of $4-5 for every $1 guaranteed as envisaged in the business case). The progress achieved at this early stage of implementation provides initial evidence that IF-CAP is working as envisaged, creating additional lending capacity for ADB to deploy as new climate finance (see Box 1 for the climate and development impacts expected from the first IF-CAP-enabled project).

Overall, we consider it appropriate to assess this output as having met expectations and therefore score this output an ‘A’. This is on the basis that (a) the guarantee had already enabled new lending to be committed within two months of becoming effective, and (b) ADB have since set out a pipeline of IF-CAP-enabled projects to be committed in the year ahead, indicating that ADB expect to develop new projects at the rate required to meet the indicator targets by the end of the Investment Period. Confidence therefore remains unchanged in ADB’s capacity to deliver the expected amount of new climate finance as a result of the UK guarantee.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

None, there have not been changes in the output indicators in this first review period and no planned changes as a result of this review.

Progress on recommendations from the previous Annual Review (if completed), lessons learned this year and recommendations for the year ahead

At the next review period, FCDO and ADB will review the milestones for the remaining years of the Investment Period. Specifically, we will test the robustness of the assumption that results will be achieved at a similar rate in future years, i.e. new climate finance commitments made by ADB will increase at a linear rate during the Investment Period. Where necessary, we will update the milestones to reflect a more ambitious or realistic profile.

Awareness within FCDO, ADB, and borrower countries of the financing and development opportunities created by IF-CAP will be critical to achieve the impacts envisaged in the business case. In the year ahead, FCDO will therefore work with ADB to identify opportunities to increase technical understanding and awareness within FCDO and ADB of how IF-CAP can unlock new climate finance (see recommendation 3 in Section A), and how we can engage with borrower countries to make best use of these opportunities (recommendation 1). FCDO will also look to increase the awareness of IF-CAP amongst other MDBs and potential guarantors, sharing knowledge on how this instrument can deliver additional and affordable climate finance for developing countries (recommendation 2). The objectives of these recommendations are to ensure that (a) there is sufficient borrower demand for ADB to develop a sufficient pipeline of projects and deliver on expected outcomes, and (b) encourage take-up and replication of IF-CAP.

Output Title	ADB exposure to sovereign default risk is reduced by the IF-CAP guarantees.
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 – Amount of ADB provision for credit loss reduced as a result of IF-CAP ($m)	IF-CAP operationalised and first IF-CAP-enabled projects approved	IF-CAP operationalised and first IF-CAP-enabled projects approved – $0.9m provision reduced as a result
2.2 – Average in-year risk-adjusted exposure (AIRE) on FCDO’s balance sheet as a result of the UK guarantee (£m)	£6m	£6m

Briefly describe the output’s activities and provide supporting narrative for the score.

Output indicator 2.1 captures the reduced amount of risk capital that ADB has to provision to cover potential sovereign defaults in the IF-CAP reference portfolio, enabling ADB to redeploy its resources and expand lending operations as a result of IF-CAP (see paragraph 2 for how IF-CAP transfers risk). As of end-2024, IF-CAP has been operational for two months and so far reduced the amount of risk capital ADB needs by $0.9m, enabling it to commit $41.2m of new lending as described above. By the end of the Investment Period, we expect the amount of provisions reduced by IF-CAP to reach $224m – enabling ADB to hit the target of committing $10.26bn in new IF-CAP-enabled lending.

Output indicator 2.2 captures the amount of risk that the UK is taking on as a result of providing this guarantee to ADB, enabling it to reduce the amount of risk capital it needs to provision and redeploy this to expand lending operations. This risk to the UK is measured in terms of average in-year risk-adjusted exposure (AIRE), representing the annual expected payout for a guarantee over the next 20 years. AIRE is estimated through FCDO’s Contingent Liabilities Model based on several variables: the credit rating of countries covered by IF-CAP as assessed by Moody’s, the amount of exposure to each country, the GBP/USD exchange rate, and interest rate. FCDO uses this metric to monitor the risk of defaults and payouts across the guarantee portfolio.

As of end-2024, the estimated AIRE of IF-CAP was £6m. This is the same level of AIRE estimated in the business case, indicating that the level of risk currently taken on by the UK is as originally expected. Milestones for this indicator are set at £6m for every review period, as achieving these milestones would indicate that the risk taken on by the UK remains in line with the level envisaged in the business case (see Section D on the implications for the Value for Money of our guarantee). Although the reference portfolio has changed since BC approval following final negotiations with ADB and the other guarantors, AIRE has remained at £6m as of end-2024. This reflects that the level of risk taken on by the UK now that IF-CAP is operational has remained as envisaged. We expect this level of risk to remain close to £6m throughout the Investment Period, which would indicate that the UK is not exposed to significantly higher risk than allowed by our risk appetite.

Overall, we consider it appropriate to assess this output as having met expectations and therefore score this output an ‘A’. This is on the basis that, as envisaged in the BC, (a) IF-CAP has started to enable ADB to redeploy its provisions and increase new lending within two months of becoming effective, and the level of risk transferred to the UK as a result of our guarantee is in line with the level envisaged in the business case.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

None, there have not been changes in the output indicators in this first review period and no planned changes as a result of this review.

Progress on recommendations from the previous Annual Review (if completed), lessons learned this year and recommendations for the year ahead

At the next review period, FCDO and ADB will review the output indicator 2.1 milestones for the remaining years of the Investment Period. Specifically, we will test the robustness of the assumption that results will be achieved at a similar rate in future years, i.e. the need for provisions will be reduced (as a result of total IF-CAP guarantee exposure increasing) at a linear rate during the Investment Period. Where necessary, we will update the milestones to reflect a more ambitious or realistic profile.

## D: VALUE FOR MONEY

Key cost drivers and performance

The value for money (VfM) of an MDB guarantee is a function of (a) the cost (i.e. risk of payout) to the FCDO from providing the guarantee, and (b) the development impact of the guarantee. In turn, the development impact is a function of (a) the volume of additional MDB finance unlocked (i.e. the leverage), and (b) how that unlocked finance is used. The assessment below of IF-CAP’s VfM below shows that it is performing strongly and in line with expectations, unlocking a high volume of climate finance to deliver climate and development impacts at low risk to the UK.

Guarantees do not create an upfront cost to the FCDO but instead carry a risk of potential future costs in the event that a guarantee is called. For IF-CAP, this potential cost is driven by the likelihood that the guarantee is called as a result of a borrower country in the IF-CAP reference portfolio defaulting on an ADB loan. The likelihood of this cost materialising (i.e. the risk of sovereign default) is monitored through FCDO’s Contingent Liability Risk Management Framework. This risk has not materially changed during the review period and remains very low, in line with the level estimated in the business case. As of end-2024, the annual expected cost of IF-CAP over the next 20 years is estimated to be £6m.

By taking on our share of the risk of sovereign default in the reference portfolio of ADB lending, the FCDO is able to unlock $1.26bn in additional ADB climate finance. Together with the $2bn in guarantees provided by the other IF-CAP guarantors, this takes the total finance unlocked to $10.26bn – i.e. leveraging $4.50 of additional lending for every $1 of guarantee. This amount of lending headroom is then used to extend lending from ADB (and mobilise private finance) to countries in Asia and the Pacific for climate change mitigation and adaptation projects that would not have otherwise been available. This final step in driving the VfM of the IF-CAP guarantee depends on the ability of ADB to approve and disburse unlocked lending in order to deliver climate and development impacts.

VfM performance compared to the original VfM proposition in the business case

The IF-CAP guarantee is judged to be economical because it increases ADB lending and mobilises private finance at low cost to the FCDO. IF-CAP involves no upfront cost to the UK and is unlikely to involve any future cost to the UK, except in the unlikely event that a borrower country in the IF-CAP reference portfolio defaults on an ADB loan.

The efficiency of IF-CAP is determined by how much additional ADB lending capacity is unlocked. As of end-2024, ADB has been able to use the provisions freed up by IF-CAP so far to deliver $41.2m of new lending for climate mitigation (of which $6m is attributable to the UK), creating $1.3m of risk on the UK’s balance sheet (see paragraph 36 on financial risk). The leverage ratio of $4.50 of unlocked lending for every $1 guaranteed is in line with the range envisaged in the business case ($4-5 for every $1 guaranteed).

The effectiveness of IF-CAP depends on the extent to which the additional ADB lending capacity unlocked by our guarantee leads to new climate-focused lending with climate and development impacts. As shown in Box 1, ADB has already been able to approve the first IF-CAP-enabled project within two months of IF-CAP becoming operational. The expected climate mitigation, development and gender-related impacts reported by ADB in relation to this project show that our guarantee will generate the impacts envisaged in the business case.

The design of IF-CAP means that our exposure to the IF-CAP reference portfolio will only increase (up to the total value of our guarantee, i.e. $280m) when new lending is committed by ADB. This ensures that our guarantee will be cost-effective, as the UK only takes on costs (i.e. risk of payout) when ADB delivers the benefits of new climate projects using the lending unlocked by IF-CAP. By the end of the five-year Investment Period, we expect ADB to have committed $10.26bn of additional lending to deliver climate and development impacts. This target is in line with the range envisaged in the BC (up to $11bn).

The equity impact of IF-CAP is determined by ADB’s policies to achieve equity both within ADB (e.g. gender balance in management positions) and in ADB’s lending. ADB’s reporting of the number of skilled jobs created for women as a result of IF-CAP-enabled projects indicates that ADB actively monitors this aspect of their lending. ADB have also committed to considering projects that contribute towards priorities including gender equality and poverty reduction, and support to vulnerable countries.

Assessment of whether the programme continues to represent value for money

The evidence above indicates that the IF-CAP guarantee represents strong VfM, as it is efficiently and effectively delivering positive development and climate impacts, in line with FCDO priorities, at no upfront cost and low risk of future costs as set out in the business case. The IF-CAP guarantee programme should therefore continue, with FCDO and ADB taking onboard the lessons learned and recommendations from this annual review to ensure it remains on track.

E: RISK

Overview of risk management

The overall risk to the success of the IF-CAP guarantee was rated as ‘moderate’ at the time of the business case. This has not materially changed since the start of the programme as the financial risk of the guarantee remains very low and programme delivery risks are unchanged. As such, we see no need to amend our risk appetite or residual risk exposure rating.

The financial risk of the IF-CAP guarantee being called and creating a cost for FCDO is driven by the risk of a borrower country covered by IF-CAP defaulting on an ADB loan. IF-CAP covers ADB loans to 29 countries in Asia and the Pacific (see Annex 1). One measure of the risk of any of these countries defaulting is its credit rating, which covers a wide range from Caa3 to Baa1 (as assessed by Moody’s). However, the level of this risk is reduced by ADB’s Preferred Creditor Status, which means countries very rarely default to MDBs and almost always repay MDBs before other creditors.

The maximum amount that the UK could be required to pay out increases proportionately as ADB commits new IF-CAP-enabled lending, from $0 when IF-CAP first became operational (i.e. when ADB had yet to commit any new IF-CAP-enabled lending) up to $280m (i.e. the total amount we agreed to guarantee) once ADB has fully committed all IF-CAP-enabled lending. As of end-2024, ADB had committed $41.2m of new IF-CAP-enabled lending through the project in Pakistan, meaning the maximum amount that the UK could be required to pay out in the event of a default in the reference portfolio is $1.3m. The magnitude (as well as likelihood) of this financial risk is therefore very low at this moment in time, though we expect it to increase as ADB develops further IF-CAP-enabled projects over time.

Average in-year risk-adjusted exposure (AIRE) is a key metric of this risk used by FCDO to manage risk across the guarantee portfolio, representing the annual expected payout for a guarantee over the next 20 years. The AIRE for IF-CAP estimated at the time of the BC was £6m, based on the reference portfolio of sovereign exposure at the time. Although the reference portfolio has changed since then in the course of final negotiations with ADB and the other guarantors, AIRE has remained at £6m as of end-2024. This reflects that the level of risk taken on by FCDO as IF-CAP enters the implementation stage remains as envisaged in the business case.

IF-CAP follows wider ADB risk management systems and processes:

  1. ADB has a risk framework built on three pillars: governance, policies, and processes. ADB’s risk management is led by the Office of Risk Management (ORM) and the management committees, e.g. Audit and Risk Committee, that have oversight of ADB-wide risk issues. All ADB payments are processed by the Controller’s department and made by the Treasury Department. All project payment approval and fund transfer functions are centralised within ADB’s Manila HQ as this allows for high level oversight and ensures that strong internal control functions are in place. As part of its fiduciary review role and processing of payments, the Controller’s Department is also responsible for ADB’s financial control to ensure that disbursements are in accordance with the Loan Disbursement Handbook.

  1. ADB’s Office of Anticorruption and Integrity (OAI) is the designated focal point of contact for allegations of fraud or corruption. OAI’s mandate is underpinned by ADB’s zero tolerance for fraud and corruption. OAI provides advice on integrity and tax-related due diligence, and advances awareness of ADB’s anticorruption policy. OAI reports directly to the President and periodically meets with the Audit and Risk Committee of the Board of Directors to discuss the significant activities of the office, including cases where findings indicate systemic control weaknesses, or where the findings are of such character that could constitute a reputational risk for ADB. IF-CAP activities are monitored by the OAI and the UK will use its position at the Board to monitor any concerns raised by the OAI.

The Board of Directors, on which the UK currently has an Alternate Executive Director, plays an oversight role. We use the ADB Board to voice concerns about human rights, alleged discrimination, social and economic inclusion and environmental concerns as part of the broader social and environmental safeguards for programmes and projects over the full project cycle.

FCDO will continue to monitor the performance of ADB loans through financial reports submitted by ADB to its Executive Board, as well as internally monitoring indicators of sovereign default through the FCDO Risk Management Framework, Default Risk Assessments, and additional internal sources on the economic outlook of countries covered by IF-CAP. FCDO aims to continue its engagement with ADB on a regular basis to understand the potential risks associated with IF-CAP enabled projects and borrower demand.

In terms of financial and fiduciary risks, ADB has appropriate policies and procedures to reduce or limit exposure to risks anticipated in the normal course of providing development banking services. Fiduciary risks of borrowers are assessed by OAI and Procurement, Portfolio, and Financial Management Departments during project design and prior to disbursement. Throughout the 2024 review period, ADB has maintained its AAA credit rating by the major Credit Rating Agencies. ADB has sound financial management processes in place, including strong risk management culture and prudent risk appetite. An ADB Risk Management Report is shared on a quarterly basis with the Board of Directors.

In terms of safeguarding risks, ADB approved a new Environmental and Social Framework in November 2024, replacing its 2009 Safeguard Policy Statement. This will come into effect from January 2026. A review of the compliance functions is also underway. We input our expertise on Sexual Exploitation and Abuse and Harassment (SEAH) through Board discussions on the new Policy Statement. The UK was also co-signatory of a letter to MDBs on SEAH. SEAH represents an overall top UK safeguarding priority, with a UK SEAH 2020 Safeguarding Strategy that outlines our approach and principles, as well as a dedicated FCDO team to lead on SEAH safeguarding across UK programs and at international organisations.

In terms of strategy and context risks, the impact of the UK’s guarantee enabling greater climate change mitigation and disaster resilience depends on IF-CAP’s wider ability to unlock additional climate finance at the outcome level. A risk therefore exists that IF-CAP successfully unlocks lending capacity as envisaged at the output level, but the IF-CAP enabled projects then do not deliver the climate finance and subsequent climate mitigation and adaptation results expected. FCDO will monitor this risk during the Investment Period to ensure that our guarantee and IF-CAP as a whole increases ADB’s climate finance lending through projects that deliver the climate outcomes and impacts envisaged in the business case.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

ADB demonstrates a strong commitment to transparency through the regular publication of an annual Development Effectiveness report and an audited financial statement. In the DFI Transparency Index 2025, ADB ranked first for non-sovereign DFIs and second for sovereign DFIs. This high ranking reflects ADB's high-quality aid data and openness in sharing results. Such transparency enhances accountability and positions ADB as a results-focused and efficient institution.

Through the Central Assurance Assessment (CAA), FCDO assesses the capacity and capability of its delivery partners from a “due diligence” perspective, across 4 pillars: governance and control, ability to deliver, financial stability, and downstream partners. The conclusion of the most recent CAA conducted in 2022 found that, overall, the risk associated with the ADB is considered to be moderate. ADB has established a strong framework to prevent aid diversion and manage conflicts of interest. Its Anticorruption and Integrity Policies also set out the strategic and operational measures underpinning these safeguards and can be found here.

ADB's Board of Directors, which includes representatives from the UK, regularly reviews ADB's financials and provides oversight during Board meetings. UK representatives, along with country and regional teams, have reported a positive working relationship with our delegate and ADB staff, which has been beneficial in achieving our goals. Representatives from ADB developing member countries have also approached ADB Senior Management to explore opportunities for closer collaboration with FCDO in the future.

Following the negotiations and implementation of IF-CAP, the FCDO programme team has identified lessons learned and recommendations (summarised in Section A) that will improve our effectiveness in delivering and risk management. We will identify opportunities to increase the technical understanding and awareness of opportunities for new IF-CAP-enabled projects in FCDO, and share our experiences with stakeholders across the MDB system. This will enable us to (a) better support the delivery of new projects through our engagement with borrower countries, (b) understand from our engagement if IF-CAP is performing as envisaged in the business case and (c) help to realise the demonstration effect for other MDBs and potential guarantors.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

During the review period, monitoring efforts primarily relied on the IF-CAP Annual Report submitted by ADB to FCDO and the other IF-CAP guarantors. This report detailed the application of IF-CAP lending headroom for climate-focused projects and the consolidated credit ratings of countries covered by IF-CAP. Supplementary insights into ADB’s risk management practices and forward-looking assessments were drawn from ADB’s risk reporting which is updated quarterly. Additional key references included:

1. 2024 Annual Development Effectiveness Review;
2. 2023 Annual Portfolio Performance Report; and
3. Internal ADB data.

The FCDO programme team have closely engaged with ADB’s IF-CAP team to inform our monitoring and wider programme management. This includes both regular reporting on a pre-agreed basis and ad hoc updates where needed. ADB has committed to hosting regular in-person meetings with all IF-CAP guarantors and relevant stakeholders on an annual basis.

Evidence

As this is the first annual review, subsequent annual reviews will review any changes in the quality and timeliness of ADB’s engagement and reporting.

Learning

Over the next year, FCDO will continue to reflect on and advance its learning objectives in collaboration with the ADB and other guarantors. Key areas of focus are below and summarised in Section A:

1. How to share knowledge and lessons learned with borrower countries, ADB shareholders and other MDBs to increase the awareness and understanding of IF-CAP across the MDB system.
2. How to use internal communication channels within FCDO and ADB to improve both technical understanding of IF-CAP’s financing mechanism and awareness of the opportunities to deliver new IF-CAP enabled climate projects.

Date of last narrative financial report	25/04/2025	Date of last audited annual statement	19/02/2025
[note] ADB 2024 Financial Report
[note] Statement of the Asian Development Bank's Operations in 2024

Annex 1: List of countries covered by IF-CAP as of end-2024

Country	Share of IF-CAP (%)	Moody’s credit rating
Armenia	0.21	Ba3
Azerbaijan	3.74	Ba1
Bangladesh	9.25	B2
Bhutan	1.01
Cambodia	4.75	B2
Cook Islands	0.27
Fiji	0.78	B1
Georgia	4.78	Ba2
India	8.33	Baa3
Indonesia	8.33	Baa2
Kazakhstan	3.40	Baa1
Kyrgyz Republic	1.96	B3
Lao People’s Democratic Republic	2.18	Caa3
Maldives	0.11	Caa2
Mongolia	4.15	B2
Nepal	6.24	N/A
Pakistan	7.50	Caa2
Palau	0.31	N/A
Philippines	5.42	Baa2
Papua New Guinea	8.33	B2
Samoa	0.01	N/A
Solomon Islands	0.16	Caa1
Thailand	0.53	Baa1
Timor-Leste	0.53	N/A
Turkmenistan	0.97	N/A
Tonga	0.01	N/A
Uzbekistan	8.33	Ba3
Vanuatu	0.11	N/A
Viet Nam	8.33	Ba2

Note: Figures as derived by FCDO.