## Annual Review Template

Title: Tanzania Health Resilience Programme
Programme Value £ (full life): 15,000,000		Review date: / August 2025
Programme Code : 400084	AMP start date: 13/8/2024	AMP end date: / 31/3/2029

Summary of Programme Performance
Year	2024/25
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005963.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007467.xlsx

Acronyms
AG / AIDS / ANC	Accountable Grant / Acquired Immunodeficient Syndrome / Antenatal Clinic
AGYW / ARVs / AMR / BHC	Adolescent Girls and Young Women / Antiretrovirals / Antimicrobial Resistance / British High Commission
CEBS	Community and Event Based Surveillance
CDC / DI	Centres for Disease Control / Direct Implementation
eLMIS	Electronic Logistics Management Information System
EPD	Ending Preventable Deaths
FP / GBV / GoTHOMIS	Family Planning / Gender Based Violence / Government of Tanzania’s Health Management Information System
GOT	Government of Tanzania
HBF	Health Basket Fund
HMIS	Health Management Information Systems
HIV / HRH / IMAF-H	Human Immunodeficiency Virus / Human Resources for Health / Improving Market Access and Financing for Health
IHR / MVD / MSD	International Health Regulations / Marburg Viral Disease / Medical Stores Department
mCPR	Modern Contraceptive Prevalence Rate
MOH	Ministry of Health
MOU	Memorandum of Understanding
NGO / NHS / NIMR	Non-governmental Organisation / National Health Service / National Institute for Medical Research
OPD	Outpatient Department
PHEOC	Public Health Emergency Operations Centers
PwDs	People with Disabilities
PHC	Primary Healthcare
PrOF	Programme Operating Framework
PORALG	President Office – Regional Administration and Local Government
RBF	Results Based Financing
R4D	Results for Development
RMNCAH	Reproductive, Maternal, Neonatal, Child and Adolescent Health
SRHR / SEAH / SWAp / TDDAP 2	Sexual and Reproductive Health and Rights / Sexual Exploitation, Abuse and Sexual Harassment / Sector Wide Approach / Tackling Deadly Diseases in Africa Programme 2
TB	Tuberculosis
TMA / ToC	Total Market Approach / Theory of Change
UHC / UHI / USG	Universal Health Coverage / Universal Health Insurance / United States of America Government
USAID / VAC / VFM	United States Agency for International Development / Violence Against Children / Value for Money
WHO	World Health Organization

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Tanzania Health Resilience programme (THRP) aims to support build a more resilient and sustainable health system, that effectively reduces preventable deaths and tackles major disease outbreaks and makes progress towards Universal Health Coverage (UHC) by 2030 by:
- Contributing to increase access, quality and equity of life-saving primary health care services by strengthening health systems that support the ending preventable deaths of mothers, newborns, and children (EPD).
- Support to improve Tanzania’s capacity to prevent, detect and respond to health threats by supporting integrated disease surveillance and a stronger initial response to outbreaks.
- Facilitate the use of data to inform decision towards more equitable health outcomes.
THRP takes a portfolio approach, combining three components, each amplifying the impact of the other. The first component is delivered via the Health Basket Fund (HBF) – a government owned pooled funding mechanism that supports system strengthening at primary healthcare facilities. The second component is technical assistance on Health Security that is delivered via an MoU with WHO Tanzania office. The Third component is delivered via an accountable grant with Results for Development (R4D), it focuses on leveraging Market Shaping and Health Financing approaches with the end goal of increasing equitable access to products and services to women and girls.

The Health Basket Fund (HBF) has been operational since 1999, and our engagement started in September 2024 after signing the addendum to HBF MoU 2021-2026 and the HBF Side Agreement for FY 2024/25 along with other eight (8) development partners. The remaining two components have been mainly at mobilization phase of the programme. Therefore, this review will focus mainly on programme mobilization for the two components, plus some aspects of implementation for the HBF. These aspects have been captured in the Year 1 log Frame that captures progress during mobilization and some specific implementation milestones.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme is assessed as an A for the first year of implementation. The assessment reflects good progress made during the review period, with all milestones but one met or exceeded expectation, and one partially met. Highlights during the review period included:

- Signing of the Memorandum of Understanding (MoU) with the Government of Tanzania and the Health Basket Fund (HBF) Side Agreement for FY 2024/25 along with other development partners. This paved the way for UK’s active engagement in the HBF mechanism.
  [note] Other HBF partners includes Korea, Ireland, Canada, Denmark, Switzerland, World Bank, UNICEF and UNFPA.
- Signed a Memorandum of Understanding with World Health Organization (WHO) to deliver on the global health security objectives, agreed work plans and results framework for the work.

Signed an accountable grant with Result for Development (R4D) for technical assistance to strengthen the systems with specific focus on Market Shaping of Life saving items including family planning, public financial management system and Universal Health Insurance policy implementation.

Successful mobilised domestic financing for Family Planning commodities to reduce the financing gap following the withdraw of USAID support. Through UK’s influencing, for the first time the HBF donors and Government of Tanzania have agreed to allocate 4.5% of HBF funds (equivalent to $2.5m) for procurement of Family Planning commodities conditional on contribution of an additional $2.8m or more by the MoH from domestic resource. Whilst this funding will not cover the entire funding requirement it is important step in the right direction given the overall reduction in aid.

- Inclusion of the monitoring framework for implementation of health sector priorities as set in the annual Side Agreement for HBF; this is to improve tracking of implementation and accountability.
- Positive progress on provision of reproductive, maternal, newborn, and child health services, including:
  - Increased availability of 290 life-saving commodities from 59%the previous year to 76%
  - Equipping of 121 newly established neonatal care units.
  - High rates of antenatal care attendance – 84% as previous year.
  - High rates of institutional deliveries –from 85.5% the previous year to 86.2%

Overall, the programme has made a good start with completion of mobilisation stage by key partners and started to deliver on some key areas including the Health Basket Fund, Improved Health security and Market shaping for life saving commodities. Also, during the reporting period, the government initiated the implementation of Universal Health Insurance (UHI) policy, and the Minister of Health requested Technical Assistance from the UK, focusing on experience and lessons from National Health Insurance (NHS England). UK’s contribution both technical and financial to the health sector reforms and priorities was well received and valued by both other development partners and government.

Major lessons and recommendations for the year ahead [1/2 page]

Major Lessons

- Sustained investment in surveillance, community engagement and health system resilience are key to effective epidemic management. As seen in Marburg Viral Disease Outbreak (Jan-March 2025) in Biharamulo, delayed identification of cases led to 100% case fatality rate.
- USG funding cuts was a shock to the entire health system, and exposed Tanzania’s vulnerability putting over 1.4 million people on antiretrovirals (ARV’s) at risk. However, the cuts remain an important window of opportunity on long-term sustainability and domestic resource mobilization. The government acted quickly by providing $64 Million to cover gaps, while some health facilities used user fees to recruit additional staff to help deliver services. UK has used this opportunity to prioritise Technical Assistance to the Ministry of Health on integration of services delivery for HIV/AIDS, TB programs into routine services as important pillar of sustainability.
- Transition to UHI Brings Opportunities and Risks: The enactment of the Universal Health Insurance (UHI) Act in 2023 presents a transformative opportunity for financial protection. However, the shift toward insurance-based reimbursement must be carefully managed to preserve public funding for preventive, promotive, and equity-sensitive PHC services.
- Rigid Expenditure Rules in the HBF: Fixed spending ratios (e.g., 35% earmark for medicines) may no longer reflect local needs, especially where government supply chains have improved. This limits facility-level flexibility and actions according to real needs.
- Leveraging UK expertise from NHS Systems Connect Programme made the programme deliver over and above the planned support. NHS England provides Technical Assistance in form of learning exchanges to Tanzania (Ministry of Health and National Health Insurance Fund) to inform Universal Health Insurance (UHI) policy implementation. This support complements the one provided by the THRP via Results for Development (R4D).
Recommendations

In response to significant delays in implementation of UHI policy and uncoordinated approaches to technical support on UHI roadmap implementation, it will be important to prioritize coordination of partners support and updating the roadmap to reflect evolving context. Political pressures (October 2025 elections), and USG Funding cuts were key to process stalling. BHC to engage other development partners and the new MoH leadership to pursue this agenda in a coordinated way.
For health security work, THRP will focus on One Health surveillance systems, working in collaboration with US CDC to strengthen the Technical Working Group (community of practice) for one Health in Tanzania in order to have an early warning system and seamless information sharing between the sectors (animal, agriculture, human health, environment, fishing etc).

- The closure of FLEMING Fund – a UK programme on Antimicrobial Resistance stewardship (AMR) using One Health approach in Tanzania may reduce financing in some areas especially in the human and animal health, THRP will work with WHO and US CDC to understand the level of impact and explore options for minimising the gap.
- To reduce reporting burden to healthcare workers and to improve quality and use of data for decision making, THRP through our engagement in HBF will advocate for electronic systems interoperability (data exchange between two or more systems).
- THRP to pursue improvements in performance management of the Health Basket Fund mechanism; first on real time tracking of agreed health sector priorities and then on root cause analyses and subsequent evidence-based action plans for poor performing indicators.
- Following US funding cuts, THRP will review the Theory of Change to assess if the level of ambition is still relevant, and the overall impact of the funding cuts on programme outcomes.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The desired impact of THRP is that Tanzania’s health system is more resilient and sustainable, reducing preventable deaths and tackling major disease outbreaks, and making progress towards Universal Health Coverage by 2030. The overarching desired outcome of the programme is enhanced health system capabilities for Universal Health Coverage and Global Health Security. This includes three specific outcomes: (i) Improved access, quality and equity of life-saving reproductive, maternal, new-born, child and adolescent health services (ii) Strengthened and sustainable delivery of health services (iii) Improved prevention, detection and response to health threats and increased political commitment to comply with International Health Regulations.

The Theory of Change (ToC) is designed to take a portfolio approach for delivery and complement other partners to achieve impact. THRP combines Health system strengthening to support ending preventable deaths of mothers, newborns, and children (EPD), Technical Assistance to strengthen diseases surveillance and response, and data and evidence generation to inform health system reforms.

The ToC has been reviewed as part of the programme and assessed to remain relevant. However, following the withdraw of USAID funding, there has been a major reduction of resources in the sector, USAID was contributing close to 40% of the health sector budget. In the following year, we will review the programme ToC to assess whether this reduction will have an impact on realising the programme impact.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The TRHP intended impact is to achieve a sustainable and resilient health system to reduce preventable deaths and tackle major disease outbreaks and make progress towards Universal Health Coverage by 2030.

TRHP’s impact will be assessed by tracking future progress on:
- Universal Health Coverage (UHC) service coverage index (baseline of 43 in 2023, tracked every 2-3 years by WHO), and
- WHO’s International Health Regulations core capacities assessment for health security (baseline of 63% average in 2024)
Prioritised outcome indicators and baseline have been identified, although it is too early to assess if these are on or off track:
- Public health spending as share of general government spending (baseline of 8% in 2024)
- Examples of improvements to resource allocation and management to strengthen health outcomes following THRP engagement.
- Key elements of Universal Health Insurance policy implementation on track
- WHO’s International Health Regulations core capacities assessment for surveillance capacity (baseline of 80% in 2024).
The reduction of US funding is a major concern for the sector, whilst the government is committed to ensure that services are not disrupted, there is likely to be impact on provision of some services such as provision of family planning which was largely financed by external partners. Continued shortage of health care workers will further constrain delivery of services. We will continue to work with the government and other partners to explore creative ways to maximise the limited resources available

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

THRP is making sufficient progress towards expected outputs, given the early stage of the programme, and is still expected to deliver the identified outcomes and impacts. Its portfolio approach enables it to make contributions in important areas and is adapting to emerging needs and priorities including.
- Advancing health financing reforms, including the implementation of the Universal Health Insurance policy,
- Expanding access to quality and equitable health services at all levels,
- Strengthening reproductive, maternal, newborn, child and adolescent health services,
- Supporting service delivery integration for vertical programs and overall sustainability of HIV/AIDS, TB and Family Planning, especially at primary health care facilities.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Mobilisation of the Tanzania Health Resilience Programme
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Agreement of a Memorandum of Understanding (MoU) between Government of Tanzania and FCDO on programme delivery via a Multi-donor Health Basket Fund	Signing of the MoU between Ministry of Finance and FCDO, and The Basket Fund MoU with accompanied side Agreement with Ministry of Health, PORALG, Ministry of Finance and Health Basket Fund donors	Met / Basket Fund MoU and side agreements signed with Ministry of Health, PORALG, Ministry of Finance, and Health Basket Fund donors.
Successful accountable grant and mobilisation of a partner to deliver Data and Evidence use component of the Tanzania Health Resilience Programme	Accountable grant signed with R4D focusing on Market Shaping of life saving items, Public Financing of Health and Universal Health Insurance Implementation support.	Met / Accountable grant signed with R4D for delivery of the Data and Evidence Use component.
Agreement of a Memorandum of Understanding with WHO Tanzania to deliver health security component of the Tanzania Health Resilience Programme.	A Memorandum of Understanding agreed with WHO, and results framework and workplans finalised, to deliver improved health security through WHO	Met / MoU signed with WHO Tanzania for the Health Security component, with results framework and workplans finalized.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

During this review period, the programme has successfully completed all foundational activities required to initiate implementation. Three key agreements were finalized; MoU between the Government of Tanzania and FCDO for programme delivery through the Multi-donor Health Basket Fund, including side agreements with the Ministry of Health, PORALG, Ministry of Finance, and other Basket Fund donors. Accountable grant with R4D, mobilizing a partner to lead the Data and Evidence Use component, with a focus on market shaping of life-saving commodities, public financing of health, and support for universal health insurance implementation. MoU with WHO Tanzania, with accompanying results framework and workplans, to deliver the health security component of the programme.

At the same time, implementation of activities has started in some areas such as through the health basket fund and response to diseases outbreaks where the UK was able to provide both technical and financial support to manage Marburg and Mpox outbreaks between January and May 2025. These achievements reflect strong coordination among stakeholders and demonstrate early programme momentum. The timely completion of these foundational steps positions the programme well for effective delivery in subsequent phases.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes were made to this output during the year. In the following year this output will no longer be used as the focus will be on tracking programme implementation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

As this is the first year of implementation, there were no recommendations from a previous Annual Review. We experienced delays in signing an MoU with WHO which resulted into delayed start of implementation. Therefore, early lessons include the importance of proactive coordination with partners to avoid delays. For the year ahead, it is recommended to maintain strong communication channels and proactively track implementation progress against the agreed workplans to ensure timely delivery and using the action log to monitor progress against agreed actions to sustaining momentum and accountability.

Output Title	Stronger health system, including on availability of medicines, equity and access of primary health and strengthening of WASH systems and community health systems.
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR.	n/a

Indicator(s)	Milestone(s) for this review	Progress
Percentage of Health Basket Fund indicators that are meeting the agreed target, covering antenatal attendance and treatment, birth location, breastfeeding, modern contraceptive prevalence, hypertension, HIV awareness, GBV and VAC reporting and TB notification.	No deterioration in the number of indicators on track or below target but on a positive trajectory	Met / 8 indicators meeting target; 1 marginally below target, 4 significantly below target (modern contraceptives uptake, pregnant women with anaemia, TB notification rate, and GBV/VAC reporting). / Baseline performance had only 6 indicators meeting target.
Percentage of Primary Health Care facilities with continuous availability of 290 items (medicines, vaccines, medical devices).	No deterioration.	Met / 76% of All primary health facilities had continuous availability of 290 items, this is an increase from the baseline of 59%.
Examples of capacity or system improvements within the health sector following Health Basket Fund engagement	At least one significant example of capacity/system improvements.	Exceeded. / HBF allocated 4.5% ($2.5m) of funding to FP commodities, leveraging $2.8million of domestic financing annually. / Equipping of the 121 newly established neonatal intensive care units in primary health facilities, key to addressing neonatal deaths in country.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

There has been an incremental improvement to the output targets. Performance assessment against the service delivery indicators shows stronger scores with 8 indicators meeting targets compared to 6 indicators in the previous year. Indicators meeting target include;
- Percentage of ANC attendees receiving at least 2 doses of Intermittent Presumptive Treatment (IPT2) for Malaria during last pregnancy (90%),
- Percent of ANC attendees receiving adequate quantity of Iron and Folate tablets until the next ANC visit (97.1%),
- Percentage of Institutional Deliveries (86.2%),
- Percentage of children-initiated breast feeding within one hour of birth (93.3%),
- Percentage of pregnant women attending first ANC visit in the first trimester (45.6%)
- Percentage of newborns who received postpartum care within two days of birth (93.8%),
- Percentage of people living with HIV are aware of their status (94.2%),
- Percentage of Hypertension among OPD at PHC health facilities (3.7%)

This achievement is the result of concerted effort by the government to improve services especially in primary health care, marked by expansion of infrastructure and launching of an improved community health care workers scheme. However, despite progress, teenage pregnancies continue to be a major problem which can potentially increase maternal deaths and affect early childhood development, and reduced US funding is likely to have further impact in the coming years especially in maternal and reproductive health and FP if there will be no concerted effort to address the financial and technical gap.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There is no change for this output. This is the first annual review for the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This is the first year of the programme, and this is the first annual review. We have noted that some indicators have performed poorly for years with insufficient mitigating interventions in place. These include; low uptake of modern contraceptives, pregnant women with anaemia and low reporting of cases of Gender Based Violence/ Violence Against Children within 72 hours after the incident. THRP will work with HBF partners and the government to undertake joint analysis of the problems, improve performance monitoring and recommend appropriate interventions to improve performance.

Output Title	Greater use of evidence to innovate and reform health investments and delivery
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR.	n/a

Indicator(s)	Milestone(s) for this review	Progress
Percent change in the Reproductive, Maternal, Neonatal, Child and Adolescent Health (RMNCAH) resource budget execution rate for Improving Market Access and Financing for Health (IMAF-H) targeted councils and facilities that received PlanRep capacity strengthening.	Evidence of effective initial work in Public Financial Management (PFM) strengthening in selected councils and facilities.	Met / IMAF-H started a baseline PFM assessment in selected councils. A study to analyse facility and council plans and budget implementation and collect baseline data to track budget execution rates over time is in final stages for approval by National Institute for Medical Research(NIMR)
Number of assessments, diagnostics, or analyses completed with IMAF-H support	Evidence of effective initial work on data and evidence generation to support Universal Health Insurance policy implementation.	Met / Provided TA to a costing study led by Ifakara Health Institute for costing the National Essential Care Health Package, / Other work such as evidence generation for inclusion of FP products in UHI package, is in initial stages.
Measured improvement in GoT capacity to carry out market management actions and functions to improve availability and access of prioritized RMNCAH products and services	Evidence of effective initial work in Market Shaping of life saving commodities	Met / Finalized list of IMAF-H priority products and started learning exchange with Government of Tanzania on Market Management function that will institutionalize Market Shaping within government structures.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output assesses progress performance of on use of data and evidence to drive reforms in the system with particular focus on financial management, commodities market especially for RMNCAH products including family planning, safe motherhood and child health. All indicators met expectation for the first year of implementation, R4D engaged the Ministry of Health, President’s Office Local Authority and Regional Administration (PORALG) and Medical Stores Department (MSD) to re-confirm, prioritise the in-depth diagnoses planned. At the time of this annual review, diagnoses on Public Financial Management and on Universal Health Insurance basic package of care have been initiated and work on Market Shaping has commenced, all these pave the way for further technical support. Responses from the government and departments have been extremely positive and their demand for expert support far exceeds the funding available for this TA. On public financial management asks we are exploring potential for some of the areas of work to be implemented under the public financial management programme.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes to this output. This is the first year of programme implementation and there are no planned changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

During this reporting period, the government initiated the implementation of Universal Health Insurance policy and had expressed the need for technical assistance to a number of different partners including the UK. It has been helpful to connect work under this component with technical support provided through the NHS Health System Connect programme (FCDO programme funded centrally) and support from other partners such as GIZ, Swiss and the World Bank to ensure that there is no duplication of efforts and that our combined efforts provide comprehensive support to the government

The withdraw of USAID financing has created a significant financing gap in the sector however, it has provided an opportunity for government to think through how it can maximise on existing resources including options for integrating vertical programmes to improve efficiency and effectiveness of service delivery.

Output Title	Improved capacity and systems to prevent, detect and respond to disease outbreaks (early warning system, integrated disease surveillance, capacity of Health Care works, legal framework advocacy.
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of Public Health Emergency Operations Centers (PHEOC) with fully functional One Health surveillance and emergence management dashboards	Initial engagement of National PHEOC for development one health dashboard (gather user requirements) is done.	Partially Met / Initial technical consultation with MOH National PHEOC on how to implement this activity building on existing efforts by MOH and Partners is done, the user requirements gathering will be done in October 2025- March 2026 period.
Number of experts capacitated on public health information management, outbreaks readiness and crisis communication tools, and synchronized community feedback mechanisms.	Additional 30 experts trained on public health information management, outbreak readiness and crisis communication tools, and synchronized community feedback mechanism	Exceeded / 50 experts trained, making a total of 170 experts ( from a baseline of 120 experts)
Number of districts where Community and Event Based Surveillance (CEBS) is fully operational.	Preparation training in additional 5 districts completed	Met / In collaboration with MoH Epidemiology Unit, key preparations for training including updating 2019 Event Based Surveillance guidelines and other training materials are completed and agreed to by both National and subnational teams.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output assess progress on improving health system capacity to prevent, detect and respond to diseases outbreaks. It builds on an existing work by WHO and US CDC but extending support to increase coverage of integrated diseases surveillance, event-based surveillance and strengthening the public health emergency centre. One indicator exceeded expectations, one indicator met expectations, and one indicator has partially met the expectation for this annual review. The indicator that was partially met depends more on the government side which has been busy battling multiple outbreaks including Marburg, Cholera, Vaccine acquired polio and ongoing Mpox outbreak.

There has been a positive response from the government counterparts including from the leadership of the ministry on UK’s support on emergency response.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is the first annual review, there are no changes to the output and there are no planned changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

- The Marburg outbreak in Biharamulo Kagera revealed major weakness in surveillance as it took nearly one month to identify cases, leading to 100% case mortality. For the year ahead, our focus is to ensure functionality of integrated diseases surveillance and event-based surveillance being implemented by the programme.
- Diseases outbreaks are being treated as both political and national security issues hence limiting the responses especially on community engagement and risk communication, hence risking further spread and mortality. This undermines the International Health Regulations on handling diseases outbreaks. BHC will continue to work with like-minded partners and the UK’s the regional programme – Tackling Deadly Diseases in Africa (TDDAP2) which supports WHO AFRO and Africa CDC in order to handle this challenge politically at that level.
- The closure of Fleming Fund support which was supporting one health in Tanzania may reduce financing in some areas especially in the animal health, BHC will work with WHO and US CDC to understand the level of impact and explore options for minimising the gap.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

As the programme is still in its early implementation phase, this review of Value for Money (VfM) focuses on the strategies and systems being put in place by partners to ensure VfM, rather than on measurable outcomes. An in-depth VfM assessment will be conducted in future reviews once implementation is more advanced and sufficient data is available.

During the mobilization and initial implementation period, several measures have been taken to embed VfM principles across programme activities:
- Standardized Financial Practices. The adoption of harmonized Daily Subsistence Allowance (DSA) rates across partners and the use of mobile wallet payments for field activities have reduced administrative overheads, minimized fraud risks, and improved the traceability of disbursements. These measures promote both economy and transparency.
- Direct Implementation (DI) Across All Partners. All three implementing partners-R4D, WHO, and the Ministry of Health; are operating under a Direct Implementation (DI) model, with no downstream partners. DI means that funds are managed and disbursed directly by the implementing entities, allowing for streamlined planning, budgeting, and execution. This approach reduces intermediary costs (economy) and enables faster decision-making and more timely disbursement of resources to service delivery points (efficiency). For example, through the Health Basket Fund, DI enables direct transfers to primary health care facilities, ensuring that funds reach health facilities with fewer delays and less overhead.
- Strategic Procurement Planning: Procurement of key inputs -such as servers, desktop computers, and laboratory reagents, has followed the best VfM practices. Technical and procurement teams jointly develop specifications and cost estimates, ensuring competitive pricing and quality assurance. For the programme, this results in lower unit costs, reduced risk of procurement delays, and greater assurance of fit-for-purpose goods, all of which contribute to the economy and timely implementation.
- Partner VfM Strategies and Equity Focus. Implementing partners are refining their VfM frameworks with a strong emphasis on cost-effectiveness and equity. The programme is actively supporting total market shaping to improve the availability and affordability of RMNCAH commodities. Through the Health Basket Fund, a defined percentage of funds has been allocated specifically for commodity procurement, ensuring consistent supply at the facility level. These efforts are designed to improve access to essential services for marginalized groups, including women, adolescents, youth, and persons with disabilities (PwDs). By aligning resource allocation with population needs and service delivery gaps, the programme is working to reduce inequities in health outcomes and ensure that no one is left behind.
These early actions align with the agreed VfM indicators such as unit cost per output, budget execution rates, and equitable distribution of benefits and demonstrate a strong VfM mindset among partners. However, actual VfM performance will be assessed more robustly in subsequent reviews once implementation data becomes available

E: RISK [½ to 1 page]

Overview of risk management

The Tanzania Health Resilience Programme (THRP) remained a Moderate risk programme this year, consistent with the programme’s cautious risk appetite and aligned with FCDO’s corporate risk appetite, particularly in areas of fiduciary risk, safeguarding, and delivery. The programme transitioned from mobilisation to implementation, and risk management has been embedded as a standing agenda item in quarterly and inception meetings, with a strong focus on fraud, safeguarding, and delivery adjustments.

FCDO maintains zero tolerance to Sexual Exploitation Abuse and Sexual Harassment (SEAH) and Fraud. Discussions on SEAH and Fraud are a standing agenda item in all partner meetings. Due diligence assessments (DDAs) include safeguarding capacity and are regularly reviewed. No SEAH or Fraud incidents have been reported to date, but vigilance remains high.

All partners underwent DDAs during mobilization. WHO’s DDA was refreshed in December 2024. Risks identified (e.g., financial management, safeguarding) are being tracked through quarterly reviews. Progress on mitigation actions has been satisfactory, with no major escalations. No DDA refresher is currently required, but this will be reassessed annually or upon material changes.

The programme has largely operated within its risk appetite. However, pressure points have emerged in delivery risk due to Human Resource constraints, and fiduciary risk related to delayed disbursements of funds to Primary Health Care from the Ministry of Finance. These are being managed through enhanced monitoring, technical assistance, and donor coordination. No changes to risk appetite are proposed at this stage. Residual risk levels remain moderate and within acceptable thresholds.

During this review period, the programme has continued to actively monitor and respond to several key risks that could impact delivery and outcomes. The following updates reflect both the evolving context and the programme’s mitigation efforts:

a. Human Resource Constraints in Primary Health Care (PHC)

Persistent staffing gaps up to 70% at the PHC level remain a critical challenge, largely due to rapid infrastructure expansion without proportional recruitment and significant rural-urban disparities in workforce distribution. This risk has been further exacerbated by the withdrawal of USAID support, which previously funded over 2,000 health workers. The loss of this support has placed additional strain on already limited human resources, particularly in underserved areas, and poses a significant risk to the delivery of essential services, including maternal and child health and family planning.
This risk is actively tracked in the programme’s risk register and remains a top priority. To mitigate the impact, the programme is leveraging the Health Basket Fund (HBF) to support national Human Resources for Health (HRH) strategies. This includes influencing the Sector-Wide Approach (SWAp) mechanisms to prioritize HRH reforms and advocating for sustainable domestic financing for health workforce expansion. Technical assistance is being mobilized to support equitable deployment and upskilling of health workers, with progress monitored through joint donor reviews and government reporting systems. The programme is also engaging with partners to explore alternative funding mechanisms to fill critical HRH gaps left by the US withdrawal

b. Digital Health Infrastructure and Utilization

While the rollout of the Government of Tanzania’s Health Management Information System (GoTHOMIS) has progressed, full utilization at the PHC level is constrained by inadequate digital infrastructure particularly limited access to computers and unreliable internet connectivity. The programme is working through the HBF to mobilize additional support for digital health investments, with a focus on improving hardware availability and connectivity. Discussions are ongoing with partners to co-finance these efforts. The programme is also advocating for improved implementation of digital health systems at the PHC level to enhance data quality, service delivery, and decision-making.

c. Commodities Availability

The risk of stockouts remains high especially on family planning commodities, due to declining donor support particularly following the withdrawal of US funding, procurement constraints at the Medical Stores Department (MSD) and limited private sector engagement. In response, the UK successfully influenced other donors to allocate 4.5% of total HBF resources to family planning (FP) commodities, which is expected to stabilize supply in the medium term. The programme is also supporting the Total Market Approach (TMA) to strengthen private sector participation and improve long-term sustainability of FP commodity availability. Monitoring is ongoing through HBF scorecard indicators and quarterly supply chain reviews.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The Tanzania Health Resilience Programme (THRP) transitioned from mobilisation to implementation during this review period, with all delivery agreements now in place. The programme is implemented through three core partners; the World Health Organization (WHO), Results for Development (R4D), and the Government of Tanzania (GoT) via the Health Basket Fund (HBF). Each partner plays a distinct role in delivering the programme’s objectives on health system strengthening, health security, and data-driven policy influence.

All inception meetings were successfully conducted, and funds disbursed. Reporting mechanisms, including narrative and financial templates, were co-developed and agreed upon with partners. The quality and timeliness of quarterly and annual reports have met FCDO expectations, with all submissions received on schedule and to a satisfactory standard.

.
WHO is delivering technical assistance on global health security under a Memorandum of Understanding (MoU). However, their engagement with us has been marked by persistent challenges in responsiveness and coordination. Despite repeated feedback from FCDO, WHO has not yet shown significant improvement in how they collaborate and communicate with our team. We remain hopeful that they will take our concerns seriously and work towards strengthening this partnership.

R4D, operating under an accountable grant, is leading the data and evidence component. Their early engagement has been commendable, with high-quality deliverables and a collaborative approach to refining the programme’ s learning agenda. Financial forecasts have been accurate, and proactive risk management.

The Government of Tanzania, through the HBF, is responsible for the largest component on health system strengthening at the primary care level. The HBF’s pooled funding mechanism has enabled efficient disbursement to over 7,000 primary health facilities. FCDO continues to engage through the Basket Financing Committee and technical sub-committees.

However, reductions in Official Development Assistance (ODA) have presented ongoing challenges. These have affected the timing of FCDO disbursements, particularly to the HBF, as the programme has had to manage within tighter budget constraints. Despite this, the programme has not experienced significant disruption to delivery. This is largely due to strong financial forecasting, close coordination with partners, and the flexibility of the HBF mechanism.

In February 2025, the programme demonstrated its agility and relevance by responding rapidly to a Marburg outbreak. The UK led the coordination effort, ensuring timely agreements were in place and funds were mobilised to support the national response. This included leveraging existing programme structures to support surveillance, case management, and risk communication. The programme’s ability to pivot and respond to emerging health threats underscores its vibrancy and alignment with national priorities.

FCDO has maintained regular engagement with all partners through quarterly review meetings, joint field visits, and technical working groups. Feedback loops have been effective in addressing implementation bottlenecks.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

Throughout the review period, the programme maintained a strong focus on monitoring, learning, and adaptive management. A key highlight was the Health Basket Fund (HBF) joint field visit conducted in Shinyanga, Iringa, and Tanga. This mission brought together stakeholders from the Ministry of Health, President’s Office, Regional Administration and Local Government (PoRALG), Ministry of Finance and Planning, and all development partners supporting the HBF. The visit focused on assessing progress in digital health implementation at the primary health care (PHC) level, reviewing RMNCAH service coverage and availability of essential commodities.

The team also examined human resource and financial management practices, particularly the timeliness of fund disbursements. It was noted that facilities often receive funds after the quarter ends, affecting implementation of plans/service. This issue is now being jointly addressed, with a commitment to identify and implement practical solutions in the coming year.

Beneficiary feedback was actively sought through client exit interviews and focus group discussions with Regional and Council Health Management Teams (RHMTs and CHMTs). These engagements provided valuable insights into client satisfaction, system usability, and service delivery gaps. The digital systems were also tested on-site to assess their operational functionality.

In addition to field visits, structured quarterly review meetings were held with all implementing partners. These meetings are preceded by preparatory engagements to align expectations and agenda items. Reports are reviewed in advance, and meetings culminate in agreed action points, which are tracked through a programme action log. This log captures decisions and follow-up actions from both formal meetings and ad hoc engagements, including email exchanges.

The programme also engages in technical working groups and other stakeholder platforms to ensure alignment with national priorities and to influence sector-wide reforms. Partners have been encouraged to adopt a proactive risk management mindset and to communicate emerging issues promptly. Multiple communication channels have been established to support timely information sharing and collaborative problem-solving.

Led by our FCDO Results Adviser and in collaboration with implementing partners, we are currently refining the programme’ s results framework to better capture outcomes and impact as we transition into full implementation. This work aims to strengthen the monitoring of progress and support more informed, strategic decision-making moving forward.

For Health Basket Fund, there was a mid-term review for the HBF that was commissioned by UNICEF on behalf of partners, and the performance indicators of HBF were verified by Independent Verification by Internal Audit General as commissioned by the World Bank on behalf of HBF partners.

The Annual Review process itself was informed by these monitoring activities and included inputs from across the FCDO team and government stakeholders. No formal evaluation was conducted during this period, but the programme continues to draw on real-time data and stakeholder feedback to inform its implementation strategy.

Date of last narrative financial report	R4D - 30/04/2025 / WHO - 09/05/2025	Date of last audited annual statement	n/a