Title: Delivering Locally Led Adaptation Action (LIFE AR). The LDC Initiative for Effective Adaptation and Resilience
Programme Value £ 12,000,000(full life)		Review date: 01/09/2025
Programme Code: 400093	AMP start date: 15/8/23	AMP end date: 31/3/28

Summary of Programme Performance
Year	1	2
Overall Output Score	B	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004546.odt
DevTracker Link to results framework:

## Scoring your programme
## The Annual Review assesses and rates outputs using the following scale.
Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. SUMMARY AND OVERVIEW

Description of programme

This review provides an assessment of progress on the Least Developed Countries Initiative for Effective Adaptation and Resilience programme, hereafter referred to as the ‘LIFE AR’ programme. The LIFE AR programme is allocated £10,052,135 of the total £12 million budget from the ‘Delivering locally led adaptation actions’ business case. This is reviewed under Outputs 1-3. The remaining £1,947,865 of the £12 million budget is allocated to complementary opportunities that support locally led adaptation.

LIFE AR works in 10 LDC countries. The first six countries to be involved are Bhutan, Burkina Faso, Ethiopia, The Gambia, Malawi, and Uganda. These countries are often referred to as the ‘first cohort’ or ‘front runner countries’(FRCs). Four more countries have joined LIFE AR, they are Benin, Madagascar, Nepal, Senegal. These are referred to as the ‘second cohort.’ For a full update on progress in these countries see Table 1 in the Annex.

The central aim of the LIFE AR programme is to change how finance is delivered and used to increase locally led climate action. It is an initiative owned and driven by the Least Developed Countries (LDCs)[1] and a pathway to realising the LDC 2050 vision[2] for a climate-resilient future.
[1] Least Developed Countries group convened under the UN Framework Convention on Climate Change (UNFCCC)
[2] LDC_Group_2050_Vision.pdf <https://www.life-ar.org/documents/4/LDC_Group_2050_Vision.pdf>

The programme is driven by key principles in support of the LDC 2050 vision and supports a shift away from ‘business-as-usual’ practice, these are known as the ‘LIFE AR Principles’[3]. The programme requires a wide range of actors and stakeholders, including donors, to do business differently and change their systems, procedures, and behaviours. The central hypothesis is that if LIFE AR succeeds in proving the viability of national governments supporting demand led process to deliver climate finance to local level in support of community priorities, then this could result in levels of transformational change that unlock large volumes of climate finance to the benefit of the poorest people in the poorest countries.
[3] LIFE-AR_ToC.pdf < https://www.life-ar.org/documents/1/LIFE-AR_ToC.pdf>

International Institute for Environment and Development (IIED) serves as the interim LIFE AR Secretariat and is directly accountable to FCDO under a Memorandum of Understanding. The LIFE AR Board (hereafter known as the ‘Board’) oversees implementation of LIFE AR and provides stewardship, accountability, and leadership. The Board is structured around 9 permanent members[4] each having an equitable position, influence and voting rights. The UK has held one of those positions since 2020. The Board is supported and advised by a Technical Working Group on which the UK has also had permanent representation since 2020.
[4] LDC Chair, LIFE AR Technical Lead, 3 Development partners, 3 LDCs, Host Board member (a trustee of IIED but not a staff member of IIED)

This Annual Review covers the period from August 2024 to March 2025, aligning with the financial year and the programme’s progress reporting cycle. Future reviews will follow this adjusted cycle, and the final Annual Review or Programme Completion Review will ensure that any remaining period up to the end of August 2028 will be fully reviewed.

In January 2025, the US Department of State (US DoS) terminated the LIFE AR funding agreement, originally for $9.27M but amended to a committed expenditure of £2,490,000 (equivalent) after the stop-work order. This had a significant impact on activities of LIFE AR at the end of 2024/2025 and considerable work has been undertaken to ‘downsize’ activities and budgets in response and work on a ‘must have’ budget and workplan for 2025/2026. Currently the LIFE AR programme is also funded by Ireland and Canada and a recent grant from the Quadrature Climate Foundation (QCF). Canada and Ireland are currently assessing their funding commitments beyond 2025/26 and at the time of writing have not yet made any decisions on future allocations. QCF funding is so far committed for just one year at this point in time.

This Annual Review acknowledges that LIFE AR’s delivery approach has evolved. While the programme remains committed to its overarching goals, it is now operating under a revised plan, a revised budget, and updated priorities. Importantly, this does not alter the FCDO’s logframe targets. Following the 2024/2025 Annual Review, FCDO worked closely with the LIFE AR Secretariat to update the logframe to enable adaptive programming. This is in line with the business case.

Given the ‘business unusual’ nature of LIFE AR, this Annual Review recognises that the programme has a defined outcome, but the approaches of the programme are adjusted drawing on emerging evidence. This flexibility allows the programme to test different options and use learning to inform key interventions. This means that when reviewing progress for this Annual Review, the review will look for tangible results at outcome level while reviewing the delivery, learning and contribution to meaningful change.
Annual Review approach

LIFE AR has been reviewed three times as a component of UNCAS in 2021, 2022 and 2023. The first Annual Review for this programme was also conducted in 2024. This Annual Review reflects on the recommendations from those reviews. The following evidence has been considered in order to assess progress:

- LIFE AR 2024/2025 Annual Narrative Report
- LIFE AR Quarterly Financial Reports of financial year 2024/2025
- LIFE AR Board papers, decisions, and minutes
- Consultations with the Secretariat, LIFE AR technical lead, internal FCDO staff, country focal points from a majority of LIFE AR countries
- LIFE AR Business Case, Logframe

Summary supporting narrative for the overall score in this review

The LIFE AR programme has been awarded an overall A (Outputs met expectation), reflecting strong progress and is contributing to the structures requires for achieve greater climate resilience. Outputs 1 and 2 scored A, demonstrating progress in establishing governance structures, delivery mechanisms. Output 3 scored B, indicating that while peer learning and knowledge sharing advanced, long-term governance of learning and integration with MEL systems require strengthening.

However, this score must be understood in the context of persistent and significant risks that continue to affect the programme’s viability and delivery. The programme remains high-risk, with critical vulnerabilities that require close and ongoing management:

- Funding instability remains a major concern. The termination of the US Department of State funding, an undetermined UK ODA commitment and uncertainty about funding from Ireland, Canada and QCF into FY26-27 means funding is currently short-term and insufficient to meet the programme’s full ambition.
- The transition to an independent LDC-led facility is a pivotal moment for LIFE AR, but it carries substantial risk. The timeline is ambitious, and current resource constraints both staffing and financial could undermine delivery and momentum. Without a realistic and well-supported transition plan, there is a risk of fragmentation and loss of institutional memory.
- Delivery challenges are emerging as countries move into the Test and Evolve phase. While progress is evident in pilot districts, scaling these models nationally is constrained by funding, capacity, and political alignment. The programme’s ability to demonstrate impact at scale is not yet proven.

Despite this, momentum across frontrunner countries is growing, with all six having had their Test and Evolve papers approved and so transitioned from the ‘Establishment’ phase to ‘Test and Evolve’ phase. Some have begun implementing investments on the ground, and four new countries have joined, with three signing MOUs and have begun onboarding. The positive trajectory and the accession of four new countries underscore growing interest and commitment among LDCs to replicate LIFE AR’s approach to locally led adaptation. Progress is detailed in Table 1 in the Annex. Viable devolved climate finance models are being rolled out to sub-national level effectively in the pilot districts in Uganda, Malawi, Ethiopia, Burkina Faso, and The Gambia. The infrastructure to do the same is in place in Bhutan. It is still premature to assess the viability that by 2030 at least 70% of climate finance is invested behind community priorities in the LIFE AR countries. This is particularly critical in a context of declining overseas development aid (ODA) and the need for diversified climate finance sources.

Efforts to establish an LDC-owned and led facility to succeed the interim Secretariat (IIED) are underway, with planning in 2024/2025 and implementation expected in 2025/2026. FCDO will continue to monitor and advise on this transition both in the capacity as a development partner and a Board member.

Peer-to-peer learning has emerged as a powerful mechanism for supporting countries in designing and delivering their own systems. Examples include Uganda’s support to Bhutan and Burkina Faso’s guidance to francophone newcomers such as Madagascar, Benin, and Senegal. Group learning sessions linked to Board meetings have facilitated cross-country exchange on establishing national and sub-national DCF systems, gender and social inclusion, and adaptation design.

Evidence of learning is increasing, supported by the launch of the LIFE AR website, which consolidates insights and resources. Monitoring, Evaluation, and Learning (MEL) systems are being refined, and Gender Equity and Social Inclusion (GESI) is being integrated into reporting frameworks. Valuable lessons have emerged from country experiences, such as Uganda’s grassroots training initiatives that foster sustainability and political support, and The Gambia’s multi-stakeholder workshops that promote collaboration and reduce duplication.

Going forward, robust risk mitigation and strategic prioritisation will be essential to sustain progress and protect the programme’s credibility. The LIFE AR Board and Secretariat must be proactive in addressing these vulnerabilities. Further and more specific recommendations are set out in 22- 25.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This annual review recommends continued support for LIFE AR based on its own positive progress and its strategic alignment with the broader FCDO strategic prioritisation and supporting development portfolio. Progress in Output 1 and 2 is demonstrating that LIFE AR is delivering measurable evidence-based progress in advancing locally led adaptation by devolving climate finance and decision-making power to the community level. It is the only FCDO-supported programme that operationalises the LDC vision that by 2030 at least 70% of climate finance is invested behind community priorities.

Consultations with in-country focal points and national government representatives confirm that LIFE AR is gaining momentum, with communities and governments expressing a strong preference for its non-paternalistic, partnership-based model. For example, consultations with focal points in Malawi are reporting that LIFE AR is being added to learning curriculum of good examples of delivering climate adaptation. They have also reported that communities have indicated preference for the LIFE AR model because of its emphasis on community ownership. Similar evidence is also coming out of other front runner countries.

There is strong evidence coming out from all six front runner countries of investments being selected that reflect local priorities and an emphasis placed on strengthening the capacity of local governments and institutions, see Table 1 below for specific examples. However, LIFE AR alone does not have the resources to deliver nationwide or global change. Its ambition is to demonstrate a proof of concept that can attract major climate funding streams to scale up and support the delivery of climate finance investment behind community priorities at significant scale in LIFE AR implementing countries and indeed to other LDCs beyond current LIFE AR cohorts.

As a long time, development partner of LIFE AR, the UK is positioned as a credible and consistent supporter of this approach and can maximise learning and alignment with other country platforms. The programme both values and delivers local empowerment, and its continuation is essential to sustaining and scaling this impact.

Major lessons and recommendations for the year ahead

These are the key recommendations for the year ahead. Full justification for the recommendations is provided in dedicated sections as indicated. The recommendations are:

For the Board to:
1. Regularly, systematically, and analytically review ambition against available resources and only approve spend plans that reflect resources available. Approval should not be contingent on the frequency of Board meetings but can be factored in as additional to those meetings as and when required.
2. Ensure there are tangible mitigation plans for risks with clear accountability and timelines, particularly for high-impact risks such as funding shortfalls and transition delays, and review progress against these regularly.
3. Agree on a realistic workable plan of transition to the new proposed LIFE AR facility factoring in resources available, including money and staff resources. If necessary, prepare to adjust the transition timetable if it is not realistic and deliverable within prior agreed time frames and budget.
4. Provide clear guidance to national platforms on the impact of funding cuts so that national platforms can manage expectations at national, sub-national and community levels.
5. Combine in-country meetings with opportunities for development partners for engagement with participating communities and field verification visits.
6. Support the learning component of LIFE AR as a critical function of the initiative and direct the Secretariat in delivering the learning component effectively and as a continuing priority.
For the Secretariat to:
1. Keep the Board fully appraised of governance challenges including staff resourcing and to discuss challenges with the Board as a whole or development partners individually to address those challenges.
2. Produce budgets that reflect actual resources available and notify Board members when major divergence is expected, well in advance (to allow development partners to reprioritise resources).
3. Commit to accurate budget forecasting to avoid repetitious reporting of underspends, which undermines donor confidence.
4. Supply the Board with the data and evidence it needs to guide advice to national platforms with respect to availability of funds for implementation.
5. Support the LIFE AR Board Chair in providing leadership to LIFE AR, including via onboarding briefings and leadership processes to ensure full and active engagement and leadership by the Chair.
For FCDO to:
1. Ensure the resources required in order to provide the in-depth review, guidance, and support particularly during a critical period of transition in 25/26.
2. Continue to lobby for and advocate on behalf of LIFE AR with a view to publicising success, accessing and securing necessary resources and providing the evidence required to prove the validity of support for effective locally led adaptation action.
3. Monitor and, with partners, support the mitigation of major risks in FY 25/26.
Major Risks

Risks of transition to a stand-alone LIFE AR facility and legal entity

The transition of LIFE AR to an LDC led facility comes at a critical point in the LIFE AR programme as countries are moving to the ‘Test and Evolve’ phase for the first time and four new countries have joined the initiative while the budget for LIFE AR has been reduced, without new long-term commitments. The target date for LIFE AR being managed by the new facility is October 2026. There are a number of elements of the transition that must be in place to ensure that the facility will be able to take on LIFE AR; financial stability, LDC commitment and leadership, organisational capacity, and strategic alignment with the LDC vision.

The current deadline is challenging and potentially risks the already limited secretariat resources being switched to the transition and away from delivery. The success of the programme depends on both delivery of a new entity that can attract and meet the requirements of potential donors and the LDC group and on LIFE AR being able to clearly demonstrate impact and value as well as continued demand from LDC countries.

Mitigation actions:
1. FCDO continues to monitor the progress and achievement of milestones along the transition plan and uses the UK Board member position to intervene where progress is off course.
2. FCDO is reviewing internal requirements and process in preparation for the due diligence of the new LIFE AR facility to facilitate a smooth transition.
3. FCDO continues to follow up with Secretariat and/or donors about ensuring there are contingencies in place if risks materialise and alternative options need to be followed.
LIFE AR is not securing enough funding to meet its current ambition

Transition – The planned transition comes with an associated cost. The most recent estimates put this at approximately £854,325 over 18 months. Given loss of US funds, an undetermined UK ODA commitment and uncertainty about funding from Ireland and Canada into FY26-27 the financial burden of the transition assumes that with an overall shrinking envelope this cost will have to be reallocated from elsewhere in the programme.

Delivery and learning – Following initial delays caused by the COVID-19 pandemic and ongoing complexities in establishing acceptable financial mechanisms for channelling climate finance to the local level, LIFE AR has gained significant momentum. The first cohort of six countries is now rapidly advancing the setup of viable devolved climate finance systems and starting to implement investments on the ground.

This surge in momentum brings with it heightened expectations for ambition, aligned with the original LDC vision. However, this comes at a time when overall LIFE AR funding has been reduced. While LIFE AR was never designed to be the primary vehicle for holding and distributing large-scale finance, there is a growing expectation, particularly at the community level of national governments and their development partners that funding will follow the establishment of platforms and systems. Managing these expectations is critical. Clear communication and strategic messaging are essential to maintain community confidence and trust, which underpin the programme’s effectiveness and long-term success.

In this new era of constrained public finance, the LIFE AR model must evolve to remain fit for purpose. The Secretariat is actively seeking alternative funding sources. Encouragingly, LIFE AR has secured funding for FY 2025–2026 from the Quadrature Climate Foundation, and there is positive movement toward securing bilateral adaptation funding at the country level. Uganda, and potentially Ethiopia and Bhutan, are progressing toward substantial support through the Adaptation Fund’s Locally Led Adaptation (LLA) window.

Mitigation actions:

1. FCDO continues to monitor the progress of fundraising as one of the criteria for a successful transition to a new facility.
2. FCDO works closely with other Board members to provide clear guidance to national platforms on the impact of funding cuts so that national platforms can manage expectations at national, sub-national and community levels.
3. FCDO works closely with the Secretariat and the other Board members to ensure that the LIFE AR strategy reflects the resources available and is fit for purpose in an era of public finance constraints.
4. FCDO will support the Board and the Secretariat to continue to showcase and champion LIFE AR’s impact and lessons in a variety of different forums in particular to interested potential donors.
5. The Board and The Secretariat will continue to monitor communication and engagement with countries and with communities to ensure that expectations around LIFE AR are managed effectively. This includes working with the Secretariat to maintain transparency on funding limitations and strategic direction, helping to safeguard community confidence and trust in the programme.
Progress of Mitigation actions from 2023/2024 Annual Review

LIFE AR is not securing enough funding to meet its current ambition

As UK Board member we have been leading discussions on the Board with regards to ‘rightsizing’ LIFE AR against available resources, that is, matching ambition realistically to resources.

Substantial effort is being made to raise additional funds by the Secretariat with some success for example Quadrature Climate Fund, a philanthropy, has now committed funding to LIFE AR. The Board is mapping trade-offs in ambition against resources and into FY25/26 based on a realistic assessment of resources available while retaining options if and when those resources are increased through new funding and will review the LIFE-AR strategy over the forthcoming year.

FCDO has also supported showcasing LIFE AR in global platforms and forums, including contributing to the Global Centre of Adaptation’s Stories of Resilience 2024 publication.

However, this continues to be an ongoing risk, and FCDO will continue to manage this risk as set out in paragraph 32.
Risks of transition to a stand-alone LIFE AR facility and legal entity

FCDO has monitored the progress of the setup of LIFE AR facility. FCDO has worked closely with the Secretariat in providing them with the information needed to better understand due diligence requirements of a new facility prior to transition to the facility. FCDO has continued to provide feedback on plans, timelines, and requirements of the new facility. FCDO has also supported coordination amongst other development partners on feedback on plans for the facility. FCDO have also pushed for a fallback position in case the goal for transition of October 2026 is not met. As a result, IIED have agreed to a fallback position of continuing to host LIFE AR until March 2027. However, this continues to be a major risk for LIFE AR, and it will be managed at the LIFE AR Board level. FCDO in its role at the Board will continue to support and guide the decision-making processing to manage this risk as set out in paragraph 28- 32.

Failure of LIFE AR to deliver and communicate progress/impacts leading to a lack of momentum and financial support

Through FCDO’s role at the Board, FCDO has monitored progress of delivering and communicating impact of LIFE AR. The Secretariat has now launched a LIFE AR website to collate and showcase its learning and impact. See paragraph 80 - 84 for further detail of LIFE AR’s work in capturing and showcasing progress and impact. However, more targeted engagement is required to achieve meaningful results, while balancing this against limited budgets and stretched staff capacity.

Mitigation actions:

  1. FCDO will continue to lobby for and advocate on behalf of LIFE AR with a view to publicising success, accessing and securing necessary resources and providing the evidence required to prove the validity of support for effective locally led adaptation action.
  2. FCDO, through its role on the Board, will communicate clear priorities to the Secretariat to ensure that limited resources and staff capacity are focused on the most impactful activities.
  3. FCDO encourages LDC Board members to actively share their own stories and evidence of impact in relevant forums and platforms as these messages would carry greater credibility and resonance.

Progress Against Recommendations from 2023/2024 Annual Review

Highlight and elevate three major risks to be actively managed by the FCDO – See paragraph 33 to 39.

Revise and update logframe and MEL and re-set LIFE AR annual review date – See paragraph 8.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programmes theory of change, including any changes to outcome and impact indicators from the original business case.

The LIFE AR Theory of Change is a live document and generic for the initiative. Each country joining the initiative will adapt the Theory of Change to suit their context while remaining faithful to the overall concept and logic. The outcomes are left deliberately broad and open to national contextualisation. The Theory of Change logic as such remains valid and unchanged in 2024/2025 from the previous version.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Outcome	Outcome indicator 2024-25	Progress
Outcome 1. Climate resilience (including focus on adaptation/or mitigation) integrated into development planning incorporating full local level voice and participation.	Number of new country development and investment plans/strategies (national and sub-national) from participating countries which incorporate climate adaptation and resilience targets based on devolving climate finance decisions and allocation to local level.	There is good progress against this outcome as Burkina Faso, Malawi, Uganda, The Gambia, Ethiopia, and Bhutan developed or updated national and sub-national development plans integrating climate resilience, with participatory processes ensuring local voices shaped investment priorities and planning frameworks. See Table 1 in Annex for further evidence.
Outcome 2. Diverse local actors accessing finance and developing and implementing climate change solutions	Ascribing a numeric target against this outcome is unrealistic given variety of contexts and range of possible solutions. The evidence here is to look for the coordination/enabling environment between the implementing actors and the disadvantaged groups voice in decision making of community led investments.	All six LIFE AR Front Runner Countries operationalised inclusive governance platforms and conducted participatory climate risk assessments, enabling community-led investment planning and direct fund transfers. Further detail on progress this outcome is detailed in Output 1 and Output 2 below for further evidence.
Outcome 3. Development Partners have brought the principles from the LIFE AR Partnership compact to life and have committed high quality patient predictable finance.	Amount and duration of development partner finance committed to initiative (tracked on an annual basis).	The programme faces a significant decline in predictable, multi-year finance following the termination of the US DoS agreement in February 2025, reducing an expected $9.27m to £2.49m (equivalent), which substantially reduced the overall resource envelope. While other funding streams remain in place, the overall outlook is uncertain, and transition costs of approximately £854,325 will likely need to be absorbed from existing budgets, further constraining delivery. Although momentum in establishing devolved climate finance systems is strong, the current funding mix does not fully meet the LIFE-AR Compact principle of high-quality, patient, and predictable finance. Urgent action is needed to secure longer-term, flexible commitments and protect core platform and transition costs to maintain confidence and sustain progress.
Outcome 4. Learning from implementation of the initiative supports adaptive management and peer exchange within and between participating countries and LDCs.		LIFE AR has made good progress in peer learning and knowledge sharing, but long-term learning governance and integration with MEL systems need strengthening. See review of Output 3 below for more detail.
Outcome 5. ICF KPI 15 Extent to which ICF intervention is likely to lead to transformational change	Progress assessed based on the ICF KPI 15 methodology	In 2024/2025, given the evidence, it was assessed that LIFE AR scored a 4 (Partial evidence that suggests transformational change is likely).

Overall, the programme remains on track, with strong progress and momentum under Outcomes 1, 2, and 5 with evidence of strong progress in integrating climate resilience into national plans and operationalising governance platforms. However, Outcome 3 is off track, and Outcome 4 has shown only limited progress, requiring targeted attention in the next period. Funding uncertainty and transition costs pose significant risks, potentially constraining delivery despite strong momentum. Close monitoring and adaptive action will be essential in 2025/26 to sustain progress and manage the transition to a new LDC-led facility. See recommendations in 22 - 32.
C. DETAILED OUTPUT SCORING

Output Title	National and local governance structures and delivery mechanisms enable finance flows to support community prioritised investments.
Output number:		1	Output Score:	A
Impact weighting (%):		33.33%	Weighting revised since last AR?	No

Output 1 Indicator(s)	Milestone(s) for this review	Progress
1.1 Extent of national LIFE AR governance and delivery arrangements established	1. National platforms, task teams and consortium established and functioning in 6 countries by 2024 and up to 12 countries by 2028. / 2. Situational analysis complete in up to 12 countries by 2028 to identify priority mechanisms for delivery, institutional framework, and flow of funds. / 3. By 2024 6 countries and by 2028, up to 12 countries, have strong systems of accountability with meaningful representation of women, young people, those living with disabilities and other disadvantaged groups in decision making and inclusive and transparent systems of monitoring and learning.	1. National platforms are now active in all six FRCs, enabling devolved climate finance. Three of four second-cohort countries are beginning similar setups. / 2. All six first-cohort countries have completed situational analyses and set up national platforms and task teams. Three of four second-cohort countries are starting this process. / 3. Five of six first-cohort countries are progressing well in the Test and Evolve phase, demonstrating strong integration of GESI principles. Uganda, Burkina Faso, and Malawi have shown high-quality inclusive practices.
1.2 Proportion of climate finance invested behind community priorities by 2030.	1. Evidence of LIFE AR countries being supported to demonstrate their capacity and capability to major funding streams such as GCF to unlock significant climate finance streams / 2. Proportion of finance supporting community prioritised investments by 2024 and 2028. The definition of ‘community prioritised investments’ is open to interpretation and may not be coherent across all countries. LIFE AR will find a globally acceptable definition of ‘community prioritised investments. / 3. Effective monitoring systems set up across LIFE AR countries, strengthening national systems for learning of what works and for reporting nationally and to UNFCCC. / 4. Reporting mechanisms agreed between LDCs and donors including quality assurance mechanisms linked to national M&E financial and narrative reporting in front runner countries.	1. Senegal has expressed commitment to apply to the GCF Readiness Fund, and Uganda is advancing a $5M proposal to the Adaptation Fund, showing strong early engagement with major climate finance streams. / 2. Uganda and Burkina Faso have developed inclusive, community-prioritised investment plans using participatory tools and national validation. LIFE AR countries are showing practical approaches despite no global definition, contributing evidence to inform future consensus. / 3 and 4 - Minimum reporting standards are in place, with countries submitting quarterly finance reports and biannual activity updates aligned to LIFE AR’s Theory of Change and GESI. Despite funding delays, countries like Uganda, Malawi, Bhutan, and The Gambia have strengthened MEL systems and shared learning, with several presenting progress at COP29.

Progress under this output met expectations, with all six Front Runner Countries (FRCs) establishing and operationalising national platforms and governance structures, enabling devolved climate finance. Situational analyses were completed in all FRCs, and inclusive systems incorporating gender and social inclusion principles are in place, though full accountability protocols and MEL integration remain uneven. Early evidence of the 70/30 principle is emerging, with several countries embedding commitments to allocate at least 70% of funds to community priorities. While expansion to 12 countries by 2028 is at risk due to funding constraints, milestones for this review period were met, justifying an A score.

Output 1.1 Extent of national LIFE AR governance and delivery arrangements established.

Milestone 1: National platforms, task teams and consortium established and functioning in 6 countries by 2024 and up to 12 countries by 2028.

National platforms (tailored to the context of each country) have been established across all of the 6 FRCs. In Uganda the national platform is closely tied to the Climate Finance Unit in the Ministry of Finance, established with the support of the UK’s programme, the Taskforce on Access to Climate Finance. National platforms have been a necessary precursor to setting up devolved climate finance mechanisms as it requires consensus across government initially at national and sub-national levels to agree the most appropriate structures.

These platforms are not only established but functioning. They are actively coordinating climate action across government levels, validating decisions, and implementing inclusive governance structures. Evidence of functionality includes regular meetings, integration with local planning systems, participatory investment processes, and documented progress such as fund transfers, MEL frameworks, and community-led adaptation planning.

3 of the 4 new second-cohort countries are in the early stages of setting up their national platforms, conducting situational analysis and establishing the coordination mechanisms across government Ministries.

The Secretariat has been analysing this progress and is producing a briefing paper on progress and lessons learned which is expected to be released in August 2025.

It should be noted that the overall goal of this milestone is to reach 12 countries by 2028. However, reaching the target of 12 countries by 2028 will require sustained funding and currently the level of funding required for 12 countries is not on track. If these resources are not secured soon, the LIFE-AR Board will need to reassess the feasibility of this ambition to ensure it aligns with the evolving financial landscape and implementation capacity as per the recommendation in paragraph 22.

Milestone 2: Situational analysis completed in up to 12 countries to identify priority mechanisms for delivery, institutional framework and flow of funds.

All 6 of the first cohort of countries have completed situational analysis and established national platforms and task teams. 3 out of the 4 second cohort of countries are beginning their establishment phase which will include a situational analysis. It is worth noting the ambition of this milestone of 12 countries by 2028 as per paragraph 49.

Milestone 3: By 2024 6 countries and by 2028, up to 12 countries, have strong systems of accountability with meaningful representation of women, young people, those living with disabilities and other disadvantaged groups in decision making and inclusive and transparent systems of monitoring and learning.

The 2024 target for 6 countries to have strong accountability systems with inclusive representation and transparent monitoring is partially met. All six front runner countries have established whole of society platforms and local structures that include women, youth, and persons with disabilities, and have advanced MEL systems. However, protocols for accountability and full GESI integration remain incomplete, and MEL capacity varies across countries. While progress is significant, for example Uganda used the ‘Pamoja[5] Voices Toolkit’ to conduct Climate Risk and Vulnerability Assessments. This toolkit integrates gender analysis, engages individuals with disabilities, empowering them to lead in the planning process. Also in Malawi, a targeted field monitoring visit was undertaken aimed at capturing community perspectives on the LIFE AR programme and verifying implementation progress at the grassroots level. Participants provided overwhelmingly positive feedback on the impact of LIFE AR, particularly highlighting enhanced women’s participation in investment decision-making and increased female leadership within local coordination structures. However, gaps remain for example in Ethiopia’s delays in fully operationalising its MEL system and rolling out training has slowed systematic data collection and adaptive learning, despite inclusive investment planning and a 30% budget earmarked for women’s priorities. Bhutan, while embedding LIFE AR in its National Climate Change Committee and creating GESI and MEL working groups, still needs to complete a gender assessment, stakeholder mapping, and finalise its Delivery Mechanism design before inclusive decision‑making can be fully institutionalised.
[5] Pamoja is the KiSwahili word for ‘together’ reflecting an aspiration of inclusivity.

To fully meet the target, LIFE‑AR should formalise accountability and transparency protocols in delivery mechanisms, complete MEL roll‑out in lagging countries with disaggregated data and feedback loops and deepen GESI analysis so representation drives decisions. It should also be noted that the ambition of reaching up to 12 countries is at risk due to insufficient funding, further consideration of this can be found in paragraph 49.

Output 1.2 Proportion of climate finance invested behind community priorities by 2030.

The target of at least 70% of climate finance target invested behind community‑prioritised investments by 2030 is ambitious and not yet fully achieved, though early progress is evident. Countries are reducing high intermediary costs by creating national implementation units, while The Gambia, Burkina Faso, and Ethiopia have embedded the 70/30 principle[6] in their mechanisms, and Malawi and Bhutan are strengthening transparency and local oversight. To fully deliver reporting on the target, LIFE AR must move from allocation commitments to verified expenditure tracking, codify the rule in all mechanisms, and integrate it into audits and quality assurance frameworks.
[6] 70% behind community priorities and 30% supporting management and delivery costs

Milestone 1 - Evidence of LIFE AR countries being supported to demonstrate their capacity and capability to major funding streams such as GCF to unlock significant climate finance streams

At the global initiative level, there is progress made with conversations between LDC Chair and the GCF Executive Director to discuss GCF support of LIFE AR and the LDC vision. Second cohort countries are eligible to apply to the GCF Readiness Fund[7] and Senegal has expressed commitment to make an application. This will better enable the start-up and establishment process. The Interim Secretariat is supporting some countries (Uganda, Ethiopia, Bhutan) in making proposals to the Adaptation Fund LLA window[8] and Uganda is advancing well in this and aims to unlock $5 million financing from this fund. While this is not yet evidence of unlocking major funding streams, it demonstrates ambition, engagement and progress with major climate finance streams towards that goal.
[7] Readiness and preparatory support | Green Climate Fund The Readiness and Preparatory Support Programme supports country-driven initiatives to strengthen their institutional capacities, governance mechanisms, and planning and programming frameworks towards a transformational long-term climate action agenda.
[8] https://www.adaptation-fund.org/apply-funding/locally-led-adaptation/lla-single-country-grants/ The Adaptation Fund pioneered the Enhanced Direct Access (EDA) funding window, as a way to devolve financial decision making to the lowest appropriate level. The funding available through the Single country LLA window is up to US$ 5 million per project/programme.
Milestone 2 - Proportion of finance supporting community prioritised investments by 2024 and 2028. The definition of ‘community prioritised investments’ is open to interpretation and may not be coherent across all countries. LIFE AR will find a globally acceptable definition of ‘community prioritised investments.

The goal of allocating at least 70% of climate finance to community-prioritised investments, as outlined in the LDC 2050 Vision, is ambitious and not yet fully met, though early progress is promising. Initial setup costs and funding uncertainties such as reduced US contributions and global ODA levels make the achievement of this target challenging, but the target is designed to be progressively realised as donor funding stabilises, and administrative costs decline. High intermediary costs, highlighted by Uganda at the July 2024 LIFE AR Board meeting, have been a barrier and in response, countries are establishing national implementation units to reduce reliance on third-party fund managers and channel more funds to local priorities. There is evidence of positive steps such as The Gambia’s Delivery Mechanism guarantees at least 70% of funds reach ward and village-level investments. Burkina Faso and Ethiopia have already allocated 70% of Test & Evolve funds to community prioritised investments. Malawi promotes transparency through community involvement in grant signing and Bhutan is innovating local planning systems to strengthen community oversight.

The initiative is on track by design and early allocations in several front runner countries however in order to truly deliver 70% of climate finance to community prioritised investments, countries need to move from demonstrating commitment to 70/30 principle to verified expenditure tracking against the 70/30 principle. Other evidence towards this would be codifying this rule in all delivery mechanism and including it in audits and quality assurance frameworks.

As countries progress further into the Test and Evolve phase, stronger evidence on meeting the 70/30 principle is expected. Four front runner countries have already begun implementing investments and refining delivery mechanisms, while others are finalising readiness steps. MEL systems are being strengthened to track actual expenditure and link local investments to national systems, and lessons from initial investment cycles will inform improvements. Continued MEL training and peer learning in 2025/2026 will further enhance reporting and verification, providing clearer proof of community prioritised spending over time.

While there is still no globally acceptable definition of ‘community prioritised investments’, LIFE AR countries are demonstrating practical approaches. Achieving consensus will likely require political coordination at global forums. LIFE AR is contributing valuable evidence to inform these discussions.

Milestone 3 - Effective monitoring systems set up across LIFE AR countries, strengthening national systems for learning of what works and for reporting nationally and to UNFCCC.

Milestone 4 - Reporting mechanisms agreed between LDCs and donors including quality assurance mechanisms linked to national M&E financial and narrative reporting in front runner countries.

For Milestone 3 and 4 to ensure accountability, the Board approved minimum reporting standards in March 2023, including alignment with country financial cycles and standardised templates. National platforms submit quarterly finance and risk reports, consolidated by the Secretariat for the Board and development partners. Annual financial statements are audited and submitted within six months of the financial year’s end. The 2024/25 audit is underway, with results expected by July 2025.

Countries also submit biannual activity reports. Reporting templates have been revised to better align with LIFE AR’s Theory of Change and integrate GESI. Despite delays due to US funding cuts, countries continued strengthening their MEL systems. Uganda contextualised MEL tools to national priorities and shared them with other countries, sparking interest from the other LIFE AR countries. This peer sharing opportunity highlighted the value of country-led adaptation of MEL tools and catalysed broader interest in localised refinement across the initiative. Malawi aligned MEL with national frameworks and built capacity through national and district-level training. Bhutan and The Gambia finalised their MEL plans and Theory of Change with support from IOD-Parc.

On reporting to UNFCCC, a number of first cohort countries (Bhutan, Uganda, Burkina Faso) shared their in-country learning at COP29 in Baku.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No further changes to the output following this annual review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

For this output, in order to strengthen national and local governance, the Board and the Interim Secretariat should support LIFE AR to formalise accountability protocols and fully operationalise MEL systems across all countries by the end of the current FY. Codifying the 70/30 principle into delivery mechanisms and audits will ensure consistency and transparency. Given funding constraints, the Board should reassess the realistic feasibility of expanding to 12 countries by 2028 and adjust ambitions accordingly to present and discuss at the 13th or 14th Board meeting in line with discussions and agreements on strategy development. See each individual respective milestone and output discussion above on progress of recommendations since the previous annual review.

Output 1
Output Title	Platform for governance, engaging donors, and advocacy and influencing international climate finance architecture
Output number:		2	Output Score:	A
Impact weighting (%):		33.33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Extent of LIFE AR platform governance and delivery arrangements established	1. LIFE AR platform systems and processes established by 2024 and 2028 (up to 6 countries by 2024 and up to 12 countries by 2028) / 2. LIFE AR Financial Mechanism is operating effectively enabling funds flow to up to 12 frontrunner countries by 2028. / 3. LIFE AR Board meets at least two times a year to approve policies and provide oversight. / 4. LIFE AR permanent secretariat established and functioning.	1. LIFE AR’s SOPs were approved and positively assessed for quality, with refinement being led by the new Compliance Manager. National platforms are active in all six first-cohort countries, while second-cohort progress is slower due to funding cuts. / 2. All six first-cohort countries have developed national financial mechanisms, with several shifting from international intermediaries to national institutions to reduce costs and boost community investment. Funds are now reaching local levels, with Uganda, Malawi, and Burkina Faso showing early signs of effective financial operations. / 3. The Board approved LIFE AR’s SOPs, which were positively assessed, and oversight remains strong through structured meetings and working groups. Despite reduced annual Board meetings, additional virtual sessions and a September 2025 in-person meeting ensure continued governance. / 4. The Board approved the independent LDC-led Secretariat to begin in October 2026, with transition planning underway and funded through LIFE AR’s existing budget. A framework and oversight system are in place to monitor progress despite funding constraints.

Progress under this output met expectations with strong progress in consolidating LIFE AR’s governance and financial systems. Standard Operating Procedures were approved and assessed as robust, and all six FRCs have developed national financial mechanisms, with several transitioning from international intermediaries to national institutions to reduce costs and increase local investment. Funds are now reaching local levels, and the Board has maintained oversight through structured meetings and working groups. Transition planning for a permanent LDC-led Secretariat is underway, though funding constraints pose risks to timelines. Overall, milestones for this period were met, supporting an A score.

Output 2.1 Extent of LIFE AR platform governance and delivery arrangements established

Milestone 1: LIFE AR platform systems and processes established by 2024 and 2028 (up to 6 countries by 2024 and up to 12 countries by 2028)

In FY 2023/24, the LIFE AR Board approved the Standard Operating Procedures (SOP). Since joining in December 2024, the new Compliance and Assurance Manager has prioritised SOP refinement and benchmarking and testing within IIED to ensure alignment with initiative goals, funder requirements, and governance standards. A recent central assessment of IIED capabilities to deliver programmes for FCDO highlighted that LIFE AR had a strong set of SOPs.

National platforms are now established in all six first cohort countries. These systems are operational and enabling investments: four countries have begun implementing community-prioritised projects, governance bodies such as Parish Climate Change Committees and national climate committees are actively validating budgets and plans, and quality assurance frameworks like The Gambia’s QAF are emerging. MEL systems are being embedded, with countries like Malawi aligning indicators to national frameworks and Uganda institutionalising regular reflection sessions. However, effectiveness is still ‑consolidating. MEL rollout remains‑ uneven in Ethiopia and Bhutan, and GESI and accountability protocols are only partially integrated partly because of the reduction in budget following the US DoS Stop Work Order. Meanwhile, three second cohort‑ countries have signed MOUs, completed onboarding workshops, and initiated steps to finalise financial agents and delivery mechanisms, positioning them to make progress in establish systems and processes in 2025/2026. It is worth noting the ambition of this milestone of 12 countries by 2028 as per paragraph 49.

Milestone 2: LIFE AR Financial Mechanism is operating effectively enabling funds flow to up to 12 frontrunner countries by 2028.

As noted in the 2023/2024 annual review, all six countries in the first cohort have identified and developed a financial delivery mechanism.

All six first cohort countries have developed national mechanisms, with several transitioning from international intermediaries to national institutions to reduce fees and better meet the 70% community investment target. For example:
- Malawi replaced UNDP with a dedicated Project Implementation Unit (PIU).
- Ethiopia shifted from GGGI to the Ministry of Finance’s CRGE Facility.
- Burkina Faso plans to move from IUCN to the national FIE fund.
- Uganda is exploring a national fund manager in coordination with the Ministry of Finance.

Evidence of effective financial operations is emerging as funds flow to investments on the ground. For example, in Uganda, district leaders successfully challenged budget allocations, prompting adjustments to prioritise community prioritised investments. Malawi has staffed its PIU and disbursed initial funds to districts. In Burkina Faso, agreements between IUCN and pilot communes ensure funds reach local levels with clear roles and responsibilities.

Milestone 3: LIFE AR Board meets at least two times a year to approve policies and provide oversight.

Following on from the recommendation of the previous annual review, FCDO has worked closely with the Secretariat to revise this milestone as part of the overall log frame review and update.

At the July 2024 Board meeting in Bhutan, the Board agreed to reduce meetings from three to two annually, effective January 2025. Mitigation measures to ensure sufficient oversight included structured Working Group meetings, a Director’s report, and standing agenda items on risk, financing, and transition.

During 2025 alone, LIFE AR will have more than two board meetings due to the loss of US funding in early 2025 requiring additional virtual Board meetings. The next in-person meeting is scheduled for September 2025 in Ethiopia. This is in addition to working group meetings and as a result, there are sufficient forums for oversight of the initiative.

A rota of working groups has also been established to support the Board covering Audit and Risk, Finance, Institutional Development.

Milestone 4: LIFE AR permanent secretariat established and functioning.

The Board has approved the independent LDC-led Secretariat to begin operations in October 2026. FCDO continues to monitor progress, through their role at the Board, towards this target and, in coordination with other development partners, to provide constructive and realistic advice in terms of managing expectations around achievement. This has included agreeing a ‘traffic light’ system of ‘go/no go’ points along the trajectory to transition where critical decisions will be made on next steps. No separate transition funding was secured, and the process is now being supported through LIFE AR’s existing budget. Taking into account the reduced funds available to LIFE AR given the decision by the US to withdraw funds, the budget for the transition has been revised to £854,325. A framework is being developed to assess new facility’s functionality, with most transition work expected in 2025/26.

Progress will be closely monitored through the LIFE AR Board, working groups, and programme management, with the next annual review expected to capture more substantial developments.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The transition to an independent Facility by October 2026 requires realistic planning and contingency options. The Board should on an ongoing basis review its governance effectiveness and ensure SOPs are consistently applied. FCDO and partners will maintain donor engagement through 25/26 and work via the Board to support second-cohort countries in establishing financial mechanisms to maintain momentum and credibility. Please refer to each individual respective milestone and output discussion above on progress of recommendations since the previous annual review.

Output 3
Output Title	Learning from the initiative is captured and shared using context-appropriate learning approaches including Communities of Practice, peer learning events, publications and others.
Output number:		3	Output Score:	B
Impact weighting (%):		33.33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 - Learning from the initiative is captured and shared using context-appropriate learning approaches including Communities of Practice, peer learning events, publications and others.	1. Mechanisms for the long-term governance of learning processes, knowledge management and dissemination are established, including communities of practice, as needed. / 2. Activities to enable peer learning held. Examples include peer learning workshops and exchange visits, both in-person and virtual, and the establishment of Communities of Practice, as needed. / 3. Learning processes for adaptive management distilling lessons across countries and effectively supporting LIFE AR Board and national delivery consortia. / 4. LIFE AR informs global good practice through evaluative reviews, robust analysis of effectiveness of mechanisms and capturing the tacit learning of “business unusual” and how to support countries’ develop effective delivery mechanisms for coherent and far-sighted adaptation responses.	1 and 2 - All six first-cohort countries completed Establishment Phase Learning, leading to further training and institutionalised reflection in Uganda. Over 10 peer learning events were held, with Bhutan and Uganda’s exchange strengthening MEL, GESI, and climate finance approaches. / 3. Global MEL and GESI working groups are strengthening peer support and aiming to form Communities of Practice. At the national level, a Community of Practice is being developed to enable ongoing exchange, especially in a resource-constrained context. / 4. First-cohort countries have documented over 20 impact stories, with several featured globally. LIFE AR’s presence at international forums has grown, with countries like Uganda, Bhutan, and Burkina Faso sharing innovations and early impacts.

Progress under this output did not meet expectation. Peer learning activities were strong, with over ten events held and mechanisms such as MEL and GESI working groups fostering exchange. Impact stories and global visibility increased, including LIFE AR’s presence at COP29 and contributions to global publications. However, long-term governance of learning remains underdeveloped, and integration with MEL systems is inconsistent across countries. While knowledge products and a dedicated website have improved dissemination, institutionalisation of learning processes is incomplete. These gaps justify a B score, reflecting that milestones were only partially met.

Learning from LIFE AR previously noted that this output should not restrict learning to a specific type or method, ultimately evidence for this output needs to demonstrate that learning is captured and shared in the format that has the most impact and is sustainable.

Milestone 1 - Mechanisms for the long-term governance of learning processes, knowledge management and dissemination are established, including communities of practice, as needed.

Milestone 2 - Activities to enable peer learning held. Examples include peer learning workshops and exchange visits, both in-person and virtual, and the establishment of Communities of Practice, as needed

The milestone on peer learning is met, and long-term governance of learning is partially met. All first-cohort countries engaged in the Establishment Phase Learning process through national workshops and formal learning reports reviewed by LDC advisors, with a synthesis report expected in 2025. Uganda has institutionalised regular reflection and learning with formal guidelines and is preparing a government-hosted national community of practice, while Bhutan has designed a community of practice model for launch in Year 6. Over ten peer-learning events were held, including global and national workshops and a Bhutan–Uganda exchange visit, which strengthened MEL, GESI, and decentralised finance approaches and fostered ongoing collaboration. Global governance mechanisms are in place through the MEL and GESI Working Groups, now operating as Communities of Practice with rotating leadership, monthly meetings, and joint sessions to integrate inclusion. Knowledge management systems, including a dedicated website, document library, impact story templates, and newsletters, are established, and over 20 impact stories have been documented. However, full institutionalisation across all countries, consistent MEL integration, and the rollout of national communities remain in progress, so long-term governance is emerging but not yet fully embedded.

Milestone 3 - Learning processes for adaptive management distilling lessons across countries and effectively supporting LIFE AR Board and national delivery consortia.

At a global level, the MEL and GESI working groups continue to exchange learning and peer support between countries with more frequent meetings and focused support, with the aim to develop into Communities of Practice. At the National Focal Point level, building on the success of the Establishment phase learning process and the connections developed in Bhutan, a Community of Practice is being developed to enable more continuous exchange between in-person meetings, particularly in the current resource-constrained landscape.

Milestone 4 - LIFE AR informs global good practice through evaluative reviews, robust analysis of effectiveness of mechanisms and capturing the tacit learning of “business unusual” and how to support countries’ develop effective delivery mechanisms for coherent and far-sighted adaptation responses.

First cohort countries have documented over 20 impact stories, and a number of them have been shared via the LIFE AR website and social media. Two global stories and one from Burkina Faso will feature in IIED’s Learning and Impact Framework report.

LIFE AR has increased its presence at global forums. At the UNFCCC meeting in June, the Secretariat hosted bilateral meetings and a partnership dinner showcasing country progress. LIFE AR featured in a climate finance paper at a C&DM meeting and co-organised two events at COP29, participating in four additional panels. Burkina Faso led a national event at COP29, while LIFE AR’s “Business Unusual” session at Development & Climate Days in Azerbaijan. Representatives from all first cohort countries and Madagascar shared innovative approaches to climate resilience. Bhutan, Ethiopia, and Uganda presented early impacts from their national learning processes.

Uganda also contributed to a significant chapter in the 2024 publication ‘Stories of Resilience-Lessons from local adaptation practice, published by the Global Centre on Adaptation [9] which reaches a global audience and was featured at COP29 in Baku and at the Regional Conference on Locally Led Adaptation convened by GCA in Kathmandu, Nepal in February 2025.
[9] Global Center on Adaptation. 2024. Stories of Resilience: Lessons from Local Adaptation Practice. Rotterdam. Chapter 2. What are Bilateral Funders doing to support LLA: The UK’s story.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No further changes to the output following this annual review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Peer learning events have shown strong value, but long-term governance of learning remains uneven, and results are not being widely dispersed, although the establishment of the LIFE AR website is improving that. The Board and Interim Secretariat should through FY 25/26 continue to support LIFE AR to strengthen national ownership of learning processes and linking them to MEL systems, which will enhance adaptive management and global influence. Please refer to each individual respective milestone and output discussion above on progress of recommendations since the previous annual review.
## D: VALUE FOR MONEY

Economy: LIFE AR demonstrates strong value for money by procuring the right capabilities (e.g., local financial management, MEL support) at lower administrative costs. Four of six Front-Runner Countries (FRCs) replaced international intermediaries with national fund managers, reducing fees and increasing local investment. The 70/30 financing rule guided budgets, and countries leveraged existing government systems to avoid duplication. Year 5 spending was lower due to US funding withdrawal. Most expenditure focused on delivery, technical expertise and governance.

Efficiency: Moderate to strong efficiency is evident, with adaptive delivery aligned to country needs. Whole-of-society platforms and learning agendas are operational in all FRCs. Countries used reflection loops and peer learning (e.g., Bhutan–Uganda exchange) to refine tools and processes. Despite funding shocks and some resulting budget mismatches (e.g., Malawi), countries adapted quickly to maintain progress.

Effectiveness: Early signs of effectiveness are promising. Four FRCs have moved from design to implementation, delivering tangible community investments (e.g., boreholes, agroforestry). National platforms are improving coordination, and MEL systems are tracking proxy indicators. Outcome-level data is still emerging, but early signals (quicker district decision cycles after local training in Uganda) show progress.

Cost Effectiveness: Tentative but positive. National fund management and direct local investment are expected to improve benefit-cost ratios. Remote due diligence and district-level training models reduce unit costs. Hard metrics will be clearer in Year 6 once outcome data (e.g., households with reduced vulnerability per GBP) is analysed. Overall, programme outcomes align with FCDO’s priority of more LDCs and SIDS with increased capability and finance to respond/adapt to climate risks and impacts.

Equity: Strong equity focus, with structures and budgets prioritising women, youth, and persons with disabilities. Examples include Uganda’s 40% female quota in local committees and Ethiopia’s 30% budget allocation for women’s priorities. A GESI Working Group supports learning and integration, though evidence on reaching the most vulnerable remains limited. The Secretariat is working to strengthen this through promotion of gender-disaggregated data collection at national and sub-national levels.

Overall: There is sufficient evidence to justify continuation of LIFE AR, with strong economy and good equity orientation, moderate–strong efficiency, promising effectiveness and early signs of cost-effectiveness.
E: RISK

Overview of risk management

The overall programme risk remains major, with key risks requiring close management in FY 2025/2026. FCDO will update its risk register and align with LIFE AR’s risk framework.

As a result of this annual review two major risks have been highlighted and elevated in paragraph 26 to 32. Some additional risks are highlighted here.

1. Governance & Financial Stability: A central assurance assessment by KPMG flagged risks in IIED’s capacity and financial resilience. An action plan is in place, with progress to be reviewed in 2026.
2. Organisational Capacity: LIFE AR’s expansion and transition to an LDC-led facility are stretching IIED’s resources amid reduced funding. FCDO will support prioritisation and donor engagement. To address this, FCDO will work encourage Secretariat to identify where IIED’s efforts can have the greatest impact. FCDO programme team will continue to support the Secretariat by offering timely advice, facilitating connections with potential donors, sharing relevant experience, and promoting LIFE AR’s work and impact across various global platforms.

Updates on risks identified in Annual Review 2023/2024.

Funding Impact: While investments are increasingly aligned with community priorities, it is too early to confirm long-term impact. MEL tools are improving tracking and FCDO will continue to monitor the results of impact coming from LIFE AR countries, see paragraph 109.

Fiduciary Risk: With more delivery partners involved, FCDO continues to monitor delivery chain risks. IIED has embedded delivery chain risk mapping requirement into sub-grant templates. The Standard Operating Procedures will also govern procedures at downstream delivery, and the Secretariat will provide more support to country leads in applying SOPs at national level as the Secretariat prepares to move to the independent Facility. FCDO will continue to maintain oversight on these risks.

Political Momentum: The impact of conflicts and increasing insecurity and shifting donor priorities threaten sustained engagement. FCDO will continue advocacy and strategic outreach to maintain support for LIFE AR and locally led adaptation within the framework of our global ODA commitments.
Gender Equality Policy Marker / LIFE AR is scored 1 (Significant) under FCDO’s Gender Equality Policy Marker- Gender equality is an important and deliberate objective, but not the principal reason for undertaking LIFE AR. / LIFE AR integrates gender and social inclusion (GESI) into adaptation efforts by addressing inequalities and promoting inclusive decision-making. The Standard Operating Procedures and governance structures embed gender transformation and social justice principles. Output 1.1 of the logframe includes gender equality as a formal objective. / A LIFE AR GESI advisor supports mainstreaming across countries. In 2024/25, Malawi, Uganda, and The Gambia strengthened local GESI accountability, including gender-disaggregated monitoring tools and inclusive delivery mechanisms. A GESI Working Group facilitates cross-country collaboration and tailored support. / MEL tools now capture gender-disaggregated data, with expectations for more evidence of gender impact as countries progress through the Test and Evolve phase.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

IIED serves as the interim LIFE AR Secretariat and is directly accountable to FCDO under a Memorandum of Understanding. FCDO holds a long-term (but not permanent) LIFE AR Board seat, influencing governance and delivery. The delivery chain is expanding as local partnerships grow, all guided by LIFE AR’s Standard Operating Procedures.
Performance and Reporting:

Programme partners have largely met financial and commercial targets. Payments are usually made in advance but not ahead of need. The Secretariat has provided timely narrative and financial reports, including four financial and two narrative reports in 2024/25. The annual audit is pending finalisation and is expected to be shared in July 2025.

Governance and Oversight:

Two regular and two emergency Board meetings were held in 2024/25, including a hybrid meeting in Bhutan that enabled local engagement. It is hoped that these types of hybrid Board meetings enabling fact checking of progress at local level will become normal as climate finance starts to reach local level. We recommend that future in-person Board meetings are timetabled to allow input from and discussion with representatives from local level communities being supported by LIFE AR. These can be on site at the Board meeting or ideally via field visits which can also serve as progress verification visits.

The Board is structured around 9 permanent members[10] each having an equitable position, influence and voting rights. The UK has held one of those positions since 2020. The Board is supported and advised by a Technical Working Group on which the UK has also had permanent representation since 2020.
[10] LDC Chair, 3 Development partners, 4 LDCs, Host Board member (a trustee of IIED but not a staff member of IIED)

Good governance at Board level requires active and committed participation and leadership by the Board Chair. FCDO recognises that the person holding the role of Chair is usually already a senior official from a national government. As such they have many demands on their time. Those demands can give the appearance that the Chair is not always fully engaged with and committed to LIFE AR. The UK has supported the transition process between recent Board Chairs, and FCDO recommend to the Secretariat that a thorough briefing during this process alerts the incoming Chair to the comprehensive demands and requirements of the role.

The Secretariat has maintained open communication and supported FCDO’s ICF KPI reporting and has always actively engaged with FCDO as a Development partner and sometimes in representing other development partners through constituency arrangements.

Operational Adjustments:

A whistleblowing hotline was procured and will be launched in 2025/26. The US funding cut in January 2025 led to cancelled activities and emergency recalibration. The LIFE-AR Secretariat handled the US Stop Work Order with a proactive and well-coordinated response. They swiftly activated a communication and risk management plan, engaged with the US grants officer to recover pre-termination costs, and implemented a reprioritised budget that reduced quarter 4 spending. Key activities were adapted with travel and workshops were replaced with virtual sessions, recruitment and external contracts were paused, and MEL and learning functions were brought in-house. They also developed two planning scenarios for Year 6 and intensified fundraising efforts, while maintaining transparency with stakeholders and safeguarding delivery momentum. Overall, the Secretariat demonstrated strong crisis management, adaptability, and strategic foresight under pressure.

Budget and Forecasting:

LIFE AR underspent by 49% in FY 2024/25 primarily because delays in countries transitioning from the Establishment to Test and Evolve phases slowed disbursements, and expected Norwegian funding did not materialise. This created a mismatch between the original budget and actual available funds, leading to apparent underspend and cashflow constraints, particularly for Bhutan, whose tranche was halved due to restrictions on using US funds with government systems. To avoid this, budgets should be based on confirmed funding with built-in flexibility for scaling if additional resources become available. Strengthening financial planning, improving forecasting of country readiness, and adopting phased disbursement linked to progress milestones would reduce recurring underspend and demonstrate‑ the programme’s capacity to absorb funds which in turn is critical for future fundraising. See recommendation in paragraph 24.
Learning and Visibility:
Despite funding challenges, LIFE AR delivered learning products and shared insights at global forums like COP29. The launch of the LIFE AR website has helped showcase progress, with 1,889 unique visitors recorded to date.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

During 2024/25, LIFE‑AR implemented a range of monitoring activities, including field visits, focus group discussions, and key informant interviews—for example, Malawi’s monitoring mission across three pilot districts captured community feedback on investment impacts and highlighted gaps in GESI coordination, informing adjustments to stakeholder engagement. Countries also piloted local MEL frameworks and reflection sessions to link grassroots data to national systems, while the global MEL Working Group reviewed semi-annual reports, refined tools, and increased meeting frequency to monthly, creating continuous feedback loops. These findings informed improvements to Delivery Mechanisms, MEL tools, and GESI integration.

The Annual Review process combined internal and external inputs. FCDO continued to review financial, semi-annual, and annual reports, monitor progress through its Board role, and engage with LDC partners, development partners, and the Secretariat to support coordination and provide technical advice. For this review, FCDO consulted climate advisors across majority of LIFE‑AR countries and held discussions with country focal points, the technical secretariat, and other development partners building on previous recommendations to ensure alignment with programme goals.

Evidence

As countries entered the Test and Evolve phase, impact stories and community feedback show growing empowerment and demand for responsive climate finance. Over 20 impact stories have been published, with communities reporting increased ownership and preference for locally led approaches. However, rising expectations present both an opportunity and a risk if funding does not keep pace.
Learning

Learning is an important part of this programme, and this is recognised and discussed in detail in Output above.

Progress on learning from annual review 2023/2024

The 2023/24 review highlighted the need for a more equitable, less extractive MEL approach. In response, LIFE AR strengthened its GESI Working Group, holding five meetings between November 2024 and end of March 2025 (two jointly with MEL teams) and supporting peer learning on inclusive data collection and reporting.

Peer-to-peer learning remains a key strength. Bhutan’s visit to Uganda and Burkina Faso’s independently led COP29 event show growing country-led momentum. Uganda is developing its own learning webinars. While still reliant on LIFE AR funding, these examples show increasing ownership of learning processes.

Date of last narrative financial report	14/05/2025	Date of last audited annual statement	14/05/2025

Annex 1

Table 1 - Summary of progress in LIFE AR countries
First Cohort/Front Runner Countries (FRCs)
Uganda / Awareness & Capacity Building: Uganda raised awareness in four pilot districts among political, technical, and community stakeholders, identifying focal persons and LIFE AR teams. A Train-the-Trainer model was adopted to scale capacity, supported by national guidelines for harmonised awareness and training. / Governance & Local Structures: Uganda established Parish Climate Change Committees (PCCCs), recognised under the National Climate Change Act 2021, to anchor devolved climate finance. PCCCs include diverse representation such as women, youth, elders, persons with disabilities, CSOs, and religious leaders who are integrated across planning levels. / Climate Risk & Planning: The Ministry of Water and Environment led climate risk assessments with academia and CSOs, training district data collectors. Using the Pamoja Voices Toolkit, Uganda prioritised investments based on technical criteria focused on public good, inclusion, and environmental sustainability. / Investments: Ten initial investments are underway, including boreholes, irrigation, access roads, cookstoves, waste management, agroforestry, and ecosystem restoration. / Fund Management: Uganda currently uses IUCN as fund manager but is exploring a national alternative with the Ministry of Finance and its Climate Finance Unit. / Learning & Reflection: Uganda institutionalised regular reflection, with guidelines for lesson tracking and follow-up. The Climate Change Department will host a Community of Practice (CoP), launching in 2025/26, to sustain learning and dialogue on climate resilience.
Malawi / Planning & Alignment: Malawi transitioned to the Test and Evolve phase, adapting its District Development Planning (DDP) process to align with LIFE AR. Participatory climate vulnerability assessments helped ensure community priorities matched climate risks and national goals. / Coordination & Delivery: Sub-national coordination was strengthened, and communities were engaged in investment planning. The Joint Technical Committee for Climate and Disaster Risk Management now includes LIFE AR as a standing agenda item, ensuring alignment with national priorities. / Implementation & Investments: A Project Implementation Unit (PIU) was established and funded, with support for governance and risk management. Three pilot districts (Salima, Mangochi, and Rumphi) were selected, with investments including irrigation schemes, protective dykes, and climate-resilient livelihoods. / Monitoring & Learning: The Malawi Task Team received training in advanced MEL methods (e.g., Outcome Harvesting, Most Significant Change). Districts also invested in local capacity, such as training extension officers in soil and water conservation.
Burkina Faso / Local Preparation & Fund Management: Seven pilot communes were prepared for climate investments, with funds managed via ADCT under the Ministry of Local Government. Collaboration agreements with IUCN clarified roles and budgets. Burkina Faso plans to transition to the nationally accredited Fonds d’Intervention d’Environment (FIE) for future fund management. / Planning & Investments: Communes integrated climate resilience into local development plans. Boussouma and Didyr used an eight-step participatory process to develop 5-year plans. A consolidated investment plan for four communes prioritised drought, heat, wind, and flood responses, including: / Ecosystem restoration / Boreholes / Forest conservation led by women’s groups / Drainage and road infrastructure / Public lighting and clean cooking solutions / Plans were co-developed and validated nationally with ministries, civil society, and media. / Governance & Learning: The National Climate Change Committee (CNACC), now LIFE AR’s national platform, held its first session in October 2024. It includes government, civil society, youth, women, disability groups, private sector, and academia. A learning workshop supported by IOD Parc identified strengths (e.g., CNACC’s role) and gaps (e.g., limited use of LDC advisors).
Ethiopia / Fund Management & Planning: A new grant agreement was signed between the Ministry of Planning and the CRGE Facility, which will manage funds for the Test and Evolve phase. The Ethiopia Task Team refined investment prioritisation through national and local stakeholder engagement, aligning with climate-smart planning and hazard projections. / Pilot Investments: Initial investments began in Kembebit Woreda, including dairy and poultry micro-enterprises, solar home systems, and related procurement support. / Learning & Community Engagement: An Establishment phase learning workshop in June 2024 highlighted the importance of community ownership and the challenge of managing expectations. A knowledge product was developed to document the community engagement process.
The Gambia / Governance & Integration: LIFE AR is now part of The Gambia’s national climate governance, with advisory roles under the National Climate Change Committee (NCCC). A national paper outlines its alignment with existing structures, and engagement from more ministries has strengthened collaboration. / Planning & Delivery Mechanism: The national team developed a design note guiding delivery, MEL, training, and quality assurance. The LoCAL mechanism was adapted to fit LIFE AR principles, with innovations led by the LoCAL Working Group. A capacity needs assessment is planned, with training co-designed by the University of The Gambia and the Rural Development Institute. / Training & Participation: A multi-stakeholder workshop shaped the design note, aiming to allocate 70% of funds to ward and village-level priorities. Online training reached 82 participants, including 21 women. / Fund Management & Risk Assessment: The Social Development Fund is the current fund manager, with additional due diligence underway to ensure local-level fund flow. / Climate Risk Assessment: A baseline and participatory climate risk assessment was completed in eight wards, identifying key hazards and coping strategies across 40 vulnerable communities. Selection criteria included remoteness, poverty, vulnerability, and population size.
Bhutan / Governance & Fund Management: Bhutan uses its national planning and financial systems to manage LIFE AR funds. In July 2024, the Board approved its transition to the Test and Evolve phase, with conditions including adapting Ministry of Finance mechanisms to better reflect LIFE AR principles. / Planning & Delivery Mechanism: Bhutan is incrementally reforming its local government planning system through a whole-of-government task team. A peer learning visit to Uganda informed its approach to inclusive climate leadership and the design of its upcoming community of practice launching in 2025/26. / Design & District Selection: A draft delivery mechanism design note is under review. Six districts were selected using criteria such as climate risk, poverty index, existing initiatives, and geographic diversity. A gender assessment and stakeholder mapping are planned for 2025/26. / Integration & Learning: LIFE AR is now a standing agenda item in Bhutan’s National Climate Change Committee (NCCC), chaired by the Ministry of Energy and Natural Resources, reflecting its integration into national climate governance.
Second Cohort
Madagascar, Senegal, and Benin have signed MOUs for LIFE AR. Nepal is still negotiating an MOU. / For Madagascar, Senegal and Benin, introductory meetings have been held with National teams to introduce LIFE AR strategic objectives for establishment phase as well as lessons learnt from the first cohort of countries. Guidelines incorporating learning from the first cohort of countries in implementing Establishment phase was also shared. Practical peer to peer learning sessions were hosted by Burkina Faso to share their experience as a francophone country in the first cohort. Emphasis for establishment phase was placed on conducting whole of government and whole-of-society awareness raising workshops from the very beginning to build the political and social capital that will set the scene for the implementation of LIFE AR in country. / The Secretariat is supporting national teams in Madagascar and Senegal to finalise selection of short-term financial agents and transferred initial disbursements to kickstart activities in-country. Benin is in the process of finalising negotiations before transfer of funds can be done

Annex 2:
Acronyms and Abbreviations

ACTADE	African Center for Trade and Development
Board	LIFE AR Board that oversees the initiative led by the LDC Chair with three representatives from LDCs, three representatives from the Development Partners and a LIFE AR technical lead
BRACED	Building Adaptation and Resilience for Climate Extremes and Disasters
CRGE	Climate-Resilient Green Economy (a facility within the Ethiopian Ministry of Finance)
COP / CoP	Conference of the Parties / Community of Practice
DCF / DFID	Devolved Climate Finance / (UK) Department of International Development
FCDO	(UK) Foreign Commonwealth and Development Office
FIE	Fonds d’Intervention pour l’Environement - The Intervention Fund for the Environment
FRC(s)	Front runner country (ies)
FY	Financial Year
GCA	Global Commission on Adaptation
GGA	Global Goal on Adaptation
GESI	Gender, Equality and Social Inclusion
GCF	Green Climate Fund
GGGI	Global Green Growth Institute
ICF	International Climate Finance
IIED	International Institute for Environment and Development
IUCN	International Union for Conservation of Nature and Natural Resources
Secretariat	Current role of IIED as interim secretariat of LIFE AR
KPI	Key Performance Indicator
LoCAL	(UNCDF’s) Local Climate Adaptive Living Facility
LDC(s)	Least Developed Country(ies)
LUCCC	Least Developed Countries Universities Consortium on Climate Change
LIFE AR	LDC Initiative for Effective Adaptation and Resilience
LLA	Locally Led Adaptation (also Action)
MEL	Monitoring, Evaluation and Learning
MoU	Memorandum of Understanding
NCCC	(Burkina Faso) National Committee of Climate Change
NGO	Non-Governmental Organisation
ODA	Official Development Assistance
Partnership Compact	The Partnership Compact reflects a commitment to ensure that LDCs receive the support they need to develop and test mechanisms that reach the local level, enabling climate informed investment in enterprise, in landscapes and in the poorest households.
REDAA	Reversing Environmental Degradation in Africa and Asia
SDF	Social Development Fund
SMART	Specific, Measurable, Achievable, Relevant and Time-bound
SOPs	Standard Operating Procedures
UNCAS	United Nations Climate Action Summit
UNDP	United Nations Development Programme
UK	United Kingdom
US(A)	United States of America
VfM	Value for money