## Annual Review Template

Title: Equipment Support for Health Training Institutions (ESHTI)
Programme Value £ (full life): Up to £4.6 million		Review date: June 2025
Programme Code: 400117	AMP start date: 15 Mar 2024	AMP end date: 31 Dec 2025

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006302.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006180.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
Nigeria has the worst maternal mortality ratio in the world, and the third worst under-5 mortality rate. One of the biggest constraints to improving health outcomes is the chronic shortage of health workers. The Equipment Support for Health Training Institutions (ESHTI) programme is designed to strengthen the capacity of health workforce training institutions across six Nigerian States: Cross River, Enugu, Jigawa, Kaduna, Kano, and Lagos. ESHTI is implemented by the World Health Organization (WHO) under a Memorandum of Understanding (MoU).
ESHTI partners with Federal and State Ministries, Departments and Agencies (MDAs) to support these institutions to meet ‘full accreditation’ standards set by regulatory authorities – by providing essential training equipment, limited infrastructure upgrades, and other key gaps identified by Nursing and Midwifery Council of Nigeria (NMCN) assessments.
ESHTI is part of a broader UK-Nigeria partnership on health workforce strengthening, including the FCDO Nigeria Lafiya programme and the DHSC Global Health Workforce programme, and direct engagement of FCDO Nigeria health advisers with government on policy reform. This reflects both Nigeria’s asks of development partners on the health workforce under the ‘Health Sector Renewal and Investment Initiative’ launched by President Tinubu in December 2023, and the UK’s strengths as a longstanding partner in this area, including through the ‘Women for Health’ programme which supported more than a doubling of training capacity in supported institutions over 2012-2020.
The intended outcome of ESHTI is to enable at least 12 health training institutions to meet equipment and infrastructure-related requirements for accreditation. The anticipated impact is that these institutions will achieve full accreditation and double their regulatory training capacity. Over the long term, this is expected to contribute to increased health worker density and improved health outcomes in Nigeria, particularly in reducing maternal, neonatal, and child mortality.
Changes in the operating context
Nigeria is facing a critical shortage of trained health workers, driven by a combination of supply and demand challenges. In response, the Coordinating Minister of Health and Social Welfare, Professor Muhammad Ali Pate, directed health workforce regulatory bodies to increase the number of students that training institutions are permitted to enrol – referred to as index places. As a result, the total number of nursing and midwifery students in training has risen from approximately 80,000 to 110,000 over the last two years.
This rapid expansion has not been matched by investment in training capacity, infrastructure, or equipment, placing significant strain on existing institutions. As a result, government partners and health workforce training institutions visited during the AR emphasised the timeliness of their partnership with ESHTI, which they noted was now needed even more urgently.
In the wake of the shift in the donor landscape in early 2025, Nigerian Ministers – including the Federal Ministers of Health and Education – have publicly highlighted the importance of accelerating the transition to self-reliance. In April 2025, the Federal Minister of Education (formerly the Minister of State for Health) launched an initiative to upgrade infrastructure, equipment, and enrolment capacity in 18 mainly federally owned medical, dentistry, pharmacy, and nursing training institutions. Initially, this has been approved at ₦110 billion (approximately £50 million) and is projected to total ₦1.5 trillion (approximately £700 million) over 5 years. This demonstrates the high priority accorded by Government of Nigeria to this intervention, and we will be sharing lessons learned from both ESHTI and ‘Women for Health’ with government partners to inform this significant domestic investment.
Partner performance
The performance of the World Health Organization (WHO), the delivery partner for the ESHTI programme, has been mixed. Initial assessments of health training institutions were delayed, procurement processes took significantly longer than anticipated, and there were periods of limited availability of key personnel. Additionally, timely access to up-to-date information on procurement timelines and associated risks was a recurring challenge.
However, these issues have been addressed through escalation to the Nigeria Country Representative and Deputy Representative, who then engaged directly to unblock and drive forward delivery. The FCDO approved a nine-month no-cost extension and agreed on a set of actions with WHO to accelerate programme delivery. Procurement timelines are now actively managed through a shared procurement tracker, which is regularly reviewed with the FCDO programme team.
WHO Nigeria has strengthened its oversight of the project, with direct supervision now provided by the Deputy Country Representative. Furthermore, bottlenecks have been escalated to the WHO African Regional Office, which has committed to fast-tracking procurement processes and has deployed additional procurement staff to support implementation. The ESHTI Senior Responsible Owner (SRO) and programme managers will share lessons learned with the ‘Integrated Strategy and Delivery Unit’ (ISDU) at the British High Commission Abuja to inform the design and oversight of future capital programmes in Nigeria, and with the FCDO health cadre to inform the approach across the network.
FCDO management of the programme
ESHTI is managed by a programme team within FCDO Nigeria’s Human Development and Demography Block. The team includes a G7 Health Adviser who serves as the SRO and Programme Responsible Officer (PRO), supported by two Programme Managers responsible for day-to-day programme management, compliance, and financial oversight.
The FCDO team holds regular meetings – at least monthly – with WHO to review programme progress, discuss risks, and ensure sound financial management. The team has also played a proactive role in keeping the project on track. For example, they facilitated early engagement with the Nursing and Midwifery Council of Nigeria (NMCN), which was instrumental in initiating the initial assessments of training institutions. The team also engaged productively with WHO to address bottlenecks in the procurement process.
Summary supporting narrative for the overall score in this review
Since approval in January 2024, the ESHTI programme has achieved the following:
1. FCDO completed a Due Diligence Assessment and signed a Memorandum of Understanding (MoU) with WHO to deliver the programme.
2. WHO has, in collaboration with the Nursing and Midwifery Council of Nigeria, selected and assessed 13 nursing and midwifery colleges in 6 States to determine equipment needs and accreditation gaps, and developed a procurement plan.
3. FCDO and WHO have engaged with participating State governments to implement complementary infrastructure upgrades, with ESHTI commitments added to Mutual Accountability Framework agreements with Kano, Kaduna and Jigawa.
4. WHO have completed procurement of the first phase of procurement sourced through the WHO e-catalogue, with items delivered to the WHO warehouse. The second (and last) phase of procurement is nearing completion, with equipment deliveries expected between June and September 2025.
During the review Government of Nigeria counterparts, including State Commissioners of Health, and officials from the Federal Ministry of Health and NMCN, expressed their appreciation for the partnership approach and support through ESHTI. They particularly praised the programme’s alignment with Government priorities and its collaborative approach.
ESHTI was initially expected to close on 31 March 2025. In February 2025 FCDO approved a nine-month no-cost extension of the programme to 31 December 2025 to provide time to: complete procurement and installation; leverage complementary infrastructure support; and strengthen the capacity of health training institutions in asset management, quality improvement, and maintenance.

Output	Score	Comment
Assessment conducted of accreditation needs in 12 health training institutions (funded through complementary DHSC programme).	A	The assessments have been completed for 13 institutions.
Equipment and other requirements for accreditation procured and supplied to at least 12 health training institutions.	A	Procurement of phase 1 equipment is now complete, in line with the revised timeframe for the project
Capacity for equipment maintenance improved in supported health training institutions.	A	Completion of this output is not yet due but on track to be achieved by the close of the project.
Overall score	A

Major lessons and recommendations for the year ahead
1. The Federal Ministry of Education (FME) recently launched a ₦110 billion (~£50 million) initiative to upgrade infrastructure, equipment, and enrolment capacity in 18 mainly federally owned medical, dentistry, pharmacy, and nursing training institutions. This demonstrates the high priority accorded by Government of Nigeria to this intervention. FCDO and WHO should engage with FME and Tertiary Education Fund to share lessons from the ESHTI programme (and its predecessor ‘Women for Health’ programme) – by the programme end-date.
2. ESHTI’s implementation experience led the programme to shift its targeting approach to focus on institutions with addressable gaps rather than just those with provisional accreditation. Changes may be needed to the programme logic to reflect this shift. FCDO and WHO should update the theory of change by end June 2025.
3. ESHTI’s assessment approach proved highly valuable to NMCN by revealing the actual conditions within training institutions and issues with its accreditation systems. With a focus on identifying and addressing gaps, institutions were more open to discussing their challenges in a frank and constructive manner. This contrasts with typical NMCN accreditation visits, where institutions often have strong incentives to downplay or conceal issues.
WHO is currently supporting NMCN – through funding from the UK Department of Health and Social Care (DHSC) – to strengthen its accreditation systems. A key lesson from the ESHTI assessments is the benefit of a developmentally focused approach. WHO should apply this insight to help NMCN adopt a more supportive and improvement-oriented accreditation model by the programme end-date.
1. ESHTI effectively demonstrated synergies with other UK-funded initiatives aimed at strengthening the health workforce. Notably, the DHSC-funded Global Health Workforce Programme supported ESHTI by financing assessments of health training institutions. Additionally, the FCDO-funded Lafiya programme facilitated engagement with State governments in Kano, Kaduna, and Jigawa, ensuring that commitments for complementary support were integrated into State Operational Plans and budgets. As ESHTI approaches its conclusion, FCDO and WHO should sustain and intensify this collaborative approach to maximise impact and ensure continuity – by the programme end-date. WHO should also collaborate with the FCDO funded Climate resilient health and education infrastructure programme (CRIBS) to ensure that specifications for any infrastructure upgrades reflect climate considerations.
2. Delays experienced during phase 2 of procurement caused misalignment in the delivery of interdependent items. As a result, the deployment of phase 1 equipment to schools is likely to be postponed until the arrival of critical phase 2 items. This delay may lead to increased warehousing costs under the project. WHO should consider strategies to minimise these costs, including leveraging existing WHO or other UN warehousing facilities where feasible – by July 2025.
3. WHO has scheduled equipment maintenance capacity building interventions for the final quarter of the project. However, this timeline is unlikely to allow sufficient time for the quality improvement and maintenance systems to be fully established and operational before the project concludes in December 2025. To mitigate this risk, WHO should fast-track these activities to begin by June 2025, ensuring adequate time for implementation and effectiveness.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
Figure 1 below illustrates the high-level theory of change for the ESHTI programme, and how it complements other UK funded health workforce strengthening programmes to deliver impact.
Figure 1: ESHTI Theory of Change

The Equipment Support for Health Training Institutions (ESHTI) programme is based on the following logic:
1. Provision of Support: FCDO provides equipment and supplies to health training institutions that do not currently meet regulatory requirements for full accreditation.
2. Accreditation Readiness: Combined with other investments in infrastructure and teaching, this support enables institutions to meet the standards required for full accreditation.
3. Capacity Expansion: Full accreditation allows institutions to increase the number of students they are permitted to train (known as index places), thereby expanding their training capacity.
4. Health Workforce and Outcomes: Increased training capacity leads to more health workers being trained and deployed to frontline health facilities, ultimately improving health service delivery and outcomes.
This theory of change has been validated by similar programmes, such as the FCDO Women for Health programme and the Global Affairs Canada / WHO Human Resources for Health programme. For example, the Women for Health programme demonstrated at least a doubling of training capacity in supported institutions, which was associated with increased employment and improved health outcomes in target states.
Emerging insights from ESHTI implementation
Recent implementation experience has revealed insights that affect the original theory of change:
1. Shifts in accreditation practice:
   The Nursing and Midwifery Council of Nigeria (NMCN) has recently granted full accreditation or increased index places to many institutions in response to political directives. However, this has often occurred despite significant gaps in infrastructure, equipment, and teaching quality. As a result, some institutions with full accreditation are at risk of losing their status or having their index places reduced. NMCN has now shifted its focus from expanding index places to maintaining and improving training standards – this is now their key steer to ESHTI.
2. Targeting challenges:
   Institutions with provisional or no accreditation – originally the primary targets of ESHTI – were found to have more substantial infrastructure and teaching gaps than originally expected. These are difficult to address within ESHTI’s limited budget, timeframe, and capital-only scope. This contrasts with earlier programmes like Women for Health (£36 million, 2012–2020), which had broader scope, timeframe and resources to address such foundational gaps.
Implications for programme logic
Given these realities, ESHTI’s targeting was adjusted to focus on institutions with addressable gaps irrespective of their accreditation status. Therefore, achieving full accreditation is no longer a suitable intermediate outcome and many of the institutions eventually selected are currently fully accredited. Instead, ESHTI’s investments are now expected to:
- Help institutions maintain their accreditation status,
- Contribute to improvements in teaching quality, and
- Expand index places where feasible.
These revised objectives are more appropriate to the current context and are also expected to impact health service delivery and outcomes. However, they will be more difficult to measure within the programme’s timeframe. As such, the theory of change should be updated to reflect this broader and more realistic set of objectives.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The table below summarises progress on the expected outcomes and impact.
Indicators	Milestone	Progress
Impact indicator 1 / Number of supported health training institutions which secure full accreditation and expand regulatory training capacity (expected to be achieved after project timeframe)	0	The following developments have been noted since 2023 in the 13 institutions to be supported (note that none have received any equipment from ESHTI, so these are not attributable to the programme) / 8 institutions maintained full accreditation, with 5 of them recording increased index places. / 2 institutions were downgraded from full to provisional accreditation, both experiencing a reduction in index places. / 2 institutions retained provisional accreditation, with 1 seeing a reduction in index places. / 1 institution improved from provisional to full accreditation and recorded a significant increase in index places. / Total index places increased from 2,815 to 3,490, representing a 24% increase.
Outcome indicator 1 / Number of supported Health training institutions that meet regulatory requirements for training equipment.	0	0 / This is on track to increase to the end-of-programme target of 13 by the revised closure date of 31 December 2025.

Given the current progress on equipment procurement under ESHTI, the outcome indicator remains on track to be achieved by the revised closure date of 31 December 2025.
It is important to note that much of the anticipated impact is likely to materialize after the project’s closure. This should be carefully considered during the Project Completion Review.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
ESHTI delivers on a commitment in the Nigeria-UK Strategic Partnership signed by the Foreign Secretary in November 2024: to work together to … support human capital development – both in terms of supporting the training of health workers, but also in terms of the benefits of this to improving health outcomes in Nigeria. It also reflects the Minister for Development’s prioritisation of ‘global health’ within FCDO development priorities. The partnership approach with the Nigerian government also exemplifies the ‘new approach with Africa’ founded on genuine partnerships and respect, to deliver mutual long-term benefit. This is also reflected in the Nigeria-UK Strategic Partnership: Nigeria and the UK are committed to a partnership that encourages long-term and sustainable development by building local institutional capacity and capability to address needs and priorities.’
ESHTI complements FCDO Nigeria’s health systems strengthening programme Lafiya, as well as the DHSC Global Health Workforce Programme, which is improving Nigerian health workforce policy, management systems and health worker skills.
Based on its strategic alignment, progress towards outcome and output achievement, and the fact that programme expenditure is already fully committed, we recommend that the ESHTI programme should continue.

## C. DETAILED OUTPUT SCORING
Output Title	Assessment conducted of accreditation needs in 12 health training institutions (funded through complementary DHSC programme).
Output number:		1	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of health training institutions assessed to determine their accreditation needs.	13	13
1.2 Project MOU agreed between FCDO and WHO	MOU extension agreed	ESHTI 9-month programme extension approved, and MOU extension agreed between FCDO and WHO.
1.3 Number of States visited by the project to conduct advocacy activities	6 States	The project visited all 6 States to conduct advocacy activities.

Briefly describe the output’s activities and provide supporting narrative for the score.
All three output indicator milestones were met, leading to a score of ‘A – achieved’.
In July 2024, in collaboration with the Nursing and Midwifery Council (NMCN), 13 Schools of Nursing and Midwifery across six states – Cross River, Enugu, Kaduna, Kano, Jigawa, and Lagos – were selected and assessed. The assessments evaluated the institutions' ability to meet regulatory requirements for infrastructure, equipment, and teaching, aiming to support accreditation standards and expand their training capacity. The following training institutions were selected and assessed:
1. School of Nursing Kano, Kano State
2. School of Midwifery Gwarzo, Kano State
3. School of Nursing Tudun Wada, Kaduna State
4. School of Nursing Pampeguwa, Kaduna State
5. School of Nursing Birin Kudu, Jigawa State
6. School of Nursing Hadeja, Jigawa State
7. School of Nursing Calabar, Cross River State
8. School of Midwifery Obudu, Cross River State
9. School of Nursing Igando, Lagos State
10. School of Nursing Parklane, Enugu State
11. School of Midwifery Awgu, Enugu State
12. School of Nursing Ogoja, Cross River State
13. Department of Nursing, LASU College of Medicine, Lagos State
  “The ESHTI assessments helped us to understand the actual condition of the training institutions”
  Mr. Ndagi Alhassan
  Acting Registrar and CEO, NMCN
Although most schools have provisional or full accreditation, many lack essential infrastructure, equipment, and tutors needed to expand their training capacity. ESHTI aims to address equipment gaps, but deficiencies in infrastructure and teaching staff must be tackled by the institutions and their State Governments. WHO has advocated to all six State governments, highlighting the need for complementary investments. These efforts have led to commitments from participating States, which in FCDO partner States Kano, Kaduna, and Jigawa have been integrated into the FCDO Mutual Accountability Framework (MAF) agreements.
These commitments are showing positive results. For example:
1. The College of Nursing in Calabar is renovating classrooms and expanding the ‘Nursing Demonstration Room’ and information, communication and technology (ICT) rooms to accommodate new equipment and additional students. They have also raised the perimeter fence and deployed armed guards for improved security.
2. The College of Nursing Ogoja is expanding science laboratories and ICT rooms.
3. The Department of Nursing, LASU, is expanding its ICT centre and has installed a CCTV system for enhanced security.
4. The Kano State Government has begun urgent infrastructural upgrades at the School of Nursing Kano and the School of Midwifery Gwarzo.
Despite this progress, much work remains to be done to ensure that supported training institutions are fully prepared to effectively utilise the equipment and expand their training capacity. WHO and FCDO plan to intensify advocacy efforts to ensure these investments are completed promptly.
To address delays in ESHTI, FCDO approved a 9-month extension until December 2025 and agreed with WHO to extend the MOU for the same duration. This no-cost extension allows additional time for the procurement, distribution, branding, and installation of items. It also provides an opportunity to continue discussions with State governments and NMCN. These discussions aim to ensure support for training institutions, facilitate regulatory re-assessment and accreditation of colleges, and strengthen the capacity of health training institutions in asset management, quality improvement, and maintenance.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No major changes to this output over the past year. The milestone for indicator 1.2 was amended to take account of the 9-month extension of the programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is the first annual review of ESHTI, so there are no recommendations from previous reviews.
The initial one-year timeframe for completing ESHTI proved insufficient to cover all planned activities. These included engaging with State governments, selecting schools, conducting gap assessments, developing procurement plans, managing procurement processes, and overseeing the delivery, installation, and commissioning of equipment. Establishing systems for ongoing maintenance also required more time.
The ESHTI business case and risk assessment flagged the risk of an inadequate timeframe given the budget constraints set, and this risk precipitated. The programme team should ensure lessons learned are fully shared with ISDU – to inform future CDEL programming. For future health workforce strengthening programmes, FCDO and WHO should factor the reality of ESHTI’s experience into design and planning.
ESHTI’s assessment approach proved highly valuable to NMCN by revealing the actual conditions within training institutions and issues with its accreditation systems. With a focus on identifying and addressing gaps, institutions were more open to discussing their challenges in a frank and constructive manner. This contrasts with typical NMCN accreditation visits, where institutions often have strong incentives to downplay or conceal issues.
WHO is currently supporting NMCN – through funding from the UK Department of Health and Social Care (DHSC) – to strengthen its accreditation systems. A key lesson from the ESHTI assessments is the benefit of a developmentally focused approach. WHO should apply this insight to help NMCN adopt a more supportive and improvement-oriented accreditation model by the programme end-date.
ESHTI effectively demonstrated synergies with other UK-funded initiatives aimed at strengthening the health workforce. Notably, the DHSC-funded Global Health Workforce Programme supported ESHTI by financing assessments of health training institutions. Additionally, the FCDO-funded Lafiya programme facilitated engagement with State governments in Kano, Kaduna, and Jigawa, ensuring that commitments for complementary support were integrated into State Operational Plans and budgets. As ESHTI approaches its conclusion, FCDO and WHO should sustain and intensify this collaborative approach to maximise impact and ensure continuity – by the programme end-date.

Output Title	Equipment and other requirements for accreditation procured and supplied to at least 12 health training institutions.
Output number:		2	Output Score:	A
Impact weighting (%):		80	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Procurement plan completed	Completed	Completed
2.2 Procurement officer recruited	In post	Procurement officer assigned by WHO
2.3 Number of Health training institutions that were supplied equipment needed to meet accreditation standards	Phase 1 equipment procured for 13 institutions.	Phase 1 equipment procured for 13 institutions

Briefly describe the output’s activities and provide supporting narrative for the score.
All three output indicator milestones were met, leading to a score of ‘A – achieved’.
After completing the health training institution assessments, WHO and the Nursing and Midwifery Council of Nigeria (NMCN) held a 3-day retreat to review the findings. Attendees included the Registrar and senior management team of NMCN, two members from each visitation panel to the 13 schools, and WHO experts in procurement, laboratory, medical technology, ICT, finance, and human resources for health. The team reviewed the assessment reports and created a prioritised list of items for each school, considering gaps, NMCN standards, ESHTI’s scope, and available resources. The WHO procurement team then developed detailed specifications for each item, conducted market surveys to estimate costs, and created a procurement plan which was approved by FCDO.
Due to the short timeframe of ESHTI, WHO assigned an existing staff procurement officer to the programme instead of recruiting a new officer. Other WHO staff, including specialists in finance, laboratory, ICT, logistics, and security, were also engaged at to support project implementation and provide technical support. The WHO Country Office and WHO Africa Regional Office procurement teams were also involved. The multidisciplinary team, led by the WHO Deputy Country Representative or the Senior Operations Officer, meets frequently to review the procurement tracker.
The procurement process is divided into two phases:
1. Phase 1 involved procuring items from the WHO e-catalogue through pre-selected international vendors. This phase is complete, and some items have arrived in-country. The first shipment of 915 computers for the 13 schools was received on February 17, 2025, at the WHO warehouse in Abuja. Most other items from Phase 1 have also arrived and are either awaiting customs clearance or are in WHO-procured warehouses. All items will be sorted, labelled, shipped to each health training institution, and installed for immediate use.
2. Phase 2 involved bidding by local vendors in Nigeria. The local procurement process is ongoing; bid submissions have closed, and bids have been reviewed and assessed. Successful bidders are now being contacted for further engagement, followed by final approvals and contract issuance. Items procured in Phase 2 will be shipped directly and installed by suppliers to each health training institution, where labelling will be carried out by WHO State offices.
Procurement delays were particularly significant in phase 2. Many items, especially those not listed in the WHO e-catalogue, lacked standard specifications, which slowed the process. Additionally, supplier closures during the Christmas season and Chinese New Year extended bid timelines.
To address these delays, FCDO approved a no-cost extension of the programme and agreed steps with WHO to accelerate programme delivery. Procurement timelines are now managed through a procurement tracker shared and discussed regularly with the FCDO programme team. WHO Nigeria also escalated its oversight of the project, with direct oversight by the Deputy Country Representative. Bottlenecks were also escalated to the WHO African Regional Office, who agreed to fast-track the procurement process for the remaining items and deploy additional procurement staff to support the project. Delivery of the phase 2 items are now expected by the end of September 2025.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The milestone for indicator 2.3 was revised to take account of the no cost extension of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is the first annual review of ESHTI, so there are no recommendations from previous reviews.
Delays experienced during phase 2 of procurement caused misalignment in the delivery of interdependent items. For example, while computers for the institutions (phase 1) were delivered in February 2025, the corresponding furniture for the computer rooms (phase 2) is not expected until June or July. As a result, the deployment of phase 1 equipment to schools is likely to be postponed until the arrival of critical phase 2 items.
This delay may lead to increased warehousing costs under the project. WHO should consider strategies to minimise these costs, including leveraging existing WHO or other UN warehousing facilities where feasible – by July 2025.

Output Title	Capacity for equipment maintenance improved in supported health training institutions.
Output number:		3	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of supported health training institutions that set up quality improvement and maintenance committees	0	0

Briefly describe the output’s activities and provide supporting narrative for the score.
This activity is scheduled for the final quarter of the programme, therefore results under this indicator are not yet due. However, assessment visits to the schools have already reviewed existing mechanisms for quality improvement and maintenance. All schools visited have implemented various systems, though their functionality and effectiveness vary. This output will provide targeted capacity-building support to enhance these systems and ensure they contribute meaningfully to sustained quality improvements.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The milestone for indicator 3.1 was revised to take account of the no cost extension of the programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is the first annual review of ESHTI, so there are no recommendations from previous reviews.
WHO has scheduled equipment maintenance capacity building interventions for the final quarter of the project. However, this timeline is unlikely to allow sufficient time for the quality improvement and maintenance systems to be fully established and operational before the project concludes in December 2025. To mitigate this risk, WHO should fast-track these activities to begin by June 2025, ensuring adequate time for implementation and effectiveness.

## D: VALUE FOR MONEY
Key cost drivers and performance
The key cost drivers for ESHTI are the costs of procurement, delivery and installation of training equipment, and the provision of WASH infrastructure (including medical waste management facilities). These account for eighty percent of the total programme cost in addition to necessary operational costs (including partner staff and compensation costs and other running costs) which are capitalised in line with the agreed approach to delivering capital investments.
VfM performance compared to the original VfM proposition in the business case
Value for money has been a central consideration throughout the ESHTI programme. In collaboration with training institutions and the Nursing and Midwifery Council of Nigeria, the project prioritised procurement of items that offer the greatest benefit at the lowest cost. A sustainable total cost of ownership approach was adopted – for example, selecting solar systems instead of diesel generators to power school computer centres and libraries.
ESHTI also leveraged domestic resources by engaging institutions and State governments to provide complementary infrastructure upgrades, enhancing impact and sustainability through a co-financing partnership approach.
Procurement processes adhered to WHO guidelines, which emphasise competitive bidding and impartial evaluation. These procedures are designed to select the most practical and cost-effective offers that meet WHO’s technical requirements.
The programme targets the training of health worker cadres – such as nurses and midwives – who are predominantly female and provide essential services disproportionately accessed by women and children.
While a full quantitative value-for-money analysis has not yet been conducted due to ongoing procurement, this will be a key component of the Project Completion Review (PCR). Nonetheless, lessons from the previous FCDO Women for Health (W4H) programme already demonstrate the strong cost-effectiveness of the ESHTI approach.
Based on performance and delivery over the last 12 months, ESHTI continues to provide strong VfM in line with the original business case proposition.

E: RISK
Overview of risk management
Risks associated with ESHTI are actively monitored and managed through monthly programme management meetings and a regularly updated risk register. Throughout the reporting period, all tracked risks remained within the programme’s defined risk appetite.
Policy and Programme Delivery Risks
The primary risk identified was that the one-year timeline for ESHTI would be insufficient to deliver all planned outputs. This risk intensified over the past year due to delays in the equipment procurement process, which extended delivery timelines beyond the original project end date. To manage this, FCDO approved a nine-month no-cost extension and collaborated with WHO to accelerate procurement activities.
Another significant risk was the potential failure of State governments and training institutions to implement the necessary complementary infrastructure upgrades. This was addressed through:
Inclusion of these expectations in Mutual Accountability Frameworks (MAFs),
1. Sustained engagement with State leadership, and
2. Regular follow-up to ensure commitments were being met.
Strategic, Contextual, and Operational Risks
While security challenges persist in parts of the country, the impact on ESHTI is expected to be minimal. This is due to:
1. Careful selection of programme sites, and
2. Strict adherence to FCDO and WHO security protocols.
WHO is currently undergoing a global restructuring process in response to a significant budget reduction following the withdrawal of funding from the United States. While this restructuring is not expected to substantially affect WHO’s capacity to implement the ESHTI programme, FCDO will continue to closely monitor the situation and assess any potential impacts.
Financial and Fiduciary Risks
To minimise procurement-related risks, ESHTI follows WHO’s established sourcing protocols. Additionally, lessons from previous projects are being applied to reduce the risk of equipment loss. For example:
1. Desktop computers were procured instead of laptops to reduce theft risk,
2. Tamper-resistant labels are being affixed to all items.
Safeguarding, Reputational, and People Risks
These categories of risk continue to be well managed, with no significant issues reported during the period. In implementing infrastructure upgrades (such as for water and sanitation) at training institutions, WHO will consult with the FCDO funded Climate Resilient Infrastructure programme (CRIBS) to ensure specifications reflect climate considerations.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Performance of Implementing Partner
ESHTI is being implemented through a partnership between the WHO and FCDO, under a signed Memorandum of Understanding (MoU). Following the approval of a time extension, the MoU has been amended to extend the programme until 31 December 2025.
During the reporting year, a high level of supervision and engagement was required from all parties to ensure that the disbursed funds of £3.8 million were fully committed. However, delays in facility assessments and the bureaucratic processes involved in contract approvals – due to adherence to WHO procurement guidelines – resulted in a reported expenditure of only 30% as of 31 December 2024. These delays significantly impacted procurement timelines and were a key factor in the decision to extend the programme duration.
To reassure stakeholders, WHO issued a letter of commitment confirming that procurement processes were at advanced stage and funds fully earmarked. Additionally, reports and warehouse inspections provide strong evidence that the programme is on track to meet its utilisation targets and key performance indicators (KPIs).
The procurement process is structured in two phases:
- Phase 1: Procurement of items listed in the WHO e-catalogue through pre-selected international vendors (largely complete).
- Phase 2: Procurement through competitive bidding by local vendors in Nigeria (ongoing).
The programme has also secured strong buy-in from policymakers in the supported States. WHO continues to monitor progress to ensure that State governments allocate aligned budgets, complementing ESHTI support . Significant progress has been made at programme sites, including facility renovations and preparations for the shipment and installation of training equipment.
Beyond its core objectives, ESHTI has demonstrated strong value for money (VfM) by helping training institutions manage high enrolment rates through increased capacity. Furthermore, both completed and ongoing site upgrades reflect inclusive and gender-sensitive design and compliance.
  Summary of Budget Allocation (FY 2024/25)
Budget (£)	Description	Percentage Allocation
£3,100,000	Procurement of equipment	82%
£ 470,464	Project support cost	12%
£ 229,536	Technical Assistance and Project staff	6%
£3,800,000

Asset Monitoring and Management
ESHTI was designed to procure tangible assets which will be donated to the beneficiary training institutions. Donated items will be tagged according to agreed FCDO visibility statements, installed and handed over. WHO will also provide technical assistance to supported institutions to improve asset management and maintenance. WHO State offices also intend to keep a watching brief over the management and use of the assets after the close of ESHTI.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
FCDO monitors the progress of ESHTI using the indicators, milestones, and targets outlined in the programme log-frame. WHO supports this process by providing monthly updates and quarterly programme reports detailing implementation progress. These reports are reviewed during monthly catch-up meetings and quarterly programme management meetings, which also serve as platforms to discuss progress, challenges, and risks.
This annual review included the following key activities:
1. Document Review: Examination of ESHTI programme reports, the annual review self-assessment report, and other relevant documentation.
2. Field Visits: On-site assessments of supported health training institutions in Kano and Lagos, and to the WHO warehouse in Abuja.
3. Stakeholder Engagement: Consultations with key stakeholders, including federal and state Ministries of Health, management and staff of health training institutions, students, and regulatory bodies—particularly the Nursing and Midwifery Council of Nigeria (NMCN).
The annual review team included the FCDO Health adviser/SRO/PRO, the FCDO programme manager for ESHTI, WHO’s Human Resources for Health technical lead and programme staff in Kano and Lagos, and representatives from the Nursing and Midwifery Council of Nigeria.
Evidence
Changes in evidence and implications for the programme are described in the theory of change section (section B).
Learning
Key lessons from the project so far are described in section A: Major lessons and recommendations for the year ahead. The Project Completion Review will include a comprehensive description of key lessons following the delivery of project outputs.
Date of last narrative financial report	February 2025	Date of last audited annual statement	First one expected by Dec 25 - end of project life.