Annual Review

Summary of Programme Performance
Year	2025	2026	2027	2028	2029
Overall Output Score	A
Risk Rating	Major

Programme title: CHOICES for Reproductive Health
Programme Value £ (full life):	£421,692,759.00	Review Date: / 16/01/2026
Programme AMP Code: 400123	Programme Start Date: 01/04/2025	Programme End Date: 31/03/2030

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0007228.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/S4001236.xlsx

Glossary
SRH	Sexual & Reproductive Health
SRHR	Sexual & Reproductive Health & Rights

AMP	Aid Management Platform
AOP	Apnoea of Prematurity
CAC	Comprehensive Abortion Care
CHAI	Clinton Health Access Initiative
CIFF	Children’s Investment Fund Foundation
COF	Catalytic Opportunities Fund
CYPs	Couple-years of Protection
DRM	Domestic Resource Mobilisation
EWENE	Every Woman, Every Newborn, Everywhere
FP	Family Planning
GFF	Global Financing Facility
HSS	Health Systems Strengthening
IM	Implementing Mechanism
IPPF	International Planned Parenthood Federation
LMA	Last Mile Assurance
LMICs	Low- & Middle-Income Countries
MA	Medical Abortion
mCPR	Modern Contraceptive Prevalence Rate
MHS	Maternal Health Supplies
MMS	Multiple Micronutrient Supplements
MNH	Maternal and Newborn Health
MnHS	Menstrual Health Supplies
MoH	Ministry of Health
NLU	New and Lesser-Used (products / medicines)
NURHT	New and Underused Reproductive Health Technologies
ODA	Overseas Development Assistance
PATH	Program for Appropriate Technology in Health
PPH	Postpartum Haemorrhage
PQ	Prequalification
(P)SEAH	(Prevention of) Sexual Exploitation, Abuse and Harassment
RHSC	Reproductive Health Supplies Coalition
SDP	Service Delivery Point
SEMA	Shaping Equitable Market Access
SRA	Stringent Regulatory Authority
SRMNH	Sexual, Reproductive, Maternal, Newborn Health
STG	Standard Treatment Guidelines
ToC	Theory of Change
UNFPA	United Nations Population Fund
UNICEF	United Nations Children’s Fund
USAID	United States Agency for International Development
VfM	Value for Money
WHO	World Health Organisation

SUMMARY AND OVERVIEW

Programme description / The CHOICES programme is the UK’s largest ODA investment in Sexual and Reproductive Health and Rights (SRHR). / CHOICES is helping to accelerate progress towards universal access to SRHR by 2030 (Sustainable Development Goal 3), supporting the UK’s commitment to defend and promote universal and comprehensive SRHR.[1] Working in partnership with Global South governments, multilateral organisations, NGOs and the private sector, it is strengthening health systems and expanding access to high quality contraceptives, abortion products, and maternal and newborn health medicines for millions of women and adolescents in over 54 of the world’s poorest countries. / Investing in family planning is a development ‘best buy’, returning as much as $120 per dollar invested.[2] When women and girls have access to contraception, they are more likely to complete their education, find employment and fulfil their potential. This in turn unlocks economic growth at the national level, supporting the emergence of strong economies and societies in predominantly low- and middle-income countries. Despite this, 221 million women and girls have unintended pregnancies, with over 60% ending in abortion and 45% of these being carried out using unsafe methods.[3] / Limited commodity availability remains a barrier to universal SRHR, alongside a range of other obstacles preventing women and girls from accessing RH services. These include weak health systems, restrictive policies, misinformation, geographic barriers, poor counselling and social stigma. Donor funding of essential health commodities delivers exceptional VfM. By pooling donor funding, aggregating demand and purchasing health commodities globally, we are able to capture economies of scale, create attractive markets for manufacturers, secure affordable prices and dramatically increase commodity availability, choice and quality in LMICs. / However, we need to do more than simply purchase commodities if we want to secure sustainable commodity availability in LMICs. RH commodity markets are fragile and complex and currently do not function as effectively as they could. This is because the journey from the product manufacturer to end user is fraught with challenges and risks. Low and uncertain demand for RH commodities due to social norms, fluctuations in financing and political priorities can deter suppliers from beginning long and costly registration processes, investing in research and development (R&D) and scaling up manufacturing capacity. As a result, RH commodity markets in LMICs are often stuck in ‘market traps’ characterised by few quality-assured suppliers, high prices, low demand and lack of innovation. These market traps ultimately constrain access to essential medicines in low-income countries, worsening health outcomes and reducing the VfM derived from donor funding. / The programme includes two main components to address these challenges: a replenishment to the UK’s funding to the UNFPA Supplies Programme, and a new and highly innovative accelerator to transform SRH markets, driven by national ownership for long term sustainability. / UNFPA Supplies – FCDO’s renewed investment in the world’s largest procurer of sexual and reproductive health (SRH) commodities. / CHOICES Accelerator – A technical assistance programme managed by the Clinton Health Access Initiative (CHAI) to increase the sustainability and value of our investment in SRH commodities. The Accelerator is building government capacity and supporting national market stewardship, to strengthen global and country markets by cutting prices, strengthening health systems and rolling out life-saving innovations. / Changes in external context / 2025 was a seismic year for SRHR. Expanding access to, and choice of, voluntary RH commodities plays a crucial role in empowering women, adolescents and girls through a rights-based approach, in order to unlock their social, economic and political agency as full members of society. With 90% of public-sector commodities in LMICs donor-funded, however, there has been significant reliance on ODA to deliver these products and SRH services – and the closure of USAID, alongside ODA cuts by other donors, meant that 70% of donor-funded family planning commodities were cut or at risk in 2025. Without access to these supplies, RH services are reduced and those most in need are prevented from enacting their rights. / Declining ODA, as well as tightening fiscal space in low- and middle-income countries (LMICs), mean that global health systems are entering a period of profound transition. ODA reductions have happened faster than expected, but these shifts have been long anticipated. The CHOICES programme was designed to respond to these changes. / The UK public, and our partner countries, want a different relationship, and so CHOICES is aligned with the UK’s modern approach to development – with the FCDO not just donors, but partners, investors and reformers. The FCDO-supported Rapid Refresh of the UNFPA Supplies Partnership will support more countries to transition away from solely donor funding, towards blended finance models and domestic resource mobilisation. The CHOICES Accelerator is strengthening national health systems to build country capacity, and providing technical assistance and expertise to partner organisations and countries alike. These activities will help to build government leadership on SRHR, supporting more sustainable and locally-led health interventions. / At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition. The reduction in ODA has resulted in some changes to this programme, although funding for 2025-26 was largely protected. ODA allocations for 2026 onwards, and the impact on the programme, are being worked through based on various factors including impact assessments. / The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect. With less money, we must make choices and focus on greater impact: every pound must deliver for the UK taxpayer and the people we support. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises. We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.
Intended policy objective(s) of projects within this programme. / See Section B
Overall Programme Score / A
Summary supporting narrative for the overall programme score in this review. / Despite funding challenges, the programme is on track to achieve or exceed all but one of the milestones set for this financial year. Work under each output is on a positive trajectory, with mitigating actions in place where progress has been delayed, and there is a possibility that the programme will exceed expectations by the end of Year 1. See Section C for further detail.
Major lessons and recommendations for the year ahead / Phase 2 of UNFPA Supplies Rapid Refresh should continue its emphasis on country leadership, domestic resource mobilisation and UNFPA’s unique value-add. / Continued and closer collaboration between UNFPA and CHAI, facilitated by FCDO. / Continue exploring opportunities to broaden scope of CHOICES (particularly the CHOICES Accelerator) to expand focus on Maternal and Newborn Health (MNH), balanced with the constrained funding landscape. / Further detail in Section C.
[1] Joint statement at the 58th Session of the UN Commission on Population and Development - GOV.UK; 7 April 2025
[2] Kohler, H. and Behrman, J. (2014). Post-2015 Consensus: Population and Demography Assessment. Accessed 24/06/2019. Available online at: https://www.copenhagenconsensus.com/publication/post-2015-consensus-population-and-demography-assessment-kohler-behrman
[3] SWP Report 2022: Impacts | United Nations Population Fund (unfpa.org); Guttmacher Institute (2019), “Adding It Up: Investing in Sexual and Reproductive Health 2019”, available online at: https://www.guttmacher.org/report/adding-it-up-investing-in-sexual-reproductive-health-2019

PROGRAMME STRATEGY OR THEORY OF CHANGE

Theory of change and objectives
The Theory of Change (ToC) for CHOICES (at Annex A) sets out how the programme will support the establishment of a more sustainable, equitable, and coordinated SRH commodity ecosystem which gives women, adolescents and babies in low- and middle-income countries (LMICs) access to life-saving, affordable and high-quality SRH commodities and services (contraceptives, safe abortion, maternal health, menstrual health and newborn health products).
The agreed objectives of the programme are to:
1. Dramatically expand access to sexual and reproductive health commodities in LMICs.
  1. Procure and deliver commodities at scale, across a comprehensive and broad set of products (covering high-quality contraceptives, abortion products, and MNH medicines) and a wide geographical footprint to reach more than 21 million women, children and adolescents annually.
2. Accelerate domestic financing of commodities and transition away from donor dependence.
  1. Support accelerated progress on domestic resource mobilisation (DRM) with aim to support 20 countries to sustainably transition away from commodity support.
3. Strengthen health systems.
  1. Collaborate with governments, NGOs, and the private sector to reinforce health service delivery, supply chains, and regulatory frameworks.
4. Drive country led market stewardship and global market shaping for more sustainable access to SRH commodities.
  1. Help countries introduce and scale life-saving new products faster and enable them to secure them more affordably to broaden access and enhance programme impact.
  2. Strengthen markets and systems nationally and globally for more sustainable access into the future.

Describe whether the programme-level objectives are likely to be achieved.
Programme implementation is on track at the mid-point of Year 1.
Changes to the programme context
The original input into the ToC was the provision of £300m over 5 years to the UNFPA Supplies Partnership programme for the procurement of RH commodities, increased country ownership, and strengthening of country health systems; and £100m to the CHOICES Accelerator implemented by CHAI, a technical assistance programme to strengthen global and country markets and increase the sustainability and value of commodity procurement.
Following the UK announcement that ODA will be reduced to 0.3% of GNI by 2027, multi-year funding for this programme has not yet been agreed. However, both UNFPA and CHAI received their full UK allocation for 2025-26 (£60m and £19m, respectively).
The ToC assumes sufficient global funding for SRH commodities, but wider donor ODA cuts and tightening fiscal space in LMICs mean ensuring consistent access is at risk. The programme is taking decisive action to address this risk. Lessons learned from the Reproductive Health Supplies Programme (RH Supplies) and adaptations made to the programme to increase a focus on domestic resource mobilisation, support the Rapid Refresh of the UNFPA Supplies Partnership, and increase sustainability and impact through the CHOICES Accelerator implemented by CHAI, have enabled positive progress against the programme objectives in 2025.
DETAILED OUTPUT OR PERFORMANCE AREA SCORING

Overall summary of progress
The findings of this Annual Review reflect on a programme operating with funding uncertainty and in an increasingly complex global landscape.
However, data to this point suggests that the programme is on track to achieve or exceed all but one of the milestones set for this financial year. Work under each output is on a positive trajectory, with mitigating actions in place where progress has been delayed, and there is a possibility that the programme will exceed expectations by the end of Year 1. The programme has therefore been scored an A for progress so far in 2025-26.
UNFPA has responded to the new financing context by designing and launching a new programme model under the Rapid Refresh. The new model will accelerate the impressive progress to date on domestic resource mobilisation (DRM) and ensure scarce resources go further; and aims to provide concrete pathways for 20 of the 54 countries to transition from donor commodity support by 2030[4]. This will ensure that the Supplies Partnership can continue providing life-saving commodities where they are needed most, and safeguard the programme against any further ‘shocks’ in the donor funding system.
[4] More detail in Section C
The programme-funded secondment of an FCDO member of staff to UNFPA continues to represent exceptional VfM. The FCDO secondee led the Rapid Refresh process, and drew on UK-funded technical support from CHAI to deliver a robust and data-driven approach that was critical to securing universal approval from the Steering Committee. This is a clear example of the UK’s leadership and unique value-add through CHOICES.
Another success of the programme has been in the closer strategic collaboration between UNFPA and CHAI. Throughout 2025, CHAI was instrumental in supporting the Rapid Refresh – providing critical technical support to redesign the programme’s country categorisation model and transition approach. Building on this successful collaboration, CHAI will continue its deep engagement in “part 2” of the RR in 2026, with a focus on supporting the redesign of the Health Systems Strengthening (HSS) fund and Country Compacts (the vehicle for government spending commitments). UNFPA and CHAI also continue to work closely on the introduction and scale-up of new and lesser-used (NLU) products, including through the interagency working groups for the Hormonal IUD and DMPA-SC. Both UNFPA and CHAI routinely exchange information regarding Catalytic Opportunity Fund (COF) applications and HSS interventions in countries undertaking product introduction and scale up efforts, to better join up and maximise the impact of their respective investments.

Outcome Indicators
In addition to the Impact Indicators set out under each Output, progress is being made against a series of Outcome-level indicators included in the CHOICES logframe. Where data on progress is available at this point in the year, it is below.

Outcome Indicator	Milestone(s) for achievement by end-March 2026 (Year 1)	Progress to date
1.1: % of countries with 85% of primary SDPs that have at least 3 modern contraceptive methods available on the day of visit or assessment (disaggregated for urban-rural and SDP type)	85%	Data will be available by end of March 2026, drawn from 2025 survey.
1.2: 85% of SDPs that have magnesium sulphate, misoprostol and oxytocin available on the day of survey/day of data collection (disaggregated for urban-rural and SDP type)	48%	Data will be available by end of March 2026, drawn from 2025 survey.
1.3: Number of countries where new and lesser-used reproductive health commodities are procured for use in the public sector in line with government-led introduction plans and women’s reproductive rights	32	34 / Full year target met.
1.4: % of countries reporting no contraceptives stock outs in at least 60% of service delivery points on day of survey/day of data collection (disaggregated for urban-rural and SDP type)	46.4%	Data will be available by end of March 2026, drawn from 2025 survey.
2.1: Number of countries where government sustain or increase the amounts allocated for procurement of contraceptives and spend more than 80% of the allocated amount for the year	16	Data will be available by end of March 2026, drawn from 2025 survey.
2.2: Number of countries covering 50% or more of their national supply plan through public funds or concessional financing.	7	7 / Full year target met.
2.3: Number of countries that have maintained or increased their domestic expenditure on quality-assured life-saving maternal health medicines over the prior year where validated data is available	7	6 / On track.
2.4: Number of countries where family planning is explicitly included in the Essential Package of Health Services	44	Data will be available by end of March 2026, drawn from 2025 survey.
3.1: Number of countries with active government-led SRMNH market stewardship approaches	8	2 new countries (beyond existing 6) supported to establish new market stewardship groups (Ghana and Senegal) making a total of 8. / Full year target met.
3.2 Savings achieved through procurement of SRMNH products at negotiated prices	£5m	£8.7m of savings between Apr-Dec 2025 through procurement of H-IUD. / Full year target met.
3.3 Percentage of target products for which the supply is adequate, affordable and reliable enough to meet financed demand	100%	Interim assessment indicates met for 3/5 (60%). Affordability of Tranexamic Acid (TXA) and drapes to be prioritised over coming remainder of year. / On track.

- Outcome 1.3: In 2025 the UNFPA Supplies Partnership procured and delivered new and lesser-used reproductive health commodities to diversify method choice, provide therapeutic options and improve access in 34 countries. This included Hormonal IUD, Tranexamic Acid injection (TXA), Heat Stable Carbetocin Injection (HSC), Mifepristone and Misoprostol (medical abortion (MA) combipack), MVA Kits, and Non-Scalpel Vasectomy Kits + Bilateral Tubal Ligation Kits. DMPA-SC is not included in the count, because it is procured and delivered to almost all programme countries plus some countries outside of the programme.[5]
  [5] As at end-Nov 2025, the UNFPA Supplies Partnership procured and delivered DMPA-SC to 49 countries. The total included countries outside of the programme such as Bangladesh, India and Venezuela. In UNFPA Supplies Partnership countries, DMPA-SC scale up continued through catalytic interventions supported by the Health System Strengthening (HSS) funding stream. The roll-out of self-administration of DMPA-SC continued in 30 countries.
- Outcome 2.2: During the reporting period, many countries translated their financial pre-commitment and commitment for reproductive health commodities into actual procurement expenditure by utilising domestic resources. Seven countries (Bolivia, Cambodia, Honduras, Niger, Madagascar, Papua New Guinea and Timor-Leste) have financed 50% or more of their national supply plans through public funds or concessional financing. These countries have also taken steps to strengthen their national supply plans.
- Outcome 2.3: As of 18 December 2025, a positive trend shows increased domestic financial commitment for procurement of quality maternal health products. Current data indicates six countries (Cambodia, Ethiopia, Niger, Papua New Guinea, Senegal and Zambia) have maintained or increased their domestic expenditure on life saving maternal health commodities. This represents an increase of one country compared to the baseline. Most of the commodities were procured through UNFPA Third Party Procurement (TPP). This outcome signals strong national ownership and sustained dedication to improving maternal health. By directing domestic resources toward quality assured maternal health products, these governments have shown commitment to invest in ensuring access to high-quality, life-saving products and reducing maternal mortality and morbidity.
- Outcome 3.1: The number of countries with government-led market stewardship groups has risen to 8 with the launch of market stewardship groups (MSGs) in Ghana and Senegal. Beyond this, CHAI teams are also supporting market stewardship through a wide set of activities that may not be directly under the remit of formal MSGs.
- Outcome 3.2: Available data only allows for calculation of savings flowing from the price reductions and procurements secured for the hormonal IUD. These savings are in excess of the target for the full year – reflecting success in maintaining funding and volumes against a very challenging funding backdrop. For the calculation of the full year target, savings from additional product price deals, such as caffeine citrate, drapes and MMS, will be included.
- Outcome 3.3: An assessment has been made of market conditions for the target products (H-IUD, MA combipack, caffeine citrate, TXA and drapes). In terms of adequacy and reliability of supply, all products are assessed as satisfactory. There is scope to strengthen affordability of both TXA and drapes, including through active supplier engagement and support.

Risk
FCDO has developed and is maintaining a comprehensive, live programme risk matrix and register on AMP which is updated regularly. This includes both risks related to programme partners, and risks specific to FCDO delivery. The programme team reviews the risk with each partner at quarterly programme meetings and reviews the aggregate risk quarterly. UNFPA Supplies and CHAI have also developed risk matrices aligned to the FCDO model, which are shared regularly with the FCDO programme team.
Many of the risks present during the previous programme, Reproductive Health Supplies, remain present for CHOICES. The geopolitical context around SRHR has only become more complex, with increasing push back on rights and growing opposition to comprehensive SRHR presenting a risk to the supply of commodities and the delivery of SRHR services: restricting access to safe, effective, high quality and affordable RH commodities for women and girls. The U.S.’ global health aid cuts caused significant and immediate disruptions across the global health architecture, particularly on supply chain management (due to the contributions previously made by the U.S. to strengthening supply chain functions, such as eLMIS and distribution and warehouse management).
FCDO funding for the programme was protected for 2025-26, with a total of £60m disbursed to UNFPA Supplies and £13m so far to CHAI (an additional £6m will be disbursed to CHAI in Q4). However, delays in approving funding, coupled with continued uncertainty over multi-year ODA allocations, continue to pose a high risk to programme delivery. A lack of funding risks delays to the introduction of new products and approval of CHAI Catalytic Opportunity Fund (COF) grants. The UNFPA Supplies Partnership designed and has begun implementing a Rapid Refresh of the Partnership model in response to ODA cuts, to ensure it makes effective use of limited resources to support these vital functions. To enhance domestic resource mobilisation (DRM) and ensure sustainable commodity financing within participating countries, the UNFPA Supplies Partnership employs the Compact and Match Fund models. These programmatic approaches enhance both country ownership and the sustainability of commodity supply, bolstering national systems for resource mobilisation and encouraging government procurement of commodities through domestic funds. Additional mitigating measures by FCDO and its likeminded partners include promoting diverse funding mechanisms such as DRM; and strategising and advocating for the protection and progress of SRHR primarily in the multilateral space, but also at the country level.
Additionally, UN80, an ambitious United Nations reform process, has proposed significant structural changes to its entities including UNFPA; risking the dilution of its distinct mandate and operations. We are carefully weighing opportunities and risks arising from UN80, and working closely on these with UNFPA colleagues.
The programme operates within a challenging operational landscape which has risks for programme execution. Financial and fiduciary risk remains closely monitored, with both the UNFPA Supplies Partnership and CHAI maintaining a low tolerance for such risk. Operational complexities in various countries constitute a considerable risk factor, potentially exacerbating fiduciary risks by hindering efficient resource monitoring and oversight; as well as certain instances of fraud and/or corruption. To address these vulnerabilities, UNFPA employs financial policies encompassing inventory control procedures designed to mitigate fraudulent activities: routine in-country inventory evaluations, spot audits, capacity building for warehouse personnel through the Health System Strengthening fund, the development of preparedness plans, and last-mile assurance protocols. For all concerns of wrongdoing, including fraud, CHAI staff and the public have multiple mechanisms available to report concerns. Further, CHAI finance staff are responsible for upholding financial controls, including active engagement in oversight for payment processing. In 2025-26 there have been very few incidents of fraud or financial loss associated with the programme. Incidents which did arise, however, were reported promptly by programme partners and comprehensive investigations and mitigations were undertaken.
There is a low risk that the CHOICES programme will cause unintended harm to people and the environment. The programme team manages this safeguarding risk robustly, with a particular focus on sexual exploitation, abuse, and sexual harassment (SEAH). This includes communicating FCDO’s zero tolerance approach for inaction and mishandling and expectation that all partners follow robust safeguarding and reporting measures through their own processes, including prompt reporting to FCDO of SEAH allegations relating to FCDO funding, or where there is a significant impact on the partnership. FCDO continues to ensure all programme partners maintain full compliance with respective safeguarding policies and ensure full transparency on reporting with FCDO. UNFPA maintains a policy of zero tolerance for SEAH. Implementing partners of UNFPA undergo capacity assessments in the protection against sexual exploitation and abuse. FCDO is actively engaged in UNFPA's initiatives to prevent and address sexual exploitation and abuse and sexual harassment through the UNFPA Executive Board. These encompass clear leadership and communication of zero tolerance, mandatory training and awareness campaigns, the establishment of a SEAH network including focal points in country offices, and clearly indicated reporting mechanisms. UNFPA Supplies collaborates with national counterparts and governmental bodies to enhance national protocols and guidelines pertaining to the disposal of medical waste and contraceptives. In conjunction with the WHO and regulatory bodies, UNFPA ensures that all supported products adhere to stringent standards of safety, efficacy and quality.
Output 1
Output Title	UNFPA Supplies Partnership effectively delivers Phase III ambition in a changing context and is underpinned by a robust operational and governance model.
Output number:		1	Output score:	A
Weighting (%):		30	Weighting revised since last AR?	N/A

Briefly summarise progress to date against the programme outputs, and provide supporting narrative for the score.
Impact Indicators
Indicator(s)	Milestone(s) for achievement by end-March 2026 (Year 1)	Progress as at end-Nov 2025 (note all data is interim and will be finalised in 2026)
1.1 UNFPA Supplies governance model is responsive and effectively operationalised to support robust decision-making, and provides donors with strong oversight and assurance	UNFPA Supplies develop priority actions on governance improvements agreed in the MTR response	UNFPA Supplies Partnership has developed priority actions to strengthen governance in response to the mid-term evaluation (MTE) recommendations. These are contained in the Management Response to MTE, which was issued in November 2025. The implementation of several priority actions for 2025 and 2026 is already underway. / On track.
1.2 UNFPA Supplies is managed by a strong, multidisciplinary team at the global, regional and country levels	100% of the UNFPA headquarters team is fully relocated to Nairobi	All 10 HQ-based UNFPA Supplies Programme staff members have now fully relocated to Nairobi. / Full year target met.
1.3 UNFPA Supplies adopts a comprehensive and integrated approach to SRHR commodities, including CAC and Maternal Health	Joint planning conducted by UNFPA Supplies and the UNFPA and the Maternal and Newborn Health Fund conducted at headquarters levels	In 2025, UNFPA Supplies and MNHF team began systematic joint work planning processes. The collaboration included working initiatives such as MNCH Accelerator, collaboration on New and Lesser Used (NLU) product introduction such as Tranexamic acid (TXA) and Heat Stable Carbetocin (HSC). It also included issuing joint mid-year reprogramming guidelines, review of joint reporting for 2025 and joint planning for 2026. / On track.
1.4 Robust results framework and accountability mechanisms in place to ensure oversight, transparency and assurance over programme performance	In-country assessments completed in 36 UNFPA Supplies Partnership implementing countries by the last mile assurance team and all recommendations made in previous assessments are taken forward in a timely manner	Across 2024-2025, UNFPA completed ICAs in 39 UNFPA Supplies countries, exceeding the biennial coverage expectation of 36. For all countries assessed, a strengthening action plan was developed and is being regularly monitored. / In 2025, UNFPA strengthened the in-country assessment approach by adopting a biennial cycle to ensure deeper follow-up, stronger implementation of recommendations, and more efficient use of country and UNFPA resources. / Full year target met.
1.5 UNFPA Supplies Partnership's domestic resource mobilisation and co-financing model supports country transition and sustainability of SRH commodity availability[6]	72% of governments have met their minimum contribution to the country compact that is fulfilled in full	By 30 November 2025, 76% (31 out of 41 countries) of governments have fully met their minimum contribution as outlined in their 2024 Annex A. / Full year target exceeded.
[6] The indicator is designed to measure the number of governments that have signed Annex A of the Compact agreement and go on to fulfil their minimum contributions as contained in the Compact. Not all 54 partner countries are required to make commitments; some are exempted each year due to acute humanitarian contexts or being new to the programme. As such, the denominator for this indicator changes over time. Data for this indicator are finalised only in the final quarter of the subsequent year. This is because country governments are likely to show performance some months after the end of the year in question. It also takes time to confirm and validate country expenditures.

Supporting narrative
UNFPA is on track to meet or exceed all milestones under Output 1 for 2025-26.
The UNFPA Supplies Partnership Rapid Refresh
In April 2025, the UNFPA Supplies Partnership launched a Rapid Refresh (RR) of its operating model for the remainder of Phase III (2021-2030) in response to the shifting ODA context. This exercise aimed to accelerate progress towards increased domestic resource mobilisation (DRM), whereby partner country governments invest more domestic funding in commodities; support countries to transition out of Partnership support; and to ensure the sustainability of the Partnership in the new global funding context by optimising resource allocation.
Following an intensive, six-month design process, the revised programme model was unanimously endorsed by the Steering Committee (SC) in October 2025. Securing SC approval of this ambitious "high risk, high reward" redesign was essential but challenging, given the scale of change being proposed. The UK, as the largest donor to the Partnership, played a critical role to maintain momentum and ensure partner concerns were addressed, securing unanimous approval and safeguarding continued access to SRH supplies.
Key elements of the revised model include:
- A new country categorisation model that will enable the Partnership to tailor the programme “offer” more effectively to different countries, based on ability to pay.
- A new commodity allocation model to better align commodity allocations with actual need, minimising the need for reallocation and increasing incentives for DRM.
- A new transition model to accelerate progress towards DRM and sustainable country transition, with the goal of supporting 20 countries to sustainably transition away from commodity support by 2030.
The revised model aims to maximise programme impact and reduce commodity funding gaps by catalysing greater government contributions. In 2026 alone, the revised model could:
- Mobilise up to $45 million in domestic resources, compared with $11 million if the model were to remain unchanged.
- Cover a third of total need for SRH commodities in UNFPA Supplies countries, compared with a quarter of total need if the model were to remain unchanged.
Phased implementation of the revised model will begin in 2026. In preparation, the UNFPA Supplies Partnership has started intensive country engagement to begin socialising the key changes with government counterparts and implementing partners. A risk assessment will also be conducted before the end of December 2025 to gain a deeper understanding of the main risks that could impede successful implementation of the revised model in 2026. Key updates and proposed risk mitigation strategies will be discussed with members of the Finance and Risk Committee (FRC) and Strategy and Planning Committee (SPC) in Q1 2026.
SC members commended UNFPA for its governance of the Rapid Refresh process, noting its transparent, data-driven approach and consistent engagement with the SC and subcommittees. Based on this feedback, part 2 of the RR in 2026 – largely focused on redesigning the programme’s Health System Strengthening activities – will follow a similar governance process.
Progress against milestones
Since the launch of Phase III in 2021, the UNFPA Supplies Partnership has significantly improved its governance model, introducing an inclusive constituency-based Steering Committee and specialised subcommittees for deeper, technical engagement. The mid-term evaluation (MTE) validated these improvements, citing the new governance arrangements as a key driver of "enhanced transparency, accountability, and donor confidence". UNFPA have developed an action plan to take forward the key recommendations from the MTE.
As part of the relocation of UNFPA’s Programme Division, all 10 staff members of the UNFPA Supplies Partnership team are now based full-time in Nairobi, Kenya. Relocations took place between June and August 2025, and operations have returned to full capacity. This move has positioned staff closer to the field, where programme delivery takes place, improving real-time engagement and significantly reducing the time gap between headquarters and country operations.
UNFPA Supplies and Maternal and Newborn Health Fund (MNHF) teams have collaborated at country level to ensure that work planning, country allocations and demand forecasting are joined up across both family planning (FP) and MNH commodities. Teams work together on New and Lesser Used (NLU) product introductions such as such as Tranexamic acid (TXA) and Heat Stable Carbetocin (HSC), and comprehensive abortion care (CAC) and maternal health medicines are routinely tracked for availability through the Last Mile Assurance process. Targeted capacity building using the quantification capacity assessment tool, and follow-up deployment of master trainers has improved forecasting practices and enhanced incorporation of maternal health medicines in national supply plans.
Across 2024-25, UNFPA strengthened the in-country assessment (ICA) approach and completed ICAs in 39 UNFPA Supplies partner countries, exceeding the biennial coverage expectation of 36. Under the new approach, countries undergo an ICA approximately every 2 years, reducing operational burden and supporting higher-quality follow-up. As a result, 6 countries received an ICA in 2025, with coverage expected to stabilise in 2026. For all countries assessed, an action plan was developed and is being regularly monitored. To maintain visibility on supply chain performance, all UNFPA Supplies Partnership implementing partners continue to participate in the Quarterly Stock Review (QSR), which provides routine oversight of stock status at central warehouses and supports early identification and mitigation of risks. UNFPA also conducted targeted strengthening missions in 2025 to reinforce QSR processes, improve data quality and support Ministries of Health (MoHs) to take increased ownership of LMA; and conducted quarterly follow-up with countries. Recommendations from ICAs and QSRs were consolidated into countries’ annual Supply Chain Strengthening Plans, and data on LMA will inform the prioritisation of Health Systems Strengthening (HSS) interventions in 2026.
Some recommendations in ICA action plans, however – particularly those related to enhancing warehouse infrastructure (construction, renovation and equipment) – are beyond the control of UNFPA and/or exceed UNFPA's capacity for direct implementation. UNFPA’s Supply Chain Management Unit (SCMU) therefore works with implementing partners, such as the Ministry of Health (MoH), to advocate for government or other stakeholders to contribute to addressing these critical infrastructure improvements. Additionally, UNFPA began developing a new ICA self-assessment tool in 2025, to be launched in 2026. This lighter-touch tool will enable countries to conduct their own monitoring in non-ICA years, report findings to the LMA team, integrate results into annual planning, and strengthen downstream monitoring of supplies – enhancing national ownership and continuous oversight.
The UNFPA Supplies Partnership continues to drive impressive progress towards domestic resource mobilisation for SRH commodities. In 2024, governments across the programme’s 54 countries spent $52 million on contraceptives – the highest amount on record and a fivefold increase since 2020. The Compact and Match Fund have played a critical role in driving this positive trend by strengthening accountability and incentives for DRM. The Compact is an agreement signed by the Ministers of Health and Finance in partner countries in which they commit to gradually increasing their countries’ domestic budget allocations for contraceptives and maternal health commodities. These instruments have proven successful in increasing domestic financing for contraceptive commodities and are being revised and expanded as part of the ongoing Rapid Refresh to accelerate progress (see below). For the reporting year, all 41 required UNFPA Supplies Partnership countries have signed Compacts and have signed Annex A, reflecting sustained political will to DRM. As of 30 November 2025, 76% (31 of 41) of countries that signed Compacts have met minimum domestic financing requirements as outlined in their Compact agreement, exceeding the target of 72%. As of 12 December 2025, 24 countries have been awarded match funding in 2025, compared to just 14 countries in 2024, reflecting increasing government interest and progress towards domestic financing.
Alongside UNFPA’s work on DRM, UK investments and expertise are making tangible progress on shifting from aid dependency to stronger government ownership, even in fragile contexts. At the International Conference on Family Planning, the Democratic Republic of Congo pledged $5 million annually to procuring SRH commodities for four years: the first such commitment since 2021, and one secured through close collaboration between FCDO diplomats in-country and the central programme team.

Recommendations for the year ahead
- UNFPA revisit longer-term vision and strategy: As the Partnership transitions into implementation of the Rapid Refresh, UNFPA should begin recalibrating its global vision and strategy to reflect its move under the new model from funder to financier and global market shaper, and its efforts to sustainably build procurement capacity in-country.
- Shift from design to implementation with Rapid Refresh Phase 2: UNFPA to build on impressive success with design of new model and work closely with countries to monitor and manage risks of rolling out of new model.
- Continue strengthening GHI collaboration and alignment: UNFPA will identify a set of priority countries to focus alignment efforts – it is critical that these drive progress on in-country coordination mechanisms flexibly, driven by country context. This also needs to consider how to strengthen the role of civil society.
- Strengthen national health logistics systems to provide a more comprehensive picture on stockouts: While UNFPA has made good progress on last mile assurance, it should seek to strengthen national systems to provide a more comprehensive picture on stockouts by country and product in each partner country as the new Partnership model is implemented.

Progress on recommendations from Supplies PCR:
- Recommendation: Future programming should continue to prioritise domestic resource mobilisation and pivot efforts to the next phase, seeking to develop agreed transition pathways and a vision for long-term sustainability of SRH commodity financing via countries’ domestic health budgets.
- Response: The Rapid Refresh aims to accelerate progress towards DRM by scaling up catalytic funding models and supporting 20 countries to transition away from donor commodity support by 2030. In 2025, advocacy efforts regarding Domestic Resource Mobilisation (DRM) continued to accelerate across UNFPA Supplies countries. SMART Advocacy workshops and plans were implemented in 13 countries (Chad, Congo, Côte d’Ivoire, Ethiopia, The Gambia, Kenya, Madagascar, Mali, Mozambique, Nigeria, São Tomé and Príncipe, Sierra Leone, and Zimbabwe). DRM Guidelines and an Advocacy and Communications Toolkit were finalised. Scheduled for launch in Q1 2026, these resources will guide countries on effectively mobilising domestic resources by building on Public Financial Management principles and leveraging SMART Advocacy. A Global Health Initiatives (GHI) collaboration strategy was developed, focusing on sustainable financing and joint DRM efforts with the Global Financing Facility (GFF). Discussions are currently underway to align efforts across different incentive mechanisms in select priority countries, specifically Ethiopia, Mozambique, Nigeria, and Tanzania.

Output 2
Output Title	UNFPA Supplies procurement, TA and DRM initiatives increase the availability of reproductive health commodities in developing countries and represent strong VfM.
Output number:		2	Output score:	A
Weighting (%):		30	Weighting revised since last AR?	N/A

Briefly summarise progress to date against the programme outputs, and provide supporting narrative for the score.
Impact Indicators
Indicator(s)	Milestone(s) for achievement by end-March 2026 (Year 1)	Progress as at end-Nov 2025 (note all data is interim and will be finalised in 2026)
2.1 Cost of contraceptives procurement per total Couple Years of Protection (CYPs)	$2.68	$2.49 / On track to exceed full year target.
2.2 Number of countries where 75% of UNFPA Supplies Partnership commodity orders are delivered on time in country	48	48 / Full year target met.
2.3 Number of countries where 75% of UNFPA Supplies Partnership commodity orders are delivered in agreed quantities by the supplier	45	46 / Full year target exceeded.
2.4 Percentage of countries with no Product Loss Due to Expiration	37%	57% / Note: The current figure reflects data from Q1-Q3 only. / On track.
2.5 UNFPA Supplies Partnership implementing countries implement strategies to strengthen humanitarian preparedness and resilience	80%	30% (8 out of 27) of UNFPA Supplies Partnership countries who were classified as having 'high' or 'very high INFORM Risk Index have implemented interventions to strengthen humanitarian preparedness and resilience. / Target not yet on track but may be met.
2.6 Number of countries procuring Comprehensive Abortion Care (CAC) supplies (disaggregated by product type)	Combipack – 13 countries / MVA – 14 countries	14 countries procured the combipack. / 14 countries procured MVA kits. / Full year target met.
2.7 Existence of functional alignment between UNFPA Supplies Partnership Programme, Supply Chain Management Unit (SCMU) and Humanitarian Response Division (HRD) to ensure uninterrupted availability of life-saving SRH commodities	UNFPA Supplies has in place a Management response to midterm evaluation recommendation that commits to strengthening coordination with HRD and SCMU	The Management response to the midterm evaluation of UNFPA Supplies, which was finalised in November 2025, specifically commits to strengthen collaboration and coordination with HRD and SCMU. These are contained in Management Response Action interventions 3.11 and 3.12. / Full year target met.

Supporting narrative
Overall, activity under Output 2 is on a positive trajectory with all but one target met, exceeded, or on track to be met or exceeded.
Cost per couple-year of protection (CYP) for all commodities procured through the UNFPA Supplies Partnership stands at $2.49, exceeding the target of below $2.68. With funding from the United States withdrawn, UNFPA Supplies stepped up to fill gaps in the commodity ecosystem particularly on long-acting methods (especially IUDs); and the substantial drop in CYP cost can be attributed to this. This 2025 figure is based on preliminary data, and will be updated and cleaned at the end of the year.
Commodity delivery targets were met or exceeded across the Partnership: in 48 of the 54 programme countries, 85% of commodity orders were delivered on time, while in 46 countries 83% of commodity orders were delivered in agreed quantities.
While orders were delivered fully and on time in most countries, however, challenges in others included manufacturer delays (long lead time) for supply-constrained products, in-country security situations, and warehouse quality assurance challenges. When commitments to the National Supply Plan from other stakeholders were delayed or did not materialise due to the impact of US government’s funding withdrawal, the Partnership stepped in to reduce the funding gaps. UNFPA also allowed ‘frontloading’ procurement of commodities at risk of stock-out, and facilitated timely second-tranche procurement in Q2-Q3. These efforts combined to improve supply planning, ensure continuous supply and mitigate the risk of stockouts or shortages.
In 2025, 31 out of 54 UNFPA Supplies Partnership countries (57%) reported no expiries at the central level in the Quarterly Stock Review (QSR), exceeding the 2025 target of 39%[7]. The QSR captures all centrally held commodities, regardless of funding source, and not only UNFPA-donated stock. This means the percentage of countries with no expiries attributable to UNFPA-supplied commodities would be even higher. For example, expiries of combined oral contraceptives reported in Ghana in Q2 resulted from a short-dated donation from another partner, not from the Supplies Partnership. In countries where expiries did occur, losses were primarily linked to broader supply chain challenges such as over-procurement and excess stock driven by forecasting and supply planning gaps.
[7] As this result reflects only the first three quarters, final performance may change once Q4 data is incorporated.
The Partnership also met its milestones on comprehensive abortion care (CAC), with 14 countries supported to procure the MA Combipack (Benin, Bolivia, Cambodia, Comoros, Ethiopia, Kenya, Lao PDR, Liberia, Mozambique, Nepal, Rwanda, Sierra Leone, Uganda and Zambia) and 14 to procure MVA kits (Burundi, Ethiopia, Eswatini, Kenya, Lao People's Democratic Republic, Malawi, Namibia, Nepal, Pakistan, Rwanda, South Sudan, Uganda, Zambia and Zimbabwe).
Following the mid-term evaluation (MTE) of the UNFPA Supplies Partnership, the Partnership team have committed to a series of actions to strengthen collaboration and coordination with UNFPA’s Humanitarian Response Division (HRD) and Supply Chain Management Unit (SCMU) (indicator 2.7). UNFPA will establish a joint internal coordination mechanism with HRD and SCMU to improve SRHR in crisis settings, including by improving preparedness efforts, closer alignment on supply chain and procurement strategies, and ensuring access to Inter-Agency Reproductive Health (IARH) kits in crisis settings. As part of phase 2 of the Rapid Refresh, focusing on Health Systems Strengthening (HSS), UNFPA will also review HSS in countries facing humanitarian crises and/or operating within the humanitarian–development–peace continuum. This will include supporting the development of integrated national strategies for procurement and distribution, supporting capacity building for last-mile assurance, and enhancing humanitarian preparedness and contingency planning.
One indicator is not yet on track for 2025. Two thirds of countries in the UNFPA Supplies Partnership are in humanitarian and fragile situations. In 2025, only 30% (8 of 27) of high-risk countries in humanitarian and fragile contexts had integrated humanitarian preparedness interventions into their applications for HSS funding. The UNFPA Supplies Partnership will conduct a Humanitarian Review in Q1 of 2026, to begin developing tailored approaches to ensuring humanitarian preparedness and response capacity.

Recommendations for the year ahead
- Review partnership’s approach to Health System Strengthening (HSS) and Humanitarian support: These reviews offer a critical opportunity for UNFPA to be clear about its added value on HSS and the capacity it needs to deliver the refresh. Humanitarian contexts will become a greater focus of the partnership as countries transition, and this review should look at how the revised model will operate in humanitarian contexts to enable a more nuanced approach.
- Review output indicator 2.4: Revisit targets to ensure that they are sufficiently ambitious and consider whether it would be possible to split targets for products procured through UNFPA supplies (which should have a very low threshold), vs. broader expiries.
- Update results framework following Rapid Refresh: Revisit results framework based on rapid refresh and following upcoming reviews on HSS and humanitarian. For example, UNFPA could fill an important gap on supporting the development of National Supply Plans following US withdrawal. NSPs are the most important tool to accurately quantify demand, avoid mis-ordering and advocate efficiently for financing gaps. This would require quite a substantial reorganisation of expertise sending people from SCMU and regional hubs to countries on a roving basis to support the process.

Progress on recommendations from Supplies PCR
- Recommendation: Maximise opportunities in future programming to support consistent and predictable funding to safeguard sustained delivery of commodities and minimise cliff edges in provision of supplies for those who need them most.
- Response: UNFPA Supplies Partnership mobilised a total of $206.2 million (cash and in-kind contribution) from 18 donors in 2025, with new agreements and increases from Gates Foundation, CIFF, Portugal, Germany, Norway, Ireland, Pfizer, and Belgium. In light of ODA reductions, UNFPA is also intensifying its engagement with philanthropies and net worth individuals to attract new donors to the UNFPA Supplies Partnership. In Q4 2025 a $2 million contribution was finalised with a high net worth individual, and discussions are underway with a number of other donor-advised funds. UNFPA has also taken a number of steps to mitigate the impact of donor funding reductions on commodity availability at country level. Critically, when commitments to the National Supply Plan from other stakeholders were delayed or did not materialise, the Partnership stepped in to avert stockouts.

- Recommendation: Future FCDO programming for SRH commodity access should seek further collaboration between UNFPA Supplies, CHAI and wider partners to support effective product introduction and leverage the UNFPA Supplies new and lesser used product fund to maximum impact.
- Response: Over the course of 2025, UNFPA has deepened its partnership with CHAI in a variety of areas, including the Rapid Refresh and new and lesser-used product introduction.

Output 3
Output Title	Accelerating sustainable country transition and access to life-saving SRHR commodities.
Output number:		3	Output score:	A
Weighting (%):		40	Weighting revised since last AR?	N/A

Impact Indicators

Indicator(s)	Milestone(s) for achievement by end-March 2026 (Year 1)	Progress achieved by end-Sept 2025 (2 quarters of implementation)
3.1 Number of critical commodities and devices INTRODUCED in priority countries	10	10 completed (caffeine citrate (CC), drapes, Heat Stable Carbetocin (HSC) in Zambia; Tranexamic Acid (TXA), HSC in Uganda; Multiple Micronutrient Supplements (MMS) in Nigeria; Drapes, HSC, TXA in Ghana; TXA in Lesotho. / Full year target met.
3.2 Number of critical commodities and devices reaching market MATURITY in priority countries	5	7 reached maturity to date (CC, MMS in Rwanda; CC, HSC, drapes, TXA in Lesotho; MMS in Nigeria) with training delivered to >50% of target facilities. Full year target exceeded.
3.3 Improved efficiency in product introductions	2 efficiency case studies produced	Potential efficiency cases studies identified. Confirmation of countries, topics and methodologies in January. On track.
3.4 Number of target quality-assured products with at least a 20% price reduction achieved through price negotiation	1 price deal achieved	Met for 3 products (drapes, CC & MMS) from individual suppliers. Work ongoing to widen to more suppliers & geographies & further reduce prices. Full year target met.
3.5 Registration footprint for targeted quality-assured SRMNH products in the 10 CHOICES Accelerator countries	At least 8/10 countries with a quality assured CC product having a dossier submitted for registration	At least 1 QA CC product is now registered in 7/10 countries. Dossier in Nigeria prepared and awaiting submission date. / On track.
3.6 Number of product introductions or expansions with COF support, aligned with global market strategies and government priorities	25 additional product introductions or expansions supported	17 COF grants (for H-IUD, MA Combipacks, and DMPA-SC) were approved in 10 countries. / On track.
3.7 Enhanced market visibility and access to learning/knowledge for procurers, governments, donors, and suppliers	3 market knowledge and learning products delivered and priorities for refreshed global enabler work defined	FP Market Memos published in June and November. FP Market Report published in December. Total market reports 3. / Full year target met.

Supporting narrative
The CHOICES approach to commodity access has government ownership and sustainability at its heart and seeks to ensure that:
- SRH financing and services are ultimately integrated into country systems, policies and plans.
- Countries have the capacity to lead and manage new product introduction and ongoing access.
- Global markets can reliably provide the affordable, high-quality products that countries need.
- The global community provides the support, such as knowledge, guidance and programmatic funding, that countries need to lead their own product access.
The CHOICES Accelerator is a new technical assistance programme, implemented by CHAI, which increases the sustainability, value for money and impact of FCDO’s funding to UNFPA Supplies within the CHOICES programme. More widely it also ‘accelerates’ the impact of FCDO’s wider SRHR engagement, as well as investments in Sexual, Reproductive, Maternal and Newborn Health (SRMNH) commodities by other donors and partner governments.
CHAI global and country teams together engage across three strategic areas to deliver the Accelerator:
Building country stewardship: Working with governments to lead and manage multiple new product introductions in 10 focal countries (Ethiopia, Ghana, Kenya, Lesotho, Malawi, Nigeria, Rwanda, Senegal, Uganda, Zambia) as well as strengthening commodity access systems (e.g. supply chains, data, financing, procurement and strategic planning).
Shaping Markets: Enhancing the reliable supply of affordable, high-quality products, including contraceptives, medical abortion (MA) combipacks and high opportunity Maternal and Newborn Health (MNH) products, such as postpartum haemorrhage commodities, multiple micronutrient supplements (MMS) and critical neonatal health commodities. The market shaping approach reflects the evolving funding context, focusing on opportunities to support regional supply, procurement and financing.
Strengthening global enablers: Effective country stewardship still depends on a set of critical foundational global functions. The Accelerator priorities are guided by ongoing dialogue in the SRMNH community but include flexible programmatic funding for countries for product introduction and access activities (through evolution of the Catalytic Opportunities Fund (COF)) and knowledge generation and sharing.
The Accelerator takes a comprehensive, integrated and systems-oriented approach which derives on the successes of, and the learnings from, the Best Practices Grant (BPG) which was funded within the RH Supplies program from 2019-2025. This includes integrating the findings and recommendations from the independent evaluation of the BPG. The programme’s strong relationships with governments and flexibility to respond to emerging opportunities mean it has been well placed to pivot in response to changes in the wider ODA context.

The design of the CHOICES Accelerator is founded on the clear evidence from BPG that complementary market shaping and access interventions can enhance VfM, sustainability and impact. The Accelerator expands the scope of the BPG across multiple dimensions. As examples:
At country-level, BPG support was provided to four countries (Kenya, Nigeria, Tanzania and Zambia). The Accelerator supports 10.
- In terms of products, CHAI led targeted access initiatives to scale access to the hormonal IUD and MA combipacks. The Accelerator has expanded to support a range of critical MNH products, including the set of products essential to the effective management of postpartum haemorrhage (the leading cause of maternal death in many countries)
- The BPG strengthened capacity primarily for product introduction. The Accelerator is broadening its systems strengthening approach to support the key elements of commodity security and access, including sustainable financing.
The output targets reflect the three strategic areas outlined above. Of the 7 output indicators, 4 have already been met (and further progress is anticipated by the end of the financial year). The remaining 3 are on track to be met by end-March 2026.
Overall, in its first 6 months of implementation, the Accelerator has ‘accelerated’ FCDO’s support to UNFPA Supplies, and wider SRHR engagement, in multiple ways:
- Faster introduction and scale-up of life-saving products for women’s and newborn health: 10 introductions of critical SRMNH products completed and access to 7 products scaled up in first 6 months of programme. Full year targets already met with more to be finalised in remainder of year.
- Successful partner country transition towards leadership and sustainability: Using government-led model of product introduction to build systems (e.g., support to market stewardship groups in 8 countries, strengthening supply chains, forecasting, information systems, financing, training, clinical practices across all countries)
- Expanded focus on high-impact new technologies and approaches for MNH: Going beyond family planning to rollout products and approaches critical to postpartum haemorrhage (PPH) (drapes and tranexamic acid), premature newborns (caffeine citrate) and nutrition in pregnancy (multiple micronutrient supplements) ​
- Reduced prices and stronger quality and supply for life-saving products for women’s and newborn health: Securing prices reduction of more than 20% for critical products such as caffeine citrate, drapes and MMS. Supporting regional manufacturers to strengthen quality and expand. Strengthening supply platforms to serve governments and private channels ​
- Supporting delivery of country commitments to strengthen the equity and inclusion of their SRHR programmes: Supporting governments across all CHOICES countries: e.g. working in Malawi to actively manage commodity stock to ensure availability in hard-to-reach regions; supporting data-led approach to better reach adolescents with SRH services in Rwanda​.
- Greater coherence in efforts to build the effective global support that countries need: Managing a global mechanism (the COF) for product introduction (17 new grants in Q3 for 3 products across 10 countries); providing technical advice to critical global reforms (UNFPA Supplies Rapid Refresh); broad-based knowledge & learning activities.
  SPOTLIGHT: Partnering for safer childbirth across Africa. Every year, thousands of mothers in sub-Saharan Africa die from heavy bleeding after childbirth—a tragedy that can happen in just two hours if help doesn’t come fast. The UK funded research into a first response bundle (E-MOTIVE) that includes a simple blood measurement tool for early detection and proven treatments that cut severe bleeding by almost two thirds. The UK is now working with partner governments in Africa through the CHOICES Accelerator to lead the roll out of this bundle in their own countries to save more lives. In Lesotho the government has rolled out the bundle in almost 90% of hospitals and Rwanda has nearly ended shortages of vital medicines. The Ethiopian government has increased detection of severe bleeding by two thirds resulting in an 80% reduction in deaths of mothers. The UK is working with partner governments to strengthen their own health systems and give mothers a safer future.

Recommendations for the year ahead
- Balance opportunities to widen the scope of MNH products with constrained financing landscape: Recognising the success on product introduction and ongoing momentum within partner countries, work with CHAI to balance opportunities to widen the scope of MNH product engagement: such as nutrition in pregnancy and newborn survival, with funding levels.
- Explore regional manufacturing and innovative partnerships to drive further price reduction: Where opportunities remain for further price reductions (e.g. TXA, drapes), particularly with regional manufacturers, efforts should be intensified and innovative partnerships considered. FCDO to bring in colleagues working on regional manufacturing and innovative financing. For products where clearer strategic market approaches would add value, greater coordination of partners should be considered.
- Strengthen strategic collaboration with COF co-funders: Build on recent dialogue between FCDO and other COF funders to support discussion of sustainable future models for programmatic support. Explore opportunities for UK to showcase COF and expand donors as part of our work to strengthen alignment within the sector.
- Deepen collaboration with UNFPA Supplies: Building on progress made to date – priorities include strengthened in-country collaboration and support on country transition. FCDO, UNFPA and CHAI to meet at working level to establish strategic priorities and oversee progress on collaboration.

Progress on recommendations from RH Supplies PCR
Under Output 2 of RH Supplies:
- Recommendation: Maximise opportunities in future programming to support consistent and predictable funding to safeguard sustained delivery of commodities and minimise cliff edges in provision of supplies for those who need them most.
- Response: The Accelerator is pivoting strongly to greater emphasis on sustainable financing – reflecting the worsening SRHR donor funding context and the PCR recommendations. Intensified efforts are recommended over the coming year. CHAI country teams have supported countries to assess financing gaps and identify alternative funding or increase their own funding. Extensive technical support has been provided to the UNFPA Supplies Rapid Refresh process in 2025, which strengthens the emphasis on domestic commodity funding. CHAI is working with country teams to increase sustainable financing activities – and additional capacity has been brought into the team to achieve this. Three market reports focused on funding have been published.

- Recommendation: Future FCDO programming for SRH commodity access should seek to further collaboration between UNFPA Supplies, CHAI and wider partners to support effective product introduction and leverage the UNFPA Supplies new and lesser used product fund to maximum impact.
- Response: CHAI has worked closely with UNFPA Supplies on the Rapid Refresh, and other areas such as medium-term commodity procurement forecasts, and signed an MOU with UNFPA laying out areas of collaboration. A key recommendation is to build momentum behind greater country-level CHAI-UNFPA collaboration.
Under Output 3 of RH Supplies:
- Recommendation: Build upon success of Best Practices to develop an approach that is systems-oriented – delivering critical cross-cutting market functions that build a durable ecosystem. At the heart of this approach should be the building of national capacity to establish and systematise product introduction processes and market access activities.
- Response: The Accelerator is designed to take a transformative systems approach with sustainability at its centre. This is reflected in the systems-led approach to product introduction at the country-level. In 2025, with global health funding under severe pressure, the sustainability focus has been intensified with increased attention to sustainable financing. The programme also takes a systems approach to strengthening the global ecosystem. A recommendation is to support partner convening on the future of the commodity access ecosystem in the coming year – and engage pro-actively on new initiatives such as the GFF commodity window.

- Recommendation: Include an explicit focus on how to strengthen equity and inclusion; mainstreaming equity in market interventions and access strategies within countries; and reflecting equity considerations in product choice.
- Response: Equity is mainstreamed at all levels of the programme – including in product choice. CHAI country teams were encouraged to strengthen equity dimensions in their work plans and case studies from countries have been gathered.

- Recommendation: Deepen and create more formal mechanisms for collaboration between CHAI and UNFPA to maximise synergies between the programmes – including a programme level steering board.
- Response: The relationship between CHAI and UNFPA has been transformed through collaboration on the Rapid Refresh – and will continue through the implementation work (Rapid Refresh Part II into 2026). UNFPA continues to request additional CHAI input and support on commodity access issues. A key recommendation is to build momentum behind greater country-level CHAI-UNFPA collaboration (also noted above).