## Annual Review
## Open Societies Enabling Fund (OSEF) FY 25/26

Title: Open Societies Enabling Fund
Programme Value £ (full life): £4.8m		Review date: Nov 2025
Programme Code: 400124	AMP start date: 09/01/2024	AMP end date: 31/03/2030

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	B
Overall programme risk rating	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004817.odt
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The Open Societies Enabling Fund (OSEF) is the British Embassy Jakarta’s flagship programme for promoting UK values and interests through supporting Indonesia’s democratic resilience and human rights. It aims to help Indonesia remain a transparent, healthy democracy with a vibrant civil society and strong protections for civic freedoms. The programme responds to a well-documented trend of shrinking civic space and increased vulnerability of human rights defenders (HRDs) and minorities, particularly during politically charged periods such as the 2024 national and regional elections and the subsequent transition.
Purpose and Strategic Rationale
OSEF was conceived as a flexible Official Development Assistance (ODA) instrument to deliver key outcomes of the UK–Indonesia Partnership Roadmap and the Embassy’s Country Business Plan. At the outset OSEF was intended to work on protecting civic freedoms and human rights defenders, strengthening the rule of law, promoting democratic participation and electoral integrity, and building public resilience against narratives that undermine open society values. This intent remains, although the Roadmap is now superseded by the UK-Indonesia Strategic Partnership.
The programme aligns with the UK Indo-Pacific Strategy, which prioritises democratic resilience, information integrity, and countering malign influence. It also reflects lessons from the FCDO Centre of Expertise for Politics, Governance, and Rights, which advocates long-term, cross-cutting approaches to democratic governance.
OSEF operates through accountable grants to Indonesian civil society organisations (CSOs), complemented by embassy-led engagement. The log-frame approved for this review was structured to have 3 outcome areas, which for the purposes of a practical review will serve as the reviewed outputs. Under each are a set of indicators and success criteria around which evidence has been collected from project partners. The three outputs are:
1. Human rights in particular civic freedoms are accepted as the normative foundation of Indonesia's democratic governance evidenced by protective measures available for human rights defenders.
2. The legal regime in Indonesia supports and protects clean and democratic governance, rule of law and civic freedom including through promoting fair and transparent law making processes, inclusive pubic participation, and law enforcement processes that abide to prevailing international human rights standards.
3. Indonesia has a robust democracy that includes a representative parliamentary, functional political parties, and clean electoral system that allows the fullest extent of public participation.
The programme began as a £600,000 initiative for FY 2023–25 but was expanded in August 2024 to a £4.8 million, multi-year programme running until March 2030, with an annual budget of £750,000. The reduction in ODA has resulted in key changes to this programme. An ODA pause began 6 months after the uplift was approved, followed by a reduction in allocation budget for FY2025/26. The Annual Review therefore reflects a year of transition and disrupted delivery and makes the case for formalising adaptive management and a consolidated issue-based approach in future. It should be noted that in the last quarter of FY 2024/25 the programme also received additional £ 70,000 Modern Slavery Fund (MSF) which was used for additional activities for the ENABLE Project implemented by LBH Masyarakat.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

In this context, OSEF paused ODA payments from March to July and was redesigned in July to offer more flexibility, fewer direct partners, and a reduced annual ODA envelope. The process of this redesign is assessed as a fourth output in this annual review.

The programme responds to ODA changes through a redesign, and remobilisation.

Summary supporting narrative for the overall score in this review

The year under review saw significant changes in external context. The first year of the Prabowo administration has seen a reallocation of the national budget, with funds redirected away from local government and notable impacts on human rights institutions. These shifts coincided with rapid progress on the criminal procedure code reform. These developments have created a dynamic and uncertain environment for policy implementation.
On delivery in this context, OSEF has made solid progress at output level, particularly on:
1. Innovative public education and media measures around inclusion and elections led by Konde (guidelines, trainings, fellowships, podcasts, videos, a short documentary, five public screenings and multiple social media activations);
2. HRDs capacity building, mentoring and network consolidation led by KAPAL Perempuan alongside convening with national rights institutions;
3. Community based mediation and interfaith dialogue sessions in West Sumatra, Banten and North Sulawesi led by Center for the Study of Religion and Democracy (PUSAD), with Memorandum of Understandings (MoUs) to sustain collaboration;
4. legislative advocacy by Community Legal Aid Institute (LBHM)/Institute for Criminal Justice Reform (ICJR)/Indonesia Ocean Justice Initiative (IOJI) on criminal procedure reform and migrant worker protection;
5. Network for Democracy and Electoral Integrity’s (NETGRIT) crowdsourced electoral vote tally platform that improved transparency and generated actionable policy recommendations after the 2024 Regional Election (Pilkada) and subsequent repeat election (Pemungutan Suara Ulang/PSU) cases.
While the programme delivered strong advocacy and capacity-building outputs, several weaknesses remain. Policy-level change is still at an early stage: partners report lobbying successes and verbal commitments (e.g., Nasdem Party and the National Mandate Party (PAN) pledging to support civil society’s Draft of the Indonesian Criminal Procedure Code (RKUHAP) recommendations), and MoUs with National Human Rights Commission (Komnas HAM) and National Commission on Violence Against Women (Komnas Perempuan) on HRDs protection, but these are not yet formalised into regulations or enforceable Standard Operating Procedures (SOPs).
Key success criteria are only partially met, partly because the ODA pause impacted activities across the programme (assessed below under each output), in particular the work of Indonesia Legal Aid Foundation (YLBHI). Delivery was constrained by time and budget, but also by procurement, logistical, and disbursement challenges.
Short project windows and late fund transfers also caused partners to scale back or rush activities, with some relying on secondary data or revising timelines to meet milestones. These factors underscore the need for longer implementation cycles, clearer policy milestones, and stronger verification of institutional changes.
Overall rating: B (outputs moderately did not meet expectation). This reflects good breadth and energy across outputs, tempered by incomplete evidence against several success criteria and limited demonstration, thus far, of policy adoption or systemic practice change. Projects delivered significant outputs despite the ODA pause, including verification of 865,000 polling station forms, mobilisation of 10,000 volunteers influencing electoral reform debates, gender-inclusive election reporting guidelines, HRD protection campaigns, and establishment of local mediation bodies in three provinces. What wasn’t achieved includes planned systemic changes – such as operational HRD protection posts, formal regulatory reforms, and full consolidation of CSO networks – which were delayed or incomplete due to compressed timelines, leadership transitions, and ODA uncertainty, limiting progress toward outcome-level results.
Major lessons and recommendations for the year ahead

Recommendations from last year were to hold additional discussions on women’s empowerment, election reform, and lesson learning, as well as to write a report of achievements, appoint a single implementing partner, and amend the theory of change. Discussions on election reform and lesson learning were held, while women’s empowerment remains to follow up. A new structure was approved with 3 top tier partners rather than 1, and the theory of change is discussed below.
This year demonstrated strong outputs but exposed structural weaknesses: fragmented delivery, short project windows, and limited agility. Policy influence remains nascent, and evidence gaps persist. These lessons further justify the redesign: fewer partners and an issue-based approach that integrates human rights, rule of law, and democratic governance. This model will simplify management, improve flexibility under ODA constraints, and enable partners to collaborate strategically for greater collective impact.
1. Advocacy needs time and continuity
Partners like LBHM flagged that three-month windows were insufficient for deep research and sustained lobbying. They resorted to secondary data and compressed consultations, limiting influence on formal deliberations. Short-term grants cannot deliver systemic policy change; advocacy requires multi-phase engagement and predictable timelines.

2. Fragmented delivery limits collective impact
Each partner worked in isolation on niche issues (HRDs protection, Criminal Code (KUHP) reform, election monitoring, media inclusion). While outputs were strong individually, there was little cross-project synergy—e.g., election integrity work (NETGRIT) and media inclusion (Konde) could have amplified each other but did not. This reduced the programme’s ability to shape a coherent democratic governance agenda.

3. Evidence gaps weaken credibility and learning
Partners often reported achievements through self-reported metrics (reach, views, participant numbers) without independent verification. Policy-level progress was framed as MoUs or verbal commitments, not enforceable instruments. Credible measurement of policy impact will need more advanced tools within the programme to measure this, rather than rely out output metrics and assumptions of change.

4. Administrative burden and capacity constraints
Managing multiple small grants placed a heavy load on Embassy staff for due diligence and compliance. Some CSOs lacked experience with international donor standards, requiring intensive support. This diverted time from strategic engagement and learning, suggesting a more efficient delivery model is needed.

5. Political timing and ODA volatility demand agility
Disbursement delays and election-year dynamics forced partners to revise timelines and outputs. Some activities were rushed or scaled back, reducing quality and sustainability. The programme needs mechanisms to pivot quickly when political windows open or budgets shift.

Recommendations for the Year Ahead
Recommendation	Responsible	Support	Timeline
Adopt an issue-based, integrated approach Structure the programme around thematic clusters (e.g., Democratic Governance, Rule of Law, Human Rights) rather than isolated projects. Encourage partners to collaborate under shared workstreams, producing joint outputs that amplify collective influence. Recognising that this model takes extra expertise and capacity from FCDO, regular support from a regional Senior Governance Advisor needs to be agreed.	SRO	SGA, PRO, programme team	Ongoing
Anticipate political windows and ODA fluctuations by managing flexibly and adaptively / Embed adaptive management and political responsiveness into programme design. Consider project management approaches that allow for a quick pivot when political windows open or close. This means workplans that allow activities to start, stop or scale up/down without lengthy approvals, rapid decision-making protocols, and short feedback loops between Embassy, lead implementers, and partners to test, learn, and adapt interventions iteratively rather than locking into rigid plans.	PRO	SRO, SGA, programme team	Ongoing
Strengthen evidence and learning systems Introduce joint MEL tools to capture cross-project impact and feed lessons into diplomatic engagement. This should include a value for money framework that allows for credible monitoring.	MEL officer	SRO, PRO, SGA, programme team	Ongoing
Develop a clear theory of change and log-frame for the revised OSEF design / Write down the theories of how change happens and identify the causal pathways and attribution routes. This should include any key assumptions. Also create a new log-frame that captures the structure and activities of the issue-based design and new partners.	SRO, PRO	SGA, programme team	April 2026
Strengthen risk management / For the coming year, the OSEF team should embed risk awareness and mitigation at every stage of delivery, ensuring oversight through regular management meetings and transparent reporting. With the new issue-based approach and sub-granting, full visibility of activities and political risks must be maintained.	PRO	SRO, SGA, programme team	April 2026 then ongoing

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

OSEF was launched to counter Indonesia’s shrinking civic space ahead of the 2024 elections. The original theory of change aimed to help civil society influence policy so that laws and their implementation uphold human rights, strengthen protection for minorities, and ensure HRDs can work safely. It also provided agile funding and capacity-building to civil society partners themselves to strengthen the sector’s resilience. The theory rested on assumptions that:
- Indonesia continues to enjoy an active and dedicated civil society sector;
- Stronger personal and institutional networks can give protection to minorities;
- There are reform-minded government actors;
- Partners are willing to work with the embassy on these issues.
Following the 2024 elections, an FCDO democratic governance diagnostic confirmed worsening governance trends—shrinking civic space, rising corruption, and reconcentration of power—and recommended a new, more strategic, politically informed approach. It also observed that civil society actors were often fragmented and disunited, which diluted their impact. In response, a business case amendment (August 2024) extended OSEF to 2030 and broadened its scope from civic freedoms to democratic resilience. The longer-term focus was key – emphasising the need for deep partnerships, systems thinking, and coalition-building rather than tactical activity. The team planned to shift to fewer partners (ideally one lead implementer) and recruit additional staff to plug the work more closely into the wider political team.

A transitional log-frame was created to account for the ongoing grants and projects that were being implemented while this change happened. In practice, the ODA pause and leadership changes for OSEF mean that this transition is still ongoing, and the transitional log-frame covers most activity in the review period.

The new log-frame had 3 outcome statements that, for practical purposes, have been treated as the outputs of this Annual Review. The reason for making this change is that assessing 10x output statements would have meant the review provides tactical rather than strategic insights into the programme – the simpler format means that reviewers can engage meaningfully in the theory of change and overall programme design and purpose. The detailed review of outputs below is based on the following interpretation of the log-frame:
- The impact statement is treated as the outcome
- The 3x outcome statements are treated as outputs
- The 10x output statements are treated as output indicators
- Indicators and sub-indicators are referred to throughout as success criteria and milestones
This has been supplemented by an additional output to track progress on programme delivery. The theory of change guiding this review is therefore:

Outcome:
Supporting Indonesia as a transparent, healthy democracy with a vibrant and protected civil society and strong protections for human rights.

Outputs:
1. Human rights, particularly civic freedoms, are accepted as the normative foundation of Indonesia's democratic governance, evidenced by protective measures available for human rights defenders.
2. The legal regime in Indonesia supports and protects clean and democratic governance, the rule of law, and civic freedom, including by promoting fair and transparent law-making processes, inclusive public participation, and law enforcement processes that adhere to prevailing international human rights standards.
3. Indonesia has a robust democracy that includes a representative parliament, functional political parties, and a clean electoral system that enables the fullest extent of public participation.
4. The programme responds to ODA changes through a redesign, and remobilisation.
Between January and April 2025, the OSEF team began redesigning the programme to reflect lessons from the Annual Review and prepare for uncertainty following the ODA pause. The redesign responds to Indonesia’s political dynamics, where unprecedented power consolidation has weakened opposition and increased governance risks. It maintains three core areas for action: democratic resilience, human rights, and rule of law. Each reflects the external context – democratic resilience emerging as a core concern following the 2024 election, human rights rising as a focus of civil society action (especially in relation to Papua), and rule of law as a locus of advocacy in response to legislative proposals on Indonesia’s criminal code and criminal procedure code.

The preferred delivery approach was to select a small number of tier 1 partners, which allows for an issue-based programme model that can accommodate alternative timelines and budgets. The key features of this redesign are as follows:

At the time of this review, the programme has recently completed the move to this model. OSEF has now appointed the Westminster Foundation for Democracy, Humanis Foundation, and YLBHI as the three component partners. Success in the new model will require upskilling on all sides on the Issue-Based Programming approach and intensive efforts in the early months to realise the benefits of this way of working. Practically, a new log-frame and theory of change will be required in order to allow proper monitoring of results in the next year.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This review period was intended as a transition toward a streamlined, longer-term approach. The redesign had to balance ambitions for sustainable change with uncertainty following the ODA pause. Despite these constraints, legacy projects delivered notable results: verification of over 865,000 polling station forms and mobilisation of 10,000 volunteers, which strengthened public trust and informed electoral reform debates. Other achievements include campaigns promoting gender-sensitive election reporting, policy briefs on HRDs protection, and the creation of local mediation bodies in three provinces. The redesign process itself—culminating in the selection of lead partners through a limited tender—positions the programme for more strategic engagement with government and stronger civil society coalitions.

Challenges persisted. Coordinating diverse partners while closing legacy projects added complexity, compounded by leadership changes, reduced budgets, and uncertainty over future ODA. These factors slowed implementation, particularly for projects launched late in the period.

In the year ahead, OSEF will pivot to an issue-based model with simplified contracting and joint planning around priority themes. This approach aims to deliver fewer, more strategic interventions that can achieve outcome-level results and provide a platform for diplomatic follow-up if funding ends early. The redesign and recommendations in this review set the foundation for that shift.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

OSEF remains a key part of the UK portfolio in Indonesia. As negotiations proceed towards a bilateral Strategic Dialogue on Human Rights, these topics remain essential topics for UK diplomacy. In the FCDO, ministers continue to signal the importance of these issues, as indicated by Lord Collins’ speech at King Charles Street in December 2024, setting out that human rights, rule of law and democratic governance are not just abstract values, but powerful enablers for the key missions of this government. The relevance increases as the UK takes on the co-chair role of the Open Government Partnership for 2026-27.

For 2026 and onwards, UK-Indonesia relations will be defined by a new Strategic Partnership, which has been under negotiation through 2025. Within the 4 pillars of this Partnership, OSEF helps deliver progress on People and Society. Democracy and human rights are explicitly referenced in this Partnership as an area of cooperation.

The UK’s wider portfolio in Indonesia drives forward growth and sustainability priorities that are necessarily underpinned by rights and governance standards. As new trade deals emerge and markets for sustainable commodities and carbon credits grow, scrutiny on rights and governance is likely to shape outcomes – whether through public pressure or through formal mechanisms such as the Equator Principles. Accession discussions to the Organisation for Economic Co-operation and Development (OECD) and Comprehensive and Progressive Agreement for Trans-Pacific Partnership (CPTPP) will bring issues of standards and governance to the fore. OSEF provides the British Embassy with key insights into the political economy as well as tools to make a positive difference.

Going forward, the programme’s next iteration will provide tools and evidence to influence governance and protect civic space.
Despite its operational challenges, OSEF has delivered impressive work in difficult areas – a testament to the dedicated teams and organisations that have been part of it. With a streamlined model and clearer focus on issues, OSEF is well positioned for 2026.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Human rights in particular civic freedoms are accepted as the normative foundation of Indonesia's democratic governance evidenced by protective measures available for human rights defenders.
Output number:		1	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Innovative measures, campaigns, studies, and guidelines are implemented by select media to champion human rights including for vulnerable minorities.	1.1.a. One documentary to mobilize support for women human rights defenders (Kapal Perempuan) / 1.1.b. Capacity building of HRDs (KAPAL Perempuan) / 1.1.c. A mentoring plan for alumni of the training for marginalised HRDs (Kapal Perempuan) / 1.1.d. 10 short videos, 10 posters and 5 audio podcasts on inclusion and diversity in elections (Konde Media) / 1.1.e. A training for least 45 journalists from 9 regions on inclusion and diversity reporting (Konde Media) / 1.1.f. Election coverage collaboration on inclusion election by trained media (Konde Media) / 1.1.g. Certified trainings on community mediation / 1.1.h Trainings on community-based and interfaith peacebuilding in 3 regions	Achieved / (with 1.1.c exceeding expectation as KAPAL Perempuan also delivered 12 events, of which alumni developed independent activities afterwards).
There are measures geared towards protecting human rights defenders at risk, including but not limited to studies, campaigns, training, legal advocacy and joint or consolidated actions.	1.2.a. There are individuals and CSOs that continuously advocate and support HRDs (YLBH, KAPAL Perempuan) / 1.2.b. There are more local actors who understand how to formulate and implement plans at local level (YLBHI) / 1.2.c. Three LBH Offices establish advocacy posts to assist victims and handle potential or ongoing cases of attacks against HRDs (SLAPP. Criminalization) (YLBHI) / 1.2.d. A forum of exchange between women leaders at national and subnational level on defending rights. (KAPAL Perempuan)	Partially achieved / Despite delays to YLBHI activities due to the ODA pause, targets were exceeded for women’s leadership networking.
Policies that impact human right defenders protection are formulated, reviewed and informed by civil society through inclusive and meaningful consultation meetings.	1.3.a. There is a policy or regulation that provides more protection for HRDs, including by collaborating with national human rights institutions (Kapal Perempuan)	Partially achieved / MoUs were signed with national institutions, though these don’t yet materially change policy.

Briefly describe the output’s activities and provide supporting narrative for the score.

During the review period, the program delivered strategic interventions that collectively strengthened Indonesia’s foundation for civic freedoms by advancing protection for HRDs.

Media innovation and campaigns shaped public discourse through Indonesia’s first gender-inclusive election reporting guideline, complemented by a documentary film, short videos, podcasts, and posters. Two national journalist trainings and fellowships equipped 61 journalists from 14 provinces to report on inclusion and diversity. These efforts embedded rights-based narratives in mainstream and alternative media, reducing stigmatization and promoting accountability.

Capacity building for women human rights defenders (WHRDs) was advanced through KAPAL Perempuan’s Training of Trainers and Masterclass, engaging 66 participants from 22 provinces and national institutions. Post-training mentoring enabled alumni to lead 12 local initiatives, reaching 818 participants, and produce advocacy content, including nine published articles. The National Consolidation Forum, attended by 96 grassroots leaders and 74 organizations, resulted in two policy briefs advocating stronger legal guarantees for HRDs protection. They were since utilised as advocacy materials to relevant state institutions which included such as the Ministry of Human Rights, Komnas HAM (National Human Rights Commission), Komnas Perempuan (National Commission on Violence Against Women), LPSK (Witness and Victim Protection Agency), Komnas Disabilitas (The National Disability Commission), Komnas Perlindungan Anak (The National Commission for Child Protection), and the House of Representatives. As a result, the policy and institutional engagement that also utilised the policy briefs as advocacy materials has delivered formal MoUs with Komnas HAM, Komnas Perempuan, and LPSK to establish a collaborative framework for institutionalizing HRDs protection mechanisms.

Community mediation and peacebuilding initiatives addressed structural vulnerabilities faced by minority groups. Certified mediation training produced 90 Supreme Court–accredited mediators, while interfaith negotiation workshops in Bukittinggi, Cilegon, and Manado engaged 278 participants, leading to the creation of sustainable mediation institutions and advocacy coalition in the three provinces the cities were situated in (West Sumatera, Banten, and North Sulawesi).

Despite these achievements, the output received a “B” score because a critical component – YLBHI-led activities on legal advocacy, SLAPP case handling, and local action plans – was delayed due to the ODA pause. These activities are essential for comprehensive HRDs protection, particularly for defenders facing criminalization and strategic lawsuits. Their absence leaves a gap in the legal and structural safeguards envisioned under this output. The output was ambitiously framed, and arguably ambition was set too high in this period.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

OSEF’s new design shifts from multiple fragmented outputs to a more integrated approach, focusing on partnerships, coalition building, and sub-national engagement. While the structure of outputs will change, advancing protection for human rights defenders remains central to OSEF’s work. This will be pursued through stronger collaboration with civil society, deeper engagement with government institutions, and targeted support for local actors to promote civic freedoms and democratic resilience.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s review recommended improving measurement of media outreach, sustaining the link between training and campaigns, building coalitions among women leaders, and formalizing national human rights institution (NHRI) collaboration. These were largely achieved: Konde Media introduced better tracking and completed its content and training pipeline; KAPAL Perempuan convened a national forum of grassroots leaders, producing policy briefs and expanding local initiatives; and MoUs with Komnas HAM, Komnas Perempuan, and LPSK were signed, followed by joint advocacy activities. However, the recommendation to accelerate legal advocacy for HRDs facing SLAPP and criminalization was not met due to funding delays, leaving a gap in comprehensive protection.

The results of this output support the overall recommendations of this review, which are to adopt an integrated, issue-based approach with fewer direct partners, embed flexibility to respond to ODA and political changes, and strengthen joint monitoring and learning systems to maximise collective impact and value for money.

Output Title	The legal regime in Indonesia supports and protects clean and democratic governance, rule of law and civic freedom including through promoting fair and transparent law-making processes, inclusive public participation, and law enforcement processes that abide to prevailing international human rights standards.
Output number:		2	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
There are legislative agendas and/or legal interpretation to stop the civil space shrinkage and protect civil liberties that includes inputs from civil society actors provided in a safe space.	2.1.a. Increased public participation through public hearings and submission of reports(LBH Masyarakat) / 2.1.b. Policy briefs on civic freedom (LBHM, ELSAM) / 2.1.c. A safe space for civil society to give recommendations on the new Criminal Code (LBHM)	Achieved / public hearings and consultations, digital engagement (kawalkuhp.id), workshops, online inputs, and formal submissions occurred. / commitments from 4 national institutions and 2 political parties. / LBHM delivered a policy brief and submitted it to government institutions, while ELSAM’s policy paper is still ongoing. / LBHM created safe spaces through workshops, hearings, and an online platform. Inputs were submitted to the Ministry of Law and shared widely.
Civil society movements consolidation in advocating the strengthening of democracy, rule of law, and human rights.	2..2.a. There are consolidated CSO groups for advocating and defending democracy, rule of law, and human rights (all projects)	Partially achieved / While theme-based CSO networks are forming, including among vulnerable groups, through all of the projects, full consolidation is still in progress
There is a reliable and operational mechanism to monitor government compliance to international human rights and good governance standards, including transparency, that is accessible to public.	2.3.a. Enhanced protection for HRDs / 2..3.b. Community-based training / 2.3.c. Regulations and SOPs are issued to enable public participation	Not achieved / not operational during the review period.
There are shifts in policies and practices in the criminal justice system to align the operation of criminal justice system with international standards on human rights and anti-corruption.	2.4.a. Studies and mapping of non-compliance with international standards / 2.4.b. Laws and regulations are amended or issued to improve compliance with international standards / 2.4.c. Capacity building to assure compliance	Partially achieved / KUHAP passed by House of Representatives in November including notable advocacy points on disability and torture prevention. / Attribution of results not proven and critiques remain of gaps to international standards.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focused on strengthening Indonesia’s legal regime to uphold democratic governance and civic freedoms. Key activities included advocacy, policy briefs, and workshops. These were done sensitively but faced delays.
Overall this output was challenging to demonstrate progress on. This is partly due to programme issues (delays to grants), partly to the external context (rapid political progress saw legislation passed with limited consultation), and partly to the overly ambition framing of the output.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

During the past year, the scope of this work was adjusted to respond to emerging priorities and partner capacity. These changes were driven by political opportunities during the transition period and the need to maintain momentum despite compressed timelines and ODA volatility.

This year also saw additional activities enabled by the insertion of Modern Slavery Fund (MSF) into OSEF. The post received GBP 70,000.- from MSF initially slated to support a civil society organisation collaboration with the government of Indonesia to incorporate Modern Slavery (MS) into the government’s Business and Human Rights Due Diligence Platform. However this project was dropped due to shifting priorities as the result of the sharp reduction of budget for most ministry level institutions.

For the year ahead, planned changes include completing ELSAM’s policy paper, and initiating joint advocacy on KUHAP reform and anti-SLAPP measures. Indicators on regulatory change will remain, but timelines will be extended to reflect the complexity of legislative processes and the shift toward an integrated, issue-based approach under the redesigned programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s recommendation to deepen policy engagement and create safe spaces for civil society was partially achieved. LBH Masyarakat successfully delivered policy briefs and convened inclusive consultations on contentious Criminal Code provisions.

Key lessons this year include:
- Advocacy requires continuity and coalition-building, as fragmented delivery and compressed timelines limited systemic impact. Multi-phase engagement and stronger coordination between partners are essential to influence policy.
- Evidence gaps also weakened credibility because progress was often reported through self-assessment rather than independent verification, making it harder to demonstrate policy-level change.
- In addition, ODA volatility disrupted timelines and political transitions, underscoring the need for adaptive planning and rapid decision-making.

The results of this output further support the overall review recommendations. In particular, they reinforce the need to:
- Prioritise integrated advocacy under thematic clusters (issue-based approach)
- Extend implementation cycles for legislative reform (embed flexibility)
- Strengthen MEL systems to track policy influence and institutional change (strengthen evidence and learning systems)
- Building synergies between partners to amplify impact and deliver on end-of-programme targets (reduce direct partners and issue-based approach)

Output Title	Indonesia has a robust democracy that includes a representative parliamentary, functional political parties, and clean electoral system that allows the fullest extent of public participation
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Improved mechanisms and conditions including within political parties that empower and support women leaders, including in the three branches of the government, to play a larger leadership roles in policy making functions	3.1.a. Created JagaSuara2024 as a policy and tool for public participation in democratic governance. (NETGRIT) / 3.1. b. Parties have internal regulations that empower women legislators. (KAPAL Perempuan) / 3.1.c. Women legislators sponsor more progressive laws. (KAPAL Perempuan) / 3.1.d. Agenda and coalition building between women in leadership positions. (KAPAL Perempuan)	Achieved / Organized “Women in Power Empowering Women” dialogue with UK Minister, attended by 70 women leaders including DPR and DPRD members. / Built networks between WHRDs and newly elected female MPs to advance women’s empowerment and child protection agendas. / Capacity building on how to use the JagaSuara2024 application for regional members by the Indonesia Women Coalition.
There is robust and dependable public monitoring of elections	3..2.a. Polling stations are covered by crowd-sourced monitoring during national elections (NETGRIT) / 3.2.b Polling stations in 37 provinces are covered by crowd-sourced monitoring during regional elections (NETGRIT) / 3.2.c Increased public awareness and election participation through trainings, conferences, and media campaigns. (NETGRIT)	Achieved / Achieved nationwide coverage through JagaSuara2024 platform, monitoring across 37 provinces and 545 jurisdictions. / Over 865,972 verified polling station forms published and cross-checked with official KPU data. / Mobilized 10,000+ trained volunteers to build coalitions and increase visibility for citizen-led monitoring during the regional re-election.
There are actionable recommendations in areas of improvement on the electoral system in Indonesia in order to retain public trust on election.	3.3.a-c. studies and policy recommendations	Achieved / Findings presented / Draft proposals made / Adoption of training

Briefly describe the output’s activities and provide supporting narrative for the score.

2024 being a national election year made electoral integrity and monitoring critical for this output. Against this backdrop, the output has made good progress and is largely on track to meet its targets. NETGRIT’s work on electoral integrity through the JagaSuara2024 platform was a major achievement last year.
Beyond technical delivery, NETGRIT mobilized 10,000+ trained volunteers and developed specific features for the regional re-election, strengthening citizen-led monitoring during the regional elections. These 10,000 members of the public had their awareness increased through targeted trainings and media campaigns, and over 8.65,972 verified polling station forms were cross-checked with official KPU data to reinforce credibility.
KAPAL Perempuan’s activities are scored under both Output 1 and Output 3, reflecting the integrated nature of their approach. While core activities such as training, mentoring, and national consolidation contribute to both the protection of human rights defenders and the advancement of women’s political leadership, care has been taken to avoid double-counting. The institutional framework set out by the MoU signed with NHRIs is reinforced by the National Non‑Judicial Settlement Team for Past Gross Human Rights Violations (PPHAM) Network created during the training of trainers on WHRD and the elimination of Gender-based Violence (GBV). Led by KAPAL Perempuan the protection network strengthens participants' capacity, reflect on the conditions for eliminating GBV, and map security risks, victim assistance guidelines, and PPHAM working principle guidelines. Under this output they organised a high-level dialogue with legislators and women leaders, attended by a visiting UK minister. The collaboration between the Indonesia Women Coalition and the JagaSuara2024 Coalition further strengthened access for women through capacity building on how to use the JagaSuara2024 application. Public campaigns reportedly reached a wide audience, such as JagaSuara2024’s social media campaign that ran on Instagram, Facebook, X (Twitter), and YouTube. One of their YouTube videos titled “Sirekap Gagal! KPU Harus Tanggung Jawab atas Kekacauan Pemilu 2024 ft. Feri Amsari & Titi Anggraini” reached 19,130 views as of August 14, 2025. and these activities show clear progress toward building advocacy networks and increasing recognition of WHRDs. However, it is still too early to know if these efforts will influence policy at scale.
Both partners faced challenges. NETGRIT had technical issues during peak data uploads, which required quick fixes. KAPAL Perempuan worked in a difficult environment where WHRDs continue to face threats and criminalisation under existing laws. These risks highlight the complexity of the issues. Overall, the output has delivered strong results and is aligned with programme objectives. This output is a strong candidate for longer-term monitoring to harvest stories of change and evidence of outcome-level results beyond the immediate programme cycle.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

NETGRIT broadened the JagaSuara2024 platform’s scope after initial testing in national elections, adding Pilkada-specific features and optimising verification workflows following stress tests. Public engagement shifted from centralised events to regional collaborations to reach universities and civil society hubs. In response to the regional re-election, an in-depth study on the electoral and voting system in Papua was conducted where one of the recommendations were adopted by the Constitutional Court when it mandated the JagaSuara2024 training as a requirement to reinforce monitoring and transparency. Planned adjustments include enhanced verification algorithms, improved server capacity, civic education modules, and AI-based data validation.

KAPAL Perempuan also demonstrated strong sustainability through alumni-led local initiatives that continued beyond the core training. Twelve initiatives in 10 provinces reached over 800 participants and resulted in new PPHAM community networks, many of which now operate independently to promote human rights and eliminate gender-based violence. Activities in academic settings, such as public lectures and workshops at universities, show that the project’s impact is embedded in local structures, ensuring ongoing advocacy and education even after the project ends.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress on last year’s recommendations has been strong, with both partners applying lessons to improve delivery. NETGRIT addressed technical challenges by optimising verification workflows and expanding the JagaSuara2024 platform to cover regional elections, which improved functionality and resilience. KAPAL Perempuan strengthened partnerships with national human rights institutions and adopted a blended training model, increasing participation from remote areas and reducing costs.

Key lessons this year include the importance of flexible implementation to respond to technical and contextual risks, and the value of formal collaboration between civil society and government institutions to enhance legitimacy and protection for vulnerable groups. As with outputs 1 and 2, this experience reinforces the overall recommendations around having an integrated, issue-based approach and a flexible delivery model.

Output Title	The programme responds to ODA changes through a redesign, and remobilisation.
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Redesign of OSEF operating model	4.1.a. Regional expertise visits x2 / 4.1.b. Design preparation and presentation / 4.1.c. Approval from Development Director for the new design	Achieved / Senior Governance Advisor visits in July and November / Slide deck prepared for internal discussion of the redesign proposal in July / Approval 14 July by Development Director / New SRO appointed 22 July
Mobilisation and inception for the new model	4.2.a. Selection of new partners / 4.2.b. Due diligence / 4.2.c. Signed agreements / 4.2.d. First disbursements	Partially achieved / New partners selected in July and August through a mini-tender, and 2x direct grants / 1 additional partner agreed in October with Ministry of Justice funding / Due diligence completed in October and agreements signed / First disbursements to partners in October and November, but technical issues with AMP delay payments
Programme funded staff	4.3.a. Onboarding of 1 new staff to support the programme	Achieved / 1 staff recruited and began work in February

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has been added to capture the programme’s strategic pivot following the ODA pause and the decision to redesign OSEF for greater impact and resilience. Activities focused on three areas: (i) redesign of the operating model, (ii) mobilisation and inception of the new approach, and (iii) staffing to support delivery.
The redesign process was completed on schedule. Two visits and regular remote inputs by the Senior Governance Advisor (July and November) provided regional expertise and informed the new theory of change and delivery model. A slide deck outlining the redesign proposal was prepared and presented internally in July, and formal approval was granted by the Development Director on 14 July. A new SRO was appointed on 22 July, ensuring leadership continuity.
Mobilisation milestones were also achieved. New partners (Yayasan Humanis and WFD) were selected through a mini-tender and two direct grants in July and August, with an additional partner (Jentera Law School) agreed in October under Ministry of Justice funding. Due diligence was completed in October and agreements signed, but technical delays pushed back actual payments. Finally, two programme-funded staff were recruited and onboarded in February, strengthening capacity for implementation and oversight.
Given the complexity of the ODA pause and the scale of change required, these achievements represent strong performance. The output is assessed as on track, with all milestones met and the programme positioned to deliver under its new design.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was introduced at the terms of reference stage of the annual review to reflect the strategic redesign and mobilisation process, which was not part of the original logframe. The indicators and milestones are therefore created post-hoc, which is not best practice but in this case is justified as it is the only practical way to reflect the redesign and mobilisation work in the annual review score.
For the next review period up to April 2026, milestones should focus on:
- Design and implementation of a first iteration of least one election law issue-based intervention, with evidence of joint action between partners, and conscious strategy reviews;
- Development of at least 2 issue-based interventions related to rule of law and human rights and progress on implementing these;
- Development and consolidation of the management and implementation process for an issue-based approach agreed and tested as the basis for future work.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s recommendation to simplify delivery and reduce administrative burden has been acted upon through the redesign: the programme will now operate through 3 lead implementers and thematic clusters rather than multiple isolated grants. This addresses lessons learned on fragmentation, short project windows, and heavy compliance overhead.
Key lessons this year:
The following lessons are reflected in Section A of this annual review.
- Agility matters: The ODA pause highlighted the need for adaptive management and rapid decision-making.
- Integration drives impact: Fragmented projects limited collective influence; an issue-based approach will enable partners to collaborate strategically.
- Capacity and compliance: Smaller CSOs require support to meet donor standards; the revised model will provide this while freeing Embassy resources for political engagement.

Recommendations for the year ahead:
These recommendations are also reflected in Section A.
- Embed and issue-based, integrated project management approach that is flexible and allows for adaptive management.
- Prioritise early inception and coalition-building to ensure partners work as more than the sum of their parts, with short feedback loops to embassy staff.
- Strengthen evidence and learning systems that capture cross-project impact and feed lessons into diplomatic engagement.
## D: VALUE FOR MONEY

Key cost drivers and performance

Throughout the period covered in this AR (November 2024-October 2025) OSEF has disbursed £632k (rounded to the nearest £1k). This spending is a combination of the conclusion of legacy projects run by KAPAL Perempuan, LBH Masyarakat, Konde Media, PUSAD Paramadina, NETGRIT, and ELSAM and the disbursement for the new projects under the new design, plus programme-funded staff.

The cost structure of the OSEF programme reflects its dual ambition: delivering impactful interventions while strengthening local civil society organisations (CSOs) at the grassroots level across Indonesia. The largest share of expenditure is allocated to capacity building (21.28%) and research, policy briefs, and monitoring (29.73%), underscoring the programme’s emphasis on equipping partners with technical skills and evidence-based advocacy tools. These investments enable CSOs to influence policy processes, engage in inclusive dialogues, and monitor governance practices effectively.
Significant resources are also directed toward public dissemination and campaigns (14.45%) and structured engagements with policymakers (14.43%), reflecting the programme’s strategy to amplify counter-narratives and foster constructive state–civil society dialogue. Meanwhile, project-funded roles within partner organisations (15.34%) ensure dedicated personnel for coordination and delivery, which is critical for sustaining momentum in complex advocacy environments.
VfM performance compared to the original VfM proposition in the business case

The programme’s approach remains consistent with the original VfM proposition:

- Supporting CSOs to advocate for legal and policy reform is a proven method in Indonesia, building on past successes such as migrant worker and sexual violence legislation.
- CSOs act as efficient policy bridges, leveraging networks and credibility to influence decision-makers.
- OSEF interventions aim to protect vulnerable groups and uphold rights, reinforcing democratic resilience and inclusive governance.
Organisational overheads among project partners accounts for 2.76% of the total budget. While this may appear modest on average, some projects have a higher percentage than others – for example those working across regions and with complex delivery systems have higher overhead costs (in a range of 5% to 9% for some partners).This reflects the operational reality of working with small, local organisations that lack economies of scale.

Across all projects, equity was a strong focus:

- LBHM (ENABLE): Prioritised vulnerable groups—LGBTIQ+, people living with HIV, persons with disabilities, religious minorities, indigenous communities, and migrant workers—through consultations (362 participants in Phase 2; 94 in Phase 3) and digital advocacy tools like kawalkuhp.id. Campaigns reached 1.3 million impressions, amplifying voices often excluded from policy processes.
- NETGRIT: Enhanced electoral inclusion via JagaSuara2024, enabling youth and women’s organisations to monitor elections. This addressed transparency gaps left by the Electoral Commission’s official platform.
- ELSAM: Advanced digital democracy by promoting civil liberties online and building youth capacity to engage safely, with gender safeguards against discriminatory practices. Women’s organisations were directly engaged to shape this work.
- KAPAL Perempuan: Reached 818 participants (80% women) across 22 provinces, including remote areas (Papua, Sumba, Gorontalo), through Training of Trainers, masterclasses, and local initiatives for Women HRDs.
- Konde Media: Embedded gender and social inclusion in electoral discourse via guidelines, journalist training (58–68% women), fellowships, podcasts, and screenings beyond Java.
- PUSAD Paramadina: Protected religious minorities through mediation and negotiation training for 700 participants in four regions, meeting 30% female participation and including persons with disabilities and minority faith groups.

Partners collectively bridged geographic gaps, extending activities to eastern and remote provinces (Papua, NTT, Sulawesi, Maluku). However, systematic disaggregation beyond gender and location was limited. Age, disability, and socio-economic data were rarely captured, and accessibility measures (e.g., disability-friendly formats, multilingual materials) were reactive rather than embedded in design.

In terms of procurement practices, the redesign offered a new opportunity to test approaches within OSEF. The Westminster Foundation for Democracy was brought in via a negotiated MoU following standard practice and a template agreed centrally between the FCDO and WfD as an arms-length body. This allowed for speed and efficient mobilisation, and was the appropriate choice because of WfD’s unique role within UK politics and potential to generate partnerships and relationships between UK and Indonesian parliamentarians.

For YLBHI, an accountable grant was agreed following a proposal from the organisation, based on extending an existing and tested programme funded by another donor to two new cities. For the main civil society component, though, the FCDO recognised both the novelty of its requirements and the potential for several partners to deliver the work. The programme team ran a tender process for this grant, offering 4 different partners the opportunity to bid against a terms of reference. Yayasan Humanis achieved the highest score in the selection and was therefore invited to prepare a full grant proposal.

Assessment of whether the programme continues to represent value for money

Yes. Despite operational constraints, OSEF delivered relevant outputs, safeguarded economy, and demonstrated adaptive management in the face of regularly changing cost and time parameters. Most importantly the supported projects placed significant focus to ensure inclusion in middle and eastern Indonesia in an attempt to close access disparity compared to western Indonesia especially Java.

The redesign aligns with strategic priorities and promises future efficiency and effectiveness gains in theory. However, VfM during this reporting period was moderate: transaction costs with multiple partners remain higher than envisaged, and cost-effectiveness was impacted by delays.

Recommendation: Continued attention to organisational overheads, timely mobilisation, and inclusion metrics should be tracked with a systematic VfM framework. This is a key recommendation and will be critical to ensure the programme fully realises its VfM potential in 2026 and beyond.

E: RISK

Overview of risk management

The programme carries an overall moderate risk rating, higher than initially set out in the business case because of higher-than-expected delivery risk. These risks partially materialised this year as the ODA pause, change in SRO leadership, and redesign caused significant delays to implementation. Other risks remained largely consistent during the review period.

Policy & Programme Delivery
Two risks previously assessed as likely with major impact remain the most significant: poor programme delivery due to political dynamics and weak programme supervision linked to limited human resources at Post. These risks persisted throughout the year, although mitigation measures, particularly the recruitment of a programme-funded HEO and the decision to streamline delivery through two principal implementers, have reduced exposure and improved oversight. Despite these steps, the risk rating remains major given the external political environment and the complexity of programme objectives.

Strategy & Context
The risk of poor integration with other Embassy programmes and policy work continues to be likely, albeit with moderate impact. This risk refers to the possibility that OSEF supports work that conflicts with key stakeholder interests elsewhere in the portfolio and risks reducing government support for activities. Mitigation efforts included regular communication with other sections and reflective exercises such as this Annual Review, which involved cross-team participation. These measures have helped maintain alignment but do not eliminate the risk entirely.

Financial & Fiduciary
The anticipated risk of budget unavailability due to ODA pressures did materialise during this period, with the ODA pause and subsequent budget reduction having a material impact. Weak financial management among local partners remains a possible risk with major impact, given that many partners are national-level associations managing relatively modest budgets which requires the projects to be pre-paid as they do not have sufficient resources to front pay the proposed activities. In order to offset risk, the FCDO only disburses further funding once 90% of the pre-paid activities have been completed. Enhanced supervision through monthly financial and substantive reporting, supported by the Project Assistant, further reduced exposure. Fraud and safeguarding risks were addressed through monthly partner meetings, review of past audits, and ensuring project-level audits for smaller organisations. We will continue to utilise these measures, including the monthly monitoring meeting and performance-linked financial disbursement to reduce risk in the future. The risk of weak financial management will also be further mitigated by the shift to a simpler operating model that relies on utilising larger civil society organisations with administrative systems more accustomed to managing international development funds as implementers

Safeguarding
Safeguarding risks were actively managed through due diligence and ongoing monitoring. No specific safeguarding concern was raised within OSEF during the reporting period. The risk as currently framed refers to generic risks in working with politically vulnerable groups. The recommended changes to risk management in this review should include a more precise articulation of safeguarding risks and mitigations.

Reputational
Reputational risks to implementers, beneficiaries, and FCDO remain inherent in some OSEF activities and could have major impact if not carefully handled. These were mitigated by selecting partners with a constructive engagement history with the Government of Indonesia and by adopting a cautious approach to public-facing activities. Decisions on visibility and communications, including this Annual Review, were made collaboratively with partners to minimise exposure for all stakeholders.

Overall risk assessment
As the programme moves forward, some risks are expected to diminish, particularly those related to administrative complexity and fragmented supervision. However, new risks may emerge, including potential delays in scaling up activities under the redesigned approach, heightened political sensitivities around democratic governance, and capacity challenges for core implementers managing larger portfolios. As the UK-Indonesia Strategic Partnership becomes operational, the reputational risks of this programme will need close attention.

Continued attention to financial controls, safeguarding standards, and proactive engagement with other Embassy teams will be essential to maintain the programme’s moderate overall risk rating and ensure resilience in a dynamic political and funding environment.

Recommendation: For the coming year the programme should consciously embed risk awareness, risk appetite understanding, and risk mitigations throughout its delivery chain, led by the embassy programme team. This means strengthening programme oversight through regular management meetings, regular and transparent internal reporting, and appropriate risk escalation. In particular, political and reputational risks with the new issue-based approach will need to be carefully managed. With a delivery chain onward from first-tier partners through sub-granting, the programme needs to make sure there is full visibility of activities and risks.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Between November 2024 and October 2025, programme management focused on completing projects under the original design while preparing for the new delivery model. The ODA pause created significant constraints, limiting new disbursements and requiring adaptive measures to maintain progress. Despite these challenges, the programme team ensured that outputs were delivered and that the redesign was completed and approved in July 2025.

The embassy team structure was strengthened during this period. A new Senior Responsible Owner was appointed in July 2025, and a programme-funded HEO joined in February 2025. These changes improved coordination between political and programme functions and supported decision-making during a complex transition. Regular meetings and structured reporting cycles helped maintain oversight and address operational issues promptly.

Partners generally performed well. Konde Media delivered its Women’s Media Watchdog project, meeting training targets and producing public education materials, although delays in content approval required timeline adjustments. NETGRIT achieved nationwide coverage for its election monitoring platform. LBH Masyarakat implemented the ENABLE project within a short timeframe, producing research outputs and convening advocacy coalitions. PUSAD Paramadina delivered mediation and negotiation training across three provinces and supported the institutionalisation of mediation practices. ELSAM advanced research and advocacy on digital governance but faced delays due to internal leadership changes. Most partners rated their Value for Money performance as good, citing efficient resource use and inclusive practices. Partners were selected through a competitive call for proposals.

During the implementation of OSEF, several challenges emerged that affected the timely delivery of activities and outputs. Institutional dynamics within partners created delays, such as ELSAM’s leadership transition, which required internal adjustments and diverted attention from project execution to organizational restructuring.

NETGRIT encountered additional complexities due to the wave of re-election in some regions. The JagaSuara2024 platform had to recalibrate its monitoring and verification processes to accommodate PSU data, delaying the timely delivery of results. In regions such as Papua, identity politics and logistical barriers intensified challenges, making transparency efforts both urgent and politically sensitive.

Capacity constraints in reporting further affected NETGRIT’s performance. While JagaSuara2024 successfully delivered real-time monitoring, converting extensive datasets and field findings into structured narrative reports required additional time and resources. Close coordination with implementing partner TAPOL added complexity, highlighting the need for stronger internal documentation systems and clearer reporting protocols.

Financial challenges also emerged due to currency fluctuations. The weakened rupiah resulted in KONDE receiving higher-than-expected funds in local currency, requiring adjustments to activity plans to maintain value for money. This misalignment underscored the importance of accurate financial forecasting and flexible programming to adapt to economic volatility.

Partners also provided feedback on FCDO’s role. They appreciated flexibility and technical support but highlighted areas for improvement. Delays in activity approvals and content clearance were a recurring issue, creating bottlenecks and requiring timeline changes. Partners recommended faster feedback and clearer communication protocols. They also requested clearer financial management guidance for large projects and suggested scheduling final reporting after project completion to allow time for accurate reconciliation and quality assurance.

Financial management followed strict controls. Since the legacy partners are local NGOs, all subsequent fund transfers are only made when 90 percent of agreed activities or budget for the period had been completed. This approach reduced fiduciary risk and ensured accountability. Partners submitted regular financial and narrative reports, and external audits are scheduled for projects closing in late 2025. Competitive procurement was applied for major activities, and co-funding from stakeholders, such as LPSK’s contribution to the WHRDs Masterclass, improved value for money. All partners also participated in the annual Finance and Fraud Management training held by the Development Management Unit.

Monitoring and learning were integrated throughout the year through monthly meetings. The Annual Review process included questionnaires, document reviews, and meetings with partners. A reflection session in May 2025 identified lessons that informed the redesign, including the need for intersectional approaches, stronger digital security for journalists and human rights defenders, and sustained public engagement through civic education. Recommendations from the Senior Governance Adviser’s visit in October 2024 also shaped the new design, which consolidates delivery under two main implementers and introduces a strategic fund for emerging priorities.

Challenges included administrative delays in approvals and the complexity of managing multiple small grants under the original model. These issues reinforced the decision to adopt a consolidated delivery structure. This approach is expected to reduce transaction costs, improve coherence, and strengthen the programme’s ability to deliver systemic impact.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

Monitoring combined routine reporting with three field visits during the review period:
- Manado (October 2024) – Observed PUSAD Paramadina’s negotiation training for interfaith leaders and Kapal Perempuan’s HRDs capacity-building activities.
- Medan (February 2025) – Attended LBH Masyarakat’s ENABLE talk show on death penalty commutation and interviewed beneficiaries from NETGRIT and Konde Media.
- Jakarta (June 2025) – Participated in Konde Media’s launch of its election coverage guideline.
Findings from these visits include
- Quality and relevance of trainings: Trainings observed generally met participation targets and provided practical skills, but some lacked contextual alignment. Negotiation exercises in Manado focused on everyday disputes rather than interfaith conflict. Human rights defender sessions highlighted the need for more in-depth legal protection content. Participants valued the sessions but requested stronger thematic focus and case studies relevant to their realities.
- Insights for advocacy: Discussions in Medan underscored gaps in legal clarity on commutation and the need for safeguards for vulnerable groups, informing LBHM’s advocacy strategy. Feedback from Konde’s guideline launch emphasized the importance of principled reporting and shifting media narratives from sensationalism to substantive issues, reinforcing advocacy for gender-sensitive journalism.
- Value of networks: Across all visits, beneficiaries stressed the importance of networking opportunities. Journalists noted that connections built during Konde’s training improved access to diverse sources and balanced reporting. HRDs reported that peer networks created through Kapal Perempuan’s sessions provided solidarity and practical support in high-risk environments. NETGRIT’s engagement with academic and civil society actors strengthened coalitions for electoral integrity.

These insights fed directly into programming decisions, including the redesign’s emphasis on intersectional approaches, digital security, and coalition-building. They also informed plans for integrate advocacy components with capacity-building and to maintain networking as a core strategy for resilience.

The Annual Review process itself was structured as a comprehensive evidence-gathering exercise. It involved a desk review of programme documents, questionnaires to all partners, and clarificatory meetings with organisations active during the period. Inputs were also sought from outside the programme team, including the Senior Governance Adviser and the Democratic Governance Centre of Expertise, whose diagnostic visit in July 2024 and subsequent advisory report shaped the redesign and informed the review’s analytical framework. No external M&E supplier was engaged during this period; monitoring and evaluation were managed internally by the programme team with partner cooperation.

After the monitoring and evaluation exercises, the following areas for Improvement were identified:
- Disaggregated Data: Strengthen requirements for partners to collect and report disaggregated data (e.g., by gender, age, disability, geography) to better demonstrate reach and inclusion.
- Outcome Measurement: Increase focus on measuring outcomes and impact, not just outputs. Use outcome mapping, beneficiary feedback, and case studies to evidence change.
- Independent Verification: Move beyond self-reported data by introducing more independent verification methods, such as spot checks or third-party evaluations.
- Standardised MEL Tools: Develop and implement standard MEL tools and frameworks across partners to ensure consistency and comparability.
- Learning Dissemination: Clarify how learning will be shared beyond the immediate team to maximise its value across the Embassy and with external stakeholders.
- MEL Capacity Building: Provide targeted support and training to partners to strengthen their MEL systems, especially for outcome measurement and data quality.

Evidence

The evidence base strengthened through research outputs and policy briefs produced by partners. LBH Masyarakat generated studies on modern slavery risks linked to criminal procedure reform and migrant worker protection, which informed advocacy strategies and engagement with policymakers. NETGRIT provided large-scale electoral data through its JagaSuara2024 platform, offering robust evidence for election integrity and influencing parliamentary discussions on electoral reform. ELSAM advanced research on digital governance and personal data protection, although delays caused by internal transitions limited the breadth of outputs within the period.

Evidence quality was generally strong, combining quantitative data such as verified polling station results and participant demographics with qualitative insights from focus group discussions and stakeholder interviews. However, although partners provided gender-disaggregated data, they were not asked to and did not provide disaggregation for other protected characteristics. The programme will address these gaps in the next phase by requiring partners to strengthen their monitoring frameworks in this area.

Learning

The May 2025 reflection meeting with partners served as a key platform for capturing lessons and shaping future priorities. Discussions highlighted the need for sustained civic education, coalition-building, and culturally sensitive approaches in regions such as Papua. Partners also stressed the importance of moving from short-term emergency responses to long-term strategies for democratic resilience. These insights informed the redesign approved in July 2025, which consolidated delivery under three principal implementers and introduced a strategic fund for emerging priorities.

At the operational level, partners identified lessons on improving coordination with FCDO, including the need for faster approval processes and clearer financial guidance.

Recommendation: For the coming year, OSEF should introduce joint MEL tools to capture cross-project impact and feed lessons into diplomatic engagement. Tools could include quarterly learning reviews and expanding the use of beneficiary feedback, and outcome mapping. The team will need to clarify which they use. To ensure adaptive delivery and maintain alignment with local dynamics, it is recommended that the Regional Governance Adviser conduct quarterly visits to Indonesia. These visits will provide technical input on democratic governance, with the added benefit of strengthening linkages between programme activities and FCDO’s wider Indo-Pacific strategy, as well support partners in embedding best practices on inclusion, safeguarding, and risk management.

Date of last narrative financial report		Date of last audited annual statement