## Annual Review Template

Title: Strengthening Humanitarian Access in Nigeria (SHAN)
Programme Value £ (full life): Up to £11m		Review date:
Programme Code: 400131	AMP start date: 04th February 2024	AMP end date: 31st December 2025

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Severe

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006183.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006184.xlsx

Acronym

AR – Annual Review
BC – Business Case
BRINNS – Building Resilience in Nigeria’s Nutrition Supplies
CO - Carbon dioxide
FAAN - Federal Airports Authority of Nigeria
FCDO – Foreign, Commonwealth and Development Office
HARP – Humanitarian and Resilience Programme
HART - Nigeria Humanitarian and Resilience Team
HMG – His Majesty’s Government
IDP – Internally Displaced Persons/People
IOM – International Organisation for Migration
MoU – Memoranda of Understanding
NE – North-East
NGOs – Non-Governmental Organisation
NSAG – Non-State Armed Group
PCR – Programme Completion Review
PrOF – Programme Operating Framework
SHAN – The Strengthening Humanitarian Access in Nigeria (SHAN) programme
SPSS – Solar Power Supply Systems
SRO – Senior Responsible Officer
TPM – Third Party Monitoring
UK – United Kingdom
UN – United Nations
UNHAS – United Nations’ Humanitarian Air Service
USAID – United States Agency for International Development
VfM – Value for Money
WFP – World Food Programme

A. SUMMARY AND OVERVIEW

Description of programme

The Strengthening Humanitarian Access in Nigeria (SHAN) programme is a twelve-month intervention designed to to enhance the delivery of aid in North-East (NE) Nigeria through two strategic capital investments. The programme value is up to £11million.

 SHAN involves:
- installing solar power in Humanitarian Hubs delivered by IOM, which provide safe housing, offices, and connectivity for aid workers in remote areas, and
- upgrading aviation infrastructure delivered by UNHAS, including fuel, passenger and cargo facilities, to improve the capacity, reliability, and efficiency of transporting vital supplies and personnel.

The programme aims to bolster access and operational effectiveness, particularly in areas with challenging security conditions.

 By supporting humanitarian objectives and contributing to Goals 5 (saving lives) and 8 (protecting vulnerable populations) of the FCDO Nigeria Country Business Plan, SHAN reinforces the UK's commitment to addressing the complex humanitarian situation and enhancing the sustainability of the response.
SHAN is designed to complement existing UK programming including aligning with the Theory of Change of the existing Humanitarian and Resilience Programme (HARP, up to £191.5m, 2022 – 2027).

SHAN adheres to environmental commitments, being 'Paris Aligned' and compliant to the PrOF rule 5 related to fossil fuels.

Summary supporting narrative for the overall score in this review

The programme has been scored an “A” for its performance over the period of implementation. There have been delays caused by a variety of factors, which meant implementation, which was for April 2024, was delayed to May 2024. However, over the past year of implementation, the SHAN programme has made significant progress in achieving its objectives.

The solarisation of nine (9) deep-field humanitarian hubs by IOM has been completed, resulting in substantial cost savings and enhanced energy operations. The hubs are now operating entirely on solar power, reducing fuel costs by nearly 90% and utility grid consumption by over 95%. Additionally, the environmental impact has been positive, with a reduction in carbon emissions by over 650 tonnes of CO₂ per year. The capacity-building efforts have strengthened the technical capabilities of local Nigerian solar vendors and IOM solar power engineers. This was achieved with more than 15% budget savings.

Separately, the longer-delayed aviation infrastructure component led by UNHAS has faced challenges due to vendor performance issues, leading to the termination and re-advertisement of several contracts for delivery by private suppliers. A factor exacerbating the challenge has been both the difficulty in procuring specialist aviation equipment in the open market and frictions with importation (arising from port clearing difficulties and forex sourcing). However, new tenders have been launched, and progress is being made in the procurement and installation of these essential equipment. Despite these setbacks, the programme remains on track to achieve its goals.

These delays led to the programme requesting and obtaining a 9-month extension to accommodate UNHAS delays, shifting the end date from the originally planned March 2025 to December 2025, which necessitated this Annual Review.

Major lessons and recommendations for the year ahead

The rationale behind developing the SHAN programme was to utilise available CDEL funding to benefit multiple actors beyond the UK’s existing partners and enable a contribution to the broader humanitarian response. The investments were developed to sustain access to remote areas of NE Nigeria where security conditions remain extremely challenging. Humanitarian actors are limited to the use of air assets as roads are unsafe. Budget constraints and priority rightly provided to lifesaving humanitarian action had previously meant that larger capital investments to improve the quality, efficiency and accessibility of the response were deprioritised in favour of providing immediate life-saving support. This programme has taken a different approach, and there will be lessons for the response in Nigeria and for the FCDO humanitarian operating model.

During the implementation period, the humanitarian sector experienced severe funding and structural shocks, particularly the uncertainty created where other donor funding enabled the functioning of the humanitarian sector. This may challenge the sustainability of components of the investment, including the continued operations of some of the solarised deep-field hubs and the potential usage volume of the new aviation infrastructure.

FCDO’s humanitarian impact and VFM may be constrained due to these rapid changes. However, the design and delivery approach taken was pragmatic and within the constraints of foreseeable risks . As such, the programme can be said to be achieving as intended.

Summary of recommendations

Recommendation 1: Downstream contract management and widely varying vendor performance represented a major area of learning. Deeper understanding of required contracting processes by partners and the market complexities, would have been useful to set more realistic delivery timeframes. Over time, the importance of thorough vetting and monitoring of vendors to ensure timely and quality delivery of services became more apparent. Although Third Party Monitoring (TPM) services played a vital role in mitigating some of the challenges of close monitoring, especially for deep-field locations, closer support during delivery remains an area for improvement. More use could be made of FCDO commercial and advisory expertise for future CDEL programmes to ensure planning is realistic; this could be done through the FCDO Centres of Expertise (CoE). Effective risk mitigation strategies are crucial in managing unexpected challenges, such as vendor performance issues, customs delays, and slow spend rates. This could range from using more results-based payments to incentivise quicker delivery to implementing more rigorous monitoring and evaluation processes to ensure suppliers meet performance standards and foresighting regulatory risks that materialised into clear issues. [Timeframe: ongoing].

Recommendation 2: In delivering capital projects aimed at sector-wide impacts, a more collaborative engagement with other major donors should be pursued to ensure broad-based ownership and commitment to supporting the sustainability of these investments. Also, FCDO will need to embed robust contingency plans in capital projects within the humanitarian sector to address potential delays and disruptions in project implementation including strengthening local technical expertise. However, due to the nature of humanitarian response we do not expect capital projects to become a dominant programme modality in the sector. [Timeframe: ongoing].

Recommendation 3: FCDO and UNHAS to establish clearer mutual expectations on project outputs delivery timelines, burn rates, and approaches for navigating regulatory hurdles, and reporting requirements. These should be documented in writing to promote clarity and aid institutional memory. [Timeframe: by June 2025].

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Theory of Change: SHAN was developed to enhance humanitarian access by financing key assets. It aimed to provide uninterrupted renewable electricity to eight deep-field humanitarian hubs, facilitating access for aid workers to approximately 1.3 million internally displaced persons (IDPs). The programme also supported the construction of cargo, storage, and fuel facilities to streamline operations and ensure efficient transportation of relief goods and essential aid, along with reliable air access for medical and security evacuations. Designed in the context of rising fuel prices, the programme sought to free up resources for humanitarian assistance and reduce CO₂ emissions by approximately 697 tonnes per year, achieving a 76% reduction in the carbon footprint in remote locations. This was based on a Theory of Change (ToC) stating that If the FCDO invests in humanitarian infrastructure and these investments are realised quickly, then fuel costs will be lower, emissions will be reduced and aviation services will be more reliable, resulting in safer, more efficient, and greener access to vulnerable populations in remote locations, improving the overall reach and sustainability of the humanitarian response.

Humanitarian staff are able to reliably access deep field locations.
Humanitarian aviation services are more reliable and efficient.
Upgraded aviation fuel storage, cargo and passenger processing facilities.
Capital Investment
 Advisory and programme management support
Vital humanitarian aviation services are often delayed and unreliable.
Hub energy costs are lowered.
Impact
Enhanced efficiency of the humanitarian response, with access to deep field locations sustained and the most vulnerable people in deepest humanitarian need continue to receive lifesaving services.
Outputs

Outcomes
Inputs
Supply of fuel to Humanitarian Hubs is costly and logistically challenging.
Problems

The key assumptions underpinning the theory of change included:

Context
- The security conditions in NE Nigeria do not deteriorate rapidly to the point where humanitarian access is severely restricted or impossible.
- Broader economic conditions in Nigeria will not worsen significantly, which could impact fuel prices, importation of necessary equipment, and overall operational costs.
- There will be no major environmental disasters (e.g., floods, droughts) or outbreaks of public health importance that could disrupt the infrastructure or overwhelm humanitarian operations & response.

Delivery and Operational
FCDO’s capital investments in humanitarian infrastructure will be implemented quickly and without significant delays and regulatory approvals would be gotten without impacting feasibility of delivery.
- The quality of infrastructure investments will be sufficiently high to effectively lower fuel costs, reduce emissions, ensure continuing operation of the hubs and that improved aviation services will lead to safer and more efficient transportation of aid workers and supplies.
- Same and maybe more demand for usage of the humanitarian facilities (deep field hubs and aviation services) by aid workers and relevant stakeholders is maintained for the medium to long-term.
- The medium to long-term usage of the facilities will be for humanitarian purposes and not re-allocated for use that contradict humanitarian principles and ODA-eligibility.

Institutional Capacity
- There will be continued and sufficient funding from international donors and the UN partners to maintain and expand humanitarian infrastructure.
- Local technical expertise and capacity will continue to grow, ensuring the sustainability and maintenance of the infrastructure investments.
- The Nigerian government and local communities will accept and support the humanitarian infrastructure and operations, facilitating smooth implementation and maintenance.

The core assumption that FCDO’s capital investments would be realised quickly and without substantial delays has been significantly challenged during delivery. SHAN was a highly innovative programme in the humanitarian sector. This is particularly reflected in the fact that regulatory, procurement and supplier performance issues have necessitated a timeline extension to December 2025.

Similarly, the critical institutional assumption regarding continued and sufficient operational funding from the wider international donor community to sustain common humanitarian services, including the solar-powered hubs, has been severely challenged by recent global ODA cuts, notably from USAID. Broader economic conditions in Nigeria, such as forex volatility and inflation, also presented hurdles for efficient procurement of specialised equipment, contrary to hopes for a more stable economic backdrop.

However, other assumptions have largely held. The quality of the successfully installed solar installations has proven effective in significantly lowering fuel costs and reducing emissions as intended, and vital regulatory approvals for aviation works, though initially slow, were eventually secured. The fundamental premise that improved infrastructure supports safer and more efficient access remains valid, even as progress to achieving all intended benefits has proven more complex and extended than originally envisaged.

Progress towards outcomes:

	Starting point	Final result
Budget	£11,000,000	£9,055,040
Timeframe	April 2024 – March 2025	April 2024 –December 2025
Outcomes	Humanitarian staff are able to reliably access deep field locations	To be reported in SHAN’s PCR

### Overall assessment of programme outcomes, sustainability and VfM

The planned outcome of the programme is that humanitarian staff are able to sustainably access deep field locations, and the most vulnerable people in deepest humanitarian need continue to receive lifesaving services. The SHAN programme has demonstrated significant progress in achieving its intended outcomes.

Outcome Indicator	Starting Target	Result Achieved
# of humanitarian facilities benefitting from continuous operation and maintenance of the hybrid SPSS	9	9
UNHAS' operations in the Maiduguri Airport have expanded capacity	No	Ongoing delivery

The successful solarisation of deep-field humanitarian hubs has resulted in substantial cost savings and environmental benefits, reducing fuel costs by nearly 90% and CO₂ emissions by about 697 tonnes per year. These achievements have not only improved the sustainability and cost-effectiveness of humanitarian operations but also strengthened local technical capacities through capacity-building efforts. Despite initial delays and challenges, including regulatory hurdles and tender failures, the programme has maintained a strong trajectory towards its goals.

The aviation infrastructure component, although delayed by vendor performance issues and procurement difficulties, is making steady progress. Given the current pace of progress, the December 2025 completion date for the aviation infrastructure will need to be closely monitored. The procurement and installation of essential equipment are ongoing, and new tenders have been launched to address delays.

In terms of Value for Money (VfM), SHAN has effectively utilised its budget to deliver results, achieving more than 15% budget savings in the solarisation component alone. The programme's design and delivery approach have been pragmatic, addressing foreseeable risks and adapting to the rapidly changing humanitarian environment. The reduction in humanitarian funding for Nigeria and globally is likely to pose significant challenges to the long term viability of the model of the humanitarian hubs, but the programme's resilience and adaptability have been commendable. The expansion of output targets for solarisation has further amplified its impact, contributing to broader environmental and sustainability goals. Furthermore, SHAN's alignment with existing UK strategies and its integration with FCDO’s other humanitarian programmes (HARP and BRINNS) will synergise its scope and impact, fostering a unified programming approach to humanitarian aid delivery within FCDO Nigeria. Overall, SHAN has proven to be a valuable and sustainable intervention, reinforcing the UK's commitment to addressing complex humanitarian challenges and improving the reach and effectiveness of the response.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	North-East Nigeria Humanitarian Hubs are equipped to use hybrid SPS Systems to meet power needs
Output number:		1	Output Score:	A++
Impact weighting (%):		70%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
% of electricity needs covered by the SPSS	95%	100%- Average of 95% supplied by the SPSS / Milestone target met expectation - A
Tonnes of Greenhouse Gas Emissions / Reduced or avoided as a result of installed fully operational and maintained SPSS across the 9 humanitarian hubs	298 tonnes of CO2	697 tonnes of CO2 / Milestone target substantially exceeded expectation - A++

Briefly describe the output’s activities and provide supporting narrative for the score.

This project involved the deployment of solar power systems across nine humanitarian hubs, which serve as critical operational bases for aid workers. These hubs are located in Maiduguri (Red Roof and Maiduguri hubs), Bama, Banki, Damasak, Dikwa, Gwoza, Monguno and Ngala. Most of the hubs are located in remote areas where traditional energy sources are unreliable and costly.

The project is being implemented by the International Organisation for Migration (IOM). Originally, it was conceived as an 18-month project, with an initial first phase of about 10-12 months focused on installation and a second phase focused on service management by the selected technical installer/supplier. This approach was supposed to serve to integrate learnings from previous solarisation projects where a one-off, turn-key installation and delivery approach had compromised the sustainability of the system.

The project was redesigned to be delivered in 12 months, from April 2024 to March 2025, due to capital eligibility constraints and programme funding approval limits. This redesign also led to a reduction in cost from an initial planned £8m to a final project-start budget of £7.25m (a 9.5% reduction) while largely maintaining the same deliverables and ensuring a post-installation service agreement, outside of FCDO’s funding was negotiated with suppliers. The redesign process was iterative, which led to delays in the start-up of the project. The eventual agreement between FCDO and IOM signed later than expected in June 2024.

The impact of the solar installations has been substantial, reducing reliance on diesel fuel and cutting fuel costs by nearly 90%. This shift has also led to a reduction in CO2 emissions by 697 tonnes, aligning with environmental goals. The solar systems now provide a reliable power supply, enhancing the operational capacity of humanitarian efforts and ensuring aid workers can focus on delivering critical services. The project has also resulted in a reduction of operational costs from $3.4 million (£2.55m) in 2024 to $2.8 million (£2.1m) in 2025, saving approximately £450,000, as at Q1 estimates.

Training local technicians was another important part of the intervention, equipping them with the skills needed to maintain and optimise the solar systems, ensuring their long-term sustainability. The project has strengthened local technical capacity in SPSS. Nigerian solar vendors and IOM engineers have gained valuable technical expertise, which supports the long-term success of the installations. This empowerment is crucial for fostering local ownership and ensuring that the systems continue to operate effectively.
The project's achievements, coupled with strategic budget management, justify the "A++" score, reflecting its success in meeting and exceeding expectations. The solar installations have set a new standard for sustainable energy solutions in the region, demonstrating the potential for renewable energy to transform humanitarian operations.

The project began with an assessment of the energy needs, standards, energy use patterns and requirements for delivering the Solar Powered Supply System (SPSS). Procurement initially focused on finding suppliers to import high-quality components. However, supply chain constraints (abroad and in-country) and accessing forex led to several tender failures, and delays in delivery timelines. Progress was delayed by 3 months, with further challenges created with the flooding in the NE between September-October 2024. IoM had to adapt a more flexible approach that allowed for local and regional procurement while maintaining similar technical standards. The planned installation finalisation was delayed from December 2024 by the procurement challenges, to March 2025.

The local technician training, originally planned to be done in the final quarter of the programme (January-February 2025) with a month left for project closing and commissioning, could not be completed on time due to the delays in completing the installation. It was moved to April 2025, requiring a time extension in the project. The training was designed to not only support the ongoing operation of the systems but also build local capacity, empowering the hub management with the skills to manage their SPSS.

Within that period, there were significant unexpected cost reductions in component prices within the global market, and some useful economies of scale were gained by bulk purchases, as well as installation cost savings due to forex arbitrage. This meant that the project which was planned to be delivered at a cost of £7.25m was eventually delivered at £5.63m, representing a savings of £1.62m (22%).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Working with IOM, the FCDO Humanitarian Team agreed to provide a time extension for the project for 6 months. This will provide adequate time to complete all installations, test performance for an extended period, and conduct the planned trainings. With the significant cost savings and the time extension, the teams also agreed to expand the scope of the project to further solarise two additional facilities – IOM’s Maiduguri and Yola sub-offices. The budgeted cost for the additional capacity is £759,749, leaving a surplus of £860,960. This surplus was repurposed to the BRINNS nutrition programme, also a CDEL-funded intervention. These added installations are ongoing and progressing well with lessons from the earlier phase of delivery being applied to ensure smooth procurement and operations.

Recent data indicates a notable increase in the utilisation of field hubs, with an 18% rise in individuals served and a 16% increase in organisations using the services. However, the Red Roof hub experienced an 18% decrease in individuals served alongside a 43% decline in organisations’ usage, attributed to decreased demand from international NGOs due to severe ODA funding cuts. Similar cuts have also impacted IOM as managers of the hubs, and it remains to be seen how the current funding model, with cost recovery from partners occupying the hubs, will be sustained.

Lessons learned this year and recommendations for the year ahead

The IOM-delivered project, through its capital investment in Nigeria's humanitarian hubs, offers valuable insights for FCDO's strategic humanitarian approach, particularly for enhancing resilience, adaptability, and the sustainable impact of life-saving interventions.

A primary lesson is the critical importance of "enabling ecosystems" for sustained humanitarian impact. This experience, where solar power installations faced operational funding challenges for the hubs they served, underscores that life-saving activities depend on a complex chain of enablers, from energy and logistics to security and proximate management capacity. FCDO's humanitarian focus must therefore extend beyond individual project outputs to foster the resilience of the entire service ecosystem. This calls for FCDO to champion a "service endurance" approach, actively engaging with partners and other donors to secure the long-term operational viability of critical shared infrastructure.

For significant FCDO investments like the solarised hubs, this would involve proactive, external-facing advocacy to secure ongoing operational funding, foster wider ownership, and integrate climate-friendly solutions more broadly, and earlier, into how humanitarian assistance is delivered. Furthermore, embedding resilience-building activities within such capital projects, such as developing local technical expertise for management, is crucial for their long-term value and operational continuity, despite strict CDEL spend eligibility rules.

Output Title	Expansive upgrade to humanitarian aviation infrastructure in North-East Nigeria implemented.
Output number:		2	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
# of fuelling operations without disruptions per month	5 disruptions per month	<5 disruptions per month / Milestone target met expectation - A
# of seats in passenger waiting areas	40 seats	Result: 30 seats / The terminal still in construction, so baseline figures still hold - Output moderately did not meet expectation - B
Reduction in passenger wait times (in Minutes) for security screening	25 minutes	Result: 0 minutes / The terminal still in construction, so baseline figures still hold - Output moderately did not meet expectation - B
Reduction in cargo processing time (hours)	2 hours	Result: 0 hours / The terminal still in construction, so baseline figures still hold - Output substantially did not meet expectation - C
Proportion of Power needs of the UNHAS operations at Maiduguri Airport met through the installed hybrid SPSS to power UNHAS facilities	0%	Result: 0% / Solar Powered Systems still in installation process - Output substantially did not meet expectation - B

Briefly describe the output’s activities and provide supporting narrative for the score.

This output of the SHAN programme, implemented by the United Nations Humanitarian Air Service (UNHAS) and managed by the World Food Programme (WFP), is dedicated to an upgrade of the humanitarian aviation infrastructure at the Maiduguri International Airport.

This £3 million component is designed to directly enhance the operational capacity, reliability, and efficiency of critical humanitarian air transport services. The project's scope includes the construction of a passenger terminal, a dedicated UNHAS operational office, an on-site medical centre, a robust powerhouse (for generators), a fuel testing laboratory, a flight planning office, and an enlarged cargo warehouse. It also aims to diversify the power sources for the facilities to use SPSS. Integral to these physical structures is the procurement and installation of essential operational equipment, a mobile fuel storage tank to ensure a consistent and independent fuel supply for aviation operations (which before now was being shared with government and private airlines), and the solar power system intended to improve environmental sustainability and reduce long-term operational running costs for the newly developed UNHAS facilities. The broader aim is to provide a standalone humanitarian aviation hub, that improves access for aid workers and the timely delivery of life-saving supplies to highly vulnerable populations in remote and insecure areas of NE Nigeria.

The 'B' score awarded to this output reflects a project that, has navigated complex initial approval and design phases and made some important progress in procurement. but has suffered from delays in awarding contracts and subsequent poor contractor performance. This included repeated tender failures for critical equipment and major contractor underperformance in executing construction components of the project. This has led to substantial delays against the original 1-year project timeline.

Consequently, the core infrastructure components including the terminal, offices, and specialized facilities—are largely still under active construction or, in some cases, awaiting re-procurement following contract terminations. This means that the anticipated operational benefits and the achievement of most key performance indicators tied to facility completion and functionality remain unrealised as of the latest reporting period.

The project was originally planned to run from April 2024 to March 2025, with the initial quarter (April-June 2024) focused on foundational activities. These included conducting detailed topographical and geotechnical surveys essential for design work and contracting external design services for the planned construction.

The final design review process for the main construction lots proved time-consuming, involving extensive input from multiple WFP technical units (covering aspects like water, ventilation, IT network, and security) and local authorities. A significant financial risk also emerged concerning the solar power component when cost estimates were significantly exceeded.

Progress continued into the third quarter, with a notable achievement being the successful acquisition of all necessary written approvals from key stakeholders including Federal Airports Authority of Nigeria (FAAN) HQ (for land allocation), the Federal Ministry of Aviation (airport works approval), and the Borno State Government (for use of the security building). The additional requirement of these approvals were unexpected, as the project had already received written approval from the FAAN but were necessitated after changes in aviation officials appointed.

Procurement delays including several retenders and lack of vendors available for some specialised equipment saw significant delays in project completion anticipated by the end of 2024. Contract terminations were also required where commitments could not be met. A time extension was subsequently agreed with UNHAS/WFP on the basis that all costs were committed appropriately (explained below).

These extensive and interconnected delays, multiple tender failures, and contract terminations explain the current status of the output indicators. The new UNHAS terminal, which would house the expanded passenger waiting areas and improved security screening facilities, is incomplete. Similarly, the upgraded cargo processing facilities are dependent on the new cargo warehouse construction. This means baseline figures for passenger numbers, wait times, and cargo processing times still currently hold, leading to 'B' and 'C' scores for these specific indicators. With the solar power system installation only recently contracted and contingent upon the completion of initial building structures (expected in July 2025), its contribution to UNHAS's power needs is presently 0%. The single ‘A’ score stems from existing fuelling arrangements maintaining a satisfactory level of operational stability for the time being.

The overall 'B' score appropriately reflects a project that, while demonstrating considerable effort and adaptive management by UNHAS/WFP in navigating an extremely difficult procurement and contracting environment in NE Nigeria, is substantially behind its original schedule. Most of the transformative physical infrastructure, which is the core of this output, is yet to be delivered, meaning the project is currently only moderately meeting expectations for its advanced stage of implementation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The most substantial change in the implementation of this component was the termination of the main construction contracts. This decision forced a major re-planning of the construction element of the project. This major reset alongside previous delays due to frictions with obtaining regulatory approvals has directly led to a revision of the overall project completion date, with the new target now being December 31, 2025, a significant extension from the original March 2025 end date. This was approved by the SRO and Development Director in February 2025.

WFP is proactively working to identify and ensure that preferable and technically capable vendors were registered within their procurement systems before re-launching tenders. This more targeted approach has since yielded positive results, culminating in the successful tenders for major equipment packages. WFP has also committed to covering any further cost escalations.

WFP aims to complete all technical and financial evaluations for the new construction tender process by the end of May 2025, with the objective of having a new, capable construction contractor mobilized and commencing work by mid-June 2025.

Lessons learned this year and recommendations for the year ahead

The challenging implementation journey of the UNHAS-led aviation infrastructure enhancement offers several lessons and recommendations for FCDO. These extend beyond the specifics of this single project, informing how FCDO might approach future complex infrastructure initiatives in similarly demanding and volatile humanitarian contexts as NE Nigeria.

First, the impact of challenges encountered when relying on standard UN procurement processes for highly specialised and short-timeframe capital infrastructure components, and subsequent procurement bottlenecks should not be underestimated. Clearer assessments should be made of the pool of qualified and technically compliant vendors during the proposal process, with options for FCDO to engage in earlier dialogue on potential risks of extensive and complex procurement processes. FCDO should also consider engaging in-house commercial expertise earlier on to assess proposed timelines and procurement risk assessments.

The successful delivery of important capital infrastructure projects managed by UN partners in severe-risk environments necessitates a more dynamic and integrated approach to joint risk ownership and adaptive programme management than is allowed within standard oversight and reporting mechanisms. UNHAS consistently identified emerging risks and provided detailed proposed mitigations throughout the implementation period. However, the project was subject to significant delays for a number of reasons which impacted the agreed timelines. This pattern suggests that while specific risks were well documented, the ability to collectively pre-emptively address cascading impacts of this could be improved. In addition, FCDO did not have the right arrangements in place to foresee the emergence of the patterns early and did not sufficiently question and test the assumptions shared by UNHAS as to ensure better delivery.

As such, FCDO should seek to establish a more robust governance and risk management approach, which will collaboratively provide the needed confidence and course correction. This could involve the development of a technical review routine with support from subject matter experts within the FCDO (an action already being explored), to clearly identify risk points through more frequent progress review conversations and establishing pre-agreed triggers for intervention (by the SRO) if major risks materialise.

Following on this, the potential limitations of standard UN partner contract management and performance enforcement mechanisms when dealing with their own sub-contractors, particularly in the context of time-bound capital projects where quick action is useful to consider, particularly where decisive action is required in the event of underperformance of contractors. FCDO should explore negotiating exemptions to standard processes with UNHAS for managing vendor performance, for the rest of the implementation duration.

FCDO could aim to negotiate time-bound performance metrics, as well as clearly defined break clauses or off-ramps for project delivery in future infrastructure projects, even in complex humanitarian settings.

## D: VALUE FOR MONEY

The programme’s core VfM proposition, outlined in the BC, aimed to enhance humanitarian operations through strategic capital investments, focusing on economy, efficiency, effectiveness, and equity. This assessment reviews performance against that proposition, considering key cost drivers, VfM dimensions, and makes an overall judgement on continued programme viability.

The SHAN programme's key cost drivers, initially expected to be the procurement of specialised supplies, technical expertise for design and installation, and core operational costs for new infrastructure, have varied across its two projects. The solarisation of humanitarian hubs was managed effectively through agile financial oversight, leveraging economies of scale and responding to favourable market price drops for components, resulting in a 22% under-budget delivery. In contrast, the UNHAS/WFP-led aviation infrastructure improvement faced significant cost drivers due to persistent procurement delays, multiple equipment tender failures, and inefficiencies from terminating and re-tendering major contracts, which would likely necessitate the activation of the contingency fund to manage overruns. This would be confirmed at the next review meeting in June 2025.

Assessing performance across the VfM dimensions, the economy delivered is exceptional. The significant underspend enabled scope expansion and repurposing of over £800,000 to another FCDO programme, generating independently verified operational cost savings for the hubs exceeding 50%, with IOM reporting fuel cost reductions nearing 90% at deep-field sites. The economic benefits could be higher, contingent on the successful completion of the delayed airport infrastructure, with current returns shaped by adaptive recovery costs from implementation setbacks.

On efficiency, the programme transformed hub operations, with independent verification confirming the new solar systems meet international standards and provide reliable 24/7 power, ensuring complete energy security for the hubs. Although intended efficiencies in aviation passenger and cargo processing are not yet achieved due to ongoing construction, current efforts aim to deliver future operational gains. This will be even more important as rising insecurity that will increase the utility of the aviation facilities and current funding pressures will elevate the benefits created.

The strategic effectiveness in improving humanitarian access remains a critical objective for the NE response. The programme has directly enhanced aid delivery by providing stable, uninterrupted power, allowing humanitarian workers to focus on their core mandates. The achievement of the output 2 indicator on minimising fuelling disruptions suggests some underlying operational resilience is maintained during the ongoing implementation phase.

The programme upholds the principle of equity by improving and sustaining humanitarian service delivery in hard-to-reach areas, serving highly vulnerable populations. The solarisation project demonstrated cost savings intended to contribute to affordable hub access for all users, including National NGOs, aligning with the Business Case. Aviation access will become even more vital for maintaining equitable and reliable air access for all humanitarian organisations operating in the region, as the humanitarian reset and rising insecurity impede safe road travel.

From an environmental VfM perspective, the programme delivers an independently verified annual CO2 emissions reduction of approximately 697 tonnes, exceeding Business Case projections and enhancing the programme's VfM when shadow carbon pricing is applied, strongly underpinning its International Climate Finance (ICF) credentials. The sustainability of programme assets is supported by extensive component warranties (10-25 years) and multi-year maintenance contracts.

Considering this performance, the SHAN programme continues to represent Value for Money, and its continuation is strongly justified. This assessment is anchored by the outstanding, multi-faceted success already achieved, delivering substantial and verifiable VfM through financial savings, enhanced operational effectiveness for critical common services, and significant environmental benefits, while enabling strategic reinvestment of its underspend. This performance has effectively de-risked a major component of the total SHAN investment and provides a robust foundation for judging the programme's overall merit.

A key long-term VfM consideration for the programme centres on ensuring the operational sustainability of the supported facilities, particularly in light of worsening external funding pressures. SHAN remains aligned with FCDO Nigeria’s strategic objectives, the UK’s 'Force for Good' agenda, and contributes to ICF targets.

E: RISK

Overview of risk management

The "severe" overall risk rating of the programme reflects the challenges of delivering humanitarian capital projects in NE Nigeria.The programme fully operated within its risk threshold

The implementation has tested the FCDO humanitarian team’s approach to managing risks through its partners, providing insights into the effectiveness of current delivery models and the tension between prioritising capital investment creation and long-term operational viability, and the demands of maintaining sufficient fiduciary assurance.

The varied efficacy of delivery modalities for capital asset creation within the UN system in this challenging context is obvious, showing the limited materialisation of some of the programme’s delivery risk expectations. While one stream of SHAN's capital investment, focused on sustainable energy for humanitarian hubs, demonstrated remarkable adaptive capacity in procurement and execution leading to exceptional outcomes and VfM, another highlighted major systemic risks when downstream vendor performance fails. This necessitated decisive programme-level interventions, including multiple contract terminations and extensive re-planning, offering FCDO useful lessons for tailoring oversight and support based on the specific nature of capital work and partner execution models, rather than a one-size-fits-all model for UN agencies.

The programme has also shown the linkage between successful capital asset delivery and the long-term operational sustainability of the services those assets are designed to enable. The very success of the solar power system installations, for instance, provides a rationale for sustained funding for it during ongoing conversations the ongoing operational viability of the humanitarian response now challenged by sector-wide funding cuts. It self-justifies the investment, especially with increasing worries on access just as humanitarian needs appear to be spiking.

This transforms a sector-wide concern into an operational risk for FCDO, highlighting the need for programmatic coherence across the humanitarian portfolio to ensure the long-term impact of UK investments in future common services. HARP serves as a mechanism to sustain the immediate-term use of the hub, while acknowledging the broader funding uncertainties in the sector—factors that should be considered when assessing the long-term benefits of the investment, which remains a valuable humanitarian asset supporting ongoing response efforts. The humanitarian team will continue to monitor the evolution of this.

SHAN’s implementation has underscored the imperative for programmatic agility within rapidly changing contexts, highlighting context risks beyond the immediate physical environment. Beyond managing standard environmental or security factors (such as the impact of flooding on delivery), the programme has required flexibility to both capitalise on unforeseen opportunities (like significant cost savings leading to beneficial scope expansion within the solar energy component) and to undertake re-adjustments in response to major delivery failures (as seen in the extensive re-planning for the aviation infrastructure elements).

Alongside this, while SHAN programme offers measurable climate benefits particularly through the solarisation effort, it does entail significant climate and environmental risks. Immediate threats include construction related issues such as soil erosion, water strain, pollution, as well as the flood related delays. Post-delivery, risks not owned by FCDO would need to still be monitored by the partners. The delivered infrastructure remains exposed to similar shocks as above, while desertification may reduce solar efficiency A rebound effect could see increased utilisation of enhanced services (aviation and hubs) offset emissions savings. Climate-driven conflict or donor shifts may also render assets underused. There is also the risk of future liability: safely decommissioning solar panels and batteries could constitute hazardous e-waste contaminating a fragile local environment.

Fiduciary risks, inherent in a procurement-heavy infrastructure programme within Nigeria, remain a constant consideration. Fiduciary oversight for this programme has been managed through a multi-layered assurance approach, combining UN partners' internal control systems with FCDO's specific CDEL guidance, TPM verification supported by due diligence assessments, regular review meetings and active direct monitoring, where possible. No major fiduciary issues have been flagged in the programme reporting during this period, but sustained vigilance is essential.

The significant re-procurements undertaken, while indicating materialised risks, also represent the application of controls to safeguard VfM, high level risk ownership by implementing partners, ensured proper fund re-allocation when initial delivery approaches proved unrealistic. It also shows the humanitarian team’s fairly adaptive management and elevated risk tolerance as well as proactively engaging seniors internally to allow for more time to deliver outputs.

Given the intensive recovery efforts for some infrastructure components and the emerging systemic questions around the operational sustainability of assets already delivered, the "Severe" risk rating for SHAN remains appropriate. This is alongside the standard physical context risks for the NE, around high levels of insecurity, and environmental factors such as localised flooding which have intermittently impacted progress but have been managed by partners without derailing overall objectives.

Overall, risk management has been necessarily dynamic, with partners and FCDO actively engaging to address significant emerging issues. The humanitarian team’s strategic risk management focus for the remainder of the implementing period will be twofold: ensuring the successful execution of all revised delivery plans for infrastructure still under development, and proactively engaging with partners and the wider humanitarian system on sustainable operational models for all assets created under SHAN. This approach will safeguard the long-term value and overall impact of this important UK investment.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The management of SHAN by FCDO Nigeria’s Humanitarian and Resilience Team (HART) has been a dynamic process of navigating complex UN partnerships, significant delivery contrasts between its major delivery component, and leveraging internal FCDO expertise to steer the innovative CDEL intervention within a high-risk context. SHAN represents one of 2 CDEL programmes, co-commissioned together as the humanitarian team’s first foray into this sort of capital-funded programming. The commercial and delivery interactions with SHAN’s two UN implementing partners have also provided significant learning.

  Summary of Budget Allocation (FY 2024/25)
Component Code	Partner	Budget (£)	Payments received (as at May 2025)	Spend & committed
400131-401	IoM	£7,250,000.00	£6,385,460.00	£6,055,668.38 (94.8%)
400131-402	UNHAS/WFP	£2,670,000.00	£2,670,000.00	£2,334,198.12 (87.4%)
		£9,920,000.00	£9,055,460.00	£8,389,866.50 (92.6%)

The solarisation project showcased a partner (IOM) with considerable commercial agility and robust financial stewardship. They effectively adapted procurement strategies to challenging market conditions, resulting in exceptional outcomes delivered significantly under budget, thereby enabling FCDO to reinvest substantial savings into expanded solarisation and another priority FCDO programme (BRINNS). This highlights a successful model of partner-led adaptive management for a particular type of capital investment. The other major stream severely tested the UN implementing partner’s (UNHAS/WFP) capacity for managing highly specialised, multi-faceted construction and niche equipment procurement within a thin and volatile market. This necessitated a much more intensive FCDO oversight role, supporting (and at times pressing for) key commercial interventions such as intensive progress updates and extensive, time-consuming re-tendering processes.

Managing SHAN and one other CDEL programme (BRINNS) in addition to the existing workload of a large humanitarian programme has been challenging for the team and necessitated intensive unplanned activity. Consideration should be given for additional resource in future such programmes.

A cornerstone of FCDO’s effective management has been the strong and continuous engagement with FCDO Nigeria’s Integrated Strategy and Delivery Unit (ISDU) from SHAN’s inception. ISDU's role extended beyond advisory; they were instrumental in co-developing the now office-wide CDEL guidance, a process SHAN helped pilot. ISDU provided crucial, ongoing specialist commercial support for the mobilisation phase and risk advice for the more challenging aviation infrastructure component, assisting HART in navigating complex assurance processes and in strategically escalating progress concerns and significant risks to FCDO Nigeria’s Senior Management through established review platforms (the Line By Line review and the Monthly Financial Reviews – MFR). This internal synergy proved vital to creating high-level acceptance of the risks and ensuing challenges.

SHAN's management has also benefited from its strategic positioning within HART’s wider humanitarian portfolio, facilitating coherence with programmes like HARP and BRINNS. Leveraging HARP’s Third-Party Monitoring mechanism for the solar energy investments provided valuable independent verification, while the ability to repurpose solar savings to BRINNS exemplified flexible portfolio management. The HART team’s proactive collation of information on global aid funding reductions and its potential impact on the operational sustainability of SHAN-created assets demonstrated strategic foresight beyond immediate delivery concerns. This forward-thinking was bolstered by high-level endorsement, with SHAN receiving ministerial support as part of the HARP extension approval, accompanied by an expectation for FCDO Nigeria to scale up similar innovative climate-led approaches and integrate lessons from SHAN’s capital funding experience into wider humanitarian programming.

Partner reporting has generally been regular and detailed, enabling FCDO to track progress and challenges. Financial oversight adapted to the performance of each programme stream: the solar energy work demonstrated accurate forecasting and excellent budget control, while the aviation infrastructure component required more intensive FCDO engagement on financial burn rates, the phasing of funding tranches which initially impacted procurement timelines, and the management of its contingency fund.

Learning from SHAN’s management journey, FCDO can further enhance its effectiveness as a partner in future complex CDEL initiatives by ensuring very early-stage integration of specialist technical (commercial, engineering) advice in project design and risk assessment phases, especially when working with UN partners on activities like infrastructure that are non-core to their mandates or BAU. Continued advocacy at a corporate FCDO level for more adaptable UN agreement frameworks specifically tailored to the unique demands of capital programming, and fostering a culture of deeply collaborative, problem-solving dialogue with implementing partners, will remain essential for successfully navigating the inherent uncertainties and co-managing the risks of such vital and innovative programming in challenging fragile contexts like NE Nigeria.

Date of last narrative financial report	WFP (UNHAS) – May 2025 / IoM – 4th April 2025	Date of last audited annual statement	WFP (UNHAS) – March 2024 / IoM – January 2020