Amendment No. 2 to the Contribution Arrangement between the United Kingdom and WFP for Support for the United Nations Humanitarian Air Service (UNHAS) to Infrastructure Development for Enhanced Humanitarian Access in North East Nigeria

The Parties to this Amendment No. 2 (the Amendment No. 2) are:

The United Kingdom, represented by the representative of the Secretary for State for Foreign, Commonwealth and Development Affairs in Nigeria:

pp Development Director, FCDO Nigeria

(the Authority);

and

the World Food Programme, represented by its Nigeria Representative and Country Director:

World Food Programme (WFP)

(the Implementing Partner):

referred to collectively as the Parties and each individually as a Party.

This Amendment No.2 sets out changes to section 6 of the Contribution Arrangement that was signed by both the above parties on 25th April 2024, for the project entitled: Infrastructure Development for Enhanced Humanitarian Access in North East Nigeria – WFP Nigeria 2023-2027 Country Strategic Plan (CSP) Outcome 5, Activity 9 (the Contribution Arrangement)

The Parties hereby agree:

That following the decision of the Authority to grant a No-Cost Extension (NCE) to the project, I propose that the end date of 31st March 2025 in paragraph 1b of the original contribution arrangement be deleted and replaced with 31st December 2025. This extension shall not involve additional funding or costs, and all other terms and conditions of the original Contribution Arrangement signed on the 25th of April 2024 and amendment letter 1 signed 21st November 2024 shall remain in full effect.

Unless otherwise defined in this Amendment No. 2, all capitalized terms and expressions used herein shall have the respective meanings ascribed to them in the Contribution Arrangement. Any reference in the Contribution Arrangement to the “Contribution Arrangement” shall be construed as a reference to the Contribution Arrangement, as amended by this Amendment No.1 and Amendment No. 2.

All other terms of the Contribution Arrangement remain unchanged. The terms and conditions of this Amendment No. 2 shall be incorporated in the Contribution Arrangement as though set forth in full therein.

This Amendment No. 2 shall enter into force on the date of signature.

___________________

Signed for the Implementing Partner	Signed for the Authority

Name:	Name:

Date:	Date:	03 March 2025