Amendment Letter No. 1/2025

FCDO Project Name: Sustainable Energy for the Humanitarian Hubs in
    Northeast Nigeria Project

FCDO Project Number: 400131-101

I refer to the Memorandum of Understanding between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) and the International Organization for Migration (IOM) (“the Partner”) signed on 31st May 2024.

Following recent discussions, FCDO proposes to decrease the amount made available to IOM by £860,540 to complete the revised scope of activities and change the end date of the Memorandum of Understanding (“MoU”).

I propose that the figures and words £7,246,000.00 (Seven Million Two Hundred and Forty-Six Thousand Great Britain Pounds Sterling) in paragraph 3 of the original Memorandum of Understanding be deleted and replaced with the figures and words £6,385,460 (Six Million Three Hundred and Eighty-Five Thousand, Four Hundred and Sixty Great Britain Pounds Sterling). The table in paragraph 3 of the initial MoU is deleted and replaced with the following

FCDO Financial year	Annual Allocation (£GBP)
01 June 2024 -31 March 2025	£6,385,460.00
Payment date	Instalment date
Upon signature of the MoU: 01 June 2024	£5,796,800.00
Upon completion of 80% of first instalment or at the latest 01 March 2025	£588,660.00

I also propose that the end date of 31st March 2025 of the original MoU in paragraph 5 of the original Memorandum of Understanding be deleted and replaced with 30th September 2025.

The Partner will provide FCDO with a progress report on the execution of the project covering the implementation period ending 31st March 2025 within six (6) weeks of the signing of this amendment. The Partner will make a good faith effort to provide a final narrative report within 3 months after the new end date of the project.

The Project Document and Project Budget attached to the initial MoU are replaced with the attached Project Document Rev. 1 and Project Budget Rev. 1, effective from the date of signature of this Amendment.

All other terms and clauses of the original MoU not revised or referenced in this amendment still apply.

Nothing in or relating to this Amendment or the MoU shall be deemed a waiver, express or implied, of any of the privileges and immunities of the International Organization for Migration.

This letter of amendment will place on record our common understanding of the above change(s) and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 1, 2025.

Please sign a copy of this letter and return to us to sign. We will share with you a fully signed copy for you to retain for your own records.

Signed on behalf of FCDO:
Name:
Position:
Address/Contact Details:
Date:

Signed on behalf of the Partner:
Name:
Position:
Address/Contact Details:
Date: