## Annual Review

Title: ASEAN-UK Supporting the Advancement of Girls Education (ASEAN-UK SAGE) Programme
Programme Value £ (full life): 30 million		Review date: May 2025
Programme Code: 400133	AMP start date: 24/01/2024	AMP end date: 31/03/2028

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400133
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400133

## A: SUMMARY AND OVERVIEW

Description of programme
The ASEAN-UK Supporting the Advancement of Girls’ Education (ASEAN-UK SAGE) programme was established following the UK’s designation as a Dialogue Partner to ASEAN in August 2021. As the first initiative under the ASEAN-UK Plan of Action (2022–2026), it represents a flagship collaboration, reinforcing the UK’s commitment to deepening strategic ties with partners across the Indo-Pacific. As a multilateral education programme operating across 10 ASEAN Member States (AMS) plus Timor-Leste, ASEAN-UK SAGE has secured strong political and institutional support from ASEAN, with full accreditation and an approved workplan for the review year endorsed by all AMS through the Programme Steering Committee.

ASEAN-UK SAGE adopts a modern, partnership-based development model, well-suited to a multilateral, middle-income context and supporting UK ambitions in a 0.3% Official Development Assistance (ODA) future. Its emphasis on technical expertise; mutual collaboration and dialogue; institutional strengthening; and research, data, evidence generation and influencing is designed to deliver sustainable improvements in education outcomes across the region. This approach is strongly endorsed by ASEAN and contributes to regional integration and the narrowing of development disparities among AMS.

The UK is the only Dialogue Partner focusing on basic education, which is greatly appreciated by the ASEAN Secretariat (ASEC) and AMS due to persistent challenges at this level of education in several AMS. The programme aligns with ASEAN’s Socio-Cultural Community Blueprint 2025, specifically by promoting human capital development, economic self-reliance, and sustainable livelihoods, especially among the poor, through access to education, employment opportunities, entrepreneurship and micro-finance. Spanning the full education lifecycle, ASEAN-UK SAGE contributes to long-term socio-economic development through three strategic pillars:

1. Foundational learning. Drawing on the UK’s global leadership and expertise to strengthen the evidence base and support governments in prioritising basic literacy and numeracy, a critical sector for long-term growth and ASEAN integration.
2. Out-of-school children and youth (OOSCY) and marginalised groups. Addressing educational inequity and supporting inclusive human capital development.
3. Gender barriers for employment. Enhancing digital and STEM skills for girls and women, including through a UK university scholarship scheme.

In the context of 0.3% ODA, ASEAN-UK SAGE remains a vital platform for UK engagement in Southeast Asia, offering agile, flexible policy engagement across 11 countries. Its broad scope also strengthens UK links to higher education and skills across the region.

This second Annual Review covers 1st April 2024 to 31st March 2025.

Summary supporting narrative for the overall score in this review
For the review year, the programme scores an A overall, with four output scores of A, B, B, A.

This was the first full year of implementation for ASEAN-UK SAGE, having completed the inception period in January 2024 and contracting by April 2024. There have been notable achievements for the programme in the review year, including establishing partnerships and strategies; recruitment of technical leads; supporting the completion of the Southeast Asia Primary Learning Metrics (SEA-PLM) 2024 survey in seven countries with specific support to the inclusion of Timor-Leste for the first time; designing and launching pilots in two countries; completing several pieces of research; and providing technical assistance to support AMS through the Southeast Asia Ministers of Education Organisation (SEAMEO) and directly to AMS to undertake the SEA-PLM survey.

Output 1 scores an A. The programme designed and delivered two agreed policy dialogues to disseminate a regional OOSCY study and discuss foundational learning at the Education World Forum 2024 in London. Additional opportunities were sought to promote data and evidence in the region through the programme.

Output 2 scores a B. Sixteen research and data products that respond to gaps in data in the region were completed in the review year across all three pillars of the programme. Dissemination was not completed for all, and several products planned for the review year will be completed and disseminated in the next review year.

Output 3 scores a B. Pilots in line with the global evidence from the Global Education Evidence Advisory Panel (GEEAP) report Smart Buys were launched in Cambodia, a digital skills pilot was launched in Timor-Leste, and the Women in STEM Scholarship scheme was delivered across all countries for students to study in the UK. Pilots did not go ahead in Lao PDR within the review year and are being discussed for the next review year.

Output 4 scores an A. A significant amount of technical assistance was provided through two main partners – the Australian Council for Educational Research (ACER), the technical partner on the SEA-PLM, and the EdTech Hub, providing technical assistance to SEAMEO with a mandate to support AMS.

Major lessons and recommendations for the year ahead
This first full year was about establishing partnerships and activities. While a significant amount has been achieved, there are key lessons and recommendations for improvement in the next review year and to deliver against strategic policy changes at the FCDO.

Lesson	Recommendation	Responsible	Deadline
With many partners and institutions in the programme, including FCDO, ASEAN Secretariat (ASEC), four delivery partners – British Council, SEAMEO, ACER, and Ed Tech Hub – and 11 AMS, the governance structure and roles and responsibilities have been tricky to pin down and needs to be clearer.	The programme needs to establish clear roles and responsibilities for coordination, accountability, and decision making.	FCDO, British Council and partners	September 2025
There have been delays in getting a consolidated joint workplan and budget for the FY 2025/6.	Quality year 3 workplan and budget to be submitted and finalised.	British Council and partners	June 2025
SAGE is strategically placed to influence and strengthen institutions in the region and work with multilaterals through its programme’s delivery and engagement with key global, regional and national actors in education to drive systemic reforms.	Develop a clearer vision of how SAGE will influence and strengthen institutions through its four output areas. / Deepen engagement with multilaterals for collaboration and sustainability.	British Council and partners with FCDO / FCDO with partners	September 2025
Further collaboration from all partners on research and communications / advocacy / influencing in the programme is necessary to maximise the benefit of all expertise within SAGE.	Put in place protocols for research to ensure all partners are collaborating; approvals go through FCDO. / Strategy for influencing at outcome level to be developed. / Develop a communications strategy to turn policy wins into clear, compelling content.	British Council in collaboration with al partners	September 2025
SAGE is a regional ASEAN focused programme, not a bilateral programme in 11 countries, though it does include bilateral activity in ODA-eligible countries that support ASEAN-wide objectives.	Set out a clear vision for how this works in practice and what we can and cannot do.	FCDO with British council and partners	September 2025
MEL processes need to be consolidated and revised, including the programme theory of change (especially how outputs will lead to outcomes), logframe, QA of deliverables, and evaluation for the end of the programme.	Review the ToC, the logframe, and MEL functions.	British Council in collaboration with all partners / Approvals FCDO	September 2025
Considering the UK ODA reductions to 0.3%, the FCDO needs to reconsider the design of the programme and future options.	Consider all options for programming beyond 2025/6.	FCDO	October 2025
A value for money indicator refresh needs to be finalised to ensure the best value for the British taxpayer.	VfM indicator review to be finalised	British Council / FCDO	September 2025

Other recommendations are embedded Section C below.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
In the inception phase of ASEAN-UK SAGE (2023–24), the theory of change (ToC) in the Business Case (Figure 1) was reworked to the current ToC (Figure 2). The programme is working to the same original goals in the Business Case.

Figure 1. ASEAN-UK SAGE ToC (Business Case)

The impact level in the ToC remains valid: Quality-of-life outcomes improved through a more sustained, supported access to an inclusive, quality education offering which also helps to narrow the development gap in ASEAN.
The original outcome was separated into three outcomes covering the three pillars of work. These are still valid. However, the ToC needs to be revisited in the next review year to ensure that the programme is making the most of its unique design and position and delivering a regional approach across the three pillars. The revision also needs to ensure that there are clear indicators at outcome level to measure in the next review year. Outcome 2 may need to be revisited considering what we now know about the Out-of-school Children and Youth (OOSCY) situation in the region through research in this review year.

The ToC overall addresses key issues in the region, including inclusion of marginalised social groups, and remains valid.
Figure 2 ASEAN-UK SAGE ToC (current)
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme has been operational for one full year at the time of the review. Based on the outputs, the programme may be on track to meet intended outcomes and impact statement, but more evidence is required, and the programme needs to be more intentional in the next review year to ensure a strong regional approach and that the outputs lead to the outcomes. For example, the programme needs to ensure that all research has a purpose and can drive policy influence at the outcome level, and that the delivery and assessment of pilots comes with ample policy influencing for scale up.

For each outcome / pillar there are four interlinking outputs which should work together for a strong offer for the region. For example, in foundational learning, combining research and data with evidence from pilots can inform policy dialogue with AMS and support decision makers to invest budget where the evidence is greatest (such as on two of the Smart Buys – structured pedagogy and Teaching at the Right Level – TaRL). Technical assistance can ensure AMS have the support to use the evidence and scale up activities. The design enables this integration, but the programme needs to be intentional and ensure it is realising this, and ensure the whole is greater than its parts. A tighter focus on evidence influencing in the region is needed.

The programme is finding its feet. Data gap mapping shows where the region is lacking data, and partners are working through plans to address some gaps. However, research in the coming review year should be more focused. Recommendations from research undertaken, such as the three pillar thematic studies by ACER, need to be followed up as they offer opportunities for a regional approach such as frameworks for regional monitoring. The programme partners will need to ensure that responding to requests (of which there are many through AMS and SEAMEO) align with the programme’s ToC and strengthen the integration of the outputs to reach the outcomes – policy influence and real change for children in the region. There are several opportunities to more tightly focus on assisting AMS to use evidence and make positive key policy decisions in the next review year a) through the regional learning assessment (SEA-PLM) follow up to address the data b) through small pilots on the ground that improve the evidence base in the region of what works c) our convening power and use of ASEAN and SEAMEO structures to directly engage with AMS d) our direct engagement through TA with three AMS in the next year.

A clear achievement of the UK Mission to ASEAN and the programme is to establish the UK as a partner in education in the ASEAN region, forming trust-based relationships with key education bodies in ASEAN including ASEC, SEAMEO, SEA-PLM, UNICEF, UNESCO, and the World Bank. These relationships make the UK a unique Dialogue Partner in education through the various support to and engagement with the convening powers and multilaterals. The UK has also been formally recognised as a regional partner in SEA-PLM. Combined, together with partners, the programme can support and influence AMS on education policy. These bodies also convene AMS on broader education areas such as higher education and skills, and UK embassies in the region bilaterally engage on key topics such as tech and Artificial Intelligence in education. Investments into regionally embedded institutions go beyond the ASEAN-UK SAGE focal areas and is a strategic investment.

Beyond influence and engagement at the policy level, the programme is also beginning to form relationships with AMS. ASEAN-UK SAGE has launched and is implementing Women-in-STEM Scholarships (2024-25 and 2025-26), evidence-based pilots, and has supported SEA-PLM learning outcome assessment in seven countries – a significant achievement in its first year of implementation.

ASEC showed strong appreciation and buy in to the programme – as reflected in its consistent coordination efforts and active participation in programme design and review, and feedback in formal mechanisms such as the ASEAN-UK Joint Cooperation Committee. In the next review year, the programme will directly support a State of Education in ASEAN Report which will for the first time in over a decade compile comprehensive data on the whole life cycle of education (preschool to higher education and skills) in the region, and support ASEC and AMS to design a new five-year workplan. The seminal report will have wider impact through dissemination and launch including UK visibility.

It is too early to have concrete impact yet, but there are emerging signs that ASEAN-UK SAGE will be able to deliver results in the region. There is good evidence that the ASEAN-UK SAGE programme is highly relevant, uniquely placed to engage with key issues in the region, and appreciated by all actors, and therefore this Annual Review recommends it be continued if wider contextual factors of UK spending allow. It is fostering a modern partnership and supporting multilateralism, offering technical expertise, policy dialogue, evidence sharing and testing rather than service delivery, which is appropriate in this mostly middle-income region. It also includes activities in digital and AI, supporting commercial opportunities for the UK. ASEAN-UK SAGE fits well into the Foreign Secretary’s vision for a ‘beyond aid’ approach. The reduction of ODA should not be a barrier to the programming continuing under the current ASEAN-UK Plan of Action or the next one from 2026 onwards, providing there is sufficient budget allocation, and education remains an important sector in which to retain expertise and support in this context because of its critical contribution to social and economic development in the region and UK expertise in this sector.

As a new Dialogue Partner, there are political and reputational benefits to continuing with our new investments into the region, especially when the education support is widely appreciated. The ASEAN-UK SAGE programme has in a very short period raised visibility for the UK in the region and delivers for ASEC, AMS, and embassies across soon-to-be 11 AMS. The next review year will see a healthy budget for the programme, but the outer years from 2026/27 onwards will need to fit into the 0.3% ODA context. The programme is flexible for different budget scenarios – low, medium, and high ODA scenarios, with technical expertise as the core of the programme. Maintaining a presence in education will be important for the UK Mission and this represents value for money of investments already made.

Four out of six recommendations in the last AR have been fully addressed or are a work in progress. The remaining ones: 1) option paper on Women in STEM scholarships and 2) consolidate and refine the MEL and longer-term work plans and structures for the programme, need to be completed by September 2025.

## C. DETAILED OUTPUT SCORING

Output Title	Policy dialogues, informed by rigorous and robust evidence on issues pertaining to the situated context
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	New output

Indicator(s)	Milestone(s) for this review	Progress
Number of policy dialogues delivered (Planned event which delivers on ASEAN-UK SAGE pillar policy goals, engages decision makers with robust evidence and or research).	2	2 / Met expectation.

Briefly describe the output’s activities and provide supporting narrative for the score.
The Output met expectation. In this first full year of implementation, the programme engaged in several discussions and panels to advance programme objectives. Two intentionally designed dialogues are being counted as agreed with the programme team and this output is considered met.

1. SEAMEO and the EdTech Hub collaborated on producing OOSCY high-level research in all 11 countries, and disseminated this at a SEAMEO High Officials Meeting, and at the Comparative and International Education Society (CIES) conference in Chicago.
2. Education World Forum 2024 provided a platform for the programme to lead a discussion at a breakfast for Ministers of Education and senior delegation leads from Asia Pacific (APAC) countries. The breakfast event at EWF was hosted by UK Baroness Barran and Sir Steve Smith and attended by ministers and high officials from AMS. Datuk Dr Habibah from SEAMEO presented the foundational learning crisis in Southeast Asia and the importance of initiatives to address this, including through SEA-PLM and support of ASEAN-UK SAGE.
Additional activities were largely through the EdTech Hub: participating in the SEAMEO-University of Tsukuba Symposium with the theme of Transforming Education to Problem Based Learning in the era of AI and Data Sciences, presenting at Cambodia’s first EdTech Summit, and presenting at the 13th ASEAN Education Ministers’ Meeting: “Transforming Education in the Digital Era.”

Describe any changes to this output during the past year, and any planned changes as a result of this review.
It was decided in October 2024 that ‘papers’ would be removed from the output: Policy dialogues and papers to distinguish dialogues (conferences etc) from paper/digital reports and tools. In this first year of implementation, it became clear that partners get invited to present at and / or attend many meetings and conferences. The programme needs to be clearer on the strategy for policy dialogue, and on ensuring it delivers a clear message to the right people (policymakers and decision makers) to influence tangible improvements in line with the programme outcomes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations for this output in the last AR as the logframe had not been finalised. The causal link between delivery or attendance in policy dialogue and desired outcomes needs to be clearer: The relevant outcomes are: 1. The gap between policy makers’ estimated and actual scale of foundation learning crisis reduced; and 2) Effective, evidence-based policy interventions result in addressing the foundational learning crisis, including supporting reforms in primary teaching and learning, with positive attitudinal shifts among policymakers.

Recommendations (continued numbering from opening section) for upcoming year:
1. A policy advocacy strategy needs to be developed that clearly shows the messages and audience which are the target of ASEAN-UK SAGE’s policy dialogues, and decisions are being targeted / and what success look like. British Council and partners, by September 2025.
2. The logframe needs to be revised to more meaningfully set the outputs and their contributions to the outcomes, and to agree the cap on the number of dialogues delivered and counted by the programme. British Council with partners, by September 2025.
Output Title	Number and type of research, evidence and data (RED) reports, products, resources and tools produced and disseminated
Output number:		2	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	New output.

Indicator(s)	Milestone(s) for this review	Progress
Number and type of research, evidence and data (RED) reports, products, resources and tools produced and disseminated	20	16 / Moderately did not meet expectation.

Briefly describe the output’s activities and provide supporting narrative for the score.
The output moderately did not meet expectation. There were 16 pieces of research, evidence, and data completed by partners in the programme, mainly by the consortium’s research partner – the Australian Council for Educational Research (ACER) – and by the EdTech Hub in collaboration with SEAMEO. ACER’s research includes thematic studies on the three pillars/outcome in the programme (foundational learning, OOSCY, and digital/STEM skills for girls), data gap mapping, to rapid evidence reviews. While 10 were planned, one was a prototype, and another three case studies were not completed and disseminated so will be counted as deliverables in the next review year.

In addition to scoping and evidence reviews relevant to the programme’s overall strategy, EdTech Hub’s work resulted mainly from their collaboration with SEAMEO Centres and the SEAMEO Secretariat. One of the major pieces of work was the Regional study on Out-of-School Children and Youth, complementing an earlier thematic study from ACER, and highlighting interrelated challenges such as limited infrastructure and transport in rural areas, bullying by peers and educators, and mental health issues. It leveraged SEAMEO Centres for data gathering. The study has been downloaded more than 900 times. ASEAN-UK SAGE drew on EdTech Hub’s expertise to produce four overviews[1] supporting the development of a strategy to underpin educational technology as a cross-cutting theme.
[1] Out-of-school children and youth EdTech for girls’ education EdTech for learners with cognitive and learning disabilities EdTech for learners with hearing and visual impairments:

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes to this as the output is new. The indicator for this output measures the RED products being ‘produced’ and ‘disseminated’ but there is lack of clear information on how and where RED was disseminated/used for some outputs, for example rapid evidence reviews. Reporting should include more detail on the dissemination aspect to demonstrate the use and usefulness of RED products produced by the programme and how they contribute to the outcomes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
There are no recommendations related to this output as it is new. As with output 1, the causal link between producing RED products and the outcomes needs to be emphasised. The purpose of producing research is to address a knowledge gap, solve problems, and inform decisions, building on previous research or contributing new ideas and evidence. Therefore, the intention and use of RED needs to be better monitored and assessed in the programme.

Recommendations for upcoming year:
1. Partners to work together to streamline RED processes and deliverables in the ASEAN-UK SAGE programme, ensuring they are complementary, deliver on the outcomes, and have clear concept notes and dissemination / use plans (to be approved by FCDO). By September 2025.
2. In the coming year, strategic and prioritised pieces of research building on findings in the review period should be completed, in OOSCY, AI in education, and further research on the SEA-PLM datasets. Ongoing.
3. As with output 1, the logframe and guidance need to be revised to more meaningfully set the outputs and their contributions to the outcomes
Output Title	Proof of concept interventions (demonstrating feasibility to apply specific interventions in ASEAN)
Output number:		3	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number and type of proof-of-concept interventions successfully implemented and validated	4	3 / Moderately did not meet expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
The output moderately did not meet expectation. Pilots supporting the Initiative for ASEAN Integration in three countries were planned – Cambodia, Lao PDR, and Timor-Leste. The Cambodia pilots were designed and launched in the review year and a pilot was designed and launched in Timor-Leste. The pilots were originally planned to be designed, launched, completed, and validated within the year. By the time the logframe was completed and uploaded at the end of 2024, there had been a delay in recruitment of the technical leads, and collaboration around the pilots between partners and the AMS ministries took longer than expected. The annual reviewers have decided to allow Cambodia and Timor-Leste to be partially counted as they started within the review year and a great deal of work and collaboration took place to achieve that. The pilots in Lao PDR were designed but were not formally agreed with the country or launched in the review year, which meant that this output underperformed. Together with the Women in STEM Scholarship programme, the output scores 3 out of 4 for country level (or 4 out of 6 individual pilots) and fell short of expectation.

There is good momentum around the pilots and collaboration with the British embassies in the region, education ministries, and multilateral partners such as the World Bank. Two pieces of work addressing foundational learning were launched in Cambodia in March 2025. The ‘Strengthening M&E capacity for improving foundational learning outcomes’ which will assess classroom practice and materials used in Grades 1 and 2, and ‘Strengthening retention through Teaching at the Right Level (TaRL) which will improve learning outcomes for 500 children in grades 4 and 5 who are at risk of dropping out. These are based on evidence from the GEEAP’s Smart Buys in education report, using UK expertise (British Council) with partners ACER, Pratham International, and SEAMEO to improve the evidence base in the region and have robust proof of concept models available for policymakers to engage with and use. There are very few TaRL programmes taking place in the region, and this is an exciting opportunity to influence this evidenced-based practice in the region. The programme is collaborating with the World Bank to ensure the TaRL intervention has an appropriate impact assessment and is scaled up nationally in Cambodia using multilateral IDA funds, representing sustainability, vfm, and leveraging the UK’s broader multilateral ODA footprint.

In Timor-Leste, co-delivered by UN Women and the government, SAGE will support young people in two municipalities to develop the skills they need to gain financial independence and contribute to their communities. It will focus on equipping rural youth, particularly girls, with entrepreneurship, digital, and soft skills aligned with local economic opportunities in line with pillar 3 of SAGE.

The Women in STEM Scholarships made 11 awards in 2024, including students from Timor-Leste, and Cambodia. The successful master’s level scholars are offered a life-changing opportunity while the programme nurtures inspirational advocates who can lead as role models for future generations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is a new output and there are no changes, however the Women in STEM Scholarships is in its second year of implementation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
There is a relevant recommendation to the Women in STEM Scholarships from the previous review, which was not completed, to develop an options paper on the future of the scholarship programme. There was also a request to develop an alumni strategy to ensure the VfM of hosting the scholars is maximised. These should be completed by September 2025.

Recommendations for upcoming year:
1. The logframe and guidance should be revised with clear milestones for the pilots, and ensure the guidance is clear what is meant by ‘implemented’ ‘validated’ and by whom. British Council with partners by September 2025.
2. Lao PDR pilots did not go ahead. There is uncertainty on the ability of the programme to continue programming with pilots in the FY 2026/7, therefore should any activity be designed for Lao PDR in the next review year it needs to take this into account, ensure VfM and sustainability of any work undertaken, and should try to work with other partners to enhance sustainability. British Council, by July 2025.
Output Title	Technical assistance services (to support AMS implement RED and pilot project-type interventions)
Output number:		4	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number and type of technical assistance services provided to ASEAN member states	60	72 / Met expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
The output met expectation. There were three main areas of technical assistance (TA) in the ASEAN-UK SAGE programme in the review year:
1. Extensive support to the Southeast Asia Primary Learning Metrics (SEA-PLM) regional learning assessment across seven countries through support to SEAMEO and ACER.
2. TA through the EdTech Hub directed towards SEAMEO, under its mandate to support AMS.
3. Capacity building support to SEAMEO, specifically in improving its abilities to measure its results and support to AMS.
Combined, this is the programme’s TA offer to build capability in AMS directly (through SEA-PLM) and through SEAMEO Centres (EdTech Hub or embedded M&E support in SEAMEO).

SEA-PLM: Co-chaired by SEAMEO and UNICEF, SEA-PLM is a programme designed by and for the region to measure learning outcomes (reading, writing, maths) in Grade 5 in line with SDG4 proficiency standards. In 2019, the data set showed 90% or more learning poverty (children aged 10 unable to read a basic text) in four countries. The 2024 survey, supported by ASEAN-UK SAGE, will show trend data for six countries and baseline data for Timor-Leste. The programme specifically supported the inclusion of Timor-Leste into SEA-PLM, and TA to undertake the survey was delivered by ACER. The data from this important assessment is key to informing decisions on system-wide reform, to improve equitable learning outcomes for students in basic education.

EdTech Hub: Experts in the use of technology in education, the EdTech Hub as a partner on the ASEAN-UK SAGE programme in the review year provided TA to SEAMEO Centres. Examples of the work undertaken include supporting SEAMEO SEN (special educational needs) with the development of a policy guideline on the use of generative AI, SEAMEO TROPMED by identifying effective ways to leverage technology to enhance teaching and learning and SEAMEO INNOTECH with the development of their 11th Five-Year Development Plan (FYDP) through conducting an environmental scan.

SEAMEO M&E: The programme is supporting SEAMEO to build a regional monitoring framework for its 26 specialist SEAMEO Centres across the region, technical assistance to SEA-PLM Strategic Plan 2026-30 development, and SEAMEO Policy Research and Publication capacity building.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There are no changes from the last review cycle as this is a new output. TA and sharing expertise are key to the UK’s modern partnership approach and appropriate for a multilateral programme in a middle-income region. However, there needs to be a more streamlined way for the programme to a) define what the TA is b) state who benefits and why c) measure its impact and get external feedback on its value, and d) ensure it aligns with programme objectives. Currently, there is some ambiguity in how the TA is designed, planned, and implemented and how it contributes to the intended outcomes. Going forward into the new review year, EdTech Hub will support three AMS directly (Indonesia, the Philippines, and Thailand) and to enable this they will reduce SEAMEO TA.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations as this is a new output.

Recommendations for upcoming year:
1. The logframe and guidance should be revised to be clearer on the categorisation by type of TA (e.g. SEA-PLM, pilot-project) and product (e.g. survey tools, capacity building), and reporting against this. This will ensure the programme is targeting beneficiaries, whilst reporting on the extent of its technical service provision and product provision. Also, the link to the outcomes needs to be better made in the logframe. British Council, by September 2025.
2. The programme should provide more transparency around the TA services being proposed so FCDO can also assess their value and should consider feedback loops by recipients. This is important because the partners are the UK’s externally facing partners with AMS. British Council, EdTech Hub and all partners, by September 2025.
D: VALUE FOR MONEY

The total budget expenditure for the year was £3,336,135. There is evidence of VfM in line with the original proposition outlined in the Business Case.

Economy
Three indicators from the business case have been used here. Consultant fee rates, in-sourced roles, and in-person vs remote time inputs. The programme has exhibited some disciplined procurement practices, focusing on cost-effectiveness and resource utilisation, although long-term value and broader impact remain to be fully assessed.

- UK consultants were recruited by the British Council to lead each programme pillar and accounted for 3.84% of the total annual budget. However, they could have been better utilised across the whole programme and not just on pilots, which represented a small proportion of the budget. The UK Mission allocated a UK-Based accredited education adviser from the FCDO education cadre which has increased quality assurance in programme delivery in the review year.
- Regional travel is expected for a regional programme; travel expenditure for core 10 programme management team amounted to approximately 0.8% of the total budget. Overall travel budget including all partners for all activities in the two agreements (including downstream partners) was 4.5% of the total budget.
Efficiency
Three indicators used in the Business Case are ratio of overheads v TA, approval times for programme with ASEC, and identifiable influence of programme activities. While there is scope to improve efficiency through enhanced governance and clearer delineation of roles and responsibilities, there is some evidence of efficiency gains.

Four main cost drivers for the programme are as follows, in % terms of budget:

Cost	British Council	EdTech Hub	Total
Staff	25%	23%	24%
Travel	4%	6%	5%
TA/Activities	58%	48%	56%
NPAC	13%	22%	15%
Total	100%	100%	100%

- ASEC engagement is mainly through the UK Mission and approvals have generally been timely, but the programme has engaged with ASEC through mechanisms such as the Programme Steering Committee and Senior Officials Meetings.
- The programme is working with SEA-PLM (SEAMEO and UNICEF) to ensure global evidence from the Smart Buys is part of the engagement with AMS and has also been used in development of pilots.
Effectiveness
Three indicators used here are activities completed on time and rated satisfactory or more by partners, improvements in SEA-PLM data, and TA/activities improving design of other investments.

- The UK Mission has successfully fulfilled all commitments under the ASEAN-UK Plan of Action in the education sector, supported by ASEAN-UK SAGE, and the programme was positively acknowledged by all AMS during the Joint Cooperation Committee meeting. ASEC has endorsed and appreciated the programme for focusing on areas other Dialogue Partners are not, and for supporting ASEC priority initiatives (State of Education Report and ASEAN workplan).
- At this stage, SEA-PLM data improvements cannot be attributed to the programme but going forward there is a potential for the programme to contribute through influence for evidence uptake. The programme did, however, enable Timor-Leste to participate and benefit from capacity-building efforts for the first time.
- On influencing other investments, a notable example is the Cambodia TaRL pilot, which will be scaled up using World Bank IDA resources. In the review year, significant work went into designing a regional technical forum and ministerial roundtable to influence AMS on two Smart Buys – structured pedagogy/early grade learning, and TaRL – to be held in May which will be followed up through SEA-PLM Initiative 2, in the next review year.
Equity
Three indicators used here are the expansion and impact of disaggregation in the SEA-PLM, gender ratio improvements in digital skills training and employment, and volume of initiatives in IAI countries providing opportunities for marginalised girls and children with disabilities.

- SEA-PLM data disaggregation was expanded in 2024, specifically to include socio-economic status and disability questions. In the next review year, equity data in the SEA-PLM will be analysed using SAGE funding.
- While it is too early to show gender outcomes from initiatives, in Cambodia and Timor-Leste interventions have been designed with clear equity strategies, specifically targeting marginalised girls and minority groups. In addition, research has consistently focused on issues of equity, for example OOSCY, disability, and girls.
Cost-effectiveness
Indicators used here are benchmarking in ASEAN to achieve minimum threshold in basic literacy, estimate of additional funding because of TA and initiatives to demonstrate global evidenced approaches, and long-term cost savings and return on EdTech investments. Information on these indicators is limited at this stage.

- Benchmark data for TaRL will be captured through the Cambodia pilot.
- While there is no data on additional funding yet, the coordination between the World Bank and the programme in Cambodia demonstrates cost effectiveness through leveraging multilateral funding for scale up of evidenced interventions and, while not in the review year, there is high potential of the SEA-PLM Initiative 2 (follow up to the 2024 data), to improve country-level coordination and crowding-in resources from all partners present to address foundational learning. In addition, the pilots in Cambodia are fully aligned with Global Partner for Education (GPE) objectives.
- Several EdTech Hub activities have supported potential cost savings for AMS and SEAMEO/partners through offering TA, although no cost saving data has been captured.
Environmental Considerations
This has not been a focus of the programme deliverables. There is scope to integrate more explicit climate and green economy considerations in a second phase of the programme.

E: RISK

Overall Risk Environment and Key Risks
The overall risk environment for the programme has remained moderate.

In the review year, the key risks to the programme were:

Commercial / budget: Delays and budget reductions. A major risk identified was the transition to the second phase of the programme which is due to start in April 2026. Procurement for the phase 2 implementing partner was due to start within the review year but a pause in the process may now pose a risk to programme continuity. Although funding has been secured for FY2025/26, budget uncertainty for 2026/27 onwards due to the reduction to 0.3% ODA is now a major risk for the programme and comes with a reputational risk to the UK as a Dialogue partner to ASEAN. Mitigating actions are for the FCDO to undertake scenario planning and regularly engage with ASEC and other partners.

Strategy and context: Complexity and scope of programme. With two intergovernmental institutions (ASEC and SEAMEO) and additional downstream partners delivering across a region of 11 countries, there is a risk of programme incoherence/fragmentation and lack of impact for AMS. There is a need for strong coordination and leadership for a coherent regional ASEAN/SEAMEO approach to supporting AMS and improving education in the region. There is also a need to ensure coherence with multilateral partners and other donors in the region to increase the impact of the programme. Commencing the programme without full time technical advisory leadership from an FCDO education adviser increased strategy and context risk. Advisory support was secured from the education cadre and an adviser joined in August 2024. Other mitigating actions in the review year have firstly been on establishing governance and programme management structures – the programme Quarterly Programme Review Board, monthly partner meetings, monthly UK mission programme meetings, instigating MEL structures with the first logframe, and quarterly reporting structures. Secondly, on partner work planning – ensuring that this is as integrated as possible and demonstrating delivery of the whole programme towards integrated outcomes. The UK Mission education adviser strengthened the links in the review year with multilateral partners – especially the World Bank and UNICEF – and the Australian Government to ensure coherence in programme interventions and to deliver regionally our collective global priorities in education. These partnerships will be further formed in the next review year with several joint policy initiatives.

Programme delivery: Delays in programme delivery. This has been a risk during the review year as the programme has been finding its feet and consortium partners have started working together to deliver against the first annual workplan. In some cases, this risk materialised. While a lot of work has been achieved in the year, some activities have taken longer than expected, such as the design and launch of the pilots, which is largely a result of the need to coordinate with many partners and AMS (IAI countries), while not having a presence on the ground in those countries as a bilateral programme would. There have been late submissions of reports and workplans. Mitigation has been to engage closely with the British Council programme team to improve timeliness and quality.

Programme delivery: Logframe / monitoring / ToC. Monitoring and data-related risks were a concern in the review year. Again, this risk materialised. Challenges included inadequate data capturing and quality, and the first logframe which did not adequately specify milestones for the pilot projects, establish indicator reference sheets, or set out the contribution of the programme outputs to the outcome level. The use of a third-party monitor (but one that is contracted through the lead delivery partner, not separately with FCDO) enabled verification of data but conversely the use of the MEL partner also meant that partners may not have ‘owned’ the MEL process. Efforts are underway to ensure that logframe indicators and means of verification are clearly defined and effectively owned by all.

Safeguarding: This is a non-negotiable in the FCDO. The risk remained within appetite. As the lead consortium partner, British Council has an existing policy on safeguarding that two downstream partners (SEAMEO and ACER) must comply with. The UK Mission invited SAGE partners to attend safeguarding training on 29 May 2024 to refresh partners on FCDO policy and compliance.

Fiduciary: To strengthen fiduciary risk management, the British Council and EdTech Hub participated in fraud prevention training in May 2024. Ongoing compliance is systematically reviewed and reported through regular updates to the UK Mission Programme Board. Fiduciary risk was also mitigated through independent audits conducted by both the British Council and EdTech Hub (via R4D).

Risk management: Based on the updated assessment, the current risk environment is being managed proportionately. The programme remains within acceptable risk thresholds for FCDO and continues to apply appropriate due diligence and assurance measures. However, it must be noted that the UK Mission was eager to set up the programme and start delivering at pace; this happened rapidly by programming standards and without all necessary capabilities and resources in place at the UK Mission at the outset (such as a full-time education adviser). Going forward, the programme team should keep strengthening programme assurances and to continue addressing programme risks through ongoing monthly and quarterly risk management reviews.

Looking ahead, the risk profile may shift in the upcoming financial year (2025/26) due to the evolving strategic context and budget allocations. To remain responsive, the programme will regularly revisit the risk register, strengthen scenario planning, build in contingency plans, and consider potential options which could be pursued to still maximise impact in future years if budgets are reduced.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

An extensive amount of work took place under the ASEAN-UK SAGE programme in the review year. This AR assesses the programme to have generally performed as expected regarding the outputs, with a mix of As and Bs and an overall score of A, which is a good result for the first full year of implementation, with recommendations for the next review year.

Programme management, delivery, commercial, and financial performance are not assessed through the scored outputs. To measure performance, the UK Mission put in place key performance indicators (KPIs) for the main agreement with British Council, as listed below.

The performance was generally acceptable but with key areas to improve on, including reporting and coordination. While foundational structures are in place, including a consortium, regular reporting, and active engagement from the UK Mission to ASEAN, some challenges were seen across planning, financial forecasting, and pace of delivery.

Narrative and Financial Reporting
Narrative reporting improved during the year with formats and templates aligned and revised with support from the UK Mission to ASEAN. Some quarterly reports were submitted slightly behind time but included key information on progress, challenges, and upcoming activities. The annual finance status reflects a slight underspend of approximately 5% against the forecast including all partners. However, this does not include a reforecast to increase the budget for implementation of pilots, which had to be re-forecasted and returned due to delays.

Workplan
Quarterly targets were partially achieved, with clear rationale for variances, and actionable follow-up plans in place. Optimism bias affected delivery timelines, highlighting the need for more realistic planning and cost projections. While considerable work took place in the review year, the UK Mission was keen to ensure a full, quality, consolidated workplan for the year 2025/6 in an elevated standard than the first year of full programming. In the reporting period, there were delays in submitting this in formats requested and was only partially achieved in the review year, but once finalised will set up the programme well for the Annual Review.

Value for Money
Progress on this objective is set out in the VfM section above.

Consortium Coordination and Governance
Regular coordination meetings between the British Council and its consortium partners began in the review year. There is also a quarterly programme board, which includes partners, FCDO, and embassies in the region as observers. These structures have enabled joint planning and information sharing. Leadership of the consortium remains stable, but the effectiveness of joint planning and implementation would benefit from more focused and streamlined engagement, particularly during high-delivery periods. The UK Mission found the joint work planning to be a very helpful exercise to understand how the partners work together to produce integrated plans. More engagement to consolidate this in the next review year is necessary, especially as the programme works more towards the outcomes of the programme.

Technical Delivery and Evidence Use
Activities have both drawn on and produced original scoping, research, and regional data which have in turn shaped pilot projects and TA. The programme has maintained alignment with the strategic themes of foundational learning, equity and inclusion, and digital skills, with a strong focus on foundational learning in the review year, and has drawn on regional and global evidence such as the GEEAP Smart Buys, for example the TaRL piloting and support to structured pedagogy approaches in Cambodia. Partners began a more coordinated approach to planning for research, pilots, and TA through monthly meetings.

Learning and adaptation
Quarterly reporting includes discussion on learning and adaptation. The final report of the review year focused on lessons of pilot delivery especially in Lao PDR which did not go ahead, on the need to improve communications and advocacy especially in the next review year which will have an increased focus on policy dialogue, on the need to improve monitoring, evidence, and learning (MEL) processing and getting behind a strong outcome level ToC, and on improving coordination and governance in the programme. MEL is discussed in more detail below.

FCDO Engagement and Partnership
The UK Mission to ASEAN has provided oversight, technical input, and feedback to the consortium in the review year, including on strategic and technical alignment with global FCDO policy. There may be opportunities to strengthen the partnership by providing more structured technical engagement and clearer expectations on decision timelines in future.

In summary, although there are areas for improvement, the programme is now in a good position to continue to improve delivery and performance in the next review year.

G: MONITORING, EVIDENCE AND LEARNING (MEL)

Strategy and Monitoring
During the inception phase of the ASEAN-UK SAGE programme, there was collaborative work involving stakeholders and the contracted MEL service provider Ipsos, to work on a MEL strategy, and to adapt the original Business Case ToC (Figure 1) to the current one (Figure 2) (in the ToC section above). Ipsos, contracted by the British Council, facilitated these sessions with partners and remote advisory staff from the FCDO network. The current logframe focuses largely on activities at the four output levels. There is a recognition within partners and UK Mission to ASEAN that MEL strategy implementation needs further progress in 2025/26, including more focus on translating the activities to achievement at outcome level – influencing AMS policy and implementation to improve education outcomes for children in the region.

Several actions will take place in the next review year to review the MEL structures to ensure we are maximising the delivery of outcomes, including reviewing the 2025/26 logframe outputs in the quarter following this review, a review of all programme MEL systems by Ipsos which will inform the MEL strategy for 2025/26, and more engagement from partners, the British Council MEL lead, and the UK Mission to ASEAN to ensure clearer accountability for all elements of MEL.

A key moment in the annual MEL strategy is the FCDO Annual Review. For this review, Ipsos supported with verification of documentation. While not a comprehensive verification, key lessons came from the process, many which are embedded in section C above, including the need for more consistency in categorising and reporting on TA and in defining the indicators more clearly with an indicator reference sheet. The AR itself was initially undertaken by a FCDO education adviser from the region, who completed 15 interviews with key stakeholders including ASEC, SEAMEO, SEA-PLM counterparts, and implementing partners, and then the AR was finalised by the UK Mission to ASEAN SAGE team.

Evidence
Overall, there is evidence that ASEAN-UK SAGE is helping to build the UK’s partnership with ASEAN, and that 2025-2026 is the right time for the programme to be ambitious with its goals for outcome level achievements of policy influence within the region. The programme has formed the right partnerships to engage in a meaningful way with influential education bodies in the region. As an ASEAN-focused programme, there is opportunity to ensure strengthened regional approaches, such as the region’s approach to OOSCY and foundational learning. The programme focuses on both the use of evidence and the production of evidence through research, TA, and pilots. But the programme needs to be more intentional with the production of robust evidence to fill gaps in the region, for example with impact assessments. The pilot projects started in the review year offer a great opportunity for the programme to improve the evidence base in the region. The learning progression and the TaRL pilot in Cambodia, the latter of which will have an impact assessment, will support scale up in country and aims to offer more policy influencing opportunities across the region to other AMS.
Learning
As mentioned above, learning and adaptation is key to the overall programme delivery and reflection points are regular, however there are improvements to be made. For example, there needs to be more collaboration between the UK Mission to ASEAN and programme partners for learning and reflection at thematic levels rather than simply through the quarterly reporting process. The important thing for the programme going forward is that there is strong coordination between all partners and relevant posts, a robust framework for delivery, and clear measurable goals.
Date of last narrative financial report	8 May 2025	Date of last audited annual statement	9 September 2024