## Annual Review Template

Title: ASEAN-UK Supporting the Advancement of Girls’ Education (ASEAN-UK SAGE) Programme
Programme Value £ (full life): 30 million		Review date: May 2026
Programme Code: 400133	AMP start date: 24/01/2024	AMP end date: 31/03/2030

Summary of Programme Performance
Year	2024	2025	2026
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400133
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400133

A. SUMMARY AND OVERVIEW

Description of programme

The ASEAN‑UK Supporting the Advancement of Girls’ Education (ASEAN‑UK SAGE) programme was established following the UK’s designation as an ASEAN Dialogue Partner in August 2021. SAGE was the UK’s first flagship accredited programme delivered as a Dialogue Partner under the ASEAN‑UK Plan of Action (2022–2026) across all 11 ASEAN Member States, including Timor‑Leste[1].
[1] Timor-Leste became a member of ASEAN in late 2025

The review year (2025–2026) was the third year of the programme and an extension year in Phase 1, allowing partners to deliver a full workplan across all three pillars and generate evidence and insights. Phase 1 focused on the following pillars:

- Foundational learning: strengthening the evidence base and supporting ASEAN Member States to prioritise basic literacy and numeracy, drawing on UK global expertise to support long‑term growth and regional integration.
- Out‑of‑school children and youth and other marginalised groups: addressing educational inequities and promoting inclusive human capital development.
- Gender barriers to employment: enhancing digital and STEM skills for girls and women, including through a UK university scholarship scheme.

The UK Government announced a reduction in Official Development Assistance (ODA) to 0.3% in February 2025. The budget for the review year remained intact; however, FCDO undertook internal work to refine the approach for Phase 2, in line with reduced resources and the UK’s modern development approach, shifting from donor to investor; from service delivery to system strengthening; from grants to expertise; and from international intervention to locally led solutions.

Phase 1 of the programme has been delivered by a consortium of British Council (lead), Southeast Asia Ministers of Education Organization (SEAMEO), the Australian Council for Educational Research (ACER), and with a separate agreement to EdTech Hub.

Summary supporting narrative for the overall score in this review

For the review year, the programme scores an A overall, with the following output scores:
- Output 1 (Policy dialogue and advocacy): A
- Output 2 (Research, evidence and data): B
- Output 3 (Proof of concept pilots): A
- Output 4 (Technical assistance): A

Following initial delays in finalising an integrated workplan and contracting arrangements, which had knock-on effects for delivery timelines, the programme demonstrated good performance across many logframe deliverables.

While there was an underspend in the programme overall, strong performance was seen in the delivery of pilots, with high-quality technical delivery and strong government engagement and ownership. Performance was especially strong in Cambodia, where pilots demonstrated clear government ownership and alignment with the country’s system reform and are already informing scale-up through the World Bank’s $100m Basic Education Improvement Programme (BEIP), with elements being integrated into government delivery. The policy dialogue output was also delivered well, although a clear advocacy and influencing strategy was missing overall. Significant technical assistance was delivered including on the regional learning assessment SEA-PLM, although evidence of how this will translate into sustained use and system-level change remains limited in several areas.

However, there was underperformance in producing research deliverables on time, which meant that several key research outputs were not fully completed/disseminated by SAGE within the year.

Overall, the programme has delivered strongly in the review year despite coordination and programme management challenges. It has generated credible technical evidence, strengthened government engagement, and positioned the UK as a trusted partner on education reform in ASEAN and the only Dialogue Partner with a strong focus on basic education, giving us a comparative advantage for engagement in countries such as Timor Leste. The programme is therefore well placed to transition into Phase 2, with a clearer and more focused model centred on technical assistance to accelerate foundational learning outcomes.

Major lessons and recommendations for the year ahead

No	Lesson	Recommendation for phase 2 (2026-29)
1	Strong technical design aligned with government reform can enable credible pathways to wider system reform and scale.	Phase 2 will prioritise government-led reform pathways with clear pathways to scale, informed by political economy analysis and focused on Smart Buys to improve learning (structured pedagogy and targeted instruction).
2	Delivery of technical assistance does not in itself demonstrate change without evidence of uptake, use, and integration into systems.	Phase 2 should strengthen monitoring of how technical assistance is used by governments, including clearer evidence of adoption, adaptation, and contribution to system strengthening and learning outcomes.
3	The programme delivered high-quality dialogues but lacked a clear and coherent approach to communications, advocacy, and influencing to drive sustained evidence uptake.	In Phase 2, strengthen communications and influencing as a core function, with clear ownership, targeted messaging, and consistent follow-up to ensure that evidence and dialogue translate into policy action and reform.
4	Programme delivery highlighted the importance of clear leadership, stronger accountability, and consistent performance management.	Phase 2 will strengthen programme management through clear accountability structures, more consistent performance management, and improved coordination across delivery partners.
5	Engagement with other partners is important for wider system support to governments but was not consistently leveraged across the programme.	Phase 2 will place partnerships at the centre of delivery, to mobilise financing, align programmes, and support sustained implementation and scale.

The full list of recommendations from the last AR (2025) and their progress is presented at the end of the report.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The Theory of Change (ToC) from the Business Case (Figure 1) was revised during implementation to produce the current ToC (Figure 2), which the programme worked to during the final year of Phase 1. The revised ToC remains broadly aligned to the original goals but provides greater clarity across the three programme pillars. A further revision will be made for Phase 2 to reflect the programme’s refined focus on foundational learning.

Figure 1.

The impact level in the ToC (Figure 2) remained valid for the review year: Quality-of-life outcomes improved through a more sustained, supported access to an inclusive, quality education offering which also helps to narrow the development gap in ASEAN. The original outcome (Figure 1) was separated into three outcomes covering the three pillars of work. In the review year, the ToC was still relevant to key issues in the region, including inclusion of marginalised social groups. In Pillar 3, in the review year the outcome was separated into two outcomes – Approaches to develop relevant, basic digital skills for marginalised social groups improved and Pathways created for girls and women to allow for wider, attainable preferences for [formal] employment.

Figure 2.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The last Annual Review recommended adding clear outcome indicators to the ToC/logframe to ensure tracking at the outcome level. These indicators were added during the review year; however, targets were not adequately defined or populated by the lead supplier and MEL team. As a result, it is difficult to conclusively assess whether outcomes were achieved by year three, the final year of phase one. The assessment below therefore draws on available evidence for each outcome.

Outcome 1: Gap between policymakers estimated and actual scale of foundational learning crisis reduced. Without baseline and follow-up data, it is not possible to confirm whether this knowledge gap has narrowed. However, several major data and advocacy interventions suggest an increased level of awareness of the learning crisis. A key data and advocacy tool is the Southeast Asia Primary Learning Metrics (SEA-PLM) 2024 regional report, supported by the UK, which provides up-to-date data on learning outcomes in grade 5 in six countries, including SDG4.1.1b benchmarking. This highlights significant variation between countries (% of children at minimum proficiency in reading spanning 86% to 11% across six countries). In addition, several policy dialogues were held at technical, senior official, and ministerial levels, focusing on the learning crisis and ways to address it. The Philippines is championing a Leaders’ Declaration on Foundational Learning to garner support from ASEAN Member states in this area. It was initiated by the UK and supported by multilateral partners and announced at the UK’s Ministerial Roundtable at the Education World Forum (EWF) in London 2025. In addition, the State of Education in ASEAN Report will further highlight the data to policymakers. Taken together, it is feasible to estimate that policymakers in ASEAN have increased information on the learning issues in the region.

Outcome 2: Effective, evidence-based policy interventions result in addressing the foundational learning crisis. While there is no comprehensive outcome-level assessment of uptake, evidence-based approaches have been key to the programme and have been consistently promoted through programme policy dialogues and technical assistance. After the Ministerial Roundtable on Foundational Learning at EWF in London 2025, the Second Congressional Commission on Education in the Philippines (EDCOM2) (who attended the meeting) released a statement calling for nationwide scale-up of Teaching at the Right Level (TaRL), a “Smart Buy” intervention discussed at the event. The roundtable likely contributed to this. The ASEAN Workplan on Education, funded through the programme, was also developed by all Member States, with Smart Buys evidence included. SEA-PLM has further supported four of six countries to analyse their data and strengthen policy linkages. In addition, the UK supported pilot interventions in three countries, including Cambodia where this has linked to a World Bank scale-up. Government ownership at senior official level was also evident across interventions at the Evidence and Insights Forum, closing the first phase of the programme in Jakarta in March 2026. Taken together, the programme has contributed to evidence-based policy interventions, some which directly improved learning (the TaRL pilot in Cambodia, for example) and others which have contributed to enabling conditions for improved learning, though evidence of sustained system-level adoption remains emerging.

Outcome 3: Policymaker systems thinking on inclusion is enhanced. Progress was made towards this outcome, including new research on out-of-school children and youth (OOSCY) and the revitalising of the ASEAN working group for OOSCY. In the review year, OOSCY research, covering governance, gender, mental health, technology and country case studies were produced. However, these came late in the programme and were not fully completed and disseminated during the year, therefore, its impact on systems thinking is not yet known. The UK was recognised at the ASEAN working group for its multiple strands of work supporting OOSCY, including efforts to prevent dropout such as TaRL, and supporting mobile phone education for children out of school in the Philippines.

Outcome 4: Approaches to develop relevant, basic digital skills for marginalised social groups improved. The revised outcome (Figure 2) was split into Outcomes 4 and 5 during the review year. There has been limited progress against this outcome, reflecting its lower prioritisation within the programme. A small skills pilot in Timor-Leste, reached 100 boys and girls with entrepreneurial and digital training. The approach was well received by government, included support to marginalised girls, and there is a commitment to embed it in the national skills curriculum. However, its sustainability is uncertain given no further support is planned under Phase 2, which will focus exclusively on high need and impact area of foundational learning.

Outcome 5: Pathways created for girls and women to allow for wider, attainable preferences for [formal] employment. The main vehicle to delivering against this outcome was the SAGE Women in STEM scholarships, run by the British Council, which provided support to cover master’s level degrees in STEM subjects in the UK. This existing programme, which was extended to ASEAN and funded through the programme, successfully sent 23 women from nine countries in the region to the UK over two years, with additional top up funding from the FCDO outside of SAGE for the review year. The aim is to equip participants with advanced skills to improve their careers and empower them as STEM experts and ambassadors in their home countries. The programme is run well and the women are inspiring. However, while scholarships are generally popular and deliver benefits for individual recipients, there is limited evidence that they translate into broader labour market impacts or expanded employment pathways for women at scale without complementary efforts to address structural barriers.

Taken together, while outputs have been largely delivered, evidence at outcome level remains partial and uneven across components. Stronger evidence exists where interventions were embedded within government systems (e.g. Cambodia pilots), while other areas – particularly research and technical assistance – have more limited evidence of uptake and system-level change.

There will be some changes to the ToC for the next phase of the programme. In particular, the programme will focus exclusively on foundational learning outcomes, with outputs centred on delivering technical assistance, generating learning, and building partnerships to accelerate learning outcomes. This approach is set out in the new Terms of Reference, with procurement for Phase 2 implementing partners ongoing at the time of writing. On balance, the programme demonstrates sufficient evidence of relevance, effectiveness, and strategic value to justify continuation into Phase 2.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme Phase 1 has now been completed including the review period (2025-26) which was an extension year. Phase 2 implementing partners will be procured through an open competitive process and activities are expected to run from August 2026 to March 2029, with the option of a further one-year extension subject to budget availability and continued strategic alignment.

This programme is central to delivering the UK’s Plan of Action with ASEAN in 2026–2031, in which education is a key area of cooperation. It will also contribute to FCDO’s modern development partnerships and strategic shifts, particularly in strengthening technical expertise and education systems through the FCDO’s development and climate goal and will also deliver against the FCDO’s women and girls’ priorities.

The design of Phase 2 has been carefully informed by lessons learned during Phase 1, ensuring a more effective and targeted approach, in particular ties to evidence and action to accelerate learning outcomes for the countries with the highest numbers of children unable to read by the end of primary school. The programme is a strong contributor to FCDO’s Leave No-One Behind agenda as it uses a Gender, Disability, and Social Inclusion (GEDSI) approach and focuses on system strengthening to support acceleration of learning for children furthest behind. Relevant data is always disaggregated by gender and where possible by other areas o disadvantage, such as socio-economic status. Given its strategic alignment and proven value, the continuation of the programme has been approved.

## C. DETAILED OUTPUT SCORING

Output Title	Policy dialogue and advocacy events promote foundational learning and raise awareness of the learning crisis, OOSCY and inclusive education.
Output number:		1	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	Yes, down from 25%. / This reflects an increased budget and importance put on to other outputs.

Indicator(s)	Milestone(s) for this review	Progress
Number of eligible regional policy dialogues (SAGE-led or significant SAGE-support)	6	6 Met

Briefly describe the output’s activities and provide supporting narrative for the score.
The programme delivered key policy dialogue events during the review year, and those have been verified by the programme team, review team, and independent MEL adviser as having met set criteria that the dialogue is programme supported or led, has clear objectives, includes use of UK-supported research, evidence, and data, engages an appropriate level of participants, and results in commitment or action plan.

1. Regional Forum (May 2025, Malacca). Met. The programme convened 92 policymakers and experts from nine countries to advance evidence on foundational learning. Delivered with UNICEF, SEA‑PLM/SEAMEO, and the World Bank, the forum strengthened regional alignment and catalysed country action plans through SEAMEO. It included two Global Education Evidence Advisory Panel (GEEAP) members, both online and in person, as well as senior members of the World Bank. It was a strong technical session, although one major lesson was the attendance list – there was limited high-level policy representation from the nine delegations to take forward discussions and decision making.
2. ASEAN Ministerial Roundtable (May 2025, London). Met. This was led by FCDO with speakers from the What Works Hub for Global Education (WWHGE), Gates Foundation/GEEAP, the former Mayor of Brazil, and SEAMEO. This high-level platform brought global evidence directly to ministers and high-level delegations present from nine countries and secured the Philippines’ commitment to champion an ASEAN Leaders’ Declaration on Foundational Learning in 2026.
3. DevEd Conference (Nov 2025, Melbourne). Met. This was co-funded by the FCDO and the Australian Department for Foreign Affairs and Trade (DFAT) through the programme and delivered by programme partner the Australian Council for Educational Research (ACER). This inaugural regional conference convened around 200 policymakers, researchers, and practitioners. It established a new platform for Asia-Pacific dialogue, with high-level participation including DFAT Minister for Development Dr Ann Aly.
4. OOSCY Working Group (Feb 2026, Bangkok). Met. The UK support helped revitalise the ASEAN Working Group on OOSCY, re-engaging Member States around data, evidence, and promising practices to reach children out of school, and setting a path for sustained collaboration. This was an active and important working group, given that up to 18m children are out of school in ASEAN. UK support to this area of work across different interventions was acknowledged.
5. SEA-PLM Engagements (throughout 2025–26). Met. The programme supported rollout of the 2024 regional assessment across six countries, as well as follow up support which included national dialogues and the establishment of steering committees to work across departments to respond to the data. These engagements have supported countries to own and understand their data and has laid some foundations for them to translate data into policy priorities.
6. Evidence & Insights Forum (Mar 2026, Jakarta). Met. This event brought together nine ASEAN Member States to consolidate programme learning. This was the last in the review year and brought together all the key learning from the year. There was strong country ownership, which highlighted the depth of support and technical assistance delivered, providing a clear and credible close to Phase 1.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output remained consistent with the previous review year; however, the design of events was refined to ensure clearer purpose and stronger alignment with the programme’s theory of change, particularly in improving policymakers’ understanding of the learning crisis and the evidence to address it. This meant the dialogues increased significantly in quality and purpose and have contributed to the UK’s agenda to promote evidence in the region, especially for foundational learning.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation (from previous Annual Review)
Develop a clear policy advocacy strategy to define target audiences, key messages, and intended policy outcomes of ASEAN-UK SAGE dialogues. Strengthen the link between policy dialogue activities and programme outcomes, including clearer articulation of how dialogues influence decision-making and policy change.

Progress against recommendation
Good progress has been made in strengthening the quality, purpose, and strategic alignment of policy dialogues. Events in the review year demonstrated clearer objectives, stronger use of evidence, and more targeted engagement with senior decision-makers. Several dialogues achieved tangible outcomes, including ministerial commitments and renewed regional collaboration on foundational learning and OOSCY.

While individual events were well designed and delivered in line with an agreed workplan, a fully articulated and consistently applied advocacy strategy was not yet in place. Feedback from implementing partners highlighted that there was limited overall leadership on advocacy and policy dialogue across the programme, and that this was not consistently managed or delivered as a coherent workstream. As a result, the link between dialogue activities and results including policy influence is not systematically tracked or evidenced.

Lesson
Through the programme and sustained diplomatic engagement, the UK has positioned itself as a trusted convener of regional decision-makers on foundational learning. It has built strong credibility and relationships with the ASEAN Secretariat, ASEAN Member States, and key multilateral partners, creating a platform for influence on policy dialogue and regional priorities.

At the same time, the programme experience shows that high-quality convening and strong evidence are not sufficient on their own. Policy dialogue requires strategic leadership, coordination, and strategic direction to maximise impact. Where this was less developed, opportunities to link dialogue to sustained policy influence were not fully realised. A more coordinated and deliberate communication and advocacy approach, with clear ownership and follow-up, and based on a robust political economy analysis, is needed to ensure that strong dialogue translates into system-level change.

Recommendation
While Phase 2 will shift focus towards technical assistance in priority countries, maintaining a strategic regional role remains important as an ASEAN programme. The FCDO should build on its established convening power and trusted relationships to drive more targeted and strategic advocacy on what works in foundational learning. This should include clearer coordination of advocacy efforts, strong integration with technical assistance, and more systematic follow-up to support policy uptake.

This should focus on amplifying evidence, reinforcing political commitment, and supporting peer learning across ASEAN to complement and strengthen country-level delivery.

Output Title	Policy relevant research, evidence and data (RED) products/package are produced, quality assured and disseminated with ASEAN partners to inform regional and national decisions on foundational learning, reducing OOSCY, and inclusive education.
Output number:		2	Output Score:	B
Impact weighting (%):		15	Weighting revised since last AR?	Yes, down from 25% / This reflects an increased budget and importance put on to other outputs.

Indicator(s)	Milestone(s) for this review	Progress
Number of SAGE RED products delivered and disseminated (internal QA-approved)	7	4 met / 3 moderately not met

Briefly describe the output’s activities and provide supporting narrative for the score.
The review team and independent MEL adviser have assessed the delivery against targets in the review year. Criteria set against deliverables for this output were that all research and data products have a concept note; that they have partner peer review and quality assurance, that they are completed in-year, and disseminated to defined target audience in-year. The output delivered the following research and data products:

1. State of Education in ASEAN (UIS/UNESCO). Met. The programme delivered a comprehensive, up‑to‑date overview of education across ASEAN sub‑sectors, updating a report last produced over a decade ago. The report drew on regional evidence (including SEA‑PLM and SAGE), UIS country data, and inputs from ASEAN Member States. It was strengthened through peer review from FCDO, programme partners, and multilateral organisations. This will be disseminated at a set date at the ASEAN Ministers Meeting in July 2026, and all other criteria were met during the review year so given ASEAN processes and set dates, this is considered met.
2. Lifecycle Analysis of Girls’ Education (Cambodia, Lao PDR, Timor-Leste). Met. ACER conducted cross-country research in Timor-Leste, Cambodia, and Lao PDR using a lifecycle analysis lens to assess outcomes for girls. The study found significant gains in education and broader human development, but highlighted a persistent gap in economic outcomes, estimating up to a six-year delay for young women to reach parity with men in the formal workforce. Findings were disseminated at the UKFIET conference (Oxford, September 2025) and the Evidence and Insights Forum (Jakarta, March 2026).
3. EdTech/AI package (6 briefs/case studies + 1 synthesis). Met. The EdTech Hub delivered a suite of evidence products on EdTech and AI to support policy and practice in Southeast Asia, drawing on regional research, country scans, and technical assistance through the SEAMEO Helpdesk. The work focused on key themes including AI for teaching and learning, supporting marginalised learners, and strengthening evidence-based decision-making. Dissemination of the landscape analysis and AI briefs was strong, with well-attended events that brought together a diverse mix of stakeholders, including government representatives, development partners, and private sector actors, supporting dialogue, knowledge exchange, and uptake of findings
4. 3 OOSCY Country Case Studies. Moderately not Met. A set of country case studies was produced, coordinated by SEAMEO, examining the drivers, characteristics, and policy responses to out-of-school children and youth across ASEAN contexts. The studies focused on Lao PDR, the Philippines, and Indonesia highlighting system-level barriers to inclusion and the role of alternative and flexible learning pathways. The target was not fully met due to incomplete finalisation and dissemination within the review year.
5. 4 OOSCY Thematic Papers. Moderately not Met. SEAMEO also coordinated a series of cross-cutting thematic papers exploring key dimensions of exclusion and re-engagement for out-of-school children and youth. These included analysis of data governance and identification gaps, the role of EdTech as alternative education, mental health and psychosocial wellbeing, and Inclusion Practices for Children with Disabilities alongside broader system-level considerations. Together, the papers highlighted the need for integrated, multi-sectoral responses and informed regional policy dialogue at the Evidence and Insights Forum. This target was not fully met due to not completing and disseminating fully within the review year.
6. SEA-PLM 2024 technical package products. Met. A suite of technical products was completed to support the SEA-PLM 2024 assessment, including core documentation and analytical outputs. These underpinned the production and successful launch of the SEA-PLM 2024 regional report in December 2025, providing robust evidence for regional and national policy engagement.
7. ASEAN Work Plan 2026–2030. Moderately not Met. The ASEAN Work Plan 2026–2030 was developed through a series of workshops facilitated by UNESCO under the SAGE programme, engaging AMS and partners to define regional priorities aligned with national education plans. The workplan represents a key strategic framework for regional collaboration over the next five years. The target was only partially completed in the timeframe due largely to significant delays in contracting between the British Council and UNESCO, which affected finalisation timelines. The workplan is scheduled for launch at the ASEAN Ministers’ Meeting in July 2026.

Recommendation (from previous Annual Review)
Strengthen the planning and coordination of research, evidence, and data (RED) outputs to ensure they are complementary, strategically prioritised, and clearly linked to programme outcomes. All products should have defined concept notes, dissemination plans, and clear pathways for use and policy influence.

Progress against recommendation
Progress has been made in increasing the volume and quality of RED outputs, with a wide range of products delivered across the year. However, implementation of the recommendation has been partial. Several products were not fully completed or disseminated within the review period, and in some cases the link between evidence generation and intended use and/or policy influence is not as strong as it could be. Coordination across partners improved with the introduction of a SAGE research board. More time was needed to consistently result in streamlined, prioritised deliverables with clear dissemination and uptake pathways, especially around OOSCY studies.

Lesson
High-quality research, while important, alone does not drive influence. Impact depends on how effectively evidence is translated, targeted to decision-makers, and supported through clear pathways for use.

Recommendation
As Phase 2 does not include a primary research component, the programme does not need to prioritise this going forward. However, there is opportunity for some light touch diagnostics and implementation science work as well as evidence translation. These need to be clearly defined for use with explicit pathways to uptake in policy and implementation.

Output Title	Proof of concept interventions in line with SAGE thematic pillars are designed to (e.g.) improve foundational learning, catch up, re engage out of school children and promote inclusion are implemented and assessed to generate actionable evidence for policy and systems uptake across ASEAN.
Output number:		3	Output Score:	A
Impact weighting (%):		35		Up from 25% / This reflects a larger budget and importance in the review year.

Indicator(s)	Milestone(s) for this review	Progress
Number of pilot concepts implemented to protocol	5	5 met
Number of pilot concepts validated with credible evidence of effect	NA	3 validated

Briefly describe the output’s activities and provide supporting narrative for the score.
Four pilots plus a scholarships programme were delivered in the review year with the following criteria: SAGE co-design pilot with AMS / ASEC; concept approved / endorsed by key stakeholders; launched; implemented in-year; and monitored and evaluated to standard agreed in the concept note.

1. M&E pilot for foundational learning pedagogy and materials (Cambodia). Met and validated. This was an integrated monitoring and evaluation pilot to strengthen system capacity to assess both teaching practice and instructional materials within the Early Grade Learning package. Three complementary tools were developed and applied, supported by national training and data collection across 120 schools. The pilot generated robust evidence highlighting key gaps, including limited focus on oral language, low student interaction, and weak differentiation. Findings were validated and are informing refinement of the EGL package and improved alignment across curriculum, materials, and teacher support systems, which is being taken forward through World Bank-supported delivery and broader government reform efforts. This pilot was delivered through the British Council and ACER.
2. TaRL implementation in schools (Cambodia, Grades 4–5). Met and validated. A Teaching at the Right Level (TaRL) pilot was implemented through government systems to support Grade 4–5 students with foundational learning gaps, reaching 821 students across 32 schools. The programme combined level-based instruction, targeted materials, and a structured system of training, mentoring, and assessment using the national digital primary learning platform. Internal monitoring showed substantial improvements in learning, with the share of students reading at paragraph level or above increasing from 39% to 85%, and those achieving at least subtraction level in numeracy rising from 42% to 99%. An impact evaluation using two assessments: Annual Status of Education Report (ASER) and International Common Assessment of Numeracy (ICAN) and International Common Assessment of Reading (ICAR) tools is underway, providing the first impact evaluation of TaRL in Southeast Asia. Initial results indicate large and statistically significant impacts, with TaRL students outperforming comparable peers in both literacy and numeracy. The pilot was delivered through British Council and Pratham International. The impact evaluation is being conducted by ACER, with design support from the World Bank and British Council, as well as the WWHGE.
3. Skills Training for Economic Participation (STEP) digital and entrepreneurial skills programme (Timor-Leste). Met and validated. The STEP programme delivered a gender-responsive model to build digital and entrepreneurship skills among marginalised youth, particularly young women, through government systems. The pilot reached 98 learners and 20 teachers, achieving high completion rates and a 62% increase in student knowledge alongside gains in confidence and business skills. The pilot strengthened community and institutional capacity and demonstrated a scalable approach to employability and economic participation, particularly for women. British Council together with UN Women delivered this pilot.
4. TaRL / Accelerated Learning Programme for out-of-school children and youth (Philippines, March 2026). Met. A targeted instruction pilot supported out-of-school learners through a government-led, flexible model aligned to government policy. The small project was delivered by Youth Impact, coordinated by SEAMEO, and delivered phone-based tutoring to strengthen foundational numeracy and generated operational evidence to inform future scale-up within national systems. Jan–Mar 2026 showed the pilot can work through the Alternative Learning System (ALS): 113 implementers were trained and 81 learners completed four-week tutoring. Results were promising, with 43% reaching division level and 58% improving, showing a simple phone-based model can deliver learning gains. There is also early policy traction, with the government exploring integration into ALS and next steps for scale.
5. Women in STEM Scholarships. Met. This British Council programme which was extended by the SAGE programme to all ASEAN countries, delivery progressed in line with targets, focusing on supporting the current cohort to commence their studies and welcoming returning alumni. Eleven scholars from across ASEAN were supported to undertake postgraduate STEM study in the UK.

Recommendations (from previous Annual Review)
Strengthen the design, implementation and validation of proof-of-concept pilots by establishing clear milestones and ensuring pilots are implemented, evaluated, and linked to policy influence and system-level uptake. Ensure pilot delivery is well coordinated with government and partners, with sufficient time for implementation, evidence generation, and dissemination.

Progress against recommendation
Strong progress was achieved in Cambodia, where pilots were well designed, implemented through government systems, and demonstrated high levels of ownership from the ministry. These pilots benefited from clear technical design, close engagement with government, and alignment with broader system reform efforts, including links to multilateral partners. Senior Ministry staff interviewed during the review highlighted the relevance of the pilots and their alignment with national priorities, as well as strong government ownership of delivery. There are plans to integrate findings into the EGL delivery and plans to adapt findings of the TaRL evaluation.

Some implementation challenges were present. Delays in agreements and mobilisation, particularly for the OOSCY pilot in the Philippines, resulted in a compressed delivery timeline. This limited the scope for implementation, reduced the ability to generate robust evidence, and constrained dissemination and policy engagement by the end of the review period. In Cambodia, government engagement and ownership were strong. Multilateral partner engagement on the ground did take place, but this was sometimes driven by the FCDO adviser support rather than consistent coordination across delivery partners. An additional pilot, not included in the logframe, went ahead with agreement to deliver a set of partial activities (with Pratham International and the British Council) due to delays in agreements between the Ministry in Lao PDR and the lead partner.

Lesson
Strong technical delivery, combined with engagement and ownership by government, is critical for successful pilot implementation. This was demonstrated particularly well in Cambodia, where pilots were embedded within government systems and delivered effectively. Strong partner coordination is also an important factor in ensuring that results are embedded within systems and carried forward beyond the pilot phase.

Recommendation
The programme has already been designed to build on lessons, particularly in Cambodia, in Phase 2, with a tighter focus on high quality technical assistance to government in evidenced approaches to accelerate learning – structured pedagogy and TaRL. In the second phase, greater emphasis has been placed on partnerships and leveraging larger funding and delivery mechanisms to support embedding, scale, and long-term sustainability of results.

The design also incorporates a strong focus on real-time learning, enabling continuous assessment of what is working and not working in the technical assistance support, and allowing for course correction throughout implementation to improve effectiveness and value for money.

Output Title	Targeted, criteria-based technical assistance (TA) leads to adopted tools, plans and process improvements that help SEAMEO Centres, ASEAN/AMS ministries and SEA PLM country teams use evidence to strengthen foundational learning, reduce OOSCY and advance inclusive education.
Output number:		4	Output Score:	A
Impact weighting (%):		35	Weighting revised since last AR?	Yes, up from 25% / This reflects a larger budget and importance in the review year.

Indicator(s)	Milestone(s) for this review	Progress
Number of TA work packages completed to standard (eligible)	7	7 met
Number of TA work packages validated through institutional change and positive feedback	NA	7 met

Briefly describe the output’s activities and provide supporting narrative for the score.
The following areas of technical assistance were conducted during the review year. The criteria for meeting targets in this review year were tightened to include problem / gap identified; objective of the TA defined and aligns with SAGE thematic pillars; builds capacity for AMS to achieve shared goals in education; implemented to agreed standard; positive recipient / beneficiary feedback.

1. SEAMEO MEL capacity building. Met. A small amount of programme funding was dedicated to supporting SEAMEO build its institutional monitoring, evaluation, and learning systems, including development of standardised tools, support to organisational MEL processes, and inputs to SEAMEO’s strategic planning to 2030, as well as generate and use evidence. These were completed as planned in the review year and was highly regarded by participants from the SEAMEO network.
2. Indonesia MoPSE policymaking toolkit and scorecard. Met. Support to the Ministry of Primary and Secondary Education (MoPSE) in their development of a policymaking toolkit and scorecard with ongoing advisory inputs on strategy, programme design, and evidence-based decision-making. This work supported more structured, data-driven policymaking and aligns with wider EdTech Hub support to ministries to strengthen policy-to-implementation pathways. This was discussed and appreciated by a senior official from the ministry at the Jakarta Evidence and Insights Forum in March 2026.
3. Philippines EdTech omnibus, M&E and tools. Met. A suite of EdTech tools, M&E frameworks, and guidance was developed to strengthen system-level planning and adoption of EdTech in the Philippines. This built on EdTech Hub engagement with the Bureau of Learning and Delivery and supported improved use of data, governance, and evidence-informed decision-making for EdTech and AI in the education system. This was discussed and appreciated by a senior official at the Jakarta Evidence and Insights Forum in March 2026.
4. VOCTECH (Brunei) iterative testing. Met. EdTech Hub supported iterative testing of EdTech approaches within the TVET ecosystem with this SEAMEO Centre in Brunei. This approach enabled partners to test solutions, generate evidence rapidly, and inform policy and implementation decisions.
5. Helpdesk tasks for SEAMEO and Ministries. Met. The SEAMEO Helpdesk provided on-demand technical assistance, supporting SEAMEO centres with evidence-based EdTech and AI policy, strategy development, and implementation planning. While a substantial number of requests were completed, final validation is pending beneficiary feedback. This is considered met because the criteria for feedback were added later than some of the Helpdesk requests were completed. The Helpdesk has highlighted demand for technical assistance, particularly in evidence-based decision-making and policy development, but also identified ongoing challenges around coordination and evidence use.
6. SEA‑PLM Initiative 1 support. Met. The programme supported SEA‑PLM 2024 to deliver extensive technical assistance to countries participating in the assessment and capacity building programme, including core technical expertise on assessment design, data management, analysis, and reporting. This underpinned the successful implementation of the assessment and strengthened national capacity to manage, interpret, and use learning data. Regional dissemination activities, including the launch of the 2024 Regional Report in December 2025, supported policy dialogue and uptake. The seventh country, which the UK supported to participate for the first time, Timor‑Leste, did not ultimately contribute data to the regional report, reducing the overall value realised from this investment. This was, however, outside the control of delivery partners, a sovereign decision taken by the ministry, and engagement has continued where possible to maximise the benefits of initial support.
7. SEA‑PLM Initiative 2 support. Met. Support under Initiative 2 focused on translating SEA‑PLM data into policy and system-level action. However, delays in getting a quality consolidated workplan delayed contracting between partners and resulted in a compressed implementation window, meaning only part of the planned work was delivered and there was an underspend. Key areas of focus included strengthening cross-departmental National Steering Committees. At country level, work included:
- Cambodia: strengthening classroom assessment and teaching and learning practices, including integration of SEA‑PLM insights into Early Grade Learning programmes and the Primary Learning Platform, alongside targeted capacity building
- Lao PDR: item-level analysis to inform curriculum reform and teacher professional development, linked to curriculum refinement and CPD systems
- Philippines: support to improve teacher assessment literacy and curriculum mapping.
While these activities are aligned with government priorities, it is not clear at the time of writing the extent to which they have translated into any changes in policy or practice. In addition, Initiative 2 placed greater emphasis on additional data analysis than originally intended, with much of the work remaining closely linked to assessment processes rather than translating fully into policy or practice change.

Recommendation (from previous Annual Review)
Clarify the definition, categorisation, and reporting of technical assistance, including who benefits and how it contributes to programme outcomes. Strengthen transparency, feedback loops, and alignment with programme objectives to ensure technical assistance delivers measurable impact

Progress against recommendation
Progress has been made in strengthening the design and targeting of technical assistance, with clearer criteria applied and stronger alignment with government priorities. Several activities demonstrated direct engagement with ministries and delivery to an agreed standard. Evidence of use / change within government as a result of the technical assistance is limited at this stage, beneficiary feedback is not consistently captured, and delays in contracting, particularly for SEA‑PLM Initiative 2, reduced the depth of delivery and follow-up. Partners fed back that some criteria were applied late to the logframe and some information was not captured.

Lesson
Technical assistance needs to be tightly defined and targeted to deliver against clear government reform priorities, with a clear purpose, use case, and pathway to scale. While it is recognised that short-term technical assistance is unlikely to deliver sustained impact on its own, it must be designed as part of a broader reform trajectory, with clear linkage to longer-term system change. Stronger focus is therefore needed on how technical assistance is used, taken up, and embedded within government systems, including clearer approaches to measuring uptake and contribution to reform.

Recommendation
As Phase 2 will focus primarily on technical assistance, the programme should ensure that all support is clearly defined, strategically targeted, and aligned to specific government reforms, and the overarching ASEAN Education Workplan, to accelerate foundational learning and tightly focus on evidence-based approaches in the Tor for the new phase – evidenced based Smart Buys that highlight structured pedagogy and targeted instruction as great buys. Technical assistance should be designed as part of a broader reform trajectory, with clear pathways for embedding, scaling, and contribution to improved learning outcomes and system strengthening. This should include stronger mechanisms to track uptake and use, and close collaboration with other partners to support sustained implementation at scale. Learning and adapting to what works through implementation science and adaptation needs to be core to the technical assistance model.

## D: VALUE FOR MONEY (1 page)

Value for Money (VfM) performance is assessed against the original VfM proposition set out in the Business Case, which focused on delivering technical assistance, regional public goods, and catalytic pilot interventions to improve education systems across ASEAN. While the overall delivery model remains aligned with this proposition, the balance of activities has shifted over the programme period, with greater emphasis in the review year on pilots and technical assistance.

VfM is assessed using FCDO’s framework of Economy, Efficiency, Effectiveness, and Equity, alongside cost-effectiveness. The programme delivered £5.84m in the review year across two primary agreements (British Council-led consortium and EdTech Hub), with financial performance and utilisation discussed further in Section F.

Updates were not made to the VfM indicators for the year, and therefore indicators from the Business Case are being used to assess VfM, as with previous years in the Phase 1 of the programme. It is recommended that an updated VfM framework be developed for Phase 2 to align with the refined model and scope of work.

Economy
Economy is assessed against three business case indicators: consultant fee rates, in-sourced roles, and in-person versus remote inputs. In this third year of the programme, there was extensive delivery compared to previous years, including running pilot projects. Overall, inputs were delivered at reasonable cost relative to market benchmarks, though reliance on higher-cost consultants reduced economy in specific areas:

- Consultant fee rates: UK-based consultants accounted for 3% of the annual budget. They were engaged to lead programme pillars and took on programme roles to avoid recruitment delays and improve reporting quality. However, their higher fee rates reduced cost-efficiency and represent lower economy relative to equivalent in-house delivery over the longer term.
- In-sourced roles: Programme insourced roles (such as an accredited FCDO education adviser), designed to steer the programme at the FCDO to improve technical relevance and delivery against FCDO’s priorities, accounted for 3.87% of the annual budget, representing an economical approach to resource allocation and raising VfM.
- In-person versus remote inputs: Regional travel accounted for approximately 2% of the annual programme budget. This level of expenditure is proportionate to the year’s delivery and monitoring requirements, with prioritised engagement in key countries, and is considered an appropriate and economical allocation of resources.

Efficiency
Efficiency is assessed against three business case indicators: approval timelines with the ASEAN Secretariat (ASEC), the identifiable influence of programme activities; and the ratio of overheads to technical assistance (TA). Efficiency has improved compared to the previous Annual Review, with a higher proportion of resources allocated to TA and activities, reflecting the year’s extensive delivery phase, particularly for pilot implementation.

- Approval timelines with ASEC: While formal approval timelines are no longer a constraint post-accreditation, programme efficiency depends on effective engagement with ASEAN processes, which functioned well during the review year. Engagement with ASEC, primarily through the UK Mission to ASEAN, supported key processes including the Programme Steering Committee, ASEAN Workplan development, and revitalisation of the ASEAN Working Group on OOSCY.
- Influence of programme activities: Efficiency is also reflected in the extent to which activities translated into policy traction. As described in the Theory of Change section above, several factors show that there has been influence of the programme in the region. Examples include take up of pilot results in Cambodia, with the government integrating elements of pilot / research findings into delivery of early grade learning to accelerate learning, and the SEA-PLM 2024 data release, which resulted in the set-up of National Steering Committees and documented data use to inform learning improvement.
Ratio of overheads to technical assistance: The table below shows the breakdown of cost drivers across the programme’s two main partners. Non-Project Attributable Costs (NPAC) are 12% overall (excluding staff costs), representing a relatively lean overhead structure for a multi-country, multi-partner programme. Technical assistance and activities account for 76% of total expenditure.

Cost	British Council	EdTech Hub	Total
Staff	9%	15%	10%
Travel	1%	4%	2%
TA/Activities	78%	64%	76%
NPAC	11%	17%	12%
Total	100%	100%	100%

Effectiveness
Effectiveness tells us whether something has been done well and achieved the results intended. Three indicators used here are activities completed on time and rated satisfactory or more by partners, improvements in SEA-PLM data, and TA/activities improving design of other investments.

- Activities completed on time: Effectiveness was constrained by delays in finalising the integrated workplan, which led to downstream delays in contracting and delivery, reducing VfM despite most activities being completed by year-end. This affected SEA-PLM implementation, the OOSCY pilot in the Philippines, and completion and dissemination of OOSCY studies. Delays in contracting with UNESCO also resulted in late delivery of ASEAN Workplan support. With no rollover permitted into the next financial year, this contributed to an underspend (see Section F).
- SEA-PLM data: While improvements in learning outcomes cannot be attributed to SAGE, the programme made a substantive contribution to the production, analysis, and use of SEA-PLM data, including establishing National Steering Committees and strengthening evidence-to-policy processes. The data highlights a continued need for accelerated learning, particularly for disadvantaged groups. Socioeconomic status remains the strongest predictor of performance, with the poorest boys performing worst on average, while girls represent a substantial share of those not achieving minimum proficiency.
Improvement of other investments: The programme has made a significant contribution to leveraging broader investment in education through the implementation of pilot projects. The programme aligned itself with the World Bank’s Basic Education Improvement Programme (BEIP) in Cambodia which is supporting improvement of early grade learning and targeted instruction. Results from two Cambodia pilots are being utilised by the Ministry and the Bank to improve delivery, and this will also support delivery of wider UK ODA support through the Global Partnership for Education (GPE). For the TaRL pilot, a dedicated impact evaluation is currently being finalised, which will provide the first impact evaluation of TaRL in Southeast Asia. Although this was based on a pilot and not on sustained and scaled delivery, it is significant and has the potential to influence other investments in Cambodia and in the region to apply targeted instruction/TaRL approaches.

Equity
Equity is assessed against three business case indicators: the extent of disaggregation in SEA-PLM, gender balance in digital skills training and employment outcomes, and the scale of initiatives in IAI countries supporting marginalised groups, including girls and children with disabilities.

- SEA-PLM disaggregation. This indicator is highly relevant to the review year, with the SEA-PLM 2024 Regional Report launched in December 2025. Through SAGE funding, the report includes strong disaggregation and additional analysis. Findings highlight persistent inequities: only 53% of students meet minimum proficiency in reading and 67% in mathematics, with wide variation across countries. Socioeconomic gaps equate to up to two years of schooling, while disparities also reflect gender, language (around 37% not using the language of instruction at home), and access, with around 1 in 10 children out of school in several countries. These findings reinforce the need for targeted, equity-focused interventions.
- Gender in skills training: This third pillar of the programme was a comparatively minor focus. Two initiatives took place that had a strong focus on supporting women and girls – seeking to address a gender imbalance – to improve digital and STEM skills for employment. The Skills Training for Economic Participation (STEP) pilot in Timor-Leste integrated digital and financial literacy, equipping a small number of participants (100) with skills relevant to local economic opportunities. In addition, the Women in STEM scholarship scheme focused on addressing the lower number of women in the STEM field in the region through UK scholarships. In the review year, the focus was on the current cohort of 11 scholars in the UK and welcoming the previous alumni back to the region.

Cost effectiveness
Cost effectiveness is assessed against three business case indicators: benchmarking against ASEAN minimum thresholds for foundational literacy, additional funding leveraged through technical assistance and demonstration of evidence-based approaches, and potential long-term cost savings and returns on EdTech investments.

- Foundational literacy benchmarks: Benchmarking against minimum proficiency thresholds is best evidenced through the TaRL pilot, which directly improved foundational learning outcomes. Impact evaluation findings indicate that students achieved accelerated progress equivalent to around one year of learning in literacy and two-thirds of a year in numeracy in less than 10% of instructional time, demonstrating strong cost-effectiveness relative to ASEAN benchmarks.
- Additional funding leveraged: This is demonstrated through the Cambodia TaRL pilot, where strong evidence of impact has informed government adoption, with integration into the World Bank-funded Basic Education Improvement Programme (BEIP), thereby influencing significantly larger-scale financing ($100m) beyond SAGE resources.
- Returns on EdTech investments: Evidence on long-term cost savings and returns from EdTech investments remains more limited within Phase 1. While SAGE has strengthened the evidence base and supported the development of national EdTech policies and frameworks, these interventions are upstream and their cost-effectiveness will depend on future implementation and scale.

Assessment of whether the programme continues to represent value for money
Based on this assessment, the programme continues to represent value for money. However, Phase 2 will require a more focused approach, with stronger alignment between inputs, reform pathways, and measurable outcome-level change to maximise VfM.

E: RISK [½ to 1 page]

Overview of risk management

The overall programme risk rating remains Moderate, reflecting a combination of delivery, strategic, and contextual risks inherent to a complex multi-country ASEAN programme.

Commercial / budget: ODA reductions. Reductions in ODA to 0.3% created a context of tightening resources across development programmes, including ASEAN-UK SAGE. While this did not affect delivery during the review year, which benefited from an established budget, it introduced risks and uncertainty for forward planning. These changes have had implications for Phase 2 design. In response, the programme strategy has been refined to focus on a single pillar, foundational learning, and to align more tightly with FCDO strategic shifts. Procurement for the second phase has progressed at the time of writing.

Programme delivery: Delays in programme delivery. Delays in finalising the integrated workplan and partner agreements led to compressed delivery timelines and some activities not being fully completed within the financial year. Regular monitoring, especially in the later months, supported though good progress to implement the workplan.

Strategy and context: Complexity and scope of programme. ASEAN programmes can be complex. Stakeholders include the multilateral secretariat and 11 Member States, and programmes operate at the regional and country level, involving the participation of British embassies and high commissions. The ASEAN-UK SAGE Phase 1 had three distinct pillars, several partners in the delivery chain, and several levels of interventions – from a large-scale regional learning assessment and bespoke multi-country research to country-level pilots and technical assistance. Therefore, the scale and complexity during the review year presented a strategic risk. Extensive delivery in the review year across multiple contexts increased operational complexity and the risk of siloed implementation across workstreams and partners. To mitigate regular monitoring and support to oversight from the lead consortium and the UK Mission to ASEAN was required to improve coordination, coherence, and alignment across programme components.

Safeguarding: This risk remains within appetite, with safeguarding policies in place across all delivery partners and compliant with FCDO standards.

Risk trends and lessons
Over the review year, overall programme risk remained stable at Moderate, though the profile of risks evolved. Early risks were driven by delays in workplanning and contracting, while later risks related to compressed delivery timelines and coordination across partners. This highlights the importance of early planning and strong programme management in complex, multi-country delivery.

Climate and environmental risk
Climate and environmental risk is assessed as low. The programme does not involve infrastructure or activities with direct environmental impacts. However, climate-related disruptions to education systems remain a contextual risk. No specific mitigation actions are required at this stage.

Equality and safeguarding
The programme remains aligned with commitments under the Gender Equality Duty and Public Sector Equality Duty. All activities incorporate strong attention to gender and marginalised groups. No material changes to equality assumptions in the Business Case have been identified.

Partner risk and due diligence
Due diligence assessments for partners remain valid. While performance varied, particularly in coordination and financial management, no significant change in overall partner risk was identified during the review period.

Risk management: Overall, risks are being managed proportionately and remain within acceptable thresholds. Phase 2 has been designed to mitigate key risks through a narrower focus, clearer accountability, and stronger alignment with government reform priorities.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

For the review year, key performance indicators (KPIs) for delivery were established and given a RAG rating each quarter. The total rating reflects the rating for the year. The performance for the two agreements (British Council-led consortium and Ed Tech Hub) are taken separately on Finance and Reporting.

British Council-led consortium:
Performance across programme management functions is assessed as moderately satisfactory (Amber). Of seven KPIs, three were achieved (Green), three were partially achieved (Amber), and one was not achieved (Red). This reflects strong technical delivery and learning in a high-intensity delivery phase that is relevant to government reform and evidence-based, alongside more mixed performance in core management functions, particularly financial management, planning, and coordination.

Technical Delivery and Evidence Use – Achieved (Green). Technical delivery was consistently strong, evidence-based, and well received by regional stakeholders. It was particularly successful in Cambodia, where two major pilots were implemented aligned with the World Bank and government.

Learning and Adaptation – Achieved (Green). The programme demonstrated effective learning and adaptation, with feedback generally informing delivery and programme improvements. The final learning event was delivered and received well, demonstrating the extent of delivery and learning in the programme, ownership of governments across the region, and relevance to policy.

Workplan – Achieved (Green). Outputs were mostly delivered by the end of the year. However, this was sometimes through adjustments to sequencing and timelines, particularly in the first and final quarter. Delays in finalising workplans and partner agreements contributed to delivery pressures and financial performance. However, this a larger budget with significant delivery and achievement across the consortium partners.

Reporting and Accountability – Partially Achieved (Amber). The quality of narrative reporting improved over the review period supported by strengthened quality assurance processes and additional analytical input. Two quarter reports experienced delays in submission.

Value for Money – Partially Achieved (Amber). VfM improved and is evidenced through efficient delivery and alignment with key indicators. However, analysis and justification were not consistently strong across all quarters. This is partly a result in not updating indicators as recommended by the last AR. On advice from the FCDO, the programme used the Business Case indicators for this year, which were relevant to the review year. Performance is assessed as partially achieved overall, and FCDO acknowledges significant achievements in the programme contributing to success, please see the VfM section above.

Consortium Management – Partially Achieved (Amber). Coordination structures were in place and improved in the review year. However, partner feedback highlighted challenges in ways of working, and delays in partner contracting and payments which has affected this review. In the final quarter, weaknesses in joint planning for the major final dissemination event required additional support to ensure successful delivery. While the outcome was strong with high levels of government engagement and ownership and a comprehensive amount of evidence presented, the process highlighted areas where coordination and collaborative working could have been improved.

Finance – Not Achieved (Red). Financial performance fell short of KPI targets, with variance reaching approximately 9% in FY 2025 to 2026 against the second reforecast and 13% underspend against the original budget. This is against target thresholds of 5% variance. In-year reforecasting exercises were required. These issues indicate some weaknesses in planning, forecasting accuracy, and financial control.

Overall Assessment
While technical delivery and learning have been strong, notably with high engagement from governments and positive feedback from Cambodia, the review year highlighted some remaining challenges in financial forecasting, coordination, and planning.

Overall programme management performance is assessed as Amber. The Annual Review score is A, reflecting strong delivery against the logframe. KPIs provide a complementary assessment of management performance and highlight areas for improvement alongside overall delivery success.

EdTech Hub
EdTech Hub has been contracted separately and directly by FCDO but engaged within the British Council-led consortium, with financial reporting submitted separately and directly to FCDO. During the review period, EdTech Hub largely met expenditure targets (Green), with one minor Q2 slippage due to internal adjustments. Reporting was both formally through the British Council report and separately through concise technical quarterly progress summaries shared with FCDO and all partners.

FCDO performance
FCDO provided good strategic oversight and technical input throughout the review year, including close engagement through the Education Adviser, Programme Manager, and Posts. This contributed to alignment with government priorities and strengthened technical delivery. However, there are areas for improvement. In Phase 2, FCDO should ensure more consistent oversight of planning and coordination across partners to support more efficient and predictable delivery.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
Following recommendations from the previous review period, the programme strengthened its monitoring arrangements, with particular attention to improving the logframe. IPSOS, providing MEL support to the programme, and the UK Mission’s Education Adviser reviewed programme outputs and indicators during the reporting period to improve clarity of accountability and strengthen the results framework. A clearer MEL review process and timeline were also introduced, supporting refinement of the programme workplan. There were, however, some delays in finalising the logframe.

Given the intensity of delivery during the review year, monitoring was also supported through field visits to pilot implementation sites. The FCDO Education Adviser visited Cambodia to observe delivery firsthand, while consultants were deployed to Timor-Leste and Cambodia to monitor pilot progress directly. These visits, alongside regular engagement with Posts, particularly in Cambodia and Lao PDR, helped strengthen the programme’s engagement with ministries. This close engagement was also reflected in the Annual Review process, which included interviews with all implementing partners and a wide range of key stakeholders / beneficiaries. In total, 11 interviews were conducted with the ASEAN Secretariat, delivery partners, government representatives, Posts, and relevant development organisations.

Evidence
The programme has made a strong contribution to data and the evidence base for improving education in ASEAN in the review year. Notably, through SEA-PLM 2024 data, and through the first impact evaluation on TaRL in Southeast Asia, with the report due in June 2026. At this stage, data and evidence provides useful insights into programme delivery, design, and early influence on policy processes. However, as pilot implementation has only concluded during this review period, and the impact evaluation of one pilot remains ongoing, it is too early to robustly assess outcome-level change, particularly in relation to policy adoption, implementation, and improvements in learning outcomes.

Looking ahead, the programme will prioritise the use of global evidence to strengthen systems and improve foundational learning outcomes in priority countries. Continued emphasis will be placed on ensuring that evidence generated through programme activities is systematically used to inform decision-making, support adaptive management, and demonstrate progress towards intended outcomes.

The evidence for this review period is drawn from partner reporting, MEL frameworks, Annual Review interviews, and regional learning events. This evidence base has helped refine key assumptions established during the inception period and has informed emerging pathways that governments can use to strengthen policy and decision-making.

Learning
Learning from this review highlights three key lessons.

First, technical delivery alone is insufficient to demonstrate outcomes. The programme delivered substantial technical assistance and evidence, but there is limited systematic data on how this support has been adopted, adapted, and embedded within government systems at this stage. Given this was the last and most substantial year of implementation in Phase 1, this has not yet been well captured, and better measurement at outcome level would have supported more robust evidence.

Second, evidence must be actively translated into policy and implementation. While the programme generated relevant evidence and facilitated policy dialogue, a more structured and coordinated approach to influencing / advocacy and follow-up is needed.

Third, timing and sequencing are critical. Delays in planning and delivery reduced opportunities for dissemination, engagement, and policy uptake, particularly for research outputs and one pilot in the Philippines.

Phase 2 will address these issues through a stronger focus on reform pathways, improved tracking of uptake and use, more deliberate influencing strategies, and an adaptive learning approach to delivery.

Learning was captured through partner reporting, MEL systems, field visits, and structured stakeholder engagement, including interviews conducted during the Annual Review process. Regional events such as the Evidence and Insights Forum also played an important role in sharing learning across countries and partners.

This review was conducted by an FCDO accredited grade 7 Education Adviser, HEO Programme Manager, and grade 7 Head of Programmes. It was reviewed and approved by the SRO and development director for the UK Mission to ASEAN.

Recommendations from the last Annual Review
There were 20 recommendations, of which 13 were achieved, 4 partially achieved, and 3 not achieved.

Recommendation (short version)	Status
Workplan & budget finalised	Achieved
Lao PDR pilot approach agreed	Achieved
Risk management & scenario planning	Achieved
Roles & responsibilities clarified	Achieved
SAGE vision for how to strengthen institutions	Partially achieved
Multilateral engagement	Partially achieved
Research collaboration protocols	Achieved
Influencing strategy (outcome level)	Not achieved
Communications strategy	Partially achieved
Regional vs bilateral working clarity	Partially achieved
ToC, logframe & MEL review	Achieved
VfM indicators refresh	Not achieved (on FCDO advice to keep Business Case indicators)
Policy advocacy strategy	Not achieved
Logframe (policy dialogue clarity)	Achieved
RED process alignment	Achieved
Strategic research priorities	Achieved
Pilot guidance & milestones	Achieved
TA categorisation & reporting	Achieved
TA transparency & feedback loops	Achieved
Programme redesign (ODA cuts)	Achieved

Date of last narrative financial report	June 2026	Date of last audited annual statement	September 2025 (British Council)