## Annual Review Template

Title: Productive Social Safety Net Programme in Tanzania Phase II & III
Programme Value £ (full life): 30 million		Review date: September 2025
Programme Code: [AMP ID#] 400135	AMP start date: 2024	AMP end date: 2029

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006216.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006511.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
The Foreign, Commonwealth & Development Office (FCDO) supports the Productive Social Safety Net Phase II Programme (PSSN II)— launched in 2019 by the Government of the United Republic of Tanzania (GoURT) in partnership with the World Bank (WB) and other development partners including, Sweden, European Union, Ireland and Switzerland. FY 2025/26 marks the final year of implementation for PSSN Phase II, with Phase III scheduled to begin in late 2025.
The UK is supporting the PSSN programme with up to £30m (60% ICF) from 2024/25 to 2028/29. It will support the final year of PSSN II implementation and three years of Phase III. The programme aims to reduce poverty and vulnerability amongst the poorest 20% of the population. In addition to financial support, the UK offers technical assistance (TA) to respond to the emerging needs of the PSSN programme by providing evidence and strengthening the delivery of the programme.
The final year of the PSSN Phase II programme has reached over 906,699 households (HH) across 186 Programme Administrative Areas (PAAs), targeting the poorest 20% of Tanzanian households to increase their resilience to economic, food and climate shocks, increase their consumption and improve health and education outcomes for their children. The programme is implemented by the Tanzania Social Action Fund (TASAF), a GoURT implementation unit operational since 1999/2000.
[note] PAA is a generic term for local Government authorities/Zanzibar Administrative Authority or District, Town, Municipal and City Councils used by TASAF. For the purposes of PSSN, the United Republic of Tanzania is divided in 186 PAAs.
At its peak in 2023/24, the PSSN Phase II programme had 1.3 million households enrolled. Due to shortage of funds, the programme had to be restructured and exit households that had been in the programme since 2015 and assessed to have sufficiently increased their income and improved living conditions following a recertification process conducted in 2023/24. Additional caseloads were reduced following the graduation of 103,096 HH that received their full enhanced livelihood productive grant. As a result the case load reduced by 400,000 households. The current number of registered beneficiary households stands at 906,699.
This annual review is first for the programme and will assess final year of Phase II implementation and preparations for Phase III programme design.

For Annual Review of programmes undergoing significant adaptation because of reductions in ODA, please include the following standard lines (which should not be changed):

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.]

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme is scoring an A overall. This score is due to achieved outputs indicators across the three program outputs.

Cash Transfers: In 2024/25, six (6) bimonthly payment cycles were completed reaching 906,699 households. This is below the target of 960,0000 households but acceptable given that the reduced number of beneficiary households was a result of the restructuring of the PSSN program and graduation of beneficiary households following the receipt of their enhanced livelihood grant. All eligible (906,699 HH) received cash transfer payments as planned.

Public works: 247,000 HH received public works payment in 2024/25 bringing the total of PW recipients to 896,746 against the cumulative target of 837,000. Public works recipients are a subset of the cash transfer beneficiaries. The public works component of PSSN has generated productive assets that have a likely potential of reducing vulnerability and increase resilience to climate change and shocks in the community. Cumulative number of public works subprojects have surpassed the 27,000 target that was set for 2024/25 with 32,712 public works projects (69% qualifying as green public works) completed at community levels.

Graduation: 103,096 HH have received livelihood grants and graduated the program.

The program has a functioning grievance reporting mechanism. Of all the complaints and grievances logged in 2024/5, 99% were, addressed within 1-2 months of initial complaint being recorded.

The endline impact evaluation report data is being processed, and the preliminary report is expected before the end of 2025. The final report to be completed in early 2026. While the preliminary results report is not complete, some initial data from the endline impact evaluation shared reveal that the PSSN Phase II’s Livelihood Productive Grant has achieved positive impacts. It was found that provision of business training, productive grants and mentoring through the new ‘Enhanced Livelihoods’ element of PSSNII increased income by 20% relative to cash transfers alone, driven by higher business profits generated by beneficiaries. PSSN Phase II programme has 29 World Bank Project Development Objectives (PDO) indicators. By August 2025, 20 were fully achieved and data collection and analysis is ongoing for the remainder.

Design elements have been agreed for PSSN Phase III that takes on board lessons learned from the implementation of PSSN Phase II. This includes transitioning towards a Climate-sensitive, and shock-responsive social protection program, institutionalising payment-based conditions to increase domestic funding, full roll out of electronic payments and soft conditions being set against cash payments.

TASAF maintains excellent working relationships with donors, the World Bank, State House, the Prime Minister’s Office and Ministry of Labour who are key stakeholders within the social protection sector in Tanzania. The operational context for social protection in Tanzania has improved following the launch of the social protection policy in 2023, that has paved the way for discussions on institutionalisation of TASAF within Government structures and the development of a midterm expenditure framework.

Major lessons and recommendations for the year ahead [1/2 page]

Lessons

Sustainability and financing of the PSSN programme. PSSN remains largely financed via a concessional IDA loan from the World Bank and grants from bilateral donor partners (DPs). This continued dependency is a threat to the sustainability of the poverty reduction gains achieved and programme continuation given trend of shrinking bilateral and multilateral development aid globally.

Weather variability and unpredictability is undermining peoples’ resilience and erodes some of the gains achieved through the programme: A significant proportion of PSSN beneficiaries depend on rain fed substance agriculture and livestock keeping as their primary source of income. Increasing frequency of climate shocks such as drought and unpredictable rain patterns coupled with limited financial buffers impede peoples’ ability to adapt. Given the structure of the Tanzanian economy, low human capital amongst poor and vulnerable communities, and their susceptibility to the impacts of climate change and shocks, a robust approach to social protection is an essential part of Tanzania’s efforts to promote inclusive, pro-poor development and growth.

Recommendations
The programme to provide support to GoURT to develop a financing strategy, Institutionalisation roadmap, and medium-term expenditure framework for PSSN Phase III to support an increasing government financial contribution to the programme. As stated in the PSSN BC continued support needs to be aligned with institutionalising TASAF within the government structures as set out in the national social protection framework. Currently bilateral donor contributions make up 25% of the total PSSN programme budget, with the majority being funded through a World Bank IDA repayable loan to Government. GoURT provides about 1% of financing from its domestic budget. The UK working closely with Development Partners and the GoURT to ensure a financial sustainability plan. [FCDO PRO – September 2026].

The UK should support PSSN ambition for a shock-responsive social protection system under PSSN Phase III through Technical Assistance, building on global evidence and the experience of Covid-19. FCDO working closely with the WB and other DPs is supporting the design of an adaptive, climate-risk, shock responsive social protection program under PSSN Phase III. The initial focus will be to build the systems needed to make this transition. The FCDO PSSN Business Case includes the provision to procure technical assistance to support shock and climate responsive social protection system strengthening. Once operationalised this should enable the disbursement of temporary cash transfers to beneficiaries in response to shocks and climate related threats. Climate and meteorological data, socioeconomic and demographic characteristics, and geographical mapping has been conducted as part of the PSSN Phase III programme appraisal processes. [FCDO PRO – by March 2026]

The PSSN programme logframe should undergo a comprehensive review ahead of launch of PSSN Phase III. This Business Case caters for two phases of PSSN (II and III). This is the final annual review that covers PSSN phase II program. Ahead of the launch of PSSN Phase III, the UK to review the PSSN logframe to ensure it aligns with the new design elements of Phase III. (Technical Adviser PSSN Programme – by February 2026].

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Through technical assistance, evidence generation, and core funding, the UK aims to enhance the design and delivery of social protection in Tanzania. This support is expected to result in a more effective and sustainable delivery of PSSN Phase II and III, with improved climate resilience, gender empowerment, and shock responsiveness. If governance and coordination across Government and donors remain strong, and commitment to evidence base, the outcome will be a cost-effective, climate-resilient, and state-owned safety net system that protects vulnerable populations. Ultimately, PSSN aims to improve poverty for beneficiaries and their communities by increasing their resilience to economic, food and climate shocks, increasing their consumption and improving health and education outcomes for their children.

This is the first year of implementation under the Business Case, and there are no changes to the outcome and impact indicators from the original version. At present, the programme’s theory of change remains valid. There is strong evidence that our interventions will improve the design and implementation of PSSN II and III, and that PSSN will continue to deliver effective social safety net interventions, as demonstrated by evaluations and results reporting to date.

We will continue to monitor areas where evidence is limited or mixed, including the prospects for graduation out of poverty once beneficiaries stop receiving cash transfers, whether improved access to health and education services translates into better outcomes in the absence of quality service provision, and the long-term sustainability of livelihood and public works interventions. A light review the theory of change and results framework will be undertaken ahead of launch of PSSN phase III, in light of reduction in UK ODA.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme is on track to contribute to the expected impact of improved life chances and reduced vulnerability of poor and vulnerable households in Tanzania. Beneficiaries have received the full round of cash transfers to support increased consumption, household expenditure and reduce negative coping strategies. 103,096 HH have graduated from the program and community assets developed are building new skills and improving resilience to climate change. Further details including but not limited to benefits derived from community assets, functional income generating activities post exit from PSSN Program and proportion of beneficiaries with food consumption above the ‘poor level’ will be detailed following the conclusion of the PSSN II endline impact assessment.

Pending final decisions on the continuation of the PSSN Progamme key milestones for PSSN in the coming review period include
- Technical Assistance through UK expertise to support shock responsive social protection system development; and the development of a financing strategy and medium-term expenditure framework.
- Funding to WB through an FCDO CMP to support data renumeration and analysis of the Tanzanian Household Budget Survey to help ensure high quality and timely poverty and household consumption analysis, through the provision of international technical assistance.
- Financing and monitoring implementation of the PSSN Phase III programme.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Despite solid economic growth over the past decade, income and regional inequality have increased, and about half of Tanzania’s population remains poor and highly vulnerable. Population growth has led to a rise in the absolute number of people living in poverty. While poverty reduction cannot be achieved through social protection alone, it plays a critical role in contributing to reducing vulnerability, avoiding deterioration of wellbeing and enabling people to move out of poverty. This is supported by global evidence showing that social safety nets are a cost-effective means of protecting the extreme poor and food insecure.

The PSSN programme has demonstrated success; however, poverty reduction is a long-term commitment. Many PSSN beneficiaries have consumption levels below the poverty line, making a sustained move out of poverty difficult in the short term. International evidence highlights the need for longer-term support and sustained financing for social protection, alongside complementary mechanisms.

PSSN has gained renewed importance in the context of COVID-19, underscoring the need for greater attention to shock-responsive social protection. The FCDO Humanitarian Sector Code guidance, updated in June 2025, states that social protection programmes are eligible for spending under the humanitarian sector code if they are building shock-responsive systems, linking humanitarian and social protection systems, preventing hunger and acute food insecurity, and increasing climate resilience in geographies and among populations at risk of humanitarian and/or food crises. Such activities may include, for example, cash transfers, public works, and the use of climate data to better prepare for crises and target responses.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Regular, predictable cash transfers to extremely poor and vulnerable households
Output number:		1	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Numbers of 1) households enrolled in the programme and receiving conditional cash transfers and 2) households receiving regular wage payments from public works. All disaggregated by sex of head of household.	1)960,000 / 2)837,000 (cumulative)	Achieved / 906,699 eligible/existing HH received six rounds of cash transfers, following the exit of 400,000 HH from PSSN programme / 247,000 HH received public works payment in 2024/25 bringing the total cumulative PW recipients to 896,746. PW beneficiaries are a subset of the cash transfer recipients. / Disaggregation: / 87% of HH recipients are female and 13% male. / HH receiving disability benefits: 93,851 HH
1.2 Proportion of households receiving timely and predictable PW benefits	100%	Partially Achieved / 70%
1.3 Learning from PSSN II is reflected in the design of PSSN III to ensure the program is shock responsive and sustainably financed	Climate-sensitive, and shock-responsive SP system / Increased domestic funding. / Use of e-payment and technology to improve efficiency / Instituting soft conditions to cash payments	Achieved / PSSN III will include development of adaptive social protection systems, PBR on increased domestic funding and institutionalisation of TASAF, near 100% roll out of e-payments and soft conditions for cash transfers

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

PSSN households received six cash transfer payments between July 2024 and August 2025 (maximum cash transfer per HH is 55,000/month (£16). The number of HH receiving cash transfer payments declined from 1.3 million HH to 906,966HH from 2024 following the restructuring/refinancings of PSSN and graduation of HH from the program. 87% of HH recipients are females and 13% male.

93,851 HH received disability grants in the final PSSN II payment window, this number has declined from 94,806 in January 2025 as a result of natural attrition, relocations and other data updates. There are 907 child headed households (below 18), and 371,328 elderly headed households.

Part of the cash transfer payments to households were tied to conditions of school age children attendance in primary and secondary schools and children in beneficiary households aged 0-24 months old attending health facilities regularly. The compliance rates for beneficiary households to the conditions stands at 97.5% for education and 98% health and was consistent throughout the review period.

PSSN Beneficiaries by age ground and sex.

Sex	Clinic age	School age	Productive age	Elders	Total
	Year 0-5	Year 6-18	Year 19-59	Above 60 / Years
Female	70,481	744,509	1,000,759	328,468	2,144,217
Male	37,523	690,885	777,624	179,461	1,685,493
Total	108,004	1,435,394	1,778,383	507,929	3,829,710
Percentage (%)	2.82%	37.48%	46.44%	13.26%

Over 247,000 HH received public works payment in 2024/25 bringing the total of PW recipients to 896,746 against the cumulative target of 837,000. PW beneficiaries are a subset of the cash transfer recipients. PWP are interventions provide temporary employment to the enrolled poor households with labour capacity to work on labour intensive activities while providing income support and skills gain to participating beneficiary households and contributing to the creation of community assets.

Timely PW payments were not achieved; the proportion of timely PW payments was 70% against the target of 100% of beneficiaries. TASAF has mandated all procurement be processed through the National e-Procurement System of Tanzania (NeST) which has impacted the implementation of PWP activities meaning that not all PAAs commenced the PW activities in a timely manner. To mitigate this and enable timely completion the program shortened the timeframe for implementation to 4 months instead of 6 and allowed beneficiaries to work for 15 instead of 10 days per month, which ensured that all sub-projects were completed by June 2025. During the review year 3 PAAs implemented a climate-smart PWP pilot in partnership with the World Food Program (WFP). More on this is discussed in Output 2.

Design elements have been agreed for PSSN Phase III that takes on board lessons learned from the implementation of PSSN Phase II. FCDO in collaboration with the World Bank and DPs made concerted efforts to reach donor consensus on these areas that enabled GoURT buy in. These are design elements that are aligned to the PSSN II & III FCDO Business Case. They have been articulated in the draft project appraisal document (PAD) for PSSN, awaiting final approval from Government before submission to the WB Board set for November 2025.

PSSN III will include the development of adaptive, climate-risk, shock responsive social protection systems. The initial focus will be on building the systems needed to make the transition and interministerial coordination (including with the Disaster Management Department and Tanzania Meteorological Authority) to distribute roles and responsibilities as per mandates. Through UK core funding to the PSSN programme, initial beneficiary targeting and payment systems overlaid with improved climate and meteorological data, socioeconomic and demographic characteristics, and geographical mapping has been conducted as part of targeting preparations during the PSSN Phase III programme appraisal processes. The FCDO PSSN Business Case includes the provision to procure technical assistance to support shock and climate responsive social protection system strengthening. The intended outcome of the program is a cost-effective, shock responsive, state-owned social safety net system.

Financial sustainability of the program remains a key concern and in particular increased domestic financing for the PSSN program. Only about 1% of PSSN budget is currently financed by domestic resources. To address this the instrument proposed for the third phase of the PSSN Program is an investment project financing (IPF) loan with performance based conditions (PBCs) linked to increasing domestic financing and institutionalising of the TASAF within Government structures. The PSSN Business Case highlights the need for Tanzania to unlock more internal financing to increase its contribution to social protection programmes and ensure sustainable financing of the PSSN programme.

PSSN III will transition into near 100% roll out of e-payments as part of a strong consensus to adopt a fully digital delivery model for PSSN phase III. This approach includes the use of mobile-based data collection to enhance efficiency, accuracy, and dynamism, while phasing out paper forms and cash-based processes.

PSSN Phase III will trial a shift from hard to soft conditions for cash transfers. Besides the basic transfer that all HH receive, variable cash payments are linked to conditions to incentives use of education and health services. Beneficiary households have achieved compliance on conditions consistently across the years and the costs related to monitoring of conditions is high. Additionally challenges related to education/health outcomes are largely due to supply side issues which the programme does not have a direct control over.

The initial endline impact evaluation findings have linked the livelihoods enhancement components to increasing likelihood of beneficiary graduation from the programme and poverty. This has been factored into the design of PSSN Phase III, thus greater investment toward productive cash transfers combined with productive inclusion or enhanced livelihood activities have been emphasised in its design.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to this output during the past year. The program will undergo a comprehensive review of the logframe prior to the next review period to reflect the PSSN Phase III design.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

First year of Business Case implementation. No previous AR recommendations.

FCDO to provide technical assistance in support of the Government of Tanzania’s commitment to develop a midterm expenditure framework. This will set out the financing requirement for the PSSN phase III programme including the time frame for increased government domestic allocation. This is aligned with recommended approach of the PSSN BC. [FCDO PRO - September 2026]

Output Title	Community assets created which reduce vulnerability to climate change and increase resilience to shocks
Output number:		2	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Proportion of public works projects identified by the climate risk assessment that include measures for reducing climate risk or improve climate resilience	60%	Achieved / 69.6% progress as of August 2025
2.2 Number of public works projects created at the community level	27000	Achieved / A cumulative total of 32,712 public works projects were created at community levels by August 2025
2.3 Proportion of communities with climate risk assessment incorporated into multi-year planning	70%	Achieved / 70% over lifetime of the programme
2.4 Livelihoods strategy developed and begins implementation	Beneficiary households receiving enhanced livelihood support – 100,000 HH	Achieved / 103,096 HH / 90,724 women (88% of LE grant beneficiaries are women)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output measures the creation of community assets that reduce vulnerability to climate change and increase resilience to shocks. Given the relationship between extreme poverty and climate vulnerability, the PSSN programme aims to strengthen communities’ climate resilience. Public works provide temporary employment to beneficiary households with labour capacity, offering additional income during lean seasons, helping them acquire new skills, and supporting community adaptation to climate change. Livelihoods support is divided into two categories: basic livelihoods for all beneficiaries, and enhanced livelihoods for a select number of beneficiary households as a pathway to graduation following receipt of livelihood grants. Livelihood enhancement support complements the cash transfers by promoting household savings and investment in livelihood activities to facilitate graduation from the program.

The PSSN programme has surpassed the targets set under indicator 2.1 (proportion of projects identified by the climate risk assessment that include measures to reduce climate risk or improve climate resilience), indicator 2.2 (number of public works projects created at the community level), and indicator 2.3 (proportion of communities with climate risk assessments incorporated into multi-year planning). Cumulatively, the programme has created 32,712 projects against a target of 27,000, with 69% contributing to climate change adaptation or mitigation, exceeding the target of 60%. Additionally, 93% of the public works subprojects have maintenance and sustainability plans in place at the local level.

In the 2024/25 financial year, a total of 4,822 out of 4,920 public works subprojects (98%) were completed by June 2025 across 5,372 villages, Mitaa, and Shehia in 63 PAAs. The remaining 2% have been incorporated into PAAs’ development plans for completion.
.
S/N	Sub-project / categories	Number of / implement / ed Subprojects / in / 63 PAAs	Number of / implement / ed Subprojects / in / 3 CS-PW / Pilot PAAs	Total Number of / Subprojects / in / 66 PAAs	Number of / completed / Subprojects / in / 66 PAAs	% / completed / Subprojects / in
	Forestry	763	11	774	770	99%
	Environment	43	4	47	39	83%
	Soil and water	18	2	20	17	85%
	Irrigation and / Agriculture	29	2	31	30	97%
	Water	657	6	663	634	96%
	Roads	3,374	11	3,385	3,332	98%
	Total	4,884	36	4,920	4,822	98

In the reporting year, TASAF made deliberate efforts to improve the quality of green public subprojects. The programme updated its climate-smart public works (PW) guidelines and launched a Climate-Smart Public Works (CS-PW) strengthening pilot in three PAAs, covering 30 villages and Shehia. The pilot was conducted in collaboration with the World Food Programme (WFP), which provided technical assistance. The post-review of the pilot and its findings will inform the preparation and implementation of the PW component under PSSN Phase III, scheduled to begin in late 2025. WFP and the pilot team have started updating the menu of interventions to guide PAA sector experts. This includes revising guidelines for selecting interventions that make road subprojects more climate-resilient and adaptive to climate shocks, given their prevalence.

Beneficiary engagement during field visits revealed that gender considerations were considered during the implementation of public works activities. This includes adjustments such as reduced working hours, the nature of the tasks, and provisions for lactating and breastfeeding women. This feedback is consistent with biannual reporting from TASAF on implementation of PW and safeguarding considerations. These findings suggest that the PW gender mainstreaming checklist is being applied. Although a final percentage is not yet available, and in line with the guideline that the head of household is prioritized for PW participation, it is estimated that approximately 80% of all PW beneficiaries are women.

Promotion of savings groups was extended to all beneficiary households with labour capacity in 186 PAAs. A total of 14,660 savings groups were formed in 2024/25, comprising 158,067 members. Among them, 20,118 savings and investment group leaders received training in management and record-keeping. Enhanced livelihoods support was provided to select households in 51 PAAs. The target beneficiary households to receive the enhanced livelihoods productive grant and become eligible for programme exit/graduation was set at 100,000HH. This support was followed by coaching and mentorship. By the close of the program this target was surpassed by 3%, 103,096 (90,724 being women) received the enhanced livelihood grants and exited the program.

Beneficiaries noted that while local government experts in sectors such as water and agriculture were available to support the implementation of PW and livelihood activities, their participation was inconsistent. This reflection received from beneficiary engagement conducted by FCDO staff is consistent with the findings of the “Internal Rapid Assessment of the Program Component” that was conducted by TASAF.

Following the conclusion of the endline Impact Evaluation for the PSSN programme, more data will become available on the full impact of the PW and livelihoods components on consumption, productivity, and resilience at the community level.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to this output during the past year. The program will undergo a comprehensive review of the logframe prior to the next annual review period to reflect the PSSN Phase III design.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The CS-PW pilot findings are critical to the roll out of PSSN Phase III and FCDO should engage actively in these dialogues and review of drafts to shape the manuals and interventions proposed [FCDO PRO – December 2025].

FCDO to utilise dialogue and existing Government to donor platforms to relay messages on increasing participation of Governmental sectoral experts (WASH, Climate, Education, etc) in the implementation of the PSSN Phase III programme thus strengthen sustainability and ownership of interventions [FCDO SRO – September 2026].

Further work should be done to integrate PSSN Phase III beneficiaries to existing supportive livelihood enhancement programmes led by GoURT under the 10% Empowerment Loans Fund and by civil society organisations. [TASAF – September 2026]

Output Title	Social protection institutions established and functional
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 PSSN aligned with National Social Protection Policy developments	PSSN program II supporting implementation of national social protection policy	Achieved
3.2 Impact evaluation conducted, and findings used to inform policy	PSSN II endline impact evaluation final report	Partially achieved. / The endline impact evaluation report data is being processed, and the preliminary report is expected before the end of 2025 with the final report to be completed in early 2026.
3.3 Effective communications and accountability systems to PSSN beneficiaries are in place and operational	80% of Complaints and grievances addressed within 1-2 months of initial complaint being recorded. / (80 percentage).	Achieved / Average 99%

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

PSSN II project activities align with the with a draft National Social Protection Policy which recognises the programme as the premier Government social assistance vehicle administering cash transfers, public works and livelihoods enhancement for productive inclusion targeting extreme poor households.

Data from the Household Budget Survey (HBS) 2017/18 launched in 2019 has confirmed the important contribution that PSSN has made to reducing poverty in Tanzania. During this review period the PSSN programme supported the training of enumerators and quality assurance and analysis of data for the 2025 HBS. This will confirm current poverty levels, and the PSSN’s impact, and is expected to be published in 2026.

TASAF’s National Steering Committee (NSC) met quarterly during the reporting period. The NSC is that national oversight body for TASAF, members of whom are appointed by the state house.

The PSSN II endline impact evaluation is near completion and initial results indicate that PSSN II’s enhanced livelihood grant has produced positive impacts. The provision of business training, larger enhanced livelihood grants and mentoring increased income by 20% relative to cash transfers alone, driven by higher business profits generated by beneficiaries in their businesses. The final evaluation should confirm the overall benefits and costs of the larger one-off livelihood grants verses the smaller regular cash transfers.

This output also tracks the effectiveness of the grievance redress mechanism (GRM) system effective in all PAAs of the PSSN programme. During this Financial Year 2024/2025, a total of 7,373 grievances have been lodged, with 99.2% resolved and only 0.8% pending. A total of 1,232 grievances were received between January to June 2025 period. Out of these, 1,175 (95.4%) were resolved and closed, while 57 (4.6%) are at various stages of resolutions. These included 46 grievances related to payment, nine (9) enquiries on Program procedures, and two (2) grievances for non-inclusion. During field monitoring visits beneficiaries were engaged as to whether they were aware of the GRM system and the nature of issues they have lodged to seek redress. Many beneficiaries were aware that the system exists and confirm that majority challenges they experience as part of the programme related to payments. Through beneficiary engagement and PSSN biannual reporting from TASAF, it is noted that beneficiaries are aware through communications they have received within their PAAs that the PSSN II programme is ending following the final cash transfer payments taking place August 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes were made to this out in the past year as this is the first year of implementation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This is the first year of the PSSN II & III business case. There are no previous recommendations.

PSSN reliance on external financing has put the programme under significant risk of early closure due to limited funding. Without a programme restructuring and reduction of case load the programme would have closed in March 2025 instead of September 2025. This would have created a big gap between phase II and phase III of the programme with negative impacts on programme effectiveness.

TASAF as an implementing entity of PSSN although sits within state house is not a formal government institution. This status presents operational and continuity risks as funding for personnel and other operations are linked to the WB loan. Agreement by the Government to cover these core expenses is welcomed and sets the programme in good position to ensure effective preparation for Phase III. In the light of this UK supported the WB proposition to include performance conditional indicators (i) domestic financing (ii) institutionalisation of TASAF as critical steps towards sustainability of social protection spend and development of social protection system in the country.
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case.

The PSSN programme delivers good VfM in line with the original business case proposition.

TASAF is integrated within existing government structures at both central and local levels. This enhances efficiency by reducing costs, including overhead expenses, in comparison to the establishment of parallel systems. TASAF has developed and adopted additional controls and guidance to strengthen these structures and ensure efficient programme operations. This includes the rollout of the e-payment system through the existing government e-payment gateway and the use of the National e-Procurement System of Tanzania (NeST) for all programme procurement down to the lowest levels. Further details related to VfM measures and metrics are provided below.

Economy
The Conditional Cash Transfers (CCTs) utilize a decentralized, low-cost model that relies on locally selected Community Management Committees to facilitate cash payments to beneficiaries. Administrative costs account for 11% of the total programme costs (including cash transfers and public works), which is lower than the 12% benchmark set at the outset based on global comparisons. The implementation of electronic systems has reduced programme costs associated with PAA administration of cash transfers. Support provided to the PSSN has enabled the UK to influence social protection policy in Tanzania and has reinforced its position as a strategic partner. As a core donor, the UK has contributed to the inclusion of a disability grant, the emphasis on green public works, and the design of PSSN III, which aims to build institutional and cross-government capacity for a climate-sensitive and shock-responsive social protection programme.

Efficiency
The adoption of the electronic payment system has improved the efficiency of cash transfers. Approximately 60% of PSSN II beneficiaries have registered for e-payment. An additional 100 households have been registered for “virtual” e-payments, which allow individuals without national identification—and therefore without phone numbers—to withdraw payments from registered telecom providers using biometric identification.

Effectiveness
The endline impact evaluation of PSSN II is nearing completion, and initial results indicate that the programme is making progress toward its intended outcomes. PSSN II has demonstrated positive impacts through the Livelihood Productive Grant. The provision of business training, productive grants, and mentoring under the Enhanced Livelihood component has increased income by 20% compared to cash transfers alone, driven by higher business profits generated by beneficiaries.

Equity
PSSN continues to perform well against gender indicators. Cash is disbursed to women on behalf of the household to promote their resilience, improve consumption, and support economic empowerment. Women represent 87% of household representatives, and 94,416 households are receiving disability grants. Gender mainstreaming protocols for CCT, public works, and community sessions are consistently observed in programme implementation. This includes prioritizing pregnant and lactating mothers during payment windows, exempting them from public works, and conducting gender awareness training during community sessions.

Assessment of whether the programme continues to represent value for money
The programme continues to deliver value for money. It reaches 20% of the poorest population and provides these households with support to escape poverty, progressively build their asset base and human capital, and strengthen their resilience to climate change and shocks—essential for sustaining long-term poverty reduction.

Support to PSSN aligns with the UK’s commitment to building resilience and helping those affected by disasters and climate change adapt to shocks, while also strengthening national food security and social protection systems.

The programme reflects the UK’s commitment to environmental sustainability, climate adaptation, and resilience, and contributes to evidence generation in the region. Sixty percent of PSSN spending will count toward UK International Climate Finance. The programme will further contribute to evidence generation, particularly regarding targeted climate-sensitive social protection measures. PSSN directly complements other British High Commission investments in Tanzania’s health and education sectors by incentivizing educational attainment to junior secondary level, promoting dietary diversity, and encouraging clinic attendance—thereby amplifying the impact of FCDO investments in these sectors.

Support to the PSSN programme also includes technical assistance to develop a financing strategy and medium-term expenditure framework aimed at increasing government financial contributions to the programme. This complements ongoing collaboration with the Government to improve the efficiency and effectiveness of its business and investment policies, enabling Tanzania to boost revenue collection and expand public expenditure for social protection.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk rating for the PSSN programme remains moderate.

Strategy and Context: Tanzania is holding national elections in October 2025. To avoid electioneering influencing cash transfer disbursement, TASAF has finalised its last disbursement of cash transfers and program implementation August 2025, prior to the election, Phase III of the PSSN Programme is set to begin after the election period.

Policy and Programme Delivery: The financial sustainability of the program is the biggest challenge for program delivery. Government disbursements to the PSSN program remain low in comparison to donor partners and the World Bank loan.

The National Social Protection Policy though UK support provided between 2015-2020 is in place and through its operationalisation will provide the institutional, legal, and administrative framework around social protection in Tanzania and formally anchor TASAF and PSSN in the country’s government structures. This also provides the backdrop for sustainability of social assistance as a right. The UK has initiated a review process that will support and provide options for transforming TASAF from a WB implementing unit to a government social protection implementation entity. Additionally, the UK will work with other donor partners to ensure the development of the medium-term expenditure framework.
FCDO monitored potential negative impacts of the PSSN programme on women’s burden of unpaid work. To mitigate this FCDO ensured that PW guidance manuals supported women’s participation in wage labour. Field visits and monitoring reports found good consideration of gender including reduced hours and labour types.

Safeguarding. The PSSN programme has a low safeguarding risk appetite. As part of the condition of the World Bank Loan, TASAF conducts environmental and social safeguards assessments to ensure they can address environmental and social challenges that may arise during the implementation of the programme. This includes an assessment and mitigations against sexual exploitation abuse and harassment. A Grievance Reporting Mechanism (GRM) allowing both anonymous and direct reporting of grievances is available and communicated to beneficiaries of the programme. Most of the grievances to date have related to beneficiary payments and eligibility within the programme. All grievances are managed and closed timely. Review of data of grievances is conducted biannually during the joint sector review missions organised by the World Bank. Maintaining a functioning and responsive GRM helps detect sexual exploitation, abuse, and harassment particularly at the local level where transfers are disbursed. Review of programme compliance to environment and social safeguarding is undertaken every six months.

The targeting process for beneficiaries uses a three-stage approach, thereby reducing (but not eliminating) the power held by any individual to abuse or exploit others. A gender working group has been established which monitors and provide technical support throughout programme implementation.

Financial and Fiduciary This programme has a low risk appetite for fiduciary risks and TASAF and DPs continue to manage risks within appetite. Money flows through the government system but in a separate account and does not go through the general revenue account. This was protected to making sure that there is no interruption in cash payment to beneficiaries. To manage risks inherent in delivering cash transfers via village authorities to end beneficiaries, beneficiaries are being encouraged to register for e-payments through bank and mobile network operators. At current 60% of beneficiaries are enrolled to receive payments electronically. Spot checks are conducted at the PAA level during payment windows to ensure and strengthen accountability.

Many aspects of PSSN are administered through Local Government Authorities (LGAs) where the financial procedures and capacities are not always as robust as at the national level. This presented additional risks that misuse of funds would occur, hampering PSSN’s ability to effectively deliver outcomes and achieve VFM. To mitigate this, TASAF has developed manuals and a set of controls, which included close monitoring of processes to identify public works, quarterly LGA audits and a taskforce consisting of donors and TASAF management to provide oversight and follow-up on audit findings. No significant discrepancies have been found between LGAs receipts and beneficiaries’ payments as measured through the Comptroller Auditor General (CAG) reports. Additionally, the program has followed Government guidance and mandated that all procurement done at local levels is administered through the Government NeST system.

Update on Partnership Principles (delete this section if n/a) [1/2 page]

The Partnership Principles Assessment for Tanzania was most recently updated in July 2024; it found that Tanzania meets basic standards across the four PPs but there are improvements that need to be made to ensure UK partnership can deliver desired outcomes.

Tanzania continues to demonstrate a long-term commitment to poverty reduction, sound management of public finances and most economic and social rights, but while some political and media freedom issues have improved over the past 5 years, Tanzania still has notable limits on freedom of expression and political pluralism. Tanzania has invested, with donor support, significant time and energy in improving its financial management but still needs to increase efforts on preventing and fighting corruption.

In relation to this program the programme has ensured that people with protected characteristics are considered and prioritised e.g. the hunter-gatherers people who are a marginalised group in the country and people with disability. The programme also pays a significant focus on gender, and females are identified as representative head of households. Currently 87% of HH recipients are female and 13% male. 52% of overall programme direct beneficiaries are women based on the national census. Finally, the government’s decision to continue to secure a loan for phase III of the PSSN programme to finance cash transfer to the extreme poor, is a positive demonstration of their commitment to poverty reduction.

Annual Statement of Progress (financial aid programmes only – delete if n/a) [1 page]

Current level of fiduciary risk and direction of travel since last ASP	Stable
Specific assessment of corruption risk and direction of travel since last ASP	Stable
Is a full FRA update required?	No

FCDO Tanzania has completed a fiduciary risk assessment in 2025.

The overall fiduciary country risk assessment for Tanzania Mainland is substantial with no change in risk rating but with a positive trajectory compared to the previous FRA 2018. After applying safeguards, the overall assessment of the GoURT’s residual risk is substantial for both fiduciary and corruption with no change in risk rating but a positive trajectory compared to the previous FRA 2018. Overall assessment of reforms, indicate that they are partially credible but after applying safeguards, they are considered credible.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

During the reporting period the PSSN programme remained compliant against the review of programme delivery and its key controls using the FCDO Management Assurance Process (MAP).
Governance and performance
The PSSN Program is led by the TASAF Management Unit (TMU), who are responsible for the day-to-day operation of PSSN and ensuring program implementation is conducted in accordance with the Operational Manual and other guidelines. TASAF is answerable to the National Steering Committee, who provide overall supervision and monitoring of PSSN activities in all PAAs, from whom they receive consolidated implementation reports. TASAF is embedded within existing government structures which improves coordination and effectiveness up to the PAA levels. TASAF has performed well in a difficult operating context and maintained good relationships with donor partners throughout the reporting period.
Financial Management and Reporting
TASAF has adequate financial management structures to produce financial reports to FCDO. Financial management was assessed as satisfactory during the biannual review periods. TASAF has submitted quarterly harmonised financial and narrative reports on time and to the expected quality. Both procurement and financial management systems were assessed by the World Bank and donor partners to be satisfactory during the latest supervision mission held in August 2025. By the review period the program expenditure has reached 99% of against the approved plan and budget activities for 2025.
TASAF procurement is managed through the WB STEP system and monitored accordingly. Overall procurement performance remains satisfactory despite some challenges observed in regularly updating and uploading documents in STEP. During the reporting period, a new requirement has been operationalised for use of NeST in procurement for public works and other local government expenditure related to the PSSN program at PAA levels. Training on the use of the tool was rolled out, but which impacted implementation of PW activities.

Audits
The latest Audit report covered the period 2023/24. TASAF received unqualified opinion during this reporting period. There were 46 audit findings, 39 (85%) of these findings had been implemented, while the remaining 7(15%) are under implementation. The TMU will continue to conduct follow ups to ensure that all outstanding issues are closed before the closure of PSSN II in September 2025.

Internal audits of PAAs are conducted on a quarterly basis. These are reviewed by the TMU and the outcomes shared with PAAs and monitored routinely.,

Programme VfM

The use of community volunteers for managing engagement with communities and delivering cash to beneficiaries and administering public works has been a very cost-effective model vis-a-vis other social protection models that are not integrated with government structures.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

TASAF confirms that quarterly national level National Steering Committee (NSC) meetings were held. The NSC is appointed by the State House and responsible for setting the strategic framework, clearing the annual work plans and budgets, as well as reviewing progress reports and monitoring the outcomes of PSSN activities.

Technical working groups (TWG) have been established between donor partners, the world Bank, and the Government of Tanzania responsible for monitoring and steering implementation progress towards the programme goals. During the review period two (January 2025 and August 2025) TWG meetings were held alongside the bi-annual joint sector review mission.
[note] There are 7 technical working groups, TWG1: CCT, Targeting, recertification, conditionalities; TWG2: PWs, Safeguards and Climate Change TWG3: Livelihoods; TWG4: Strengthening institutional capacity and integrated delivery systems; TWG5: fiduciary issues/ FM Subgroup; TWG6: Cross cutting issues; TWG7: e-payments.

Biannual Joint Review and Implementation Support Missions (JSRM) were held between donor partner, Government led by the World Bank. The review mission included in-depth meetings with TASAF on roll out, implementation and monitoring, meetings with GoURT ministries and field visits to monitor programme performance and engage with beneficiaries of the programme.

FCDO undertook an additional field visit in August 2025 to engage with beneficiaries and review program implementation and these engagements all contributed to this annual review. A team of internal FCDO staff cross cutters were engaged in the field monitoring visits and provided substantive inputs to the annual review. The annual review was also shared with TASAF for feedback and comment before submission for approval to the Development Director.

Learning

Several studies were conducted during this annual review period. This includes the PSSN II endline impact evaluation and Endline survey and the Stawisha Maisha impact evaluation which have not concluded and will be discusses in full in the upcoming PSSN programme annual review period 2026. FCDO has initiated the process to commission a short study to develop recommended options for formal integration of TASAF within government systems with clear options and timelines, with the aim of transforming TASAF from a WB implementing unit to a government social protection implementation entity.

Study	Key Lessons / Findings
PSSN II endline Impact Evaluation and Endline survey	Preliminary findings: / PSSN II has achieved positive impacts on Livelihood Productive Grant. It was found that provision of business training, productive grants and mentoring through Enhanced Livelihood increased income by 20% relative to cash transfers alone, driven by higher business profits generated by beneficiaries in their businesses. / Enhanced Livelihoods (EL) alone is as effective as implementing PW and EL together.
Gender Mainstreaming in Tanzania’s Productive Social Safety Net Program: An Assessment of the Gender Action plan of 2019-2024	There is sufficient integration of gender across the program components. / There is improvement on gender sensitivity across several level of implementers and in the community compared to PSSN I. / Insufficient time for gender training of PAA staff vis a vis other trainings provided. / There is insufficient duration and frequency of gender related training during community sessions. / More efforts needed for gender transformation and addressing negative gender norms.
Internal Rapid Assessment of the Program Components (LE And PWP)	The program has been successful in empowering many of its beneficiaries to participate in saving and investment groups. / From sample study, 82.9% of saving and investment groups had existed for more than one year whereas 17.1% had existed for less than one. / Group saving is an important factor in mobilizing resources for members to access loans for investing in income generating activities. / Beneficiaries note inadequate support from local Government extension services. / Climate change related PW sub-projects accounted for 49.2% of all implemented subprojects in the PAAs, underscoring the need to intensify efforts to raise awareness and promote the prioritization of climate change sub-projects. / Although more effort is needed the program has been successful in creating awareness about the need for beneficiary households to graduate from the Program after their socio-economic status have improved.
Comprehensive Analysis of Social Protection Intervention in Tanzania Mainland	Tanzania does not have a national registry to guide a comprehensive system of social protection. / Although has made significant effort to support and advance social protection, social assistance and employment programmes remain underfunded relative to the needs of the population. / Social assistance in terms of cash transfer is implemented within the Productive Social Safety Net and is the most extensive cash transfer programme in Tanzania. / There is inadequate coordination between social protection programmes at national level and local government authorities, and poor coordination between local government authorities and programmes implemented by non – governmental organizations.

Date of last narrative financial report	August 2025	Date of last audited annual statement	June 2024