## Sheet1
PROJECT TITLE | TANZANIA PRODUCTIVE SOCIAL SAFETY NET PROGRAMME Phase II
IMPACT | Impact Indicator 1 |  | Baseline (September 2019) | Milestone 1 (September 2020) | Milestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
Improved life chances and reduced vulnerability for poor and vulnerable people in Tanzania | Proportion of PSSN households with consumption below the adjusted food poverty line | Planned | 70% | 70% | 70% | 70% | 70%
|  | Achieved |  | 64% | 64% | 64%
Source
PSSN Impact evaluation baseline, mid-term and final reports,
| Impact Indicator 2 |  | Baseline (September 2019) | Milestone 1 (September 2020) | Milestone 6 (September 2021)
| Proportion of beneficiaries households with an increase food consumption | Planned | 30% | 30% | 30% | 30% | 45%
|  | Achieved |  | 44% | 44% | 44%
Source
PSSN Impact evaluation baseline, mid-term and final reports
OUTCOME | Outcome Indicator 1 |  | Baseline (September 2019) | Milestone 1 (September 2020) | Milestone 6 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
A sustainable safety net established as a foundation for a national social protection system and improved coping strategies amongst households | Government takes two concrete steps to establish evidence based climate sensitive social protection systems | Planned |  | Climate change recognised by national structures as an integral part of social protection systems. NSPF vision and policies promote climate resilience. |  |  | Climate sensitive social protection evidence feeds into national social protection policy making and planning | Assumptions
|  | Achieved |  |  | 1.Climate assessments mainstreamed in public works. 2.National thematic working group within TASAF on Environmental Safeguards. 3. Draft NSPP includes climate resilience, but policy is not yet approved by the Cabinet. | 1.Climate assessments mainstreamed in public works. 2. National thematic working group within TASAF on Environmental Safeguards 3. Draft NSPP includes climate resilience, but policy is not yet approved by the Cabinet. |  | Political commitment is maintained and strengthened under a new government, economic conditions allow for an expansion of social protection spending above current commitment. Other DPs support FCDO in exploring mechanisms for a responsive (expanding) social protection mechanism to respond to the risk of climate change, PSSN implementation proceeds as plan and is robust enough to begin discussions around an additional instrument, GoT sees value in the approach Programme payments are made on time, and are sufficient enough and reliable enough to prevent negative coping strategy, shocks are at a low enough level to allow asset accumulation, community assets mitigate the effect of major climate shocks
Source
TASAF Climate Change TA reports, TASAF reporting, NSPF, NSPF action plan, SPWG minutes
| Outcome Indicator 2 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
| Reduction in households using negative coping strategies to cope with climate and/or other shocks | Planned | 10% decrease from baseline | 15% decrease from baseline | 15% decrease from baseline | 15% decrease from baseline | 18% decreased from baseline
|  | Achieved | 1)likelihood of employing negative coping strategies reduced to 6.5% from 7.8% . 2)Protected income and asset losses following negative shocks. 66.7% of beneficiaries lost income or assets due to shocks in comparison to 71% in the control group | 1) likelihood of employing negative strategies (e.g. selling of productive assets, withdrawing children from school, etc.) reduced by 16%. 2) likelihood of income or asset loss was also reduced by 4.3%. | Met - reduced by 16% | Met - reduced by 16%
Source
PSSN Impact evaluation baseline, mid-term and final reports
INPUTS (£) | FCDO (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
0.3
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
Regular, predictable cash transfers to extremely poor and vulnerable households | Numbers of 1) households enrolled in the programme and receiving conditional cash transfers and 2) households receiving regular wage payments from public works. All disaggregated by sex of head of household. | Planned | 1) 920412 2) 250,000 | 1) 920412 2) 250,000 | 1) 920412 2) 250,000 | 1) 1,300,000 2) 250,000 | 1)960,000 2)837,000 | Assumptions
|  | Achieved | Exceeded Expectations. 1)1,118,751, reaching 5,726,101 direct beneficiaries. 52% of beneficiaries are female. 2)250,404 | 1) 1.1 HH reaching 5,474,231 direct beneficiaries 2) 321,975 HH on registry but did not complete work or receive payments in the reporting year due to agreed pause in component | By the last payment in February 2020: 1) 995,500 HH were reached as some beneficiaries had passed away or moved out of project areas. 2) 321,975 HH on registry but did not complete work or receive payments. Disaggregation: 84% of HH recipients are female and 16% male. | 1). 1,356,607 existing HH received two rounds of cash transfers in March and April 2023 2). 581,553 HH received one round public works payment in 2023. | 1) 906,699 existing HH received six rounds of cash transfers between 2). 896,746 HH received regular public works payments as of August 2025 Disaggregation: 87% of HH recipients are female and 13% male. HH receiving disability benefits: 93,851 HH | TASAF receives GoT and DP funding in a timely manner and can effectively distribute to LGAs to allow all planned transfers to happen in a timely manner. Corruption and leakage do not affect transfer levels and frequency. Public works preparation can be carried out by all LGAs in time for works to take place in the lean season. Policy space for the next phase of PSSN welcomes, reflects and adapts to evidence generated in the course of this programme.
Source
TASAF annual reports
| Output Indicator 1.2 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
| Proportion of households receiving timely and predictable PW benefits | Planned | 65% | 80% | 80% |  | 100%
|  | Achieved | Not Met, 55% of 250,000 | Not achieved | Not Achieved Due to budget constraints during transition from PSSN I to PSSN II, no public works payments were made during the reporting period. | Public works payments were made in June – July 2023 but these were delayed payments that should have been made in the January – February window | Partially Achieved 70%
Source
TASAF annual reports
IMPACT WEIGHTING | Output Indicator 1.3 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
40% | Learning from PSSN II is reflected in the design of PSSN III to ensure the program is shock responsive and sustainably financed | Planned | E-payment pilot complete in 8 LGAs and report disseminated to TASAF and donor partners TASAF finalise effective and feasible recertification strategy and action plan | Payment mechanism within PSSN II reflects key findings of epayment pilot to ensure payments are timely, regular and cost-efficient. PSSN II approach incorporates recertification strategy. | Payment mechanism within PSSN II reflects key findings of epayment pilot to ensure payments are timely, regular and cost-efficient. PSSN II approach incorporates recertification strategy. |  | Learning from PSN II is reflected in desing of PSSN III
|  | Achieved | Exceeded expectations. The’ e-payment pilot has been completed in 16 Project Area Authorities (PAAs)/ LGAs. The findings of the pilot will inform the national rollout of e-payments during PSSN II | Achieved | Achieved | Achieved. Payment mechanism within PSSN II reflects key findings of e-payment pilot to ensure payments are timely, regular, and cost-efficient. PSSN II approach incorporates re-certification strategy. | Achieved PSSN III will include development of adaptive social protection systems, PBR on increased domestic funding, near 100% roll out of e-payments and soft conditions for cash transfers
Source
|  | TASAF annual reports | [5 empty] | RISK RATING
INPUTS (£) | FCDO (£) |  |  | FCDO SHARE (%) |  |  |  | Medium
INPUTS (HR) | FCDO (FTEs)
0.3
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
Community assets created which reduce vulnerability to climate change and increase resilience to shocks | proportion of projects identified by the climate risk assessment that include measures for reducing climate risk or improve climate resilience | Planned | 60% | 60% | 60% | 60% | 60% | Assumptions
|  | Achieved | Achieved | Achieved | Achieved | Achieved 60% | Achieved 69.6% | Public works planning and administration are conducted well at the LGA level, with appropriate oversight and technical expertise to ensure that assets produced are 'green' and support mitigation/adaptation to climate change Public works are implemented in the lean season and raise household income rather than detracting labour from other household activities (particularly farming)
Source
TASAF annual reports
| Output Indicator 2.2 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
| Number of public works projects created at the community level | Planned | 3700 | 3700 | 3700 | 3700 | 27000
|  | Achieved | Not met expectations. 1,542 public works projects completed this review period. This brings the total to 7,231 (cumulative) public works projects | Achieved. This target was exceeded prior to the pause on PW activities. A cumulative total of 7231 public works projects created at community level. However, no public works activities were conducted in the reporting year. | Achieved A cumulative total of 7775 public works projects were created at community level | Achieved A cumulative total of 7775 public works projects were created at community level | Achieved A cumulative total of 32,712 public works projects were created at community levels by August 2025
Source
TASAF annual reports
| Output Indicator 2.3 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
| Proportion of commnunities with climate risk assessment incorporated into multi-year planning | Planned | 70% | 70% | 70% | 70% | 70%
|  | Achieved | Achieved. 70% of communities have included climate risks into multi-year plans. | Achieved. 70% over lifetime of the programme | Achieved. 70% over lifetime of the programme | Achieved. 70% over lifetime of the programme | Achieved 70% over lifetime of the programme
Source
TASAF annual reports
IMPACT WEIGHTING | Output Indicator 2.4 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
40% | Livelihoods strategy developed and begins implementation | Planned | Livelihood strategy financed and begins implementation | Livelihood strategy implemented as per work plan (target to be defined following completion of strategy) | Livelihood strategy implemented as per revised work plan | Livelihood strategy implemented as per revised work plan | Beneficiary households receiving enhanced livelihood support
|  | Achieved | Off track Stratergy in place but implementationnot started | Not Achieved. Delayed due to budget constraints and then COVID-19. Implementation to restart in 2021. | Achieved Training of trainers on basic economic skills was conducted for 180 facilitators in 6 PAAs Further activity was delayed due to budget constraints and Covid-19. | Achieved Training of trainers on basic economic skills was conducted for 180 facilitators in 6 PAAs Further activity was delayed due to budget constraints and Covid-19. | Achieved 103,096 HH 90,724 women (88% of LE grant beneficiaries are women)
Source
|  | TASAF annual reports, consultancy ToR, draft strategy, financing commitments of GoT, development partners, TASAF financial forecasting | [5 empty] | RISK RATING
INPUTS (£) | FCDO (£) |  |  | FCDO SHARE (%) |  |  |  | Medium
INPUTS (HR) | FCDO (FTEs)
0.3
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
Social protection institutions established and functional | PSSN alligned with National Social Protection Policy developments | Planned | FCDO supports and participates in consultation on national social protection policy and implementation strategy, and ensures PSSN II design process reflects SP Policy developments. | PSSN II design and SP policy are aligned and mutually supportive. | PSSN II design and SP policy are aligned and mutually supportive. | PSSN II design and SP policy are aligned and mutually supportive. | PSSN program II suporting implementation of national social protection policy | Assumptions
|  | Achieved | 1)Met expectations. The National Social Protection Policy has been finalised yet to be submitted to Ministers for approval. 2)PSSN II design process reflects SP Policy developments including a new conditional cash transfer for disabled persons | Achieved. | Achieved. | Achieved. | Achieved
Source
Taskforce ToR, Taskforce meeting minutes, NSPF document, coordination/dialogue mechanism meeting minutes,
| Output Indicator 3.2 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
| Impact evaluation conducted and findings used to inform policy | Planned | Evaluation end-lin data collected | Impact evaluation final report | Impact evaluation final report | Impact evaluation final report | PSSN II impact evaluation final report
|  | Achieved | Not met.The end-line survey data collection has been postponed.TASAF will finance the end line impact evaluation within the PSSN II programme as part of their baseline assessment. | Not Achieved The Midline Impact Evaluation Report was produced and disseminated, but the Final Evaluation Report was paused. | Not Achieved The Midline Impact Evaluation Report was produced one year behind schedule and disseminated but the End line Evaluation was merged with the baseline for the PSSN II programme. | Not Achieved The Midline Impact Evaluation Report was produced one year behind schedule and disseminated but the End line Evaluation was merged with the baseline for the PSSN II programme. | Partially achieved. The impact evaluation report data is being processed, and the preliminary report is expected before the end of 2025 with the final report to be completed in early 2026.
Source
Impact evaluation baseline, mid-term and final reports, policy briefing, meeting minutes
IMPACT WEIGHTING | Output Indicator 3.3 |  | Baseline (September 2019) | Milestone 1 (September 2020) | MIlestone 2 (September 2021) | MIlestone 4 PCR (September 2023) | MIlestone 1 (New Bussness Case) (September 2025)
20% | Effective communications and accountability systems to PSSN beneficiaries are in place and operational | Planned | Review and revision of effective communications and grievance mechanisms for PSSN II which are aligned with PSSN objectives and revisions to payment mechanisms | Effective roll-out and implementation of new communications and grievance mechanisms in PSSN II. | Effective roll-out and implementation of new communications and grievance mechanisms in PSSN II. | Effective roll-out and implementation of new communications and grievance mechanisms in PSSN II. | 80% of Complaints and grievances addressed within 1-2 months of initial complaint being recorded (80 percentage).
|  | Achieved | Partially met expectations. Communication plan is finalised but has not been rolled out. The GRM systems have been rolled out and aligned to the PSSN objectives. | Achieved. | Achieved 90% of grievances were resolved in a timely manner | Achieved 90% of grievances were resolved in a timely manner | Achieved Average 99%
Source
|  | TASAF annual reports and review missions | [5 empty] | Risk
INPUTS (£) | FCDO (£) |  |  | FCDO SHARE (%) |  |  |  | Medium
INPUTS (HR) | FCDO (FTEs)
0.3