Key Information for ZAMBIA POVERTY REDUCTION PROGRAMME
Directorate/ Post	East Central and Southern Africa - Lusaka	SRO Name and Contact Details	Nicola Oldham / Nicola.Oldham@fcdo.gov.uk
Total Budget	£38,500,000	Start and end dates	01/11/2025 - 31/03/2031
Overall Risk Rating	Moderate	AMP Number (if applicable)	400138

Detailed information
Programme summary, outcomes and outputs, and non programme dependencies	Reducing poverty and building human capital to drive inclusive growth are crucial to achieving the UK’s growth and development goals in Zambia. The Zambia Poverty Reduction Programme (ZPRP) will contribute to delivering the UK Government’s international priorities on economic growth, climate and nature, security and development. Specifically, it will contribute to delivering three of the five development outcomes: growth, humanitarian systems and human capital, supporting Zambia to make sustained progress to self-reliance, build resilience and prevent and respond to shocks. / Through ZPRP, the UK will take an “investor, not donor” approach to provide systems-driven technical support to reduce multi-dimensional poverty, vulnerability and inequality in Zambia. Over the next six years ZPRP will contribute to achieving two outcomes: / Sustainable, effective locally-led shock responsive systems to better protect the poorest and enhance resilience of the most vulnerable people in Zambia; / Expanded human capital development opportunities to unlock inclusive growth for the poorest and most marginalised households in Zambia, and build sustainable pathways out of poverty. / ZPRP will deliver on the commitments made in the ‘Poverty Reduction Pledge’ signed by the Minister for Development and the Zambian Government in December 2024. This bilateral compact reflects the FCDO’s approach to knowledge exchange and builds upon the commitments made in the Brazil-led Global Alliance against Hunger and Poverty (GAHP). ZPRP will seek to understand where there are opportunities for change in Zambia and how the UK can convene, coalesce and strengthen coalitions to support pro-poor policy and system strengthening. FCDO will leverage the British High Commission’s diplomatic convening power and access to achieve impact and the timing is opportune to contribute to the priorities outlined in the Ninth National Development Plan. / FCDO has identified the opportunities to tackle poverty in Zambia and ZPRP will take an evidence-based approach and build on decades of learning and a deep, trusted relationship with the Zambian government, and our ability to deliver impact here, to achieve the following outputs: / Strengthened, comprehensive and fiscally viable Government of Zambia (GRZ) social protection system / Strengthened shock response and recovery systems / Stronger voices for change in favour of pro-poor public policy / Improved economic opportunities for the poorest to unlock human potential and support sustained escapes from poverty / Strengthened systems to improve the quality of human development services (e.g. education, health, nutrition, and sexual and reproductive health) for the poorest. / This programme learns from the pivotal and innovative role that the UK has played in supporting the development of Zambia’s Social Cash Transfer (SCT) system over the past two decades. The SCT system has grown from a UK-funded pilot to a government owned nationwide system, largely financed by GRZ and on track to be 100% government financed by 2028. ZPRP seizes the opportunity to enhance resilience and future proof Zambia’s SCT system as part of a wider approach to strengthen locally led-humanitarian systems. Learning from previous programmes, ZPRP will enable the UK to be an ‘engaged reformer’ to leverage multilateral investments. The programme adopts the proven “investor, not donor,” approach utilising UK technical expertise and political analysis to strengthen systems to build human capital, enable self-sufficiency, enhance resilience and innovate to support inclusive growth and sustainable pathways out of poverty.
Portfolio Fit	The UK’s win-win partnership with Zambia supports a prosperous and stable future for Zambia’s people based on inclusive and sustainable growth and resilience to poverty and shocks, while creating opportunity for UK companies in key growth sectors including critical minerals and renewable energy, contributing to delivery against key UK priorities across climate, growth and development. / FCDO’s 2025/2026 Country Business Plan for Zambia is centred on delivering four goals: / Core service delivery / Climate and Nature / Development – reduce extreme poverty / Growth / ZPRP will be one of the main instruments to deliver the goal on Development. In line with BHC Lusaka’s development strategy, we will alleviate the impacts of severe poverty by supporting Zambia to reform its social service systems, improve its health security and enhance resilience to shocks, underpinned by country led partnerships and strong democratic institutions and values. ZPRP will also contribute over the long term to the growth agenda in Zambia, as well as strengthening resilience to climate shocks. ZPRP will draw upon the high-quality political analysis, influencing, communications and soft power skills in the core service delivery goal. / The programme incorporates FCDO’s work to support Zambia’s National Development Plan and policies where they align with UK priorities. These include: / Inclusive growth: reduced inequality and jobs which unlock human potential / Humanitarian systems: anticipatory action to reduce humanitarian need, enhanced preparedness and resilience to shocks, local partnerships and stronger crisis architecture / Human capital: harnessing health and education opportunities, system strengthening and empowerment of women and girls / The programme has been designed in a way that enables it to maintain the flexibility to scale up or scale down funding to elements of the programme as required, and trade-offs will be considered.
Geography	This programme will benefit Zambia. The Head of Mission/ Development Director approved ZPRP operating in Zambia on 16th September 2025.
Budget	This programme will cost £38,500,000 over six financial years (2025/26- 2030/31). No funding has been spent on design. The ZPRP budget will largely be classified as Resource Departmental Expenditure Limit (RDEL). FCDO will allocate up to a third of its annual ODA RDEL budget in Zambia to ZPRP over the programme lifetime. ZPRP will include humanitarian RDEL.
Timing	ZPRP will begin spending in FY2025/26. The expected budget for FY25/26 is £2.1m which includes contribution to multilateral funds and programme funded roles. Expenditure will ramp up in 2026/27 and will include establishing a partnership with a research institution and some ‘quick start’ activities. The commercial contract will be launched in 2026/27, and expenditure through this component will be low during the inception phase. / From 2026/27 – 2029/30 we expect the spend per year to be between £8m - £10m, then will taper off in the last two years. Expenditure for 2026/27 – 2029/30 is based on indicative ODA allocations. FCDO will confirm partners’ budgets annually to ensure the programme remains affordable within the delegated ODA budget. Break clauses and scale down provisions will be included in all contracts to enable flexibility to respond to budget changes. Accountable Grants and MoUs do not legally commit the UK to providing funds.
Delivery modality	ZPRP will be delivered through 3 components: / A commercial contract (procured either through the FCDO’s Global Development Delivery Framework or through an open tender). / Direct partnerships managed by FCDO enabling FCDO to hold direct accountable grants, MoUs or low value contracts with strategic partners / Multilateral partnerships through multi-donor funds which are effective in system strengthening and where FCDO is an engaged reformer, specifically the World Bank Girls Education and Women’s Empowerment and Livelihoods project (GEWEL) and UNICEF-led United Nations Joint Programme on Social Protection (UNJPSP).
Strategic rationale and evidence base	ZPRP takes a ‘beyond-aid’ approach through exchange of knowledge and expertise, grounded in genuine respect and partnership, working to strengthen systems and build locally led coalitions to drive forward Zambia’s development priorities. It will deliver against three of the UK’s development priorities: / supporting sustainable and inclusive growth in markets of the future; / lifting vulnerable people out of crisis and building state and community resilience to shocks; and / building human capital to drive growth. / Zambia’s economic growth is profoundly exclusive. Zambia’s political settlement- the way power is distributed across social groups in the country - has resulted in a governance system that benefits a subset of society to the detriment of the majority, and exacerbates rather than alleviates poverty. Mining has created an economy where there is almost no relationship between economic growth and poverty reduction. Poverty, particularly in rural areas, is acute and rising, and Zambia is forecast to become the third poorest country in Africa by 2060. Women and girls are often marginalised in development processes: underserved by services and on the sidelines in decision-making and economic growth. The Human Capital Index shows that a child born in Zambia will be 40% as productive as they could be with complete education and full health. / A multi-pronged and politically informed approach is necessary to reduce poverty in Zambia. ZPRP will strengthen sustainable, effective shock responsive systems that better protect the poorest and enhance resilience of the most vulnerable people in Zambia, making progress towards self-reliance. It will expand human capital development opportunities, including investing in education to unlock inclusive growth for women and girls in poor and vulnerable households, contributing to a stronger UK-Zambia economic partnership. Finally, ZPRP will work with Zambian actors to increase public, media, and political support for pro-poor policies in Zambia, to embed domestic voice and support coalitions for poverty reduction.
International Climate Finance (ICF)	ZPRP is expected to include a large proportion of eligible activities. Exact proportions of ICF-eligibility will be determined during inception (and monitored as the programme evolves). ZPRP’s ICF contribution will be included in the logframe. ICF KPIs that are likely to be included are detailed in the financial case.
Clearance chain confirming scrutiny of programme and review comments
Submission Date	24 September 2025
All programmes / Confirm here that approval timelines were met (2 weeks for Board & 1 week for HoM/Director)	The UK’s Zambia Country Board approved the Business Case in March 2025 which and subsequently adapted and agreed to reflect ODA allocations and clarity on multi-year ODA allocations. The Board agreed that ZPRP will make important contributions in human capital development and resilience building – essential to inclusive growth in Zambia and aligning with the UK’s growth objectives in Zambia. / Endorsed by Development Director - Simon ten Brinke-Jackson
	This programme will form the foundation of our work on poverty reduction and building sustainable pathways out of poverty. It will work hand in glove with delivery of the UK’s climate and nature objective and underpins delivery of our growth and energy transition objectives – both covered by other programmes in the portfolio. ZPRP takes an evidence-based and politically informed approach to building resilience to shocks and expanding human capital development opportunities to unlock inclusive growth. I am therefore happy to approve this programme. / Head of Mission, Rebecca Terzeon
Programmes between £20m and £40m	Director/ Director General

Strategic Case

Overview Country Context

Zambia's economic growth has been profoundly exclusive, with GDP per capita rising from ~$400 in 2000 to $1,454 in 2022, yet 64% of the population still lives in extreme poverty. Persistent poverty is driven by weak, exclusive economic growth, low human development, and high exposure to shocks. The benefits of growth have not been evenly distributed, particularly affecting remote areas and the poorest segments of society. The governance system favours the urban elite, exacerbating poverty and inequality. Mining has not translated into poverty reduction, and regional disparities remain significant. Women and girls are often marginalized, lacking access to essential services and decision-making roles. It is in the UK’s long-term interest that Zambia thrives, becoming more equal and less poor and creating the markets of the future.

Figure 1: Rising GDP per Capita and Poverty Rate

Despite rising GDP per capita, Zambia has one of the highest poverty rates in Africa and poverty is worsening, becoming deeper and more widespread. The proportion of people living in extreme poverty increased from 54.5% in 2002 to 64% in 2022. This is higher than the average across SSA (~37%) and all low-income countries (45%). Zambia is in the 15 poorest countries in the world.[1] Human development outcomes are on par with Africa’s conflict affected states, despite longstanding stability and GDP per capita close to lower middle-income.[2] Numbers of extreme poor have more than doubled from 1990, from 4.5m to 12.9m in 2022. Poverty incidence is more than twice as high in rural areas (80%) as urban (32%), driven by an urban-rural divide as well as spatial divides in prosperity between Lusaka and the Copperbelt, and the rest of the country. The World Data Lab projects that without tangible and transformative policy reform, Zambia is on track to have the 9th highest number of extreme poor by 2030, with other models suggesting Zambia could have the 3rd highest number of poor in Africa by 2060.[3]
[1] Highlights-of-the-2022-Poverty-Assessment-in-Zambia-2023.pdf (zamstats.gov.zm)
[2] Highlights-of-the-2022-Poverty-Assessment-in-Zambia-2023.pdf (zamstats.gov.zm)
[3] Chronic Poverty Research Centre – Zambia Poverty to 2060 Paper

Table 1: Regional Poverty Comparisons
	Poverty Headcount ($2.15)	GINI	Multidimensional poverty headcount ratio (% pop)	Stunting (<5)	Income / (GNI per capita, Atlas method)
Ghana	25.2%	43.5	32.8	17.5%	$2,380
Malawi	70.1%	38.5	78.3	35.5%	$640
Mozambique	74.5%	50.5	73.7	37.5%	$440
Tanzania	45%	40.5	54.6	35%	$1,200
Uganda	42.1%	42.7	52.2	25.4%	$930
Zambia	64.4%	51.5	65.8	34.6%	$1,240

What is driving persistent high poverty rates in Zambia?

Geographical

Zambia faces significant geographical challenges due to its landlocked status, being over 1,500 km from the nearest major seaport. This increases transportation costs for imports and exports, making goods more expensive and less competitive on the global market. There is also a considerable in-country geographic variation in poverty levels, with poverty in Muchinga, Western, Northern, Luapula and Eastern provinces higher than 70% based on the national poverty line. Zambia is huge country with a sparse population outside of main population centres; this creates specific development challenges. Zambia is 3 times the size of the UK, with less than a third of the population.

Figure 2: Incidence of Poverty by Province (2015-2022)

Source: Living Conditions Monitoring Survey Report 2022

Economic

Despite recent increases in social expenditure consistent with IMF benchmarks, overall Zambia has struggled to harness the potential benefits of a mineral-based economy and to invest domestic resource revenue sufficiently in essential services. Heavy reliance on copper means that when copper prices fall, the economy suffers, leading to job losses and reduced government revenue in social programmes. Mining growth has not translated into significant improvements for the bottom 40%[4], as the sector is capital-intensive and does not create many jobs. Mining revenues (accrued mainly in urban provinces) have created a powerful ruling elite who have disproportionate influence in policy-making and exacerbates the urban-rural inequality.
[4] The bottom 40% refers to the average annual growth rate in income or consumption of the bottom 40 percent of the population in a country. The growth in real per capita income of the bottom 40 percent of the income distribution is an important indicator of inclusion that is correlated with reductions in poverty and inequality Growth of the Bottom 40: Monitoring Inclusive Growth

Stagnation in the agricultural sector is driven by distortive public policies, exacerbated by climate change. Limited diversification restricts growth and job creation, with returns from smallholder agriculture and informal economies are insufficient to escape poverty. Agricultural productivity levels are strikingly low, and declining – out of step with regional and global trends. Labour productivity in agriculture has fallen by almost 50% in the last 20 years. Inefficient and distortive public policies for the sector, increasing climate hazards and resource degradation, and limited diversification are hampering the sector’s growth. The evolution in food supply is not keeping up with the nutrition needs of the country’s expanding population and changing consumption patterns. The average farmer who solely produces maize, even when supported by Farmer Input Support Programme (FISP) and Food Reserve Agency (FRA), earns below the poverty threshold of $2.15/day. 55% of women earn their livelihoods in the agriculture sector (compared to 45% of men), therefore improving farm income – for women and men - is crucial for more inclusive growth. Overall, access to economic services including agricultural extension, financial services and business development for the poorest remains limited and hinders economic growth.

Women face significant barriers to economic participation, presenting untapped potential for more inclusive growth. Women comprise a large percentage of the workforce in the agricultural sector, but do not have access and control over land and productive resources which is required to effectively and efficiently engage in farming.[5] The limited financial services available favour men over women, with it much harder for women to access credit. Female labour force participation remains low. In 2020, male labour force participation was 43.7 %, compared to 27.2% among women.[6] In 2020/2021, the COVID-19 pandemic significantly worsened the situation, widening gender gaps in employment. The absence of adequate care arrangements causes high levels of time poverty for women and girls, further inhibiting their economic opportunities.
[5] World Bank. 2019. Zambia Enterprise Survey.
[6] 2020 Labour Force Survey, https://www.mlss.gov.zm/wp-content/uploads/2022/03/2020-Labour-Force-Survey.pdf

Limited rural-urban migration. Rural-urban migration is an important pathway out of poverty, but high inequalities mean that cities are not inclusive of migrants, and drought-related power outages, cholera outbreaks and inflation have taken their toll on vulnerable people in cities. Poor land management, lack of urban planning and formal housing has led to increased unplanned settlements and slums that have become breeding grounds for disease outbreaks and unacceptable and unattractive living conditions. In the early 2000s urban areas saw a fall in poverty, however more recently urban labour markets have become increasingly saturated, driving down wages in the informal sector. COVID-19 and other shocks have increased urban poverty, and there is evidence that this increase is structural as labour markets fail to produce enough urban jobs.

Zambia became the first major country to complete a debt restructuring through the G20 Common Framework and has performed well under an IMF Extended Credit Facility, demonstrating its commitment to fiscal discipline. However, its inherited debt crisis limits its ambitions on economic and social reform. Zambia’s significant debt challenges have limited government spending on essential services like health, education and infrastructure development. The United Party for National Development (UPND) Government has been successful in brokering a deal to restructure $14bn of its external debt; part of a broader, ambitious programme of economic reform that has the potential to transform Zambia’s long-term development trajectory. Although the pace of the reforms has been slowed by successive crises (cholera, drought and an energy crisis), this remains a once-in-a-decade opportunity to make progress on key reforms. The pressure to manage debt and meet fiscal obligations will limit discretionary spending, reducing the ability of political elites to distribute state resources to maintain loyalty and control.

Political

Zambia has a stable democracy, and one of the most competitive political systems in Africa, yet competitive politics has led to an urban bias in Government spending. The frequent changes of ruling party through the ballot has been a source of renewal, but has simultaneously made politics short-term, focused on pleasing urban swing voters. Government spending is some of the least progressive in Africa. The poorest pay more into the tax system than they get back, and rural services are consistently neglected. Large subsidies on fuel, agriculture and electricity worth around 5.4% of GDP have primarily benefitted the top 10%. This is exemplified by the orientation of fiscal policy towards subsidies; until their recent removal, the richest 10% of households captured nearly 90% of the total fuel subsidies and over 50% of the total electricity subsidies. Influential groups who benefit from such policies ensure they are held in place in exchange for their political support, maintaining the status quo. Under the Government’s IMF backed reform programme, subsidies are being removed, whilst growing social spending.

Zambia’s public sector remains politicised, and capacity is generally low, hampering better delivery of public goods and services. Historically, politicians have rewarded their supporters by appointing them to government positions and awarding contracts to allies and cronies by flouting tender procedures. This undermines the separation of power and the independence of public officials. The overlap of public positions and private business interests entrenches corruption, particularly in public procurement, as individuals seek to maintain their power and control over resources. As a result, attempts to reform the public sector and government policy are met by strong resistance (and are therefore politically difficult). The public sector is also critically underfinanced, has a shortage of specialised skills and there is high staff turnover, limiting its effectiveness and ability to implement policies on the Government’s behalf. Rather than trying to deliver its ambitions through the public sector, politicians attempt quick fix approaches that eschew more complex administrative reforms in favour of time bound results. Although this has spearheaded more focused policy and implementation around key priorities (for instance the expansion of the Social Cash Transfer Programme in response to the drought), in general, prioritisation of spending to areas of highest impact remains a challenge. The status quo suits political leaders because it allows them to maintain control over public sector resources and deliver (populist) policies that secure votes.

Impressive steps have been taken to decentralize power and resources in Zambia, yet significant challenges remain. Zambia has one of the most centralised governments in the region. Despite some commitment to devolution, past initiatives have failed due to implementation failures, low institutional capacities, and weak political incentives. The government’s new Decentralization Implementation Plan for 2022-2026 aims to empower Local Authorities with resources and capacity building, building on frameworks like the Constituency Development Fund (CDF). The 2023 Decentralization Policy seeks to enhance local service delivery, revenue mobilization, and citizen participation. However, decentralization remains a political process requiring the central government to cede authority and resources. Historical centralization and control over resources pose challenges, and the CDF's effectiveness is hindered by central approvals and administrative weaknesses. Successful decentralization requires improved coordination and devolved decision-making across all government levels.

There have been efforts to increase local financing in a devolved governance system through the Local Government Equalisation Fund, the Constituency Development Fund (CDF) and sector grants for devolved functions which include health, education, nutrition, social welfare and community development. The devolution of functions to Local Authorities is intended to improve the efficiency and effectiveness of local service delivery as part of a broader state-led poverty reduction and economic development strategy. However, operational challenges remain significant with the local service delivery as devolved government Ministries continue to operate in silos and their respective implementation local structures still operate independently without any form of integration. The challenge of providing government services to scattered and diverse communities has led to uncoordinated local level community structures, fragmented volunteer efforts and intra-governmental silos. As a result, there is an urgent need for a more integrated approach using fewer, multi-purpose community structures to better meet community and households' diverse needs.

Human Capital

Although significant changes in social spending have taken place since 2022, including the education budget increasing (from 10.4% of the budget in 2022 to 15.4% in 2024), there is a critical need for improvements in Zambia’s human capital. A child born in Zambia today will be only 40% as productive when they grow up as they could be if they enjoyed complete education and full health. This is lower than the average for Sub-Saharan Africa region and lower than the average for lower middle-income countries. This significantly limits Zambia’s economic potential.

Gender inequality negatively impacts human capital development in Zambia affecting various dimensions including health, education and economic participation, hindering economic development and poverty reduction. Zambia ranks 138 out of 170 countries on the Gender Inequality Index in 2021.[7] Women in lower income quintiles are more likely to be survivors of gender-based violence; 40.4% of women in the lowest wealth quintile experience violence, compared to 28.8% of women in the highest wealth quintile.[8]
[7] UNDP. 2023. Gender Social Norms Index. Breaking Down Gender Bias: Shifting Social Norms towards Gender Equality.
[8] World Bank 2023, Zambia Gender Assessment

Women and girls in Zambia continue to be disproportionately affected by worsening poverty and vulnerability, facing multiple depravations. GRZ’s 8th National Development Plan presents a mainstreamed approach to women and girls, this is also reflected in the National Social Protection Policy which identifies gender as one of the three cross-cutting issues. Despite flagship gender equality and women’s empowerment programmes, implementation is weak and underlying social norms undermine the ability of women and girls to achieve their full potential.

Despite the introduction of fee-free education, and the subsequent rise in school enrolment, poor learning outcomes limit young people’s opportunities. The GRZ’s ‘Education for All’ policy (2022) introduced fee-free education from ECE to secondary and has resulted in over 2 million children entering or re-entering school. The transition rates from primary to secondary have increased substantially (from 63% in 2020 to 84% in 2024) and, while the net enrolment rate remains low for secondary (49.9% in 2024, up from 37.6% in 2020) it is at 97.2% for primary.[9] Resources remain a challenge, however: there are not enough teachers, schools, classrooms or desks to meet demand. Despite this increase in access, there is a crisis of education quality. Learning poverty is exceptionally high: 99% of 10-year-olds in Zambia are not proficient in reading, this is 12 percentage points higher than the SSA average, and 38 percentage points higher than the LMIC average.[10] Data from 2021 shows that only 4% of Grade 2 students can read at grade level.[11] There is a lot of anecdotal evidence that students are reaching the start of secondary school (and even through to Grade 10) unable to read. Low educational attainment has a clear correlation with high levels of poverty as shown in 2022 LCMS data which found that households with less educated household members have the highest incidences of poverty.[12]
[9] Education Statistics Bulletin 2024, Ministry of Education
[10] World Bank, 2024, Zambia Learning Poverty Brief
[11] UNICEF, 2024, Language of Instruction (LOI) Research in Zambian Primary Schools.
[12] Zambia Statistics Office, Living Conditions and Monitoring Survey, 2022

Zambia has made progress on gender parity across the education system. The gender parity index shows that, in general, there are more girls than boys in school (index was 1.05 in primary, 1.09 in secondary in 2024). This is also true across all grades (ECE to Grade 12), and nearly all provinces. In addition, in school exams (at Grades 7, 9 and 12) more girls than boys are sitting exams, and the distribution of results is very similar across genders. Nonetheless, there remain gendered barriers to education in Zambia. Dropout rates in secondary are almost twice as high for girls compared to boys (1.3% vs. 0.7% in 2024). (Teenage pregnancy is a major contributing factor for girls: with 12,799 pregnancies in 2024, of which 56% were primary learners. Other barriers to education include long distances to schools, child marriages, and lack of menstrual hygiene facilities.

Zambia has one of the highest teenage pregnancy rates in the world. One in three (29%) girls becomes a mother by age 18 – in rural areas this jumps to 35% of girls. Adolescent pregnancy is one of the main contributing factors to school dropout, hindering the full potential and meaningful participation of women in national development. Overall fertility levels have been decreasing, with the average woman now having 4.2 children. However, adolescent fertility rates are stubbornly high. Fertility rates are five times higher amongst the poorest adolescent girls. An estimated 22% of women in Zambia want to prevent or delay pregnancy but are not using modern contraception, and rates of unmet need are even higher, at 25% among women aged 15-19. As result, Zambia’s population is one of the fastest growing in the world; with a population growth rate of 2.7% and the population is expected to double by 2050. The 2022 LCMS indicated that both in rural and urban areas, the large household size averaging 9 members, accounted for the largest proportions of the poor at 85.6 and 59.6 percent, respectively.[13] Sustained population growth, without commensurate planning and investment, can depress GDP per capita growth and reduce resources at national through to household level.
[13] Zambia Statistics Office, Living Conditions and Monitoring Survey, 2022

Zambia remains one of the most undernourished countries in the world. In the 2022 Global Hunger Index, Zambia ranks 108th out of the 121 countries. The main concern is the low nutrition status of the poorest children and mothers in Zambia for human capital accumulation, which has been exacerbated by climate-induced shocks that negatively affect food security and nutrition outcomes. Undernutrition is a key underlying cause of 45% child deaths and 20% maternal deaths in Zambia. It leaves young children vulnerable to infection and disease and stunting impedes physical growth and cognitive development. As a result, malnutrition hinders school achievement, work productivity and earning potential, impacting on human capital and contributing to an estimated 10% loss on annual GDP growth. Overall, 48% of the population is unable to meet their minimum calorie requirements.5 The 2018 Zambia Demographic and Health Survey (DHS) revealed that average stunting rate among children below five years of age stood at 35 percent, worsening to 40 percent for the lowest wealth quintile, and minimum dietary diversity among all children ages 6-23 months stood at 23% nationally, worsening to 11% for the poorest.[14] One of the challenges for the nutrition sector is that although the strategic responsibility for nutrition sits with the National Food and Nutrition Commission (NFNC) under the Office of the Vice President, given the multi-sectoral nature of nutrition, much of the delivery on nutrition outcomes is through other ministries such as the Ministry of Health and the Ministry of Agriculture, resulting in coordination and ownership challenges.
[14] Government of the Republic of Zambia, Zambia Demographic and Health Survey (ZDHS), 2018

HIV/AIDS and malaria impact productivity, and despite improvements over the last decade, maternal mortality rates remain relatively high. Progress on total fertility rates and neonatal mortality are slower than expected and there are indications that teenage pregnancy rates have risen in the context of recent shocks such as Covid and drought. Zambia’s health system has made reasonable progress in extending health coverage with its service coverage score improving from 28 in 2000 to 56 in 2021, just below the mean for lower-middle income countries.[15] However health service delivery remains highly inequitable (skewed towards urban populations), and women and girls continue to bear a high disease burden, as seen in HIV prevalence which is higher among women than men (14.2% versus 7.5%).[16] Child marriage and teenage pregnancies are key contributors to the high levels of maternal mortality and generational multi-dimensional poverty and stunting. Likewise, childbearing at a very young age is associated with an increased risk of complications during pregnancy, and with higher rates of neonatal mortality.
[15] WHO Health Financing Matrix Assessment for Zambia June 2024
[16] Zambia Demographic Household Survey, 2018.

Access to essential services for the poor remains limited. Connecting communities to essential services such as health, nutrition, family planning and education is a major challenge in countries like Zambia where populations are scattered, access is difficult, and needs vary across the country. Meeting this challenge is however vital to combat poverty and harness the capacity of all people in the country. A range of important initiatives are underway in Zambia that aim to develop effective models of social and economic outreach that rely on community volunteers to extend the reach of district and programme administration right down to the community and household level.

Climate Change and Shocks

Climate change is significantly worsening Zambia's vulnerabilities, both causing and exacerbating poverty. According to the Notre Dame Global Adaptation Initiative, Zambia has the highest vulnerability and lowest resilience to climate change globally. The severe drought in the 2023-24 farming season, the worst in 40 years, led to over 70% crop loss, affecting over 10 million people, with at least 6 million needing food aid. This drought has highlighted the lack of household resilience, increasing the risk of food insecurity and malnutrition. Structural issues like weak land governance and reliance on subsistence agriculture further exacerbate Zambia's vulnerabilities. With 75% of the population dependent on rainfed agriculture and 94% of land under customary tenure, there is little incentive for long-term land investments. Addressing climate change impacts requires comprehensive, inclusive policies and interventions. However, Zambia's political dynamics hinder necessary reforms, leaving those most affected with the least power to demand climate action.

Rural populations, poorer people and women are hit harder by climate change because their survival depends on activities which are the most affected by climate change (notably agriculture, forestry and fishing) and because they lack the assets needed to absorb climate shocks. Over the past decade, climate change and a rapidly increasing population have exacerbated pressures on Zambia’s land, forest and water resources. These pressures have had direct impacts on soil fertility, fish stocks, agricultural and fishing livelihoods, and hydroelectric power generation.[17] Temperatures in Zambia are rising faster than the global average. Increasing climatic variability continues to drive cycles of floods and drought, reducing incomes and whittling down resilience.
[17] Chronic Poverty Advisory Network (CPAN), Rural Pathways Out of Poverty

More frequent and severe disease outbreaks are impeding progress. Climate change, combined with long term underinvested WASH infrastructure has resulted in almost annual severe cholera crises, the last of which affected all provinces including the capital. Recent measles, anthrax and Mpox outbreaks mean that public health systems are continuously responding and reacting to an emergency with little time and resources to build systems to improve health status. With so many borders, Zambia remains vulnerable to regional outbreaks including viral haemorrhagic fevers, underlining the need for a one health approach.

The growing impacts of these intersecting crises (climate, debt, pandemic) and stressors (ill health, eroding soil fertility, declining fish stocks) have made escaping and staying out of poverty extremely challenging.

Policy Context: Progress To Date Towards Addressing Zambia’s Complex Poverty Challenge

Significant changes in social spending have taken place since 2022, suggesting greater pro-poor spending and improved systems building. This is evident in the social protection sector, which, with UK support has expanded and matured over the last two decades. More recently, the widespread drought in 202/2025 catalysed improvements in shock response and locally led humanitarian systems, building on existing social protection systems. Other major developments include the removal of general fees in 2022 through the ‘Education for All’ policy and in 2025 guidance was issued on the integration of Food and Nutrition planning in national budgeting to strengthen the government’s multi-sectoral approach to tackling malnutrition. Given the significant role of social protection in tackling poverty, this section provides a deep dive on the progress made in building the social protection system to date.

1. Service delivery to systems building: In the last 20 years, the Zambian government with its cooperating partners such as the UK and the World Bank, has invested in the use of social protection as a mechanism for poverty reduction. This is a sector that the UK played a significant role in initiating in Zambia, working with GRZ to take it from a small service delivery pilot to systems building which has resulted in a fully owned and led, nationwide programme supporting GRZ to deliver its own services. The Girls’ Education and Women’s Empowerment and Livelihoods (GEWEL) project is a flagship social protection project of the Zambian government. GEWEL became effective in April 2016 and is a “cash plus” project, whereby productive inclusion and women and girls’ empowerment components are layered over a social safety net to build human capital, and provide pathways out of poverty. The GEWEL project comprises complementary activities which are layered on a foundational social assistance programme for enhanced welfare impacts to support pathways out of poverty. These include:
  1. foundational Social Cash Transfers (SCTs) to the poorest and most vulnerable households;
  2. an economic inclusion programme for ultra-poor rural women through the Supporting Women’s Livelihoods (SWL) activity;
  3. an education initiative for vulnerable and poor girls through the Keeping Girls in School (KGS) intervention. GEWEL supports

SCTs: By 2024, the Social Cash Transfer (SCT) programme had expanded to over 1.3 million households nationwide, surpassing the target of 1.026 million. This coverage represents about 30% of the population and 50% of the poor, making it one of the most effective safety nets in the region with strong pro-poor elements. According to the World Bank, the expansion of the caseload and increase in transfer value are estimated to have reduced poverty by 6 percentage points, primarily by enhancing household resilience through predictable and reliable cash assistance to cope with climate and other shocks.

Shock responsive social protection: The SCT has been effectively used to respond to various shocks, including COVID-19 in 2020, droughts in 2022 and 2024. The 2024/2025 drought catalysed the development of a shock responsive social protection system which saw the government increase the value of cash transfer to provide an Emergency Cash Transfer (ECT) and temporarily expand the reach to provide ECTs to one million more households.

KGS: The KGS programme successfully enrolled 148,616 girls in secondary schools across 65 districts, surpassing the end-project target by 86%. It has also made significant progress in tackling school-related gender-based violence (SRGBV), a major factor in adolescent girls dropping out. The programme introduced SRGBV Clubs in schools to create safe spaces for boys and girls to discuss gender norms and GBV issues, trained teachers and administrators on SRGBV, and engaged communities in gender-transformative dialogue to promote positive mindsets and behaviours. Additionally, the KGS piloted and expanded the Case Management System (CMS) to identify and support at-risk girls, helping to keep them in school and reintegrate those who had dropped out. The success of these initiatives has prompted the Government to allocate its own resources to expand these efforts to non-KGS schools as well.

SWL: The SWL programme has shown impressive results, especially as a potential model for graduation out of poverty. So far, it has supported 139,351 poor rural women in 81 districts with livelihood packages, and an additional 4,000 women are expected to be reached by the project's end, surpassing the target of 129,400 beneficiaries. Though limited in its coverage, a recent impact evaluation highlighted that SWL interventions have increased overall consumption by 38%, household income by 62%, business profits by 80%, and savings by 234%.

Investments in enhanced social protection (SP) systems have improved beneficiary management and introduced digital payments with a beneficiary choice model under the Zambia Integrated Social Protection Information System (ZISPIS). These investments have also led to more timely and responsive grievance redress mechanisms and strengthened the prevention, mitigation, and response to gender-based violence (GBV).

1. Government established National Health Insurance in 2018 under the NHI Act No.2 of 2018 as a Health Financing Mechanism to complement General Tax Revenue financing to the health sector and as a vehicle to achieving Universal Health Care to enable all individuals and communities to receive the health services, they need without suffering financial hardship. By 2024, 3.8 million people were registered on the scheme which is also extended to beneficiaries of SCTs. However, the financing of the social insurance scheme is under threat as government has no sustainable financing mechanisms to manage the scheme and only relies on 1% contribution of those in public service. We see four main opportunities for tackling poverty:
  1. Social Protection (including shock responsive social protection),
  2. Investing in Inclusive Growth for the bottom 40%,
  3. System Strengthening and Expertise in Essential Services and
  4. Supporting locally-led Drivers of Change.

OPPORTUNITY 1: SYSTEM STRENGTHENING IN SOCIAL PROTECTION

The Zambian government’s main tool to tackling poverty is a comprehensive social protection programme that utilises the ‘Floor’ and ‘Ladder’ approach. Zambia’s current framework - Integrated Framework of Basic Social Protection Programmes (IFBSPP) seeks to strengthen the ‘floor’ which supports the basic needs of persons and households in poverty, especially income supplementation through social cash and access to health care to provide relief from poverty and deprivation.[18],[19] This is complemented by the ‘ladder’ which promotes resilience and graduation by layering the provision of other support packages to promote sustainable income generation and increase resilience to future shocks and pathways out of poverty, for example through the enrolment in social insurance schemes and livelihoods initiatives.
[18] Zambia’s Integrated Framework of Basic Social Protection Programmes (IFBSPP) sets out the two pillars of the framework: the Social Assistance Pillar (the Floor) and the Livelihoods and Empowerment Pillar (the Ladder). The Social Assistance Pillar encompasses the Social Cash Transfer Programme, subsidised access to Zambia’s National Health Insurance Scheme, primary and secondary school fee waivers and the Home Grown School Meals feeding programme, as well as the Public Welfare Assistance Scheme. The Livelihoods and Empowerment Pillar consists of three complementary strategies contributing to the “graduation ladder”: targeted Tertiary bursaries, the Food Security Pack and the Integrated Empowerment Microfinance Scheme (IEMFS).
[19] This is in line with the ILO Recommendation 202 on Nationally Defined Social Protection Floors (of 2012).

Figure 3

The Floor

Cash transfers are recommended in multiple FCDO “Best Buys”, they are a good buy (strong evidence of cost effectiveness across many contexts in the Best Buy Improving Incomes of the Poorest; and a great buy (extraordinary potential to be highly cost effective in the Best Buy in Humanitarian Contexts.

Zambia has one of the most comprehensive SCT programmes in Africa, which the UK has been supporting since its inception in 2003. Having begun with just 169 households as a UK-funded pilot, the programme has become a flagship multi-donor programme primarily driven and funded by GRZ. The programme has a nationwide reach to over 1.3 million households, with an average household size of 4.8 people, it is estimated that in 2025 the programme reached over 6.2 million people across the country’s 116 districts, representing 30% of the population and 50% of the poor (75% of which are women and 13% households with persons with disabilities). GRZ has committed to increase the SCT caseload to 1.6 million households by 2026. Strengthening systems for the delivery of the SCTs have been part of the expansion agenda. This has built strong delivery channels for the cash transfers from national to sub-district levels focusing on robust management information systems and grievance redress mechanisms to enhance accountability and transparency. However, as outlined in the 2023 Zambia Social Protection Expansion Programme Phase II Annual Review, further strengthening is required to futureproof and modernise the systems, increase digitalisation, and ensure fiscal viability and sustainability. Continued learning will be necessary to support the SCT’s to adapt to the context as required.

Figure 4. Expansion of SCT Since 2017

The Government’s strong commitment to social protection is evidenced in its financial and political commitments to SCTs – a government owned and led programme. This commitment has attracted stakeholders to support, both World Bank financing, but also the IMF which has included social protection coverage in the conditions of the economic recovery facility. In 2023 the government financed 70% of the SCT budget, with the social protection sector representing one of the largest growing sectors in terms of resource allocation and accounts for a historical high of 7.5% of the total national budget in 2025. As shown in Figure 5, the programme has expanded its reach and increased the transfer value, and at the same time, the donor contribution has gradually reduced as a percentage of the total SCTs.

The UK has been an engaged reformer, supporting two key projects that strengthen the GRZ SCT system. The next phases of these projects are GEWEL, led by the World Bank and UNJPSP, led by UNICEF (box 1).

 Figure 5: Trend analysis of Government and Donor Budget to the Social Cash Transfer (in ZMW billion)[20]
[20] WB financing is included under donor counterpart budget. In most years, these were loans under the IDA portfolio of the WB and thus externally financed, but substantively government funded, bringing the percentage of government funding even higher.

GRZ’s response to the 2024 drought showed the fundamental value of the social protection system in smoothing negative shocks, protecting the most vulnerable from the effects, while pointing to areas requiring improvement in its shock-responsive capacity. The increase in poverty 2015-22 was partly due to the poorly managed 2019 droughts and related prolonged power outages alongside agricultural and economic slowdowns, COVID-19 pandemic and post-pandemic inflation, and associated failures of governance. This is why social safety nets to protect the poorest and most vulnerable against shocks are so vital. World Bank simulations estimate that the scale up in SCT programme coverage and increased transfer value in 2021, which government undertook with the support of the World Bank, reduced poverty in Zambia by over 6 percentage points.[21] The cash transfers form the base for layering on ‘accompanying measures’ focused on economic inclusion, human capital and climate adaptation, which are a key policy tool to help diversify livelihoods to increase resilience to climate shocks.[22]
[21] Zambia - Social Protection and Jobs Public Expenditure Review 2021 (English). Washington, D.C.: World Bank Group.
[22] Bodewig, Christian and Stéphane Hallegatte. July 2020. Building Back Better after COVID-19: How social protection can help countries prepare for the impacts of climate change. World Bank Blogs

Developing a dynamic social registry will help to strengthen the shock response actions by enabling real time and quick access to information on who needs support, what types of support, and where. GRZ is preparing to develop a social registry which would provide an integrated information system on beneficiaries and potential beneficiaries that can be used by multiple government agencies will aid shock responsive actions – the ‘floor’ during emergencies and facilitate cash plus initiatives. This management information system will enhance cross-sector coordination and improve timely delivery of services when required by those in need. The UK is supportive of this initiative as part of developing shock responsive systems considering the frequency and intensity of the recent disasters experienced in Zambia. Strong coordination between government ministries will be a critical enabling factor for the success of the social registry. For example, strengthening anticipatory action and coordination should enable strong integration of nutrition in shock response and active case-finding of malnutrition cases could be linked proactively to the onset of the annual lean season and/or shock response early warning systems. Similarly a range of social protection interventions could be provided in a coordinated way, for example the roll out of cash for work during the lean season could be a complementary mechanism targeting those able to work.

The Ladder

A social protection floor alone is not sufficient to support sustained escapes from poverty. Policies and programmes need to focus on sectors that directly impact the bottom 40%, such as nutrition, education, healthcare and savings. Linking cash transfers to other interventions can increase their effectiveness, enabling the poorest to participate more effectively in the economy. Building on the ‘floor’ by layering packages of support and linkages to services to increase income generation, diversification and improved access to essential services provides a ‘ladder’ out of poverty which can be described as a ‘cash plus approach’.

Cash plus programmes are social protection interventions that provide regular cash transfers in combination with additional components or linkages that seek to (i) augment any income effects from the cash transfer; and (ii) be more effective in achieving and sustaining the desired impacts than cash transfers alone.[23] Evidence shows that cash plus interventions that add combinations of targeted support can address a range of other outcomes such as nutrition, girls’ education, behaviour change, prevention of violence and empowerment as well as supporting sustained escapes from poverty.[24] The table below outlines the different implications for time, resources and capacity required to design and implement different cash plus models, which can vary in complexity and level of integration across external sectors. Overall, there is mounting evidence that cash plus is more effective than cash transfers alone across many outcomes, however data varies across sectors and contexts.
[23] Roelen, K., Devereux, S., Abdulai, A-G., Martorano, B., Palermo, T., & Ragno, L.P. (2017). How to Make ‘Cash Plus’ Work: Linking Cash Transfers to Services and Sectors, Innocenti Working Papers, no. 2017-10, Florence: UNICEF Office of Research - Innocenti. https://www.unicef-irc.org/publications/915-how-to-make-cash-plus-work-linking-cash-transfers-to-services-and-sectors.html
[24] Zambia Cash Plus Paper’, 2024. Internal evidence paper produced by the Chronic Poverty Advisory Network: Kate Pruce, Rachel Sabates-Wheeler and Roz Price, from the Institute of Development Studies, UK.

Table 2 Cash Plus Models

Source: McLean, 2020: 3, adapted from Sammon et al., 2019

Zambia’s approach to cash plus is nascent, and there is a huge opportunity to learn from existing programmes, innovate, test new initiatives, scale up successful interventions and integrate packages of support with essential services systems. Utilising the Global Alliance Against Hunger and Poverty’s Fast Track Initiative GRZ plans to enhance the human capital (nutrition and education) and productive capacity (livelihoods) and resilience of low-income households through integrated cash transfers and complementary services through its Cash-Plus Approach. The Cash Plus Approach was officially approved by GRZ in 2022 and the government is rolling out cash plus approaches to enhance the efficacy of social protection programmes and offer sustained escapes from poverty. GRZ’s cash plus strategy outlines how GRZ plans to lift individuals out of extreme poverty and set them on a pathway to resilient and sustainable livelihoods. Zambia’s current approach to cash plus has a strong focus on the needs of women and girls, it encompasses a range of focus areas which include:
  1. Adolescent girls, including school attendance
  2. Women’s empowerment and livelihoods
  3. Nutrition, especially during the first 1,000 days with a focus on pregnant and lactating mothers
  4. Health insurance pilot – including SCT beneficiaries in the national health insurance scheme
  5. Coordinated access to government services and integrated case management

To effectively scale and standardize these innovations, robust research and evidence are essential, along with the creation of a social registry that enables seamless integration of services like social protection, health, and education. Nutrition serves as a prime example where cash assistance, combined with nutrition behaviour change and enhanced connections to health services for pregnant women and malnourished children, can significantly improve the delivery of essential services, breaking down siloed and inefficient approaches.

Zambia has potential to be a trailblazer in the region, demonstrating how cash plus interventions can be harnessed and scaled alongside more coordinated and integrated essential services systems to support sustained escapes from poverty. In the face of rising frequency and severity of crises, ZPRP aims to support GRZ to demonstrate how countries facing climate shocks can adapt to better protect the poorest and most vulnerable people. This will support GRZ’s ambition to deliver “Socio-Economic Transformation for Improved Livelihoods” as well as delivering on the UK’s commitment to end extreme poverty through genuine partnership to support locally-owned priorities to achieve self-reliance, build resilience, tackle climate change, prevent and respond to shocks. This programme will deliver on the UK’s modern development approach through the following development outcomes:
  1. Outcome 1 - Growth: Growth and jobs which unlock human potential, clean energy and resilience;
  2. Outcome 3 - Humanitarian: Lift vulnerable people out of crisis and build state and community resilience to shocks through stronger, more locally-led humanitarian systems;
  3. Outcome 5 - Human Capital: Harness health and education opportunities and build human capital to drive growth.

Improving access to services requires greater coordination of essential services systems at local and central level. In the spirit of decentralisation, GRZ is rolling out the Single Window Initiative (SWI) through local councils, to address the coordination gaps in the social protection sector by providing single entry points to access services at a lower level of implementation. The SWI provides a “one-stop shop” approach for delivering social protection and social security programmes hosted in the decentralised government structures. The SWI facilitates better coordination between the local level (responsible for service delivery) and the central/national level (responsible for policy development, planning, monitoring and evaluation). Single Window access to essential services is regarded as a coordination mechanism to actualise the cash plus policy. With the devolution of health, social services, and community development functions, some Ministries are now operating under the supervision of the Local Authorities. This shift presents an opportunity to harmonize and integrate delivery systems. Building on the SWI, it is necessary to develop and test a model that aligns and integrates lower-level structures into local government frameworks, supporting a more effective decentralized service delivery approach to households. Evidence from this new approach should be utilized to influence changes in the policy and legal frameworks of local government.

It is important to situate the cash plus interventions within the context of government essential service delivery systems and decentralisation. The Government has made significant commitment towards decentralisation through a devolved governance system with emphasis on community inclusiveness, participation and engagement on service delivery. Under the reformed CDF, Zambia’s local authorities receive approximately £1.3 million to spend on local infrastructure, bursaries, skills training and economic empowerment initiatives for youth, women and persons with disabilities and significant power is devolved to local bodies to decide on how money is used. While this move from delegation to decentralisation remains tentative, the Government’s direction of travel represents a significant opportunity to change the way local development and services are delivered, and to deepen social accountability and democratic processes. Devolved functions are intended to bring services and decision-making processes closer to the people.

Graduation from poverty remains a challenge, but strong systems and linkages, as well as greater use of evidence to inform policy, are critical. The Zambian government is eager to test graduation pathways to sustainably move households out of poverty through enhanced and resilient livelihoods. The layering of services through cash plus is a key approach to enable inclusive growth of the bottom 40%, human capital development, recovery from shocks and access to the essential services that prevent people from falling back into poverty. GRZ’s vision is that cash transfers will provide the lifesaving ‘floor’, while cash plus services provide a ‘ladder’ out of poverty for sustainable graduation out of poverty. To maximise the value of the cash plus interventions, it will be crucial for GRZ to continue to strengthen access to effective, accountable and integrated essential services.

Box 1: Existing Programmes Strengthening GRZ’s Social Protection System

Existing Programmes Strengthening GRZ’s Social Protection System
Girls Empowerment and Women’s Economic Livelihoods (GEWEL): The World Bank GEWEL project is emerging as the centrepiece of government financing, donor coordination and implementation support on social protection, and this role is expected to embed in the second phase of GEWEL. As an IDA contributor, this means that approximately 6% of the IDA is funded by FCDO. The next phase of GEWEL will consist of $80 million for foundational SCT and nutrition cash top ups, $70 million for cash plus interventions and $7 million for institutional strengthening and systems building for “cash plus” delivery. The second phase will utilise the ‘cash plus’ agenda to promote human capital development through targeted cash plus initiatives, with the share of cash plus programmes making up a greater share of the budget as the cash plus agenda expands its reach. Cash plus interventions include:
- Keeping Girls in School (KGS) – $35m: complements the Government’s ‘Education for All’ policy aimed at tackling a decade of underinvestment in the sector by breaking down the cost barriers which prevent the poorest and most vulnerable girls from enrolling in and attending upper primary and secondary schools.
- Supporting Women’s Livelihoods for climate smart inclusion (SWL) - £35m: aimed at improving economic independence in adulthood, SWL works with the Ministry of Agriculture to provide grants, training and mentorship, and savings group formation to vulnerable women to transform household-based subsistence activities to more sustainable, productive and profitable enterprises. SWL interventions aim to directly contribute to climate adaptation for resilience of climate-induced shocks by beneficiary households and supports sustainable climate-smart pathways out of poverty.
- Nutrition cash top-up (included in amount for foundational SCTs): a nutrition cash top-up will complement the regular SCT payments to an estimated 25,000 eligible households, recognizing that buying nutritious food and accessing nutrition services incur additional costs that may be outside a household’s capacity. This is intended to strengthen a household’s climate adaptation capabilities for enhanced resilience, given the links between climate shocks, food insecurity, and availability of nutritious food.

UN Joint Programme on Social Protection – UNJPSP: UNJPSP phase 3 will leverage social protection for strategic objectives and contribute to human capital development, climate resilience and economic growth. It will deliver the programme through three pillars.
- Rights based, evidence-informed sustainable social protection system to provide the protective social protection floor, including in response to shocks, for example through diversification of income generating opportunities, as well as designing active labour market policies as a key tool for closing the poverty gap.
- Leveraging social protection for climate change adaptation and food security, to improve resilience and food security for social protection beneficiary households
- Enhancing the responsiveness of the social protection system to the needs of women and persons with disabilities so that they are better able to navigate their exit from poverty.

OPPORTUNITY 2: INVESTING IN INCLUSIVE GROWTH FOR THE BOTTOM 40%

Growth needs to become more inclusive to make a dent on poverty and inequality in Zambia.[25] Inclusive growth requires that poorer people, women and excluded groups are aware of and able to take up better work opportunities, requiring access to information to find genuine opportunities, ability to demonstrate their skills and capability to employers, and to physically travel to take up work easily and safely. Growth in the ‘Bottom 40’ measures the extent to which economic growth is inclusive by focusing on household consumption or income growth among the poorest population relative to the population as whole.
[25] World Bank, 2025, Poverty and Equity Assessment, Turning Things Around After a Lost Decade.

Improved economic opportunities for women and girls will unlock human potential to support sustained escapes from poverty. Emphasizing a gender focus is crucial, as female-headed households are more likely to be poor, have less access to services, and display significantly poorer labour market conditions. Research on poverty reduction in Zambia concludes that boosting the productivity of small-scale farmers – particularly women - and translating asset accumulation into productively used income generating activities are crucial to breaking the cycle of poverty.

Rural poverty has not declined in over 15 years amidst substantial underinvestment, inadequate policies, and recurrent exposure to weather shocks. Over the past decade, climate change and a rapidly increasing population have exacerbated pressures on Zambia’s land, forest and water resources. These pressures have had direct impacts on soil fertility, fish stocks, agricultural and fishing livelihoods, and hydroelectric power generation.[26] Both rural villages and urban areas have experienced increased unemployment, which in turn has negatively impacted livelihoods reliant on the demand for goods and services.
[26] Changes in rainfall patterns and water availability due to climate change have led to reduced water levels in rivers and reservoirs, impacting hydroelectric power output. This results in frequent power outages and increases in electricity costs, affecting both residential and commercial energy users ​ (SA-TIED Archive)​. SA-TIED-PB2020-3-climate-change-impacts.pdf. This particularly affects electricity dependent rural farm livelihoods, such as for timely irrigation, agricultural machinery, cold storage, agro processing, etc and non-farm rural livelihoods.

Roughly 40% of the rural non-poor receive most of their income from agriculture, yet they earn about three times more than the poor who also depend mainly on agriculture. Behind this contrast is better access to resources such as land, water, and capital. The non-poor can afford to invest in high-quality seeds, fertilizers, and irrigation systems, which significantly boost their agricultural productivity. They are more likely to engage in diversified agricultural practices, which provide multiple streams of income and are able to adopt new technologies such as mechanized farming equipment, mobile apps for market and weather information, and digital financial services. These technologies enhance productivity and efficiency.

Those in rural areas can still achieve a pathway out of poverty by climbing the agricultural ladder. The World Bank Poverty and Equity Assessment (2025) showed households that managed to transition into medium-scale farming (correlated with higher productivity and diversification) seem to be better-off than those who abandoned subsistence agriculture for non-farm options. Working for wages within the agricultural sector was seen as comparable to being engaged in non-farm businesses.​ This in part signals the limited availability of quality off-farm employment. Asset accumulation also plays an important role for rural pathways out of poverty, but will not result in poverty reduction unless the assets can be productively used in income generating activities. Rural areas close to urban areas such as those around Lusaka and the Copperbelt have benefited from more pro-poor asset accumulation, which led to higher consumption growth arguably due to better connectivity and access to markets.

There has been a strong reversal in the urban poverty trend since 2015. Although the prevalence of urban poverty is lower compared with rural poverty, urban poverty has risen to approximately 31.9% of the urban population living below the poverty line.[27] Urban areas exhibit high levels of inequality, with stark contrasts between affluent neighbourhoods and poorer township. Those living in the poorer townships often live in informal settlements with inadequate housing, working in informal sectors with low and unstable earnings. As a result, individuals previously at risk of poverty have fallen into poverty, while those in lower economic tiers have faced destitution and severe food insecurity during this period. These scenarios are worse for women as many rely on subsistence farming and informal labour, making them vulnerable to economic instability and climate change impacts.
[27] 2022 Living Conditions Monitoring Survey Report | United Nations Development Programme

Analysis by the UK based Chronic Poverty Advisory Network (CPAN) identified three important factors which inhibited mobility out of poverty over the last three years: the pandemic, fuel price rises, and new polices in 2021. COVID-19 meant that farmers faced challenges accessing inputs and markets, perishables spoilage and price volatility. Traders faced reduced activity, especially in border hubs, due to the fall in consumer spending and border closures. Fishermen struggled with declining fish stocks, market access and supply issues. Casual workers, especially migrant workers, lost work; and the hospitality (tourism) industry as well as domestic workers were hit by loss of employment. 2021 came with currency depreciation, rising fuel prices, and supply chain disruptions. In December 2021, fuel prices rose by 21% due to the removal of fuel subsidies. By March 2022, an additional increase of 20% occurred, driven by rising global oil prices and escalating general inflation across the country.[28] These hikes in fuel prices had a cascading effect on the economy as rising transport costs bumped up the prices of goods.
[28] In October 2023, fuel prices decreased by 2% following the introduction of an equalization mechanism. Navigating Zambia's Fuel Pump Prices in 2024 (2024) - ZambiaPrice. Early 2024 fuel prices have risen again with a reduction in fuel subsidies and reinstatement of value-added tax and excise duty. This has affected the costs of living and working and have intersected with the 2024 drought and rising food prices. The government’s reduction of fuel subsidies was aimed at reducing government spending aligned with conditions from the International Monetary Fund (IMF) to reduce the debt burden​ (Climate Home News)​​ (Amnesty International)​. The government also reinstated value-added tax (VAT) and excise duty on fuel to align prices more closely with market realities​ (Africa Energy)​. This policy shift has sparked significant public debate and concerns over rising living costs and general inflation and impact on the poorest. Conversely, the government argues that ending fuel subsidies is both fiscal responsibility and reallocating funds towards critical sectors like education and health​ (Zambia Monitor | Zambia Monitor)​.

CPAN’s research identifies several interventions to support upward mobility for the extreme poor.[29] These are: 1) psychological empowerment addressing deeply entrenched feelings of self-worth, 2) economic empowerment through training for example in income-generating assets or capital, and 3) social inclusion through forging relationships through cooperatives and village savings. Additionally, supporting the integration of livestock into smallholder farming systems through extension services, where feasible, further enhances resilience and income diversification. Livestock can provide additional sources of income, improve soil fertility through manure, and offer a buffer against crop failures, thereby contributing to overall household stability and prosperity. CPAN’s qualitative research also found that those who achieved sustained escapes from poverty often diversified their activities into non-farm livelihoods such as salaried wage employment and non-agricultural businesses.
[29] CPAN, 2024, Rural Pathways out of Poverty in Zambia

1. Qualitative research by CPAN found that diversification of livelihoods and inclusion in savings groups boosts resilience by allowing capital to move between various livelihood activities and help households withstand economic shocks. Zambia has a strong network of local and international actors delivering Village Savings and Loans Associations (VSLAs) within a range of development programmes and these have potential to offer a powerful accelerator out of poverty. Other groups such as cooperatives enable finance to be utilised in a productive way.
  1. Village Savings Groups: Membership allows women to save and receive pay-outs that can be invested in farm inputs and non-farm activities.
  2. Cooperatives: Participation in cooperatives provides access to subsidized fertiliser, joint marketing opportunities, and camaraderie among members.

Research also shows that incorporating a stronger focus on behaviour change, and community cohesion into VSLAs as well as better linking groups to access finance for livelihood diversification or insurance can multiply the benefits of VSLAs. Self Help Groups (SHG’s) a form of VSLA’s, are formal and informal groups of 10-25 people who come together to address their common problems or development challenges at household or community levels. Women kick start initiatives on their own to address their needs, enabling them to drive poverty alleviation in their communities.[30] These groups enhance the equality of the status of women as participants, decision-makers, and beneficiaries in the democratic, economic, social, and cultural spheres of life.[31] A study observed that SHGs play a pivotal role by mobilizing local resources, providing financial support to their members to improve their livelihoods, and fostering community cohesion. SHGs have been effective in improving access to credit and enhancing the entrepreneurial capabilities or their members. This offers opportunities for INGOs to invest in SHGs in Zambia. However, their impact is often constrained by limited access to larger financial networks and technical support.
[30] Self Help Groups — The Share Trust
[31] Munyenyembe .H; (2021), School of Business and Management, PhD, Texila American University-Zambia: The Effectiveness of Rural Investment of Self Help Groups (SHG) on the Economic and Social Wellbeing of Women: A Case Study of Katete District - Eastern Province.

OPPORTUNITY 3: SYSTEM STRENGTHENING AND EXPERTISE IN ESSENTIAL SERVICES

Essential services delivered through public systems in Zambia have seen improvements in recent years. Access to education in Zambia has increased hugely with the introduction, in 2022, of the Education For All (EFA) policy, providing fee-free schooling from early childhood to secondary levels. This has resulted in an additional 1.5m enrolling in school.[32] At the same time, there has been large teacher recruitment with at least an additional 40,000 teachers entering the in system[33] and increasing numbers of health workers. The unprecedented increase in the level of funds in the CDF has faced implementation challenges owing to the current weakness of decentralised administration in a traditionally centralised system. The political will and momentum towards decentralisation, driven by the commitment to leaving no one behind and bringing services closer to the people, presents a significant opportunity to identify and implement effective solutions for improved service delivery through decentralisation.
[32] Total enrolment increased from 5m in 2021 to 6.5m in 2024. Education Statistics Bulletin, 2024, MoE.
[33] Total number of teachers increased from 120,000 in 2021 to 159,000 in 2024. Education Statistics Bulletin, 2024, MoE. In addition, in March 2025, the MoE announced that it would recruit 4,200 and 2,400 replacement teachers.

Fundamentally, the growth mission for Zambia will not be achieved with the current lack of human capital. For example, investing in education, in particular foundational learning skills, is critical for any chance of broad-based, inclusive economic growth. Strengthened systems for essential public services are crucial to the country’s growth agenda.

Education

Improving the quality of education can have large-scale impact. The education system is well embedded across the entire country with existing structures at national, provincial, district and local levels. School enrolment is at a record high (6.5 million learners were enrolled from ECE to secondary in 2024) as a result of the Education for All policy. The schooling system reaches the hardest to reach areas and households. This provides an opportunity to enhance an essential service, that can have widespread positive impacts. There is strong evidence that delivering education which is high quality will have long-lasting sustained impacts.[34] In Zambia There is a gap in supporting foundational skills, most noticeably in the early years of primary school. There are over two million children in these grades, and there could be work to ensure that they are learning the essential building blocks of literacy and numeracy through evidence-based approaches (e.g., structured pedagogy). UK expertise can strengthen foundational learning, in particular by improving sector coordination and by helping GRZ allocate and spend their own funds more efficiently. The public education budget – approximately $1bn – far exceeds ODA to the education sector (around $50m - $90m). There is potential to deliver big wins with small amounts of money.
[34] For example, Crawfurd, Lee. 2025. The Economic Returns to Foundational Literacy and Numeracy: Evidence from Indonesia. Center for Global Development.

Currently there appears to be political will to improve education outcomes. As well as introducing free education, Zambia has – from 2025 – begun the roll-out of a new, progressive competence-based curriculum. In 2024 President Hichilema was announced as the Champion of Foundational Learning Champion in Africa by the Association for the Development of Education in Africa (ADEA).[35] Zambia was, in 2025, the first country in Africa to launch an “Ending Learning Poverty for all in Africa” campaign aimed at improving foundational learning.[36] The MoE champions the near-nationwide Catch Up programme (delivering TaRL interventions across Grade 3 – 5). The MoE has recently published national remedial learning guidelines – emphasising the aim of delivering basic foundational skills for all learners. And the 2025 Joint Sector Annual Review focussed on foundational learning, with an aide memoire developed setting out actions.
[35] Africa has a Champion for Foundational Learning | ADEA, PRESIDENT HICHILEMA, IS CHAMPION OF FOUNDATIONAL LEARNING IN AFRICA. – Ministry of Education
[36] Zambia launches the ‘End Learning Poverty for All in Africa’ campaign led by the Ministry of Education, the African Union and UNICEF

A Coordinated and Integrated Approach

Zambia’s scattered and diverse communities present a huge challenge in connecting people to the essential human development services they need. Key issues include uncoordinated community structures that are not linked to local government, missing vital connections between district offices and households; fragmented volunteer efforts where projects with strong volunteer networks are focussed on specific development aspects but not embedded in government systems; and limitations where sectoral or project-based systems fail to address the comprehensive and multi-sectoral needs of households. A more integrated approach, such as using a multi-purpose community structure through one entry point, would better meet the diverse needs of households. Other opportunities to strengthen services are outlined below.

Develop coherent community service delivery models: Create and test effective models that use community structures to bridge the gap between district/programme administration and households. The need to enhance the coherence and effectiveness of social and economic outreach is not unique to Zambia. Many countries face similar challenges with programme-level outreach leading to uncoordinated community groups and volunteers. This is a crucial time to evaluate the current model, explore alternatives, and chart a new course for Zambia. The Zambian government is committed to expanding access to essential services and implementing a 'cash plus' model to integrate services and support for needy households, accelerating their progress out of poverty.

Enhance System Efficiency: Enhancing the efficiency and effectiveness of the community outreach model is crucial for a broader state-led poverty reduction and economic development strategy. In Zambia, the most challenging aspect of public service delivery is reaching households in the most remote areas. Developing systems that operate at the community's lowest level may offer solutions to fundamental poverty challenges. Vulnerable households often have multiple needs related to education, health, social protection, nutrition, shock response and safeguarding. Therefore, an integrated case management system through a single-entry point can be a more effective approach to addressing multi-dimensional poverty and vulnerability.

Strengthen Linkages to Decentralisation: Ensure community volunteers, who have valuable insights into household and community needs, are formally linked to local governance structures. This will integrate their information into local planning and resource allocation processes. As it stands, Ward Development Committees are the only community structures well linked to decentralised structures and no formal linkages to lower structures below the Ward level exists despite a ward being too vast with the high number of households ranging from 1500-2500.

Policy/Legislative change: Enshrining evidence of what works in the policy and legal framework will be central to improving approaches to service delivery and presents a mechanism to commit the government to action. UK technical assistance and exchange of expertise has potential to provide thought leadership and peer to peer expertise to support improvements.

OPPORTUNITY 4: SUPPORTING LOCALLY LED DRIVERS OF CHANGE

Zambia's mining sector has led to an economy where economic growth does not translate to poverty reduction. Mining revenues, concentrated in Lusaka and the Copperbelt, have empowered a ruling elite with significant policy influence. In urban areas, higher education levels, better access to information, and proximity to decision-makers make people more politically active. Urban voters, who are more likely to switch party allegiance, benefit disproportionately from the political system. Consequently, politicians favour urban areas with policies and resource allocation to secure electoral success. To achieve systemic changes, Zambia will need to shift its stable status quo. The equilibrium sustains because vested interest groups make decisions which are most logical for that group to protect its interests.

Poor development outcomes are the result of poor systems or incentives. Analysing and responding to the political economy of different issues (using the twinned tools of development and diplomatic expertise) has enabled us to tackle entrenched barriers to reform. We need to be clear about the reasons the status quo persists and why it is a logical course of action for those who benefit from it. ZPRP will complement FCDO Zambia’s Effective States and Democracy programme which seeks to strengthen the democratic norms necessary for poverty reduction in Zambia.

To build alliances for pro-poor policies in Zambia, we need to ‘think and work politically.’ Development is a deeply political process, not a linear one. Our strategies for change need to be well thought out and politically sound. We will draw on the UK’s unique blend of political acumen, influence and strategic programming to apply appropriate political strategies and ZPRP will seek partners that have sophisticated political understanding on three levels:
- Causal Pathways: A deep understanding of how change happens in Zambia and the areas where reforms are possible.
- Interests and Mobilization: A thorough grasp of the interests around specific issues, both for and against, and a practical approach to mobilizing interest groups to support change, even if they disagree on other matters.
- Practical Skills: The ability to convene, coalesce, and animate reform coalitions.

Examples of approaches that could be taken to support Zambian drivers of change on pro-poor policies include:
  1. Strengthening locally-led coalitions on pro-poor policy: supporting civil society coalitions to build and maintain support for poverty reduction, creating champions of change to drive the poverty and equality agenda forward and raise the profile of poverty reduction.
  2. Parliamentary engagement on evidence for poverty reduction and human capital development: creating platforms for discussions and experiences of what works on poverty reduction and human capital development for members of parliament (MPs). Engaging and empowering MPs with critical arguments to enable them to participate in debates that inform policy change.
  3. Promoting policy dialogues on poverty reduction and pro-poor political commitments: constructive dialogues on poverty reduction to steer political interests and public engagement. Creating platforms for public scrutiny of political manifestos to ensure pro-poor policies are taken into consideration.
  4. Budget analysis and tracking: Pro-poor budgeting is a prerequisite for poverty reduction success, hence the need to show the financing landscape of poverty reduction interventions and hold policy makers accountable through tracking actual expenditure against budget.

Real change is rarely initiated by outside actors – domestic politics drive progress. In line with the UK Government’s focus on locally led partnerships, this programme will focus on asking the question ‘where is meaningful change happening in Zambia to strengthen pro-poor policies’ and ‘how can the UK support it’. In seeking out change opportunities, we will use deep political analysis to understand why a particular issue is ‘in play’ – that is, where the balance of power has potential to shift - and offer the best opportunities for impactful engagement. Based on comparative global evidence, we know that change happens when there is a sufficiently powerful set of interests supporting it. This is true across societies and has been true for the UK’s work on reform in Zambia. We will be selective about which changes we support and where we are not moving the needle, we will know when to fail fast. Where a change would happen without external engagement, the UK should not be involved.

What needs to be done

The social protection ‘floor’ has been effective in providing life-saving support to the poorest and most vulnerable, but it cannot deliver inclusive growth or offer a ‘ladder’ or sustainable pathways out of poverty. We identify that a combination of interventions will be required to achieve multi-dimensional poverty reduction, these are:

Strengthening a comprehensive and fiscally viable GRZ social protection system: Enhancing the existing social protection 'floor' to better support the poorest and most vulnerable in Zambia. This includes strengthening systems and adopting gender-transformative approaches to address the root causes of poverty, particularly for women and girls. Efforts should also target improving nutrition outcomes by addressing chronic malnutrition and stunting in the first 1000 days of life through integrated nutrition-sensitive social protection strategies. Additionally, securing fiscal sustainability will be crucial, where a strong partnership of donors and support from the World Bank and the UN can work with GRZ to ensure regular and emergency payments to respond to shocks, while maintaining GRZ’s ownership of and long-term commitment to its social protection system amidst national economic reforms.

Strengthening locally-led response and recovery to shocks such as climate and health: Multiple and sequential crises underline the need to build community resilience and enhance recovery from shocks through a robust shock-responsive system. This includes strengthening Zambia’s Disaster Mitigation and Management Unit (DMMU) for better coordination and capacity. There is potential to leverage social protection systems to enhance anticipatory action including through early warning systems, provide intensified nutrition support during crises – particularly to the most vulnerable people, and improve targeting and transfer values based on food costs. The UK can also help to unlock pre-arranged disaster risk financing.

Using evidence from research, monitoring and evaluation to influence policy and programming: The UK should generate evidence on effective poverty reduction strategies in Zambia and to better understand how to strengthen resilience and recovery from shocks. This evidence can be used to inform government policies and diplomatic engagements, leveraging the UK's strong relationship with Zambia to influence policy for greater impact. By prioritizing monitoring, evaluation, and learning, the UK can optimize spending and enhance the effectiveness of multidimensional poverty reduction efforts.

Improving economic opportunities for women and girls to unlock human potential and support sustained escapes from poverty: Growth is necessary for poverty reduction, and to complement top-down growth it will be essential to invest in interventions that support inclusive growth for the bottom 40%. Investing in interventions that support diversified incomes strengthen pathways out of poverty and build resilience against shocks. Economic opportunities linked to climate-smart agriculture and rural market development could include Village Saving Loans Associations (VSLA), digitisation of savings groups, increasing access to finance, women’s economic empowerment initiatives such as training and mentorship, inclusion in socio-economic relationships through cooperatives and value chain development.

Strengthening voices for change in favour of pro-poor public policy: To drive change, the UK should seek to leverage growth of an educated middle class to drive structural change, prioritizing meritocracy and accountability over traditional patronage networks. Efforts could include building alliances for pro-poor policies through political analysis and strategic partnerships, supporting civil society coalitions, engaging parliamentarians with evidence on poverty reduction, promoting policy dialogues, and ensuring pro-poor budgeting and accountability. The aim would be to create a more responsive and accountable governance system that prioritizes poverty reduction and inclusive development.

Improving access to, and quality of, essential human development services for the poorest, particularly women and girls: Access to essential services (health, education, nutrition, SRH) and ensuring that these services are of good quality faces a real challenge posed by Zambia's scattered and diverse communities. This is central to poverty reduction. This includes developing coherent community service delivery models to bridge gaps between district administration and households, enhancing system efficiency through integrated case management, and strengthening linkages to decentralization by formally connecting community volunteers to local governance structures. Enshrining evidence of effective approaches in policy and legal frameworks will be crucial for improving service delivery and ensuring government commitment to action. Efforts should also address educational and non-educational barriers to girls' education and improving sexual and reproductive health and rights (SRHR) to enable women and girls to achieve their full potential and contribute to economic growth and break the cycle of inter-generational poverty.

Improving foundational learning outcomes for Zambian schoolchildren and strengthening the education system: This does not mean that the UK undertakes service delivery at scale. The UK’s approach will be to build on Zambian priorities around foundational learning and strengthened education systems. Technical assistance to MoE will build on lessons from the EDGE programme to work with a tightly defined set of directorates in the MoE, with clearly defined goals linked to helping the GRZ deliver on existing, larger efforts on foundational learning or systems strengthening. These include the upcoming GPE programme, the ELPAF action plan, multilateral programmes in the sector, delivery of JAR commitments, etc. Bringing expertise around foundational learning and/or helping GRZ spend and allocate their own funds more efficiently could be big wins with small money. The UK will also work on influencing the sector via technical expertise offered by a full-time, programme-funded education adviser in BHC Lusaka. This role will provide technical advice to ZPRP and spend a large proportion of time on convening, inputting to donor structures and programmes, bringing in best practice and evidence, and best use of the FCDO’s CMP/CoE landscape, and influencing multilateral investments. There may also be scope to support pilot interventions addressing foundational learning. Funding a small set of pilot projects which focus on a narrow set of strongly evidenced interventions (only the “great buys”: structured pedagogy, TaRL, raising community awareness of learning levels), and have a specific plan for attracting wider funding for scaling (e.g., from foundations).

1. This approach would deliver a multi-dimensional approach to poverty reduction in Zambia and is outlined in the Theory of Change below. This programme transitions to a modern approach to reducing poverty in Zambia, learning from previous human development programmes, ZPRP will harness UK expertise to strengthen and future-proof systems, invest in human capital and inclusive growth, and help to drive locally led reforms. This will be demonstrated through:
  1. An engaged reformer in multilateral investments: Whilst continuing to support multilaterals (as in previous programmes), this programme will ramp up the use of UK expertise and additionality through genuine partnerships to help shape and leverage bilateral and multilateral investments in the human and social development systems.
  2. Strengthening locally led humanitarian systems: Importantly, it responds to the UK’s experience in Zambia that has shown that repeated shocks such as drought, cholera, and covid demand flexibility. As such the programme builds in multiple opportunities to enable flexibility to adapt and pivot support, as well as strengthen anticipatory action, access disaster preparedness and response expertise. Rather than retrofitting a humanitarian response into the programme, this prepares for and anticipates the need to respond to shocks.
  3. Supporting self-reliance and local ownership: It will build stronger voices for more pro-poor policies building coalitions for change, through parliamentary engagement, increased policy dialogue on poverty and budget tracking and elevating local voices.
  4. Strengthening systems: ZPRP marks a shift away from service delivery to system strengthening
  5. Innovating: It seeks to take risks, innovate and explore new and nascent initiatives that will support sustained escapes from poverty. Previous human development and social protection have had a heavy reliance on multilateral partners to deliver tried and tested approaches, where the multilaterals carry the risk. This new programme will test new and potentially risky approaches, alongside the tried and tested.

ZPRP: A UK Strategic Investment

The UK’s vision for a modern development approach supports countries to make sustained progress to achieve self-reliance, build resilience, tackle climate change, prevent and respond to shocks. To tackle global crises and deliver sustainable, inclusive growth, we need to draw on the strength which comes from equal and genuine partnerships based on trust and respect. The UK and Zambia’s long-term relationship and joint ambition to tackle poverty is reflected in the Poverty Reduction Pledge, signed between the UK and Zambian Governments in December 2024. Both governments committed to creating a future where poverty and hunger are eradicated, and every individual has the opportunity to thrive and contribute to their communities on a liveable planet. This requires long-term solutions to poverty and inequality. The UK’s long-term investment in poverty reduction in Zambia has evolved and adapted over the past decades, flexing to political changes and opportunities. For example, UK investment has moved away from sector budget support to multi-donor partnerships, innovative programmes, knowledge exchange, expertise and technical assistance as well as unlocking much-needed finance.

The UK government has made it a priority to help partners to build resilience to climate impacts and other shocks, supporting stronger, more locally-led humanitarian systems. Cultivating a virtuous cycle of global resilience and growth is in all our best interests. ZPRP presents an opportunity to build on decades of investment to consolidate Zambia’s social protection system and strengthen Zambia’s ability to respond to shocks whilst testing innovative approaches to build human capital to drive growth – in particular opportunities for women and girls. This programme will leverage synergies across multiple sectors including social protection, women’s economic empowerment, health, education, nutrition, climate and disaster preparedness to create a coherent and impactful package of support that tackles the policy and institutional barriers to effective delivery.

The UK’s expertise, technical assistance and ideas will be at the heart of reliable development partnerships, including in empowering women and girls and championing rights and equality. The ZPRP will support the delivery of the FCDO Strategic Vision for Gender Equality 2018-2030, and FCDO’s Women and Girls strategy 2023-2030, which places strong emphasis on empowering the most vulnerable girls, enhancing access to education, preventing gender-based violence and eliminating harmful practices.

The UK-Zambia partnership is strong and growing, with a long history of investment in people, private sector development and government engagement based on a strong sense of shared values and interests. The ZPRP will contribute to the UK achieving its vision of a prosperous and stable future for Zambia’s people by supporting: sustainable and inclusive growth, greater resilience to shocks, building human capital to drive growth, and unlocking climate finance – all delivered through a gender equality lens. The programme will also play a key role in enabling the vital reforms that the Zambian government is spearheading as part of debt restructuring, with a focus on protecting the poorest from the impacts while maintaining the momentum for the critical reforms.

To deliver on the UK’s diplomatic agenda in Zambia, FCDO plans to implement four independent but complementary programmes, which will include:

Figure 6: UK Portfolio in Zambia

The programme will draw upon FCDO centres of expertise to access knowledge exchange and complement the programme, including but not limited to areas such as sexual and reproductive health and rights (SRHR), education and resilience and adaptation. It will also take a One HMG approach, working with partners across government, such as the UK Health Security Agency to draw on technical expertise to enhance programme interventions and policy work.

Assurances

Development Act: ZPRP is fully compliant with the Development Act. The long-term aim is poverty reduction and to strengthen human development in Zambia. It will provide lasting benefits for the population it reaches by working with the Zambian government to strengthen national systems.

Gender Equality Act: Zambia ranks 87th in the Gender Equality and Governance Index. Key challenges for women and girls include the lack of gender parity in school completion rate, women’s participation in decision-making and formal employment, and high levels of poverty among women. Women and girls continue to be in the periphery of development and most of them remain underserved with limited life opportunities, facing multiple deprivations and vulnerabilities, including harmful gender norms such as gender-based violence and norms regarding male ownership of home and assets. ZPRP is fully compliant with the Gender Equality Act 2014. The programme will contribute significantly to reduced gender inequality and will place specific emphasis on reaching marginalised women and girls and improving their outcomes, across the lifecycle. This will be reflected in and monitored through the logframe.

Disability: Prevalence of disability is estimated to be 10.9% among adults (18+ years) and 4.4% for children in Zambia. People with disabilities still endure high levels of discrimination and inequality, in part because of entrenched negative public attitudes and a lack of or limited awareness. There are significant barriers to accessing services, including about 1 in 10 persons with disabilities experiencing problems with accessibility.[37] Disability considerations will be included in contracts to ensure partners build it into project design. Disaggregated data collection will help assess whether people with disabilities are meaningfully included in programme activities. The programme will disaggregate all data by gender and disability status, using the Washington Group set of questions and drawing on the learnings from the Zambia Social Protection Expansion Programme Phase II. ZPRP will include opportunities to scale evidence-based interventions that support people with disabilities, capacity development of government ministries to improve disability inclusiveness and programme design will be driven by meaningful engagement with local Organisations of Persons with Disability.
[37] https://www.unicef.org/zambia/reports/zambia-national-disability-survey-2015

Public Sector Equality Duty: ZPRP complies with the Public Sector Equality Duty under the Equality Act 2010. The programme will include a strong focus on increasing equity within social protection systems and in access to essential serves to enable poverty reduction. This includes work to address explicit discrimination and foster good relations between different groups, especially, women, children, the elderly, people living with disabilities and chronic illnesses, and pregnant and lactating mothers.

Conflict and Fragility: ZPRP will operate in Zambia which is considered a fragile state. The programme will build resilience to shocks and adapt to deliver in the face of security concerns, violence, and fragility. The programme will include components to support the government to strengthen systems to adapt to deliver during shocks, including climate, economic and health risks.

Safeguarding: GBV is widespread in Zambia, with girls and women, particularly those in rural areas, facing high rates of GBV and SEA/SH. As such, the main potential safeguarding risks associated with the project are related to GBV and SEA/SH. ZPRP will leverage the existing Girls’ Education and Women’s Empowerment and Livelihoods (GEWEL) programme’s Grievance Redress Mechanism (GRM) which has been designed to be responsive to GBV and SEA/SH and is already receiving and addressing grievances and questions related to SCT and cash plus initiatives under GEWEL. The GRM includes a referral pathway that supports GBV survivors in accessing safe services. FCDO will continue to work with the World Bank and GRZ to continually improve the way that the GRM operates, learning from feedback and adapting accordingly. One of the areas of greatest risks is in the education sector through the Keeping Girls in School initiative, which FCDO will continue to monitor closely. Grievances will continue be handled in a transparent and culturally appropriate manner, upholding principles of confidentiality and ensuring a survivor-centred approach in the handling of GBV/SEA cases.

Climate and Environment: A Climate and Environment Risk Screening has been undertaken for ZPRP. The programme scored 20 (major risk), meaning that climate related risks could possibly impact on the programme’s success. The nature of the proposed support is such that no harm will be done to land or biodiversity, nor will the programme involve any investment in fossil fuels or go against Zambia’s climate plans. Shadow carbon pricing is not assessed to be needed. However, the impact of climate hazards on Zambia’s vulnerable population could exacerbate pre-existing governance challenges (and conversely, improvements in governance will reduce vulnerability to climate change). ZPRP is expected to deliver International Climate Finance (ICF) eligible activities. ZPRP will increase Zambia’s resilience to climate change by supporting the state to deliver for those most affected by climate change (people living in poverty, women and girls, people with disabilities, marginalised groups), ensuring the most affected have greater representation in demanding for climate action and improving the policies and institutions that are instrumental in reducing climate vulnerability (such as natural resource and land governance). Exact proportions of ICF-eligibility will be determined once focus areas are agreed (and monitored as the programme evolves. Social protection has four functions that support climate risk management: 1) reducing poverty and vulnerability, both ensuring basic wellbeing and enhancing the ability to deal with climate shocks and stressors ex-ante (before these hit); 2) protecting people from the immediate impacts of climate shocks through shock-responsive measures at times of shocks; 3) contributing to climate change adaptation by helping to reduce disaster risk and to enhance adaptive capacity; and 4) compensating for or incentivising measures that support a just societal transition to a climate-resilient future and a green economy. GEWEL will be one of the main components of the programme contributing to climate and environment priorities and able to deliver ICF.

Counter-Terrorist Financing and Anti-money Laundering: The threat of terrorism in Zambia is low, although terrorism is prevalent in neighbouring countries and in the region and so risks remain. ZPRP, in line with FCDO policy, will have a zero-tolerance approach towards terrorist financing and money laundering. ZPRP will comply with domestic law and international sanctions on terrorist financing. Strong financial controls and risk management guidance will be implemented Appropriate measures will be put in place to manage any risk (see Financial Case). This risk will be reassessed, and mitigating measures revised, as necessary throughout the life of the project.

Partnership Principles: Partnership Principles are one of the tools the UK uses to inform and shape our overall strategy for engagement in Zambia. These principles will be used to assess the UK and Zambia’s shared commitment to reducing poverty. We assess there to be a credible commitment to the Partnership Principles in place by the Zambia Government. Poverty is becoming more entrenched over time. 64.3% of the population lives below the international poverty line and rural poverty is increasing. The entrenched status quo that underpins poverty in Zambia remains. However, the Government’s Eighth National Development Plan outlines its commitment to reducing poverty and there is positive policy potential to contribute to the development of the Ninth National Development Plan. Civic space remains broadly open, creating the environment for domestic accountability. Zambia’s commitment to (and history of) holding credible democratic elections supports this, but the day-to-day accountability of officials to citizens is weak. No funds will be channelled directly through partner government budgets in this programme.

Risk: Risk throughout the life of a programme will be managed in line with the agreed risk appetite using appropriate controls. The risk appetites for ZPRP, the overall risk rating and the risk management processes are outlined in the Management Case. A risk matrix is included in Table 12.

Appraisal Case

The Strategic Case provides an analysis of the underlying causes of, and challenges in tackling multi-dimensional poverty in Zambia and identifies five outputs necessary to reverse the trend of rising poverty in Zambia. These outputs are areas where the UK can add value through its policy leadership, innovative approach and technical expertise. The viable options are appraised against their ability to deliver on these five outputs and cross-cutting objective on use of evidence and MEL.

The Appraisal Case explores how we will address the need presented in the Strategic Case in a way that optimises value for money (VFM). It appraises genuinely feasible options of interventions to fund and how to deliver them to achieve the objectives, including high level commercial choices. It critically appraises evidence and considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a summary VFM statement for the preferred option.

OPERATING PRINCIPLES

Flexibility and adaptability: This programme will be flexible, meaning it will proactively deal with uncertainty and complexity through systematic political economy analysis, and building in mechanisms to respond to and manage change. This will allow the programme to continue operating under significantly different circumstances, including across election cycles, and managing the risks of political and contextual shifts, including changes in UK ODA budgets. ZPRP will have the ability to move funds and resources to scale up components in response to climate and other shocks and opportunities identified to deliver the most impact with the budget available. The programme will also have elements which are adaptable. For some areas of the programme, there is sufficient evidence of the needs and pathways to change to have confidence that our investments will deliver the desired outcomes. For other areas, there is less evidence on effective pathways to change. An adaptive approach, one that tests different options before scaling (or failing) and uses feedback loops to build the evidence base, is therefore more appropriate. The approach to flexibility and adaptability is covered in further detail in the Management Case.

Gender equality and inclusion: To be successful, every intervention under ZPRP will consider opportunities for strengthening gender equality and inclusion. ZPRP will integrate gender equality into the analysis, design, implementation and monitoring and evaluation of each activity.

Locally owned and sustainable: Our work will be grounded in respect and partnership, prioritising Zambia’s needs for development; this matters both for the success of the programme and for sustainability beyond the life of the programme. We want to create genuine, equitable, strategic and long-term partnerships that are beneficial to Zambia, supporting the strengthening of Zambian systems. This means promoting Zambian leadership, working within Zambia’s existing political realities, building trust, and establishing stronger, more equal relationships. By recognising and engaging with the political structures as they are, we can deliver politically informed interventions that are responsive to Zambia’s priorities for sustainable and inclusive growth and poverty reduction.

THE COUNTERFACTUAL

Decentralisation and system strengthening for human capital development: If FCDO does not invest in the ZPRP, Zambia’s decentralization journey will continue, with CDF is likely to remain and additional powers being devolved. However, none of the partners involved in decentralization are focused on enhancing service delivery systems at the community level, below the ward level. The large size of some wards makes it difficult for people to access services through the Ward Development Committee (WDC) structures, highlighting the need for a lower-level decentralized model to bring services closer to the people. Without this investment, there is a risk of continued weak service delivery for the poorest and a missed opportunities to leverage the decentralization agenda for improved, coordinated, and multisectoral systems. Fragmented service delivery will persist, leading to duplication, resource wastage, and ineffective poverty reduction at the household level. The UK’s technical expertise, strategic investments plus political acumen are highly valued in this sector and no other cooperating partners offer this unique combination.

Inclusive growth for bottom 40%: If FCDO does not invest in ZPRP, other donors will continue to support rural growth, in particular access to microfinance, irrigation and livestock. Gaps are likely to remain in resilience of the poorest to shocks, rural livelihoods linkages to the social protection system and social dimensions of economic opportunities. GRZ structures beyond the realm of social protection, exhibit significant weaknesses and without UK support to take some of the risk and drive innovation, there is unlikely to be large scale innovation that complements but goes beyond what initiative sin the social protection space.

Social Cash Transfers (SCTs) have been one of the Zambian government’s flagship approaches to tackling rising poverty. More recently GRZ has developed a cash plus approach (the ladder) to support pathways out of poverty, which the Zambian Government is seeking support to accelerate progress on as a fast-track initiative through the Global Alliance Against Hunger and Poverty. Given the FCDO’s long-term support to the Zambian social protection system, particularly SCTs since 2003, and deep knowledge of the sector, the analysis below provides more detail on the potential impact of FCDO’s cessation of support to the social protection sector.

Social Protection system: If FCDO does not invest in ZPRP, two projects which seek to strengthen GRZ’s social protection system would likely continue but with limited technical leadership and oversight from cooperating partners. The World Bank GEWEL, would utilise IDA funds ($150) and other donor funding to operate at a smaller scale and the UN Joint Programme on Social Protection would continue with a lower budget scale and ambition. However, the potential impact of these largescale projects would not be realised as the FCDO would not have a seat at the table to influence their design and implementation, or to seize opportunities to enhance impact and ensure high quality delivery. A seat at the table would better position the UK to drive forward a gradual decrease in the contribution that GEWEL makes to cash transfers, and shift funding towards cash plus interventions and system strengthening technical assistance.

Shock response and recovery systems: If FCDO does not invest in ZPRP, the UK in Zambia would be reliant on the FCDO’s planned new programme - Resilience in Agriculture and Investing in Nature Zambia (RAINZ) - to strengthen resilience to shocks. However, RAINZ does not focus on the chronic poor or linkages to social protection systems and does not address health shocks. As Zambia emerges from a period of chronic drought and remains vulnerable to climate and health shocks, it will be vital to strengthen the social protection system’s shock response to support the poorest and most vulnerable.

Political will and pro-poor policies: If FCDO does not invest in ZPRP, opportunities to build stronger voices for more pro-poor policies will be limited and the UK will have less leverage to contribute to these policy debates. Buying a seat at the table through multi-donor programmes such as GEWEL and UNJPSP would open opportunities for influencing key stakeholders in the social spending space. Yet the social protection programme is not enough alone to change the trajectory of poverty in Zambia. The UK, as a trusted and politically informed partner, has a strong role to play in supporting voices for change that can enhance political will for more pro-poor policies.

Education sector: Without continued UK engagement in the sector Zambia’s progress towards inclusive and quality education provision may stall. Critical challenges – such as low learning outcomes – would remain inadequately addressed. The absence of UK support would mean the loss of high-quality technical advice and strategic leadership provided by an Education Advisor – this can be instrumental in shaping policy direction, strengthening coordination and guiding programming. The UK’s withdrawal would diminish the impact of existing investments and also represent a missed opportunity to catalyse systems change.

IDENTIFICATION OF FEASIBLE OPTIONS

Through the UK’s long-term engagement on poverty reduction in Zambia, we have developed a broad and deep understanding of the challenges and opportunities. Building on experience and cognisance of the need for innovation in the sector, we have identified three feasible options, presented below. We have ruled out direct financial support to the Government of Zambia (GRZ) as fiduciary risks are assessed to be too high and additionality too low.

Three delivery options have been considered:
Option 1: Multilateral partnerships only
Option 2: Multilateral partnerships PLUS direct partnerships
Option 3: Multilateral partnerships PLUS direct partnerships PLUS a technical assistance and innovation facility

Option 1: Multilateral Partnerships only

This approach would continue investment in multilateral funds such as the World Bank’s GEWEL programme and UNJPSP, enabling FCDO to influence and shape investments. This would deliver similar programming to that previously implemented through the Zambia Social Protection Expansion Programme Phase II.
Option 1

GEWEL (World Bank)

UNJPSP
(UNICEF)

Under this option GEWEL serves as the main delivery and system-strengthening partner and the UNJPSP will provide complementary technical assistance on policy and piloting. Cash plus innovations including Supporting Women’s Livelihoods (SWL) and Keeping Girls in School (KGS) will be piloted through GEWEL, and new pilots such as ‘cash plus care’ will be tested through UNJPSP.

UNJPSP will also be an important channel to deliver coordinated responses to shocks working through government systems. FCDO’s contribution would buy a seat at the table, maintaining the UK’s position of technical expertise and political analysis as an engaged reformer. FCDO would continue identifying opportunities for influencing key stakeholders in the human and social development space and shape the direction of these programmes, to maximise synergies, and to leverage and enhance the impact of Zambia’s domestic resources to fund its own essential service systems, promoting self-reliance.

Option 2: Multilateral partnerships PLUS direct partnerships

Option 2

GEWEL (World Bank)

UNJPSP
(UNICEF)

Direct partnerships
Building on option 1, this option would renew existing multilateral partnerships, complemented by direct partnerships to deliver on expanding economic and human capital development opportunities. It could include direct partnership with research institutions to use expertise and knowledge exchange, build evidence and influence policy. It would partner with local and international NGOs to undertake advocacy, respond to shocks and build on the cash plus agenda to support locally led increased resilience.

In the context of increased frequency of crises, it is vital to maintain flexibility to access funding which can be used to respond to shocks. One of the key lessons emerging from the Zambia Health Systems Strengthening Programme was the importance of taking an adaptive approach, which made it possible to provide much needed support to evolving needs and priorities during the Covid-19 pandemic.[38] This delivery channel will provide an option to enable flexible funding to respond to shocks. If the shock response funding is not required, it can be reallocated to help scale successful inclusive growth and cash plus interventions in the final year.
[38] Programme Completion Review, June 2022: Zambia Health Systems Strengthening Programme

These partnerships will work with local and international partners to utilise FCDO’s role to influence systems and advocate for evidence based policy-making to strengthen essential services systems. These partnerships could operate in a range of sectors such as nutrition, SRH, economic and social empowerment, education, emergency response and cross-cutting research and evidence, but will need to be selective to match ambition with capacity to deliver.

Direct partnerships with NGOs, research institutions and consultants will serve as a flexible modality able to provide expertise to deliver on objectives such as (but not limited to):

- Work with local partners to undertake comprehensive research and analyse evidence to strengthen evidence-based policy-making and shape programming.
- Pilot projects (no more than 3 at any one time) to test innovative ideas on a small scale, to improve economic and human development opportunities for women and girls, and essential services for the poorest.
- Prepare for and respond to shocks such as climate and health and support locally led responses.
Utilise consultants to add value to and assess risks of multi-donor investments, such as Fiduciary Risk Assessments of government systems and Annual Statements of Progress.

Option 3: Multilateral partnerships PLUS direct partnerships PLUS a Technical Assistance and Innovation Facility

Option 3

GEWEL (World Bank)

UNJPSP
(UNICEF)

Technical Assistance and Innovation Facility

Direct partnerships
This option would build on option 2, with the addition of a technical assistance and innovation facility called ZAMBRIDGE (Zambia - Building Resilience, Inclusive Development, Growth and Evidence). This would enable FCDO to play a more catalytic role in building the political drive for poverty reduction, innovating and influencing change as well as consolidating and modernising sustainable systems through the multilateral partnerships. This option would increase FCDO’s catalytic potential through a combination of a political analysis hub, Technical Assistance (TA), innovative pilots that respond to opportunities and Monitoring, Evaluation and Learning (MEL) which informs the adaptive programming. Further detail on how ZAMBRIDGE will function is outlined in Box.

How will ZAMBRIDGE work?

ZAMBRIDGE will drive significant change for poverty reduction through a multifaceted approach. By focusing on policy and advocacy, aiming to influence and shape policies that address the root causes of poverty. This could include building coalitions for pro-poor policies, engaging with legislators, increasing policy dialogue on poverty, tracking budgets, and influencing political manifestos.

ZAMBRIDGE will focus on elevating local voices to ensure that the perspectives and experiences of those directly affected by poverty are heard and considered in policy-making processes, driving locally led sustainable change and creating a comprehensive and inclusive approach to poverty reduction.

ZAMBRIDGE will leverage strong political analysis, through a deep understanding of the local context. Through a flexible and adaptable design, this approach ensures that poverty reduction initiatives are contextually relevant, politically informed, and adaptable to changing circumstances. How ZAMBRIDGE will take an adaptable approach is outlined in the management case.

Management Team: ZAMBRIDGE will be managed by a core team consisting of a team lead and a management team. The team will ensure successful delivery of all elements of ZAMBRIDGE. The Management Team will lead the day-to-day implementation of ZAMBRIDGE, including operations, administration and compliance. Inception activities will include mobilising the core team, creating, documenting and implementing all required programme management, governance and financial management policies and processes, and developing an initial portfolio for Year One. They will be responsible for ensuring the all the different element of ZAMBRIDGE are interlinked with each other and deliver on sustainable impacts.

Monitoring, evaluation and learning (MEL): ZAMBRIDGE will lead the monitoring evaluation and learning across the programme, ensuring that evidence and learning informs policy and programming. Success of the MEL will be dependent upon high quality delivery by the partners and ZAMBRIDGE’s ability to work effectively with the multilateral partners in the programme (which are delivering at scale) to draw on learning and evaluation. The new position of donor coordination focal point in GEWEL will provide a key person within the World Bank to liaise with on high-level coordination and strategic engagement.
  1. Monitoring: the MEL team within ZAMBRIDGE will monitor the activities delivered including undertaking field visits. The monitoring will be a routine activity to ensure that partners are delivering as per their agreements. It will undertake key compliance activities including risk management. The team will also review the routine reporting by the other partners in the programme, including the World Bank and UNICEF, enabling ZAMBRIDGE to have a whole programme view on progress. Data will be disaggregated, including by sex, enabling the MEL team to ensure gender mainstreaming.
  2. Evaluation: the ZAMBRIDGE MEL team will assess whether activities across the programme are leading to the intended outcomes and contributing to the intended impact as set out in the logframe. The team will draw on evaluation reports and impact assessments from across the other components of the programme beyond the ZAMBRIDGE. Some parts of the programme, such as the innovative pilots will require more intensive evaluation than others and this will be determined at the outset of the activity. The MEL team will also develop a clear methodology for evaluating progress made through the TA components. Evaluation findings will be reported to FCDO through quarterly and annual progress reports.
  3. Learning: although some components of the programme are better able to adapt than others, learning will be central to the culture of ZAMBRIDGE and the way that it operates. ZAMBRIDGE’s MEL team will establish strong relationships with other partners in the programme to ensure that their learning is fed into ZAMBRIDGE. Key lessons learned will be fed into FCDO through the Programme Steering Committee and BHC Lusaka’s internal governance structures.
  1. Decision Making: At times ZAMBRIDGE will require authorisation from the FCDO to start or stop a project. These decisions will be made through the programme steering committee. Decisions will be informed by the political analysis hub and the information from the MEL. All decisions will be taken on a case-by-case basis. Any project will need to align with the theory of change and have strong value for money indicators. The PSC will consider if the project is politically balanced, in the right geographical area and is there need for the work.
  2. Managing Risk: To manage risks related to ZAMBRIDGE, the management team will be required to have a risk register that will be discussed during monthly meetings and updated on a quarterly basis. Risks that the FCDO team deem out of appetite will be escalated as necessary. This will feed into FCDO’s wider risk management tools at team and portfolio level.

Box 2: ZAMBRIDGE

ZAMBRIDGE (ZAMBIA - Building Resilience, Inclusive Development, Growth and Evidence)

Political Analysis Hub, led by a team of experts, the hub will conduct initial scoping for opportunities, undertake political economy analysis (PEA) and power mapping, provide regular updates on how the landscape is changing and actors are shifting, and identify and potential coalitions for change.

Technical Assistance (TA) through technical and politically savvy experts will provide advice on specific thematic areas and questions to offer solutions to poverty reduction challenges. It includes direct technical assistance in specific ministries, both short and long term, for example through embedded TA in DMMU, Ministry of Green Economy, and the Ministry of Health.

Innovation Pilots will focus on rapid start-ups, including piloting enhanced VSLAs with links to accessing resources; exploring innovations and linkages for smallholder agriculture; and strengthening community volunteer structures for improved service delivery. In the medium term, it will address inclusive insurance for preparedness and identify opportunities to expand and strengthen health insurance.

The Monitoring, Evaluation, and Learning will provide high-quality evaluations and RCTs, learning will inform pilots and evidence-based policy-making.

What will ZAMBRIDGE do?

As an adaptive facility ZAMBRIDGE aims to build on and develop new and innovative ways of working on issues described in the Strategic Case. It will be able to deliver across the five outputs assessing political, contextual and strategic changes and new or emerging opportunities, towards outcomes and impacts. Examples of this may include:

1. Strengthened comprehensive and fiscally viable GRZ social protection system
  1. TA and evidence are used to shape GEWEL and GRZ’s social protection system to support a more comprehensive and systematic approach to supporting pathways for upward mobility.

1. Strengthened shock response and recovery systems
  1. TA to agencies such as DMMU and Ministry of Local Government and Rural Development to strengthen disaster preparedness and response.
  2. Pilot to strengthen anticipatory action to shocks and embed early warning systems in adaptive social protection systems and community led approaches to disaster preparedness and resilience.
  3. TA to support enhanced access to and utilisation of disaster risk financing, including pre-arranged finance.

1. Stronger voices for change in favour of pro-poor public policy
  1. These activities will be informed by the political analysis hub and could include:
    1. building coalitions for change and elevating local voices
    2. parliamentary engagement on poverty reduction priorities
    3. increased policy dialogue on poverty
    4. strengthening budget tracking skills

1. Improved economic opportunities for the poorest to unlock human potential and support sustained escapes from poverty
  1. Enhancing GRZ’s monitoring and evaluation of interventions to support income diversification and women’s economic empowerment to steer future investment decisions based on evidence of what works
  2. Cash plus initiatives to strengthen graduation and sustained escapes from poverty e.g. financial inclusion initiatives, strengthened government approach to sequencing and staging cash plus packages to support sustained poverty escapes based on careful targeting.
  3. Strengthening cross ministry collaboration for rural development and smallholder agriculture will also play a key role in creating opportunities for upward mobility beyond social protection.

1. Strengthened systems to improve the quality of human development services (e.g. education, health, nutrition, and SRH) for the poorest
  1. Strengthening referral mechanisms to improve access to essential services and integrated case management.
  2. Access to universal health coverage or strengthening the national health insurance scheme.
  3. Piloting scalable and sustainable innovations in health, nutrition or education sectors.
  4. TA to improve domestic resource mobilisation for human capital investment.
  5. As the level of political will and institutional capacity to move towards genuine decentralisation of essential services may fluctuate during this programme period, ZAMBRIDGE will need to adjust ambition and identify the most appropriate interventions for the context and be ready to adapt quickly where opportunities for greater decentralisation arise to build skills, ownership and sustainability.

Cutting across these areas will be better use of evidence from research, monitoring and evaluation for more effective essential services systems. This includes TA in government ministries will be informed by evidence emerging from all components of the programme. Strong monitoring and evaluation will be led by ZAMBRIDGE and embedded across the programme to ensure that we can test, learn and adapt through flexible programming. The governance structures will be crucial to ensuring that learning and evidence feeds in to inform programming.

Box 3: ZAMBRIDGE principles for operation

PILOTS – All pilot proposals will be considered by FCDO’s Programme Steering Committee (see detail in the management case). Proposals will require a sustainability and/or scalability plan. Where possible, they will need to be integrated into existing systems and structures to enhance their longevity. Through regular monitoring, break clauses, and report, the pilots will evaluate the impact and FCDO’s programme steering committee may at times need to decide to change direction or stop all together.

SUSTAINABILITY – Partners will need to consider not only how change happens, but how to embed it in the lives of the most vulnerable individuals and communities. Partners should support target people in identifying their own unique barriers to escaping poverty and having clear plans through behavioural and mindset/social norms change initiatives.

ADAPTIVITY - Partners will be expected to test different options before scaling (or failing) and use feedback loops to build the evidence base. In the design of activities, partners will need to factor in flexibility to increase, or slow down pilots and/or activities given increasingly rapid contextual geo-political shifts. This will require more intensive management and monitoring and evaluating (further information on adaptive management in management case).

APPRAISAL OF FEASIBLE OPTIONS

Option 1: Costs
The total resource cost of this option would be £35 million, comprising £23 million to GEWEL and £12 million to UNJPSP and their successor programmes. This is based on FCDO’s historic contributions to the multilaterals working on social cash transfers, building resilience through social protection systems and cash plus approaches. In FCDO’s recent programmes with UNICEF in Zambia, the management and overhead costs for the UN were fixed including a 1% coordination levy and 7% indirect costs, whilst the indirect rate for the GEWEL II (World Bank) were set at 17%. These amounts could be further scaled down or up by amending the administrative arrangements or MoUs to respond to changing contexts.

The estimated staff resource required to deliver this option would be a paired back team with:
- 0.4 FTE of a Senior Responsible Owner
- 0.4 FTE of a Programme Responsible Owner
- 0.5 FTE of a Programme Manager
- 0.2 FTE of a Programme Officer
- 0.7 FTE of a Human Development/Social Development Adviser

Option 1: Benefits
Social protection system strengthening: A key benefit of continuing to fund the multilaterals working in this area is the impact the UK can have on the overall effectiveness of the SCT system in Zambia. As the largest donor to the MDTF during the first phase of GEWEL, the UK utilised its position to provide policy leadership as Chair of the Social Protection Cooperating Partners Group and has played an active role in shaping the design of GEWEL. The UK was pivotal in unlocking further World Bank IDA financing (over $200m) to respond to the 2024 drought, which enabled GRZ to increase the value of the cash transfer (vertical expansion) and reach more vulnerable households (horizontal expansion) during the drought period. With sufficient advisory capacity the FCDO can also strengthen the quality and utilisation of data to inform more evidence-based policy making and can draw on centrally managed programmes to access TA to help strengthen the quality and uptake of evidence.

Enhanced coordination: Following recent UK-led advocacy, the World Bank has committed to strengthen donor and government coordination with the addition of a new dedicated Donor Coordination Focal Point within the World Bank. This responds to lessons learned from Ethiopia, where the Donor Coordination Team has enhanced coordination across multiple donor and government ministries, and increased opportunities for improving impact and value for money of investments. The Donor Coordination Focal Point will reduce the burden on the UK to take a leading role in policy coordination among the donors and will deepen the partnership with the government on evidence-based policymaking. Having a seat at the table in both GEWEL and UNJPSP would enable FCDO to shape the direction of these programmes, and support GEWEL and UNJPSP to maximise synergies, use their comparative advantage and avoid duplication – a lesson learned from the 2023 annual review in the social protection programme.

Option 1: Assessment of ability to deliver against the outputs

The ability of Option 1 to deliver against the five outputs is summarised in the table below.

Table 3: Option 1
Output / Criteria	Option 1: Multilateral Partnerships only
1.Ability to strengthen comprehensive and fiscally viable GRZ social protection system at scale	HIGH / Through GEWEL II the merged donor/GRZ funding strengthens government systems and operates at scale. UNJPSP delivers tailored TA and policy to shape a comprehensive and adaptive social protection system on targeted priorities.
2. Ability to strengthen shock response and recovery systems	MEDIUM-HIGH / GEWEL works through existing mainstreamed mechanisms and UNJPSP has experience of leading pilots to adapt SCTs to emergency response. Strong approach to evidence to enhance GRZ policy. UNJPSP has experience of leading pilots to adapt SCTs to emergency response. Strong approach to evidence to enhance GRZ policy.
3. Ability to strengthen voices for change in favour of pro-poor public policy	LOW / Multi-donor channels do not have components that aim to support stronger voices for change in favour of pro-poor public policy. Delivering on this output would be reliant on the advisory capacity of FCDO staff which is a scaled back team in this option.
4.Ability to improve economic opportunities for the poorest to unlock human potential and support sustained escapes from poverty	MEDIUM / GEWEL has a small scale pilot on supporting women’s livelihoods. UNJPSP had a strong track record in gender transformative initiatives and supporting a social protection system that promotes economic inclusion will be one of the pillars of UNJPSP.
5. Ability to strengthen systems to improve the quality of human development systems	MEDIUM-HIGH / GEWEL has limited linkages across the multiple cash plus initiatives and has limited ability to strengthen systems beyond social protection. UNJPSP has a track record of playing a key role in linking nutrition interventions to SCTs and strengthening single window and case management and community level.
Cross-cutting: / Ability to use evidence from research, monitoring, evaluation for more effective delivery and empowerment and inclusion of women and girls	LOW-MEDIUM / GEWEL’s scale and implementation nationwide means there is some evidence generation through impact evaluations, but it is slow to adapt and reflect lesson learned. UNJPSP has proven ability to pilot SCTs, shock response, and nutrition cash plus, with strong evaluation components, effective in influencing GRZ. UNJPSP had a strong track record in gender transformative initiatives.

Option 1: Risks and opportunities
This option is the simplest model, with the smallest FCDO team and lowest risk as both the GEWEL programme and UNJPSP are tried and tested delivery mechanisms in this context. The multilaterals provide strong assurances through their own centralised processes, which means that the multilaterals shoulder most of the risks.

A heavy reliance on multilaterals reduces the ability of the programme to be agile and quickly respond to opportunities. Whilst UNJPSP has piloted approaches to shock response, annual reviews have highlighted the weaknesses of GEWEL and UNJPSP in responding quickly to changing demands. However, as a large donor to these funds, the UK would have a strong voice to seek to influence the World Bank and UNICEF on its direction and response to changing demands.

Limited opportunity to innovate: Although this model would include the expansion of cash plus initiatives such as Keeping Girls in School, Supporting Women’s Livelihoods and nutrition cash top ups, it would provide limited opportunity to innovate and test UK-led pilots to deliver on the ‘ladder’ aspects of the theory of change. Working only through multilaterals would offer a limited opportunity to support voices for change in favour of pro-poor public policy.

Option 2: Multilateral partnerships PLUS the direct partnerships

Option 2: Costs

The total resource cost of this option is £38.5 million, with a reduction in the multilateral contribution to fund direct partnerships. £20 million would be allocated to GEWEL II, £10 million to UNJPSP and £8.5 million would be delivered through direct partnerships.

1. Based on previous experience of direct partnerships in the human development space, cost drivers are likely to include:
  1. Consultancy fees of researchers, academics and consultants
  2. Travel for consultants to Zambia and their travel and accommodation within Zambia
  3. Trainers/facilitators and venue to deliver training
  4. Venue hire and costs associated with events to disseminate research and convene stakeholders
  5. Direct delivery (preparedness and response) for emergency WASH facilities or ready to use therapeutic foods to prevent severe acute malnutrition
  6. Management costs of NGOs delivering pilots or community led emergency response activities
  7. Capacity building support TA to local CSOs and NGOs

The estimated staff resource required to deliver this option would be:
  - 0.8 FTE of a Senior Responsible Owner
  - 1.0 FTE of a Programme Responsible Owner
  - 1.5 FTE of a Programme Manager
  - 2.5 FTE of a Programme Officer
  - 1.0 FTE of a Lead Adviser
  - 0.8 FTE of a Human Development/Social Development Adviser

Option 2: Benefits

The benefits of this option build on option 1. The reduction in the allocation to the multilaterals is not expected to have a significant effect on the benefits and impact delivered by GEWEL and UNJPSP.

Additional benefits will be delivered from the £8.5 million through the direct partnerships. Based on previous experience we anticipate that this will deliver activities such as:
- a comprehensive research and evidence project working with local partners to strengthen evidence-based policy-making;
- projects with local and international partners to respond to shocks, such as surveys;
- WASH interventions and other forms of humanitarian assistance to support locally led preparedness for and responses to shocks;
- pilot projects to test innovative ideas on a small scale, and
- additional financial checks such as Fiduciary Risk Assessments and Annual Statements of Progress.
This option is also assessed to be relatively low risk in that it is largely a continuation of existing programming which has consistently been assessed as delivering good VFM.

Option 2: Assessment of ability to deliver against the outputs

As this option builds on option 1, the assessment against the outputs above largely stands and is not repeated in the table. Where it differs, is in the ability to use evidence from research, monitoring and evaluation for more effective delivery (cross-cutting) and in building stronger voices for change. The addition of the direct partnerships increases the cross-cutting research objective due to the high capacity to undertake research and package evidence from pilots to influence policy. The ability to strengthen voices for change also increases to low-medium. The ability of the direct partnerships facility to deliver against the output criteria is summarised in the table below.

Table 4: Option 2
Output Criteria	Option 2: Multilateral Partnerships + Direct Partnerships Facility
1.Ability to strengthen comprehensive and fiscally viable GRZ social protection system at scale	HIGH / Direct partnerships allow for additional assessments of financial support to strengthen GRZ systems.
2. Ability to strengthen shock response and recovery systems	HIGH / Direct partnerships provide a flexible modality to respond to shocks.
3. Ability to strengthen voices for change in favour of pro-poor public policy	LOW-MEDIUM / Direct partnerships offer an avenue to work with one partner to strengthen voices for change. Due to programme management capacity, it would not be possible to work directly through multiple partners to maximise impact. This would limit the flexibility of the approach but provide some opportunity for increased activity towards this output.
4.Ability to improve economic opportunities for the poorest to unlock human potential and support sustained escapes from poverty	MEDIUM / Direct partnerships enable the opportunity to conduct research with a strong gender lens and test gender transformative pilots for economic opportunities. Scope would have to be limited to a narrow set of interventions due to programme management capacity.
5. Ability to strengthen systems to improve the quality of human development systems	MEDIUM - HIGH / Ability to undertake pilots through direct partnerships and build evidence to influence policy on essential services.
Cross-cutting: / Ability to use evidence from research, monitoring, evaluation for more effective delivery and empowerment and inclusion of women and girls	HIGH / High capacity to undertake pilots, research and package evidence to influence policy. Opportunity to explore initiatives with strong gender lens and test gender transformative pilots.

Option 2: Risks and opportunities

This option attempts to deliver on a wide portfolio of outputs with a relatively limited team. As a result, the greatest risk for this option is the programme management capacity within FCDO as there is a heavy reliance on the FCDO team to manage a range of partners directly to deliver across multiple sectors. Whilst this option would enable FCDO to have greater control and decision-making power to steer the activities with close oversight, the risk is that the programme team would be stretched too thinly which could erode the effectiveness of the programme, and/or make FCDO less able to prevent and mitigate fraud and safeguarding risks.

The start date of activities to deliver on outputs 3-5 are likely to be slow due to the capacity for the FCDO programme team to establish and manage new partnerships. This approach would require a staggered start, meaning that some activities would not begin until at least 18-24 months into the programme. This would limit the impact of the programme and delay expenditure in the first few years.

The main advantage of this option is the flexibility that the direct partnerships offers FCDO to respond to the changing context, whereby FCDO has direct control of how the different direct partnerships are managed.

Option 3: Multilateral partnerships PLUS direct partnerships PLUS Technical Assistance and Innovation Facility (ZAMBRIDGE)

Option 3: Costs

The total resource cost of option 3 is £38.5 million. This will be allocated across the three components and programme funded roles. Estimated breakdown of the budget is outlined below and may be adapted during the inception phase or in response to changes required:

Table 5: Estimated Budget Across programme components
Component		Tentative allocation	% of BC
1.Technical Assistance and Innovation Facility – ZAMBRIDGE	Political Analysis Hub	£2.4m	35%
	TA to national and local government	£2.2m
	Innovative pilots	£6.5m
	Monitoring, evaluation and learning	£2.5m
2.Multilateral investments	A. World Bank MDTF GEWEL	£11m	40%
	B. UNICEF – UNJPSP	£4.3m
3.Direct partnerships	3. Direct partnerships	£8m	21%
4.Programme funded roles / (£1.6m)	4.Programme funded roles to enable delivery	£1.6m	4%
	TOTAL	£38.5	100%

One of the main cost drivers of ZAMBRIDGE will be the management costs, which will likely be around 20% given the adaptive nature of the facility. The other cost drivers will be consultancy costs for the technical expertise placed within government, and the costs to deliver the pilot innovations, which will include management costs for downstream partners as well as direct project implementation costs.

In addition, due to the flexible nature of the programme, its complexity and multiple partnerships, the management of the programme will be time intensive and complex. This will require a strong programme management team and advisory capacity. The staff time required for this option is estimated to be:

- 0.6 FTE of a Senior Responsible Owner
- 0.6 FTE of a Programme Responsible Owner
- 0.5 FTE of a Lead Advisor
- 0.8 FTE of a Programme Manager
- 0.8 FTE of a Programme Officer
- 0.2 FTE of a Programme Officer
- 0.6 FTE of a Human Development/Social Development Advisor
- In addition to 2 FTE programme funded advisors

Option 3: Benefits

Reducing FCDO’s contribution to the multilateral funds whilst retaining a strong position to share policy expertise and influence the agenda enables FCDO to add value through complementary technical assistance, pioneering innovative approaches that have potential to scale; and using MEL to influence future government investments to support sustained escapes from poverty. These interventions will be informed by political analysis.

Working through ZAMBRIDGE will allow expertise to be deployed across a range of sectors with a high degree of agility to lean into the opportunities to catalyse change. This enables FCDO to work across ministries through a politically informed approach to explore opportunities and buy-in for TA and innovations to strengthen essential human development systems, strengthen economic opportunities for the poorest, and build stronger voices for changes in favour of pro-poor public policy.

The innovative pilots through ZAMBRIDGE will test new approaches to innovations. For example, this could include the establishment of operational pilots on decentralised, integrated service delivery, that are not currently part of existing UK programmes. The monitoring and evaluation embedded in ZAMBRIDGE will inform policy and programming by partners, including GRZ. Delivering high risk interventions and using evidence to make bold recommendations on pathways out of poverty would be difficult to achieve through multilateral interventions or direct partnerships facility only. By pairing innovative pilots with MEL and TA in a politically informed way, working with and through local actors, presents a strong package for influencing and driving change.

The investment in additional programme funded advisory roles within FCDO will enable FCDO to take a ‘beyond aid’ approach to leverage additional finance, maximise the impact of UK investments and exercise the UK’s comparative advantage in convening stakeholders, building alliances, elevating local voices, contributing high quality technical expertise and shaping evidence-based policy making.

The combination of delivery channels means that ‘quick-start options’ will be possible and the programme can begin spending early on, following programme approval.

Option 3: Assessment of ability to deliver against the outputs

As this option builds on option 2, the assessment against the output criteria set out above largely stands. However, the addition of ZAMBRIDGE strengthens the assessment in the following areas:

Table 6: Option 3
Output Criteria	Option 3: Multilateral Partnerships + Direct Partnerships + ZAMBRIDGE
1.Ability to strengthen comprehensive and fiscally viable GRZ social protection system at scale	HIGH / Additional, strategically placed and agile TA will strengthen the social protection and essential services systems enabling opportunities to be seized that the multilaterals may not be able to flex to. This further strengthens the already high rating.
2. Ability to strengthen shock response and recovery systems	HIGH / ZAMBRIDGE can undertake pilots to test locally led approaches to strengthen response and recovery to shocks, as well as utilise TA to GRZ to strengthen preparedness, anticipatory action and resilience to shocks. This further strengthens the already high rating.
3. Ability to strengthen voices for change in favour of pro-poor public policy	HIGH / High potential to utilise the political analysis hub to inform political engagement with local stakeholders through ZAMBRIDGE. This can be done through an adaptive approach over several years, providing time to build and support coalitions. This increases the rating to high.
4.Ability to improve economic opportunities for the poorest to unlock human potential and support sustained escapes from poverty	HIGH / Scope to work across ministries and with non-governmental actors, explore opportunities and buy in to test small scale innovations which have potential to be scaled. ZAMBRIDGE has the potential to take a high-risk approach to testing interventions to improve inclusive economic opportunities.
5. Ability to strengthen systems to improve the quality of human development systems	HIGH / ZAMBRIDGE provides a thinking and working politically approach to provide agile TA and pilot innovations to strengthen systems to improve human development system. This increased the rating to high.
Cross-cutting / Ability to use evidence from research, monitoring, evaluation for more effective delivery and empowerment and inclusion of women and girls	HIGH / High capacity to design evidence work linked across multiple components and to use evidence from pilots to influence policy. This further strengthens the already high rating. ZAMBRIDGE will have clear requirements to deliver on gender inclusion priorities.

Option 3: Risks and opportunities

This model is strong on innovation but that is accompanied with higher risks. Investing in innovative pilots requires an acceptance that some may fail or bring with them unintended consequences, exposing FCDO to risk. The TA, which entails direct engagement with government can be applied in an agile and politically informed way and helps contribute to UK additionality, bringing potential high reward but also high risk. These risks can be managed by the governance mechanism and by ensuring a clear approach to testing, learning and adapting. The MEL component will be integrated into ZAMBRIDGE. This will underpin the whole programme and synthesise learning, assess impact, support programme adaptation and provide evidence that seeks to inform future government investments and ensure the programme is more than the sum of its parts.

Summary VFM For the Preferred Option

This option takes an innovative and multisectoral approach to tackling poverty that focusses on system strengthening and exchange of expertise. It introduces new investments and partnerships underpinned by strong monitoring, evaluation and learning to utilise evidence alongside voices for change to expand opportunities for pathways out of poverty – particularly for the poorest. At the same time, it balances these higher-risk activities, with lower risk investments through multilaterals to consolidate and strengthen the shock responsiveness of existing systems that protect the poorest and most vulnerable.

There is strong global evidence on the VFM of cash transfers and their impact on reducing poverty. Cash transfers are assessed as being a development ‘Good Buy’ in reducing poverty as assessed by the FCDO Chief Economist’s office, as part of their Best Buys analysis. They also deliver very good VFM, as regular cash transfers, if well designed, have benefit cost ratios of 1.8 – 6.2 ex-post.[39] Cash transfers are one of the most effective mechanisms for directly reaching poor and vulnerable people, at scale, are shown in multiple studies to be generally well used by recipients, and are a more dignified form of assistance, empowering recipients with more choice than in-kind transfers. Their effects go beyond the individuals or households receiving the cash transfers, to multiplier effects in the wider community. The Best Buys analysis in economic development also found cash transfers to be ‘high potential’ (evidence emerging but promising).
[39] FCDO, 2021 “Best Buys in improving incomes for the poorest, focussing on social protection and agriculture.”

Consolidating and strengthening shock responsiveness of existing systems: Repeated impact evaluations of cash transfers in Zambia have shown that the government’s SCT programme is effective in alleviating poverty, with a return of £1.87 for every pound spent.[40] Cash transfers are considered a “Good Buy” by the FCDO, meaning there is strong evidence of cost-effectiveness across many contexts. Specifically, the “Best Buys” work reports that there is long-term impact of regular unconditional cash transfers for those still in receipt of payments in Zambia. Further, the evidence finds that if income gains from cash transfers do not persist over time, they still represent good value for money and there are little negative spillover effects to non-recipients.[41] From a humanitarian perspective, cash transfers are considered a ‘best buy’, and are highly cost effective because they allow people to buy the goods and services they need through local markets and are characterised by flexibility that would be hard to match through in-kind responses that do not account for the varied needs of households. A well-functioning emergency cash transfer system that can be initiated rapidly will be faster and more effective than other types of humanitarian assistance.
[40] American Institutes for Research. (2014). Zambia’s Child Grant Program: 36-month impact report.
[41] FCDO Economics and Evaluation Unit (2021). Best Buys in improving incomes for the poorest, focusing on social protection and agriculture.

Investing in education systems is good VfM and one of the is one of the most important investments to harness human capital for long term growth and prosperity. Each additional year of schooling can raise a person's earnings by about 10%,[42] making education an effective tool for poverty reduction. In particular, a focus on foundational learning and the skills gained in the early years of school, has evidence of long-term impact. The returns to education are large and cross-sectoral. Education, and specifically foundational numeracy and literacy skills, are a key driver of economic outcomes.[43] Recent evidence shows that foundational literacy and numeracy skills directly increase earnings in adulthood.[44] As an approach, working to support the existing government systems is very likely to deliver higher VfM – public money accounts for the vast majority of expenditure in the education sector.[45] There is big potential, therefore, for small, agile projects which can influence the quality of public spending on education.
[42] Education Overview: Development news, research, data | World Bank
[43] Kaffenberger et al. 2025. The benefits of foundational learning to individuals and society: A review of the evidence. What Works Hub for Global Education.
[44] “a one standard deviation difference in foundational skills is associated with an 11 percent increase in adult earnings”. Crawfurd, 2025. The Economic Returns to Foundational Literacy and Numeracy: Evidence from Indonesia. CGD.
[45] The education share of the GRZ budget has increased substantially: from 10.4% (2022) to 15.4% (2024). The MoE budget in 2025 was K28.6 billion (approx. $1bn). ODA to Zambia’s education sector has never exceeded $90m, in 2023 it was $52m.

Testing innovations and gathering evidence through pilots presents good VFM as interventions can be tested, refined, and scaled to find cost-effective solutions before committing significant resources. Targeted, well-monitored pilot projects have high potential to lead to higher long-term cost-effectiveness, reduced implementation risks, and better outcomes for poverty reduction. Initiatives piloted through ZAMBRIDGE will be assessed based on their potential VFM before being approved. FCDO’s Best Buys work will be a key resource in assessing the VFM of interventions proposed.

While option 3 has the highest risk and high management costs, our assessment is that the potential for changing the poverty trajectory is sufficient to justify the additional costs and therefore represents good VFM. The FCDO advisory roles required to support this option enable FCDO to draw on our strengths as policy leaders, and positions FCDO to seize opportunities to catalyse and get behind change.

1. Option 3 is the recommended approach, presenting the most agile and impactful model for implementation of the outputs to address the need set out in the strategic case. This package of interventions will:
  1. draw on UK technical expertise, political analysis and diplomacy to drive forward improvements in GRZ policy, programming and strengthen opportunities for pathways out of poverty
  2. support Zambian leadership, consolidating and building upon systems through genuine partnership
  3. deliver impact at scale through the multilateral investments
  4. innovate to seek new approaches to improve human development and economic opportunities, particularly for women and girls.
  5. ensure the programme can be launched with ‘quick start’ options, and targets UK priority results while maintaining the capacity to further develop the portfolio of intervention
  6. keep FCDO at the policy table to influence the direction of the multilateral investments but reduces the size of the contribution to the multilateral funds, enabling greater UK influence and agility
  7. put women and girls’ empowerment at the centre.

Components of the preferred option

Multilateral Investments
GEWEL
(World Bank)
UNJPSP
(UNICEF)
Direct Partnerships
Research and Evidence partner
Shock response partner
Pilot inclusive growth partner
Consultancy projects e.g. FRA
ZAMBRIDGE
Political Analysls Hub
Technical
assistance
Innovative
pilots
Monitoring, evaluation and learning

Theory of Change

The draft Theory of Change (ToC) of the programme is summarised in the diagram in the strategic case, and will be further refined during the inception phase of this programme.

The ToC is that ZPRP will reduce multi-dimensional poverty, vulnerability and inequality in Zambia by taking a ‘floor’ and ‘ladder’ approach to support pathways out of poverty. Investing in GRZ’s social protection system and strengthening the shock response and recovery systems through targeted, high quality technical assistance, and shaping evidence based policy-making will contribute to more sustainable, effective shock responsive systems that better protect the poorest and enhance resilience of the most vulnerable people in Zambia. In parallel, investments in innovative pilots, accompanied by politically informed and high-quality technical assistance will improve economic opportunities for the poorest, and strengthen systems to improve the quality of human development services, leading to expanded human capital development and opportunities for the poorest, which will help to unlock human capital to support inclusive growth. ZPRP will ‘think and work politically’, this includes supporting voices of change to increase the public, media and political support for pro-poor policies to drive sustainable and locally led poverty reduction through modern development partnerships. Empowerment and inclusion of women and girls will be mainstreamed throughout the programme and women and girls will be targeted through specific interventions such as supporting women’s livelihoods.

MEASURES USED TO ASSESS VFM

1. Value for money (VFM) in this programme will be assessed at two levels:
  1. The overall system level. As a key objective of the programme is to improve the effectiveness of delivery through better use of evidence and innovative approaches, we will monitor whether the poverty reduction systems, and specifically whether the SCTs and cash plus interventions, are becoming more costs effective.
  2. Direct delivery i.e. whether the activities that we are funding directly are delivering good VFM.

The literature on SCTs emphasises key determinants of cost-effectiveness are the size, duration and frequency of the transfer; how well the targeting mechanism is designed and implemented; and implementation systems (including registration and enrolment, payment mechanism, management information, grievance mechanisms)[46]. These will all be considered as part of our monitoring. VFM assessments for other aspects of the programme are newer and less well documented, therefore VFM analysis for these dimensions will be further developed during the programme.
[46] IBID

The approach to VFM of this programme will evolve as the agreements are put in place with the delivery partners and the inception phases begin. Key VFM metrics will be reflected in the logframe, and progress against these will be monitored during each annual review, alongside a portfolio level assessment of VFM. Approaches, principles and examples of some of the metrics that could be used are presented in the table below.

 Table 7: VFM Approaches, Principles and Possible Metrics
	VFM approaches and principles	Examples of possible metrics
Economy	The management structure is streamlined (relative to programme complexity), minimising overhead costs. / Where possible, overhead costs will be fixed as a percentage of programme costs. / Where appropriate (e.g. GEWEL), deliver at scale.	Total management and overhead costs as a percentage of the total programme cost. / The cost per learner of education initiatives.
Efficiency	Promising pilots are scaled, while less successful pilots are stopped early to deliver effective performance management. / Work through existing well-established multilateral models where there is high Zambian Government ownership and momentum, across all public service delivery sectors. / Take a holistic and coordinated approach to poverty reduction, including by leveraging existing initiatives to connect social protection beneficiaries to cash plus initiatives and essential services. / Invest in utilising and scaling up timely digital payments to beneficiaries.	The number of pilots scaled or stopped early. / Total cost transfer ratio of SCT (total cost transfer ratio of administration or non-transfer costs of GRZ’s SCT programme in 2023 was 1.2 which is excellent when compared to regional benchmarks) / % of total payments made digitally and on time / Number of ministries utilising the social registry / Costs per teacher or education official trained
Effectiveness	The size of the transfer value is sufficient to increase household food security and prevent negative coping mechanisms. / Monitor beneficiary feedback to assess effectiveness of interventions.	Transfer value of SCT per beneficiary household as a percentage of household consumption and percentage of GDP per capita. / Number of cases where activities designed (including TA) have led to changes in government policy or programming. / Percentage of SCT budget funded by Government of Zambia / Improvements in learning outcomes (foundational literacy and numeracy)
Equity	Target interventions to deliver improved outcomes for women and marginalised groups, including people with a disability. / Target interventions to deliver improved outcomes for the poorest people.	Percentage of targeted SCT beneficiaries who are women (at least 70%). / Percentage of SCT beneficiaries living with a disability. / Number of research and evidence pieces specifically focussed on marginalised groups. / Number of girls receiving regular payments through the keeping girls in school cash plus programme and/or participating in the TaRL programme. / Gender and disability disaggregation of education outcomes.

In summary, it is recommended that the UK invests £38,500,000 in this programme. Reducing poverty and inequality and investing in human capital development to drive inclusive growth and enhancing preparedness and resilience to shocks are priorities for the UK and the Government of Zambia. ZPRP will complement UK investments in economic development, climate and resilience, and strengthening democracy and governance. The activities will be delivered through a hybrid model comprising ZAMBRIDGE; investments in well-established multilateral programmes working with and through government systems; and direct partnerships to embed research and evidence and maintain flexibility. The programme will have a strong focus on enhancing response to shocks through locally led humanitarian systems, demonstrating UK added value, ensuring Zambian leadership through genuine partnership, and facilitating innovation and agility.

Commercial Case

The appraisal case has set out the rationale for the preferred mechanism to deliver ZPRP through option 3: ZAMBRIDGE; use of well-established multilateral partners; and a direct partnerships facility. ZPRP will therefore be delivered through a combination of a commercial contract, MOUs and accountable grants. These models for implementation have been identified based on lessons learned through previous human development and social protection programmes. This hybrid approach will enable FCDO to deliver impact through tried and tested approaches with multilateral partners, while simultaneously building the evidence base and innovating with new partners.

The overall combination of delivery models provides the optimal package to enable the programme to respond quickly to shocks, be agile to seize opportunities to support change, to strengthen existing systems and to innovate, test and adapt new, and riskier initiatives. This section outlines the commercial rationale for each of the chosen delivery mechanisms.

Table 8: Components and Modality

Component	Allocation	Scope	Modality
1.ZPRP ZAMBRIDGE	£13.6 million	Political analysis hub / Technical assistance / Innovative pilots / MEL / Multi-sectoral: education, nutrition, SRH, humanitarian	Contract – competition through framework or open
2A. World Bank MDTF GEWEL	£11 million	Cash payments for cash plus (SWL) as part of Social Protection system strengthening / Technical assistance for system strengthening, shock response and cash plus initiatives	MoU
2B. UN joint programme UNJPSP	£4.3 million	Technical assistance to for policy and implementation support	MoU
3. Direct partnerships facility	£8 million	Shock response fund, research and evidence, including Fiduciary Risk Assessment/Annual Statement of Progress where funding goes through government systems	Accountable grants and low value direct contracts
4.Programme funded roles to enable delivery	£1.6 million	1 UK based Adviser / 1 Country based Adviser	See management case

Component 1: Zambia - Building Resilience, Inclusive Development, Growth and Evidence (ZAMBRIDGE)

This component will be procured through a commercial contract to give FCDO the control needed to direct the supplier’s work by pre-defining clear deliverables and actively managing supplier performance through a schedule of payments aligned with delivery against FCDO priorities. We will contract a managed fund to provide flexible support for expertise (including embedded TA to government) and sub-contracted partnerships, including with local partners to deliver pilots and innovations linked to the programme outputs and outcomes as well as undertaking MEL. At the heart of ZAMBRIDGE will be a political analysis hub which informs a thinking and working politically approach, seeks to identify and support opportunities and coalitions for change. The managed fund will work in close partnership with the FCDO programme team to design and deliver activities (see management case). It will also strengthen the VFM and impact of multilateral investments under component 2. ZAMBRIDGE will work across a range of sectors - which may include humanitarian preparedness, education, health, nutrition – it will get behind opportunities to support change.

An Early Market Engagement (EME) held in March 2024 was attended by over 100 participants from a range of organisations including private sector, small to medium enterprises, local and international NGOs, civil society and academia. The event provided FCDO with a greater understanding of the market to source from within a mixed economy of competitive market. The EME provided insight into how best to measure success and results, risks and the preferred route to market. EME participants indicated their preference in the routes to market, either the FCDO’s Global Development Delivery (GDD) (47%) or open (53%), showing that there is sufficient capacity and interest for the GDD.

The GDD has two lots that would cover the scope of this component: Lot 2 Health & Humanitarian; and Lot 3 Education, Gender and Social Inclusion. The alternative route to market is via open / restricted route. Lot 2 has 13 suppliers and Lot 3 has 15 suppliers. The framework usually takes 12-16 weeks from signing the terms of reference (ToR) and the tender pack to the contract award. The open route would take 16 – 36 weeks to reach the award of the contract based on the strict phases and complexity. There has been strong engagement from bidders on the framework to date and we anticipate that strong interest will remain. Interest remains with parties who have registered on the sourcing portal to access a copy of the slides and post event summary of the EME.

The timing of the competitive process is being considered to ensure there is sufficient capacity and interest from potential bidders which does not clash with other FCDO requirements. This will continue to be monitored by FCDO’s Commercial team and will determine the final route to market. The ODA pipeline has been updated and issued as part of Cabinet Office transparency requirements – this has up to date timings of likely readiness to tender. The framework is time and cost efficient in comparison to the open / restricted route to market and will support programme’s intentions to ensure a rapid start-up of the contract. Whilst suppliers on the GDD have pre-approved sub-contract partners there is also potential to for suppliers to work with local downstream partners too once due diligence and compliance with UK legislation has been assessed and approved.

The FCDO team intends to run a further EME process as the terms of reference is being developed to ensure sufficient capacity and interest, and to gauge competition. Another EME will help to strengthen VFM by increasing the competition and driving up the quality, and driving down the market price. The commercial contract will include break clauses as well as a provision to increase the contract by up to 50% in cost without re-tender in the case that the overall Business Case is extended or other significant amendments are made.

Performance monitoring and management

Key Performance Indicators (KPIs): KPIs will be used to incentivise supplier performance (and linked to payment). These will include ‘Delivery KPIs’ (relating to delivery of outputs and outcomes) and ‘Contract KPIs’ (relating to contract management performance). FCDO is acutely aware of the risk of setting perverse incentives through the KPIs (e.g. by linking payment to the quantity of outputs, rather than the quality); this will be a key consideration in the design of the KPIs.

Reporting requirements: A strong reporting framework verified by field visits and spot checks by FCDO will be established to monitor and enhance partner capacity. The contract will specify reporting requirements, including quarterly progress reports to monitor activities and spending, annual work plans and results pathways, annual and mid-term reviews, project completion reports, quarterly financial forecasts and bi-annual financial expenditure reports.

Break clauses: ZAMBRIDGE will be designed to operate in a flexible and agile manner, therefore the contract will be structured to reflect this. The contract will include break clauses allowing for termination after inception if partner performance is unsatisfactory. Clear review points will be built into the contract, including the end of the inception period, after Zambia’s 2026 election and two years after the election (2028). The contract will also allow for termination in the event of changes in the UK’s financial position or profound changes in the political environment which mean that progress towards the outcomes is unviable.

Component 2: Multilateral Investments

The second component, ‘multilateral investments’ will be implemented through two delivery partners A) the World Bank; and B) UNICEF. As outlined in the appraisal case, there are two leading programmes working with and through government systems to deliver and strengthen the social protection ‘floor’ and ‘ladder’. These two programmes GEWEL (World Bank led) and UNJPSP (UNICEF led) have successfully delivered results through their most recent phases. ZPRP will consolidate and build on progress made through previous FCDO investments to deliver impact at scale and influence government policy and programming. FCDO will continue to play the role of engaged reformer to shape and leverage multilateral investments.

This component is designed to provide flexibility, enabling FCDO to respond to shocks, budget changes and strategic priorities during the lifespan of the programme. FCDO will have direct MoUs with the respective partners based on indicative commitments (‘up to’) that can be adjusted according to the need.

As part of the initiation of new multilateral investments, a review of administration and management costs, unit costs and results of these programmes will be conducted to ensure value for money of both multilateral delivery channels. Both partnerships will take a ‘soft ringfencing’ approach which will enable UK investments to be allocated to specific areas of the programme based on the UK’s strategic interests, including to support humanitarian activities.

Component A - Girls’ Education and Women’s Empowerment and Livelihoods Project (GEWEL), led by the World Bank: GEWEL commenced in August 2024 and is an IDA-funded programme (total $150 million IDA) with an integrated multi-donor trust fund (MDTF). Initially designed as a four-year project, it is expected that GEWEL is likely to be extended or supplemented.

Component 2 B - UN Joint Programme on Social Protection (UNJPSP), led by UNICEF: complements the GEWEL programme through provision of policy advice, technical assistance and piloting approaches which can be scaled. A £20m - £25m UNJPSP programme will run from 2025 – 2029, building on the strong relationship and trust with GRZ.

Performance monitoring and management

Results framework: A clear results framework that aligns with national development objectives will be developed and implemented for the respective projects, with key indicators also captured in the FCDO logframe. Progress against the indicators will be monitored by the dedicated monitoring and evaluation leads within the respective projects. Evaluation and learning will be conducted by the ZAMBRIDGE MEL unit which will synthesise evaluations and impact assessments to inform decision making at key points during the programme, including annual reviews. ZAMBRIDGE’s MEL unit will also use evidence from the multilaterals to undertake analysis on graduation and pathways out of poverty.

Reporting requirements: A strong reporting framework verified by field visits and spot checks by FCDO will be established to monitor and enhance partner capacity. The MoU will specify reporting requirements, including quarterly progress reports to monitor activities and spending, annual work plans and results pathways, annual and mid-term reviews, project completion reports, quarterly financial forecasts and bi-annual financial expenditure reports.

GEWEL: The World Bank will lead six-monthly GEWEL missions which provide opportunities to take stock of progress, reflect on lessons learned and adapt the programme accordingly. GEWEL will place a strong emphasis on documenting lessons learned, conducting process and impact evaluations and generating insights for ongoing improvement of project activities and informing policy development. The Donor Coordination Focal Point will support strategic engagement with the GRZ and high-level coordination of GEWEL interventions and relevant government policies to support a system that is fully led and implemented by the GRZ.

UNJPSP: This project will operate in a similar approach to phase II, which included quarterly steering committee meetings to reflect on progress against the workplan and milestones, and the Joint Annual Review (JAR). As of August 2025, the concept note has been approved and the workplan and results framework are still under development. Cooperating Partners (CP) groups such as the Climate and Environment CP or Social Protection CP groups provide important opportunities to ensure a strong multisectoral approach.

Component 3: Direct Partnerships
This component will enable FCDO to hold accountable grants, MoUs or low value contracts directly with partners to complement ZAMBRIDGE and the multilateral partnerships. Direct partnerships provide a flexible tool to prepare for and respond to humanitarian shocks. An accountable grant to undertake in-depth research on poverty reduction and to shape evidence-based policy making will comprise one of the first partnerships through this component to support the inception phase of ZAMBRIDGE. Although the other funding arrangements under this component will not be allocated at this stage of the programme, we anticipate that this is likely to include partnership(s) directly responding to shocks; procurement of consultants to undertake the Annual Statement of Progress on the Fiduciary Risk Assessment where funds are channelled through government systems; and innovative pilots not being funded through ZAMBRIDGE. Tasks such as the fiduciary risk assessment will be procured through FCDOs Global Development Delivery (GDD) Framework or other suitable drawdown frameworks.

The number of partnerships held through this component at any one time will be carefully aligned with the programme management capacity. Where appropriate, decisions regarding direct partnerships under this component will be made by the ZPRP Steering Committee to ensure alignment with the wider programme.

As outlined in the appraisal case, the FCDO has strong added value in convening, driving forward policy priorities and using small funds to get behind change. To manage these components effectively and maximise their impact it will be essential to fund advisory roles, to undertake the complementary policy engagement and development diplomacy. Advisers will also be pivotal in leveraging other UK financing through CMPs and Centres of Expertise that deliver on human development outcomes for women and girls such as SCALE and WISH, as well as drawing on FCDO’s global partnerships such as the Global Partnership for Education (GPE) and the Global Financing Facility (GFF) to complement investments. This will ensure that FCDO maximises the collective impact of its investments towards delivery of the UK’s Country Business Plan in Zambia.

How FCDO will ensure Value for Money through these components:
FCDO will identify key VFM metrics and reflect these in the programme logframe. VFM will be assessed in all proposals and VFM criteria will form part of the criteria for evaluating the commercial contract bid. Key approaches to VFM are set out below for the three components across the 4 Es, economy, efficiency, equity and effectiveness. Further detail on VFM is presented in the Appraisal Case. This assessment is informed by the BHC Lusaka VFM Strategy.

1. Economy: FCDO will assess how partners manage economy throughout the programme.
  1. Commercial supplier/ZAMBRIDGE: FCDO can achieve economy by pre-agreeing limits for programme staff costs (international and local) and administrative charges for travel, overheads and training.
  2. Multilateral investments: FCDO will undertake a review of the administrative costs and management costs, unit costs and results to ensure value for money of both multilateral delivery channels. Delivery at scale will facilitate good economy.
  3. Direct partnerships: FCDO will assess proposals based on their costs alongside the quality of the proposals and experience of consultants proposed.

1. Efficiency: FCDO will build strong, streamlined management systems (including the Programme Steering Committee) that bring all elements of the programme together.
  1. Commercial supplier/ZAMBRIDGE: Ensuring a highly competent Team Leader and team capable of managing a diverse portfolio will be crucial to establishing efficiency in the programme. Designing and operationalising management structures that enable ZAMBRIDGE to pivot quickly and close less effective initiatives will be essential to efficient delivery.
  2. Multilateral investments: This model will seek to strengthen government systems through well-established multilateral programmes which present an efficient model with high levels of government ownership. We will build on learning to date and capitalise on partners’ existing structures and ways of working to enable rapid, high-quality delivery.
  3. Direct partnerships: This model allows for a more agile and timely response to local challenges and the administrative overheads will be lower for direct partnerships compared with the cost of funding through intermediaries.

1. Equity: This programme directly targets the poorest and most vulnerable, with a strong focus on the human development of women and girls.
  1. The overarching intended impact is to reduce multidimensional poverty and inequality.
  2. All activities must demonstrate how they deliver for the most marginalised groups including women, girls and people with disabilities.

1. Effectiveness: ZPRP will be effective if investments successfully contribute to reducing multidimensional poverty and inequality in Zambia.
  1. Commercial supplier/ZAMBRIDGE: Investments in TA and innovative pilots will be successful if they can demonstrate successful approaches to improving economic opportunities and human development outcomes for women and girls that can be scaled; and success will also be demonstrated by working with government to improve the utilisation of essential services; and being able to support coalitions of change to increase support for pro-poor policies in Zambia. Suppliers’ bids will be assessed based on their ability to do this.
  2. Multilateral: Previous multilateral programmes to support the floor and ladder of social protection have demonstrated their success and effectiveness in achieving the intended results through government systems and at scale. However, these are accompanied by relatively high administration costs. ZPRP will be successful if FCDO can use its seat at the table to influence these largescale funds.
  3. Direct Partnerships: This approach allows investments to align closely with local priorities to deliver on poverty reduction priorities and provides flexibility to respond to shocks. This flexible model enables FCDO to direct funds where we assess strong opportunities to successfully influence policy.

Financial Case

Costs profile and forecasting
This section sets out the affordability, sources of funding and budget for the programme, including demonstrating how the budget could adapt to changing context if required. It describes the mechanisms for disbursement, reporting requirements and FCDO’s assurance framework.

1. FCDO will invest up to £38.5 million in the ZPRP over six years. The programme is designed to enable flexibility to respond to changing needs (namely humanitarian crises, context, and assessments of opportunities to influence and get behind change, final project proposals of downstream partners and GRZ and ODA budget) during the programme life cycle. To maintain flexibility allocations will be revised based on Programme Steering Committee (PSC) agreements and the programme will have flexible components which can be scaled up or down if required. The initial allocation is based on a costing exercise that sought to:
  1. ensure programme funding is allocated to areas where there is strong UK additionality e.g. innovation, technical assistance, humanitarian preparedness, direct partnerships and programme funded roles.
  2. balance investment in riskier components (e.g. pilots) with those that are well-established (e.g. multilateral funds).
  3. Funding for the ZPRP has been included under the ODA framework allocation for BHC Lusaka. The ZPRP budget will be classified as Resource Departmental Expenditure Limit (RDEL), and we expect this programme to have none, or only very limited spend classified as Capital Department Expenditure Limit (CDEL). The programme will include humanitarian RDEL which will be determined by FCDO ODA allocations and will be spent in line with humanitarian sector code guidance. FCDO will confirm partners’ budgets annually to ensure the programme remains affordable within BHC Lusaka’s delegated ODA budget for the Spending Review period. To manage unforeseen changes in the UK’s financial context, break clauses will be included in all contracts. Accountable Grants and MoU do not legally commit the UK to providing funds. Following programme approval, BHC Lusaka will seek HMT approval for financial commitments beyond the existing spending period. The multilateral partner component and the direct partnerships component are the component which provide the most flexibility to scale up or down as required during the lifetime of the programme.

1. It is anticipated that spend under the ZPRP will contribute to the UK’s International Climate Finance (ICF) target. ZPRP will increase Zambia’s resilience to climate change by supporting the GRZ to deliver for those most affected including people living in poverty, women and girls, people with disabilities and marginalised groups. ICF KPIs will be included in the log frame to track the contribution that ZPRP is making to the UK’s ICF target. An independent review of GEWEL’s contribution to climate resilience has been commissioned by FCDO and will help to inform the project’s contribution to achieving ICF indicators as well as the methodology used to assess this. The programme will complement BHC Lusaka’s planned programme on climate resilience. ZPRP will contribute to the following ICF KPIs:
  1. ICF KPI 1: Number of people supported to better adapt to the effects of climate change as a result of ICF.
  2. ICF KPI 4: Number of people whose resilience has been improved as a result of ICF.
  3. And, potentially to ICF KPI 11: Volume of public finance mobilised for climate change purposes as a result of ICF.

The table below presents the budget profiling of the components.
Table 9: Breakdown of Expenditure by Component for Each Financial Year
Component	Inputs	Allocation (in millions £)	FY 1 / 2025/2026	FY 2 / 2026/2027	FY 3 / 2027/2028	FY 4 / 2028/2029	FY5 / 2029/2030	FY6 / 2030/2031
1.Technical Assistance and Innovation Facility – ZAMBRIDGE / (£13.6m)	Political Analysis Hub	2.4		0.3	0.6	0.6	0.6	0.3
	TA to national and local government	2.2		0.2	0.6	0.6	0.5	0.3
	Innovative pilots	6.5		1	1.5	1.5	1.5	1
	Monitoring, evaluation and learning	2.5		0.4	0.5	0.5	0.6	0.5
2.Multilateral investments / (£15.3m)	A. World Bank MDTF GEWEL	11	2	3	2	3	1	0

	B. UNICEF – UNJPSP	4.3	0	1.3	2	1	0	0
3.Direct partnerships / (£8m)	3. Direct partnerships	8	0	1.6	1.6	1.5	2	1.3

4.Programme funded roles / (£1.6m)	4.Programme funded roles to enable delivery	1.6	0.1	0.3	0.3	0.3	0.3	0.3

	TOTAL	£38.50	2.1	8.1	9.1	9	6.5	3.7

ZAMBRIDGE: This component will comprise 35% of the total programme budget, or 13.6 million. ZAMBRIDGE will be the most innovative part of the programme and reflects FCDO’s ambition to drive forward new ideas and solutions to tackle poverty. The first year (FY1 and FY2) will be dedicated to procurement of the commercial contract and inception phase, therefore we expect expenditure to be low in FY1 and FY2, but will launch into ‘quick start’ activities at the end of FY 26/27. For planning purposes, FCDO has used tentative allocations, but we will not stipulate these amounts in the Terms of Reference to drive competition amongst suppliers. Spend on the TA and pilots will vary depending on BHC Lusaka’s delegated ODA budget, but for planning purposes a consistent level of spend is profiled following the inception year. Break clauses in the contract will enable flexibility to respond to changes in budgets or context and will allow for termination of the contract.

Multilateral investments: The previous phases of GEWEL and UNJPSP are well-established, therefore this component provides reliable delivery channels through which annual contributions will be made to pooled funds. These are also one of the most flexible instruments, where FCDO can scale up or down as required to respond to changing contexts.

2A World Bank, GEWEL: FCDO’s contribution to the first phase of GEWEL comprised approximately 62% of the total budget for FCDO’s Social Protection Expansion Programme (2016-2025). Given the strategic decision to reduce multilateral contributions and expand other investments in human capital development and areas of UK added value, the contribution to GEWEL will reduce as an overall percentage of the programme. We will provide indicative budget allocations to the partner and will confirm allocations (which may be lower or higher than the indicative allocation) on an annual basis once post budget allocations have been confirmed. Contributions can be made to this pooled fund in FY 2025/26.

2B UNICEF, UNJPSP: FCDO’s contribution to the second phase of UNJPSP comprised approximately 32% of the total budget for FCDO’s Social Protection Expansion Programme (2016-2025). This will comprise a much smaller share under ZPRP (around 11%). This project is in the design phase but is expected to be operational by early 2026. A smaller contribution will be made in the first and final year of the project’s implementation as these are the years where there will be less activity. We will provide indicative budget allocations to the partner and will confirm allocations (which may be lower or higher than the indicative allocation) on an annual basis once post budget allocations have been confirmed. Payments made will be subject to satisfactory progress.

Direct Partnerships will comprise approximately 21% of the budget and will vary during the programme period. FCDO will seek to establish a research and evidence partnership early in the programme which will continue throughout the programme period. Other partnerships such as locally led disaster preparedness and responses to shocks, or technical assistance to strengthen education systems, or pilots will likely have a shorter period of implementation and will not be up and running in the first six months of the programme. This is a flexible tool holding Accountable Grants (AGs) with partners. AGs will specify that budget allocations may change during the lifespan of the agreement.

Programme funded posts are essential to the success of the programme. They are likely to have a smaller spend in the first and final year due to the time taken to recruit the right candidates and the likelihood that some may leave before the end of the programme as their employment is not guaranteed.
Payment process
All payments will be denominated in GB pound sterling. We will require all partners to monitor and manage exchange rate losses and gains, as per FCDO budget policy. This is crucial given the likelihood of fluctuations in the Zambian Kwacha.

ZAMBRIDGE Commercial Contract, and any other contracts through the direct partnerships: payment will be made, in part, based on delivery of KPIs. The proportion of payment linked to KPIs will be agreed once further engagement with the market has taken place. The Terms of Reference for both contracts will stipulate performance-related pay mechanisms for both inception and implementation phases (based on achievement of agreed milestones and delivery of KPIs). Break clauses will be included in contracts.

Multilateral partners with Memorandums of Understanding: partners must provide detailed financial reports that set out actual expenditure to date against the approved budget and quarterly forecast expenditure for FCDO’s financial year.

Partners with Accountable Grants under the direct partnerships component: payment will be contingent upon submission of satisfactory progress report, expenditure report, costed work-plan, invoice and forecast expenditure for FCDOs financial year. FCDO will provide up to three months of advance funding provided we are satisfied with the forecasts for the forthcoming quarter. No payments will be made in advance of need. Partners will adhere to FCDO’s Eligible Cost Guidance for Accountable Grants, including for Non-Project Attributable Costs (NPAC).

Fiduciary risk and fraud
1. FCDO operates in an environment that is susceptible to fraud and financial mismanagement. In line with FCDO’s ‘Counter Fraud and Aid Diversion Action Plan’, our approach will ensure that systems and processes across the programme are fit for purpose. We will ensure adequate controls are in place that adhere to legislative and policy requirements, including in support of FCDO’s zero tolerance approach to fraud. Detailed mitigation measures will be taken to reduce the likelihood and impact of fiduciary risks. These include:
  1. Undertaking fit-for-purpose due diligence assessments (DDAs). FCDO will conduct DDAs on all direct partners. As part of the tendering and contracting process, FCDO’s Procurement Department will conduct DDAs of suppliers. We will implement due diligence action plans arising from DDAs. For downstream partners, we will require assurances that DDAs have been completed which assess that partners have adequate financial, audit and fraud reporting systems in place.
  2. Delivery chain risk mapping exercises will be completed to assess risks throughout the flow of funds. Partners will be reviewed at every Annual Review and verified through spot-checks and field visits.
  3. Given the higher level of financial risk carried in the flow of funds to government systems through the World Bank and UNICEF, in addition to central assurances, measures will be taken to monitor the flow of funds through the multilateral projects. This will include conducting an Annual Statement of Progress to assess progress on the Fiduciary Risk Assessment (FRA) and identify new risks. A new FRA will be undertaken when there is a wider or different portfolio of work that merits a fresh FRA. Annual Statements of Progress will also be undertaken on any new FRA.
  4. All partners will be required to share information on all allegations of fraud and corruption cases as per FCDO policy. We will promote an open and proactive approach to fraud with our partners, including through biannual events hosted by FCDO to discuss responsibilities with partners as well as regular programme meetings with partners.
  5. FCDO will scrutinise all financial reports on receipt and prior to making further payments. Partners’ spend will be assessed at least quarterly to reduce the risk of financial mismanagement.
  6. FCDO will require the return of funds that cannot be adequately accounted for.
  7. All partners will be required to submit annual audited financial statements, conducted by an independent and qualified audit firm.
  8. If concerns arise, the FCDO reserves the right to conduct a special audit of the funds at any point in time. If concerns remain, the FCDO will consider suspension or termination in full or in part, will stop further disbursements and reclaim any funds already paid that have been used in a manner that is inconsistent with FCDO policies or contractual and grant agreements.
  9. FCDO and partners will maintain programme risk registers to continually assess fiduciary risks. Risk registers are reviewed and discussed with partners at least quarterly.
  10. Timely use of FCDO tools including Delivery Plan, Logframe, VFM framework, Annual Reviews and evaluations through the lifetime of the programme.

Asset management
All partners will be required to maintain an up-to-date asset register of all assets purchased using UK funds. The register will be submitted to FCDO annually. FCDO will conduct annual asset spot-checks of all partners and expect direct partners to do the same for their downstream partners. FCDO will ensure that the disposal of any assets at the end of the programme maximises value for money in line with the FCDO Programme Operating Framework (PROF) rules.
## E. Management Case

Management arrangements for implementation

This section outlines the governance and management arrangements necessary for the successful delivery of this programme. This includes the monitoring and evaluation processes and how the management structure will contribute to promoting a joint approach to human capital development while strengthening adaptive social protection systems. It also sets out the approach to risk management.

The ZPRP programme will be managed by a team of programme management and advisory staff within BHC Lusaka’s Human Development Team. The team will meet the requirements of the PrOF by officially appointing a Senior Responsible Owner (SRO) and a Programme Responsible Owner (PRO) to manage the intervention. The SRO and PRO will seek support from key members of staff for advisory and programme management input.

As outlined in the Appraisal Case UK additionality is often achieved through FCDO’s in house advisory expertise in country and how these advisers utilise the central resources such as CMPs and diplomatic engagement to support and drive change in country. Therefore, it is essential that there is sufficient advisory and programme management capacity within the team to deliver impact.

Given the flexible nature of the programme, its complexity and multiple partnerships, it is anticipated that management of the programme will be time intensive and complex. This will require a strong programme management team. FCDO proposed that the programme is directly managed by FCDO (as opposed to appointing a fund manager). Direct programme management affords FCDO the greatest control of the programme, enables FCDO to use its added value through development diplomacy and represents better VFM than alternative management options. Based on the number of partners that the team is currently managing, FCDO assess that the team can manage up to 7 delivery partners and have concluded that the administrative burden is manageable. The composition of the team proposed to deliver the ZPRP Business Case is set out below:

Table 10: Roles and responsibilities

Role	Responsibility	Time (FTE)
Senior Responsible Owner	- Strategic oversight ensuring effective delivery of the programme, complementarity with other programmes and its contribution to the country business plan / - Overall leadership and decision maker for material changes, direction and programme adaptation	60%
Programme Responsible Owner	- Leadership within the programme to drive delivery of outputs and achievement of outcomes set out in the approved concept note and BC, and manage partner relationships / - Ensure PrOF compliance throughout the programme cycle / - Manage the programme finances and risks	60%
Lead Advisor	- Lead on technical inputs and support counterparts (GRZ and partners) on programme design and implementation / - Lead on policy engagement and development diplomacy	50%
Programme Manager	- Support delivery of project outputs / - Support programme management on risk and compliance issues / - Manage programme finances	80%
Programme Officer 1	- Support delivery of programme outputs / - Support programme finances / - Support programme management on risk and compliance	80%
Programme Officer 2	- Support delivery of programme outputs / - Support programme management on risk and compliance	20%
Human Development / Social Development Advisor	- Provide advisory inputs to delivery partners on women and girls empowerment and safeguarding / - Use emerging research and evidence for integrated approach to programming, ensuring synergies with other programmes in the portfolio	60%

Programme funded posts
Recent programmes have shown that FCDO’s advisory capacity and diplomacy have been essential in helping to translate evidence into policy change. To deliver on the high demand on advisory capacity, including branching out into more nascent policy areas, the programme will include two programme funded posts. They will be an essential resource to enable programme delivery. The roles will be technical in nature, providing advisory inputs on strategic direction, opportunities and risks as well as being at the forefront of disaster preparedness and responding to shocks, liaising with central humanitarian teams and resources. Sufficient advisory capacity is a key assumption in the logframe.

Previously BHC Lusaka have leveraged the Humanitarian Stabilisation Operations Team (HSOT) facility, however this approach is usually time bound and can be expensive. Whilst the HSOT facility may remain as suitable option to cover gaps and surge during emergencies, a programme funded post will be better suited to driving long term change in the sector and more appropriate to the Zambian context which faces a rising frequency of climate and health shocks. An in-house role will be more efficient, enable FCDO to respond quickly and better integrate shock response in the broader BHC portfolio, building long-term resilience and being able to flex when shocks are acute.

2 x Advisors / (UKBS and CBS)	Provide technical advice to deliver outputs and ensure linkages across the programme / Engage partners and other stakeholders in the education sector to support programme objectives / Lead on disaster risk preparedness, disaster risk financing and resilience building / Coordinate BHC’s response during shocks to find suitable financing options, coordinate with regional humanitarian leads and liaise with and support Zambian emergency infrastructure / Build linkages with UKHSA to support system strengthening in response to health shocks / Work closely to coordinate with BHC’s programming on climate resilience	100%

Given the importance of the ICF contribution within the programme, and strengthening resilience, response to and recovery from climate shocks the programme will utilise expertise from the Climate and Environment Adviser. The team will be supported by BHC Lusaka’s commercial, monitoring and evaluation, finance, compliance, health, economic, climate and environment, governance, and political staff. The Head of Mission and Development Director will provide strategic-level support. The team will also collaborate with the UK’s Health Security Agency to complement their work on strengthening systems and preparedness to improve public health security in Zambia.

Programme Governance

Strong programme governance will be essential to ensuring that the 4 delivery channels of ZPRP are aligned to deliver a coherent and coordinated approach to achieving the same end goal of reducing poverty, vulnerability and inequality in Zambia. The diagram below presents an overview of the intended programme governance structure. Detail on the operation of the Programme Steering Committee will be fleshed out further during the inception phase, however the text below provides an overview of the type of approach that we intend to take.

Figure 7: Diagram outlining key relationships and information flows

To support this process there will be a Programme Steering Committee (PSC) chaired by the BHC Lusaka Development Director. The PSC will meet every six months and members will include representatives with decision making authority from each of the partners, FCDO Lusaka Team Leaders (Green Growth, PGT and Finance and Delivery) as core committee members, with invitees from APEX (African Directorate) and the Desk Officer.

The PSC will have the capacity to call in external experts to review documents and provide technical inputs through ZAMBRIDGE, as well as advisers from the BHC Lusaka. The PSC will have two primary functions:
  1. Setting the strategic direction: The PSC will assess the operating context, political dynamics, opportunities and risks to guide the strategic direction. This will ensure the programme remains relevant, agile to opportunities to help drive change and aligned with UK priorities.
  2. Fostering coherence and integration: The PSC will be responsible for ensuring different interventions under ZPRP are coherent. The programme will harness the UK’s convening power to encourage coordination with other donors, cooperating partners and relevant ministries and units within the Government of Zambia through existing working groups, national steering groups and technical committees. The Terms of Reference for bilateral partners will also outline how partners are expected to integrate with GRZ and cooperating partner groups outside of the PSC.

The inception period will be used to test this model and further refine the nature of this committee and how it will operate with the wider programme governance structures and BHC Lusaka portfolio.

Coordination structures
Coordination with government: learning from programmes across BHC Lusaka has shown that the best way to drive change is to have a direct relationship with the government stakeholders at multiple levels and across the relevant sectors. This programme will draw on the expertise of in-house advisors to expand and maintain these relationships, influence and advise the relevant ministries, to bring UK technical expertise and practical support to the table. BHC Lusaka will engage regularly with government at senior levels (e.g. with Ministers, Permanent Secretaries, and Directors, including in the Treasury), as well as at the technical levels, and through joint field visits. These stakeholders will include well-established relationships such as those with Ministry of Community Development and Social Services, Ministry of Local Government, and the Ministry of Health, those more nascent, such as Gender Division, Office of the Vice President, and Disaster Management and Mitigation Unit and developing new relationships with ministries such as the Ministry of Green Economy, Ministry of Local Government and Rural Development. Engagement with district and provincial level representatives will be crucial to enhancing utilisation of essential services, and appropriate coordination structures will be developed as partnerships are established.

Cooperating partner (CP) coordination: The UK is an active participant in key human development CP groups including nutrition, health, education and the humanitarian coordination team. Previous experience, for example working through the nutrition cooperating partners groups has demonstrated the value of these technical groups to raise sectoral priorities with government and coordinate policy and programme objectives. One of the most active groups, is the Social Protection CP group, which has been chaired by FCDO in recent years, and which holds quarterly meetings with representatives from the Ministry of Community Development and Social Services to discuss priority issues and maintain strong relationships with government.

Multi-lateral coordination: The World Bank and UNICEF are the key agencies leading multilateral funds to strengthen coordination in poverty reduction policy and programming. The World Bank will support MCDSS to effectively coordinate the Human and Social Development Cluster under the 8NDP, operationalise the Social Protection Coordination Strategy and strengthen oversight and reporting capacity to update the Presidential Delivery Unit. Cross sectoral collaboration with cooperating partners will be crucial and a new donor coordination focal point included within the GEWEL structure is intended to strengthen policy coordination. GEWEL and UNJPSP will use existing institutional arrangements such as GEWEL 6-monthly missions; quarterly UNJPSP steering committee meetings; and Social Protection monthly CP meetings. This programme will utilise these structures to ensure that evidence-based learning emerging from partners is brought to the table and shapes decisions being made in these fora.

This programme will also seek to broaden its stakeholder group, identifying and engaging with new coalitions to drive change, including with civil society, the private sector, academics and others.

Within BHC Lusaka: given the multisectoral nature of this programme and its strong climate resilience component coordination within FCDO will enable FCDO to maximise its impact. This will be achieved through formal governance within the mission as outlined in figure 7 as well as ad hoc follow up with relevant colleagues.

Monitoring, Evaluation and Learning

Monitoring, evaluation and learning will be essential to ZPRP underpinning the whole programme. It will run continuously throughout the lifetime of the programme to ensure robust, real-time evidence supports programming decisions, leading to improved results and impact. This programme will adopt the PrOF template for logical framework (logframe) as the standard management tool for reviewing performance. Each partner will have their own performance monitoring framework which will feed into the overarching programme logframe. The programme will assess the performance of outputs, and test it with the theory of change, VfM, beneficiary feedback, risk assessment and financial management through robust annual reviews.

ZAMBRIDGE will play a key role in reflecting learning from the previous phases of FCDO’s human development and social protection. ZAMBRIDGE will assess findings from impact evaluations from the projects, and will forge linkages to CMPS, such as the WISH D programme focused on adolescent sexual and reproductive health. ZAMBRIDGE will be designed to identify areas of programming that are working and have the flexibility to innovate and develop the policy approach based on responsive support and testing what works.

The programme will hold learning meetings and conduct tailored research where necessary, responding to the demand of partners and programme gaps, to generate additional learning about the different interventions and the impact of human development and social protection initiatives. These learning opportunities will allow partners to learn from each other and understand how what they are doing is working towards the same outcomes.

Monitoring Progress and Results

The Human Development Team and the PSC will monitor the performance of partners through regular field visits (FCDO and Joint Donor/GRZ reviews), annual reviews as well as programme completion reviews. The PRO will ensure that activities are reviewed are part of the programme delivery plan. Monitoring will include:

- Verifying interventions are being delivered to a high quality, based on agreed standards.
- Verifying results through spot checks and interviews with beneficiaries (including to feed into governance decisions).
- Checking on fraud, fiduciary risk, and safeguarding through regular inspections and data verification interviews.
- Assessing data trends and emerging issues needing policy attention.
- Evaluating programme performance.
- Evaluating partner performance including of the programme insourced roles.

Partners will provide FCDO with high-quality quarterly monitoring updates as well as annual reports. These will indicate whether partners are on track to achieve the target results. A reporting template will be agreed with partners and will include a narrative report on progress made against the logframe indicators as well as dedicated sections on risk management, finances and VFM. The reports will be augmented by quarterly bilateral meetings with FCDO to monitor progress on the delivery of workplans, assess risks and key challenges to delivery, scrutinise financial management and identify issues that require escalation. These bilateral meetings will help inform the agenda for the PSC meetings.

The programme will have high standards for data disaggregation. Implementing partners will be required to disaggregate data at a minimum by geography, age, gender and disability. Feedback from all monitoring, evaluation and activity-based budgeting sources will help inform all the performance review processes defined above.

FCDO will monitor overall programme performance through Annual Reviews. The Annual Review will enable the PT to assess progress against the outputs and whether results are on track whether the components continue to represent VfM. Annual Reviews will be informed by desk-based reviews, third party monitoring reports, meetings with implementing and downstream partners, engagement with beneficiaries and with other key stakeholders.

Agile and Adaptive

ZAMBRIDGE will also support the FCDO team with ensuring the programme follows principles of flexible and shock responsive programming as appropriate. This will enable rapid scale up or reallocation of resources, or flex in the type of assistance, in response to unexpected shocks and changes in context such as climate or health.

ZPRP will use an adaptive approach selectively, in cases where there is insufficient evidence of the needs and pathways to change to have confidence that our investments will deliver the desired outcomes (for instance in our pilot interventions), or where the operating environment is fluid and is likely to demand an evolving approach. For projects which use an adaptive approach, partners will be expected to test different options before scaling (or failing) and use feedback loops to build the evidence base. This will require more intensive management and MEL (which will be agreed during the project design). The precise approach will be co- created with the supplier, building on FCDO’s experience of adaptive management in Zambia.

Box 4: Lessons Learned on Adaptive Management
Lessons Learned on Adaptative Management in Zambia
- For some partners, an adaptive way of working is new and can be challenging to implement. The decision to use this approach should be cognisant of the additional resources required to do it well, and weighed against opportunities where the pathway to change is clearer.
- Our greatest impact has been achieved when we focus externally on Zambia’s political economy, scanning for where change is happening. Where we have built informal coalitions to support change and got behind domestic change actors we can have good impact. When we do more general activities that are built around our priorities but not rooted in domestic change processes, we have sometimes achieved very little that is durable. Being aware of where change is happening and adapting to getting behind it is thus key.
- UK programmes contribute to governance reforms (causation) when they understand and act on leaders’ political base for reform. That is, when they think and work politically. There is a dizzying array of causal mechanisms through which political leaders find support for change but understanding the menu of these is key to understanding why key actors were motivated by the UK programmes to initiate or institutionalise reforms.
- Many reforms would have happened anyway without UK support. Other reforms are necessary but ultimately not in play. We add value in the “sweet spot” – where reforms could go either way, and UK support probably tipped the balance
- Scale matters. Adaptative projects can take significant time to design, implement, reflect and adapt. The output needs to be proportionate to the input to maximise efficiency.
- A certain level of decision-making must be delegated to the supplier. Day-to-day oversight by FCDO, in a changing context, is inefficient. Delegated authority levels must be clear.
- Leverage partners strengths. Partners integrate most effectively when they complement each other. Be clear on what value each partner adds so encourage joint working.
- Zambia isn’t homogenous. What works in some places, won’t work in others. When delivering at local levels, work with local partners who understand local dynamics and cultures. This approach also delivers value for money when operating across big distances.
- ‘Failing’ is a critical part of an adaptive programme, but it can be counterintuitive for partners. Willingness to fail will depend on the incentives partners have and the team, the ethos, relationships.

Scalability and Sustainability

This programme will work within the limit of available resources, which may change during the programme period. As a result, this programme has multiple options whereby the programme could be scaled up or down by adding or reducing the number of partners and/ or the size of funds. Some partners, such as the multilaterals will find it easier to scale up or down, as compared with smaller partners. Adaptations will be approved through Business Case Addendums, revisions to the logframe will be made and decisions will be captured in Annual Reviews.

ZPRP will work with a range of partners and will ensure that all partnerships have options to respond to different budget scenarios. Through the governance structures, partners will work closely with the Government to establish means of sustainability within the different elements of the programme.

The design of the ZAMBRIDGE will facilitate agile delivery within the boundaries of the commercial contract. This will limit its ability to scale up or down at the same speed as the multilateral agreements.

Through the direct partnership model, the team will have a close working relationship with partners, and will use evidence from, learning to manage partnerships. Where there is evidence that pilots are working, the team will work with the government to explore and test how these models can be scaled up or sustained through existing government mechanisms and locally-led systems.

Exit strategy

An exit strategy will need to be designed in collaboration with the Partners ensuring the sustainability and the necessary impact of the program. It will be important to work with GRZ, both at the national and local level from the inception of the program to help align with existing policies and frameworks, facilitating smoother implementation and greater support that will deliver on the outcomes and impact of ZPRP.

Risk Management

The ZPRP has a moderate overall risk rating. The programme will be highly affected by risks that may materialise under strategy and context such as poor performance of the economy, declining government financing of public services, increasing poverty levels, and climate change induced and health emergencies. The programme will be flexible to provide for interventions that help reduce the impact of such events. A detailed risk register has been developed in table 12 which considers mitigations for risks around the seven FCDO categories.

Table 11: Risk appetite by risk category

Risk Category	Risk Rating	Rationale
Strategy & Context	Receptive	The Government of Zambia has continued to support poverty reduction programmes and initiatives through financing and policy. There has been a substantial increase in spending on non-contributory social protection programmes in per capita terms since 2015. In 2025 a total of £230m was allocated towards Social Protection programmes. / However, these initiatives have been impacted by the economic performance, which has led to an increase in the cost of goods and services. The withdrawal of USAID funding may have further knock-on effects, including to the health system and wider poverty reduction goals. Additionally, the effects of climate change are evident through unpredictable rain patterns, flooding, and droughts in certain areas.
Policy & Programme Delivery	Cautious	The ZPRP programme will collaborate with various implementing organisations. Multilateral partners, such as the UN and the World Bank, have strong capacity to deliver. The Zambian government's ability to manage and execute programmes is also improving. Additionally, systems are being established within government structures to support implementation.
Public Service Delivery & Operations	Minimal	The local context remains stable, with no current security issues affecting staff or beneficiaries involved in the programme. However, there are potential risks related to FCDO budgets and approval processes that need to be monitored with the decline in ODA budget, the changing aid landscape and FCDO 2030.
People	Minimal	This remains a strategic programme for FCDO with high demands for both technical engagement and programme management oversight. The adaptive nature of ZPRP means it requires significant input from FCDO. We need to ensure the programme is manageable and there is a consistent, clear governance structure in place along with the required staff skills and staffing levels.
Safeguarding	Cautious	The nature of the programme working with vulnerable communities requires constant monitoring of safeguarding risks. Implementing partners need to keep adhering to their set policies and regulations on safeguarding.
Financial & Fiduciary Risk	Cautious	FCDO operates in an environment that is susceptible to fraud and financial mismanagement. It is vital that we maintain a robust approach to financial management to reduce the likelihood of fraud or financial mismanagement.
Reputational	Minimal	Donor pooling and support for GRZ leadership lower any reputational risks that could arise largely from political and corruption risk at the contextual and operational levels.

Table 12: Risk Matrix

Strategy and Context
Description	Gross Risk Rating	Mitigation Strategy	Residual Risk Rating	Risk within Appetite
Humanitarian and emergencies negatively affect quality and pace of programme implementation.	Major	The programme has been designed to be adaptive to humanitarian crises and includes shock responsive initiatives that enhance preparedness and response to shocks.	Moderate	Yes
Poverty trajectory worsens and undermines the support from ZPRP.	Major	Continue building resilience in low-income households through different initiatives of the programme and connections to other FCDO programmes. Invest in coalitions to support pro-poor policymaking.	Moderate	Yes
The Zambian government reduces funds available for poverty reduction due to poor performance of the economy.	Major	Support, advocate, and support locally-led coalitions that can influence government (including through domestic stakeholders) to ensure poverty reduction remains high on their agenda.	Moderate	Yes
Change in Zambian government reduces political and financial commitment to the poverty reduction agenda after 2026 election.	Moderate	Support, advocate and influence government (including through domestic stakeholders) to ensure poverty reduction remains high on their agenda.	Minor	Yes
Other donors pull out of social protection agenda thereby reducing commitment and financial support towards the sector.	Moderate	Encourage/continue donor coordination meetings to emphasize the importance and impact of joint efforts. Ensure high level engagement with other donors and multilaterals on this agenda.	Minor	Yes
Policy and Programme Delivery
Description	Gross Risk Rating	Mitigation Strategy	Residual Risk	Risk within Appetite
Inadequate capacity of partners including GRZ negatively affects the quality of outputs and delivery of programme.	Major	Support GRZ staff by contracting staff on short-term to bridge gaps; Provide TA support to GRZ for continuous capacity building, lesson sharing and shadowing.	Moderate	Yes
Weak/poor coordination between partners and across projects negatively affects the quality and delivery of programme.	Major	Use governance structures to effectively coordinate partners across projects. Continue supporting coordination initiatives to ensure that implementing partners and stakeholders work together.	Moderate	Yes
Inability to secure the right skills or severe delays in securing appropriate skilled suppliers and partners to deliver hampers delivery of programme.	Major	Engage commercial team early to avoid future delays in contracting. Hold Early Market Engagements to have an idea of availability of suppliers.	Minor	Yes.
People
Description	Gross Risk Rating	Mitigation Strategy	Residual Risk	Risk within Appetite
BHC Lusaka does not have sufficient resources to effectively manage the programme, reducing oversight and increasing risks related to quality of delivery.	Major	Managing the number and complexity of agreements, will help ensure the programme is manageable for FCDO. Delegating accountability for compliance to commercial suppliers further reduces the burden on FCDO. Recruiting as early as possible to minimize gaps.	Minor	Yes
Partners' management structures and staff numbers do not provide sufficient capacity to effectively deliver programming.	Moderate	Ensure the set-up of management structures and staff are embedded as a key deliverable in the initial stages of the contract.	Minor	Yes
Public Service Delivery and Operations
Description	Gross Risk Rating	Mitigation Strategy	Residual Risk	Risk within Appetite
Shift in political direction and priorities of UK government leads to reduction of ODA budget.	Major	Leverage multi-donor programmes to ensure sustainability of initiatives. Manage ODA allocation effectively within mission to enable continuity. Utilise diplomatic and advisory skills to maximise impact of ODA available.	Moderate	Yes
Financial and Fiduciary
Description	Gross Likelihood	Mitigation Strategy	Residual Risk	Risk within Appetite
Mismanagement/diversion of programme funds reduces funds meant for beneficiaries thereby affecting attainment of programme objectives	Major	Undertake Due Diligence, fraud and fiduciary risk assessments and annual statements of progress to ensure partner has tight systems and policies to safeguard from such type of risks. Provide constant oversight and risk management of the programme implementation and undertake various assessments on partners to provide assurance. Partners will also be encouraged to report on fraud and corruption regularly.	Moderate	Yes
Weak financial management systems and delayed internal and external partner audits does not provide required assurance to donors/funding organisations	Moderate	Provide constant oversight and risk management of the programme implementation and undertake various assessments of partners to provide assurance.	Minor	Yes
Loss of funds/value though exchange rate conversation reduces funds meant for beneficiaries thereby affecting attainment of programme objectives	Major	Partners will be encouraged to monitor and record exchange rates closely; revise budgets and workplans regularly to make necessary adjustments and ensure expenditures and payments remain within budget and alert FCDO should fluctuations in exchange rates be significant.	Moderate	Yes
Safeguarding
Description	Gross Risk Rating	Mitigation Strategy	Residual Risk	Risk within Appetite
Household conflicts due to programme benefits (e.g. SCTs, VSLAs, SBCC) increases safeguarding cases contrary to programme objectives.	Major	Ensure partners develop/use systems and channels of reporting such cases at beneficiary level as a way of identifying, managing and monitoring cases relating to GBV/SEAH.	Moderate	Yes
Low quality implementation of safeguarding policies by partners in the context, including abuse of position by staff in power and weak or slow implementation of policies.	Major	Provide constant oversight and risk management of the programme implementation and undertake various assessments on partners to provide assurance.	Moderate	Yes
SEAH of adolescent girls targeted (ladder) works in contrast with programme objectives and affects reputation of partners and the UK Government.	Major	Ensure partners develop/use systems and channels of reporting such cases at beneficiary level as a way of identifying, managing and monitoring cases relating to GBV/SEAH. Provide constant oversight and risk management of the programme implementation and undertake various assessments on partners to provide assurance.	Moderate	Yes
Reputational
Description	Gross Risk Rating	Mitigation Strategy	Residual Risk	Risk within Appetite
The nature of the UK’s support to Zambia is poorly perceived domestically and internationally affecting Zambia’s ability to support poverty reduction and work with the FCDO.	Moderate	Use communication, policy and programming to continue maintaining positive perceptions of UK support to Zambia.	Minor	Yes
Inclusion and exclusion errors, including community level conflict – FCDO seen to be favouring some beneficiaries at the expense of others has negative reputational consequences on the UK Government and partners.	Major	Use objective methods of selection and recruitment of beneficiaries; provide tools and channels for beneficiaries and community to report such cases; undertake community awareness on the beneficiary selection process.	Moderate	Yes
Politicisation of programme raises UK reputation risks and unfavourable press coverage – linked to election, possible new government, new pilots may be unpopular or politicised.	Major	Continued engagement with politicians to explain reputational risks on politicisation of the programme. Support sensitisation of communities to understand the rationale behind the programme. Support implementation of MCDSS integrated Communication Strategy.	Moderate	Yes