Key Information for: / EFFECTIVE STATE AND DEMOCRACY PROGRAMME
Directorate/ Post	East Central and Southern Africa - Lusaka	SRO Name and Contact Details	Kate Wilkinson / kate.wilkinson@fcdo.gov.uk
Total Budget	£38,000,000	Start and end dates	01/04/2025 - 31/03/2032
Overall Risk Rating	Moderate	AMP Number (if applicable)	400139

Detailed information
Programme summary, outcomes and outputs, and non-programme dependencies	Through the Effective State and Democracy (ESD) Programme, the UK will work with Zambian partners, including government institutions, the private sector, community groups, faith-based organisations, civil society and other interest groups, to strengthen the democratic norms necessary for poverty reduction in Zambia. Over the next seven years, ESD will be the main instrument for the UK to contribute to: / Zambia having a more pro-poor state which delivers poverty reduction and inclusive economic growth for all its citizens. / Zambia’s democracy being more inclusive, accountable, transparent, independent, and participatory. / This programme will build strong partnerships, supporting domestic constituencies for reform, and will be locally led recognising that real change is rarely initiated by outside actors. ESD will seek to understand where meaningful change is happening in Zambia and how the UK can convene, coalesce and strengthen coalitions to support it, leveraging the British High Commission’s diplomatic convening power and access. ESD will be flexible and adaptive, shifting focus and partnerships to maximise opportunities for impact and respond to political changes in Zambia. All activities under ESD will work towards delivering three interconnected outcomes: / The Government makes more effective decisions on how to maximise its own internal resources to lift Zambians out of extreme poverty and build climate resilience. / Formal and informal institutions are better able to deliver equitable access to services on behalf of citizens, especially poor and marginalised groups. / There is increased public, media and civil society demand to drive deep, structural reforms that enhance democratic processes long-term. / In line with the UK Government’s clear priorities for its international objectives, ESD will focus on economic growth, delivering free, fair and credible elections in 2026, public sector reform (particularly anti-corruption) and civic space. / Specific deliverables will include: / Support to civil society to monitor the 2026 elections, to ensure they are free and transparent. / Strengthen Zambia’s anti-corruption institutions, helping to recover millions of pounds of funds looted under previous regimes. / Technical advice to deliver growth enhancing reforms including: / Maintaining the removal of fossil fuel subsidies in Zambia which cost over $1bn, through improved governance of fuel procurement. / Implementation of agriculture subsidy reform in 100% of districts, saving $80m per year and promoting local jobs. / Technical advice to improve the governance of the mining sector, opening investment opportunities. / Support to Zambian trade associations and professional bodies to lobby for policy changes in mining, manufacturing and agriculture which will unlock growth. / Partnerships with civil society to increase public understanding of Zambia’s IMF backed domestic economic reform programme, to safeguard long term macro-economic stability
Portfolio Fit	The UK envisages a prosperous and stable future for Zambia’s people based on inclusive and sustainable growth, strong democratic institutions and values, and resilience to poverty and shocks. FCDO’s Country Business Plan for Zambia is centred on delivering three goals: / Green and resilient economic development / Freedom and democracy / Poverty reduction, resilience and empowerment / ESD is the main instrument for delivering the ‘Freedom and Democracy’ goal. This goal incorporates our work to support Zambia's international ambitions and policies where they align with UK interests; secure and deepen democratic practice and voice; increase transparency, reduce corruption and improve internal security; and support the Government to design, implement and improve policies that deliver development and promote growth. / FCDO has considered the trade-offs of implementing this programme against investing in other areas. If we do not invest in ESD, we could invest the (time and financial) resources directly into other FCDO priorities including climate, green growth and human development. However, deeper political and governance failures underpin all these challenges. Building more effective, accountable and inclusive institutions is a critical enabler for success in every sector and therefore a key driver of development in Zambia. Trade-offs will be considered within the programme (based on strategic need, opportunity for impact and UK comparative advantage) to maximise value for money. The option to focus the programme on one area of democratic governance (such as reducing corruption) was ruled out on the basis that Zambian political commitment and UK strategic alignment are key determinants of success (and may shift over the programme lifetime).
Geography	This programme will benefit Zambia. The Head of Mission/ approved ESD operating in Zambia on 28th October 2024.
Budget	This programme will spend up to £38,000,000 over seven financial years (2025/26- 2031/32). No funding has yet been spent on design. The ESD budget will largely be classified as Resource Departmental Expenditure Limit (RDEL); expenditure classified as Capital Department Expenditure Limit (CDEL) will be extremely limited. FCDO will allocate roughly one quarter of its annual ODA RDEL budget in Zambia to ESD over the programme lifetime.
Timing	ESD will begin spending in FY2025/26. The expected budget for FY25/26 is £3,500,000. The first half of the year will be an inception period during which time partners will mobilise and activities will be agreed. Partners will then move into implementation for the remaining six months. Affordability for FY25/26 will be determined following the October 2024 Spending Review. For FY26/27-31/32, we expect the maximum spend per year to be roughly consistent (around £5,750,000 in total). Affordability will be determined based on the multiyear Spending Review in 2025. FCDO will confirm partners’ budgets annually to ensure the programme remains affordable within the delegated ODA budget. Break clauses will be included in all contracts. Accountable Grants and MoU do not legally commit the UK to providing funds.
Delivery modality	ESD will be delivered through three projects: / A commercial contract (procured through the FCDO’s Global Development Delivery Framework) for the Deepening Democracy Facility. / A commercial contract (procured through the FCDO’s Global Development Delivery Framework) for the Strategic Economic Reform Facility. / A direct partnership project to enable FCDO to hold agreements with multilateral agencies or partners where there is a strategic reason to do so.
Strategic rationale and evidence base	ESD will deliver against two of the UK’s development priorities: accelerating sustainable and inclusive economic development, and championing rights, equality, and empowerment of women and girls. It will be grounded in genuine respect and partnership, by working through locally led coalitions it will prioritise Zambia’s needs in its own development. / Zambia’s economic growth is profoundly exclusive. Zambia’s political settlement- the way power is distributed across social groups in the country- has resulted in a governance system that is responsive to the needs of some but not others, benefits a subset of society to the detriment of the majority, and exacerbates rather than alleviates poverty. Mining has created an economy where there is almost no relationship between economic growth and poverty reduction. Poverty, particularly in rural areas, is acute and rising, putting Zambia on track to become the third poorest country in Africa by 2060. Women and girls are often marginalised in development processes: underserved by services and underutilised in decision-making and economic growth. / ESD will work in partnership with Zambian actors to address this. It will tackle political and institutional barriers to poverty reduction so that democracy delivers for more Zambians. Evidence shows that as democracy improves in Zambia, so does economic growth. A more inclusive democracy - one that is accountable, transparent, independent, and participatory - will drive improved service delivery, more equitable use of resources, greater climate resilience and adaptation, reduced corruption and increased gender equality. ESD will prioritise women’s political, social and economic empowerment, and champion the voices of women and girls, so that they can lead their development. It will capitalise on the commitment Zambia has made to implementing ambitious economic and social reforms, positioning the UK as a partner that is enduring and supports its allies in achieving their ambitions. And it will demonstrate that there is an alternative path to economic growth, one that is inclusive and sustainable, in a region that is increasingly authoritarian.
International Climate Finance (ICF)	ESD is expected to include ICF eligible activities. Exact proportions of ICF-eligibility will be determined during inception (and monitored as the programme evolves). ICF KPIs will be included in the log-frame to track the contribution ESD is making to the UK’s ICF target.
Clearance chain confirming scrutiny of programme and review comments
Submission Date	Enter date sent to Country Board or HQ equivalent
All programmes / Confirm here that approval timelines were met (2 weeks for Board & 1 week for HoM/ Director)	The UK’s Zambia Country Board approved the Business Case on 30/08/2024. The Board agreed that ESD aligns with the UK’s growth, climate and gender equality objectives and recognised the contribution good governance and democracy make to achieving all the UK’s objectives in Zambia. The Board requested additional information on three areas (the SROs response is summarised here and detailed in the Business Case): / How trade-offs will be managed throughout the life of the programme: This programme has the potential to invest across a wide range of thematic areas. Making accurate decisions about trade-offs will therefore be critical to maximising impact and value for money. ESD will focus on areas where there is domestic momentum towards reform and where UK support can tip the balance. / A deeper understanding of what is meant by working with local actors: The Business Case was amended to make clear that alongside elite engagement (which is crucial for driving reform in a highly centralised system), a key aspect of this programme will be working with (formal and informal) grassroots organisations. The supplier Terms of Reference will indicate the percentage of funding that should be reserved for local organisations. / How we will ensure investments are sustainable once UK funding ends: ESD will be effective if it sustainably increases demand for more democratic governance, and if investments to support the government and its partners lead to improved policies and programmes that better meet the need of citizens. By working in partnership and grounding our investments in Zambia’s priorities for development, we will ensure sustainability beyond the life of the programme. / Endorsed by Berni Smith – Acting Development Director
	Head of Mission / HQ Director / This programme will tackle the underlying governance failures that impede Zambia’s development and poverty reduction, forming a key pillar of the British High Commission’s business plan. Its approach learns from previous interventions; by working in partnership with domestic constituencies for reform the programme will ensure that issues it works on are relevant and politically tractable. I am therefore happy to approve this programme.
Programmes between £20m and £40m / Confirm here that approval timelines were met (3 weeks for Director General)	Director General / APPROVED 21/02/2025

Strategic Case

GOVERNANCE IN ZAMBIA: THE STATUS QUO
Zambia is known for being a stable democracy, with one of the most competitive political systems in Africa. Zambia is in the top five countries on the African continent in terms of support for democracy: 87% of Zambians believe that democracy is preferrable to any other kind of government[1]. 91% of Zambians believe they are completely free to vote without pressure, and 76% believe citizens should be able to hold their government to account. Yet despite 71% of Zambians feeling satisfied with democracy, 60% of people disapprove of the way their MP performs, and 89% think their MP never or only sometimes listen to what ordinary people have to say.
[1] Afrobarometer Policy Paper No. 85 | January 2023
        Support for democracy and rejection of non-democratic alternatives Choose leaders through elections or other methods

Source: Afro Barometer, 2021
1. Zambia’s democracy works better for some than others. Zambia’s large (and exclusive) mining sector has created an economy where there is almost no relationship between economic growth and poverty reduction. Mining revenues (accrued mainly in the urbanized provinces of Lusaka and the Copperbelt) have created a powerful ruling elite who have disproportionate influence in policy making. More broadly in urban areas, higher aggregate levels of education, better access to information and closer proximity to decision makers enable people to be more critical participants in the political process. Urban voters have captured the political system. They have proven far more likely to ‘swing’ from the incumbent party than their rural counterparts and they benefit disproportionately from the political system in return. Zambian politicians have strong incentives to favour urban areas with policies and public resource allocation because they ensure electoral success. This is exemplified by the orientation of fiscal policy towards subsidies; until their recent removal, the richest 10% of households captured nearly 90% of the total fuel subsidies and over 50% of the total electricity subsidies. Influential groups who benefit from such policies ensure they are held in place in exchange for their political support, maintaining the status quo.
2. Rural neglect is the flip side of Zambia’s urban-centric democracy. The hallmark of democracy in rural Zambia is the receipt of personal aid. Citizen demands of their MPs are usually for private goods (such as funeral expenses) or for ‘club goods’ - local projects (such as a new school), rather than systemic national scale improvement. Political participation is therefore a relatively low-cost way to capture resources. Elections are often fought based on patronage and MPs directly ‘bringing development’ to their areas. MPs respond to citizen demands by either lobbying Ministries to divert projects to voters’ area (which makes opposition MPs vulnerable to co-option by the party in power) or by using funds from Ministerial positions to pay for projects privately. Pressure for reform on issues which are acute for rural populations, such as land reform, is diffuse or comes from sources who are not able to threaten the state. This creates an equilibrium where democracy is responsive to the needs of some but not others, benefits a subset of society to the detriment of everyone else, and entrenches rather than alleviates poverty.
3. Climate risks are already being realised and will only increase. Zambia’s climate vulnerability is driven by poverty, the unsustainable use of natural resources, limited access to basic services, and high levels of climate-vulnerable livelihoods (such as smallholder farming). In rural areas of Zambia, most of the population work in low-productivity agriculture and have remained deeply poor. Temperatures in Zambia are rising faster than the global average and increasing climatic variability continues to drive cycles of floods and drought, reducing incomes and whittling down resilience. Poorer people (and women in particular) are hit harder because their survival depends on activities which are the most affected by climate change (notably agriculture, forestry and fishing) and because they lack the assets needed to absorb climate shocks. As the negative effects of climate change further intensify, Zambia will experience increasing loss of incomes, livelihoods, and rising competition over resources.
4. Climate change is exacerbating Zambia’s existing vulnerabilities. Many of the structural reasons for Zambia’s persistent poverty and vulnerability are not a result of climate change. Rather than being a root cause, climate change impacts are exacerbating existing vulnerabilities, such as poor economic growth or environmental degradation. For example, land is central to livelihoods and economic growth, but land governance systems in Zambia are chronically weak. An estimated 94% of land in Zambia falls under a customary (or informal) land tenure system[2]. Insecurity around land governance is a barrier to sustainable rural development because it reduces incentives to pursue medium-to-long-term land investments which would protect the remaining natural resource base. Reducing vulnerability to climate change will therefore depend on Zambia’s ability to address the drivers of climate vulnerability in its existing systems. Beyond the necessary finance, this will require carefully designed and implemented laws, policies, processes, and interventions that are climate resilient and inclusive (i.e., that consider the linkages between climate systems, ecosystems and human society, and prioritise equity and justice in climate adaptation planning and implementation)[3]. However, Zambia’s political settlement – the way power is distributed across social groups in the country –means the people who are most affected have the least power to demand a focus on climate action, and the reforms required to increase inclusive growth (and thus reduce vulnerability to climate change) are thwarted by the forces maintaining the status quo.
  [2] World Bank, Systematic Country Diagnostic- Republic of Zambia, Mar 2018
  [3] IPCC Summary for Policymakers, https://www.ipcc.ch/report/ar6/wg2/downloads/report/IPCC_AR6_WGII_SummaryForPolicymakers.pdf
5. The state is highly centralised in Zambia. The Zambian state is characterised by an executive presidential system, in which incentives, rewards or sanctions are centred around the President and State House. The President holds significant formal and informal power to appoint key positions and influence decisions. This makes it possible to place loyal individuals in key decision-making positions. While the presidency as an institution is extremely strong and influential, the willingness to abuse executive powers and act unilaterally is limited by political considerations and the need to manage the interests of diverse political elites from around the country to maintain a broad-based national coalition to sustain the administration. This balancing act maintains stability but can often limit the scope for implementing significant reforms, particularly those that may be politically sensitive or those that threaten the interests of the political elite.
6. Efforts to decentralise power and resources to areas most in need have not been realised. The Government’s 2023 Decentralization Policy envisions achieving the most extensive form of decentralisation- improving the capacity of local authorities to deliver services, mobilise revenue and increase citizen participation. But decentralisation is an inherently political process, which requires the central government to cede authority, relevance, and resources to subnational entities. The concentration of power within the central government has deep historical roots in Zambia, and control over resources is a source of power in the patronage-based system. The substantial increase to the Constituency Development Fund (CDF), the flagship decentralisation policy of the ruling party, exemplifies these challenges. Utilisation of funds still depends on central approvals and the President maintains the ability to direct expenditure. It has also demonstrated weaknesses in administration at local levels and between different levels of government. The risk that the CDF doesn’t translate to improved development outcomes at local levels highlights that decentralisation is not merely about allocating more money at the local level, but a whole of government effort to improve coordination and devolved decision making.
7. Zambia’s public sector is politicised, and capacity is generally low, hampering better delivery of public goods and services. Historically, politicians have rewarded their supporters by appointing them to government positions and awarding contracts to allies and cronies by flouting tender procedures. This undermines the separation of power and the independence of public officials. The overlap of public positions and private business interests entrenches corruption, particularly in public procurement, as individuals seek to maintain their power and control over resources. As a result, attempts to reform the public sector and government policy are met by strong resistance (and are therefore politically difficult). The public sector is also critically underfinanced, has a shortage of specialised skills and there is high staff turnover, limiting its effectiveness and ability to implement policies on the Government’s behalf. Rather than trying to deliver its ambitions through the public sector, politicians attempt quick fix approaches that eschew more complex administrative reforms in favour of time bound results. Although this has spearheaded more focused policy and implementation around key priorities (for instance the expansion of the Cash Transfer Programme in response to the drought), in general, prioritisation remains a challenge. The status quo suits political leaders because it allows them to maintain control over public sector resources and deliver (populist) policies that secure votes.
8. Corruption is endemic at all levels. One person out of ten pays a bribe to access a service, and over 62% of people, when solicited to pay a bribe at a public institution, end up paying[4]. Corruption in public procurement is consistently cited as a particular vulnerability, especially in sectors where public spending is high (e.g. agriculture, infrastructure). Illicit financial flows from commercial activities, particularly in the extractives industry, contribute to major losses in tax revenue[5]. Weak transparency and accountability mechanisms allow political and economic elites to bend rules, mismanage vast resources and conceal ill-gotten gains. In 2023, for the first time in ten years, Zambia improved its Corruption Perceptions Index score[6]. Corruption was a major factor in the 2021 change of government narrative, however little structural change has taken place. There is risk that rather than reducing, corruption is now more centralised amongst a smaller group of elites who wield both political and economic control. This has the potential to strengthen the informal structures that benefit most from weak formal anti-corruption institutions and make it more difficult to effect holistic reform[7].
  [4] Transparency International Zambia, 2024 https://tizambia.org.zm/
  [5] United Nations. Economic Commission for Africa (2015). Illicit financial flows: report of the High Level Panel on illicit financial flows from Africa. Addis Ababa. © UN.ECA. https://hdl.handle.net/10855/22695
  [6] Transparency International Zambia, Corruption Perception Index 2023 https://tizambia.org.zm/
  [7] The Money Laundering and Terrorism Financing Trends Report, 2023 points to the increased use of shell companies by politically influential persons and more sophisticated masking of beneficial ownership involving high-level government contracts.
9. Zambia has consistently held competitive elections that have often resulted in peaceful transitions of power. Zambia’s legal framework allows for multiparty elections and, since independence, seven Presidents from four political parties have been elected. The Electoral Commission of Zambia has historically conducted relatively well-run elections, with a track record of managing peaceful transitions of power even in tightly contested elections where the incumbent is unseated. Nevertheless, there are persistent concerns about the lack of independence of the Electoral Commission of Zambia and weaknesses in electoral processes, eroding public trust and narrowing participation. Key areas for reform include regulation of political party financing, enhanced independence and capacity of the Independent Broadcasting Authority to ensure fair media coverage and access, and improved enforcement of the electoral code of conduct.
10. Opposition parties are unpredictable and fluid, making for unconstructive political debate and limiting the role the opposition play in holding the ruling party accountable. There is no legislation specifically governing political parties in Zambia. Parties do not receive public funds, nor are they required to disclose sources of funding. This leads parties to be largely dependent on the personal finances of party leaders (which limits participation in politics to those who have already acquired substantial wealth) or private donations (from legitimate or illicit sources), which increases Zambia’s vulnerability to malign influences. This allows political elites to maintain control over political parties by pricing out new entrants and entrenching influence and patronage amongst a small core who have money and influence. There is growing demand for transparency around the finances of public officials and those who seek to enter public office, with 65% of Zambians believing asset declaration laws should be strengthened[8]. While the legal structure remains weak, rising public interest could lead to greater scrutiny of political parties’ internal operations and democratic structures, potentially driving legal reforms to enforce greater accountability.
  [8] Afrobarometer, 2024
11. While some parties have been a stable presence across electoral cycles since 2001, dozens of smaller parties have been formed and dissolved. It is common for politicians to circulate between parties (or form allegiances behind the scenes) as it serves their interest. Because opposition parliamentary candidates are largely left to self-fund their campaign efforts, they have few incentives to remain in parties that appear to be unpopular with the electorate. In 2016 a constitutional amendment was passed to change the voting system from First Past the Post to 50%+1 of the vote share. This made building a winning national coalition even more challenging. Prior to 2016, presidential candidates could secure a majority from their regional strongholds alone. Now, parties must form broad coalitions across regions to build a winning coalition. This change in the formal electoral institution heightens the informal expectation for ethnically representative appointments. Pressure to accommodate various interest groups and factions in appointments can force compromises and dilute the merit-based governance and delivery agenda.
12. Political participation at all levels is overwhelmingly dominated by men; women, young people (aged 15-35) and people with disabilities face major barriers to participation. Only one member of Parliament in Zambia is below the age of 35, despite young people making up 27% of the population[9]. Four candidates with disabilities (out of 857) stood in the 2021 parliamentary elections, and only was one elected.[10] Of the 156 elected members of parliament, only 20 are women. At the district level, only 12.8% of candidates in Mayor and council chairperson elections were women, and less than 10% amongst ward councillor candidates[11]. Within political parties, there are no existing regulations or legislation focused on protecting or improving the participation of women and youth. According to women activists, the political environment is hostile and discourages women from standing. Harassment, (cyber) bullying, socio-cultural stereotypes and the finances needed to run a campaign are barriers that women face[12]. Many Zambians say it is very likely that communities will attack and harass women for seeking public office, and a third say that women seeking election will face issues within their own families.[13] The overwhelming male dominance in political participation at all levels is rooted in deep-seated socio-cultural beliefs about gender roles, and the relationship between MP and constituents, built on patronage and personal capacity to deliver, entrenches this. Cultural norms around age further shape behaviours in ways that are not codified in law. There is small but growing discussion amongst civil society around affirmative action policies to increase representation. While not a silver bullet, the discussion around affirmative action suggests there is a window of opportunity to build support for inclusion within political party legislation.
  [9] The National Youth Policy 2024, Republic of Zambia
  [10] Carter Centre “Analysing Zambia’s 2021 General Elections”.
  [11] EU Electoral Observer Mission Report 2021
  [12] EU 2021 election Observation Mission Report | Electoral Violence In Zambia – Southern Africa Institute for Policy and Research
  [13] Zambians Endorse Gender Equality, Afrobarometer Dispatch 706.
13. Zambia’s judiciary has been perceived, in the past and present, as subject to political influence. Although Zambia’s Constitution guarantees the separation of powers, challenges persist in ensuring the judiciary can operate without political interference. Weaknesses in the judicial system allow for executive overreach, including in the appointments process, how cases are allocated and judicial corruption. This has damaged public trust. 78% of Zambians think at least some judges and magistrates are involved in corruption[14]. Ensuring the Judiciary can remain independent and impartial is essential for maintaining the rule of law, a fair political environment and fostering trust in democratic process. Current focus on governance reform presents a timely opportunity to encourage changes that can reinforce greater judicial independence and resilience.
  [14] Afrobarometer, 2024

1. Public dialogue is typically unconstructive and there is a lack of ‘middle ground’ voices to mediate differences in views. The media is perceived to be weak. Civil society organisations are widespread but are typically more service than advocacy based. Advocacy based CSOs are thin, predominately in Lusaka and largely dependent on limited donor funds. Governments (including the current government) regularly co-opt the limited handful of nationally prominent civil society leaders by appointing them to senior roles in the civil service or civic institutions[15]. The church and traditional leadership play a powerful role in the civic and political space, and are a trusted source of representation, particularly in rural areas. Historically the churches have played a role in mediating election disputes, although they are not entirely independent of party politics. The private sector’s economic power allows it to influence political actors through donations, lobbying and partnerships. Trade unions can play a role in mediating between large sections of the labour force and the government, but there is also the risk that unions can be captured by politicians, particularly during election cycles. Given this landscape, it is crucial to scan the horizon for organic coalitions coalescing around key issues. These movements, reflecting rare broad-based consensus, have historically been effective at driving change, even if that change is more behavioural than structural. The opposition to ‘Bill 10’, which brought together civil society, opposition and ordinary citizens to defeat regressive legislative changes to the Constitution, is an example of how such informal coalitions can create significant impact on formal institutions. Understanding and engaging with these informal networks, whether to support positive change or mitigate negative behaviours, is essential for operating effectively within Zambia’s governance landscape. By identifying and providing early support to these coalitions, it is possible to translate broad informal and formal consensus into impact.
  [15] BTI Zambia Country Report 2024, 27.
2. Cumulatively, these various characteristics result in a democratic system which benefits some citizens but excludes many others, has deep values but weak safeguards, is stable and peaceful but difficult to reform. Zambians’ preference for democracy sets them apart from people in many other African countries, but democracy isn’t delivering development for most Zambians. Zambia’s governance system functions primarily to serve the interests of those in power. Urban and elite biases have led Zambia to be the 6th most unequal country in the world, reinforced by some of the least progressive government spending in Africa. Deep vested interests thwart efforts to reform institutions and practices, preserving a status quo that is profoundly exclusive and there is limited demand from the wider public, civil society or media to challenge it.

OPPORTUNITIES FOR CHANGE
1. Systemic changes are needed in Zambia to lift people out of poverty, transform the economy and build resilience to shocks; this will be determined by Zambia’s ability to govern itself effectively. Tackling long term issues of poverty and unleashing the potential of Zambia’s mineral wealth will take time. If Zambia is to change its poverty trajectory, it will require sustained and diversified economic growth, greater inclusion of women and marginalised groups, and reorienting Zambia’s policies and resource allocations to alleviate rather than entrench poverty. Zambia has the natural capital for its agricultural sector to become an engine of economic growth and poverty alleviation. It also has access to regional markets, allowing for the kinds of job-rich growth that can pull Zambians off the land. Yet the country’s agricultural productivity is well below potential and on a downward trend, driven by inefficient and distortive public policies, increasing climate hazards and resource degradation, and limited diversification.
2. To achieve systemic changes, Zambia will need to shift its stable status quo. The equilibrium sustains because vested interest groups make decisions which are most logical for that group to protect its interests. Zambia will need to transform the institutions and incentives that lead to poor development outcomes to become more democratic (more accountable, transparent, independent, inclusive, and participatory). Changing the deeply embedded status quo is difficult, but it can be done. By identifying the opportunities for change, and by getting behind Zambian interest groups in favour of change, FCDO has the potential to tip the balance in favour of reform. There are several broad trends that have the potential to form the context necessary for change:
- The current government was elected on a platform of economic and social reform. In response to the debt crisis it inherited, the United Party for National Development (UPND) Government has been successful in brokering a deal to restructure $14bn of its external debt; part of a broader, ambitious programme of economic reform that has the potential to transform Zambia’s long-term development trajectory. Although the pace of the reforms has been slowed by successive crises (cholera, drought and an energy crisis), this remains a once-in-a-decade opportunity to make progress on key reforms. The pressure to manage debt and meet fiscal obligations will limit discretionary spending, reducing the ability of political elites to distribute state resources to maintain loyalty and control.
- The growth of a more educated middle class in Zambia is a demographic shift that could drive structural change. As more Zambians move to urban areas, attain higher education, and secure stable employment, there is likely to be a departure from traditional patronage networks that have sustained the status quo. Fewer people will depend on loyalty to political elites and instead will place greater value on the principles of meritocracy and accountability. This could influence a shift towards prioritisation of skills and expertise over loyalty in public appointments, building a more capable and professional civil service, driving institutional reform from within. Reduced dependence on politicians for short term gains like urban infrastructure development, alongside a better understanding of how institutions should function and enhanced issue-based voting, could lead to a more responsive and accountable governance[16].
  [16] Hangala Siachiwena and Michael Whaman, “The Political Economy of Urban Party Switching in African Elections: Evidence from Zambia”, Journal of Modern African Studies, 1-25.
- Zambia’s youth population is demographic shift that could drive a change in Zambia’s governance landscape. Zambia’s youth, who make up most of the population, are currently an underutilised force for driving broader governance reforms. Young people are prioritising the economy and management of resources because they see this as critical to improving their livelihoods, but 50% of youths believe that the government is performing poorly in this area.[17] The 2021 election was driven by young, first-time voters. Growing dissatisfaction amongst young people is both a risk and opportunity for the Zambian Government; if harnessed, young people have the potential to engage in deeper processes that go beyond elections.
  [17] Afrobarometer, 2024.
- The electorate’s 2021 rejection of violence as a tool of political control indicates a shift in political culture and expectations. As there is less acceptance of violence and coercion, political leaders are compelled to adapt their tools of political engagement. The 2021 election also produced evidence that rural voters were voting based on governance and economic policy, as well as clientelism.[18] This could create more room for policy driven campaigns and more constructive engagement. When electoral success is more closely tied to policy performance than patronage or intimidation, this can create a virtuous cycle where political survival depends on delivery, incentivising good governance and development[19].
  [18] Journal of Eastern African Studies – Special Issue on 2021 Zambian elections
  [19] Infrastructure and Perceptions of Democracy in Zambia: Democracy off the Rails, African Affairs, Vol. 119, Issue 477, Oct 2020, 604-632.
- The strength of support for democracy provides a strong foundation on which to build coalitions and grassroots movements. Zambians overwhelmingly feel that elections are the best way to choose leaders[20]. 73% of Zambians believe that they should be able to criticise elected officials without fear of reprisal.[21] Zambia’s democratic system provides some positive incentives for reform, as power is not guaranteed, and political elites can lose elections. Understanding how electoral dynamics positively influence policy is key, and civil society has a central role in defending and institutionalising reforms once they are achieved. Despite civil society being significantly weakened in recent years (in part due to an over subscription to project-based funding that prioritises activities over institutional strengthening), history shows that Zambian civil society can be influential in demanding and shaping reforms. Core funding to civil society organisations can enable them to rebuild their advocacy base, maintain independence, be an effective counterbalance to government and sustain long-term efforts for reform.
  [20] Afrobarometer, 2024.
  [21] Afrobarometer, 2024
- The foundations on which Zambia can progress its National Green Growth Strategy are already in place. Zambia’s national policy frameworks[22] all aim to tackle poverty and vulnerability, develop the agricultural sector and build resilience to climate change in rural systems. In December 2024, Zambia passed its Green Economy and Climate Change Bill, which is a positive legislative step. Zambia is increasingly well-positioned to translate its ambition into action if it invests more resources and capacity, improves coordination, and delivers more effective leadership.
  [22] 8th National Development Plan, National Determined Contribution, National Determined Contribution (NDC), NDC implementation framework, Green Growth Strategy, Forestry Act, and the Climate Change Act of 2024
- Wider use of mobile technology is empowering citizens by enabling greater access to information and reshaping the delivery of services. For instance, the use of mobile fintech platforms in social cash transfers has reduced costs, time delays, and expanded access to hard-to-reach populations, but it has also started to address the power imbalance between officials and voters. Traditionally, social cash transfers could be politicised, with communities feeling beholden to politicians who are positioned as benefactors. Technology is shifting the perception from one where communities are dependent on politicians to one where they recognise these benefits as entitlements provided by the system, and that services are rights, not favours. The rise of social media, particularly amongst young people, is allowing people outside of urban centres to be more aware of government decisions and to engage in the political process in new ways. This has potential to shift political incentives towards addressing the needs of a wider section of society.

PROGRAMME APPROACH – WHERE IS CHANGE ‘IN PLAY’ AND HOW CAN THE UK SUPPORT IT
Zambia is changing; to be effective, the UK needs to get behind Zambian change efforts. The UK has been implementing governance programmes in Zambia for over two decades, building a bank of experience on which to draw. There are six key lessons from our implementation experience in recent years that underpin our proposed approach to ESD:
  1. Real change is rarely initiated by outside actors – domestic politics drive progress. In line with the UK Government’s focus on locally led partnerships, this programme will focus on asking the question ‘where is meaningful change happening in Zambia’ and ‘how can the UK support it’. In seeking out change opportunities, we will use deep political analysis to understand why a particular issue is ‘in play’ – that is, where the balance of power has potential to shift- and offer the best opportunities for impactful engagement. Based on comparative global evidence, we know that change happens when there is a sufficiently powerful set of interests supporting it. This is true across societies and has been true for the UK’s work on reform in Zambia. We will be selective about which changes we support. Where a change would happen without external engagement, the UK should not be involved. Equally, where we identify an issue where reform is necessary but for which there is no domestic constituency for change, we will also not invest our resources. Our focus will be on issues where the equilibrium is such that our engagement can tip the balance in favour of change (the ‘seesaw approach’). The British High Commission has a close and trusted partnership with the Government of Zambia developed over many years of mutually respectful collaboration. Where opportunities are identified, we will leverage the British High Commission’s access and influence to support positive change. Service providers will be expected to integrate their influencing agenda closely with the diplomatic engine of the mission.
    THE ‘SEESAW APPROACH’

    Influencing systemic change is like balancing a see saw: on one side there are forces for reform, and on the other, forces for maintaining the status quo. Change happens when the balance tips in favour of reform. But this process is rarely straight forward; it requires an iterative approach where coalitions are formed and continuously strengthened, adding weight bit by bit until the system shifts. Most importantly, true change is driven by local actors, not external ones. Our focus must be on understanding the domestic context: identifying the equilibrium that keeps the status quo in place, and then working with local change agents to shift it. Our role is not to lead change, but to spot where change is already ’in play’, seek out the interest groups - both formal and informal - that are pushing for reform, and strategically support them. By working politically to understand where our involvement can boost domestic momentum, we can leverage our networks and diplomacy to convene, protect and strengthen these coalitions.
  2. We need to ‘think and work politically’ to build alliances for reform. Development is not linear, and it is a deeply political process. Governance approaches to development aim to transform institutions and shift power and behaviours into order to change the way the system works – including how decisions are made and implemented. At the heart of this is the understanding that poor development outcomes are the result of poor systems or incentives. Analysing and responding to the political economy of different issues (using the twinned tools of development and diplomatic expertise) has enabled us to tackle entrenched barriers to reform. We need to be clear about the reasons the status quo persists and why it is a logical course of action for those who benefit from it. Our strategies for delivering change need to be well thought through and politically sound. The programme will therefore expect sophisticated political understanding from partners, on three levels. First, a deep understanding of causal pathways around reform – how change happens in Zambia, and the kinds of issues that can be moved as a result. Second, a deep understanding of interests around a specific issue, both for and against, and a practical and creative approach to mobilising interest groups (even if they disagree on other issues and might never have met), to support change. This requires a deep understanding of power and interest groups in Zambia. Third, having the practical skills to convene, coalesce and animate reform coalitions.
  3. We need to depart from conventional approaches built solely around funding formal organisations. Political interest groups are diverse and are not always represented by formal organisations. More important than direct UK influence are domestic interest groups – change happens when enough domestic voices shift the balance of power around an issue. Community groups, faith-based organisations, and civil society can influence political elites, particularly when they collaborate with other powerful actors like the private sector or trade unions. Traditional NGOs are not the sole drivers of this type of influence. This programme will depart from conventional approaches built around solely funding NGOs in both our partner choice and our approach. First, our partner choice will be broader and more strategic than orthodox governance programmes, recognising that the most impactful interest groups may not be formal organisations, and may not even be formally organised. Secondly, we will focus on how we can bring interest groups into play around a specific issue, looking beyond funding alone to convening, organising, and facilitating. This effort should be deeply integrated with the British High Commission, which has significant networks and convening power that can add value to such approaches.
  4. We need to address both the ‘supply and demand’. This means supporting the state to be more effective, transparent, and accountable so it can respond to the needs of its population (the ‘supply’) and promoting bottom-up social accountability and participation (the ‘demand’). Working on only one or the other risks missing opportunities for a holistic approach. Maintaining this balance is also critical for long-term stability; it requires equal attention to the state’s policy and implementation capacity, as well as mobilising demand for accountability and ‘voice’[23]. Where we invest in direct engagement with the state on reform, we will also work with reform coalitions to sustain the political pressure necessary to embed change.
    [23] Twenty years of UK governance programmes in Nigeria, Oct 2021, https://cdn.odi.org/media/documents/Flagship_UK_Governance_Programming_in_Nigeria__final_corrected.pdf
  5. We need to balance incremental change with long term transformation. Elections can significantly shift the opportunities for development and diplomatic engagement, but so too does the period between elections. The UK’s ability to work differently at different stages of the electoral cycle has been a key determinant of our success in recent years. We have successfully managed to balance support to short-term priorities which has opened space for impact in areas where change can happen, whilst also working towards more complex reforms that will take time and cross election cycles.
  6. We need to be clear on what we are trying to achieve. Previous UK investments have suffered when disparate interventions were not guided by a strong Theory of Change. This led partners to achieving individual successes, but not amounting to more than the sum of their parts. To correct this, ESD needs a delivery and governance structure which coalesces partners around joint outcomes (and monitoring and evaluation to measure this). By operating in this way, we can be clear on what we are trying to achieve, while giving partners the flexibility to determine how they achieve their objectives.
ESD represents a departure from some previous FCDO governance programming in Zambia which took an ‘orthodox’ governance approach. In line with the UK Government’s new approach to development, this programme will adopt a humbler stance on the role of non-Zambian actors and be more focused on locally led development and domestic constituencies for reform. This will require a flexible programme which can shift focus and partnerships to maximise opportunities for impact.

THEORY OF CHANGE
Impact
The impact we expect this programme to contribute to is two-fold (reflecting the twinned supply and demand concepts of ‘effective state’ and ‘democracy’):
- Zambia has an effective state which delivers poverty reduction and inclusive, climate-resilient economic growth for all its citizens.
- Zambia’s democratic space is more inclusive, accountable, transparent, independent, and participatory.
1. Evidence shows that countries with more effective governments have been able to make more progress towards the Sustainable Development Goals (SDGs)[24]. The state is at the centre of economic governance not just as the designer and decision maker for the national policy agenda, but also as the provider of key public services that are necessary for growth, structural change and poverty reduction[25]. Grant aid represents less than 3% of government resources in Zambia, so development outcomes depend firmly upon the vision, strategies and spending choices of the Zambian Government. The UK wants to support the Zambian state to be more accountable for delivering inclusive growth and reducing poverty, and to have the capacity to design and implement the services and policies necessary to do so. However, more than policies themselves, it is the politics of policies that are fundamental in shaping their implementation and effectiveness. ESD will therefore ‘think and work politically’ to unblock the political barriers to more inclusive development.
  [24] Road to the SDGs: Review of Evidence and Implications for Policy, internal FCDO paper 2023
  [25] IGC evidence paper on State effectiveness, https://www.theigc.org/sites/default/files/2019/12/IGC-State-effectiveness-evidence-paper_June2021.pdf
2. Good institutions also matter for development. Institutions enable societies to address challenges- from managing irrigation and school systems, to raising and spending revenues and conducting free and fair elections. Countries with better institutions are more likely to experience sustained and equitable growth[26]. ESD will sustainably strengthen formal institutions by going beyond building the capacity of individuals, to address deeper structural factors (like leadership, systems, culture and funding). Alongside formal institutions, informal institutions play a significant role in Zambian governance. These are the widely understood but unwritten rules, norms and practices that influence decision making. Often more powerful and influential, these informal institutions are deeply embedded into governance, running parallel to and intertwining with formal institutions. ESD will engage strategically with these networks to leverage the interplay between formal and informal institutions to build coalitions and align incentives towards reform.
  [26] World Bank- To end poverty, we need to get better at improving institutions. Feb 2013
3. Alongside the ‘supply’ of improved governance, ESD will build ‘demand’ for deep, structural reforms that enhance democratic processes long-term. Maintaining the balance between the state’s capacity to deliver and the public’s demand for good governance and democracy is critical for long term stability. Support for democracy is high in Zambia, but there is limited pressure and engagement from the public to strengthen the institutions that uphold democracy outside election periods. Communities most affected by national issues like climate change have the least power demand change. ESD will work with citizens, civil society and the media to build demand for deep, structural reforms that enhance democratic processes long-term.
Outcomes/ Outputs
The UK Government has set clear priorities for its international objectives. ESD will deliver these priorities, focussing on areas where there is meaningful change happening in Zambia and where the UK’s involvement can help tip the balance in favour of reform. It will work towards the following four outcomes:
Growth- The UK wants to enhance global economic security and support sustainable and inclusive growth. Growth is also the top priority of the Zambian Government. We will build on existing programming interventions that provide advice at the highest levels of government, but significantly scale up this offer, recognising the results that have been achieved in delivering poverty-reducing policies. Outputs will include:
- Technical assistance to policy makers (e.g. in State House, Cabinet Office, Presidential Delivery Unit and Ministries) to design, implement and reform policies that will support inclusive, climate-resilient economic growth. We will focus on sectors which have the potential to transform Zambia’s economy, including critical minerals, job creation, agriculture, crisis resilience and energy.
- Providing data, research and capacity building to policymakers to improve decision making. There is a wealth of underutilized administrative data in Zambia. While technical evidence alone rarely drives policy change, leveraging this data effectively and strengthening its translation into policy making can create opportunities for informed evidence-based reforms.
- Generating evidence on the most effective ways for Zambia to invest its finite resources to support green growth and climate resilience, and translating this evidence into policy making at a national and sub-national level.
Elections- Zambia will host its next national election in 2026. Zambia’s elections are amongst the most competitive in Africa. The UK will support Zambia to deliver a free, fair and credible election. This will underpin Zambia’s reputation as a stable democracy, enhance the resilience of its electoral institutions and promote trust and legitimacy in the electoral process. Outputs will include:
- Support process and results verification by deploying monitors to a representative sample of polling stations nationwide to verify election processes and results.
- Work with the Judiciary to develop and implement Electoral Dispute Resolution (EDR) mechanisms to support pre- and post-election disputes.
- Promote voter education focused on increased participation amongst marginalised groups.
- Working with media organisations to improve journalism standards, advocate for media freedoms and counter the risk of mis/dis information.
Public Sector Reform- To reduce poverty, Zambia needs an effective public sector to manage its public finances, administer policies and services, collect revenue and reduce corruption. Public sector reform is considered by FCDO to be a ‘great buy’. Outputs will include:
- Tackling corruption through prevention and prosecution. This will build on the UK’s £2,000,000 investment to strengthen Zambia’s anti-corruption case investigations which resulted in recovered assets at an estimated value of at least £41,000,000.
- Support to decentralisation efforts, including building the capacity of ministries and local authorities to deliver services and local development.
- Strengthening governance in social sectors to build human capital, including social protection, education, and health to improve targeting, resource allocation, delivery, and accountability to ensure that service delivery is equitable, effective and transparent, enabling better and more inclusive outcomes for vulnerable populations.

Civic Space- Support for democracy is high in Zambia, but there is limited pressure and engagement from the public to strengthen the institutions that uphold democracy outside election periods. Communities most affected by national issues like climate change have the least power demand change. ESD will work with citizens, civil society and the media to build demand for deep, structural reforms that enhance democratic processes long-term. Outputs will include:
- Promoting bottom-up advocacy on climate action, connecting communities with policy and law makers and supporting local communities to demand the changes they want to see.
- Strengthening civil society capacity to analyse and engage with key development challenges and policy issues, including core funding to local civil society to rebuild a largely paralysed sector.
- Countering the risks of polarisation and mis- and disinformation. Increasing constructive engagement in policy and politics at the local and national levels and enhancing media freedoms and journalism standards.
ESD will have two cross-cutting outcomes, which are integral to achieving its objectives:
- Broader, more inclusive coalitions- Building wider, more inclusive coalitions of state and non-state actors (politicians, bureaucrats, business leaders, social movements, religious groups, traditional structures and citizens) to generate progressive ideas, advocate for reforms and increase the impetus for deeper, structural change. Coalitions can be formalised but more often they represent an alignment of interests behind an issue and may never meet. Partners will convene, coalesce and strengthen coalitions on different issues to build momentum towards reforms.
- Identifying opportunities for change- This output will focus on monitoring the trends, opportunities and political economy around issues and aligning investments to areas that can deliver the most impact, including by:
- Producing dynamic analysis to understand the political economy and power dynamics of key issues, helping identify where change is already happening and to mobilise to tip the balance in favour of reform.
- Testing proposals and ideas against political realities.
- Providing an independent review of the portfolio of engagement.

Summary of Outcomes and Outputs
Outcome 1: Growth
Outputs
Technical assistance to policy makers
Data, research and capacity building
Green growth and climate resilience
Outcome 2: Elections
Outputs
Process and results verification
Electoral Dispute Resolution
Voter education
Media freedoms
Outcome 3: Public Sector Reform
Outputs
Corruption
Decentralisation
Governance in social sectors
Outcome 4: Civic Space
Outputs
Climate action
Civil Society
Media freedoms
Cross-Cutting Outcomes
Broader, more inclusive coalitions
Identifying opportunities for change

1. Monitoring, evaluation and learning will be embedded across the programme to ensure we can assess impact and support adaptation/ flexible programming. This is outlined further in the Appraisal, Commercial and Management Case.
2. In the current context, we assess the four outcome areas to have the greatest chance of making transformational change. However, ESD will begin implementation in 2025 and will run to 2032; during that time, there will be political, context and strategic changes (some of which we can predict, and others we cannot). Having a seven-year programme gives partners the opportunity to work on systemic, transformational changes that take time to achieve. As such, we anticipate most of the investments under ESD will be multi-year commitments (subject to UK fiscal allocations). However, having the flexibility to shift focus, approach and partnerships during implementation is central to the design of the ESD Theory of Change.
3. As the context evolves (for example, following the 2026 election), new opportunities will arise and existing areas of work may lose momentum. To be effective, and maximise value for money, ESD will need to respond to this. For example, based on our current assessment of the 2026 election risks and opportunities, we have prioritised working with the Judiciary. We are not proposing to provide support to strengthening parliamentary processes and accountability of MPs, political parties and other local political actors. However, if an opportunity arises to do impactful work in this space that could support our objective of Zambia delivering free, fair and credible elections, then we would consider this. Likewise, under the existing Government, corruption and decentralisation are areas of public sector reform that have traction. If the administration changes in 2026, we may achieve better value for money by shifting our support to higher priority areas. To manage this flexibility, investments will be guided by an annual strategy which will assess the ongoing relevance and impact of investments, as well as emerging opportunities. This is detailed in the Appraisal Case and Management Case.

ESD: A STRATEGIC UK INVESTMENT
1. The UK sees democratic governance as an important enabler for Zambia’s development agenda. Evidence shows that, on average, democracies outperform autocracies in multiple measurements: democracies have higher economic growth[27], better health outcomes, improved access to education, better gender equality and are less prone to domestic and international conflicts. But the strength of the democracy also matters. Moderate levels of democracy are often tainted by high levels of corruption, violent civil conflicts, and meagre economic outcomes, as well as deficient delivery of public goods[28]. Whereas mature democracies, those with fully free and fair elections, free media and civil society, and a strong rule of law promote the accountability and incentives needed for ruling elites to invest in the welfare of their citizens. They are better at absorbing and channelling discontent through legal and political structures and accountability mechanisms.
  [27] Democracy Does Cause Growth – Darren Acemoglu et al., 2019
  [28] V-Dem Institute, Case for Democracy Report 2023, https://v-dem.net/documents/34/C4DReport_230421.pdf
2. A more inclusive democracy will support Zambia to achieve its development ambitions. Studies show that as democracy improves in Zambia, so does economic growth[29]. A more inclusive democracy, one that is accountable, transparent, independent, and participatory, will drive improved service delivery, more equitable use of resources, greater climate resilience and adaptation, reduced corruption and increased gender equality. Zambia can also be a positive example to others. Across the southern African region, and the continent, there is a growing trend of non-democratic governments looking towards non-UK aligned actors for economic and security support. By demonstrating an alternative path to economic growth, one that is inclusive and sustainable and underpinned by a resilient democracy, Zambia’s path out of poverty could support wider UK continental and geo-political objectives.
  [29] Giovanni Marco Carbone, Vincenzo Memoli & Lia Quartapelle (2016) Are lions democrats? The impact of democratization on economic growth in Africa, 1980–2010, Democratization
3. ESD will support Zambia to deliver the ‘democratic dividend’. It will contribute to the UK achieving its vision of a prosperous and stable future for Zambia’s people based on inclusive and sustainable growth, strong democratic institutions and values, and resilience to poverty and shocks. ESD will form part of a package of bilateral programmes which will address the well-established drivers of poverty in Zambia. All programmes are focused on the same goal – to prevent Zambia from becoming the third poorest country in Africa by 2060, by ending extreme poverty. Chronic, deep and multi-dimensional poverty is widespread in Zambia, particularly in rural areas. Poverty is the result of a vicious cycle of exclusive economic growth, low levels of human development and high exposure to shocks. Long term under-investment in basic services has resulted in human development outcomes being on par with Africa’s conflict affected states[30]. Zambia has one of the highest teenage pregnancy rates in the world (one in every three girls in becomes a mother by the age of 18 years) and it remains one of the most undernourished countries in the world. Access to services (health, nutrition, family planning, education, financial services) for the poor is constrained by inadequate infrastructure, systemic inequalities, and socio-economic barriers.
  [30] World Inequality Database Zambia - WID - World Inequality Database - note the quality of data is considered poor. Gini coefficient: Zambia's Inequality Levels | 2023 | Economic Data | World Economics
4. FCDO will implement five independent but complementary programmes to support the UK’s diplomatic influencing, which will include:
  Effective State and Democracy Programme, which will support an effecive state to deliver strategic reforms, strengthen institutions to be more democractic, increase demand for democracy and build broader coalitions of support for reforms.
  UK/Zambia Poverty Reduction Programme, which will build on decades of UK support for social protection, to enhance responses to shocks and opportunities for women and girls, including in nutrition, sexual and reproductive health, education, empowerment and livelihoods.
  Zambia Rural Climate Resilience Programme, which will alleviate rural poverty through inclusion of smallholder farmers within sustainable and climate resilient agricultural value chains that can raise incomes and provide resilience to climate impacts.
  Private Enterprise Programme Zambia Phase II, which creates investment in Zambia by building the capacity of micro, small and medium sized enterprises and systematically transform the finance and investment environment.
  Enhancing the Quality of Education in Zambia, which will work with Zambia’s Ministry of Education to tackle some of the key challenges to strengthening quality of education for all.

ASSURANCE STATEMENTS

- Gender Equality Act- Zambia ranks 87th in the Gender Equality and Governance Index, recognising the lack of gender parity in school completion rate, women’s participation in decision-making and formal employment, and women’s high levels of poverty. Women and girls continue to be in the periphery of development and most of them remain underserved with limited life opportunities, facing multiple deprivations and vulnerabilities, including harmful gender norms such as gender-based violence and norms regarding male ownership of home and assets. To be successful, every intervention under ESD will need to consider opportunities for strengthening gender equality and inclusion. ESD will therefore integrate gender equality into the analysis, design, implementation and monitoring and evaluation of each activity through its operating principles (see Appraisal Case).
- Public Sector Equality Duty- ESD will endeavour to promote equality amongst its staff and beneficiaries, regardless of age, disability, gender, pregnancy and maternity, race, religion or belief, sex and sexual orientation. Inequality (including between people who share protected characteristics and those who do not) is at the heart of Zambia’s governance challenges, and will be central to the activities supported through ESD. All partners will be required to take steps to meet the different needs of people who share a relevant protected characteristic, actively encourage participation by underrepresented groups and take steps to meet the different needs of people with disabilities.
- Climate and Environment- A Climate and Environment Risk Screening has been undertaken for ESD. The programme scored 14 (moderate risk), meaning that climate related risks could possibly impact on the programme success. The nature of the proposed support is such that no harm will be done to land or biodiversity, nor will the programme involve any investment in fossil fuels or go against Zambia’s climate plans. Shadow carbon pricing is not assessed to be needed. However, the impact of climate hazards on Zambia’s vulnerable population could exacerbate pre-existing governance challenges (and conversely, improvements in governance will reduce vulnerability to climate change). ESD is therefore expected to deliver International Climate Finance (ICF) eligible activities. ESD will increase Zambia’s resilience to climate change by supporting the state to deliver for those most affected (people living in poverty, women and girls, people with disabilities, marginalised groups), ensuring the most affected have greater representation in demanding for climate action and improving the policies and institutions that are instrumental in reducing climate vulnerability (such as natural resource and land governance). Exact proportions of ICF-eligibility will be determined once focus areas are agreed (and monitored as the programme evolves). ICF KPIs will be included in the log-frame to track the contribution ESD is making to the UK’s ICF target.
- Counter Terrorist Financing and Anti-Money Laundering- The threat of terrorism in Zambia is low, although terrorism is prevalent in neighbouring countries and in the region and so risks remain. ESD, in line with FCDO policy, will have a zero-tolerance approach towards terrorist financing and money laundering. Appropriate measures will be put in place to manage any risk (see Financial Case). This risk will be reassessed, and mitigating measures revised, as necessary throughout the life of the project.
- Disability and Meaningful Engagement of Organisations of Persons with Disabilities (OPDs)- Prevalence of disability is estimated to be 10.9% among adults (18+ years) and 4.4% for children in Zambia. People with disabilities still endure high levels of discrimination and inequality, in part because of entrenched negative public attitudes and a lack of or limited awareness. There are significant barriers to accessing services, including about 1 in 10 persons with disabilities experiencing problems with accessibility[31]. Disability considerations will be included in contracts to ensure partners build it into project design. Disaggregated data collection will help assess whether people with disabilities are meaningfully included in programme activities.
  [31] https://www.unicef.org/zambia/reports/zambia-national-disability-survey-2015
- Safeguarding- FCDO takes safeguarding seriously and will communicate this clearly to all partners. Mitigation measures will be put in place to reduce the risk that staff delivering/ engaging in the programme abuse positions of power and inflict forms of harassment, sexual exploitation or abuse against programme participants/ beneficiaries. All partners will be expected to have strong safeguarding protection and zero tolerance policies against bullying, harassment, and sexual exploitation. They are expected to ensure that all employees understand and adhere to policies, including reporting suspected cases of abuse or misconduct. If cases arise, FCDO has strict procedures in place for managing the response.
- Risk- Risk throughout the life of a programme will be managed in line with the agreed risk appetite using appropriate controls. The risk appetites for ESD, the overall risk rating and the risk management processes are outlined in the Management Case. A risk register is included in Annex A.
- Partnership Principles- Partnership Principles (PPs) are one of the tools the UK uses to inform and shape our overall strategy for engagement in Zambia. These principles will be used to assess the UK and Zambia’s shared commitment to reducing poverty, respecting human rights, strengthening financial management and accountability and strengthening domestic accountability. The UK’s PPs will be updated for Zambia in 2024, and an assessment will be included in the Annual Reviews of this programme.
Appraisal Case

The approved Concept Note sets out the need to embed democratic values in Zambia’s institutions and practices and support an inclusive, effective state, which delivers poverty reduction and growth for all its citizens. The Strategic Case sets out the challenges Zambia faces, the opportunity the UK has to support Zambia on its reform path, and the approach ESD will take to support Zambia in achieving positive change. The Appraisal Case assesses the options for delivering the core programme elements (as outlined in the Strategic Case). It sets out the operating principles that are required to operationalise this programme, scores the possible delivery options and develops, in more detail, the preferred option.

OPERATING PRINCIPLES

Four principles will operationalise the approach:
- Flexibility and adaptability- This programme will be flexible, meaning it will deal proactively with uncertainty and complexity, identifying where it exists, through systematic political economy analysis, and building in mechanisms to respond to and manage it. This will allow the programme to keep operating under significantly different circumstances, including across election cycles, and manage the risks of political and contextual shifts. ESD will have the ability to move funds and resources where they can have the most impact. Flexible partnership arrangements will give FCDO access to the right partners at the right time. The programme will also have elements which are adaptable. For some areas of the programme, there is sufficient evidence of the needs and pathways to change to have confidence that our investments will deliver the desired outcomes. For other areas, there is less evidence on effective pathways to change. An adaptive approach, one that tests different options before scaling (or failing) and uses feedback loops to build the evidence base, is therefore more appropriate. The programme will use the Strategy Testing approach pioneered by the Asia Foundation.[32] The approach to flexibility and adaptability is covered in further detail in the Management Case.
  [32] Strategy-Testing-An-Innovative-Approach-to-Monitoring-Highly-Flexible-Aid-Programs.pdf (asiafoundation.org)
- Coalitions for Change/ Issues Based Working- The approach centres on building and strengthening coalitions that can drive meaningful change. To do this, we require a nuanced understanding of the forces at play - those that seek to drive change, those that want to maintain the status quo, and their respective interests – and the ability to engage with them productively. This means not only understanding the key players but also tapping into the informal networks and underlying incentives that influence their decisions. In mapping these actors and the dynamics between them, we can identify opportunities where the right alliances can tip the scales. As the political landscape inevitably shifts, we need to be able to sustain these coalitions, ensuring they remain cohesive, adaptable and resilient. Through this approach, we will prioritise where our involvement can tip the balance of power toward reform, ensuring decisions regarding trade-offs are made consciously and investments maximise impact and value for money.
- Locally owned and sustainable- Our work will be grounded in respect and partnership, prioritising Zambia’s needs for development; this matters both for the success of the programme and for sustainability beyond the life of the programme. We want to create genuine, equitable, strategic and long-term partnerships that are beneficial to Zambia. This means promoting Zambian leadership, working within Zambia’s existing political realities, building trust, and establishing stronger, more equal relationships. By recognising and engaging with the political structures as they are, we can deliver politically informed interventions that are responsive to Zambia’s priorities for sustainable and inclusive growth. As far as possible, the programme will be steered and implemented by Zambians, whether through government or through non-state actors. Power in Zambia is highly centralised, making elite level engagement crucial for driving reform. Persuading key decision makers and aligning with their interests is often essential for progress. Most successful change aligns with elite motivations and vested interests of those who hold power. Alongside elite engagement, a key aspect of this programme will be working with (formal and informal) grassroots organisations. The supplier Terms of Reference will indicate the percentage of funding that should be reserved for local organisations. The UK will offer our expertise and deploy our diplomatic capabilities to bring together diverse actors for coalition building and to amplify Zambian voices.
- Gender equality and inclusion- To be successful, every intervention under ESD will need consider opportunities for strengthening gender equality and inclusion. ESD will therefore integrate gender equality into the analysis, design, implementation and monitoring and evaluation of each activity. For some activities, gender equality will be the main objective (such as increasing women’s political participation). In other areas, gender equality will be mainstreamed, meaning gender equality is not the main objective, but gender dimensions are fully integrated.

DELIVERY OPTIONS

The approved Concept Note set out four options to be tested during the design stage:
- Do nothing.
- Deliver all programme activities through a single supplier.
- Split the programme into smaller projects delivered through multiple agreements.
- In-source the management of the programme.

COUNTERFACTUAL/ DO NOTHING

1. The UK could choose to not implement this programme. The decision about whether to implement this programme is about trade-offs: whether reform would happen anyway; the opportunity cost of investing in good governance and democracy over other development areas; and whether the UK is the best partner to deliver.
2. The trajectory on a range of democracy and governance indicators has been broadly positive in recent years[33]. The UK has made a moderate contribution to this effort through a combination of programming (£4.95 million, 2021-2024) and development diplomacy. Other Cooperating Partners are providing support across a range of democracy and governance areas in Zambia. The US and Germany support the country’s decentralisation agenda, Germany, EU and US support Zambia to reform its public finances, and the EU is investing in civil society participation and access to justice.
  [33] Our World in Data, Democracy: Civil Society Participation, Deliberative Democracy Index, Deliberative Political Institutions Index, Freedom of Association, Freedom of Expression, Judicial Constraints on the Executive, Participatory Democracy
3. However, as set out in the Strategic Case, our analysis is that there are opportunities now to tip the balance in favour of deeper, locally led reforms that deliver for citizens, and we believe that the UK is well placed to do this. The UK has a close partnership with the Zambian Government, built on decades of trusted working relationships and aligned values. Our joint diplomatic and development mission allows us to apply a political lens to development issues and use our diplomatic reach to engage key political actors to unblock barriers to development. We have been, and will continue to work in lockstep with reformers within the Zambian system to deliver and protect the governance structures that underpin economic reform.
4. The funds spent on this programme could instead be spent in other areas of the BHC portfolio; for example, on education, social protection, nutrition or climate-resilient agriculture. All areas are important for addressing poverty in Zambia. However, all are contingent on having effective state and governance structures. The counter-factual is a state which does not deliver for its citizens, is undermined, and a drift towards populism and the non-democratic regimes which make up much of the region. Hence, while building more effective, accountable and inclusive institutions at all levels is a standalone SDG (SDG 16), it is also a critical enabler for success in every development sector. As such this programme is characterised as a necessary enabler for poverty-reducing programmes in Zambia.

APPRAISED OPTIONS
1. It is recommended that the UK does intervene and invests £38,000,000 in this programme. The £38,000,000 value was derived from a bottom-up cost assessment of the investment needed to substantially increase the UK’s ambition in this space, using the UK’s average expenditure on similar activities from 2021-2024 as a baseline. The assessment was based on a three-fold increase in spend to the range of democracy and governance support[34], a two-fold increase in support to the policy and strategy[35] work, plus the addition of a programme funded role to support the increase in ambition. This gives a total programme value of £38,000,000 over seven years. Investing a smaller amount is not recommended on value for money grounds because the UK can optimise the ratio of management costs to project delivery.[36] As such, FCDO appraised the options outlined in the Concept Note (plus an additional option) to deliver maximum impact for the £38,000,000 investment.
  [34] FCDO invested roughly £1,500,000 per year on support similar to that which is proposed under the DDF/DFC.
  [35] FCDO invested roughly £500,000 per year on support similar to that which is proposed under the SERF.
  [36] Through the Zambia Democratic Governance Programme (ZDGP, 301270, 2021-2024), the UK implemented a similar programme to this one but on a relatively micro scale. ZDGP, like ESD, was designed to be a highly flexible mechanism. It required substantial time and resources to operate for the outputs achieved. A review of ZDGP determined that it would be more cost-effective to operate at a larger scale because the ratio of management costs to project delivery would be optimised. This review formed the basis for the proposed scale of ESD.
2. The option of in-sourced management was discounted. A ‘make vs buy’ cost analysis shows that FCDO would pay 19% less over the life of the programme if management was insourced. However, managing a programme of this scale and complexity would require more staff than the British High Commission Lusaka can accommodate within the headcount limits set by HM Treasury for the FCDO. Moreover, this saving does not account for the investment FCDO would need to make in recruiting, upskilling and managing additional staff within FCDO rather than accessing this expertise from experienced professionals already available in supply market. The lack of flexibility this model would create could also limit the programme’s ability to respond quickly to change, the cost of which could easily exceed the 19% differential. As such, in-sourcing is not a viable delivery option. The three remaining options are:
- Option 1: The single ‘Fund Manager’ approach- FCDO competitively procures one supplier to deliver all aspects of the programme.
- Option 2: The project approach- The programme is split into four projects: ‘Effective State’, ‘Democratic Accountability, ‘Strategic Vision, Approach and Coherence’ and ‘Monitoring, Evaluation and Learning’. Each project is delivered by a lead partner, who in turn manages downstream delivery partners. The lead partners could be private sector suppliers, NGOs, a consortium or a multilateral agency.
- Option 3: The hybrid approach- This is a variation on Option 1. It places most of the resources into a substantial fund which is designed to be delivered flexibly and adaptably. This option differs to Option 1 in that it splits into a separate project the workstreams which focus on supporting Zambia to deliver strategic reforms. This option also includes a project which enables FCDO to directly fund through multilateral agencies or accountable grants/ contracts where there is a strategic reason to do so.

SCORING OF BENEFITS AND COSTS

The relative strengths and limitations of each delivery option were compared and scored against a set of key criteria. The following criteria were used:
Thematic flexibility- The ability to operate across different sectors and deploy a wide range of high calibre technical expertise.
- Programmatic adaptability- The ability to adapt ESD’s focus throughout the life of the programme, scale fast and fail fast, explore new ways of working, and establish continuous learning mechanisms to maximise impact.
- Partnership opportunities- The ability to create genuine, equitable, locally led, strategic and long-term partnerships that are mutually beneficial to Zambia and the UK.
- Timing- The ability to mobilise the programme and deploy resources in a timely fashion.
- Risk- The ability to manage risk, including managing a diverse set of activities and actors in a politically sensitive way.
- Resource Cost- The percentage of FCDO full-time equivalent (FTE) staff required to manage the programme day to day. This is determined by the number and complexity of agreements, how much accountability for compliance is expected to be outsourced to partner/s and FCDO’s role in strategy, design and coherence. Economic, social development, climate, M&E and compliance inputs will also be required across all options, so have not been included in the scoring.
Each option was scored against each criterion between 0 and 5, where:
0 = not fit for purpose
1 = inadequate for purpose
2 = slightly fit for purpose
3 = moderately fit for purpose
4 = mostly fit for purpose
5 = fully fit for purpose
Results of the scoring are set out in the following table, followed by a narrative summary of the pros and cons of each delivery option. Results were determined by a multidisciplinary team, consisting of governance, political, economic and programming expertise and overseen by FCDO’s Development Director for Zambia:
Criteria/ Option	Option 1	Option 2	Option 3
Thematic flexibility	4	3	5
Programmatic adaptability	4	2	4
Partnership opportunities	2	4	4
Timing	2	3	4
Risk	3	2	4
Resource Cost	4	2	3
Total	19	16	24

- Option 1- the single ‘Fund Manager’ approach:
  - The main advantage of this approach is programme coherence; a single fund manager would oversee the entirety of the programme’s strategy, objectives and analysis, and translate this into the incremental design, testing and monitoring of sub-projects. A single fund manager would work closely with the FCDO on governance of the programme, and enable lower direct transaction costs in the procurement and management of a single contract.
  - This option would, however, result in a complex sub-contracting structure of government counterparts, civil society organisations and sectoral experts. In practice, this will mean increasing downstream transaction costs. Internalising strategy and monitoring within the lead implementation partner could undermine independence and ‘critical challenge’. It is also a single point of failure; if the supplier fails to deliver to FCDO’s expectations, the entire programme will suffer. This option is also likely to have a slower set up timeline given the size and complexity.

  - Resource Cost- This option is expected to require 40% Full Time Equivalent (FTE) Grade 7, 40% FTE SEO, 30% FTE HEO and 50% FTE EO. Option 1 is expected to require the lowest resourcing costs (owing to FCDO having only one direct agreement, with accountability for compliance largely outsourced and a single management structure overseeing all activities).

- Option 2- the Project approach:
  - This approach would allow partnerships to be tailored more effectively to different stakeholders; FCDO would hold more direct agreements, overcoming the challenges of a complex sub-contracting model. More specific projects would open the market to more specialist providers (and more locally led partnerships). It would give a degree of separation between highly political work and lower risk governance activities, particularly when programming across an election cycle. Further, separating strategy and MEL from delivery would ensure independent analysis and assessment guides programme level decisions and choices.

  - Dividing the programme into four main projects does, however, increase the programme management costs to FCDO considerably. The second major disadvantage of this approach is that it has potential to undermine coherence (particularly if different partners are working on both the supply and demand side of an issue) and adaptability (where funds might require relocation across partners). In practice, the independence of the strategy and MEL projects could limit the translation into programming, increasing the reliance on FCDO to provide this function.

  - Resource Cost- This option is expected to require 60% FTE Grade 7, 60% FTE SEO, 50% FTE HEO and 60% FTE EO. Option 2 is expected to require the highest resourcing costs (for both FCDO advisory and programme staff). There will be four lead partners and significant responsibility on FCDO to manage coherence.

- Option 3- the hybrid approach:
  - The benefits and risks for Option 3 are similar to Option 1. Most activities will fall under the large fund, giving a single partner oversight over a substantial amount of the programme. This supports coherence and adaptability. Support to strategic government reforms would be separated into a different project. This work has the potential to deliver high returns, but it is inherently more volatile and at risk if the political environment changes. Isolating this support from the wider programme enables FCDO to work in this higher risk environment, and to have a direct relationship with the partner implementing this support. It will also allow the UK to capitalise on the trusted relationships FCDO has built with key decision makers in the Zambian government.

  - There is a risk that these two projects operate in isolation, or even adopt divergent approaches or theories of change. This would need to be closely managed as we would want both to drive significant innovation. The risk of putting a large portion of the programme under one project remains, although is somewhat reduced by separating out the higher risk economic reforms work. This option also increases the management burden on FCDO: there would be at least two direct agreements (plus the potential for other direct agreements where there is a strategic reason to do so).

  - Resource Cost- This option is expected to require 50% FTE G7, 50% FTE SEO, 30% FTE HEO and 60% FTE EO. Option 3 is expected to require the median amount. There will be two commercial agreements, meaning most of the compliance accountability will be outsourced. Having a high benchmark for agreements directly held by FCDO will further reduce resourcing on FCDO.

RECOMMENDED APPROACH

Option 3 is the recommended delivery option for achieving the desired outcomes and delivering the best value for money (maximising each pound spent). Options 1 and 2 were explored through an Early Market Engagement (EME) exercise in December 2023. Option 3 was developed following the EME based on FCDO’s assessment of the requirements and risks. At the EME event, the market expressed a preference for an integrated approach (Option 1), believing that it will foster integration, mutual reinforcement and flexibility between projects. This option scored highly in these areas. However, the long mobilisation period and the risks involved with having a single point of failure make it a less desirable option for FCDO. The market broadly agreed with the tentative projects proposed under Option 2, but recognised that the investment needed to make the programme adaptable and coherent is unlikely to outweigh the benefits accrued in partnership opportunities. Option 3 balances the opportunities and risks. Having one substantial fund with the ability to operate across the democracy and governance spectrum responds to the market’s preference for an integrated approach (like Option 1). Isolating the support to strategic reforms will enhance the opportunities of working politically and reduce the impact on the broader fund if a change of government makes this aspect of the programme unviable. It is a moderate increase in programme management for FCDO, and coherence which can be managed by a strong governance structure (as outlined in the Management Case).

DETAIL ON PREFERRED OPTION (STRUCTURE OF ESD)

Figure 1- ESD Structure

ESD would be delivered through three projects:
1. The Deepening Democracy Facility (DDF): This will be the largest project by a significant margin and forms the centrepiece of the programme. The DDF aims to build on and develop new ways of working on issues described in the Strategic Case using an issue based, coalitions for change approach. The DDF will take a flexible, adaptive and locally owned approach to delivering the intended outcomes. In practice, this means the successful supplier will have the capacity to provide grants and technical assistance across a wide range of (ODA eligible) democracy and governance issues to allow them to shift focus, approach and partnerships during implementation. As outlined in the Strategic Case, a strategy will be developed at the start of each year to assess the ongoing potential of investments. The strategy will assess political, contextual and strategic changes, new or emerging opportunities, longer term opportunities on more complex reforms, and overall progress towards outcomes and impacts. This will form the basis for decisions on investments.
2. Funding under the DDF will be divided into three ‘pots’:
  1. Managed Fund: The majority of the DDF (up to 70%) will take the form of an unallocated managed fund to support delivery of the objectives. Resources to be programmed over time based on agreement by the Steering Committee (see Management Case). This fund can be allocated to:
  - Grants: Most of the managed fund will be reserved for grants to deliver projects. This could include grants to international organisations, but will emphasise support to local partners (in line with the operating principles). Operational guidelines for the management of the grants will be established by the management team, including, for example, different modalities for the awarding of grants and implementation of smaller and larger agreements. In specific cases, material support (such as equipment) may also be provided.
  - Technical Assistance: A small amount of the fund will be used for technical assistance, with a focus on convening, facilitating, enabling and connecting coalitions. Technical assistance may also be deployed to directly deliver the objectives of the DDF (e.g. embedded technical assistance in Zambian Ministries), or to support grants as part of a joint implementation package. The DDF is expected to be able to deploy expertise across a wide range of issues depending on where change is happening and therefore what change the UK can get behind. This will require a more flexible partnership approach than conventional consortia or consultant rosters.
- Management Team: The DDF will be led by the Programme Director, who has ultimate accountability for all programme activities. A Management Team will report into the Programme Director. The Management Team will lead the day-to-day implementation of the DDF, including operations, administration and compliance. There will be an allocation of around 15% of the funding to management (exact allocations will be led by the supplier to maximise competition and thus, increase value for money). We expect this team to be streamlined throughout the life of the programme, but it can flex to suit the needs of the programme as it evolves. The Management Team can also use its budget to draw on discrete technical advice to support the management of the fund as required.
Monitoring, evaluation and learning (MEL)
  - Monitoring- As part of its assurance requirements, the Management Team will be required to monitor activities delivered under the Fund. This will be a routine activity to ensure partners are delivering as per their agreements. It will also support performance and risk management. Monitoring findings will be reported back to FCDO through quarterly and annual progress reports.
  - Evaluation- Evaluation of projects will also sit under the Management Team. This function will assess whether activities are leading to the intended outcomes and contributing to the intended impact. Some activities (particularly where an adaptive model is being used or where there is limited evidence to support the Theory of Change) may require more intensive evaluation than others; this will be determined at the outset of the activity. Supplier bids will be assessed based on their proposed solutions for ensuring integrity and independence in evaluations. Evaluation findings will be reported to FCDO through quarterly and annual progress reports. It is not anticipated that there will be a mid/end line evaluation at the programme level; evaluations will be conducted for activities as required.
  - Learning- The Management Team will be responsible for embedding a culture of learning across the DDF. This will ensure the DDF supplier, and its grantees, improve over time through gaining experience, create and share knowledge, adapt approaches and scale/fail. Learning is a continuous process, but highlights will be captured in the annual strategy development for ESD (led by the Horizon Scanning Team). These highlights will be fed into FCDO through the Steering Committee and FCDO’s internal governance structures to ensure learning from the DDF (and other projects) contributes to FCDO’s broader understanding of operating in Zambia, what works in delivering democracy and governance programming and taking a flexible and adaptive approach.
- Horizon Scanning Team- The purpose of this team is to identify where change is happening, such that ESD can ‘get behind it’. This team will monitor the trends, opportunities and political economy around issues that can deliver the most impact. It will include political scientists, economists and social policy experts. The Horizon Scanning Team will have a mandate to provide analysis beyond the scope of individual projects under the DDF; it will provide a coherent assessment of the wider political, social, development and economic context, identifying opportunities for change, and where shifts in the balance of power may open space for reform. As such, the Horizon Scanning Team will act as an analysis and learning resource to the entire ESD programme and the broader FCDO portfolio in Zambia. It will be instrumental in ensuring that investments made under ESD (through the DDF, SERF and DFC) are strategic, innovative, and aligned with emerging opportunities for impactful change. The team will focus on understanding the political economy and power dynamics of key issues, helping identify where change is already happening and to mobilise to tip the balance in favour of reform. Products delivered by this team will be driven by demand, emphasising our focus on locally led interventions and equitable partnership with Zambian actors. One of the primary products will be the DDF strategy document produced at the start of each year, ensuring that ESD remains adaptable, responsive and influential in a constantly evolving context. The Horizon Scanning Team will also be crucial to advising the decisions taken by the ESD Steering Committee (see Management Case).

1. The Strategic Economic Reform Facility (SERF): This project will support Zambia to implement the transformational economic reforms needed to achieve poverty reduction. It will be highly opportunistic, responding to issues where the balance of power suggests reform is possible by building coalitions for change. Issues that are most likely to have an impact on Zambia’s economic structure and the growth elasticity of poverty will be prioritised. Reform areas could include (but are not limited to) growth areas where the politics suggests change is possible such as job creation, agriculture, drought and energy. This will involve working across the system to understand and unblock (political) barriers to change, build coalitions of support and provide technical advice to the government on improvements to its policies and programmes. The success of this workstream will be determined by the partner’s ability to analyse the political economy of different reforms, identify promising workstreams, recruit technical experts in the relevant fields and build trusted relationships with key policy makers in the Zambian Government. It is expected to be highly political, have the ability to deploy deep technical expertise, and be extremely agile. It is expected that the SERF will continue to work through the 2026 election and beyond, but it will demand a high degree of agility to adapt to changes at the policy and political levels.
2. The Direct Funding Project (DFP): This project will be an FCDO managed fund for direct procurement of multilateral, grant based partnerships (accountable grants) and commercial partnerships. The DDF and SERF are expected to be delivered through a commercial supplier. However, FCDO cannot manage multilateral agreements through commercial suppliers. Where a multilateral has a comparative advantage in delivering project objectives, the DFP will allow FCDO to put in place a Memorandum of Understanding with a multilateral agency. In addition, there may be other areas where it is more economic (or preferable for proximity purposes) for FCDO to have direct agreements with partners. It is expected that this project will only be used in limited circumstances; all partners will otherwise be managed by the DDF.
Programme Funded Post
In addition to the delivery projects, there will be one programme funded Senior Governance Adviser post to support delivery of the programme. This post will be at Grade 6 and will report to the ESD Senior Responsible Owner in FCDO. The advisor is likely to be a UKB staff member appointed through an internal recruitment process. If a suitable candidate is not identified, the positions will be advertised to external and/ or Zambian candidates. In line with FCDO Programme Operating Framework rules, the post will spend at least 80% of their time providing technical support to programme delivery and supporting the integration of outsourced and FCDO influencing. The other 20% will be spent giving FCDO real time insights into the functioning of ESD and maximising links with the broader UK portfolio in Zambia. The role will include:
- Driving integration between the suppliers and the British High Commission to ensure the suppliers’ influencing agenda is closely aligned with the diplomatic engine of the mission and that suppliers are leveraging the UK’s access and influence to support positive change.
- Being the lead technical adviser for ESD, ensuring that the programme delivers results and excellent value for money.
- Developing and maintaining relationships with the Government of Zambia in key ministries.
- Providing technical and strategic advice to the ESD Steering Committee (see Management Case) and ensuring that FCDO has a good understanding of the inner functioning of ESD and any emerging risks.
- Undertaking discrete analysis and reviews as part of the wider ESD team, for example on political trends, financial and commercial analysis and VFM assessments.
- Ensuring that the work of the SERF is well integrated into the Economic Development and Green Growth Team.
- Act as the bridge to FCDO programme management and compliance functions to ensure ESD suppliers have a deeply embedded understanding of FCDO expectations and interests.
- Creating links and partnerships across HMG in Zambia and with other centrally and regionally funded programmes.

VALUE FOR MONEY
The approach to measuring the value for money (VfM) of this programme will evolve as (i) the agreements are put in place with the delivery partners and (ii) areas of intervention are formally agreed. Knowing the parameters of the contract will be essential for assessing whether the programme is delivering “economy” and knowing what the areas of intervention are and consequently what the results will be is key to assessing “efficiency” and “effectiveness”. At each annual review, FCDO will complete a portfolio level assessment of VFM. Broadly, we assess that this programme will achieve VfM throughout its lifetime if:
Economy	The management structure is streamlined (relative to programme complexity), minimising overhead costs.
Efficiency	The process for turning inputs to outputs results in maximum benefit for the least amount of time and resources (particularly for adaptive elements). / Projects are scaled or stopped early due to effective performance management.
Effectiveness	The activities undertaken lead to changes in government policy or delivery. / Activities are designed and delivered as far as possible by Zambian partners.
Equity	The impact is distributed fairly and leads to improved outcomes for women and marginalised groups.

In summary, it is recommended that the UK invests £38,000,000 in this programme. Strengthening democracy and governance is a priority for the UK in Zambia; ESD will enable the UK to meet its strategic objectives and deliver a high return on investment. The activities will be delivered through a hybrid model (comprising of a large flexible fund, a smaller facility focussed on strategic reforms) and a project for direct FCDO agreements, with a strong focus on flexibility, adaptability, strategic prioritisation, local ownership and gender equality.

Commercial Case

The Appraisal Case advised that ESD be delivered through three projects: the Deepening Democracy Facility (DDF), the Direct Funding Project (DFP) and the Strategic Economic Reform Facility (SERF). The route to market for each project is outlined in turn.

DEEPENING DEMOCRACY FACILITY

1. A mini competition under the FCDO’s Global Development Delivery (GDD) framework will procure a commercial contract for delivery of the DDF. To deliver the DDF, FCDO will require access to the fullest possible range of specialist expertise, including the for-profit sector and the non-profit sector. FCDO’s GDD procurement framework offers direct access to a pool of pre-qualified suppliers experienced in delivering international development and governance programmes. Lot 7 of the GDD framework provides a means to approach a sub-sector of the market (including profit and non-profit organisations) specialising in governance-related programme work for contracts over £7,000,000 in value. Many suppliers on the GDD framework are already delivering or have delivered commercial contracts for FCDO in this area. Suppliers on the GDD framework have been pre-assessed in the specific area of grant fund management, giving strong confidence in the ability of this pre-defined pool of suppliers. Furthermore, as GDD has pre-assessed suppliers on their ability to comply with all relevant UK legislation (including compliance, supply chain monitoring etc.), potential bidders can focus solely on generating good quality tender responses addressing the specific requirements of the proposed contract.
2. A commercial contract is preferred because it will give FCDO the control needed to direct the supplier’s work by pre-defining a set of KPIs/deliverables. FCDO can actively manage the performance of the supplier’s grant management, technical assistance delivery and management and learning teams in line with a clear schedule of payments to incentivise timely, effective delivery against FCDO priorities.

STRATEGIC ECONOMIC REFORM FACILITY

An open tender will procure a commercial contract to deliver the SERF. Like the DDF, we assess that a commercial contract would be the most suitable route to market for the SERF. SERF is a unique piece of work, and running an open tender would provide a wider range of supplier options to assess, rather than being limited by the GDD Framework. This is because:
- We have a concrete understanding of the remit and scope of the requirement; FCDO can therefore task the supplier to complete work (in line with the existing understanding the UK has with the Zambian government for this kind of support).
- It is preferable to actively manage the performance of services in line with a clear schedule of payments to incentivise timely, effective delivery against FCDO priorities.
- We require access to the fullest possible range of available expertise, including the for-profit sector (grants cannot be awarded to for-profits and would artificially limit the supply market).
- FCDO requires maximum ability to actively direct the Supplier’s work, by pre-defining a set of KPIs/deliverables.
- Using a formal technical evaluation should incentivise suppliers to propose a locally oriented delivery model.
- A commercial evaluation should incentivise competition on pricing and focus suppliers on the importance of offering value for money in the delivery model.

DIRECT FUNDING PROJECT

1. This project will allow direct agreements with multi-lateral agencies and grant/ contract-based partnerships. The number of agreements that can be funded under this project has not been capped (although the bar will be high for direct agreements given the management implications). Where appropriate, decisions regarding partnerships under the DFC will be made by the ESD Steering Committee to ensure alignment with the wider support provided under ESD. Funding under this project will not be allocated at the outset of the programme; instead, funding will be allocated once a proposal has been received (by a multi-lateral or for/ not-for profit partner) and a decision is made to award funding. Memorandums of Understanding, Accountable Grants or commercial contracts will then be put in place.
2. In summary, this means that FCDO will be directly managing two commercial contracts (and overseeing activity delivered through a contract held by FCDO centrally). There is potential for additional Accountable Grant/s, Memorandum/s of Understanding or commercial contracts.
3. FCDO will also draw on its global partnerships to complement the investments made under this programme. This includes centrally managed programmes operating in Zambia and ‘buying in’ to agreements held centrally by FCDO. For example, British High Commission Lusaka will ‘buy in’ to FCDO’s agreement with the International Growth Centre (IGC) to deliver an evidence lab embedded within the Zambia Ministry of Finance and National Planning. The lab will prepare, analyse and build capacity within ministries on the use of data for policy making. The SERF and DDF suppliers will advise the IGC on the opportunities for strategic reforms, and the data and policy being produced by IGC will drive the advocacy and focus of the SERF and DDF suppliers. This will ensure that FCDO maximises the collective impact of its investments towards delivery of the UK’s Country Business Plan in Zambia.

CONTRACT DESIGN AND MANAGEMENT

Commercial suppliers will be invited to respond competitively. This provides a valuable opportunity to use competition to drive costs down, encouraging focus on value for money in the selection of partners. By requiring a coordinated approach and leaving open different possible delivery models, we will increase the chance that partners develop dynamic and responsive project proposals that meet FCDO requirements and work in partnership to deliver more efficient responses. For the two commercial contracts (under SERF and the DDF), performance will be managed throughout the life of the contract through:
- Contract design: The contract design will be outlined in a Terms of Reference (ToR), which will stipulate the specific requirements (during inception, implementation and closure), the payment model (including the Key Performance Indicators), roles and responsibilities (including in the governance structure), timelines, Value for Money indicators and compliance requirements. The ToRs will be used as the basis for the contracts and the bid assessments.
- Break Clauses: As described, ESD will evolve. The contracts will therefore be structured flexibly. They will include break clauses allowing for termination after inception if partner performance is unsatisfactory, in 2026 following Zambia’s election, and two years after that. Outside of these review points, the contracts will also allow for termination in the event of changes in the UK’s financial position or profound changes in the political environment which mean that progress towards the outcomes is unviable.
- Key Performance Indicators: KPIs will be used to incentivise supplier performance (and linked to payment). These will include ‘Delivery KPIs’ (relating to delivery of outputs and outcomes) and ‘Contract KPIs’ (relating to contract management performance). FCDO is acutely aware of the risk of setting perverse incentives through the KPIs (e.g. by linking payment to the quantity of outputs, rather than the quality); this will be a key consideration in the design of the KPIs.
- Value for Money:
- Economy: FCDO will assess proposals based on their costs. Through a commercial supplier, we can achieve economy by pre-agreeing limits for programme staff costs (international and local) and administrative charges for travel, overheads and training. We will also assess how partners will manage economy throughout the programme, such as their procurement strategies for inputs.
- Efficiency: Efficiency for ESD means having strong, streamlined management, having the systems and capacity to manage a diverse portfolio of work, being able to pivot, scale and close work quickly and economically, ensure that delivery partners efficiently convert inputs into outputs, and using the strategy and MEL functions to guide investments. Supplier bids will be assessed for all these areas.
- Equity: Given the level of inequality in Zambia, ensuring the programme reaches marginalised groups will be key to its success. All activities must demonstrate utility for those in rural areas, encourage and facilitate the participation of women and people with disabilities and measure success based on inclusivity.
- Effectiveness: ESD will be effective if it succeeds in sustainably increasing demand for more democratic governance, and if investments in support of the government and its partners leads to improved policies and programmes that better meet the need of citizens. Effectiveness is therefore about scalability and leveraging results that are far beyond what can be achieved with UK funding alone. Suppliers bid will be assessed based on their ability to do this.
Reporting requirements: The contracts will specify reporting requirements, including quarterly progress reports to monitor activities and spending, annual work plans and results pathways, annual and mid-term reviews, project completion reports, quarterly financial forecasts and bi-annual financial expenditure reports.
BID ASSESSMENTS
1. Technical assessment will be undertaken by (at least) three staff from FCDO at Grade 6, Grade 7 and SEO level. The evaluators will have governance, political, economic and programming expertise, and will include a Senior Governance Adviser. Commercial aspects of the bids will separately be evaluated by commercial experts in FCDO’s Commercial Directorate. Evaluators will assess prospective partners’ technical and organisational capacity to deliver the objectives of the contract and deliver value for money.
2. The technical tender evaluation criteria will focus on[37]:
  [37] These should not be taken to be the final criteria as they will evolve as the sourcing strategy and bid documents are developed. The final criteria will be made public with the Invitation to Tender.
  - Ability to recruit an effective politically savvy team leader: This is the most important determinant of success but a consistent challenge for politically informed adaptive programming. Across a whole range of similar programmes, the market has failed to deliver good managers who can be politically savvy and facilitate change, or to assemble teams with these skills. The selection criteria will put emphasis on the strength of the team leadership and the core team; the resources and skills to use monitoring and learning as a core part of programme management; a clear plan to support grantees to influence policy change in priority areas; and solid financial management systems that can assure fiduciary integrity.
  - Politically and contextually informed approach: Ability to understand the context deeply and to build deep relationships of trust with key stakeholders. Ability to convert this understanding and these relationships into practical delivery.
  - Flexibility & Adaptability: Ability to focus selectively on issues with political traction and to withdraw support if needed. Experience of managing wide ranging projects and partnerships and responding to changing circumstances and new requests flexibly.
  - Quality of technical inputs: Demonstrate expertise in applied governance and political economy analysis, accountable and inclusive political systems, open societies and civic space, human rights, the role of institutions in service delivery, anti-corruption and illicit finance and pro-poor public sector governance (including the drivers and constraints to reform and the role of collective action problems).
  - Mainstreaming of operating principles and climate considerations: Extent to which the supplier has operationalised the operating principles and climate considerations within its proposal. Bids will be reviewed by FCDO’s Climate, Environment and Nature Helpdesk to assess its approach to mainstreaming.
  - Value for Money: Coherence between the technical and commercial aspects of all bids.

Financial Case

This section sets out the affordability, sources of funding and budget for the programme. It describes the mechanisms for disbursement, reporting requirements and FCDO and FCDO’s assurance framework.

AFFORDABILITY AND SOURCES OF FUNDING
1. This Business Case seeks approval for £38m over a seven-year period (2024-2031). 2024 will be a design year, during which time FCDO will procure the commercial suppliers. There is no spend anticipated in FY24/25. Inception (and spend) is likely to begin in FY2025/26. Launching of the contracts is likely to be staggered, with the SERF contract launched first (given the smaller scale), followed by the DDF contract. Staggering the launch of the contracts will support FCDO resourcing and (where applicable) will give suppliers sufficient time to prepare bids for both contracts. We expect the SERF implementation period to last roughly three months. The DDF inception period is likely to be around six months (recognising that this will be a larger, more complex model).
2. Funding for ESD has been included in FCDO’s ODA allocation plans for Zambia. The ESD budget will be classified as Resource Departmental Expenditure Limit (RDEL); and we expect this programme to have only very limited spend classified as Capital Department Expenditure Limit (CDEL), mostly around research. FCDO will confirm partners’ budgets annually to ensure the programme remains affordable within FCDO’s delegated ODA budget for the Spending Review period. To manage unforeseen changes in the UK’s financial context, break clauses will be included in all contracts. Accountable Grants and MoU do not legally commit the UK to providing funds.
3. It is anticipated that spend under ESD will contribute to the UK’s International Climate Finance (ICF) target. ESD will increase Zambia’s resilience to climate change by supporting the state to deliver for those most affected (people living in poverty, women and girls, people with disabilities, marginalised groups) and ensuring the most affected have greater representation in demanding for climate action. Given ESD won’t deliver a pre-defined set of results (rather it will aim to influence transformational changes), it is not possible at this stage to determine exact proportions of ICF-eligibility. However, all proposals under ESD will be tested for their contribution to climate positivity. Exact proportions of ICF-eligibility will be determined once focus areas are agreed (and monitored as the programme evolves). ICF KPIs will be included in the log-frame to track the contribution ESD is making to the UK’s ICF target. It is anticipated that the programme will contribute to:
  - ICF KPI 4: Number of people whose resilience has been improved as a result of International Climate Finance (for example, by supporting the government to implement agriculture policies that increase farmers adaptive capacity and increasing communities’ ability to collectively manage shocks through social accountability).
  - ICF KPI 15: Extent to which ICF intervention is likely to lead to Transformational Change (for example, through building wider coalitions of support for climate action, and by supporting the state to make evidence-based decisions on policy and resource allocation).

BUDGET PROFILING
Tentative Allocations to Each Project
Element	Total Allocation	% of BC Value
DDF project	£19,500,000	51%
DDF Contract- Management Team	~£2,925,000	~8%
DDF Contract- Horizon Scanning Team	~£2,925,000	~8%
DDF Contract- Fund to cover TA & grants	~£13,650,000	~36%
SERF project	£14,000,000	37%
DFC project	£3,000,000	8%
Programme Funded Advisor Role	£1,500,000	4%
Total	£38,000,000	100%

Tentative Allocation by Financial Year (FY)
Financial Year	DDF	SERF	DFC	Project-Funded Post	Sub-Total by FY
Inception Costs
2025/26	Six months, £500,000	Three months, £250,000	N/A	N/A	£750,000
Implementation Costs
2025/26	£500,000	£1,750,000	£500,000	N/A	£2,750,000
2026/27	£3,083,000	£2,000,000	£416,000	£250,000	£5,750,000
2027/28	£3,083,000	£2,000,000	£416,000	£250,000	£5,750,000
2028/29	£3,083,000	£2,000,000	£416,000	£250,000	£5,750,000
2029/30	£3,083,000	£2,000,000	£416,000	£250,000	£5,750,000
2030/31	£3,083,000	£2,000,000	£416,000	£250,000	£5,750,000
2031/32	£3,083,000	£2,000,000	£416,000	£250,000	£5,750,000
Total	£19,500,000	£14,000,000	£3,000,000	£1,500,000	£38,000,000

1. DDF- This project will be allocated £19,500,000, or 51% of the total programme value. This is the most wide-ranging and complex project under the programme and as such, will be the largest allocation under ESD. The allocation for the DDF will be broken down into three pots. For planning purposes, FCDO has used tentative allocations, but we will not stipulate these amounts in the Terms of Reference to drive competition amongst suppliers. We anticipate the spend on the Management and Horizon Scanning Teams to be relatively consistent throughout the life of the contract. Spend on the Managed Fund will vary depending on the size of the portfolio within each year and FCDO’s delegated ODA budget, but for planning purposes, a consistent level of spend is profiled.
2. SERF- £14,000,000, or 37% of the total programme value, will be allocated to the SERF over the seven years of the programme. This money will pay for a team of specialists to provide high-quality technical support, political analysis, communications advice and advocacy on key policies and public/private sector engagement to key government decision-makers. We expect the size of the team to be relatively consistent over the lifetime of the programme, and as such a consistent level of spend (~£2,000,000 per year).
3. DFP: This project will be allocated £3,000,000. Funding under this project will not be allocated at the outset of the programme; instead, funding will be allocated once a proposal has been received.
4. Programme Funded Advisor Role: This project will be allocated £1,500,000. This is an upper limit of expected costs, based on a Grade 6 UK staff member appointed through an internal recruitment process. Costs include National Insurance and Pension contributions, and the average costs associated with the FCDO providing the package of support given to UK based staff posted overseas. Funding for this project is profiled from FY2026/27 to account for the lead time on recruitments of UK staff based overseas.

PAYMENT PROCESS
All payments will be denominated in GB pound sterling. We will require all partners to monitor and manage exchange rate losses, as per FCDO budget policy. This is crucial given the likelihood of fluctuations in the Zambian Kwacha.
- For the DDF and SERF Commercial Contracts, payment will be made, in part, based on delivery of KPIs. The proportion of payment linked to KPIs will be agreed once further engagement with the market has taken place. The Terms of Reference for both contracts will stipulate performance-related pay mechanisms for both inception and implementation phases (based on achievement of milestone and delivery KPIs).
- For partners with Accountable Grants under the DFC, payment will be contingent upon submission of satisfactory progress report, expenditure report, costed work-plan, invoice and forecast expenditure for FCDOs financial year. FCDO will provide up to three months of advance funding provided we are satisfied with the forecasts for the forthcoming quarter. No payments will be made in advance of need. Partners will adhere to FCDO’s Eligible Cost Guidance for Accountable Grants, including for Non-project Attributable Costs (NPAC).
- For partners with Memorandums of Understanding under the DFC, partners must provide detailed financial reports that set out actual expenditure to date against the approved budget and quarterly forecast expenditure for FCDO’s financial year.

FINANCIAL RISK AND FRAUD
FCDO operates in an environment that is susceptible to fraud and financial mismanagement. In line with FCDO’s ‘Counter Fraud and Aid Diversion Action Plan’, our approach will ensure that systems and processes across the programme are fit for purpose. We will ensure adequate controls are in place that adhere to legislative and policy requirements, including in support of FCDO’s zero tolerance approach to fraud. Detailed mitigation measures will be taken to reduce the likelihood and impact of fiduciary risks. These include:
- FCDO has mechanisms to ensure that fit-for-purpose due diligence assessments (DDAs) are conducted. FCDO will conduct DDAs on all direct partners. As part of the tendering and contracting process, FCDO’s Procurement Department will conduct DDAs of suppliers. We will implement due diligence action plans arising from DDAs. For downstream partners, we will require assurances that DDAs have been completed which assess that partners have adequate financial, audit and fraud reporting systems in place.
- Delivery chain mapping exercises will be completed to assess risks throughout the flow of funds. Partners will be reviewed at every Annual Review and verified through spot-checks and field visits.
- Bidders will be expected to set out their approach to managing and reporting fraud. All partners will be required to share information on all allegations of fraud and corruption cases as per FCDO policy. We will promote an open and proactive approach to fraud with our partners, including at biannual events hosted by FCDO to discuss responsibilities with partners.
- FCDO will scrutinise all financial reports on receipt and prior to making further payments. Partners spend will be assessed at least quarterly to reduce the risk of financial mismanagement.
- FCDO will require the return of funds that cannot be adequately accounted for.
- All partners will be required to submit annual audited financial statements, conducted by an independent and qualified audit firm.
- If concerns arise, the FCDO reserves the right to conduct a special audit of the funds at any point in time. If concerns remain, the FCDO will consider suspension or termination in full or in part, will stop further disbursements and reclaim any funds already paid that have been used in a manner that is inconsistent with FCDO policies or contractual and grant agreements.
- FCDO and partners will maintain programme risk registers to continually assess fiduciary risks. Risk registers are reviewed and discussed with partners at least quarterly.

ASSET MANAGEMENT
All partners will be required to maintain an up-to-date asset register of all assets purchased using UK funds. The register will be submitted to FCDO annually. FCDO will conduct annual asset spot-checks of all partners and expect direct partners to do the same for their downstream partners. FCDO will ensure that the disposal of any assets at the end of the programme maximises value for money in line with the FCDO Programme Operating Framework rules.
Management Case

GOVERNANCE
There will be three levels to governance of ESD:
- Internal FCDO governance (how FCDO will manage this programme and ensure it is aligned with UK strategic priorities).
- Partner level governance (how the DDF, SERF and DFC partners govern their own work).
- Portfolio level governance (how all the aspects of ESD are governed to deliver towards common outcomes).

Internal FCDO Governance

1. This programme will be the principal instrument for delivering on the ‘freedom and democracy’ goal in the UK Country Business Plan for Zambia. This goal aims to support inclusive policies, democratic institutions and an engaged civil society. It also supports Zambia to project democratic values internationally. ESD’s contribution to this goal will be monitored through working-level Business Plan Delivery Meetings and overseen by the FCDO’s Country Board in Zambia. This will ensure the programme consistently delivers and responds to the UK’s objectives and strategic direction.
2. This programme will sit within BHC Lusaka’s Political and Governance Team. The core Management Team will consist of:
- Senior Responsible Officer (SRO)- accountable for ensuring that ESD meet its overall objectives and delivers in compliance with FCDO’s Programme Operating Framework (PRoF) Rules.
- Programme Responsible Officer (PRO)- The SRO will hold the PRO to account for providing day to day leadership, making effective decisions and providing direction for the Programme Manager and Programme Officer.
- Programme Manager- The Programme Manager will lead on financial management (making payments, managing budgets), risk management and compliance.
- Programme Officer- The Programme Officer will support with financial management and compliance, including tracking recommendations and arranging engagements.
1. In practice, the core Management Team will include a Grade 7 SRO (0.5 FTE), a Senior Executive Officer PRO (0.5 FTE), a Programme Manager (0.3 FTE) and a Programme Officer (0.6 FTE). The programme team will be supported by FCDO’s climate and environment, commercial, M&E, finance, compliance, economic, political and social development staff. The Development Director and Political and Governance Team Leader will provide strategic-level support.
2. The following Management Tools will be used by FCDO to aid programme management:
- A delivery plan will be used to keep track of the main programme activities, key decision points, and financial performance.
- A risk matrix and delivery chain risk map will be used to track programme risks and mitigation measures. This will be updated monthly. Partners will be required to provide risk analysis as part of their regular quarterly reporting to FCDO.
- A logical framework to track progress against the theory of change at the output and outcome level.
- A VFM framework to allow the programme team to track VFM over time. The framework will include metrics to measure economy (unit costs, key cost drivers), efficiency (performance of service providers, delivery of results), effectiveness (performance on output and outcome targets) and equity (how well the programme is benefitting disadvantaged and marginalised groups).
- The Annual Review will review programme performance on an annual basis. It will review partner performance, assess VFM (making use of the VFM framework), assess confidence of achieving the desired outcomes and assess risk.
The programme is designed to ensure that the level of complexity remains commensurate with the available programme management capacity. However, this will need to be actively managed throughout the life of the programme. Complexity for ESD will be driven by both the number of partnerships and the complexity of those partnerships (e.g. number of sectors, number of grantees, level of adaptability). The DDF will be the most resource intensive aspect; it will be delivered through a commercial contract (the supplier could be profit-driven and therefore incentivised to increase outputs at the highest cost- FCDO will need to closely manage the contract to achieve VfM), it will be the most wide-ranging (both in sectors and partnerships), and it will be the most adaptable element of the programme. The SERF will also be a commercial contract. It will be a smaller and more straightforward delivery model, but it will need to be highly responsive to government priorities and is the most at risk of political changes. Complexity at the portfolio level will also be factored into the decision on whether to allocate funding through the DFC. FCDO can limit complexity by:
- Staggering implementation- FCDO will stagger implementation within contracts while trust and capacity is built with the partners.
- Capping the number of subgrants if needed- FCDO will maintain the right to set a cap on the number of grants within the DDF. This is to ensure that the programme remains within the management capacity of the FCDO programme team. This will be established in the Terms of Reference.
The Programme Funded Advisor Role, as the lead advisor for ESD, will be a critical resource for the programme team. It will ensure the programme team has deep insights into the functioning of ESD and maximise links with the broader UK portfolio in Zambia. This role will be technical in nature, providing advisory inputs on strategic direction, opportunities and risks. Having an advisor with oversight over all partners will mitigate the risk that partners operate independently, rather than towards collective outcomes.

Partner Level Governance
1. Each partner will be expected to govern itself in a way which delivers the intended outcomes within FCDOs financial, risk and compliance requirements. Each partner will recruit, unless already in place, a core team to ensure successful delivery of their projects. Implementation for each partner will be preceded by a short inception period (the length of which will be determined by the complexity of requirement). Inception activities will include mobilising the core team, creating, documenting and implementing all required programme management, governance and financial management policies and processes, and developing an initial portfolio for Year One.
2. The Supplier will be responsible for producing annual and quarterly work plans for FCDO. For commercial suppliers, FCDO’s ‘contract management toolkit’ will be used on a quarterly basis to assess suppliers’ performance against KPIs, their financial management and whether they are capacitated to continue to deliver a quality programme. Partners will be expected to design and implement projects for approval at the agreed thresholds. Partners will manage any sub-grantees as per agreed criteria, including undertaking detailed due-diligence assessments of the grantee partners as well as all other mandatory due diligence.
3. Results will be at the core of all activities under ESD. Partners will need to demonstrate that their activities are leading to the intended outcomes and impact. Each partner will develop a comprehensive Monitoring, Evaluation and Learning (MEL) strategy which will be evaluated as part of the technical bid assessment or proposal. The reporting mechanism will be agreed during the inception phase (as this may differ for different partners). Results will be aggregated at the programme-level to demonstrate impact from partners working on a wide range of different issues, enabling the combining of qualitative and quantitative data to give a clear picture of how results are being achieved, in which sectors, at which levels of government and by which actors.
Portfolio-Level Governance
ESD is a relatively large and complex programme. To achieve its potential, integration and coherence between partners will be essential. ESD will therefore have a programme level Steering Committee. The ESD Steering Committee will be chaired by the FCDO Development Director. It will meet every six months and members will include senior staff from each of the suppliers, the International Growth Centre, government officials and external experts, as well as advisers from the British High Commission. The Steering Committee will have three primary functions:
  1. Setting the strategic direction- Drawing on outputs from the Horizon Scanning Team (particularly the annual strategy document), the Steering Committee will assess the operating context, political dynamics, opportunities and risks to guide the strategic direction. This will ensure the programme remains relevant, agile and aligned with UK priorities.
  2. Overseeing funding allocations- Thresholds for Steering Committee approvals will be determined in the Terms of Reference for suppliers, but it is envisaged that the Steering Committee will guide funding decisions made under ESD in line with the agreed strategic direction. Ultimate decision-making power will remain with FCDO.
  3. Fostering coherence and integration- The Steering Committee will play a crucial role in ensuring different interventions under ESD add up to more than the sum of their parts. Leaders in the committee will be expected to embed integrated ways of working within their respective organisations. The Terms of Reference for each partner will also outline how partners are expected to integrate outside of the Steering Committee.
The secretariat function for the Steering Committee is likely to be led by the Programme Funded Adviser Post, with input from each partner. This will also ensure that if contracts are staggered (and partners are brought on at different times), they are integrated into the Steering Committee seamlessly and with equal weighting.

ADAPTIVE MANAGEMENT

1. As outlined in the Operating Principles, all projects under ESD will need to be flexible. This means dealing proactively with uncertainty and complexity, being responsive to opportunities as they arise and building in ways to respond to and manage changes in the operating environment. ESD is a seven-year programme, so flexibility will be key to its success. To achieve this, partners will need to ‘think and work politically’. Transforming institutions and behaviours is not a technical approach, it’s about politics and power. This requires strong political economic analysis to understand the underlying interests, incentives and institutions that enable or block change.
2. The programme will also have elements which are adaptable (where the end goal is clear, but the pathways to achieving it are not). FCDO has used an adaptive approach in programmes around the world to address complex development challenges. Within the governance sector, new approaches have emerged[38] from the recognition that a conventional approach to programme design and implementation does not work in the face of complexity, often because the lever to change is hard to determine and the operating environment changes over time. In the classic example, court houses are constructed to increase access to justice, but they are never used because of a lack of judges or bureaucratic delays in court proceedings. Adaptive governance programming requires spending time understanding the underlying drivers of the problem and designing responses that will address them.
  [38] Including: - The Problem Driven Iterative and Adaptive (PDIA) approach, a step-by-step approach which helps break down problems into root causes, identify entry points, search for possible solutions, act, reflect upon what you have learned, adapt and then act again. - Issue-based programming (IBP), which involves choosing an issue that already has traction, digging into the detail of why it is taking place, who is gaining from it and what it would take to shift the balance to create a positive change. - Thinking and Working Politically (TWP), which points to the centrality of domestic politics in development outcomes. TWP has three core principles: strong political analysis, insight and understanding; detailed appreciation of, and response to, the local context; and, flexibility and adaptability in program design and implementation.
3. ESD will use an adaptive approach selectively, in cases where there is insufficient evidence of the needs and pathways to change to have confidence that our investments will deliver the desired outcomes (e.g. on the role of social accountability in building demand for democracy), or where the operating environment is fluid and is likely to demand an evolving approach. For projects which use an adaptive approach, partners will be expected to test different options before scaling (or failing) and to use feedback loops to build the evidence base. This will require more intensive management and MEL (which will be agreed during the project design). A critical aspect of ESD’s approach will be seamless integration with UK diplomacy work, ensuring coherence between programming and UK diplomatic outcomes. ESD delivery will be guided by BHC Lusaka internal governance structures such as Outcome Delivery Plans, Business Plan Delivery Meetings, and Team and Mission influencing goals. This alignment will ensure that programme interventions complement broader UK diplomatic objectives, leveraging the diplomacy resource alongside technical interventions for impact. The precise approach will be co-created with the supplier, building on FCDO’s experience of adaptive management in Zambia and integrating UK diplomatic access, networks and convening power to amplify ESD outcomes.
  Lessons Learned on Adaptative Management in Zambia
  - For some partners, an adaptive way of working is new and can be challenging to implement. The decision to use this approach should be cognisant of the additional resources required to do it well, and weighed against opportunities where the pathway to change is clearer.
  - Our greatest impact has been achieved when we focus externally on Zambia’s political economy, scanning for where change is happening. Where we have built informal coalitions to support change and got behind domestic change actors we can have good impact. When we do more general activities that are built around our priorities but not rooted in domestic change processes, we have sometimes achieved very little that is durable. Being aware of where change is happening and adapting to getting behind it is thus key.
  - UK programmes contribute to governance reforms (causation) when they understand and act on leaders’ political base for reform. That is, when they think and work politically. There is a dizzying array of causal mechanisms through which political leaders find support for change but understanding the menu of these is key to understanding why key actors were motivated by the UK programmes to initiate or institutionalise reforms.
  - Many reforms would have happened anyway without UK support. Other reforms are necessary but ultimately not in play. We add value in the “sweet spot” – where reforms could go either way, and UK support probably tipped the balance.
  - Scale matters. Adaptative projects can take significant time to design, implement, reflect and adapt. The output needs to be proportionate to the input to maximise efficiency.
  - A certain level of decision-making must be delegated to the supplier. Day-to-day oversight by FCDO, in a changing context, is inefficient. Delegated authority levels must be clear.
  - Leverage partners strengths. Partners integrate most effectively when they complement each other. Be clear on what value each partner adds so encourage joint working.
  - Zambia isn’t homogenous. What works in some places, won’t work in others. When delivering at local levels, work with local partners who understand local dynamics and cultures. This approach also delivers value for money when operating across big distances.
  - ‘Failing’ is a critical part of an adaptive programme, but it can be counterintuitive for partners. Willingness to fail will depend on the incentives partners have and the team, the ethos, relationships.

RISK MANAGEMENT

1. The overall risk rating for this programme is moderate, recognising that although Zambia is a stable country, political and contextual changes are likely over the course of the programme. The programme is designed to be flexible in response to this, but a flexible model will require more intensive management from FCDO. We accept that risks we take to achieve our objectives could impact our reputation, but we will manage these risks through careful communication and engagement with partners (both inside and outside the programme). We are receptive to taking risks where the benefit outweighs the cost and hold ourselves accountable in doing so. We only accept limited risks to our people and public service delivery and will implement strong measures to reduce fiduciary and financial and safeguarding risks. Programme management tools to manage risk are outlined above, and a risk register is included in Annex B.
2. FCDO will manage the programme using a portfolio approach. This means having a balanced portfolio of interventions with different risk levels. FCDO is focused on the hardest most intractable development challenges. Many policy reforms in this space are challenging to influence, making change difficult. We will not achieve change on every issue ESD invests in. We will actively engage on issues that we judge to be high impact, but also high risk. At the same time if the programme invests in areas with no political traction, it will not deliver value for money. The programme will be expected to de-risk interventions through excellent political and context analysis, but then to ‘fail fast’ when necessary. The programme will have a bias towards early exit of non-performing interventions; we would rather exit too early than risk investing in issues with the expectation that they may change.
Risk appetite by risk category:

Risk Appetites
Strategy and Context	Receptive	The nature of governance work means the context will fluctuate but we are receptive to this because it is critical to delivery of a successful programme. With a fluctuating context, FCDO also needs to be receptive to adapting its strategy. The programme is designed to allow this to happen.
Policy and Programme Delivery	Receptive	This programme is aiming to undertake very challenging, but potentially transformational work with government, civil society and the private sector. The programme is designed to be clear on the desired outcomes but with significant flexibility built in to allow for changes in how outcomes are achieved.
Safeguarding	Cautious	This risk appetite recognises that we cannot mitigate safeguarding risks entirely, but we can reduce the likelihood of them happening through policies and practices. We operate within our international obligations, including for human rights and for environmental conservation and protection. We aim to set high ethical and moral standards.
Public Service Delivery and Operations	Cautious	This appetite reflects our limited acceptance of risk to the security of our people, assets, and interests. FCDO implements policies that protect staff as far as reasonably possible through clear duty of care processes.
Financial and Fiduciary	Cautious	FCDO operates in an environment that is susceptible to fraud and financial mismanagement. It is vital that we maintain a robust approach to financial management to reduce the likelihood of fraud or financial mismanagement.
Reputational	Cautious	Given the nature of governance programming, it is possible that the UK will attract criticism for engaging in topics which can be politically sensitive or contentious. However, we will continue to manage this risk with careful communication and engagement with partners. The UK has good economic, political and cultural links in Zambia. While the UK’s work in Zambia currently has limited scrutiny in the UK, the scrutiny is much higher in Zambia.
People	Cautious	The adaptive nature of ESD means it requires significant input from FCDO. We need to ensure the programme is manageable and there is a consistent, clear governance structure in place.

Annex A: Risk Register

Risk Description	Gross Risk Rating	Mitigating Actions	Residual / Risk Rating	Within appetite?
Strategy and Context
There is a risk that the 2026 election significantly changes the operating context and reduces the political will for democratic governance. This would impact the ability of the suppliers to deliver activities and reduce the impact of the programme.	Moderate	FCDO has worked well with successive ruling parties in Zambia. An election strategy will be developed with contingency plans for different scenarios. UK engagement with all political stakeholders builds trust and means the UK is seen as a credible and impartial partner.	Minor	Yes
Policy and Programme Delivery
There is a risk that the SERF will not be able to operate if there is a change in government in 2026. The SERF is designed to be demand driven and shaped by the priorities of the government. If a new government did not want this support or has priorities that are not aligned to the UK, this aspect of ESD will need to be closed. This would have substantial implications for delivering the intended outcomes.	Moderate	The SERF is politically at-risk, hence the decision to deliver it through a separate supplier to the DDF. The contract will have a built-in break clause in 2026, which gives FCDO an opportunity to end the SERF contract. Regular engagement with the opposition will increase the likelihood of the UK quickly building a strong relationship with a new government.	Minor	Yes
There is a risk that the DDF supplier cannot deliver to the UK’s expected standard for this relatively large programme, and a significant portion of the programme is affected. This could lead to the DDF needed to be closed or substantially reduced, impacting programme outcomes.	Major	A strong Terms of Reference will allow FCDO to assess supplier bids effectively; a contract will only be signed if FCDO is confident the supplier can meet FCDO requirements. Staggering implementation while trust and capacity is built and reserving the right to limit complexity will help ensure the DDF meets FCDO’s standards. Break clauses will allow FCDO to exit the contract if required and pivot to a new delivery model.	Moderate	Yes
Output level activities do not lead to the intended outcomes and impact (or we do not have enough evidence to know).	Major	There is good evidence underpinning the Theory of Change. ESD partners will incorporate a Monitoring, Evaluation and Learning Framework across the programme that includes clear, measurable, and realistic indicators in the log-frame.	Moderate	Yes
There is a risk that suppliers operate in silos, reducing their collective impact. Suppliers may be fragmented or have misaligned objectives.	Moderate	The ESD Steering Committee will play a primary role in ensuring coherence, supported by the Programme Funded Advisor. Integration will also be encouraged through log-frame targets and KPIs.	Minor	Yes
People
FCDO does not have sufficient resources to effectively manage the programme, reducing oversight and increasing risk.	Major	Managing the number and complexity of agreements, and staggering them, will help ensure ESD is manageable for FCDO. Delegating accountability for compliance to commercial suppliers further reduces the burden on FCDO.	Moderate	Yes
Public Service Delivery and Operations
This programme is not affordable for the UK in the delegated ODA budget for FCDO, increasing instability in the delivery of this programme and limiting partners ability to operate.	Major	FCDO will confirm partners’ budgets annually to ensure the programme remains affordable within FCDO’s delegated ODA budget for the Spending Review period. To manage unforeseen changes in the UK’s financial context, break clauses will be included in all contracts. Accountable Grants and MoU do not legally commit the UK to providing funds.	Moderate	Yes
Financial and Fiduciary
Mismanagement of programme funds (in violation of FCDO regulations) by partners could result in losses of UK taxpayer funds, reduced development impact and reputational damage to the UK.	Major	The UK’s zero-tolerance approach to fraud and financial mismanagement is communicated to partners in their agreements, assessed through due-diligence assessments and continually monitored. FCDO clearly communicates to partners that we expect controls to be in place and for those controls to be followed. If fraud is suspected, FCDO have measures in place to pause or suspend funding as required.	Moderate	Yes
Safeguarding
Staff delivering/ engaging in the programme abuse positions of power and inflict forms of harassment, sexual exploitation or abuse against programme participants/ beneficiaries. This could result in significant harm to those impacted and reputational damage to the UK and partners if safeguarding policies and procedures are not in place/ followed.	Major	FCDO places high importance on safeguarding and will communicate this clearly to all partners. We cannot reduce the impact of safeguarding incidents, but we can reduce the likelihood. Primary partners are expected to update their safeguarding policies, and further cascade this to their downstream partners. They are expected to ensure that all employees understand and adhere to policies, including reporting suspected cases of abuse or misconduct. If cases arise, FCDO has strict procedures in place for managing the response.	Moderate	Yes
Reputational
The promotion of democratic governance can be politically contentious. If the UK and its partners raise issues which challenge the government's actions, there is a potential for backlash. The UK's ability to manage issues diplomatically and maintain the reputation of a critical friend is central to our ability to deliver this programme (and for the UK's wider equities in Zambia).	Major	The UK's political analysis and diplomatic strength supports our positioning on contentious issues. Under this programme, each activity will be assessed to determine potential risks and mitigation measures. Where activities are deemed to pose high reputational risks, we would either seek external advice by alerting government counterparts directly or amend activities to mitigate the risk of backlash.	Moderate	Yes
The nature of the UK’s support to Zambia is poorly perceived domestically and internationally thereby reducing Zambia’s ability to support peace and democracy on an international level.	Major	ESD will promote local ownership of programme implementation, working with Zambian partners in the design and implementation of projects supported by the DDF. The SERF will be demand led and will focus on delivering according to the priorities of the Zambian government, based on the interests and objectives of the government.	Moderate	Yes