## Annual Review Template

Title: AgDevCo Ventures - targeting early-stage enterprises in the agriculture sector to scale up activities
Programme Value £ (full life): £24,300,000		Review date: August 2025
Programme Code: 400140	AMP start date: / 24 October 2024	AMP end date: / 31 March 2035

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006681.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007096.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The FCDO AgDevCo Ventures programme (AV Programme) has provided design funds and seed capital for AgDevCo Ventures (AV), a highly additional investment vehicle which will provide patient capital in an underfunded market segment targeting early-stage investment capital to small and medium sized enterprises in the African food and agriculture sector required to scale-up their activities. FCDO will take a first loss approach which enables AV’s parent organisation, AgDevCo Ltd, to mobilise additional senior capital to raise a total investment amount of US$50m.
[note] Additionality refers to positive developmental outcomes that would not have occurred in the absence of the activity.
[note] Patient capital refers to longer-term risk tolerant investments, typically equity or debt, where investors are willing to wait a significant period (often several years) for financial returns, prioritising sustainable growth over quick profit.

The food and agriculture sector is critical for Africa. The programme supports the objective of driving Africa’s growth through a thriving commercial African agriculture sector that benefits people, economies and the environment.

The objectives of AV are to:
- create commercially sustainable agricultural and agribusiness enterprises that deliver a positive social impact directly through providing a variety of employment opportunities and attracting private sector capital;
- create direct and indirect economic benefits through more efficient markets and increased economic and investment activity in the agriculture sector; and
- support emergent commercial farmers and smallholders with the aim of increasing productivity and incomes, diversifying livelihood opportunities and moderating risks.

This Year 1 Annual Review measures delivery against process-based indicators and milestones that capture the initial setting-up of AV, informing the AR and overall output score.

Summary supporting narrative for the overall score in this review

AgDevCo Ltd is an experienced social impact investor with a proven track record of investing in agribusinesses in Sub-Saharan Africa. As set out in Section C below, AV has made a strong start with the successful recruitment of staff into key positions, agreed Investment Policies and Procedures (IPPs) and a healthy pipeline of around 60 agricultural and agribusiness companies exploring potential investment opportunities. Even though in the early stages, the AV Programme has delivered the year one process output milestones effectively and we have confidence that the programme will move swiftly into full implementation. We have therefore given the Programme an overall output score of A.

Major lessons and recommendations for the year ahead

FCDO should continue to press AgDevCo to complete the negotiations with other investors as soon as possible to bring about financial close i.e. finalising the fundraising process from investors and complete the establishment process, so that investments can start.

The programme team should agree appropriate logframe targets for the next stage of the programme with the AV team as soon as the total investment amount is clear. These targets should be built from the bottom up, based on the individual deliverables of the investee companies within the investment portfolio.

The programme team should agree appropriate methods of measuring VfM for AV as soon as is practicable. A series of indicators/metrics should be developed (together with the AgDevCo and the AV team) covering Economy, Efficiency, Effectiveness, Equity and Cost-effectiveness as foundation for systematically assessing and reporting on VfM. These metrics should be used to assess the performance of AV’s management and investment portfolio in the 2026 Annual Review and thereafter (see section D below for details).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC) posits that successful FCDO funding into well-targeted debt and equity-like investments in smaller scale African food and agriculture companies (food production, input supply, extension services, storage, processing etc.) together with focussed business advice and technical assistance, will showcase the opportunity and viability of these types of businesses to the wider investment market. In addition, a focus on gender equity, smallholder farmer inclusion and climate change adaptation will lead to a greater adoption of environmental, social and governance (ESG) best practise. Increased, reliable, responsible activity in this sector will lead to greater availability of foods and agricultural services, improved incomes, more jobs, and wider societal benefits. The graphic below provides a visualisation of this ToC:

Investing to support growth in this sector will also enable UK growth through improved access to the growing African consumer base in the future.

AV will work with investees to strengthen management and operational capacity, and to improve ESG and agronomic practices by pairing the capital provided with input from specialist Technical Assistance. Monitoring, evidence and learning (MEL) are key elements of the AV Programme. See Section G for details of the MEL plan that is being developed.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

It is too early to assess if the AV Programme is on or off track to deliver the expected outcomes and impact set out in the Business Case. AgDevCo have made considerable progress delivering the process-based output milestones and establishing the operating company for AV required for the successful implementation of the programme.

In the year ahead AV aims to complete negotiations with potential investors to enable the first financial close, agree the full suite of operational policies and procedures and start deploying capital into African agribusinesses that meet the AV Programme criteria.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The AV Programme is expected to contribute to the delivery of the Africa Directorates’ Country & Business Plan goal on inclusive and sustainable growth. It has laid the basic framework for successful investments over the lifetime of the programme. As the full programme budget is already committed, there will be no further financial outlay by FCDO to AV.

Based on overall progress (including the achievement of the output milestones in section C), the theory of change and VfM analysis, there is sufficient evidence to justify that the programme should continue as planned.

## C. DETAILED OUTPUT SCORING

Output Title	AgDevCo Ventures organisational structures in place
Output number:		1	Output Score:	A
Impact weighting (%):		100	Weighting revised since last AR?	No

Indicator(s)		Milestone(s) for this review	Progress
Output Indicator 1.1	East Africa local office established	Y/N	Met. Office has been established.
Output Indicator 1.2	AgDevCo staffing: / - Director appointed / - Recruitment of first Analyst/Associate / - Legal resource appointed	3	Met. / Director (Head of Ventures) appointed / Legal counsel appointed / ESG manager appointed / Associate position appointed
Output Indicator 1.3	IPPs finalised with FCDO engagement	Y/N	Met. IPPs were approved at the AV board on 28 Aug 2025.
Output Indicator 1.4	Due diligence with at least two investor groups initiated	2	Met. Due diligence has been initiated with potential investor organisations.
Output Indicator 1.5	Initial pipeline of four investee companies identified	4	Exceeded. A pipeline list of more than 60 companies has been developed.

Briefly describe the output’s activities and provide supporting narrative for the score.

This Year 1 Annual Review measures delivery against a set of process-based indicators. These milestones capture the initial creation and establishment of AV.

The target for Output indicator 1.1 has been met. The AV office, a separate space with essential systems, has been set up in Nairobi, Kenya, housed within the AgDevCo Ltd office to ensure inter-operability with the wider AgDevCo portfolio operations. This location also brings the benefits of synergies and experience from being co-located. Formal fitting out (a distinct identity) will commence following the formal establishment/financial close of AV.

The target for Output indicator 1.2 has been met. The three positions listed above have been appointed, in addition, an associate position has been recruited and an offer accepted. The Director, ESG Manager and Legal Counsel have commenced work, and the Associate is due to start in August 2025.

The target for Output indicator 1.3 has been met. FCDO has provided comments on the IPP documents to AgDevCo. These have been received and incorporated in the formal documents. The IPPs will be presented for approval by the AV Board at the next meeting.

The target for Output indicator 1.4 has been met. The due diligence processes required by potential investors have been initiated and are progressing. A due diligence visit to Kenya and Uganda took place from 9 to 13 June 2025.

The target for Output indicator 1.5 has been exceeded. A long-list pipeline opportunities has been developed with interest from more than 60 companies identified, significantly more than the four targeted. The AV team is having conversations with these potential investees, with the aim of screening initial deals in late 2025 and securing a first investment in late 2025 or early Quarter 1 2026.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year.

The AV Programme team should agree appropriate logframe Outputs with the AV team for Year 2 and beyond as soon as is practicable. These milestones for these Outputs should be built from the bottom up, based on the individual investments made.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

AV is operating in a specialised development investing space and global events mean that investment from investor groups providing risk tolerant-patient capital is harder to secure; while AV has met targets for this year, final agreement on additional investment has been slower than initially expected. The AV management team will continue to keep FCDO informed of progress as it negotiates with other investor groups and moves towards financial close.
RECOMMENDATION 1: FCDO should closely monitor AV’s progress in attracting additional investors, noting the significant impact of this factor on the programme’s viability. FCDO should also include a Year 2 logframe target for the total value of the funds which AV will manage.

The AV team has developed a broad and varied pipeline of potential investments which they should continue to develop as investment opportunities, so that they are in a strong position to progress these through the Investment Committee as soon as possible after AV is established.
RECOMMENDATION 2: the AV team should continue progressing their investment process while they wait for confirmation of additional investors into AV.

## D: VALUE FOR MONEY

Key cost drivers and performance

In the year 1 set up period, AV management and legal costs are being fully covered by interest earned from the capital advance (which was placed in an interest-bearing account, as agreed with FCDO).

Once operational AV will report against a range of VfM metrics. The FCDO management team will develop (together with the AgDevCo team) a series of VfM indicators/metrics to be used in the 2026 Annual Review and thereafter, based on those outlined in the Business Case. These might include:

Economy
Fund management administrative cost ratio (the ratio of fund management costs to total investment funds). AV is expecting to cover all normal fund management e.g. origination, structuring, executing and managing a portfolio of investment, and including normal support provided to investee businesses in terms of expertise, and investee support, e.g. additional support and advice that is provided to the investee both by AgDevCo staff and external services providers.

Efficiency
A leverage ratio (e.g. the ratio of private and DFI finance committed to AgDevCo investment).

Effectiveness
- Smallholder engagement rate, disaggregated by sex (ratio of total committed investment to number of smallholders engaged);
- Job creation rate, disaggregated by sex (ratio of total committed investment to number of jobs created); and
- Investee business survival rate

Equity
- Active portfolio investments that meet the 2 X Challenge Criteria;
- Active portfolio investments that meet Black Ownership & Leadership Development (BOLD) 30 criteria;
- Annual income generated ($) for low-income households per $ invested

Assessment of whether the programme continues to represent value for money
At this stage, based on the theory of change, outputs attainment and cost/VfM analysis, there is sufficient evidence for the programme to continue. The programme has a strong VfM framework in place for when the investment activities commence.

E: RISK

Overview of risk management

The overall risk score for the programme is Major. The risk appetites for each of FCDO’s seven risk categories (as noted below) remain appropriate when considered against residual risk levels. All programme risks are currently within appetite.

Risk Appetite Category	Level
Strategy & Context	Receptive
Policy & Programme Delivery	Receptive
Safeguarding	Cautious
Public Service Delivery & Operations	Cautious
Financial & Fiduciary	Receptive
Reputational	Cautious
People	Cautious

The risk appetite for Financial & Fiduciary risks was increased in June 2025 from cautious to receptive. This was facilitated by a decision to accept a greater level of financial risk taken at the APEX Department portfolio level; this was then reflected at the programme level. This acknowledges that AV Programme funds are at risk (as FCDO first loss funds would be used to absorb any initial losses before affecting the investor's senior capital) should businesses fail.

While risk exposure at this early stage of the programme is limited, a major risk recognises that other investor organisations (senior capital) may decide not to support AV. If AV does not have sufficient investment capital it could be less impactful, or in the worst-case scenario, unviable. This risk is being mitigated by AgDevCo (who are maintaining an active dialogue with prospective investors) consulting FCDO when appropriate. Should AV not proceed, unspent funds will be returned to FCDO.

Most risks will only arise once AV is formally established, investments are approved and made - at this point risks will be tied more closely to the activities of those companies, with added scrutiny should those businesses not behave in an appropriate manner.

As outlined in the Business Case, the FCDO team maintains an AV Programme oversight level Risk Register, which is updated every six weeks in line with FCDO best practice. The Audit and Risk Committee of the AgDevCo Board will maintain senior level oversight/ownership of risks under AV. The AV team will manage operational risks through their own Risk Register, updated quarterly, identifying risks into the following categories - Business Integrity, Development Impact, Environmental & Social, Financial and Operational. Each risk has an identified owner, a gross risk level, and a net risk level after mitigation controls are put in place. Particular scrutiny will be given to safeguarding and security, corruption, fraud and tax evasion, and issues in the supply chains of investees (e.g. child labour, human rights abuses, environmental damage).

AV’s downstream due diligence will operate as a two-stage process. Screening stage (culminating in a screening note) - a preliminary assessment, where AV would visit the company and understand their general ways of working and operating. This stage would look at the general appearance of the business, senior management (capability, integrity and technical competence), certifications, available reports on technical operations, marketing (customer base) and the specifics of the investment proposal AV is looking to fund. The Due Diligence stage (culminating in an investment approval paper) - a comprehensive and in-depth process of assessing the business and benchmarking its performance and standing in the market.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

AgDevCo has been a very cooperative partner. FCDO, AgDevCo and the AV team have a schedule of monthly meetings to discuss issues such as staffing arrangements, progress against fund raising targets, risks and other technical/legal arrangements involved in the set-up of AV.

In the year 1 set up period, AV management and legal costs were fully covered by the interest on capital prior to investments being made (which was placed in an interest-bearing account, as mutually discussed).

Once AV is fully operational, FCDO and the AV team will develop appropriate programme management mechanisms. Under the current arrangements there is no requirement for accurate budgeting, forecasting or payment requests.

AgDevCo will provide FCDO with detailed six-monthly financial statements for AV, covering management, legal, investee support, M&E costs etc. AgDevCo produced their 2024 Annual Report for the year ended 31 December 2024 and Consolidated Financial Statements for the Year ended 31 December 2024 in July 2025. These gave an overview of progress on establishing the Ventures Fund and showed the FCDO financial contributions. The Consolidated Financial Statements were approved by the Board on 27 June 2025 (AgDevCo Limited), 10 July 2025 (AgDevCo Holdings).

AgDevCo is committed to accountability and transparency and publishes data to the International Aid Transparency Initiative. They have confirmed that AV will also follow this process.

FCDO’s representation as a non-Executive Director on the Board of AgDevCo Holdings Ltd. provides a level of independent oversight and strategic guidance to the parent company's board. The role allows FCDO to bring external perspectives, challenge executive decisions, and ensure the company operates in the best interests of stakeholders, while keeping the day-to-day management of AgDevCo (and AV) at arms-length.

G: MONITORING, EVIDENCE AND LEARNING

The FCDO AV Programme budget allocated funding of £1m for M&E costs. This sum was provided to AV alongside the investment capital.

AgDevCo’s wider investment portfolio has an established impact framework, which defines a set of core Key Performance Indicators (KPIs) which enable it to monitor progress against its Theory of Change, ensuring that investments lead to the desired social, economic, and environmental outcomes. AgDevCo’s approach to M&E for AV will use a similar impact framework which will create public good lessons on both (i) the impact of the investments (particularly as it relates to additionality); and (ii) the case for blended finance to achieve these impacts.

Each AV investment will be given its own targets (in the areas of business performance, developmental objectives and financial returns) against which they will be tracked. These individual targets will be aggregated to build an overarching set of targets for the AV portfolio.

The AgDevCo impact team will provide Oversight, Quality Assurance and Analysis and Evaluation (at programme and investee level) of AV. In addition, the team will:
•	Define the investment specific impact thesis (with the investment teams);
•	Monitor disaggregated annual impact data; and
•	Prepare the annual AV impact summary (for the AgDevCo Board, FCDO and Shareholders).

External data collection will focus on how investees value chains impact beneficiaries e.g. small holder suppliers, or downstream traders drawing on ‘lean data’ and tech-enabled principles to undertake widespread, efficient, engagement of these beneficiary groups. The AgDevCo impact team aim to cover 50-75% of the portfolio and data collection will be repeated periodically throughout the investment. Deep dive technical impact evaluation studies using combined methodologies will enable AV to get a deeper understanding of relevant markets, and impacts generated by investment. These will be conducted on thematic areas of interest to both validate impact and generate learnings. AV will seek to collect benchmarked business and social impact data (AgDevCo has previously worked with organisations such as 60 decibels) to help verify self-reported information.

Other potential investors might also bring with them additional reporting requirements (we understand IFAD for example, if they were to invest, would be keen to include metrics for the inclusion of youth in investee companies). This would be welcomed by FCDO.

Date of last narrative financial report	30 July 2025	Date of last audited annual statement	31 December 2024