BUSINESS CASE ADDENDUM

PROGRAMME TITLE
Directorate/ Post	Research and Analysis Directorate (RAD)	Contact name
Original programme budget	£7.4m	Country or region targeted	Global (including a focus on Pakistan, Ethiopia & Nigeria)
Cost extension value (if applicable)	ODA up to £16m (consisting of EGRT £6m; non-RAD headroom £10m for Post buy-in) / non-ODA up to £5m	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Director, Chief Scientific Adviser
New increased or reduced programme budget (if applicable)	ODA total £23.4m / non-ODA total £5m / Total £28.4m	Original programme start and end dates	14 August 2025 to 31 March 2027
Latest AR programme score	N/A	New programme end date (if applicable)	31 March 2030
		Programme ID	400141

Detailed information
Programme summary	The demand-driven Research on Infrastructure in Developing Economies (RIDE) programme builds on the UK’s expertise in innovation, AI and transport research to push the frontier of knowledge and the evidence base that policymakers and investors need to improve transport systems globally. The scale of investments in transport globally are huge with World Bank investing $11 billion in 2025 and the Asian Development Bank citing $1.7 trillion annually from sovereign domestic budgets in Asia and the Pacific. Making these investments even incrementally more evidence-based has significant positive potential on value for money and impact on prosperity and climate. / RIDE was originally envisaged as a research programme on both sustainable transport (70%) and mobilising private finance for infrastructure (30%). Due to ODA reductions, director-level strategic prioritisation in 2025 determined that funding should continue for the sustainable transport element only from April 2027. / RIDE is a global partnership platform showcasing UK academic expertise and partnerships across HMG, bilaterals, multilateral development banks and philanthropies. / FCDO is the primary donor, leveraging DESNZ, BMZ, Canadian IDRC and Shell Foundation co-funding. It focuses on catalysing change through science and innovation in Emerging Markets and Developing Economies and seeks to influence global action through the first UN Decade of Sustainable Transport.
Changes	The RIDE platform has been running for six months with implementing partners (GIZ) contracted since December 2025. RIDE was originally designed as a five-year programme. However, due to ODA budget uncertainty, initial approval for FYs 25/26 and 26/27 only were granted at a total ODA budget of £7.4m. During the director-level strategic review of the R&D portfolio in late 2025 it was agreed to progress the core part of RIDE only, reducing the focus to sustainable transport research. The prioritised focus means ending research funding for mobilising private finance for infrastructure (MPF-infra) beyond March 2027. / This addendum covers a costed extension of RIDE for an additional three years beyond 2027 up to March 2030 (totalling a five-year platform). / Other changes: / RIDE has initiated and facilitated the formation of a collaborative UK academic transport research network which aims to amplify the UK’s impact on global transport challenges and unlock new funding opportunities. The network of eight UK Universities[1] (Transport Research into Practice or TRiP) are now able to be contracted through one contract. TRiP is currently responding to a research call under RIDE. / RIDE has initiated the formation of a Transport Global Intelligence System (TGIS) which will aim to draw together transport data from across 25+fragmented data platforms and geospatial sources to enable improved access to data on a local to global level building a layer of AI tools to enable structured use and visualisation of data. / The current RIDE BC already has an approved funding line for multilateral development banks. As one part of this, EGRT will close the ieConnect project (innovative, real-time IEs on large scale transport investments with current portfolio covering $5.6bn transport investments) and fold any future FCDO support to ieConnect into RIDE. / RIDE will build on past work on VAWG (including sexual harassment on public transport) to look for opportunities of increasing this work including through research at transport hubs (e.g. bus stations) for protection of vulnerable children. / RIDE has built on a strong FCDO / BMZ relationship and is exploring joint work on rail in Africa which could potentially respond to the G20 commitment made by the Prime Minister on UK support to rail in South Africa. / Demand for the RIDE ‘offer’ to Post is high, particularly on rail expertise including from Post in Jakarta, South Africa, Kenya and Brazil. RIDE is yet to reach out to Turkey and Vietnam. This is at early stage of development but likely to include an initial summary of existing and planned work looking for common challenges that RIDE could respond to in the short term and exploring potential for Post buy-in medium term. / The cross-HMG Joint Unit on Sustainable Transport which FCDO (RAD) is leading will launch in March. RIDE is aimed at being one part of that Unit, which will ensure cross-HMG R&D and policy coordination on transport. / RIDE is capable of spending non-ODA R&D funds which would respond to UK security and UK growth opportunities on both maritime and wider trade and transport including research to underpin the UK's efforts to maintain a secure, prosperous, and technologically advanced maritime sector for the future, working with both private and public sector UK leaders such as Lloyds Register and International Maritime Organisation (IMO) alongside UK academics with the Transport Research into Practice (TRiP) to respond to the UK National Security Strategy (NSS) which calls for investment in maritime tech, shipbuilding, and indigenous R&D to counter threats. Actual non-ODA spend is dependent on a separate RAD allocation process, but this addendum provides a £5m facility for this spend if approved. / The RIDE platform is in inception phase and finalising both programme outcome(s) and the theory of change. The extension and changes in the RIDE platform will be reflected in the final programme outcomes and theory of change. / The EGRT budget extension is up to £6m until March 2030 (covering FY 27-28, 28-29, and 29-30) at up to £2m per year, with actual annual spend determined by in year affordability. Overall, this is affordable at the RAD level against planned budgets.
Implementation	The changes to the programme will be an extension of the MoU with the main Implementing Partner (GIZ). There will be no changes required to the overall management arrangements as a result of the amendments to the business case.
Budget	The current ODA approval for RIDE is £7.4m (approved 14/08/2025). / The total amount spent is £1.9m (in FY 25/26). / Costed and time extension: / - additional ODA £16m (consisting of RAD/EGRT £6m over three years at ~£2m per year; non-RAD headroom for Post buy-in of £10m) / - additional non-ODA £5m (not yet allocated, but to accommodate possible future RAD spend or for Post buy-in) / Revised total budgets: / ODA total £23.4m / Non-ODA total £5m / Total £28.4m / The cost and time extension of ODA £6m over three financial years (FY 27/28, FY28/29 & FY29/30), at approximately £2m per year, is financially affordable within EGRT and RAD allocation. The cost extension includes £10m headroom for Post to buy-in to RIDE. To date there has been interest expressed from Indonesia, South Africa and Kenya and that will be further explored. Department for Transport (DfT) have expressed interest in TRiP, again on rail. / The allocations for non-ODA are currently unclear within RAD and wider FCDO however the non-ODA budget could give headroom for other parts of FCDO to access RIDE including BII and non-ODA Posts. BC addendum approval gives permission to spend non-ODA only if non-ODA is allocated to the programme. / The proposed cost extension will not take the programme beyond this SR period (29-30 for CDEL).
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	There are no significant new risks associated with this extension. However the uncertainty of FCDO budget (ODA and non-ODA) in the medium term is a risk to the sustainability of the platform. / To mitigate this risk EGRT has worked hard to diversify co-funding to RIDE and broaden the coalition of investors. The co-funding is detailed below: / Confirmed co-funding until March 2027: IDRC £470,000; DESNZ £250,000+; Shell Foundation £600,000; BMZ are part-funding GIZ staff time. Total = £1.32m / Additional co-funding FY 26/27 – 28/29 under discussion: DESNZ ringfencing of part of £9m; Shell Foundation £1.5m; BMZ £1m; IDRC to be decided; Kuehne Foundation £500,000.
Results/Monitoring and Evaluation	The original BC submission detailed two options, the first was for an initial period of approximately 18 months and the second a full five-year programme. This addendum is primarily looking to extend the programme in line with the five-year programme as outlined in the original BC and therefore the M&E activities are broadly in line with those details. / The theory of change is being reviewed as part of the inception period and currently the details suggest there are no amendments needed as the information is fully valid.
[1] University of Birmingham, Durham University, Imperial College, University of Leeds, University of Manchester, Newcastle University, University of Oxford, Heriot-Watt University