## LOGFRAME Phase 1
|  | File Type: | RIDE Phase 1 Log frame for annual progress reporting
|  | Data last updated: | 19 May 2026
|  | Version: | DRAFT
IMPACT:
i) | Sustainable, safe transport investments optimised for inclusive economic growth, a liveable planet and improved livelihoods for poor men and women.
ii) | Sufficient investment in sustainable, economic infrastructure in LMICs
….both lead to achieving inclusive growth, SDGs and Paris Agreement
OUTCOME: Participating countries, regions and organisations use RIDE knowledge products and activities to inform policy, planning and programming with more evidence based, inclusive and scaled investments | [11 empty] | Notes
# | Outcome Indicator | Outcome Indicator definition |  | responsible | accountable | Yearly Progress
[6 empty] | FY 25/26 | FY 26/27 | FY 27/28* | FY 28/29* | FY 29/30*
1 | Partnerships & Uptake: Embedding RIDE research, data, innovation, tools and evidence in policy, planning, standards and programming at national level; international / organisational level; sub-national level [see Explanatory Notes] | Instances of uptake at national, sub-national, and international or organisational level through policy references, integration into planning and investment processes, adoption of standards or methodologies, and incorporation into operational systems or institutional guidance. |  | all |  | 0 | tbd | tbd | tbd | tbd
2 | Research, Global Public Goods (GPGs) & Frontier of Knowledge: Number of Global Public Goods developed or informed by RIDE research and innovation | Instances whereby research findings, open-access datasets, digital platforms, analytical tools (e.g. HDM5), methodologies, standards, models, frameworks, and other knowledge products developed or informed through RIDE research for wider public or institutional use (e.g. curriculum development). |  | all |  | 0 | tbd | tbd | tbd | tbd
3 | Capacity: Stronger research and policy capacity in RIDE focus themes including increased LMIC profile, leadership and challenge at international, regional & national events | Instances of increased participation, leadership, representation, collaboration, authorship, or technical engagement of LMIC researchers, institutions, and policymakers in RIDE priority themes at international, regional, and national level. |  | all |  | 0 | tbd | tbd | tbd | tbd
4 | Women’s Economic Empowerment (WEE): Practical changes attributable to RIDE made to public transport infrastructure and services improving mobility for women and the vulnerable | Cumulative numbers of changes to transport infrastructure, services, policies, planning approaches, or operational practices informed by RIDE outputs or activities that improve mobility, safety, accessibility, or inclusion for women and vulnerable groups. |  | all |  | 0 | tbd | tbd | tbd | tbd
OUTPUTS: | [5 empty] | Target |  |  |  |  | Weighting
# | Output Indicator | Indicator definition (Phase 1) | Indicator definition (Phase 2) - *indicatively as not part of the current contract / MoU | responsible | accountable | Yearly Progress |  |  |  |  | 100%
[6 empty] | FY 25/26 | FY 26/27 | FY 27/28* | FY 28/29* | FY 29/30*
Output 1: Partnership & Uptake | [10 empty] | 35%
1.1 | Uptake: RIDE research and innovation products embedded in policies, manuals and programming in LMICs and contribute to international organizations & convening bodies as well as educational institutions & courses | Number of policy, planning, standards, programming and curriculum development influenced by RIDE knowledge products at national level; international / organisational level; sub-national level [see Explanatory Notes] 2.1 a: One uptake pathway with a specific uptake output on VAWG / WEE |  | GIZ |  | 1 | 4.8 | tbd | tbd | tbd
[6 empty] | 0 | 1 | tbd | tbd | tbd
1.2 | Southern-leadership & challenge: Southern Ambassadors and Southern-led advisory engagements contributing to RIDE profiling, dissemination/ uptake, strategic advisory and governance | Number of participants / formal participation of Southern Ambassadors and LMIC experts in RIDE governance, advisory, CoPs, and uptake activities at national, regional, and international level. |  | GIZ |  | 0 | 13 | tbd | tbd | tbd
1.3 | Number of Transport Community of Practise (CoPs) established and kept vibrant through regular engagements | Number of individuals participating in Communities of Practice through regular meetings, workshops, knowledge exchange activities, advisory engagement, or thematic discussions related to RIDE. |  | GIZ |  | 0 | 100 | tbd | tbd | tbd
1.4 | Number of engagements, partnerships, or instances of uptake involving Development Finance Institutions (DFIs) and related financing institutions [see Explanatory Notes] | Cumulative number of engagements with MDBs through policy dialogue, technical collaboration, research partnerships, CoPs, advisory/ council support, joint events, etc. | Uptake of RIDE evidence or tools in DFIs programmes, investments or incorporation of RIDE outputs into DFIs strategies, planning, standards, or operational processes | GIZ |  | 0 | 19 | tbd | tbd | tbd
1.5 | UK Partnerships: Integration and strategic alignment of RIDE transport research and evidence across UK Government priorities, initiatives, and sectoral agendas. | Cumulative number of engagements contributing to cross-sectoral and strategic agendas such as: climate and resilience, economic development, trade and logistics, gender and inclusion, etc. | Number of formalised cross-government partnerships or joint initiatives | GIZ / FCDO |  | 0 | 5 | tbd | tbd | tbd
1.6 | Cross-cutting research & cross-workstream thinking: Periodic cross-cutting thematic synthesis on cross-cutting themes produced and disseminated by Ride | Number of RIDE published disseminated outputs synthesising activities on road safety, gender / VAWG, data & digitisation, transparency, from research projects, Communities of Practice, and RIDE partner activities |  | GIZ |  | 0 | 2 | tbd | tbd | tbd
Output 2: Research, Global Public Goods (GPGs) and Frontier of Knowledge | [10 empty] | 30%
2.1 | High quality research projects undertaken in line with RIDE priority research themes | Number of RIDE research calls; Number research projects commissioned i) in-house, ii) external |  | WRI |  | 11 | 8 | tbd | tbd | tbd |  | FY25/26: 5 WRI, 2 TRL, 4 MPF-infra FY26/27: 5 TRiP, 2 WRI, 1 TRL
2.2 | Research partners: Integration of research institutions and national / regional partners from LMICs | Number of research institutions or LMIC partners commissioned through i) in-house and ii) external research projects |  | WRI |  | 5 | 9 | tbd | tbd | tbd |  | FY25/26: WRI, TRL, UCL, SOAS, Oxford FY26/27: ODI + TRiPx8
2.3 | Academic influence: Evidence published (Externally peer-reviewed) and citations in academic articles of peer-reviewed publications | Number of externally peer-reviewed knowledge products (journal papers, book chapters etc.) 1.4 a: Cumulative disaggregation indicator by proportion of publications with more than 40% female / LMIC authors OR proportion with first author female / LMICs. | additional: number of citation counts in google scholar, MDPI citation tracker and other citation indices. | WRI |  | 0 | 15 | tbd | tbd | tbd
|  |  |  | WRI |  | 0 | 40% | tbd | tbd | tbd
2.4 | Public research outputs: Evidence published (not externally-peer reviewed) | Number of internally-reviewed knowledge products published 1.5 a: Cumulative disaggregation indicator by proportion of publications with more than 40% female / LMIC authors OR proportion with first author female / LMICs. |  | WRI |  | 0 | 25 | tbd | tbd | tbd
|  |  |  | WRI |  | 0 | 40% | tbd | tbd | tbd
2.5 | Frontier knowledge: Open-access transport data platforms, digital public goods, or tools strengthened through RIDE research and activities | Number of RIDE supported digitalisation / data system activities, databases, modelling platforms, digital twins, interoperability/ analytical tools, or open standards |  | WRI |  | 0 | 2 | tbd | tbd | tbd
2,6 | High-quality rapid analytical, technical, or advisory responses delivered by an RIDE Agile Response Unit (ARU) to FCDO Posts, CMPs, or programme partners | Number of timely delivered country-level responses, thematic or sub-regional analyses, horizon-scanning and foresight products 1.9 a: Cumulative amount of buy-in to RIDE from post or other CMPs for ARU services |  | TRL |  | 0 | 36 | tbd | tbd | tbd
|  |  |  | TRL / GIZ / FCDO |  | 0 | 100000 | tbd | tbd | tbd
Output 3: Capacity, Knowledge Management & Communications | [10 empty] | 20%
3.1 | Co-funding & leveraging to showcase RIDE's function as "Platform Programme" and to support RIDE's VfM Principle | Cumulative amount of formalised co-financing, leveraged funding, or other financial commitments mobilised from governments, development partners, DFIs, research institutions, etc through RIDE-supported activities or engagement. |  | GIZ / FCDO |  | 200000 | 450000 | tbd | tbd | tbd
3.2 | Event engagements profiling RIDE using reach of external events at national level; international / organisational level; sub-national level [see Explanatory Notes] | Number of event engagements showcasing RIDE activities and research outputs (TT, UN Decade WS Geneva, TDC Launch Glasgow, WBG Annual / Spring Meetings, CoP-PF4SD Conference, etc) 3.2 a: For RIDE-own events: Cumulative disaggregation indicator by proportion of participants with more than 40% female and LMIC representation |  | GIZ |  | 3 | 15 | tbd | tbd | tbd
[6 empty] | 0 | 40% | tbd | tbd | tbd
3.3 | Increased capacity: Stronger research & policy capacity in participating countries on sustainable transport and investments | Number of individuals trained and reporting high satisfaction and improved knowledge or skills. 3.3 a: Cumulative disaggregation indicator by proportion of participants with 40% female participation and LMIC representation |  | GIZ |  | 0 | 50 | tbd | tbd | tbd
[6 empty] | 0 | 40% | tbd | tbd | tbd
3.4 | Transport Legacy: Integration of FCDO legacy programmes (HVT/ ReCAP) into RIDE to showcase continuity and longstanding expertise in frontier research | Cumulative number of HVT, ReCAP & other FCDO-funded knowledge products integrated into RIDE website and promoted through RIDE digital outreach activities |  | GIZ |  | 549 | 1628 | tbd | tbd | tbd
3.5 | Comms & Outreach: Reach and engagement of RIDE communications, dissemination, and visibility activities | Cumulative number of digital reach activities (website visit/ views, publication downloads, newsletter subscribers, social media subscribers & number of social media posts), media features (podcasts, op-eds), produced branding & dissemination materials (videos, newsletter, event materials, campaign/ launch kits) |  | GIZ |  | 1200 | 3000 | tbd | tbd | tbd
Output 4: Lives Impacted/ Emissions Reduced (Transport Innovation Hub by Shell Foundation) | [10 empty] | 15%
4.1 | Create jobs - DIRECT JOBS (CUMULATIVE) | Headcount of new direct jobs within the business model. | Headcount of new direct jobs within the business model. | Shell Foundation |  | 20 | 100 | 400 | 800 | 1200
4.2 | Mobilize capital - CAPITAL MOBILISED $ (CUMULATIVE) | Total additional capital mobilised by the business model disaggregated by funding type (grant, debt and/or equity) and source (public or private). Capital mobilised can include the following: 1) capital committed by partner contributing to the initiative; 2) additional capital raised into the business model; 3) capital raised and disbursed by financial intermediaries. | Total additional capital mobilised by the business model disaggregated by funding type (grant, debt and/or equity) and source (public or private). Capital mobilised can include the following: 1) capital committed by partner contributing to the initiative; 2) additional capital raised into the business model; 3) capital raised and disbursed by financial intermediaries. | Shell Foundation |  | 3.21 | 6.63 | 12.52 | 20.54 | 30.31
4.3 | Test and Validate Business Models - NEW BUSINESS & APPLICATIONS | These new models and applications will be delivered by (a) existing partners or financial intermediaries in the SF partner portfolio or (b) new partners or intermediaries incubated/supported to deliver the RIDE strategy | These new models and applications will be delivered by (a) existing partners or financial intermediaries in the SF partner portfolio or (b) new partners or intermediaries incubated/supported to deliver the RIDE strategy | Shell Foundation |  | 1 | 2 | 4 | 5 | 5
Output 5: Activities by co-funders / parallel funders | [10 empty] | (non weighted)
5.1 | Contributions to multi-donor trust fund | Financial contribution World Bank's Global Facility to Decarbonize Transport (GFDT) |  | DESNZ
5.2 | Contribution to the UN Decade | Support for SLOCAT in launching the UN Decade of Sustainable Transport to shape global transport narratives in the lead up to the UN Decade and to support Decade launch activities |  | IDRC |  |  |  | (verbal / written integration in log frame only)
5.3 | Curriculum Development | Transport Leadership Capacity Advancement Program for Africa – Trans CAP-Africa – to support the development of an MSc in Transport Leadership in collaboration with 7 African Universities. Builds on results achieved under HVT and ReCAP. |  | IDRC
5.4 | Foundational studies | Three landscape/gap studies lay the foundation for further transport programming in 2027 |  | IDRC

## Explanatory Notes
Explanatory Notes
a) | Phasing:
| Phase 1 | FCDO FY25/26 = 1 Dez 2025 - 31 Mar 2027
| *Phase 2 | FCDO FY26/27 = 1 Apr 2026 - 31 Mar 2030
b) | Actor Levels:
|  | National level | Sub-national level | International / Organisational level
| Key distinction: | [sovereign/state-level policymaking and planning] | [local, city, corridor, operator, or regional implementation level] | [multilateral/global/institutional actors}
| Examples: | LMIC Governments | Cities / municipalities | MDBs (Multilateral Development Banks)
|  | National ministries/agencies | Provincial or state governments | IFIs (International Financial Institutions)
|  | National regulators | Metropolitan transport authorities | DFIs (Development Finance Institutions)
|  | National transport authorities | Corridor authorities | UN organisations/agencies
|  | Country-level development programmes | Port authorities | Development Partners (DPs)
|  | FCDO Posts / CMP engagement (country-facing) | Railway operators | G7
|  |  | Local transport agencies | G20
|  |  | Regional planning bodies | OECD
|  |  | Community-level institutions | COP processes/platforms
|  |  | Urban mobility authorities | Universities
c) | Development Finance Institutions (DFIs) and related financing institutions.
| Key distinction: | [bilateral and national DFIs] | [MDBs and regional development banks] | [IFIs and global financing institutions]
| Examples: | BII | World Bank | IMF
|  | KfW | EBRD | IFC
ADB
AfDB

## logframe revision - tracks (hidden)
ieConnect FCDO Logframe
Notes: ** All targets are stocks or percentages of stocks (meaning that they are cumulative since the inception of ieConnect)
** Year refers to a calendar year
Phase legend and # IEs in each Phase:
Phase 1 | 8 | #REF! | Before CN Review
Phase 2 | 11 | #REF! | After CN Review but before baseline results are available for discussion (or before implementation starts if the IE has no baseline)
Phase 3 | 12 | #REF! | After baseline results are available for discussion (or after implementation starts if the IE has no baseline) but before IE results are available for discussion
Phase 4 | 0 | #REF! | After IE results are available for discussion
ieConnect FCDO Logframe
Outcomes |  |  | Indicators | Targets | [10 empty] | Current Progress | [9 empty] | Definition of indicator (relevant base) | Source
|  |  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | Total | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Total |  |  | Notes/Rationale
1. Improved awareness, demand for and use of transport evidence in decision making | outc_1_2 | 1.2 | Proportion of transport impact evaluations with multi-arm evaluation designs to test project innovations. |  |  | 35% | 35% | 40% | 40% | 40% | 40% | 40% 45% | 40% 45% | 40% 45% |  | 60% | 45% | 42% | 43% | 41% | 44.44% | 44.44% | #REF! |  | % of IEs that have more than one treatment arm or iterative experiments (of the ieConnect-supported IEs in phase 2 and above).* | Monitoring system | We have increased this indicator to reflect the progress in previous years.
[16 empty] | (3/5) | (5/11) | (8/19) | (10/23) | (11/27) | (12/27) | (12/27) | #REF!
| outc_1_3 | 1.3 | Proportion of impact evaluations that influence transport project during design or implementation. |  |  | 55% | 55% | 55% | 55% | 55% | 55% | 55% 60% | 55% 60% | 55% 60% |  | 60% | 64% | 58% | 56% | 63% | 62.96% | 67% | #REF! |  | % of IEs that improved design based on clear understanding of the underlying theory of change or whose baseline results were used to stimulate policy dialogue / help identify problems and solutions (of the ieConnect-supported IEs in phase 2 and above).* | Monitoring system | While there was progress in the last few years, we are proposing to increase this target to 60%. Given the increase in total projects that will be reflected in the denominator, this will affect the overall percentage we would expect in 2024 & 2025 for this indicator.
[16 empty] | (3/5) | (7/11) | (11/19) | (13/23) | (17/27) | (17/27) | (18/27) | #REF!
| outc_1_4 | 1.4 | Proportion of completed transport impact evaluations that generate evidence used to support project adoption, targeting, scale-up, scale-down, continuation or cancelation decisions, or that influence discussions on complementary interventions. |  |  |  |  | 45% | 45% | 45% | 45% | 45% 55% | 45% 55% | 45% 55% |  |  |  |  | N/A | 67% | 50% | 53.85% | #REF! |  | % of IEs (where project being evaluated has complementary programmes or polices) that contributed to change the "how many receive the policy or programme" (of the ieConnect-supported IEs in phase 4).* | Monitoring system | We have increased this indicator to reflect the progress in previous years.
[20 empty] | (2/3) | (4/8) | (7/13) | #REF!
2. Improved effectiveness and impact of new and existing transport interventions from FCDO, MDBs and wider community | outc_2_1 | 2.1 | Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself. |  |  |  |  | 15% | 15% | 16% | 16% | 25% 35% | 25% 35% | 25% 35% |  |  |  |  | 17% | 27% | 27.27% | 33.33% | #REF! |  | % of IEs that have influenced the design or implementation of other projects outside of the IE itself (of the ieConnect-supported IEs in phase 3 or 4).* | Monitoring system | We have increased this indicator to reflect the progress in previous years.
[19 empty] | (2/12) | (4/15) | (6/22) | (9/27) | #REF!
| outc_2_2 | 2.2 | Proportion of completed and published transport impact evaluations that are cited in the academic literature | [5 empty] | 25% | 25% | 25% | 75% | 75% | 75% |  |  |  |  | N/A | 100% | 100% | 100% | 100% |  | % of IEs with academic publications that are cited. | Google Scholar | We have set this target at 75% despite the progress in previous years as we expect more projects to have published outputs as results are available. Given it typically takes some time for recently published papers to be cited, we have set the target at 75% to account for recent publications that may not have had a reasonable opportunity to allow for citations at the time of the annual review.
[20 empty] | (6/6) | (6/6) | (6/6) | (7/7)
| outc_2_3 | 2.3 | Downloads of ieConnect research working papers |  |  |  | 500 | Low: 500 Med: 650 High: 800 | Low: 1600 Med: 1700 High: 1800 | Low: 1900 Med: 2000 High: 2100 | Low: 2700 Med: 2900 High: 3100 | Low: 15,000 Med: 17,000 High: 19,000 | Low: 17,000 Med: 19,000 High: 21,000 | Low: 17,000 Med: 19,000 High: 21,000 |  |  |  | 0 | 1301 | 5091 | 8828 | 13224 | #REF! |  | Cumulative. Number of times ieConnect working papers or journal articles are downloaded based on collated metrics from working paper and journal websites. | Working paper and Journal websites | We have increased this indicator to reflect the progress in previous years.
Outputs |  |  | Indicators | Targets | [6 empty] | Targets |  |  |  | Current Progress | [6 empty] | Current Progress |  |  | Definition of indicator | Source
|  |  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | Total | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Total
1. Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation | outp_1_1a | 1.1a | Number of ongoing projects across key sub-sectors (total): urban mobility, transport corridors, and road safety. | 8 | 16 | 16 | 22 | Low: 24 Med: 25 High: 26 | Low: 24 Med: 25 High: 26 | Low: 24 Med: 25 High: 26 | Low: 24 Med: 25 High: 26 | Low: 29 Med: 30 High: 31 | Low: 29 Med: 30 High: 31 | Low: 29 Med: 30 High: 31 | 6 | 23 | 26 | 25 | 31 | 28 | 27 | 27 | #REF! |  | Cumulative. Total number of projects across all sub-sectors that are in any Phase 1-4. | Monitoring system | The proposed targets reflect the additional projects from the costed extension.
| outp_1_1b | 1.1b | Number of completed outputs (the sum of 1.1c-1.5) |  |  | 1 | 3 | 10 | 31 | 38 | 47 | 59 63 | 72 77 | 72 77 |  |  |  |  | 22 | 32 | 41 | 53 | #REF! |  | Cumulative. Number of completed outputs is the sum of Outputs 1.1c, 1.2, 1.3, 1.4, and 1.5. | Monitoring system | We have increased this indicator to reflect the progress in previous years.
| outp_1_1c | 1.1c | Number of Grant-supported knowledge products, for example, IE papers or IE reports (excluding outputs detailed below) |  |  |  |  | 4 | 18 | 25 | 30 | 40 | 50 | 50 |  |  |  |  | 11 | 19 | 26 | 34 | #REF! |  | Cumulative. Total number of baseline, midline, or endline reports, final papers, or working papers. Does not include outputs counted elsewhere. | Monitoring system | We have increased this indicator to reflect the progress in previous years.
| outp_1_2 | 1.2 | Thematic knowledge reviews or technical notes for policymaking |  |  |  | 1 | 2 | 3 | 3 | 4 | 4 5 | 5 8 | 5 8 |  |  |  | 1 | 2 | 3 | 3 | 4 | #REF! |  | Cumulative. Total number of thematic knowledge reviews, e.g., mechanism, sector, country, pillar reviews, global indicators. Does not include outputs counted elsewhere. | Monitoring system | Given that we're proposing these changes in September, we have slightly increased the target for 2024 but then will invest in developing more short technical notes based on our last discussion and increase this type of output more significantly in 2025.
| outp_1_3 | 1.3 | Number of cross cutting reviews in FEE and FCAS |  |  |  |  | 1 | 1 | 1 | 2 | 2 3 | 2 3 | 2 3 |  |  |  |  | 1 | 1 | 1 | 2 | #REF! |  | Cumulative. Total number of cross cutting reviews in FEE and FCAS. Does not include outputs counted elsewhere. | Admin data | We have increased this indicator to reflect the progress in previous years.
| outp_1_4 | 1.4 | Developed data infrastructure (with ability for scale up) |  |  | 1 | 1 | 2 | 6 | 6 | 7 | 8 9 | 9 10 | 9 10 |  | 1 | 3 | 3 | 5 | 6 | 7 | 8 | #REF! |  | Cumulative. Pilot data systems for collecting data on an ongoing basis that have the ability to scale-up. Does not include outputs counted elsewhere. | Admin data | We have increased this indicator to reflect the progress in previous years.
| outp_1_5 | 1.5 | Developed and validated measurement framework that is able to disaggregate impact (male/female or rural/urban). |  |  |  | 1 | 1 | 3 | 3 | 4 | 5 6 | 6 | 6 |  |  |  | 1 | 3 | 3 | 4 | 5 | #REF! |  | Cumulative. Cost effective ways to collect the efficient set of indicators in each outcome space of interest to better understand how transport investments contribute to poverty reduction and economic development. Does not include outputs counted elsewhere. | Admin data | We have increased this indicator to reflect the progress in previous years.
| outp_1_6 | 1.6 | FCDO program co-financing share |  |  |  | <45% | <40% | <40% | <40% | <40% | <40% | <40% | <40% |  |  |  | 44% | 39.5% | 38.59% | 37.22% | 36.04% |  |  | % of the secured financing for the ieConnect program that comes from FCDO's GRT financing of ieConnect to i2i TF. IEs beginning in 2019 and onward will not included in this indicator until 2021. | Monitoring system and Admin data | We are keeping this target at its current level given the large influx of FCDO funding through the costed extension, which is split between existing projects (already counted towards current results) and some new projects.
| outp_1_7 | 1.7 | Thematic distribution: Gender (cross-cutting) |  | 30% | 30% | 30% | 30% | 30% | 30% | 35% | 40% 55% | 40% 55% | 40% 45% |  | 30.43% | 31% | 32% | 39% | 39% | 44.44% | 44% | #REF! |  | % of ieConnect-supported IEs. | Monitoring system | We have increased this indicator to reflect the progress in previous years. This indicator includes all projects that have any of the following: (i) gender as a thematic or cross-cutting area; (ii) a gender-specific treatment; or (iii) include gender analysis, e.g., can separate a component of the impact by gender.
| outp_1_8 | 1.8 | Geographic distribution: FCAS |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% |  | 82.61% | 69% | 64% | 61% | 57% | 59.26% | 59% | #REF! |  | % of ieConnect-supported IEs. | Monitoring system | As discussed, we are keeping this target at the same level since we benchmark this against the FCAS list that was adopted at the start of the program.
| outp_1_9 | 1.9 | Income level distribution: FCDO focus countries |  | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% 65% | 60% 65% | 60% 65% |  | 86.96% | 81% | 76% | 77% | 75% | 74.07% | 74% | #REF! |  | % of ieConnect-supported IEs. | Monitoring system | Same as above; we benchmark this indicator against the FCDO (DFID) focus countries from the start of the program.
|  | 1.1 | Female Economic Empowerment (FEE): | [21 empty] | % of ieConnect-supported IEs (in phase 2 and above).*
| outp_1_10_1 |  | Proportion of IEs with FEE specific intervention |  |  | 30% | 30% | 30% | 30% | 30% | 30% | 30% 35% | 30% 35% | 30% 35% |  |  | 35% | 36% | 26% | 36% | 33.33% | 33% | #REF! |  | % of IEs designed to empower women or contribute to the theory of change for female economic empowerment. | Monitoring system | We have increased this indicator to reflect the progress in previous years.
| outp_1_10_2 |  | Proportion of IEs disaggregated by sex or age |  |  | 30% | 30% | 30% | 30% | 30% | 35% | 45% 55% | 45% 55% | 45% 55% |  |  | 50% | 52% | 45% | 46% | 51.85% | 52% | #REF! |  | % of IEs that can separate a component of the impact by sex or age. | Monitoring system | We have increased this indicator to reflect the progress in previous years.
2. Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policy making | outp_2_1a | 2.1a | Number of MDBs involved at the operational level | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | #REF! |  | Cumulative. Number of distinct organizations worked with at any point during the program. Involved at the operational level means has participated in discussions about planning and executing the impact evaluation either as a member of the project team or research team. Includes multilateral development entities such as the EU. | Monitoring system | As discussed, we have kept the same targets given the maturity of the program and MDBs we have involved at the operational level.
| outp_2_1b | 2.1b | Number of bilateral donor institutions involved at the operational level |  | 2 | 3 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 |  | 4 | 4 | 5 | 6 | 6 | 6 | 6 | #REF! |  | Cumulative. Number of distinct organizations worked with at any point during the program. Involved at the operational level means has participated in discussions about planning and executing the impact evaluation either as a member of the project team or research team. | Monitoring system | As discussed, we have kept the same targets given the maturity of the program and bilateral partners we have involved at the operational level.
| outp_2_2 | 2.2 | Number of IEs or projects working directly with a non-WB implementing partner |  |  |  | 10 | 12 | 12 | 12 | 12 | 14 15 | 14 15 | 14 15 |  |  |  | 10 | 12 | 14 | 14 | 14 | #REF! |  | Cumulative (total engagements instead of distinct institutions). Includes each IE or mobility analytics country case that has an MDB or bilateral donor institution "involved at the operational level" either with or without the presence of a WB project, or is working directly with the government, NGO, or other actor in the absence of a WB project. | Monitoring system | We have increased this indicator to reflect the progress in previous years.
| outp_2_3 | 2.3 | Proportion of co-financed transport programmes |  | 90% | 90% | 90% | 90% | 90% | 95% | 100% | 100% | 100% | 100% | 67% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | #REF! |  | % of IEs that evaluate a project that is part of a broader transportation programme where that programme is financed by more than one entity. | Admin data | We have kept this indicator at 100%.
[16 empty] | (14/16) | (14/14) | (12/12) | (14/14) | (14/14) | (11/11) | (11/11) | #REF!
| outp_2_4 | 2.4 | Spend on non-WB IEs or co-funded IEs where WB contribution <=25% | 20% | 20% | 20% | 25% | 25% | 25% | 25% | 25% | 25% 40% | 25% 40% | 25% 40% | 17% | 21% | 23% | 28% | 32% | 39% | 44.44% | 44% | 45.45% |  | % of IEs that evaluate non-WB projects or evaluate WB projects where the proportion of the project’s financing from the WB is less than 25% of the total financing. | Admin data | While there was progress in the last few years, we are setting this target at 40% given the increase in projects that will be reflected in the denominator and affect the overall percentage we would expect in 2024/2025 for this indicator.
[16 empty] | (4/19) | (6/26) | (7/25) | (10/31) | (11/28) | (12/27) | (12/27) | (15/33)
| outp_2_5 | 2.5 | Proportion of people participating in workshops that come from low or lower-middle income countries |  | 75% | 75% | 75% | 75% | 75% | 78% | 80% | 80% 85% | 80% 85% | 80% 85% | 61% | 77% | 87% | 90% | 84% | 85.45% | 83.94% | 85% | #REF! |  | Calculation is based on "target participants", excluding attendees who are World Bank staff or invited speakers. | Admin data | We have increased this indicator to reflect the progress in previous years.
[16 empty] | (79/103) | (187/214) | (243/271) | (291/346) | (329/385) | (371/442) | (431/509) | #REF!
| outp_2_6 | 2.6 | Proportion of people participating in workshops that come from FCASs |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 61% | 46% | 50% | 58% | 53% | 57.4% | 58.37% | 58.55% | #REF! |  | Calculation is based on "target participants", excluding attendees who are World Bank staff or invited speakers. | Admin data | Given we are adding countries that are not FCAS in the costed extension, we are proposing to keep this target at 50%.
[16 empty] | (47/103) | (106/214) | (156/271) | (183/346) | (221/385) | (258/442) | (298/509) | #REF!
| outp_2_7 | 2.7 | Number of people trained in workshops and / or by ieConnect supported teams/ researchers. |  | 150 | 250 | 350 | 400 | 495 | 510 | 520 | 680 | 700 | 700 | 32 | 185 | 292 | 376 | 483 | 527 | 584 | 661 | #REF! |  | Cumulative number of people (MDBs, governments, universities, other partners, etc.) trained in ieConnect workshops and IE specific capacity building events. | Admin data | We have increased this indicator to reflect the progress in previous years.
| outp_2_8 | 2.8 | Number of workshops |  | 1 | 2 | 4 | 5 | 13 | 14 | 15 | 23 | 25 | 25 | 1 | 3 | 6 | 9 | 12 | 13 | 17 | 22 | #REF! |  | Cumulative number of IE design workshops, research clinics (thematic and cross-cutting), regional and country-specific strategy development workshops, or dissemination events. | Admin data | We have increased this indicator to reflect the progress in previous years.
3. Increased Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy making | outp_3_1 | 3.1 | Number of organisations participating in ieConnect workshops |  | 15 | 60 | 80 | 185 | 186 | 190 | 200 | 210 | 212 | 212 | 19 | 79 | 138 | 165 | 186 | 193 | 204 | 209 | #REF! |  | Cumulative number of organizations (donors, MDBs, government agencies, academic institutions, NGOs, etc.) that have participated in at least one ieConnect workshop. | Admin data | We have increased this indicator to reflect the progress in previous years. Note that given the stage of the program, the set of organizations that we work with and participate in workshops is already set based on the set of projects.
| outp_3_2 | 3.2 | Number of organisations, universities, research centers, and government agencies participating in ieConnect networks |  | 30 | 30 | 50 | 55 | 82 | 83 | 83 | 92 | 92 | 92 | 15 | 44 | 34 | 50 | 81 | 84 | 87 | 87 | 87 |  | Cumulative number of organizations engaged in ieConnect-supported IEs (researcher and counterpart affiliations in the full transport portfolio). | Monitoring system | We have increased this indicator to reflect the progress in previous years. Note that given the stage of the program, the set of organizations that we work with is already set based on the set of projects.
| outp_3_3 | 3.3 | Number of non-WB hosted dissemination events |  |  | 4 | 25 | 30 | 60 | 65 | 70 | 100 | 105 | 105 |  | 6 | 19 | 26 | 48 | 67 | 77 | 91 | #REF! |  | Cumulative number of non-WB hosted dissemination events. | Admin data | We have increased this indicator to reflect the progress in previous years.
| outp_3_4 | 3.4 | Number of presentations in high-level meetings with multi-stakeholder MDB and/or bilateral transport leadership |  |  | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 5 | 5 |  |  | 1 | 1 | 2 | 3 | 3 | 4 | #REF! |  | Cumulative number of presentations to the MDB Working Group on Sustainable Transportation or similar committee of MDB and/or bilateral transport leadership. | Admin data | We have retained our original targets for 2024 and 2025 given that the 2024 review year is almost over. For 2025, we are aiming to increase our target.
Notes. *Indicators defined for a subset of IE project phases (e.g., only those in phase 3 or 4) imply changes in the denominator (number of IEs per phase) across years and, therefore, the corresponding annual estimates as projects progress over time.

## list_projects_2020_2021 (hidden)
id | ietitle | country | ttl | in_2020 | in_2021_fcdo_only | in_2021_alltransport | s0 | s1 | s2 | s3 | s4 | sd | sdetail_1 | sdetail_2 | phase_project | subproject | hold | spinoff | project_type | phase_iecon
57 | Rio de Janeiro gender segregated public transport | Brazil | Florence Kondylis | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 - After IE results are available for discussion | 0 | 0 | 0 | 1 - IE | 1 - ieConnect Phase 1 (2015)
89 | Impact Evaluation of the Peru Support of the Subnational Transport Program Project | Peru | Javier Morales Sarriera | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 0 | 1 - IE | 1 - ieConnect Phase 1 (2015)
279 | The impact of a targeted fare subsidy program on public transportation usage and labor market outcomes: a regression discontinuity analysis from Bogota | Colombia | Sveta Milusheva, Javier Morales Sarriera | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 - After IE results are available for discussion | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
146 | Road Safety in Kenya: Matatu and Insurance Markets | Kenya | Guadalupe Bedoya, Sveta Milusheva | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 1 | 1 - IE | 1 - ieConnect Phase 1 (2015)
352 | COVID19 Mobility Analytics Task Force | Global | Sveta Milusheva | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | Questionable |  | 3 - After baseline results are available for discussion | 0 | 0 | 0 | 2 - Data project | 3 - ieConnect Phase 3 (2019)
353 | Hawassa Industrial Park COVID-19 Impact Evaluation | Ethiopia | Alice Mortlock | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 1 | 1 - IE | 3 - ieConnect Phase 3 (2019)
133 | Impact Evaluation of the Rural Access and Mobility Project | Nigeria | Vincenzo Di Maro | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 0 - On hold | 0 | 1 | 0 | 1 - IE | 1 - ieConnect Phase 1 (2015)
332 | Matatu Efficiency and Safety in Nairobi | Kenya | Erin Kelley | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 - Subproject | 1 | 0 | 1 | 1 - IE | 3 - ieConnect Phase 3 (2019)
41 | Ethiopia Expressway | Ethiopia | Alice Duhaut | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Potential to remove |  | 0 - Dropped
254 | Creating a Transport Data System to Evaluate Improvements to Transport Efficiency and Road Safety | Ethiopia | Theophile Bougna, Alice Duhaut | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Potential to remove | Aidan - potential to drop | 0 - Dropped
338 | Roads for Rural Transformation in Mandul and Chari Provinces of Chad | Chad | Theophile Bougna | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 |  | Aidan - potential to drop | 0 - Dropped
340 | RAAMP Impact Evaluation | Nigeria | Theophile Bougna | 1 | 0 | 0 | [8 empty] | 0 - Dropped
51 | Experimental Evidence on Urban Transport and Mobility: Impact Evaluation of the Dar es Salaam BRT System | Tanzania | Sveta Milusheva, Hee Kwon Seo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 4 - After IE results are available for discussion | 0 | 0 | 1 | 1 - IE | 1 - ieConnect Phase 1 (2015)
82 | Impact Evaluation of Rwanda Rural Feeder Roads | Rwanda | John Loeser, Maria Jones | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 1 | 1 - IE | 1 - ieConnect Phase 1 (2015)
247 | Impact of Highway Upgrading on National Integration and Local Economic Development | Tunisia | Alice Duhaut | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
248 | Understanding and Addressing Gender-Based Violence in Public Transportation in Dar es Salaam | Tanzania | Girija Borker | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 1 | 2 - Data project | 2 - ieConnect Phase 2 (2017)
249 | The Route for Development: Complementary Effects of Improved Roads and Agricultural Extension Services | Mozambique | Paul Christian, Astrid Zwager | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
250 | Lake Victoria Transport Program Rwanda Corridor | Rwanda | Maria Jones | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 |  | Aidan - potential to drop | 2 - After CN review but before baseline results are available | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
252 | Impact Evaluation of the Transport Systems Improvement Project (TRANSIP) in Addis Ababa | Ethiopia | Girija Borker | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
253 | Hawassa Industrial Park Community Impact Evaluation | Ethiopia | Alice Mortlock | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | Potential to remove |  | 2 - After CN review but before baseline results are available | 0 | 0 | 1 | 1 - IE | 2 - ieConnect Phase 2 (2017)
255 | smarTTrans: Road Safety in Kenya | Kenya | Guadalupe Bedoya, Sveta Milusheva | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 1 | 2 - Data project | 2 - ieConnect Phase 2 (2017)
256 | Guinea-Bissau Rural Transport Project: Impact Evaluation on Women's Access to Essential Services and Economic Opportunities | Guinea-Bissau | Theophile Bougna, Sveta Milusheva | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
257 | Impact Evaluation of Emergency Response and Post-Crash Care in Malawi and Tanzania | Malawi | Sveta Milusheva | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 4 - After IE results are available for discussion | 0 | 0 | 1 | 1 - IE | 2 - ieConnect Phase 2 (2017)
258 | Effects of Large Transportation Infrastructure Projects on Worker Well-Being | Senegal | Sveta Milusheva | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 1 | 1 - IE | 2 - ieConnect Phase 2 (2017)
259 | Measuring and Enhancing Mobility in Dakar | Senegal | Sveta Milusheva | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 1 | 1 - IE | 2 - ieConnect Phase 2 (2017)
260 | Liberia Road Safety Impact Evaluation | Liberia | Theophile Bougna | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
261 | Connecting the Dots: The Impact of Enhanced Bridge Connectivity | Nepal | Theophile Bougna | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
262 | Impact Evaluation of Iraq Transport Corridor Project | Iraq | Theophile Bougna | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
266 | Understanding the Impacts of CAREC Corridor Investments in Pakistan on Connectivity and Local Economic Development | Pakistan | Alice Duhaut | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 1 | 1 - IE | 2 - ieConnect Phase 2 (2017)
267 | Impact Evaluation of Emergency Response and Post Crash Care in Tanzania | Tanzania | Sveta Milusheva | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 4 - After IE results are available for discussion | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
276 | Slow down! Pilots to Decrease Speeding and Incidence of Fatal Traffic Accidents at “Critical” Road Spots | Nicaragua | Alejandro De la Fuente, Elizaveta Perova | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 1 | 1 - IE | 2 - ieConnect Phase 2 (2017)
278 | Enhancing Female Participation in Household Decision-Making for Improved Impacts of Rural Roads on Factor Accumulation and Productivity in Nicaragua | Nicaragua | Alejandro De la Fuente, Elizaveta Perova | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 1 | 1 - IE | 2 - ieConnect Phase 2 (2017)
282 | Measuring Violence Against Women in Public Spaces: Drawing on Experimental Evidence | India | Girija Borker | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 0 | 1 - IE | 2 - ieConnect Phase 2 (2017)
296 | Efficiency of Informal Transit Networks: Evidence from Lagos, Nigeria | Nigeria | Alice Duhaut | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 3 - After baseline results are available for discussion | 0 | 0 | 0 | 1 - IE | 3 - ieConnect Phase 3 (2019)
297 | Transport and trade facilitation at the border, trade costs and revenue mobilization | Malawi | Alice Duhaut | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 1 - Before CN review | 0 | 0 | 0 | 2 - Data project | 3 - ieConnect Phase 3 (2019)
335 | Rural Roads and Agricultural Value Chains | Rwanda | John Loeser, Maria Jones | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 1 | 1 - IE | 3 - ieConnect Phase 3 (2019)
337 | The social costs and benefits of infrastructure construction: Air pollution and bus rapid transit (BRT) in Dakar | Senegal | Sveta Milusheva | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2 - After CN review but before baseline results are available | 0 | 0 | 1 | 1 - IE | 3 - ieConnect Phase 3 (2019)

## scenarios (hidden)
Logframe Indicators
Scenarios using 2020 data sources
link | <--- folder with data and dofiles
Indicators with values below targets
Indicators close to target; need to flag for attention in myIE updates
Other indicator definitions/calculations to be discussed
ind_no | ind_title | unit | filter | 2020 Replication (N=31) *31 projects used in 2020 logframe (differs slightly from the 31 projects in scenarios here updated for 2021) |  | Scenario 0 (N=28) *Excl. Hawasssa, Sierra Leone, Ethiopia road safety, Covid Mobility) |  | Scenario 1 (N=29) *Excl. Sierra Leone, Ethiopia road safety, Covid Mobility) |  | Scenario 2 (N=30) *Excl. Sierra Leone, Ethiopia road safety) |  | Scenario 3 (N=31) *Excl. Sierra Leone |  | Scenario 4 (N=28) *Excl. Sierra Leone, Ethiopia road safety, Chad, Rwanda LVTP) |  | Notes | Data notes
|  |  |  | N | value | N | value | N | value | N | value | N | value | N | value
outc_1_2 | Proportion of transport impact evaluations with multi-arm evaluation designs to test project innovations. | % of projects | Phase 2+ | 23 | 0.39 | 26 | 0.31 | 27 | 0.33 | 28 | 0.32 | 29 | 0.31 | 27 | 0.33 | [AC]: these two indicators are most concerning. since we're above target on number of IEs, do we have flexibility to selectively not report on a set of IEs that are (i) single arm and (ii) haven't influenced project during design? that would bring down our total IE numbers, but get us better on these indicators. not a great option, but an option to look into... [AM]: guessing changing the phase isn't possible/would make things worse? | [AD]: Minor differences with 2020 logframe replication (see "logframe" tab). There was a manual change made for 1 project that cannot track yet.
outc_1_3 | Proportion of impact evaluations that influence transport project during design or implementation. | % of projects | Phase 2+ | 23 | 0.52 | 26 | 0.5 | 27 | 0.52 | 28 | 0.54 | 29 | 0.52 | 27 | 0.56 | [AM] would changing the Phase work/not work? | [AD]: Minor differences with 2020 logframe replication (see "logframe" tab). There was a manual change made for 1 project that cannot track yet.
outc_1_4 | Proportion of completed transport impact evaluations that generate evidence used to support project adoption, targeting, scale-up, scale-down, continuation or cancelation decisions, or that influence discussions on complementary interventions. | % of projects | Phase 4+ | NA | NA | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | [AD]: To discuss with Aidan/Sveta. This would be updated with new myIE data. [AM]: do we have any sense on this scenario?
outc_2_1 | Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself | % of projects | Phase 3+ | 12 | 0.17 | 13 | 0.15 | 13 | 0.15 | 14 | 0.14 | 14 | 0.14 | 14 | 0.14 | [AC]: givn the low numbers expected,would make sense to do a case-by-case look at the projects and see which onese we could make a concerted effort on. e.g. the EMS work packaged to contribute to other EMS projects, or BRT work feeding into new BRT PCNs etc. taking an active role on this would probably be useful anyway if we have the bandwidth - bringing evidence to pipeline PCNs in a timely way. [AM] Could we argue that earlier phased projects have an impact? [AD]: Added this subset of projects in a new tab in this file -- "outc_2_1". You can filter by the scenarios (s1, s2, etc.) for the denominator and then the outcome variable is highlighted in yellow
outc_2_2 (opt 1) | Proportion of completed and published transport impact evaluations with an academic publication | % of projects | Phase 4+ | NA | NA | 3 | 0.66667 | 3 | 0.66667 | 3 | 0.66667 | 3 | 0.66667 | 3 | 0.66667 | [AD]: Alternative definitions to discuss.
outc_2_2 (opt 2) | Proportion of transport impact evaluation publications that are cited in the academic literature | % of projects | Projects with at least 1 publication | NA | NA | 2 | 1 | 3 | 1 | 4 | 0.75 | 5 | 0.8 | 4 | 1 | [AC]: I think we'll be fine on most definitions, so maybe makes sense to propose whatever would be easiest to track? where is the original definition for comparison? [AM]: agree [AD]: Original definition in the row below, and in the "logframe" tab see outcome 2.2, which shows the differences in the indicator name and definition. Also, we discussed at some point whether this be % of projects or publications? If projects, can discuss how to assign publications not linked to a specific project.
outc_2_2 (opt 2) | Proportion of completed and published transport impact evaluations that are cited in the academic literature | % of projects | Phase 4+ | NA | NA | 3 | 0.33333 | 3 | 0.33333 | 3 | 0.33333 | 3 | 0.33333 | 3 | 0.33333 | [AD]: From the 2020 logframe calculation notes: "Proportion of completed and published transport impact evaluations that are cited in the academic literature" Note: Look up all of the ieConnect publications available in Google Scholar and calculate the % of academic publications in Google Scholar that are cited. Even 1 DIME citation counts.
outp_1_1a | Number of ongoing Impact Evaluations (IEs) | Number of projects | None | 31 | 31 | 28 | 28 | 29 | 29 | 30 | 30 | 31 | 31 | 28 | 28 | [AM]: Arianna made a note that she did not see this as an input but more of an outcome. We have recommended however, to remove the breakdown by topic.
outp_1_1a_1 | Number of ongoing Impact Evaluations (IEs) across key sub-sectors: Urban mobility | % of projects | None | 31 | 0.32 | 28 | 0.36 | 29 | 0.34 | 30 | 0.37 | 31 | 0.35 | 28 | 0.39 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_1a_2 | Number of ongoing Impact Evaluations (IEs) across key sub-sectors: Transport corridors | % of projects | None | 31 | 0.35 | 28 | 0.32 | 29 | 0.34 | 30 | 0.33 | 31 | 0.35 | 28 | 0.32 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_1a_3 | Number of ongoing Impact Evaluations (IEs) across key sub-sectors: Road safety | % of projects | None | 31 | 0.32 | 28 | 0.32 | 29 | 0.31 | 30 | 0.3 | 31 | 0.32 | 28 | 0.32 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_1a_4 | Number of ongoing Impact Evaluations (IEs) across key sub-sectors: Rural roads | % of projects | None | 31 | 0.26 | 28 | 0.25 | 29 | 0.24 | 30 | 0.23 | 31 | 0.23 | 28 | 0.21 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_7 | Thematic distribution: Gender (cross-cutting) | % of projects | None | 31 | 0.39 | 28 | 0.39 | 29 | 0.41 | 30 | 0.4 | 31 | 0.39 | 28 | 0.36 | [AM] 1.7-1.9 on geographic/gender/FCV/income distribution – FCDO said these could be removed
outp_1_8_1 | Geographic distribution: Africa | % of projects | None | 31 | 0.77 | 28 | 0.75 | 29 | 0.76 | 30 | 0.73 | 31 | 0.74 | 28 | 0.71 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_8_2 | Geographic distribution: South and SE Asia | % of projects | None | 31 | 0.1 | 28 | 0.11 | 29 | 0.1 | 30 | 0.1 | 31 | 0.1 | 28 | 0.11 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_8_3 | Geographic distribution: FCAS | % of projects | None | 31 | 0.61 | 28 | 0.54 | 29 | 0.55 | 30 | 0.53 | 31 | 0.55 | 28 | 0.5 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_9_1 | Income level distribution: Low income, lower-middle income, or high fragility | % of projects | None | 31 | 1 | 28 | 1 | 29 | 1 | 30 | 1 | 31 | 1 | 28 | 1 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_9_2 | Income level distribution: DFID focus countries | % of projects | None | 31 | 0.77 | 28 | 0.68 | 29 | 0.69 | 30 | 0.67 | 31 | 0.68 | 28 | 0.68 | [AM] this was proposed to be dropped. Are we ok with this going?
outp_1_10_1 | Female Economic Empowerment (FEE): Proportion of IEs with FEE specific intervention | % of projects | None | 31 | 0.26 | 28 | 0.29 | 29 | 0.31 | 30 | 0.3 | 31 | 0.29 | 28 | 0.29 | We can rule out scenario 0 with this indicator (which means we would include Hawassa as separate project)
outp_1_10_2 | Female Economic Empowerment (FEE): Proportion of IEs disaggregated by sex and age | % of projects | None | 31 | 0.45 | 28 | 0.46 | 29 | 0.48 | 30 | 0.47 | 31 | 0.45 | 28 | 0.43
outp_2_2 | Number of IEs or projects working directly with a non-WB implementing partner | Cumulative sum of projects | None | 31 | 12 | 28 | 12 | 29 | 13 | 30 | 14 | 31 | 14 | 28 | 13
outp_2_3 | Proportion of co-financed transport programmes | % of projects | None | 31 | 1 | 28 | 1 | 29 | 1 | 30 | 1 | 31 | 1 | 28 | 1
outp_2_4 | Spend on non-WB IEs or co-funded IEs where WB contribution <=25% | % of projects | None | 31 | 0.26 | 28 | 0.32 | 29 | 0.35 | 30 | 0.37 | 31 | 0.35 | 28 | 0.39 |  | [AD]: Minor differences with 2020 logframe replication (see "logframe" tab)
vfm_5 | Number of government or other operational counterparts directly participating in ieConnect's learning-by-doing approach to implementing impact evaluations | Cumulative sum of counterparts | None | 31 | 83 | 28 | 83 | 29 | 84 | 30 | 88 | 31 | 90 | 28 | 85 | [AM] Output 2 Capacity Building: quantitative numbers of people involved but don’t have something that captures quality of capacity building and quality of participation – Anne asked the so-what question. As discussed by Arianna and Sveta, we will endeavor to provide more substantive qualitative narrative in the next Annual Review to better capture examples of quality when it comes to capacity building and participation
vfm_6 | Number of government or other operational counterparts from FCV locations | Cumulative sum of counterparts | FCV countries | 19 | 37 | 15 | 35 | 16 | 36 | 16 | 36 | 17 | 38 | 14 | 33 | [AC] is there a reason why a cumulative number would change depending on if we drop some projects? how are we defining "cumulative" in this case? same applies to the other cumulative indicators here
vfm_7 | #REF! | % of projects | None | 31 | 0.42 | 28 | 0.46 | 29 | 0.45 | 30 | 0.47 | 31 | 0.45 | 28 | 0.46
vfm_9 (opt 1) | Number of female researchers | Cumulative sum of researchers (Only PIs and research team) | None | 31 | 31 | 28 | 30 | 29 | 31 | 30 | 31 | 31 | 32 | 28 | 31
vfm_9 (opt 2) | Number of female researchers | Cumulative sum of researchers (PIs, research team, RAs/FCs) | None | 31 | 43 | 28 | 44 | 29 | 45 | 30 | 45 | 31 | 46 | 28 | 45 | [AC] second version is more inclusive which i like, but would go with whtever is easiest. we're just taking this from myIE anyway right, so either option is straightforward?

## scenarios_list (hidden)
id | ietitle | country | ttl | notes | fcdo | alltransport | p2020 | s0 | s1 | s2 | s3 | s4 | sd | sdetail_1 | sdetail_2
250 | Lake Victoria Transport Program Rwanda Corridor | Rwanda | Maria Jones | Potential to remove | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | Potential to remove | Aidan - potential to drop
253 | Hawassa Industrial Park Community Impact Evaluation | Ethiopia | Alice Mortlock | Potential to remove | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | Potential to remove
352 | COVID19 Mobility Analytics Task Force | Global | Sveta Milusheva | Questionable | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | Questionable
41 | Ethiopia Expressway | Ethiopia | Alice Duhaut |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Potential to remove
254 | Creating a Transport Data System to Evaluate Improvements to Transport Efficiency and Road Safety | Ethiopia | Theophile Bougna, Alice Duhaut |  | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | Potential to remove | Aidan - potential to drop
338 | Roads for Rural Transformation in Mandul and Chari Provinces of Chad | Chad | Theophile Bougna |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 |  | Aidan - potential to drop
341 | Impact Evaluation of the Integrated and Resilient Urban Mobility Project | Sierra Leone | Nino Pkhikidze, Theophile Bougna |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Potential to remove | Aidan - potential to drop