Annual Review
(Template for Smaller Projects Programmes[1])
[1] A Smaller Project is defined as a funding arrangement with a single implementing partner normally not exceeding £250k. Such projects can be grouped as a Programme for approval and reporting purposes provided the total budget envelope does not exceed £2m. See PrOF Guide.

Summary of Programme Performance
Year	2023-24	2024-25
Overall Output Score	A+	A
Risk Rating	Moderate	Major

Programme title: UK – Rwanda Trade and Investment Partnership Programme
Programme Value £ (full life): up to £2m		Review Date: / November 2025
Programme AMP Code: 400150	Programme Start Date: / November 2023	Programme End Date: / October 2028

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-400150
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-400150

SUMMARY AND OVERVIEW

Programme description / The UK and Rwandan governments have a strong strategic partnership, which supports Rwanda's growth journey through work on reforms aimed at improving the investment and business climate, green transition, facilitation of investment into manufacturing, tax policy, and official statistics collection. In the recent past, the UK has also supported land tenure reform and public administration strengthening in Rwanda. / The economy of Rwanda grew by 8.9% in 2024[2], primarily due to increased agricultural production, government investment in infrastructure, foreign investment in tourism and hospitality, and an increase in private sector credit. Total trade in goods and services (exports plus imports) between the UK and Rwanda was £133 million in the four quarters to the end of Q2 2025, an increase of 118% or £72 million in current prices from the four quarters to the end of Q2 2024. Whilst overall trade with Rwanda is a very small portion of the UK’s trade (Rwanda was the 149th largest trading partner) the UK is the 5th largest export destination for Rwandan exports, with room for growth. / The UK-Rwanda Trade and Investment Partnership has a programme budget of up to £3.28m (of which £208,655 has been spent in this year of review, to support increased trade and investment in Rwanda. The programme aims to strengthen the bilateral relationship between the UK and Rwanda and as such, promote mutual prosperity and inclusive economic development. The planned portfolio of interventions is designed to be both proactive and responsive to the market and priorities of the UK and Rwanda in the areas of trade and investment. The interventions leverage on the UK’s high-level convening power, and strategic relationship with the Rwandan government. Interventions are summarised in the section on intended policy objectives below. / The funding mechanism for this programme is through ODA and non-ODA budgets, allowing post the flexibility to deliver on a more inclusive economic development ambition, encompassing both UK commercial interests and development priorities. In the year under review, the majority of programme spending was ODA, as planned non-ODA spend on some trade promotion events did not go ahead (in part due to UK measures, as described below). However, some non-ODA spending was made on designing and mobilising a British Chamber of Commerce, as well as facilitating a visit by Rwandan Government Officials to visit UKEF and Mabey Bridge/Acrow in the UK. / In February 2025 the UK imposed Restrictive Measures on Rwanda in response to its role in conflict in Eastern DRC. One of these measures was to “limit trade promotion activity with Rwanda”[3] resulting in the need to change programme activities in-year. The logframe was therefore no longer applicable and had to be changed late in the year. Consequently, this review reports on project activities and performance but does not compare with targets (as previous targets are no longer relevant). A review and update of the logframe for the programme will be made after this annual review.
Intended policy objective(s) of projects within this programme. / The policy objectives of the programme include: / Through the convening power of the UK Government, the programme will deliver a series of trade and investment events, including trade and investment roundtables and missions; and capacity building sessions with both government and the private sector. The aim of these convenings is to promote UK trade and investment with and in Rwanda. This will at times be through non-ODA spending when the focus is on UK business particularly exports to Rwanda, although still with a view to enhancing mutual prosperity. Some events, focused on Rwandan exports to the UK, or on investment that will deliver growth and jobs in Rwanda will be through ODA spending. / Through targeted support, and leveraging the wider UK trade and investment toolkit (other programming, development finance vehicles) such as British International Investment (BII), Private Infrastructure Development Group (PIDG), SheTrades, and Manufacturing Africa (MA) to support Rwanda in delivering on its policy priorities – creating decent and productive jobs as well as boosting exports. This policy objective aligns with the Post’s bilateral programmes that are leveraging private investments in the tea sector (one of Rwanda’s top exports) and supporting crucial infrastructure projects to boost trade. This objective is delivered through ODA funding as is supports jobs and livelihoods in Rwanda. / Deliver capacity building, including acting as a source of knowledge sharing and capacity building channel for both the Government of Rwanda and the private sector on trade and investment issues, e.g., providing knowledge and information on trade preferential agreements – including the Developing Country Trading Scheme (DCTS), which could promote adoption of the agreements and thereby enhance trade flows between the two countries; long-term support to the Rwanda Development Board and MINICOM on investment facilitation and promotion, as well as identifying new growth/emerging sectors of investments. This objective is delivered through ODA as it builds capacity in government and private sector for pro-developmental trade and investment policy-making. / .
Overall Programme Score / Programme score: A (meeting expectations) / Programme risk rating: Major, reflecting the impact on delivery from changes to UK government policy on Rwanda (the Restrictive Measures)
Performance against Outcome and Impact indicators / Impact Description: Increased Trade and Investment between the UK and Rwanda / Impact Indicators Progress / 1 Total value of bilateral trade between the UK and Rwanda £122m in four quarters ending Q2 2025 / 2. Volume of foreign direct investment (FDI) flows between UK and Rwanda Our internal estimates (not official) indicate that UK FDI inflows into Rwanda reached roughly USD 300 million in 2025. Figures for Rwanda’s outward FDI to the UK not currently available. / 3. Number of UK businesses newly registered or operational in Rwanda and members of the newly established BCCR. Fifteen companies have registered as members of the BCCR, and four new British companies have commenced operations in Rwanda. / Outcome Description: Increased engagement and capacity of UK and Rwandan businesses to explore and act on trade and investment opportunities. / Outcome Indicators Progress / 1 Number of businesses supported to pitch or showcase trade/investment opportunities 30 local companies were supported to participate in the Taste of Rwanda event and the International Food & Drink Exhibition (IFE) in London, where they showcased their products and services. / 2 Number of MoUs, deals, or expressions of interest signed with support from HMG Four deals were finalized, and four expressions of interest were supported by HMG / 3. Businesses facilitated to understand market opportunities and resolve issues Five British firms were facilitated to understand market prospects, and four others were supported via escalation to government agencies to overcome business-related obstacles. / Summary supporting narrative for the overall programme score in this review. / Over the last year, the UK-Rwanda Trade and Investment Partnerships programme has pivoted to take account of the UK’s Restrictive Measures – this meant for example that an incoming trade mission organised by Invest Africa could not go ahead. We also had to put on hold plans for developing a 2nd UK-Rwanda Business Forum to be held in January 2026. The programme shifted to lower-profile events, and providing long-term capacity building to 2 Rwandan institutions: the Rwandan Development Board (RDB) and the Ministry of Trade and Industry. / At the Output level: due to the shift in activities and change to the logframe, we cannot compare output performance to targets. However, there was solid performance across the output areas. This included the establishment of a British Chamber of Commerce in Rwanda, which by the end of this review period had 15 paid up members. A business advocacy forum was held to promote public-private dialogue on the business environment; a visit was organised for Rwanda Transport Development Agency to the UK to meet with senior officials at UK Export Finance (UKEF) and also Mabey Bridge/Acrow - a British bridge manufacturer. In addition, two long-term, embedded advisors are building capacity in Government of Rwanda. / At the Outcome Level: again, we are unable to compare outcome performance with targets. However, there is progress on all indicators demonstrating that the programme is directly supporting UK and Rwandan firms to engage in bilateral trade. Thirty Rwandan companies were funded to participate in trade missions to the UK, leading to four deals being signed, while five British companies were facilitated to enter the Rwandan market for the first time. / At the Impact Level: Impact indicators have shown a strong improvement this year. Total trade between UK and Rwanda was £133m from July 2024 to June 2025, a 118% increase over the same period last year[4]. Outward British investment in Rwanda of an estimated $300m in 2025 would compare very favourably with official data showing that the stock of UK FDI in 2023 was worth £7m, although the estimate should be treated with caution as it is not official data. / Although not all of the impact can be attributed to this programme, programme activities have contributed in a significant way. Trade missions, Chamber of Commerce activity and the advocacy week have all facilitated Rwandan businesses trading with the UK and/or UK businesses trading and investing in Rwanda. The embedded advisors in the Rwandan Development Board and Ministry of Trade & Industry have informed policies and initiatives which have improved the overall investment climate. These activities were complemented by activities delivered by central UK ODA programmes managed at the FCDO’s HQ, but which received some funds transferred from UK-Rwanda Trade and Investment Partnership. These centrally managed programmes include SheTrades, which brought Rwandan women-owned businesses on trade missions to the UK, and Manufacturing Africa which helped manufacturing firms in Rwanda to raise new investment funds (including some UK-based firms investing in Rwanda, and some Rwandan firms trading with the UK). / .
Major lessons and recommendations for the year ahead / In the past year the UK Government has also made the decision to reduce ODA spending from 0.5% to 0.3% of GNI. As a result the British High Commission in Kigali will have a lower level of ODA for the bilateral programme in Rwanda. Yet, growth will continue to be a major focus of the remaining ODA programme. The BHC Green Growth and Trade team will develop a strategy for our growth work going forward, including how the BHC will draw on and reflect progress on centrally managed programmes. / As a result of changes mid-year the targets set for the logframe for this project were no longer valid. The team will conduct a thorough review of the logframe, including to reflect the new strategy (recommendation above), so that future annual reviews can be made on the basis of milestones and targets.
[2] World Bank data, GDP growth (annual %) - Rwanda | Data
[3] “UK Statement on response to the situation in Eastern DRC” (25th February 2025), accessed at UK Statement on response to the situation in Eastern DRC - GOV.UK
[4] 2025-10-31 Rwanda - UK Trade and Investment Factsheet

PROGRAMME STRATEGY OR THEORY OF CHANGE

Impact
Increased Trade and Investments between the UK and Rwanda

Number of new and additional UK investments attracted into Rwanda and increased UK-Rwanda trade flows
Number of businesses supported to pitch investment / trade opportunities and forge partnerships with their counterparts from the UK
Outcomes

Production of high impact knowledge products.
Facilitate Trade and Investment Missions to the UK

Record high attendance of the UK-Rwanda Business Forum

Outputs

Organise trade and investment missions, roundtables, deal rooms, exhibitions, where Small and Medium-sized businesses (including women- and youth-owned SMEs) can connect with investors access markets.

Commission market research and disseminate of high impact knowledge products, as well as build capacity and capability of the Rwandan market – including private/public.
Activities
Facilitate the convening high-level bilateral trade and investments events, such as the UK-Rwanda Business Forum and the UK-AIS that brings together key stakeholders in the UK, Rwanda and SSA.

Capacity Building & Market Research
Trade & Investment Missions
High-Level Trade and Investment Convenings

Components

Figure 1: Theory of Change

Figure 1 represents the original Theory of Change (ToC) of the UK-Rwanda Trade and Investment Partnership. The ToC is anchored on three components, i) Delivery of high-level Trade and Investment Convenings, ii) Organising of Trade and Investment Missions, and iii) Delivering impactful Capacity Building and Market Research Interventions. It brings together the logical flow of inputs across these components into the delivery of Outputs, Outcomes and Impact.

This year the programme has had to shift activities (as discussed in Part A). While the overall objectives remain similar, some changes to the ToC are needed:

- Capacity building (the third output) is now delivered through embedded advisors in Government of Rwanda
- Second outcome is split into two new outcomes: (2) Number of businesses participating in missions and (3) Number of follow-up engagements resulting from missions.

DETAILED OUTPUT OR PERFORMANCE AREA SCORING

Delivery of Projects.
Performance area:	Bilateral Engagement Platforms: Facilitation of strategic platforms for UK-Rwanda business engagement to promote trade and investment dialogue
Number:		1	Score:	A
Weighting (%):		10	Weighting revised since last AR?	Yes, down

Indicator(s)	Progress
1.1 Number of bilateral forums/events hosted.	All the events met expectations, and a work plan to address business issues was adopted. / BCCR and EBCR jointly organized an Advocacy Week featuring sector-specific sessions on Tourism & Hospitality, Mining, Employment, and Tax to identify barriers to doing business in Rwanda. / BCCR and EBCR jointly organised the CEO Forum as a platform to present business challenges identified during Advocacy Week to senior government officials - including the Minister of Trade and Industry and the RDB CEO - with the goal of addressing these issues and developing practical solutions.
1.2 Satisfaction rate of attendees (via post-event surveys).	The process of conducting the satisfaction survey is still underway

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

Due to the Restrictive Measures, we could not host a Business Forum this year (we had originally intended to hold one in early ’26 to repeat the success of the 2024 Forum). Instead, the focus shifted to creating a chamber of commerce for British businesses in Rwanda, in order to have a platform supporting and advocating for British business. The programme spent £24,813.04 on design and inception work leading up to the creation of the British Chamber of Commerce Rwanda (BCCR) and £8,147 on the launch event and logistical support.

Through Advocacy Week and the CEO Forum, BCCR in partnership with the European Business Chamber in Rwanda (EBCR) provided platforms for businesses to present challenges directly to policymakers, strengthening the public-private dialogue. High-level engagement with the Minister of Trade and Industry and the RDB CEO demonstrates Rwanda’s commitment to improving its business climate and investor confidence. This programme part- funded these strategic events.

Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).
Last year’s AR recommended that we sign a formal MoU with GoR in order to collaborate on the next Business Forum. As it was not possible to run a forum this year, this recommendation became less relevant, but it remains important for future years if and when a forum is organised.

Performance area:	Trade and Investment Missions: Support and coordination of targeted trade and investment missions to enhance market access and business linkages between the UK and Rwanda.
Number:		2	Score:	A
Weighting (%):		10	Weighting revised since last AR?	Yes, down

Indicator(s)	Progress
2.1 Number of trade/investment missions facilitated (UK to Rwanda and vice versa).	Two trade missions were successfully organised by HMG, enabling local companies to participate in the Taste of Rwanda and International Food Exhibition (IFE) events held in the UK in November 2024 and March 2025 respectively. As a result, participating companies secured new UK buyers and signed contracts for the export of horticultural products. / Both missions successfully met expectations. We continue to support and monitor the implementation of signed contracts.
2.2 Number of businesses participating in missions.	Two trade missions attracted participation from 35 companies, reflecting strong interest and engagement. Feedback indicates that 35 local companies were satisfied with the level of organisation and delivery of the two trade missions
2.3 Number of follow-up engagements resulting from missions.	Five follow-up engagement have been successfully undertaken to reinforce collaboration and track implementation of prior agreements. The results reports have been drafted and shared, indicating that 85% of participating companies were satisfied with the connections established during the events.

Briefly summarise how projects have contributed to programme objectives and provide supporting narrative for the score.
Trade missions are a cornerstone for advancing trade and investment objectives. They open new markets for local companies, attract foreign investment, and foster strategic business partnerships between local businesses and UK buyers or investors.
For example, the Taste of Rwanda event in November 2024 was designed to connect suppliers of Rwandan agricultural and horticultural products with distributors and consumers in the UK. A key highlight of the event was a coffee cupping session, which showcased Rwanda’s premium coffee bean exports. Attendees had the opportunity to sample a diverse selection of Rwandan coffee varieties and engage directly with suppliers. This programme also funded attendance by Rwandan horticulture growers at the International Food Exhibition, held in London in March 2025. This allowed them to showcase their produce and find new buyers, leading to supply contacts being signed.
Beyond commercial benefits, trade missions in the UK have strengthened the UK’s soft power influence in Rwanda with relatively modest budget, provided critical insights into international standards, and created high-level platforms for engagement and networking. These interactions are continuously building trust and long-term commercial relationships that drive mutual prosperity.
Ultimately, consistent trade missions will enhance the competitiveness of local enterprises, support sustainable economic growth, and reinforce the bilateral relationship between the UK and Rwanda- delivering tangible economic and diplomatic outcomes.
Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).
N/A – no recommendations for this output in last year’s annual review

Performance area:	Provision of technical assistance to strengthen institutional capacity for trade and investment.
Number:		3	Score:	A
Weighting (%):		80%	Weighting revised since last AR?	Yes, up

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of long-term advisors delivering capacity building to Rwandan institutions (RDB, Minicom)	2	2

Briefly summarise any planned learning that has taken place, using the table below (if helpful) or a simple narrative supporting the score.

The majority of programme spending this year funded two embedded, long-term advisors delivering capacity building in two government institutions: the Rwandan Development Board (RDB) and the Ministry of Trade and Industry (known by its French abbreviation, MINICOM). These advisors were previously placed in Rwanda by the Overseas Development Institute (ODI) Fellowship Scheme, and on completion of the scheme, this programme took on funding the placements by making direct grants to ODI. Financial management and oversight of the advisors remain with ODI.

The advisor to RDB focused on building capacity and giving guidance on policy frameworks, e.g. revisions to the Investment Code to update investor incentives, developing a new mining sector strategy and guiding the institutional reform which brought the (previously separate) Rwanda Mines, Petroleum and Gas Board into the Rwanda Development Board.

The advisor to MINICOM conducts analysis and builds internal analytical capacity. This year he has covered topics including supply chain analysis, fiscal policy impacts, market access and opportunity/risks from trade. He also provided analytical inputs on a cabinet paper on industrialisation, and a new trade policy for the department.

Both advisors are building capacity within their respective institutions by building analytical tools and automating data processes, then training local staff to use these tools and take over development in the long run. Nonetheless, the dependency of senior leaders on analysis from embedded international advisors from ODI and other organisations like Tony Blair Institute poses a risk for sustainability if funding is withdrawn.

Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).
It is important for the SRO and programme managers from the High Commission to maintain regular contact with the long-term advisors and their line managers within Government of Rwanda, in order to monitor progress of this technical assistance. The High Commission can also make use of these contacts where there is cross-over with other development programmes.
Looking forward, the GGT should include a capacity building element as part of their future strategy in order to maximise the sustainability of capacity building activities.