Title: Expertise to Support Economic Reform in Sierra Leone
Programme Value £ (full life): £5.45m		Review date: November 2025
Programme Code: 400154	AMP start date: 21/11/2023	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2023-24	2024-25	2025-26
Overall Output Score	B	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003894.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006309.xlsx

SUMMARY AND OVERVIEW

Description of programme

The Expertise to Support Economic Reform (ESER) in Sierra Leone programme is a bilateral ODA programme in the British High Commission (BHC) Freetown’s portfolio. It primarily provides technical assistance (TA) to the Government of Sierra Leone (GoSL) on public financial management (PFM), revenue mobilisation and energy and water infrastructure investment.

The programme’s objectives are:

- On PFM: To improve the integrity, efficiency and control of public spending and thereby reduce government borrowing, in turn improving macroeconomic stability.
- On revenue mobilisation: To increase domestic revenue while minimising harm to the business environment and impacts on the poor. As above, this should reduce government borrowing and in turn improve macroeconomic stability.
- On energy and water infrastructure investment: To support the effective prioritisation and planning of infrastructure investment deals and reduce barriers to infrastructure investment, thereby increasing responsible Development Finance Institution (DFI)/private investment in infrastructure projects.

All of the above should help alleviate key barriers to economic growth - macroeconomic instability, government borrowing crowding out lending to the private sector, and an infrastructure deficit - in Sierra Leone.

The original programme business case was for a two-year £4.95m programme, with an end date of 31 March 2025. This has since undergone two changes:
- The end date was extended by 12 months in October 2024 to 31 March 2026 with the budget ceiling remaining unchanged. This time extension was to accommodate plans for activity to track and assess the impact of public spending in Sierra Leone’s health and education sectors (in support of the first objective above), which was going to extend beyond the original business case end date of 31 March 2025.
- The original £4.95m business case budget ceiling was increased to £5.45m in March 2025, following Ministerial approval for this. This happened because expenditure against budget had been faster than anticipated as we increased programme activity in summer 2024 in response to a significant opportunity to support electricity sector reform following an electricity crisis in April 2024. This cost extension was done to allow the programme to provide ongoing technical assistance to GoSL to operationalise its emerging package of critical reforms for the sector over the upcoming 12 months.

The programme is currently constituted of three components:
- A contract with Adam Smith International (ASI) to provide TA to the central government on PFM, revenue mobilisation and infrastructure investment.[1] ASI has a ‘core team’ of long-term, largely Sierra Leone-based staff overseeing various short-term ‘expert pool’ consultants and downstream partners to deliver specific TA interventions to GoSL.
  [1] Please note – due to budget constraints - from April 2025 this component has focused on providing TA to the central government on infrastructure investment, largely stopping all TA on PFM and revenue mobilisation from that point.
- A funding arrangement with the International Growth Centre (IGC) to support property tax reform in the three largest cities in Sierra Leone, with a focus on Makeni and Kenema during the review period.[2]
  [2] This arrangement was an Accountable Grant Agreement (AGA) until end of March 2025. Since then, it has been managed via the wider contract the FCDO has with the London School of Economics (LSE) to deliver the overall IGC programme. For this reason, only the activity delivered up to end of March 2025 is covered in this annual review, as activity beyond that point will be covered in the annual review for the overall IGC programme.
- An externally financed output (EFO) arrangement with the World Bank to conduct a Public Expenditure Tracking Survey (PETS) and Quantitative Service Delivery Survey (QSDS) in the health and education sectors in Sierra Leone.

Summary supporting narrative for the overall score in this review

The programme has performed well during this review period. Some key achievements have included:

- Securing substantive investor interest in two infrastructure projects:
  - There has been material engagement with GoSL by a private sector investor on a renewable energy transaction. This engagement began at an ESER-supported half-day event at which GoSL[3] presented ten energy and water infrastructure investment opportunities to a British International Investment (BII)-led delegation of DFIs and other organisations[4] in November 2024.
    [3] The National Investment Board, the Ministry of Energy, the Guma Valley Water Company, and the Sierra Leone Water Company.
    [4] British International Investment (BII), PIDG-Infraco, Development Finance Corporation (DFC), United States Trade and Development Agency (USTDA), USAID, African Development Bank, FMO (the Dutch DFI), Proparco (the French DFI), DEG (the German DFI).
  - A DFI-backed investor travelled to Freetown in early November 2025 to engage with GoSL on a water transaction. This could result in the financing of a pre-feasibility and feasibility study on the project in the first half of 2026.

Producing a revised electricity Collection Account manual that was provisionally agreed by the Ministries of Energy and Finance, the Electricity Generation and Transmission Company (EGTC) and the Electricity Distribution and Supply Authority (EDSA) in June 2025 (though is currently still to be finally agreed and approved by Cabinet). Revising the manual is necessary for a World Bank-supported procurement of an independent fiduciary agent to manage the electricity sector’s financial transactions, a critical reform to improve investor confidence in the sector (and a Prior Action for the disbursement of World Bank budget support to GoSL).

EDSA’s Board and Management responded very constructively to the findings of a pilot investigation (in one EDSA District, covering ~20,000 EDSA customers) into the sources of EDSA’s revenue losses[5] despite these findings containing difficult messages. The findings resulted in EDSA contracting Deloitte (the same partner used for the ESER-funded intervention) to deploy a distribution expert to overhaul EDSA’s commercial department, funding this themselves.
[5] I.e. technical losses of electricity along the distribution network (e.g. due to poor-performing equipment) and insufficient payment for electricity supplied by EDSA to consumers.

More than doubling collected property tax revenue in Kenema and subsequently piloting enforcement activity there that was proven to more than double property tax compliance among treated properties.
However, there have also been the following challenges:

As the programme is almost entirely focused on providing technical assistance and/or capacity building support to GoSL, the programme’s performance against log frame targets relies on actions taken by GoSL counterparts rather than the delivery partners alone. Given limited capacity, scarce resources and the considerable competing demands on GoSL counterparts’ time, some log frame indicator targets have been missed.

The programme is seeking to support infrastructure projects that are at a very early stage to secure investment. This process takes longer than the timeframe of this programme. It will therefore probably not be possible to progress these projects to the final point of securing investment by the programme’s end date – although they will have moved significantly closer to this point by the end of the programme relative to where they were at the programme’s outset.

In addition, the financial viability of the electricity and water utilities (specifically, EDSA and Guma Valley Water Company, GVWC) in the near-term poses a significant barrier to securing DFI/private infrastructure investment in the electricity and water sectors. If DFI/private investments in on-grid electricity generation and water supply in Freetown are made prior to significant improvement in these two utilities’ finances, there’s a risk these investments will not succeed, thereby deterring further investment in the sector (and even in the wider economy) as a result. These improvements will take time to materialise. For example, on the energy side, the programme has supported EDSA’s efforts here, but it seems possible that significant progress will only be made once EDSA’s operations are being managed by a private sector participant. The process for this is ongoing, and the potential benefits will likely be realised over several years.

Despite these challenges, of the programme’s seven outputs that had milestones during the review period, five scored A (with a combined weighting of 65%) and two scored B (with a combined weighting of 35%), demonstrating that the majority of outputs are meeting their log frame indicators. In addition, although it may take longer than the programme’s duration to finally secure DFI/private investment the programme has put specific projects on a very positive trajectory towards this.

Table 1: Mapping of components, outputs and output scores

Component	Output	Weighting	Output Score
TA on infrastructure investment, delivered by ASI	1. Infrastructure Investment Project Pipeline	5%	A
	2. Transaction support to one water and one energy investment project	20%	A
	3. Key electricity sector reforms progressed	20%	B
	4. Support to reduce EDSA’s technical and commercial losses	20%	A
Property tax reform, delivered by the IGC	8. A reformed property tax system in Makeni City	5%	A
	9. Property tax enforcement in Kenema City	15%	A
A Public Expenditure Tracking Survey (PETS) for health and education, delivered by the World Bank	10. PETS and QSDS for health and education	15%	B

Major lessons and recommendations for the year ahead

On securing DFI/private investment in energy and water infrastructure

As described above, the programme is seeking to support infrastructure projects that are at a very early stage to secure investment. This process takes longer than the timeframe of this programme. This means there’s a risk that the work delivered to-date will become a ‘stranded asset’ if further support outside of the programme itself is not provided (either by other FCDO programmes, other donors, GoSL, or potential investors themselves). It is therefore recommended that the programme team proactively explore the options for other support to progress these ESER-supported projects further towards the point of securing investment.

Even if the FCDO can support these projects further outside of the ESER programme, large-scale spending (particularly for feasibility studies, which are very expensive) is needed to meaningfully progress them. FCDO funding at this scale is not likely to be available, so we need to coordinate closely with other development partners working in relevant areas that do have sufficient funds for this type of work (e.g. the World Bank) or the potential investors in these projects who may be willing to cover these costs. We need to ensure any other further TA we provide on these projects is appropriate given this wider funding. It is therefore recommended that the programme team proactively coordinates with relevant development partners working in related areas in Sierra Leone to ensure our respective support to ESER-supported projects is complementary, maximising the collective value of our resources.

On supporting electricity sector reforms

Technical assistance and capacity building to support key electricity sector reforms to progress is not sufficient by itself. Sustained political engagement is needed to ensure that reforms are implemented. We should consider discontinuing technical assistance in areas where progress on reforms stalls.

The programme has supported EDSA’s efforts to improve its financial sustainability by reducing its revenue losses, but it is possible that significant progress will only be made once EDSA’s operations are being managed by a private sector participant. This process is ongoing and the benefits could take several years to materialise. It is therefore recommended that the programme team consider the value of providing further support in this area in the interim, given this longer-term solution may be the only means of delivering significant impact.

On supporting revenue mobilisation

Property tax enforcement work can be done very effectively at low cost, provided relevant government authorities are willing to pursue this. The FCDO programme and the partner’s team should present the impressive findings on the effectiveness of enforcement activity at increasing property tax compliance in Kenema to the Fiscal Decentralisation Division at the Ministry of Finance and to Freetown and Makeni City Councils, to encourage them to undertake similar enforcement action there.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case

A summary of the programme’s current theory of change is set out in table form below. This remains broadly the same as the theory of change set out in the programme Business Case, though now with more detail - particularly on outputs – added. The steps required to achieve outcome and impact are still considered to be valid and are clearer now that specific outputs have been defined. However, as described below, some challenges are expected when it comes to translating outputs and outcomes into impact on the infrastructure investment side within the programme’s timeline (given the amount of time it typically takes to take infrastructure projects from pre-feasibility stage to commercial close, and the need for significant improvements in the financial viability of the electricity and water utilities) and in attributing outcomes and impacts on the PFM/revenue side to the programme’s activities.

Table 2: Current theory of change for the programme

Input / Activity	Outputs	Intermediate Outcomes	Outcomes	Impact
Expertise in power and water infrastructure investment and related reforms to the enabling environment – provided to GoSL / Capacity building of GoSL in these areas	A GoSL-owned and independently managed infrastructure investment project pipeline / DFI/ private investor engagement with the pipeline projects / Targeted support for some of the most ‘bankable’ projects in the pipeline to progress along the ‘transaction process’ / Support for key electricity sector reforms – to improve the enabling environment for electricity sector investment	Specific power and water infrastructure projects progressed to the point of being ‘investor ready’ / Enabling environment for power and water infrastructure investment improved, such that DFI/private investment in these sectors is feasible		Increased investment in power and water infrastructure… / …alleviating Sierra Leone’s infrastructure deficit, which is a key constraint to economic growth
PFM and revenue expertise (and associated expertise in data / digital technologies) – provided to GoSL / Capacity building of GoSL in these areas	Robust macro-fiscal forecasts	A credible national budget (i.e. based on a realistic resource envelope)	Reduced budget over-runs / and / Increased revenue / …and therefore… / A reduced budget deficit / reduced government borrowing	Improved macroeconomic stability / & / Reduced crowding out of bank lending to the private sector / And therefore… / Alleviation of these two key constraints to economic growth
	A systematic and comprehensive process for preparation of the payroll budget	Reduced in-year payroll budget requests / Reduced variance between the payroll budget and actual payroll expenditure
	An expanded data warehouse at the National Revenue Authority (i.e. more digital revenue systems integrated into it) and accompanying data dashboards	Increased enforcement of taxes / Removal of barriers to tax compliance
	Support to EDSA to reduce its technical and commercial losses	Increased revenue collection at EDSA and therefore a reduced need for electricity subsidies
A comprehensive package of support to property tax reform implementation	A reformed property tax system in Makeni City / Increased enforcement of property tax in Kenema and/or Makeni City / Ongoing implementation of reformed property tax systems in Freetown, Kenema and Makeni handed over to city councils there	Increased revenue potential from property tax / Additional property tax liability largely accounted for by higher value properties	Increased property tax revenue in Freetown, Kenema & Makeni, sustained over the long-term / …and therefore… / A reduced budget deficit / reduced government borrowing
A Public Expenditure Tracking Survey (PETS) & Quantitative Service Delivery Survey (QSDS) conducted in the health and education sectors, and publication of the findings	PETS & QSDS methodologies and questionnaires developed and agreed in collaboration with the Ministry of Finance, Ministry of Health, Ministry of Basic & Senior Secondary Education, and World Bank. / PETS & QSDS data collection complete. / Report on findings of PETS & QSDS published and actively disseminated among GoSL, civil society and donor stakeholders	Increased transparency around public spending on health and education, both internally within GoSL (i.e. improved MoF understanding of this) and among civil society and development partners	Increased accountability for public spending on health and education, both internally within GoSL (i.e. improved MoF understanding of this) and among civil society and development partners / …and therefore… / Increased integrity, efficiency and control of public spending on health and education
Ongoing institutional and political economy analysis to guide the above		NA

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Given where the programme is at, how likely is it that outcomes and impact will be achieved within the time and budget originally planned?

In terms of the programme’s objective to support specific water and energy infrastructure investment deals to progress to the point of securing DFI/private investment, the intended impacts and outcomes are as follows:

Table 1: Intended Impacts and Outcomes

IMPACT 1	Impact Indicator 1.1		Baseline (Nov 2023)	Target / (31 Mar 2026)
Increased amount of responsible DFI/private sector investment in power and water infrastructure	Number of ESER-supported power and water infrastructure investment projects that have secured DFI/private investment	Planned	0	2
		Achieved	NA
	Impact Indicator 1.2		Baseline (Nov 2023)	Target / (31 Mar 2026)
	Total projected financial value of ESER-supported power and water infrastructure investment projects that have secured DFI/private investment	Planned	0	$150m
		Achieved	NA

OUTCOME 1	Outcome Indicator 1.1		Baseline (Nov 2023)	Target / (31 Mar 2026)
Specific power and water infrastructure projects progressed to the point of being 'investment ready'	Number of ESER-supported power and water infrastructure projects that are ready (in terms of legal and financial planning and documentation) for investment.	Planned	0	2
		Achieved	NA
	Outcome Indicator 1.2		Baseline (Nov 2023)	Target (31 Mar 2026)
	Total projected financial value of ESER-supported power and water infrastructure projects that are ready (in terms of legal and financial planning and documentation) for investment.	Planned	0	$150m
		Achieved	NA

OUTCOME 2	Outcome Indicator 2.1		Baseline	Milestone 2 / (Nov 2025)	Target / (31 Mar 2026)
A more conducive enabling environment for energy and water investment.	Number of priority investment barriers being addressed with ESER support.	Planned	0	5	7
		Achieved	NA	5
	Outcome Indicator 2.2		Baseline	Target (31 Mar 2026)
	Number of meaningful reforms GoSL has made to improve the enabling environment as a result of ESER support.	Planned	0	3
		Achieved	NA

In terms of the prospects for the programme’s outputs and outcomes to translate into the intended impacts re securing DFI/private infrastructure investment by the programme’s end date, the financial viability of the electricity and water utilities (specifically, EDSA and GVWC) in the near-term poses a significant barrier. In addition, the programme is seeking to support infrastructure projects that are at a very early stage to secure investment. This process takes longer than the timeframe of this programme. For both of these reasons, it may not be possible to progress these projects to the final point of securing investment by the programme’s end date. Although they are expected to have moved significantly closer to this point than they were when the programme began.

In terms of the programme’s objective to improve the integrity, efficiency and control of public spending and increase domestic revenue (and thereby reduce government borrowing, in turn improving macroeconomic stability), the intended impacts and outcomes are as follows:

Table 2: Intended Impacts and Outcomes

IMPACT 2	Impact Indicator 2.1		Baseline	Milestone 2 (end of 2024)	Target / (end of 2025)
Improved macroeconomic stability	Size of budget deficit[6] (% of GDP)	Planned	-2.9%	-1%	0%
		Achieved	NA	-2.7%	0.6% (projected)
			Source: IMF, December 2025
	Impact Indicator 2.2		Baseline (Nov 2023)	Milestone 1 / (Sep 2024)	Milestone 2 (Sep 2025)	Target / (Jan 2026)
	Level of year-on-year consumer price inflation	Planned	54.2%	<30%	<20%	<10%
		Achieved	NA	20.9%	5.4%
			Source: Statistics Sierra Leone, October 2025
[6] Which in turn determines the level of new public borrowing in that year.

OUTCOME 3	Outcome Indicator 1		Baseline	Milestone 1 (Dec 2024)	Target / (Dec 2025)
Reduced budget over-runs	Reduced overall budget over-runs / (Amount actual Total Expenditure exceeded budgeted amount, in percentage terms)	Planned	38%	<10%	0%
		Achieved	NA	15%	-15% (projected)
			Source: GoSL Budget Speeches for respective years
	Outcome Indicator 2		Baseline	Milestone 1 (Dec 2024)	Target / (Dec 2025)
	Reduced payroll budget over-runs / (Amount actual spending on Wages & Salaries exceeded budgeted amount, in percentage terms)	Planned	0	<5% of payroll budget	0% i.e. payroll spend is within budget
		Achieved	NA	-2.1%	-6.0% / (projected)
			Source: GoSL Budget Speeches for respective years

OUTCOME 4	Outcome Indicator 1		Baseline	Milestone 1 (Dec 2024)	Target / (Dec 2025)
Increased tax and non-tax revenue collection at both central government and city council level	Amount of revenue collection at central government level (% of GDP)	Planned	7.9%/GDP	8.5%/GDP	9%/GDP
		Achieved	NA	8.9%/GDP	9.8%/GDP / (projected)
			Source: IMF, December 2025
			Baseline	Milestone 1 (Dec 2024)	Target / (Dec 2025)
	Outcome Indicator 1	Planned	0	+50%	+50%
	Amount of property tax revenue collection at Kenema and Makeni City Councils	Achieved	NA	+163%[7]
			Source: Figures provided by implementing partner
[7] This figure only reflects increased revenue collection at Kenema City Council as the reformed property tax system only became operational in Makeni in 2025.

The programme has already achieved very positive outcomes in terms of reduced payroll budget over-runs and increased property tax revenue. Performance in terms of increasing revenue collected at central government level and in reducing the budget deficit is also expected to be positive by the end of the programme (compensating for under performance in some areas in 2024), though it will be harder to measure the exact contribution to this made by programme activities given this is likely to reflect a far wider effort.

Have there been any significant changes in the budget or timetable for delivery of the programme?

As mentioned above, the original £4.95m business case budget ceiling was increased to £5.45m in March 2025, following Ministerial approval for this. This happened because expenditure against budget had been faster than anticipated as we increased programme activity in summer 2024 in response to a significant opportunity to support electricity sector reform following an electricity crisis in April 2024. This cost extension was done to allow the programme to provide ongoing technical assistance to GoSL to operationalise its emerging package of critical reforms for the sector over the upcoming 12 months.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

BHC Freetown’s primary development objective going forwards is to support inclusive and sustainable economic growth in Sierra Leone. The programme therefore continues to fit with the wider BHC Freetown portfolio given its overall focus on delivering economic growth via increased DFI/private investment and increased macroeconomic stability. The programme also aligns well with the wider FCDO goal of mobilising private investment at scale into developing markets. Based on this and the above analysis of programme performance, it should continue until its end date.

The programme is due to end in approximately four months’ time. BHC Freetown should determine between now and then how well the focus on increasing DFI/private investment in energy and water infrastructure projects (as opposed to non-infrastructure investments e.g. in light manufacturing/agri-processing) fits with its future strategy going forwards.
C: Detailed Output Scoring
Output Title	Output: A GoSL-owned and independently managed infrastructure investment project pipeline, with a focus on power and water projects / Delivered via contract with Adam Smith International (ASI)
Output number:		1	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – revised down from 18% (reflecting the reduced level of activity under this output under this review period compared to the last)

Indicators	Milestones for this review	Progress
Please note: The majority of the activity under this output was completed during the previous annual review period (i.e. Dec 2023-Nov 2024) – see previous annual review for output indicators 1.1 and 1.2, and milestones related to these.
1.3 Number of prospective investors (DFIs and private companies) that have provided quality feedback on the infrastructure investment project pipeline	Three by 31 December 2024.	Met

Briefly describe the output’s activities and provide supporting narrative for the score
Output’s Activities
ASI’s Infrastructure Investment Adviser within the core team worked collaboratively with ARIA[8] to organise engagement between GoSL[9] and an ARIA delegation[10] visiting Freetown in November 2024, including through a two-hour GoSL-hosted event on 6th November that had the specific purpose of presenting the pipeline to the delegation and eliciting their feedback/securing follow-up. This event generated a large amount of investor and DFI interest in some of these projects. Follow-up meetings were held between GoSL and a private sector investor on a renewable energy project, and FMO and PIDG-Infraco provided written feedback on some of the pipeline projects. In addition, a DFI-backed investor travelled to Freetown in early November 2025 to engage with GoSL on a water transaction.
[8] ARIA = Africa Resilience Investment Accelerator; a group of Development Finance Institutions.
[9] The National Investment Board, the Ministry of Energy, the Guma Valley Water Company, and the Sierra Leone Water Company.
[10] British International Investment (BII), PIDG-Infraco, Development Finance Corporation (DFC), United States Trade and Development Agency (USTDA), USAID, African Development Bank, FMO (the Dutch DFI), Proparco (the French DFI), and DEG (the German DFI).
Justification for Score

This output scored an A over this annual review period (Dec 2024-Nov 2025) as the single relevant output indicator was fully met on time.

Describe any changes to this output during the past year, and any planned changes as a result of this review
Output indicator 1.4 - GoSL is independently managing the infrastructure investment project pipeline on an ongoing basis - was removed from the programme’s log frame in April 2025. This output was removed due to budget limitations – it was reasoned that available resources would be best deployed supporting the most bankable projects in the pipeline to progress along the transaction process (i.e. closer towards securing investment) rather than supporting the future sustainability of the pipeline as a tool.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The recommendations from the previous annual review were:

- Continue to put GoSL stakeholders in the lead, supporting them to do things rather than doing things on their behalf. Set realistic milestones for this and be willing to flex plans to reflect the time and resource this requires.
- Continue to consider how to best navigate relevant GoSL stakeholders, given the various Ministries, Departments and Agencies (MDAs) with an interest in this work.

As activity under this output was largely completed during the previous annual review period (because the main activity remaining did not proceed due to budget limitations), these recommendations have not been taken forward in the case of this output. However, the programme team and delivery partners are following these principles more generally, as they apply across most outputs under the programme.

Lessons learned and recommendations for remainder of programme
Not applicable – too little activity was delivered under this specific output during the annual review period to have generated additional lessons relative to those already included in the previous annual review, when the bulk of the activity under this output took place.
Not applicable – as above.

Output Title	Output: Technical assistance has been provided to progress at least two specific water and/or energy infrastructure projects (both in the pre-feasibility phase) along the ‘transaction process’, moving them closer to securing DFI/private investment / Delivered via contract with Adam Smith International (ASI)
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – no previous weighting as output is new since last AR

Indicators	Milestones for this review	Progress
Project 1: The Mountain Communities bulk water supply project[11]
2.1. Information Memorandum for the Mountain Communities bulk water supply project (for use by Guma Valley Water Company (GVWC) and the National Investment Board (NIB)) completed / (Binary indicator: yes/no)	Info Memo completed by 31 March 2025.	Met
2.2 Topographic surveys (LIDAR surveys using drones) conducted for the Mountain Communities and Western Urban bulk water supply project sites[12] / (Binary indicator: yes/no)	Topographic surveys completed by 31 March 2025.	Met
2.3 New water willingness to pay study conducted for the Western Area (last time conducted was 2014) – to determine the realistic water tariff that can be charged / (Binary indicator: yes/no)	Target date does not fall within review period.
2.4 Water tariff review conducted for the Western Area / (Binary indicator: yes/no)	Target date does not fall within review period.
Project 2: 20 MW solar plus 10MW battery storage project[13]
2.5 Study evaluating the feasibility[14] of integrating five[15] 20 MW solar power plants with 10 MW battery storage into Sierra Leone’s 224kV CLSG electricity transmission line	Study completed and report delivered by 31 March 2025.	Met
[11] An estimated capital investment of approximately $128m for the design and construction of two dams (to create the Toothik and Kongo 2 reservoirs), water treatment facilities and a transmission system to an upgraded water distribution network (the upgrade of the water distribution network is outside of the scope of the project itself). It is estimated that this project would supply water to up to ~300,000 people in Freetown over a period of ~27 years.
[12] To improve the accuracy of the data required for detailed design and construction work (which is an important element in the financial analysis of the projects), thereby increasing investor confidence in the projects’ financial viability.
[13] An initial pilot investment project worth $42m, within a programme of 12 such projects along the Côte d'Ivoire-Liberia-Sierra Leone-Guinea (CLSG) transmission line.
[14] In terms of whether: i. the capacity of the 225kV CLSG interconnecting line is sufficient to take the load from the solar power plants, and ii. the effect on the stability of the grid of injecting the power from these power plants into the interconnecting line.
[15] At the following sites: Kamakwie, Yiben, Bumbuna, Bikongor, and Kenema.

Briefly describe the output’s activities and provide supporting narrative for the score
Output’s Activities
Indicator 2.1: Info Memo for Mountain Communities bulk water supply project

ASI deployed three ‘expert pool’ consultants (a Senior Infrastructure Investment Expert, a Legal Expert, and a Finance Expert) to produce the Information Memorandum between January and March 2025. In addition, two ‘core team’ members – the Infrastructure Team Lead and the Infrastructure Investment Adviser – proactively facilitated and oversaw this work.

Table 3: ‘Expert Pool’ days worked on this output during the review period

Senior Infrastructure Investment Expert	25
Junior Expert	18.5
Finance Expert	9.375
Total	52.875

Additionally, the presentation of the information memorandum document was developed in collaboration with communications and graphic design experts.

These ‘expert pool’ consultants did the following (with the facilitation and oversight of the relevant ‘core team’ members):
- Collated and reviewed existing detailed technical information on the Mountain Communities bulk water supply project.
- Assessed the accuracy, consistency and transparency of available project data.
- Determined core economic assumptions and devised a financial model for the project (covering capex, opex, revenue and debt).
- Devised a credible transaction structure for the project.
- Identified the relevant legal framework (e.g. Public-Private Partnership legislation, permitting and land, Local Content Act) and the formal roles and responsibilities of respective MDAs.
- Drafted a concise information memorandum (essentially, a marketing document) for an investor audience clearly outlining the information necessary – as far as it is currently available - for them to meaningfully gauge their interest in investing in the project.
- Presented the draft information memorandum to NIB and GVWC for distribution to relevant DFIs and other potential investors.
- Worked closely with NIB and GVWC throughout, applying a ‘learning through doing’ approach.

Indicator 2.2: Topographic surveys for the Mountain Communities and Western Urban bulk water supply projects

ASI contracted a specialised drone survey firm who carried out surveys of both sites and produced a detailed technical report setting out the findings during January to March 2025. This has been shared with Guma Valley Water Company and other MDAs.
Indicator 2.5: Study evaluating the feasibility6 of integrating five 20 MW solar power plants with 10 MW battery storage into Sierra Leone’s 224kV CLSG electricity transmission line

ASI deployed an electrical systems engineer who conducted the study and produced a report during January to March 2025.

Table 4: ‘Expert Pool’ days worked on this output during the review period

Electrical Systems Engineer	40
Total	40

The study evaluated the feasibility of integrating solar power plants with battery storage (PV+BESS) into Sierra Leone’s electricity grid. The study specifically examined five proposed 20MW solar PV +BESS sites (Kamakwie, Yiben, Bumbuna, Bikongor, and Kenema) along the CLSG transmission line and assessed how their connection would impact on the stability and reliability of the national grid by conducting simulations and technical assessments that reflect expected conditions between 2025 and 2030.

Justification for Score

This output is assessed to have scored an A during the review period as all activities and deliverables were completed on time and to the required standard.

Describe any changes to this output during the past year, and any planned changes as a result of this review
At the start of the annual review period, this output had only been defined at a very high level – just the output title with no detail on output indicators and milestones. This was necessarily the case because it was not possible to determine what specific work would be needed under this output until the projects it relates to had been identified. It was not possible to identify these projects until work on an earlier output (on an infrastructure investment project pipeline) had been completed, which did not happen until November 2024.
No further changes are currently planned over the remainder of the programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations for this output in the previous annual review as work on this output did not begin until the end of last year’s annual review period, as explained above.
Lessons learned and recommendations for remainder of programme
Given the very early stage of these two projects at the start of the programme, there will likely not be enough time and budget to progress them to the final point of securing investment by the programme’s end date – although they will have moved significantly closer to this point relative to where they were at the programme’s outset. This means we risk the work delivered to-date becoming a ‘stranded asset’, if further support outside the programme itself is not possible. It is therefore recommended that the programme team proactively explore the options for other support to progress these ESER-supported projects further towards the final point of securing investment.

Even if the FCDO can support these projects further outside of the ESER programme, large-scale spending (particularly for feasibility studies, which are very expensive) is needed to meaningfully progress them. We are not likely to have this scale of funding so need to coordinate closely with other development partners working in relevant areas that do (e.g. the World Bank) or the potential investors in these projects who may be willing to cover these costs. We need to ensure any other further TA we provide on these projects, is appropriate given this wider funding. It is therefore recommended that the programme team proactively coordinates with relevant development partners working in related areas in Sierra Leone to ensure our respective support to ESER-supported projects is complementary, maximising the collective value of our resources.
The financial viability of the electricity and water utilities (specifically, EDSA and GVWC) in the near-term poses a significant barrier to these investment projects securing DFI/private investment and succeeding if and when they do. If DFI/private investments in the electricity and water sector are made prior to significant improvement in sector finances, there’s a risk these investments will not succeed, thereby deterring further investments as a result. On the financial viability of the electricity utility, it is possible that significant progress will only be made once EDSA’s operations are being managed by a private sector participant. The process for this is ongoing, but the benefits could take years to materialise. We should consider pausing technical assistance to support DFI/private investment in electricity generation until it’s clear that EDSA’s finances are on a positive trajectory.

Output Title	Output: Key electricity sector reforms – that will improve the enabling environment for electricity sector investment - progressed / Delivered via contract with Adam Smith International
Output number:		3	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – no previous weighting as output is new since last AR

Indicators	Milestones for this review	Progress
3.1 Short-term (covering 2025 and 2026) reform plan for the electricity sector delivered / (Binary indicator: yes/no)	Reform plan completed by 31 March 2025	Met
3.2 Training on electricity sector financial modelling (to be used for planning purposes) delivered to staff from the Ministry of Energy (MoE), EDSA, EGTC and the Electricity and Water Regulatory Commission (EWRC) / (Binary indicator: yes/no)	Training delivered by 31 March 2025	Partially met – this training was delivered on time and in full, but its value was limited as - in delivering the training - it was discovered that the model in question was not necessarily appropriate for its intended use
3.3 Electricity sector ‘Collection Account’ manual revised / (Binary indicator: yes/no)	Revised manual completed by 31 March 2025	Met with delay – revised manual completed on 27 June 2025, around three months late.
3.4 Electricity sector ‘Collection Account’ manual adopted by GoSL / (Binary indicator: yes/no)	Revised manual adopted by GoSL by 31 March 2025	Not yet met – the revised manual was provisionally agreed by the Ministries of Energy and Finance, the Electricity Generation and Transmission Company (EGTC) and the Electricity Distribution and Supply Authority (EDSA) in June 2025, but is currently still to be finally agreed and approved by Cabinet.
3.5 Debt position of electricity sector clarified by historical audit / (Binary indicator: yes/no)	Historical audit completed and audit report delivered by 31 March 2025	Partially met – the historical audit was delivered on time but was incomplete due to limited access to financial records.

Briefly describe the output’s activities and provide supporting narrative for the score
Output’s Activities
Indicator 3.1: Short-term reform plan for the electricity sector delivered

ASI deployed three ‘expert pool’ consultants (a Senior Infrastructure Adviser, a Senior Financial Adviser, and a National Legal Adviser) to work with relevant MDAs to develop the reform plan between November 2024 and March 2025. In addition, two ‘core team’ members – the Infrastructure Team Lead and the Infrastructure Investment Adviser – proactively facilitated and oversaw this work.

Table 5: ‘Expert Pool’ days worked on this output during the review period

Senior Infrastructure Adviser	65.875
Senior Financial Adviser	5.25
National Legal Adviser	2.875
Total	74

These ‘expert pool’ consultants did the following (with the facilitation and oversight of the relevant ‘core team’ members):
- Reviewed all relevant reports (including the various existing electricity sector reform plans/roadmaps) and met with stakeholders from the various relevant MDAs (MoE, EDSA, EGTC and EWRC).
- Delivered an inception report on 4 December 2024 proposing all relevant details of the plan.
- Held a workshop in mid-January 2025 with stakeholders from the MoE, EDSA, EGTC, and EWRC. This agreed the following:
  - The reform plan’s pillars (i.e. thematic areas to be covered by the plan)
  - Actions within each pillar that are of high enough priority to be included in the plan
  - Deliverables, milestones and targets for each action, and metrics for measuring performance against targets (including baseline performance for each of these, where possible)
  - Clear institutional and personal accountabilities for delivering against each action
  - Resourcing of activities under each action and requirements for external funding/support
- To support ongoing monitoring and reporting of performance against the plan, a presentation was delivered to the MoE’s Director of Planning and Policy and his team on the processes to follow.

Indicator 3.2: Training on electricity sector financial modelling (to be used for planning purposes) delivered to staff from MoE, EDSA, EGTC and EWRC
- ASI deployed the same Senior Infrastructure Adviser as under indicator 3.1 (above) to deliver this training.
- A two-day workshop on electricity sector financial modelling was delivered to staff from MoE, EDSA, EGTC and EWRC. This included analyses of the existing model and descriptions of how the model handles key processes (load forecasting, revenues and tariffs, generation costs, transmission capex and opex, distribution capex and opex, subsidies and working capital). Participants received the original model, the presentation incorporating conclusions and the process descriptions.

Indicator 3.3: Electricity sector ‘Collection Account’ manual revised

ASI deployed two ‘expert pool’ consultants (an International Legal Adviser and a National Legal Adviser) to work with relevant GoSL stakeholders to revise the collection account manual between November 2024 and June 2025. In addition, two ‘core team’ members – the Infrastructure Team Lead and the Infrastructure Investment Adviser – proactively facilitated and oversaw this work.

These ‘expert pool’ consultants did the following (with the facilitation and oversight of the relevant ‘core team’ members):
- During the inception phase, held consultations with relevant GoSL stakeholders (EDSA, MOF, MoE, and the Public-Private Partnership Unit of NIB) and development partners (World Bank and the Millennium Challenge Corporation, MCC), and reviewed the following materials (to understand and assess Sierra Leone’s current Collection Account system for the electricity sector):
  - List of GoSL’s Power Purchase Agreements (PPAs) and MOUs with all Independent Power Producers (IPPs), including status of each of these (i.e. whether signed, cabinet approved, parliament approved).
  - Collection Account arrangements for the electricity sector as of June 2022.
  - Updated interim term sheet from 12 March 2020 and the previous interim term sheet from 2018.
  - The Operations Manual for the Collection Account Arrangements for the Sierra Leone Electricity Sector prepared by Herbert Smith Freehills/MRC (funded by the World Bank) from 22 February 2018.
  - Sierra Leone’s Electricity Act, 2011 and the 2018 Amendment.
- Produced a blueprint for a revised Collection Account, including relevant notes on the overall collection system. This was delivered on 10 December 2024.
- Held a two-hour meeting between GoSL (MoF, EDSA, MoE, NIB – PPP Unit, EGTC, EWRC) and relevant development partners (FCDO, World Bank, Millenium Challenge Corporation) on 10 December 2024 at which they presented, discussed and agreed the blueprint for the revised Collection Account manual.
- Produced a report reviewing current Collection Account arrangements and another report setting out policy issues in December 2024.
- Produced a draft revised Collection Account manual (as well as a PowerPoint on the CA manual providing a ‘quick read’). This was delivered on 27 March 2025.
- Also produced the following reports: on legal and regulatory issues,[16] a draft implementation memorandum,[17] and a review of the terms and conditions of GoSL’s existing Power Purchase Agreements (PPAs).[18] These were all delivered in March 2025.
  [16] Identifying current legislative gaps and the regulatory measures required to support effective implementation of the Collection Account.
  [17] Outlining the transitional path and conditions precedent required to operationalise the manual, including banking arrangements, budget structures, and contractual alignment.
  [18] Highlighting key inconsistencies and risk areas within existing PPAs that must be addressed to align with the proposed Collection Account framework.
- Due to limited capacity, scarce resources and the considerable competing demands on GoSL counterparts’ time, GoSL decisions on policy aspects of the manual were received on 17 April 2025, rather than on 10 December 2024 as originally planned, so that key parts of the Collection Account manual remained in draft at end of March.
- A validation workshop with GoSL (MoF, EDSA, MoE, NIB – PPP Unit) and relevant development partners (FCDO, World Bank, Millenium Challenge Corporation) was held on 26 June 2025 to secure provisional agreement on the final draft manual. Although the manual is currently still to be finally agreed and approved by Cabinet.
- The final draft Collection Account manual incorporating all revisions in light of stakeholder inputs was delivered on 27 June 2025.

Indicator 3.4: Electricity sector ‘Collection Account’ manual adopted by GoSL
The revised manual was provisionally agreed by the Ministries of Energy and Finance, EGTC and EDSA in June 2025, but is currently still to be finally agreed and approved by Cabinet.

Indicator 3.5: Debt position of electricity sector clarified by historical audit
- Moore Sierra Leone was engaged to conduct this historical audit of the electricity sector, with a particular focus on: i. payments due to EDSA from MDAs for energy used, and ii. electricity subsidies provided to EDSA by GoSL. The audit was conducted and a report delivered by 31 March 2025.
- Unfortunately, the audit was incomplete due to incomplete access to financial records for certain years, delayed authorisations hindering the timely release of financial documentation, and differences in reported transactions between relevant stakeholders.

Justification for Score

This output is assessed to have scored a B over the review period because most output indicators were only partially met or were met with delay. While the partner delivering the technical assistance on this output (ASI) performed to a very high standard, some log frame indicator targets have been missed due to limited capacity, scarce resources and the considerable competing demands on GoSL counterparts’ time.

Describe any changes to this output during the past year, and any planned changes as a result of this review
At the start of the annual review period, this output had only been defined at a very high level – just the output title with no detail on output indicators and milestones. This detail was populated early in the review period.
No further changes are currently planned over the remainder of the programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations for this output in the previous annual review as work on this output did not begin until the end of last year’s annual review period.
Lessons learned and recommendations for remainder of programme
Technical assistance and capacity building to support key electricity sector reforms to progress is not sufficient by itself. Sustained political engagement is needed to ensure that reforms are implemented. We should consider discontinuing technical assistance in areas where progress on reforms stalls.
Output Title	Output: Technical assistance and capacity building support has been provided to EDSA (the state-owned electricity distribution utility) to reduce its technical and commercial losses / Delivered via contract with Adam Smith International – who contracted Deloitte Ghana as a downstream partner to deliver this output
Output number:		4	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – no previous weighting as output is new since last AR

Indicators	Milestones for this review	Progress
4.1. Review of EDSA’s current revenue protection function and recommendations for a revised organisational structure completed / (Binary indicator: yes/no)	Review of EDSA’s current revenue protection function to be completed by end-November 2024. / Provide a description of comparator electricity distribution utilities’ revenue protection functions where these provide examples of best practice – to be completed by end-November 2024. / Propose a revised organisational structure aligned with international best practice by end-November 2024.	Met / Met / Met
4.2. Preparations for pilot of revenue protection measures in one EDSA district completed / (Binary indicator: yes/no)	Identify EDSA counterpart staff to work with the Deloitte team and establish survey field teams with designated supervisors by end-November 2024. / Collect the following data by end-November 2024: customer billing; prepaid purchases; customer debts; single-line diagrams (i.e. showing the path of power flow); the number and locations of feeders and substations. / Conduct analysis of collected data on customer billing and prepaid purchases to identify anomaly accounts by end-November 2024. / Identify the EDSA district likely to be experiencing the highest revenue losses (to use this district as the test area for the pilot) by end-November 2024. / Provide an updated methodology for calculating energy loss by end-November 2024. / Deliver classroom-style training to survey field staff and supervisors by end-November 2024. / Develop communications materials to facilitate access to properties in the pilot district by end-November 2024.	Met / Met / Met / Met / Met / Met / Met
4.3. Pilot of revenue protection measures in one EDSA district completed / (Binary indicator: yes/no)	GIS mapping of feeders, substations and customers in pilot district, including auditing of customer meters and hands-on training of counterpart EDSA staff in GIS survey and meter inspection – to be completed by end March 2025. / Energy balance and data analysis conducted to estimate technical and non-technical loss profiles in the pilot district to support targeted interventions to address these – to be completed by end March 2025. / Determine transformer loading and assess the physical condition of transformers and associated equipment at the substations. Make recommendations to address the identified issues. To be completed by end March 2025.	Met (19,583 customers were successfully mapped) / Met / Met
4.4. Recommendations provided on the effective management of ‘T4 customers’ (large electricity users, who are charged the highest tariff) to reduce revenue losses / (Binary indicator: yes/no)	Gather and analyse six months of commercial data on T4 customers to detect discrepancies or irregularities by end-November 2024. / Select a pilot sample of 100 T4 customers with meters installed in their distribution feeders; perform GIS Survey of 100 T4 customers and related equipment. To be completed by end February 2025. / Identify areas for improving revenue collection and determine whether independent management of T4 customers is appropriate and, if so, make recommendations regarding its implementation. To be completed by end February 2025.	Met / Met / Met

Briefly describe the output’s activities and provide supporting narrative for the score
Output’s Activities
ASI contracted Deloitte Ghana to deliver this output between October 2024 and March 2025. In addition, one ASI ‘core team’ member – the Infrastructure Team Lead – proactively facilitated and oversaw this work.

Indicator 4.1: Review of EDSA’s current revenue protection function and recommendations for a revised organisational structure completed

Deloitte Ghana did the following (with the facilitation and oversight of the ASI Infrastructure Team Lead) between mid-October and March 2025:
- Reviewed EDSA’s current revenue protection function (i.e. structure and processes).
- Produced a description of comparator electricity distribution utilities’ revenue protection functions that provide examples of best practice.
- Proposed a set of 25 key performance indicators (KPIs) for the purpose of measuring and improving the effectiveness of EDSA’s revenue protection function going forwards, with a sub-set of seven of these recommended for quick adoption. These KPIs would enable quantifiable tracking of revenue recovery, electricity theft detection, operational efficiency, and enforcement effectiveness.
Indicator 4.2: Preparations for pilot of revenue protection measures in one EDSA district completed

Deloitte Ghana did the following (with the facilitation and oversight of the ASI Infrastructure Team Lead‘) between mid-October and end-November 2024:
- Identified EDSA counterpart staff (and their designations) to work with the Deloitte team and establish survey field teams with designated supervisors.
- Collected the following data: customer billing; prepaid purchases; customer debts; single-line diagrams (i.e. showing the path of power flow); the number and locations of feeders and substations.
- Conducted analysis of collected data on customer billing and prepaid purchases to identify anomaly accounts, working in close collaboration with designated counterpart EDSA staff to strengthen their capacity.
- Identified the EDSA district likely to be experiencing the highest revenue losses (to use this district as the test area for the pilot) – based on: incidence of zero consumption, abnormal consumption, outstanding balances, number of consumers that have not vended consecutively in last three+ months, consumer complaints.
- Reviewed EDSA’s current methodology for calculating energy loss and provided a clearly outlined updated methodology.
- Delivered classroom-style training to survey field staff and supervisors to equip staff to undertake GIS mapping and to determine the level of losses in the pilot district.
- Worked with EDSA to develop communications materials about the survey exercise for customers in District 80 and official letters to high-level customers to facilitate access to their properties by the survey field teams.
Indicator 4.3: Pilot of revenue protection measures in one EDSA district completed

Deloitte Ghana did the following (with the facilitation and oversight of the ASI Infrastructure Team Lead) between December 2024 and March 2025:
- Conducted GIS mapping of feeders, substations and customers (to create an accurate geospatial database of the electricity distribution network and customer connections – mapping customers to the network components supplying them) in the pilot district, including auditing of customer meters and hands-on training of counterpart EDSA staff in GIS survey and meter inspection.
- Integrated this geospatial data on feeders, substations and customers with the metering and billing systems to produce a network model for energy flow analysis for the pilot district. Used this network model to calculate energy supplied and consumed at different points in the network (feeders, transformers and customer endpoints) and thereby estimate technical and non-technical loss profiles in the pilot district to support targeted interventions to address these.
- Determined transformer loading (load imbalances and neutral overloads) and assessed the physical condition of transformers and associated equipment at the substations. Produced recommendations to address the identified issues.

Indicator 4.4: Recommendations for the effective management of ‘T4 customers’ (large electricity users, who are charged the highest tariff) to reduce revenue losses

Deloitte Ghana did the following (with the facilitation and oversight of the ASI Infrastructure Team Lead) between mid-October 2024 and February 2025:
- Gathered and analysed six months of commercial data on T4 customers to detect discrepancies or irregularities, such as customers with abnormally low usage or non-recharging of prepaid meters for extended periods.
- Selected a pilot sample of 100 T4 customers with meters installed in their distribution feeders.
- Compiled and analysed the 100 customers to determine those who have not billed, not vended, have irregular payment patterns and have outstanding arrears.
- Conducted a GIS Survey of 100 T4 customers and related equipment (including verifying meter installations and detecting faulty or non-communicating meters) and undertook energy accounting and energy balance analysis on the distribution transformers and feeders that supply them.
- Identified areas for improving revenue collection and made recommendations on whether an independent management structure is needed for T4 customers.

Justification for Score

This output is assessed to have scored an A during the review period as all activities and deliverables were completed on time and to the required standard. Moreover, the findings resulted in EDSA contracting Deloitte (the downstream partner used for the ESER-funded intervention) to deploy a distribution expert to overhaul EDSA’s commercial department, funding this themselves.

Describe any changes to this output during the past year, and any planned changes as a result of this review
At the start of the annual review period, this output had only been defined at a very high level – just the output title with no detail on output indicators and milestones. This detail was populated early in the review period.
No further changes are currently planned over the remainder of the programme because all activity under this output is already complete.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations for this output in the previous annual review as work on this output did not begin until the end of last year’s annual review period.
Lessons learned and recommendations for remainder of programme
EDSA revenue increases are not guaranteed as a result of this activity. Instead, this relies on i. EDSA implementing the recommendations produced as a result of this activity, and ii. EDSA expanding this activity on a sustained basis to the rest of its network. It’s possible that significant progress will only be made once EDSA’s operations are being managed by a private sector participant. The process for this is ongoing. The programme team should consider the value in providing further support in this area in the interim, given this longer-term solution may be the only means of delivering significant impact.
Output Title	Output: A reformed property tax system in Makeni City / Delivered via Accountable Grant Agreement with the International Growth Centre
Output number:		5	Output Score:	TBC
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – revised down from 30% (reflecting the reduced level of activity under this output under this review period compared to the last)

Indicators	Milestones for this review	Progress
Please note: The majority of the activity under this output was completed during the previous annual review period (i.e. Dec 2023-Nov 2024) – see previous annual review for output indicators 5.1 and 5.2, and milestones related to these.
5.3 % increase in property tax revenue potential in Makeni City as a result of the reform	50% increase once reformed system operational i.e. by 31 March 2025	Exceeded – actual increase of 67%
5.4 Share of additional property tax liability in Makeni City accounted for by higher value properties (%)	>40% (i.e. the reformed system should be progressive; with a majority of the additional liability to come from higher value properties) by 31 March 2025	Met – actual share of 43% (with high value properties representing just 10% of the total property stock)

Briefly describe the output’s activities and provide supporting narrative for the score
Output’s Activities
The International Growth Centre (working in collaboration with the International Centre for Tax and Development) continued to deliver the remaining elements of their comprehensive package of support to Makeni City Council during the first four months of the review period (December 2024-March 2025), working through their downstream partner, the West Africa Rice Company (WARC).
They provided support to Makeni City Council to deliver the following during the review period:
- A new IT system (MOPTAX 2.0) for property tax administration (including integration with payment providers) was implemented at Makeni City Council.
- Printing and delivery of Rate Demand Notices (i.e. tax bills) to all 47,000 taxable properties in Makeni City.

Justification for Score
This output is assessed to have scored an A during the review period as all relevant log frame targets were met.

Describe any changes to this output during the past year, and any planned changes as a result of this review
No changes were made to this output during the past year. No changes are planned as a result of this review because all activity under this output was completed as of 31st March 2025.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The recommendations from the previous annual review were:
- The link between this output (a reformed property tax system) and its intended outcome (increased collected property tax revenue) hinges on the assumption that property taxes will be enforced by Makeni City Council. This link could be strengthened by expanding this output to include support on property tax enforcement.
- This is now the third city this support has been provided to, yet the reforms in the previous two cities (Freetown and Kenema) are not yet fully sustainable. Going forwards, focus on sustainability/consolidation rather than further expansion into other cities.
On the first of these, we have taken forward pilot work on property tax enforcement at Kenema City Council during the annual review period (i.e. Nov 2024-Dec 2025) – see Output 6 below. On the second of these, we are continuing to support property tax reform in Sierra Leone in financial year 2025-26 by buying into the FCDO centrally managed International Growth Centre programme. This support is entirely focused on supporting a sustainable handover of the property tax systems to the three city councils supported so far (Freetown, Kenema and Makeni).

Lessons learned
Not applicable – too little activity was delivered under this specific output during the annual review period to have generated additional lessons relative to those already included in the previous annual review, when the bulk of the activity under this output took place.
Recommendations for remainder of programme
Not applicable – as above.

Output Title	Output: A strategy for tax enforcement and sensitization that involves civil society actors has been designed, piloted and implemented in the city of Kenema. / Delivered via Accountable Grant Agreement with the International Growth Centre
Output number:		6	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes – no previous weighting as output is new since last AR

Indicators	Milestones for this review	Progress
Collaboration agreements have been reached between the Kenema City Council and relevant civil society actors to implement property tax sensitization and enforcement activities / (Binary indicator: yes/no)	Memorandum of Understanding (MOU) signed between Kenema City Council (KCC) and the Kenema Interreligious Council to deploy religious leaders to sensitize property owners to the reformed property tax system that has been implemented and to conduct property tax enforcement activities in the city – by 30 November 2024. / MOU signed between KCC and the Council of Chiefs of Kenema to establish a Court System for enforcing property tax (one that holds KCC accountable and is viewed as legitimate by property owners) – by 30 November 2024. / MOU signed between KCC and the Sierra Leonean Association of Journalists to promote journalism informing property owners of the property tax reform and enforcement actions – by 1 March 2025.	Met / Met / Met
Property tax enforcement strategy implemented among a random sample of property owners in Kenema city	Property tax enforcement notices[19] distributed to a sample of 3,094 property owners across Kenema city – by 29 November 2024. / Court summons distributed to the set of property owners that received an enforcement notice but have still not complied with their property tax obligations - by 20 December 2024. / Court hearings held to evaluate the cases of property owners who remain in default as of 13 January 2025 – by 30 January 2025.	Met / Met (court summons were successfully delivered to 2,092 property owners in default) / Met
A property tax education campaign (visits by religious leaders to property owners) has been implemented, aiming to promote semi-voluntary tax compliance	Tax education visits involving at least one representative of the Kenema Interreligious Council have taken place for a sample of 3,069 property owners in default in the city by 30 January 2025.[20]	Met
[19] These enforcement notices explain that failure to comply with the property tax by December 2024 will result in a formal court summons in front of Kenema's Traditional Local Court.
[20] These visits are to motivate property owners to comply and explain the necessity of tax enforcement among those that fail to comply.

Briefly describe the output’s activities and provide supporting narrative for the score
Output’s Activities
The output’s activities over the annual review period are clearly detailed in the table above. These activities were undertaken to pilot two means of seeking to increase property tax compliance among a sample of properties in Kenema City – taxpayer education and legal enforcement action. The impact of these two methods was rigorously measured through a randomised controlled trial (RCT) approach.
Justification for Score

The output is assessed to have scored an A as all output indicators were met on time and in full. Moreover, the enforcement activity was estimated (via a rigorous RCT-based methodology) to have more than doubled compliance among the treated sample (from 26.3% in July 2024, to 56% in January 2025).
Describe any changes to this output during the past year, and any planned changes as a result of this review
This output was added to the ESER programme’s log frame during the annual review period as this activity had not been planned prior to that.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations for this output in the previous annual review as work on this output did not begin until the end of last year’s annual review period.
Lessons learned
Property tax enforcement work can be done very effectively at low cost, provided the City council is willing.
Recommendations for remainder of programme
Present the impressive findings on the effectiveness of this type of activity at increasing property tax compliance to the Fiscal Decentralisation Division at the Ministry of Finance and to Freetown and Makeni City Councils, to encourage them to undertake similar enforcement action there.

Output Title	Output: A Public Expenditure Tracking Survey (PETS) and Quantitative Service Delivery Survey (QSDS) conducted in the health and education sectors, and publication of the findings / Delivered via Externally Financed Output arrangement with the World Bank
Output number:		8	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes – no previous weighting as output is new since last AR

Indicators	Milestones for this review	Progress
PETS & QSDS methodologies and questionnaires developed and agreed in collaboration with the Ministry of Finance, Ministry of Health, Ministry of Basic & Senior Secondary Education, and World Bank.	PETS methodology and questionnaires developed and agreed by 30 October 2025 / QSDS methodology and questionnaires developed and agreed by 30 October 2025	Partially met – PETS methodology and questionnaire developed and agreed on time, but QSDS now de-scoped due to insufficient budget.
PETS & QSDS data collection complete.	Target dates do not fall within review period.
Report on findings of PETS & QSDS published and actively disseminated among GoSL, civil society and donor stakeholders.	Target dates do not fall within review period.

Briefly describe the output’s activities and provide supporting narrative for the score
Output’s Activities
The output’s activities during the review period have focused on designing the PETS questionnaires. This has encompassed the following:
- An initial meeting was held on 4 February 2024 between FCDO leads (the Economic Adviser, Education Adviser and Health Adviser at the British High Commission, Freetown) and World Bank leads to decide which areas of spend within health and education the PETS should focus on. This was supplemented by written follow-up to confirm focus areas based on the which items of spend account for the largest shares of GoSL’s education and health budgets.
- World Bank leads shared the draft PETS questionnaires with FCDO for review in early June 2024. FCDO leads submitted detailed written feedback on the PETS questionnaires on 17 July 2024.
- The following consultation meetings on the PETS questionnaires were held with relevant GoSL counterparts and development partner stakeholders:
  - Health development partners[21] on 24 June 2024.
    [21] UNICEF, GIZ, WHO, UNFPA, Irish Aid, Helen Keller International.
  - Ministry of Health stakeholders on 1 July 2024.
  - GoSL payroll stakeholders[22] on 16 July 2024, and again on 31 July 2024.
    [22] The Budget Bureau at the Ministry of Finance, Accountant General’s Department, the Teaching Service Commission, the Health Service Commission.
  - The overall GoSL working group for the PETS (chaired by the Chief Economist at the Ministry of Finance) on 9 September 2024.
  - Minister of Basic and Senior Secondary Education on 11 September 2024.
- In August 2024, the World Bank contracted Innovations for Poverty Action (IPA) to conduct the data collection. The decision was taken at this point not to proceed with the QSDS under the EFO arrangement due to there not being sufficient budget to complete both the PETS and QSDS to a high standard.
Justification for Score

Activities under this output are considered to have gone very well - collaboration with World Bank colleagues has been very positive and there has been extensive consultation on the questionnaires. The score of a B is explained by the need to de-scope the QSDS – this decision was necessary to remain within budget while also maintaining a sufficiently large sample size for the PETS so that its findings could be considered nationally representative. The World Bank is expected to take forward a QSDS or similar separately under another World Bank programme.
Describe any changes to this output during the past year, and any planned changes as a result of this review
This output was added to the ESER programme’s log frame during the annual review period as this activity had not been planned prior to that.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations for this output in the previous annual review as work on this output did not begin until the end of last year’s annual review period.
No significant lessons were learned relating to this output during the review period that can be applied during the remainder of the programme. The PETS questionnaires are due to be piloted at the end of November 2025. Lessons and recommendations are likely to emerge from that process. It will be important to reflect on lessons learned from using this type of delivery mechanism (an EFO arrangement with the World Bank) for future programming, including around FCDO’s scope to review budget estimates provided by the Bank under the terms of this arrangement. This could help avoid under-budgeting in future, as happened in this case.
In terms of recommendations for the remainder of the programme, we should seek to engage with the Bank on their plans to take forward the QSDS or similar separately under another World Bank programme, as this output is complementary to the PETS, so their findings will be most valuable when considered together.

## D: VALUE FOR MONEY

Key cost drivers and performance

As of end October 2024, spending over the review period on each programme component was as follows:
- TA on infrastructure investment (delivered by ASI): approximately £1.4m.
- Property tax reform (delivered by the IGC): approximately £480,000.
- A Public Expenditure Tracking Survey (PETS) for health and education (delivered by the World Bank): approximately £235,000.

In the interests of proportionality, this section focuses on the VfM performance of the first component (TA on infrastructure investment, delivered by ASI) as this accounted for around 66% of total spending over the review period.

As is to be expected in the case of a technical assistance programme, daily fees (plus hardship allowances, where applicable) for both ‘core team’ members and ‘expert pool’ consultants accounted for the majority of spending over the review period under this component. As this is the largest cost driver, the section that follows (on economy, efficiency and effectiveness) mainly focuses on this.

Economy

Spending under this component has been economical in the following ways:
- The supplier was procured via an FCDO procurement framework, which sets caps for the daily rates that can be charged for each category of consultant based on a market assessment of competitive rates.
- The daily rates for consultants contracted under the programme compare well (i.e. are often lower) to other programmes ASI is the supplier for.
- Where suppliers (rather than individual consultants) have been contracted, ASI has conducted a competitive process through requests for proposals, saving significantly against forecast costs for delivery of these interventions.
- ASI’s margin for the programme is much lower than the average for programmes ASI is the supplier for. In part this reflects the use of passthrough (i.e. ASI earning a zero margin on inputs) in some cases to allow the programme to hire delivery partners who would not otherwise be affordable.
- A consistent emphasis has been placed on engaging national experts wherever feasible, with key core team roles increasingly filled by Sierra Leonean professionals, reducing reliance on more expensive international consultants.
- ASI has also used employees in significant roles rather than consultants, who tend to be more expensive.
- ASI have successfully economised on other (i.e. non-staff time) expenses by:
  - Moving to a cheaper and better office space, and subsequently downsizing this office space in response to a reduced budget, thereby keeping overheads low as a proportion of overall spending.
  - Running an exercise to widen their supplier pool for key procurements (hotels, event venues, stationary, vehicle hire).
  - Proportionally allocating shared expenses between ESER and another FCDO programme delivered by ASI in Sierra Leone (the Green Cities, Infrastructure and Energy Programme programme).
  - Using a combination of remote and in-country working for international consultants to minimise travel and subsistence costs.

Efficiency
Efficiency in this case can be understood as the amount of partner staff time (inputs) it has taken to deliver technical assistance interventions (outputs). Providing technical assistance to the Government of Sierra Leone is time and resource-intensive given GoSL counterparts’ limited capacity, their scarce resources and the considerable competing demands on their time. Navigating this efficiently requires strong existing relationships with GoSL counterparts, particularly at senior levels, and an in-depth understanding of the context and how to work optimally within it. ASI maximised efficiency in this respect by deploying core team members with strong existing relationships with relevant GoSL counterparts and significant local knowledge. ASI have also paired international and local expert pool consultants on a number of interventions to ensure there is the right combination of technical skill/experience and local relationships/understanding so that the technical assistance delivered gains traction.

Effectiveness

Of the programme’s seven outputs that had milestones during the review period, five scored A (with a combined weighting of 65%) and two scored B (with a combined weighting of 35%), demonstrating that the majority of outputs are meeting their log frame indicators. Effectiveness has been maximised by ASI drawing on recommendations from their network for consultants and re-using the same consultants on new interventions if they performed to a high standard on previous ones.
VfM performance compared to the original VfM proposition in the business case

The VfM proposition in the business case focused on the use of an FCDO framework for procurement of the contract for the main programme component. As referenced above, this has happened, therefore the reality of programme delivery has matched up to the VfM proposition in the business case.
Assessment of whether the programme continues to represent value for money

Based on the various measures taken to ensure economy and efficiency, and the A score demonstrating a good level of effectiveness, the programme is assessed to continue to represent value for money and should therefore continue.

E: RISK
Overview of risk management
The ESER programme operates within a complex political and institutional landscape; the programme applies a nuanced risk management approach whereby risk appetites are carefully set to balance ambition with caution, safeguarding resilience and integrity.
The programme has a comprehensive risk register that is maintained, monitored and updated regularly by FCDO as well as risk registers maintained by the programme partners. Monthly Programme Management meetings are held with ASI and risk is discussed every third meeting, i.e. quarterly, while risks that are materialising are covered as and when this is occurs.
A summary of the main risks over this year are outlined below:
Financial and Fiduciary:

There is a risk that incidents of fraud, bribery and corruption could lead to the misuse of funds, reputational damage, and reduced programme impact. This risk is inherent to the operating environment. All partners for the programme have policies and processes to minimise and track fiduciary risks while the programme team continues to scrutinise monthly payments on partner invoices.
Safeguarding:
The programme maintains a cautious risk appetite for safeguarding, aligned with BHC Freetown’s portfolio level risk appetite for this category of risk. The main safeguarding efforts under the programme during the review period have been focused on infrastructure investment interventions, as some of these have involved a significant amount of field work. Safeguarding has been integrated into the delivery of these intervention through training and daily briefings for field staff.
Recommendations
- Risk discussions with partner organisations are held regularly but are not systematically documented. It is recommended that these discussions be formally minuted.
- Mitigation actions should be tracked and implemented, including conducting a Programme Fraud Risk Assessment to identify and address fraud risks specific to ESER.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
The ESER programme has now entered its final year of implementation. All implementing partners have good financial and commercial management systems in place. The programme team meets with programme partners on a monthly or quarterly basis to discuss technical issues and review progress for the quarter. Throughout the year, the programme team reviewed the reports of implementing partners and ensured that they meet the standard FCDO guidelines as per the funding instruments signed with them.
Additionally, dedicated monthly meetings on safeguarding, financial and risk management were held with the partners to ensure they develop comprehensive risk registers and reflect a realistic risk appetite. The programme’s financial management and overall financial controls have been assessed as having good standards such as keeping forecast variances within a 5% range, timely submission of reports, adhering to audit compliance requirements and categorising invoices by cost heads to ensure transparency.
Project 1. Expertise to Support Economic Reforms (ESER) Lead contract with Adam Smith International (ASI)
ASI is working through a commercial contract signed via the International Multi-Disciplinary Programme (IMDP) Framework Agreement. ASI have demonstrated consistent good performance on financial management and financial reporting has been timely and aligned with KPIs. Delivery has largely met expectations, and adaptive management has supported continuity despite external challenges. Programme management has remained robust, with close coordination and transparency between FCDO and the delivery team. Accuracy and timeliness of reporting have been strong, and all quarterly reports, monthly reports and forecast and invoices have been delivered within agreed deadlines.
Project 2: Property Tax reform in City Councils in Sierra Leone
Under this output the FCDO signed an Accountable Grant Agreement (AGA) with the International Growth Centre (IGC) to support property tax reform in three of the largest cities in Sierra Leone. This AGA ended at end of March 2025. Since then, it has been managed via the wider contract the FCDO has with the London School of Economics (LSE) to deliver the overall IGC programme. For this reason, only the activity delivered up to end of March 2025 is covered in this annual review, as activity beyond that point will be covered in the annual review for the overall IGC programme.
The overall performance of this partner during the review period (until end March 2025) was good. The AGA was monitored at quarterly intervals for programme delivery and performance, financial management including analysing progress towards the milestones and the status of achievement of the programme outputs. Release of tranche payments was contingent on utilisation of previously disbursed funds to ensure no payments are made in advance of need.
Project 3: An Externally Financed Output (EFO) agreement with the World Bank to track public spending on health and education
In line with the standard terms of an EFO arrangement, the Bank will provide an end of programme report in March 2026. To ensure transparency and accountability, a technical team comprising Education, Health and Economic Advisers hold regular engagements with the World Bank team. Where appropriate, the team undertakes targeted engagements, such as observing the Public Expenditure Survey Tracking pilot, to identify potential challenges prior to full implementation.
Commercial
Within the programme year, there has been four amendments to the ASI contract. This included a cost amendment in January 2025 to increase the contract value from £2,000,000 to £2,785,000, and two no-cost extensions (first to end-June 2025, and subsequently to end-July 2025) were done to give the programme team time to subsequently undertake a planned cost extension once FY25/26 ODA allocations were confirmed, if the allocation amount meant this cost extension was affordable. Following confirmation of final FY25/26 ODA allocations a further contract amendment was signed to increase the contract from £2,785,000 to £3,385,000 and a time extension to 31st March 2026.
The programme continues to retain 20% of fees incurred each month, payable on satisfactory delivery of key performance indicators assessed by the programme team. Within the reporting period, all the programmes key performance indicators were met, these KPIs ensures strategic delivery through targeted intervention selection, timely implementation, partner coordination, skilled consultants, strong safeguarding, and best-practice programme management.
Asset Management
The programme maintains an asset register at the programme and project levels. As part of the annual asset review, in September the PRO conducted an asset verification check on assets previously stored at FCDO since March 2025. These assets were successfully transferred to ASI to ensure continuity of programme activities through March 2026.
All assets were accounted for and confirmed to be in good condition. However, minor adjustments are needed to improve the visibility of asset tag numbers. Additionally, recommendations were made to enhance the use of vehicle logbooks to ensure greater transparency in tracking vehicle movements and fuel usage.
FCDO is expected to carry out a spot check during the year to verify the existence and condition of these assets and to review the disposal plan prior to the programme’s closure.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
Throughout the year, the programme team maintained regular engagement with partners and key stakeholders. Quarterly progress and monthly reports were completed consistently, providing a structured overview of the implementation progress, ensuring transparency and accountability. As part of the annual review process, the team held consultations with implementing partners to self-assess their delivery capability.
Since the last Annual Review, a variety of monitoring activities have been carried out to support risk management and inform programming decisions. Notably, FCDO’s Programme Responsible Officer and the Safeguarding Lead conducted a field visit to assess delivery mechanisms and safeguarding practices during the revenue pilot work with the Electricity Distribution and Supply Authority (EDSA).
To assess programme effectiveness, feedback was gathered through surveys of training participants across three PFM components i.e. macro fiscal, payroll, and the National Revenue Authority. The results were shared with FCDO and used to refine programme design.
Evidence and Learning
Evidence generated through the ESER Programme’s inception report, political economy analysis, and intervention concept notes has been instrumental in guiding the programme’s development. This learning has helped identify key policy areas with strong potential for reform and has informed the strategic selection of interventions across both the public financial management and infrastructure investment workstreams.
The programme’s ability to pilot and adapt activities and delivery approaches has yielded valuable insights into what works within the local context. However, there is a recognised need to more systematically document and share these lessons to strengthen knowledge exchange. These insights will be critical for informing the sustainability and long-term impact of future programming.
In the area of property tax reform, a recent report by the International Growth Centre (IGC) provided robust evidence on the effectiveness of frugal enforcement strategies and the resulting increase in tax revenues from implemented property tax reforms in Sierra Leone.
Date of last narrative financial report	October 2025	Date of last audited annual statement