## Annual Review

Title: Climate, Energy and Water security for Central Asia
Programme Value £ (full life): £19.5m		Review date: 30/4/26
Programme Code: [AMP ID#] 400156	AMP start date: 30/01/2024	AMP end date: 31/12/2030

Summary of Programme Performance
Financial Year	2024/25	2025/26	2026/27	2027/28
Overall Output Score	A	A
Risk Rating	Moderate

DevTracker Link to Business Case:	Link
DevTracker Link to results framework:	Link

A. SUMMARY AND OVERVIEW

Description of programme

The Climate, Energy and Water Security for Central Asia (CEW-CA) programme aims to improve Central Asia’s resilience and sovereignty by delivering low carbon and climate resilient growth across the region. It will strengthen regional cooperation on water and energy whilst providing targeted and catalytic support to climate mitigation and adaptation interventions at national, sub-national and community levels.

Reflecting the FCDO 2030 shift to partnership, thinking like an investor, supporting systems change and sharing expertise, the programme’s approach is to support initiatives which can have a catalytic impact (e.g. by funding analysis to inform regional dialogue & policy reform, funding innovative pilot projects) and to be enabling (e.g. by building capacity and strengthening systems), which we expect will then lead to transformative results with investments by the government, through the IFIs or private sector (e.g. for renewable energy, interconnections, and irrigation modernisation). This approach ensures UK funding, alongside our diplomatic and technical expertise is targeted to areas where we can maximise impact and leverage the larger resources of the IFIs.

The programme has two primary components.

Component 1 supports regional cooperation to improve water and energy management and ensure it is resilient in a changing climate, with funding to the 4th phase of the World Bank’s multi-donor trust fund, Central Asia Water Energy Programme (CAWEP).
Component 2 supports national, sub-national and community climate outcomes through adaptation, resilience and mitigation measures that support the most vulnerable. It is delivered by GIZ and has three sub-components:
1. The Climate Innovation Facility (SGCIF) supports non-governmental organisations (NGOs), civil society groups (CSOs) and research institutions to tackle issues with the region’s climate, energy and water resources.
2. Contract Negotiation Support ‘CONNEX’ engages with governments at their request to provide advice in their negotiations with private investors on new climate, critical minerals and renewable energy projects.
3. The Dialogue on Bankable Projects (DBP) has been paused as outlined in Section B.

Three ancillary activities are also supported:
- “Six Inches of Soil” – Holding screenings of the documentary following three British farmers as they adopt regenerative agriculture. This is to amplify the conversation around this climate smart approach across the region.
- Oxford University – Updating the map of seismic faultlines in the Naryn basin (Kyrgyzstan) so the regionally strategic Kambarata 1 dam is designed with them in mind. (This activity supports CAWEP’s preparatory work.) Plymouth University is using the satellite data Oxford had secured to determine sediment flows into the future reservoir.
- Electricity Transition Playbook – Convening a workshop on decarbonising the electricity grid in Central Asia using the UK’s example, and aligning with the World Bank project, Regional Energy Market Integration and Trade (REMIT).

Summary supporting narrative for the overall score in this review

The programme is assessed as fully achieved ‘A’ for FY25/26, reflecting strong progress across outputs with achievement of most milestones and continued strategic relevance in a shifting geopolitical and climate landscape.

CEW‑CA made notable contributions to significant regional cooperation initiatives and investments through its support to a World Bank managed multi-donor trust fund, Central Asia Water and Energy Programme (CAWEP-4). Examples include the preparation of the World Bank funded Regional Electricity Market Interconnectivity and Trade programme (REMIT), debate around the reform of the International Fund for Saving the Aral Sea (IFAS), informing the evidence base for negotiations between Kazakhstan, Kyrgyzstan and Uzbekistan on the construction and operation of the Kambarata 1 hydropower plant in Kyrgyzstan, continued support for regional cooperation on the Rogun hydropower plant in Tajikistan, and preparatory studies to modernise the region’s irrigation schemes starting in Uzbekistan through the World Bank’s Irrigation Multi-Phase Approach. The five governments’ willingness to participate in regional discussions and agreements related to energy and shared water resources demonstrates significant political will to further strengthen regional economic cooperation and resilience.

UK’s support to CAWEP continues to enable greater understanding of the regional water and energy opportunities and challenges, with a range of analytical outputs such as technical modelling of water‑energy scenarios under a changing climate which help inform the region’s development of climate‑aligned infrastructure projects. A key indicator for CAWEP is the value of climate-smart water and energy investments by the World Bank that it informs, currently US$2.8 billion.

GIZ used its extensive network in the region to invite effective organisations to bid for the Small Grants and Climate Innovation Facility. Against, a shortened deadline rather than a full year, a process was created to directly award grants to five consortia comprising entities from at least two countries in the region. The proposals still needed to be high quality and were selected from a larger pool of invited participants. The process was completed at pace so the recipients still had six months to deliver the work, which they have done. In parallel, the GIZ team developed the process for a competitive pipeline in FY26/27.

CONNEX continued to raise awareness of its offer for contract negotiation support to governments in the region with the assistance of the British Embassies and the FCDO Regional Climate Team. The increased visibility enabled deeper technical conversations and resulted in four requests from the Tajik and Uzbek governments, two of which are now supported by experts.

The CEW-CA programme demonstrated strong performance across the four Outputs:
1. Investment - Exceeded expectations on project preparation and effectiveness of regional water‑energy investments.
2. Knowledge – Met expectations with substantial training delivery and evidence generation, with CAWEP producing multiple climate‑relevant analytical products and CONNEX providing targeted capacity‑building.
3. Dialogue – Exceeded the planned numbers of events, strengthening regional coordination and creating space for cross‑sector policy dialogue.
4. Coordination – Demonstrated improvement particularly with GIZ joining the CAWEP Steering Committee. However, more structured partner-level coordination is needed.

Major lessons and recommendations for the year ahead

Lessons learned:
- Regional cooperation is strengthened by expert technical groundwork to help inform political agreement and alignment. CAWEP’s success in fostering agreements such as for the Kambarata‑1 IGA negotiations and advancing REMIT programme effectiveness demonstrates the pivotal role of analytics, modelling, and neutral convening in driving cooperation.
- It takes time to build the demand for unfamiliar services. Though CONNEX expected uptake to be slow, the region presented its own challenges which reflected its wariness of external negotiation support, the wider geopolitics and greater reliance on state-to-state investments. This reaffirmed the need for sustained engagement and awareness-building.
- Programme agility is essential in dealing with complex administrative processes within FCDO and its partners. The introduction of a dual‑track SGCIF approach in response to GIZ procurement delays highlighted the value of flexible delivery models to mitigate slippage.
- Climate‑smart investment planning relies on ensuring credible evidence base and filling critical data gaps. Oxford University’s seismic mapping initiative shows the role technical evidence plays in reducing infrastructure risk and improving investment quality amidst climate change.
- Behavioural shifts toward regenerative agriculture require reframing the narrative and demonstrating its effectiveness. Screenings of “Six Inches of Soil” catalysed new conversations on soil health and private investment, demonstrating the influence of effective storytelling in shaping policy appetite.
- Once again in FY25/26, we were asked to absorb underspend in other parts of the organisation at short notice. And once again, it was only possible because of our partners willingness to be flexible. It perpetuates the tension between leaning on tried and trusted partners and building up local partners’ capacity.

These recommendations build on lessons from the previous two Annual Reviews:
- Continue to amplify CAWEP’s messages regarding regional cooperation over water and energy to support momentum and ensure regional mechanisms transition from planning to implementation.
- Continue structured outreach on CONNEX, using ambassadors, senior officials, and FCDO networks to encourage formal requests for support.
- Consolidate SGCIF delivery to achieve substantive results in FY26/27 with the existing budget.
- Strengthen programme‑wide coordination, including formalising partner-level meetings and aligning reporting and learning processes.
- Advance discussions on innovative climate finance and private sector engagement initiated in FY25/26.

And this is our response to last year’s Recommendations:

Recommendations from FY25/26 AR	Our actions
For the Programme Team to work with the implementing partners to articulate more clearly how CEW-CA supports the Foreign Secretary’s priorities on growth and climate in Central Asia.	This is an ongoing process as the Programme Team improves its communication of results vis-à-vis FCDO priorities in coordination with CEW-CA’s partners.
For the Programme Team to work with the EECAD MEL Adviser to refine the results framework, and re-visit whether an independent evaluation would be desirable at some point in CEW-CA’s life cycle.	The Programme Manager consulted the EECAD MEL Adviser and it was decided that.no major revisions were currently needed regarding the Results Framework. The Programme Team may still decide an independent evaluation is needed in the future.
Continue to use ‘Six Inches of Soil’ screenings to develop a conversation around regenerative agriculture in the region. And for the SRO to build a network of impact investors willing to invest in emerging markets.	This is an ongoing process. Screenings continue to be held; and the SRO is building a network of impact investors, and connecting them to opportunities in the region.
Engage with the CAWEP team and the co-donors (SECO and EU) on the planned workplan and Results Framework. To request, where appropriate given the confidential nature of some engagements, for CAWEP to share more information with the donors, and hold update sessions periodically for His Majesty’s Ambassadors (HMAs). And to connect CAWEP to other relevant partners e.g. Oxford University’s seismology work on the Naryn basin.	Done: / Gave coordinated feedback to the Bank team regarding the workplan and Results Framework. / The CAWEP team periodically met HMAs when in country to update them on issues and progress. / CAWEP was connected to Oxford University’s findings, and the ETP participants given the alignment with REMIT.
Given the volatile funding context, the CADP Climate Team will scope out strategic partnerships with other development partners/networks and provide recommendations by October 2025.	Other donors reducing budgets or pivoting their focus. Started looking at private climate finance.
For the SRO to review and ensure appropriate FCDO staffing levels by June 2025.	We achieved full FCDO staffing levels by February 2026 after having recruited a Climate Policy Officer in Tajikistan, a Climate and Infrastructure Policy Officer in Kyrgyzstan, and a Senior Regional Infrastructure Adviser.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

CEW-CA’s Theory of Change (TOC) connects its interventions with the programme’s Impact statement. Thus, CEW-CA’s expected Impact is a more resilient Central Asia which is moving towards a decarbonised development path and greater coherence and cooperation, with better governance, sustainable infrastructure investments, inclusive economic growth and community resilience. The expected Outcome is to enable inclusive, low carbon development by addressing emerging climate-related needs through regional cooperation while enhancing resilience at community, local and national levels – especially for the vulnerable and marginalised groups.

To deliver this, CEW-CA is structured around four interlinked Outputs:
1. Facilitation of good-quality, low carbon, climate smart water and energy investments.
2. Generation and dissemination of evidence and training for informed climate decision making for governments and civil society.
3. Creation of spaces for civil society and governments to engage on climate dialogue.
4. Enhanced coordination among CEW-CA partners to scale impact and avoid duplication.

The outcome and impact indicators remain as outlined in the original Business Case.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

### The programme is “On Track”.

Across all three Outcome indicators, the programme demonstrated strong performance:
1. Number of regional mechanisms involving two or more countries – Seven were delivered by CAWEP, GIZ’s innovation fund and Oxford University. (Milestone: 4)
2. Number of policy and investment decisions influenced by CEW-CA –CAWEP, CONNEX and Oxford University delivered six decisions. An innovation fundrecipient, the Global Green Growth Initiative (GGGI) may influence 3-5 decisions. (Milestone: 2)
3. Amount (US$) of public and private finance raised through CEW-CA partners for low carbon development – CAWEP raised US$408 million (including US$375 million in World Bank loans and US$33 million in public co-finance), and Tajikistan and Uzbekistan requested CONNEX’s advice on private investment deals worth US$3,375 million. GGGI’s figures will be reported in next year’s annual review to avoid a speculative figure now. (Milestones were not set.)

One sub-component was paused following the difficulty of getting officials to participate in CONNEX’s launch workshop in February 2025. The Dialogue on Bankable Projects relied on government officials engaging in the process and building a rapport with the private sector. After the experience of the CONNEX workshop, this seemed premature It was decided to pause the DBP and build the case for it at a slower pace. Screenings of Six Inches of Soil form part of that case.

Pausing the DBP also gave the programme headroom to absorb underspend from across the Central Asia Development Programme Team (CADP) and fund the ad hoc activities. This included the opportunity to have the UK’s National Energy System Operator (NESO) deliver its highly acclaimed ETP workshop on decarbonising electricity supply together with Loughborough University. The annual budget has more than halved as ODA spend moves towards of 0.3% of GDP. This has required adjustments to the funds and workplans for the innovation fundand CONNEX. CAWEP’s funding was frontloaded.

Actions Planned for the Year Ahead

To maintain progress, the following actions are planned:
- Involve His Majesty’s Ambassadors where needed to amplify to CAWEP’s strengthening of regional water and energy systems planning.
- Strengthen innovation fund implementation through direct and competitive awards.
- Consolidate demand for CONNEX by building senior officials’ understanding of it.
- Promote regenerative agriculture by holding more screenings of Six Inches of Soil.
- Enhance partner coordination to strengthen alignment across delivery channels.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

CEW-CA’s long term ambition to improve Central Asia’s climate resilience means tackling interwoven issues such as climate finance, energy and water resources management. The programme should continue as it is closely aligned with the Foreign Secretary’s Growth and Climate priorities, and supports strategically important regional cooperation over key resources for the economies and society. CAWEP and CONNEX are helping to unlock climate finance. Oxford University, SGCIF and regenerative farming are helping the governments to improve their adaptation responses to climate risks and impacts. CEW-CA also contributes to the UK’s International Climate Fund (ICF) £11.6 billion commitment as it is 100% ICF.
## C. DETAILED OUTPUT SCORING

Output Title	INVESTMENT: Good quality low carbon, climate smart water and energy investments are facilitated.
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 No. of formal letters from Central Asian governments requesting support on negotiations with private investors.	1	Exceeded: 4 / [CONNEX]
1.2 No. of feasibility studies informed by CEW-CA activities.	1	Exceeded: 3 / [CAWEP]

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 tracks CEW-CA’s contribution to facilitating climate-smart water and energy investments primarily through the CAWEP’s early-stage investment inputs such as feasibility studies and advisory support, and CONNEX’s negotiation support. CAWEP’s influence on regional investments combined with CONNEX’s expanding visibility justify an ‘A’.

Under Indicator 1.1, CONNEX’s persistent engagement with governments with the support of His Majesty’s Ambassadors (HMA) and the Regional Climate Team resulted in four formal requests. This aligns CONNEX’s global experience that it takes sustained engagement to build trust and demand for its services. The four requests were to support: (a) Tajikistan in its talks with a solar energy developer; (b) Tajikistan and Uzbekistan jointly on their hydropower projects on the Zarafshan river; (c) Uzbekistan vis-à-vis a critical minerals project; and (d) Uzbekistan regarding a water supply and sanitation project. Given Germany’s focus on critical minerals on the CONNEX Board, BMZ agreed to fund the critical minerals work. FCDO had enough funds to support the first two requests (solar power and hydropower) with a total capex of US$720 million. (The private finance amounts are captured in CEW-CA’s return under the UK’s International Climate Finance (ICF) commitments.)

Under Indicator 1.2, through CAWEP, the programme informed multiple aspects of Kambarata‑1’s preparatory work including the ‘Equity for Water’ options study; modelling of shared water–energy operations; analysis supporting the trilateral Inter‑Governmental Agreement between Kyrgyzstan, Kazakhstan, and Uzbekistan; and updated seismic mapping by Oxford University identifying critical fault‑line risks. These studies were essential in advancing the hydropower investment pipeline.

Key lessons identified:
- High‑quality feasibility studies accelerate government appetite for regional energy and water cooperation.
- Addressing data gaps, particularly seismic and hydrological is essential for derisking climate relevant infrastructure.
- For CONNEX, trust‑building and senior‑level engagement remain prerequisites to formal negotiation requests.

Recommendations for next year:
- Align the overall UK climate offer with Kambarata1 and REMIT preparatory activities.
- Sustain high‑level outreach on CONNEX through embassies and regional diplomacy.

Output Title	KNOWLEDGE: Evidence and training generated for governments and civil society to make more informed decisions regarding climate smart water and energy management.
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. No. of officials able to successfully negotiate and co-develop projects with private finance on climate investments.	40	Not achieve: 0 / [CONNEX 0, Dialogue n/a]
2.2. No. of training events held in person and online across the region for officials and civil society.	4	Exceeded: 51 / [CAWEP 10, Small Grants 9, Oxford 3, Six Inches 28, ETP 1]
2.3. No. of knowledge products generated for governments and civil society.	5	Exceeded: 18 / [CAWEP 16, Oxford 1, Plymouth 1]
2.4. Percentage of men and women directly benefitting from CEW-CA activities.	% of men / % of women	Didn’t set 2026 milestone. / c.4,500 (75% men, 25% women) / [CAWEP (994: 573 men, 421 women), GIZ (c.2,230), CONNEX (18: 16 men, 2 women), Oxford (28: 23 men, 5 women), Six Inches (c.1,200), ETP workshop (15: 12 men, 3 women)]

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 tracks CEW-CA’s building of knowledge and capacity. Given the range of evidence generated and trainings delivered, Output 2 merits an ‘A’.

Under Indicator 2.1, it was expected that DBP and CONNEX would facilitate the ability of officials to negotiate directly with private investors. With DBP’s pause, and CONNEX’s focus on explaining its offer, this indicator was not achieved.

Under Indicator 2.2, CAWEP, SGCIF, CONNEX and Oxford enhanced capacity in the region. CAWEP held ten training events. Through the SGCIF, GIZ and the grantees held nine training events for civil society. CONNEX worked with individual officials to build their understanding of negotiation frameworks, risks in private sector transactions, and examples from hydropower and renewable energy developers. Oxford University held a training workshop in Kazakhstan for the national institutions responsible for seismology research. There was significant demand for follow up which has included an inward visit to Oxford. NESO held the Electricity Transition Playbook (ETP) workshop. The Six Inches screenings held, raised awareness regarding regenerative agriculture amongst government officials, farmers and academics.

Under Indicator 2.3, CAWEP built the evidence underpinning regional coordination and national investments that included updating assessments of the National Hydromet Services; analysis of infrastructure using spatial data; and regional modelling of renewable energy, basin wide water and energy flows, and climate risk scenarios. Oxford and Plymouth Universities provided evidence on seismic activity and sediment loads for Kambarata 1.

Under Indicator 2.4, a failure to set a milestone for the gender representation was an oversight. But it is estimated that 4,500 people benefited directly from activities undertaken through CAWEP, SGCIF, CONNEX, Oxford University, the ETP workshop and screenings of Six Inches of Soil. Given the region’s ongoing gender imbalance, it is estimated that 75% would have been men, and 25% would have been women overall.

Key lesson identified:
Climate smart decision making requires high quality models that integrate hydrology, energy, and spatial data. And there is strong demand from governments.

Recommendations for next year:
- Update logframe and finalise milestones.
- Track the number and gender of participants.
- Strengthen connections between the region’s governments, civil society, UK government and UK Plc.

Output Title	DIALOGUE: Space created for civil society and also governments to engage on climate related issues.
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1. No. of workshops and dialogue events held for and by governments, civil society and the private sector.	5	Exceeded: 10 / [CAWEP]
3.2. Percentage of stakeholders reporting improved understanding and engagement between the public and private sectors regarding climate investments.	30%	Not measured / [CONNEX, Dialogue n/a]

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 focuses on creating space for multi-stakeholder dialogue on climate issues. The World Bank reported a greater willingness amongst the region’s governments to cooperate that is not visible in the counting of meetings and workshops.

Under Indicator 3.1, CAWEP provided a structured platform for political and technical engagement focused on shared infrastructure, climate risk and regional cooperation:
- High-Level Ministerial Dialogue on Kambarata1 Hydropower – CAWEP supported a sequenced series of ministerial and technical dialogues between Kazakhstan, Kyrgyzstan and Uzbekistan including trilateral roundtables in Dubai (May 2025) and Brussels (September 2025). Discussions focused on project preparation timelines, feasibility and environmental and social studies, financing options, and joint institutional arrangements, reinforcing political commitment to Kambarata1 as a flagship regional waterenergy investment.
- IFAS reform and transboundary water/energy governance – CAWEP facilitated renewed regional dialogue to enhance IFAS’ relevance under climate change. Meetings in Dushanbe and the regional forums brought together water and energy authorities to discuss governance reforms, expanded mandate, and stronger integration of water and energy considerations.
- The regional water–energy nexus – CAWEP supported regional climate dialogue through major conferences and forums including the Central Asia Climate Change Conference (CACCC‑2025) in Ashgabat in May, which addressed water–energy nexus solutions and climate finance. Additional regional forums and foresight exercises promoted long term climate, water and energy risks, and the need for cooperative planning.
- Regional electricity markets – CAWEP supported ongoing technical and institutional dialogue on regional electricity market development among energy ministries, system operators, and international financial institutions. These discussions directly informed preparation of the REMIT initiative, linking policy reform with infrastructure investment to enable cross‑border electricity trade and renewable energy integration.

Key lessons identified:
- Regional meetings build shared understanding and identify common priorities.
- Regular dialogue is required to maintain political appetite for cooperation.

Recommendations for next year:
For FCDO to echo CAWEP in its messaging on regional cooperation.
Output Title	COORDINATION: CEW-CA partners and sub-partners foster coordination to amplify the region's climate resilience.
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1. No. of internal meetings between CEW-CA partners (World Bank, GIZ/CONNEX, grant recipients).	4	Exceeded: 20+
4.2. No. of events, training workshops, dialogues and knowledge products that involve more than one CEW-CA partner.	2	Exceeded: 4

Briefly describe the output’s activities and provide supporting narrative for the score.

The FCDO Regional Climate Team (RCT), which is spread out across all five countries and the UK, uses CEW-CA as a springboard to connect and coordinate across the board including with other donors, the private sector and wider civil society in the region and the UK. Against this backdrop, Output 4 aims to breakdown any internal silos within the programme and encourage the implementing partners and their downstream delivery partners to talk to each other. The expectation is that this will have a bigger impact on the region’s climate resilience.

Under Indicator 4.1:
- There has been regular coordination between FCDO, GIZ and CONNEX. Weekly meetings were held while both MOUs were being set up and went through their Inception Phase. With implementation, these meetings have now become fortnightly. This has proven to be useful in dealing with administrative purposes such as contract amendments as FCDO budgets change.
- FCDO participates in steering committee meetings for CAWEP and CONNEX with other donors. With the latter, it ensures that other parts of FCDO are aware of requests coming from their host governments.
- GIZ participated in CAWEP’s Steering Committee in November 2025 with a view to strengthening alignment across CEW-CA’s analytical and grant‑making activities.
- The SGCIF was designed with coordination at its heart by ensuring only activities happening in two or more countries with local partners were eligible. GIZ organised three events for the successful grantees which spurred mutual interest in working across the consortia.
- CONNEX met the World Bank to discuss whether it could augment the Institutional Transition Consultant’s work on Kambarata 1. It was deemed unnecessary.
- CAWEP periodically meets His Majesty’s Ambassadors (HMAs) and the RCT to give them an update on progress.

Under Indicator 4.2:
- Oxford University’s research results were given to the World Bank to inform the design of Kambarata 1.
- FCDO has convened an Informal Research Group (IRG) of academics based at UK universities who are researching climate issues in Central Asia. The purpose is to connect FCDO and academics so UK policy can draw on cutting edge research on the region. It is housed by Reading University and meets periodically. After the last meeting, a professor in riverine sediment management from Plymouth University used the satellite data Oxford University had acquired to predict sediment flow into Kambarata 1’s reservoir.
- The Electricity Transition Playbook’s message of decarbonising the electricity network links strongly with the World Bank’s REMIT programme. And Switzerland is pivoting towards focusing more on energy. Therefore, the Bank and Switzerland were invited to meet the national delegations when the ETP was held in Tashkent in February 2026.
- Valor Carbon, which invests in carbon credit projects, was introduced to the NGOs, Ecojer in Kazakhstan and Sharikon Baroi Rushd (SBR) in Tajikistan. Valor is supporting them to develop a methodology to trade carbon credits as commercial farms adopt regenerative agricultural practices.

The RCT continues to connect people outside of the programme. For example, Valor Carbon was introduced to an Uzbek commercial hemp farmer who is experimenting with regenerative practices. Private investors from the USA, and UK universities were introduced to commercial opportunities in Uzbekistan.

Key lessons identified:
- It’s good to talk – whether through shared governance mechanisms such as steering committees, or as opportunities arise in a more ad hoc fashion.
- Persistent challenges include differing internal processes, reporting systems, and timelines across partners.

Recommendations for next year:
Given the reduced budgets and draw on partners’ time, to make tracking coordination as light touch as possible.

## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

CEW‑CA’s value for money (VfM) performance in FY25/26 reflects the programme’s ongoing emphasis on generating high‑quality evidence, delivering catalytic technical assistance, leveraging co‑financing, and influencing major regional investments. The cost drivers listed below align closely with CEW‑CA’s focus on catalytic interventions that provide high‑quality evidence, reduce risk for future climate investments, and strengthen institutional capacity.

The programme’s principal cost drivers continue to relate to:
- Specialist technical assistance delivered under CAWEP including hydrological modelling, economic analysis, feasibility studies, advisory services, climate risk diagnostics and facilitation of regional policy dialogue.
- Grant making and downstream partner mobilisation under the SGCIF including inception design, due diligence, partner coordination and monitoring frameworks.
- High‑value expert negotiation support delivered through CONNEX which mobilises international specialists to advise governments on public–private transactions. It also uses the International Senior Lawyers Project‘s (ISLP) pro bono network.
- Data procurement and technical analysis for seismic risk mapping undertaken by Oxford University to de‑risk major hydropower investments.

Assessment of whether the programme continues to represent value for money

CEW-CA continues to deliver value for money for now across all categories. The programme remains well‑aligned to the UK and programmatic objectives, excels at leveraging larger investments, and continues to deliver high‑quality analytics and policy influence at relatively modest cost. Key VfM strengths include leverage and influence; being flexible with funding for high impact opportunities; regional convening power; and cost‑effective delivery through trusted partners. Given the programme’s demonstrable contribution to climate resilience, its significant policy influence, and its catalytic role in unlocking forthcoming climate finance, CEW‑CA continues to justify investment from both a VfM and strategic standpoint.

Economy — CAWEP’s trust fund structure allows FCDO to procure specialist modelling, analytical reports, and hydromet assessments at competitively benchmarked multilateral rates, consistent with VfM expectations. Plymouth University is using the satellite data secured by Oxford University to extract more information; and Oxford has used its own budget to co-fund some seismic research activities.

Efficiency — CAWEP rapidly mobilised technical teams, enabling early delivery of studies that went beyond planned milestones (such as advanced Kambarata‑1 modelling and REMIT design). This reflects efficient use of funding and the World Bank’s established regional presence. GIZ’s flexibility resulted in a dual‑track SGCIF grant‑making approach which reduced delays inherited from FY24/25 and enabled both immediate delivery and longer‑term pipeline development. And weekly coordination between FCDO, GIZ and CONNEX improved delivery oversight and reduced transaction costs by streamlining engagement.

Effectiveness — The programme influenced major regional energy and water policy decisions, validating the Business Case expectation that CEW‑CA would leverage technical analysis to shape climate‑smart investments. For example, CAWEP’s analytical work underpinned four regional mechanisms (REMIT, IFAS reform discussions, Irrigation MPA, Kambarata‑1 IGA) directly contributing to Outcome Indicators 1 and 2. And CONNEX improved negotiation literacy through in‑person sessions with all five governments, reinforcing its longer‑term effectiveness resulting in four requests for support.

Equity — Gender disaggregated monitoring continued across training and knowledge events, with CAWEP achieving 40% women’s participation in hydromet and climate data capacity building. SGCIF’s design explicitly targets NGOs, civil society, and community level organisations, with criteria emphasising inclusion of vulnerable and marginalised groups.

E: RISK

Overview of risk management

CEW‑CA’s overall risk rating remains moderate despite the complex geopolitical environment, a reliance on multiple implementation partners, and the sensitivities of transboundary water–energy cooperation in Central Asia. Risks are actively monitored through quarterly updates to the internal risk register, regular partner engagement, and due diligence processes, in line with FCDO requirements.

The programme manages risks across the following categories:
- Strategic context – Regional geopolitical uncertainty and variable political commitment continue to affect progress on regional mechanisms including IFAS reforms and the development of REMIT. These risks are mitigated through CAWEP‑led evidence‑based dialogue, clear articulation of economic and climate benefits and sustained diplomatic engagement.
- Programme delivery – Delivery risks arise from differing partner systems, timelines, and internal procedures particularly in downstream grant mobilisation. Mitigation measures include fortnightly coordination with GIZ and CONNEX, participation in CAWEP and CONNEX steering committees, and FCDO due diligence.
- People – As a regional programme operating across multiple countries, there is a continued risk of stretched oversight and coordination. This is mitigated through clear delegation of roles, regular internal coordination within the FCDO Regional Climate Team, and continuity planning.
- Safeguarding – The programme team is committed to reducing risks of fraud and sexual exploitation, abuse, and harassment (SEAH) but acknowledges that it remains a key risk due to multi‑country delivery and engagement with downstream partners. CEW‑CA applies FCDO’s zero‑tolerance approach, requiring compliance with safeguarding standards, partner due diligence, and robust reporting systems.
- Financial and fiduciary – Financial risks relate to misuse of funds and variable reporting capacity among partners. These are mitigated through World Bank trust fund fiduciary systems, annual financial and narrative reporting, advance due diligence on GIZ and CONNEX, and regular spend forecasting by the SRO and PRO.

Overall, the mitigation measures have kept residual risks broadly stable. While delivery, safeguarding, and strategic context risks persist, CEW‑CA’s structured approach to risk management ensures risks remain within acceptable levels for a regional climate programme of this scale.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery

The CEW-CA Business Case was approved in January 2024 with implementation starting in February 2024. The FCDO programme team is now complete and comprises the Regional Climate Adviser (Senior Responsible Owner, SRO) based in the UK, Senior Regional Infrastructure Adviser (based in UK), the Regional Programme Manager (Programme Responsible Owner, PRO) in Kyrgyzstan who is supported by Climate Policy Managers in Tajikistan, Uzbekistan and Kyrgyzstan. They are supported by the rest of the regional Climate Team based in Kazakhstan and Turkmenistan, and the two new recruits, the Senior Regional Infrastructure Adviser based in the UK, and the Climate and Infrastructure Policy Manager based in Kyrgyzstan. The programme team regularly meets the implementing partners to track progress.

CEW-CA has several implementing partners – the World Bank, GIZ, Oxford and Plymouth Universities, the UK’s National Energy Systems Operator (NESO). As noted in last year’s Annual Review, the World Bank submits an annual report and there are periodic check-ins with the CAWEP team. Two MOUs were signed in November 2024 with GIZ for SGCIF and CONNEX and there are fortnightly check-ins. FCDO have also updated its Accountable Grant with Oxford University this financial year to continue the earthquake risk analysis for Kambarata 1, and there are regular updates and it submitted a report. Plymouth University was subcontracted through Oxford as a one-off, and it has submitted its report. Using another FCDO programme, Climate Compatible Growth (CCG), NESO was hired to deliver one regional workshop which was delivered in conjunction with Loughborough University.

Financial and commercial performance

Overall, CEW‑CA’s programme management remained strong and adaptive. Delivery partners demonstrated solid performance, commercial relationships functioned effectively, and financial management provided high levels of assurance. Regular coordination, strengthened oversight, and maturing delivery systems have positioned the programme well for acceleration in FY26/27.

CEW‑CA maintained sound financial performance in FY25/26 through close coordination between the SRO, PRO, and implementing partners. Key financial management practices included:
- Quarterly spend forecasting and monitoring across delivery partners.
- Annual reporting from the World Bank, including audited financial statements and aggregation of programme‑level expenditures.
- Annual advance payments to GIZ, linked to receipt of workplans and financial projections.
- Tranche‑based disbursements to Oxford University, released upon satisfactory reporting and progress updates.

Amendments to the World Bank Administrative Agreement allowed CAWEP to accelerate delivery of critical climate analyses, feasibility studies, and regionally coordinated interventions. FCDO monitoring ensured that no funds were disbursed in advance of need and that spending aligned strictly with approved activities.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation. Monitoring and evaluation (MEL) systems continued to strengthen during FY25/26, building on the mechanisms established during CEW‑CA’s inception and first full delivery year. The FCDO programme team worked closely with the EECAD MEL Adviser and implementing partners to track progress against the logical framework, review delivery challenges, and ensure that monitoring remained proportionate, useful, and aligned to FCDO standards.

Regular internal engagements—including weekly meetings between FCDO, GIZ, and CONNEX—supported continuous monitoring of milestones, risks, VfM practices, and delivery performance. The RCT’s participation in the CONNEX Governing Board further enabled direct oversight of decisions affecting negotiation‑support delivery and multi‑donor platform shaping. The programme team also maintained ongoing contact with the World Bank, receiving updates through CAWEP Steering Committee meetings, in‑person and virtual consultations, annual reporting, and technical briefings. These provided a comprehensive view of technical progress, evidence outputs, and linkages to regional cooperation processes.

Evidence. The Annual Review draws on multiple evidence sources, providing a high level of assurance regarding the programme’s performance such as CAWEP’s self‑assessment report, annual report, and detailed results framework, providing high‑quality technical and performance data; and GIZ and CONNEX progress updates, including financial reporting, inception deliverables, downstream partner updates, and narrative assessments aligned with FCDO requirement. Collectively, the evidence base provides robust insight into CEW‑CA’s influence on regional policy, capacity building, and investment planning.

Learning. Learning continued to be a central component of CEW‑CA’s adaptive management approach. The Results Framework includes an explicit output on coordination and learning, ensuring that lessons and best practices are captured, shared among partners, and used to inform adaptation. The programme team used quarterly conversations with partners to discuss what worked, what needed improvement, and how learning should influence future design and delivery.

Learning will continue to inform programme adjustments, including revising indicators, improving gender measurement, and refining coordination across partners. The key areas of learning identified in FY25/26 include:
- Regional cooperation requires both technical and political traction—with CAWEP’s analytics enabling progress on REMIT, IFAS reform, and Kambarata 1, demonstrating the importance of evidence in unlocking political agreements.
- Time and trust are essential for government uptake of negotiation support—a lesson reaffirmed through CONNEX’s gradual engagement trajectory.
- Dual‑track grant‑making can mitigate administrative delays, as demonstrated by GIZ’s revised approach to SGCIF.
- Regenerative agriculture requires narrative framing and demonstration, reflected in the early impact of Six Inches of Soil screenings.

Date of last narrative financial report	World Bank – 27 Feb 2026 / GIZ – 22 Oct 2026 / CONNEX – 27 Apr 2026	Date of last audited annual statement	World Bank – September 2025 / GIZ / CONNEX – expected Sept 2026