## Annual Review Template

Title: Annual assessed contribution to the United Nations Educational, Scientific, and Cultural Organisation, 2024- 2026
Programme Value £ (full life): £22,894,809.35		Review date: August 2025
Programme Code: 400169	AMP start date: 05/06/2024	AMP end date: 31/12/2026

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	Annual assessed contribution to the United Nations Educational, Scientific, and Cultural Organisation, 2024- 2026 Business Case
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The Foreign, Commonwealth & Development Office (FCDO) is the lead department for the UK’s relationship with the United Nations Educational, Scientific and Cultural Organisation (UNESCO) and is responsible for paying the UK’s annual assessed contribution to UNESCO. The annual assessed contribution is mandatory and pays for the UK’s membership to this multilateral organisation. UNESCO member states’ assessed contributions are based on the UN scale of assessments adjusted to take into account differences in the membership between the UN and UNESCO.

UNESCO is a specialised agency of the UN with 194 member states. As an intergovernmental organisation it provides a normative forum for the negotiation of global agreements, and a facility for policy exchange and capacity building across its mandate covering education, sciences, culture, and information and communication. The Organisation is a key partner for the UK on issues including: the delivery of global education (SDG4); protection of cultural heritage; ensuring the protection of journalists and a free media; the promotion of open science; ethics of AI and neurotech; oceans; and climate change. UNESCO is also responsible for World Heritage Sites, biosphere reserves, global geoparks UNESCO University Chairs, Creative Cities and other similar accreditations. UNESCO is also the holder of Conventions of which the UK is a signatory – for example the Convention for the Safeguarding of the Intangible Cultural Heritage, the Convention for the, Protection of Cultural Property in the event of Armed Conflict and the Internation Convention against Doping in Sport.

Summary supporting narrative for the overall score in this review

This programme has scored an A consistent with its score since 2018. UNESCO's strengths continue to be its central position in advancing Sustainable Development Goal 4 – education for all, and its normative leadership across its mandate. Its mandate is broad which means UNESCO has to work hard to focus on impactful and strategic programming. The 2025 MOPAN assessment showed that UNESCO has strengths in innovation and agility and providing high-quality policy advice to governments. MOPAN also identified that UNESCO made a number of improvements but still had further to go on strengthening its results-based management systems, and tracking poor performance, as well as risk management systems and ensuring the field network is fit for purpose.

The UN Secretary-General launched UN80 this year, and UNESCO has been engaging with other Specialised Agencies through their cluster, on identifying efficiencies. UNESCO has also launched a consultation for Member States on UN80 engagement, and so there will likely be changes as a result of this process. Alongside UN80, the US announced on 22nd July 2025 of its withdrawal from UNESCO on 31 December 2026, the organisation is having to make budgetary cuts and reconsider its next four-year budget. This may have implications for the assessed contribution.

UNESCO’s current Medium-Term Strategy has introduced significant measures to better leverage the organisation’s expertise to promote a more integrated and less siloed approach to addressing global challenges. In November 2025 the next four-year programme and budget will likely be adopted, and the draft budget already shows outputs with greater integration across the mandate. However, this may be delayed given the US announcement.

Major lessons and recommendations for the year ahead

The key recommendations for this programme for the year ahead:

- Pursue a narrower, more targeted approach to realising SDG4, focussing minds through international events and communications on making meaningful, measurable progress to tackle the global learning crisis.
- Ensure that gender continues to be a global priority, particularly in the education sector.
- Support the Institute of Statistics in improving its data collection, monitoring and analysis.
- UNESCO continues to fund, and find alternative sources of voluntary contributions, to ensure effective programming continues for all outputs.
- There is sufficient funding for the IOC to lead international efforts in ocean science, climate resilience and marine biodiversity protection.
- UNESCO to engage with the MOPAN findings and to make improvements in line with their areas for improvement. In particular, strengthening its results-based management systems, tracking poor performance, as well as improving its risk management systems and ensuring the field network is fit for purpose.
- UNESCO closely engages with the UN80 initiatives where relevant.
- UNESCO carefully considers how to reduce programming to meet new budgetary challenges.

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

A theory of change is not applicable for this programme.

UK funding provided through this programme is an international subscription, an assessed contribution which is an obligation of membership. The funding is provided in accordance with the pre-agreed schedules and spent as per the budget agreed by the governing bodies.

The business case for this assessed contribution was the first full business case as predecessor programmes were business case exempt under previous programme management rules. Predecessor programmes have scored an ‘A’ for programme performance in each DfID/FCDO annual review since 2018.

Performance and progress of UNESCO as an Organisation and its programmes are assessed and monitored on a continuous basis.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to contribute to the expected outcomes and impact. It scored an A in four of the five outputs reviewed, and a B in one of the five outputs. The overall risk of the programme remains at moderate, reflecting ongoing organisational reform and the recent positive MOPAN assessment.

The four outputs that scored an A are reflective of UNESCO’s own rating of its outcomes related to their strategic objectives listed in their Medium-Term Strategy 2022-2029. The four strategic objectives correlate to our outputs one to four. The lowest output, scoring a B is related to UNESCO's internal organisational efforts. This output scores lower for a number of reasons. Firstly, UNESCO made a budgetary overcommitment which came to light in July 2024 which was due to poor internal processes and controls. Secondly, MOPAN, in its latest 2025 assessment recommended a number of improvements regarding internal processes. Finally in the broader context of UN80, a global tightening financial landscape, and US withdrawal, UNESCO needs to focus on reducing programming and accelerate its reform efforts.

UNESCO will likely adopt a four-year programme and budget in November 2025. Following this, the FCDO will consider whether the outputs and indicators in the delivery framework remain appropriate.

There are external factors which may impact on UNESCO’s ability to deliver over the coming year. Firstly budgetary constraints from both US withdrawal but also reductions in voluntary contributions from donors who are making reductions to ODA, will likely lead to programme cuts and cost-cutting across the organisation. Secondly, the election of a new Director General might change the direction of the organisation which may or may not lead to an increased focus on internal reform. Thirdly, UN80 and the changes to the UN system may impact UNESCO – there may be greater efficiencies with shared functions across agencies, but also may distract UNESCO from core reforms.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The UK pays a mandatory annual assessed contribution to UNESCO, which is a legal obligation under international law. The UK is obligated to pay this as a condition of our membership to the Organisation.  Therefore, as long as the UK remains a member of UNESCO this programme should continue.

## C. DETAILED OUTPUT SCORING

Output Title	Ensure quality equitable and inclusive education and promote lifelong learning opportunities for all, in order, inter alia, to reduce inequalities and promote learning and creative societies, particularly in the digital era.
Output number:		1	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Indicator 1: Education policy and finance decisions to achieve SDG 4 are informed by improved coordination, data and monitoring, knowledge and innovative partnerships / Indicator 2: Global leadership in the monitoring of the SDG 4-Education 2030 agenda enhanced through the development of internationally agreed norms and standards and the collection, production and distribution of timely and high-quality data / Indicator 3: Education systems equipped to promote inclusion, address marginalization and advance rights, including in crisis-affected and post-disaster contexts / Indicator 4: Gender-transformative education systems empower learners, ensure safe learning environments and address the educational barriers, particularly for girls and women, exacerbated by the learning crisis / Indicator 5: Learners equipped with relevant skills to meet individual, labour market and societal demands through literacy, technical and vocational education and training (TVET), science, technology, engineering and mathematics (STEM) and higher education / Indicator 6: Teachers trained and supported to improve learning outcomes and address the changes brought forth by the digital and AI transformation and the COVID-19 crisis	Decisions and content of Executive Board papers in October 2024 and April 2025 show progress across the indicators.	On indicator 1: UNESCO has advanced SDG 4 through global coordination efforts, improving education data systems, promoting inclusive and gender-responsive policies, and supporting lifelong learning and digital literacy through youth engagement, regional initiatives, and strategic partnership. This is set out in Executive Board paper 221 EX/6. UNESCO organised major events like the Global Education Meeting. In 2024, UNESCO provided technical support to 187 countries across the nine outputs of the Education Sector’s programme, including 54 countries in Africa and 25 countries in fragile or conflict-affect contexts. / Lack of funding continues to undermine progress towards SDG 4. Four out of ten countries have not reached recommended targets of investing at least 4% of GDP and 15% of public spending in education – the two agreed benchmarks established by the Incheon Declaration. / On indicator 2, there has been a recent leadership change at the UNESCO Institute for Statistics, which may lead to changes in its operations. The institute has improved data quality through stronger partnerships, launched the SDG4 Scorecard Dashboard. These efforts have made education data more actionable and aligned with global goals. However, there continues to be large gaps in data availability, and the increased scope and large number of SDG 4 indicators can be challenging for Member States, both in terms of coverage and efficiency of data collection methods. For example, SDG4 indicators are still only available for 62% of the population and 58% of the countries. UNESCO Institute of Statistics convened the first ever International Conference on Education Data and Statistics. / Regarding, indicators 3 and 4, UNESCO estimates that it empowered some 27 million learners with access to quality and gender equitable education. UNESCO strengthened education systems in 12 crisis-affected countries, responding to challenges such as natural disasters, civil unrest, forced displacement, and health emergencies. / For indicator 5, through policy development, capacity-building, and partnerships, UNESCO helped align education systems with labor market needs, directly supporting over 1.8 million learners, including 1.2 million through the Global Skills Academy. / On indicator 6, UNESCO trained 538,000 teachers in 2024. The Global Report on Teachers spotlighted the need for 44 million teachers by 2030 to achieve universal primary and secondary education. UNESCO held the Policy Dialogue Forum (26-28 February, Johannesburg), we advanced solutions to address teacher shortages, elevate the profession, and explore revisions to key recommendations to reflect modern realities.

Briefly describe the output’s activities and provide supporting narrative for the score.

The UK as part of the Executive Board agreed with UNESCO’s assessment that its own indicators are on track, which is why this output is assessed as an A.

However, overall progress on SDG4, of which UNESCO is the custodian, is off track. According to the UN’s SDG 2025 Progress Report: “Enrolment and completion rates have improved since 2015, with girls outperforming boys in most regions, progress is slowing. Meanwhile, 272 million children and youth remained out of school in 2023.” There remain problems with the data collection and monitoring of SDG4, which is the responsibility of UNESCO’s Institute of Statistics. UNESCO has identified a funding gap on education but its leadership of the High Level Steering Committee and other convening moments, has not led to a marked change in the importance of education policies in national strategies.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first Annual Review for this business case.

The recommendation is for UNESCO to ensure that resources match the ambition of UNESCO future programmes and mandate without being spread too thinly. This aligns with a recommendation from the MOPAN assessment.
Three recommendations:

- Pursue a narrower, more targeted approach to realising SDG4, focussing minds through international events and communications on making meaningful, measurable progress to tackle the global learning crisis.
- Ensure that gender continues to be a global priority, particularly in the education sector.
- Support the Institute of Statistics in improving its data collection, monitoring and analysis.
- UNESCO continues to fund, and find alternative sources of voluntary contributions, to ensure effective programming continues for this output.

Output Title	Work towards sustainable societies and protecting the environment through the promotion of science, technology, innovation and the natural heritage.
Output number:		2		Output Score:		A
Impact weighting (%):		20		Weighting revised since last AR?		N/A

Indicator(s)			Milestone(s) for this review		Progress
Indicator 1: Inclusive knowledge and capacities of Member States strengthened to advance and apply science for sustainable management of natural resources, ecosystem and biodiversity conservation and restoration, and disaster risk resilience. / Indicator 2: Water science, innovation, education, management, cooperation and governance bolstered for a water secure world in a changing environment. / Indicator 3: Member States critically supported in strengthening their capacity to conduct marine scientific research, generate knowledge, and develop and implement science-based tools, services, and policies in order to reverse the decline in ocean health and accelerate the transition towards sustainable management of ocean-related risks and opportunities. / Indicator 4: Member States capacities strengthened to improve Science, Technology and Innovation policies, access to scientific and technological advancements and enhance knowledge sharing, including through Open Science.			Decisions and content of Executive Board papers in October 2024 and April 2025 show progress across the indicators.		On indicator 1, UNESCO Biosphere Reserves span 759 sites across 136 countries, and received three times more candidatures for new Biosphere Reserves in 2025, reflecting the interest from Member States. The Global Geopark network expanded to 229 sites in 2025 (including a new UK site – Arran). However, the rapid growth of biosphere reserves and UNESCO Global Geoparks has exceeded available financial and human resources, placing strain on the Secretariat. / Regarding indicator 2, UNESCO reinforced global water science efforts across 119 Member States through early warning systems, groundwater monitoring, and transboundary governance, while training around 69,000 individuals and publishing key reports on water risk management. It also advanced environmental education, science, technology, and innovation by integrating climate action into curricula, promoting women in science, and expanding digital tools for open data sharing. / UNESCO has strengthened national capacity through its Intergovernmental Hydrological Programme (IHP) by providing strategic policy support and specialised training in water management and sustainable use of ocean and coastal resources. Through collaborative initiatives, the IHP has helped countries develop biosphere reserves and geoparks, integrating science, education, and conservation to promote resilient ecosystems. UK experts are closely involved in IHP. / For indicator 3, through its Intergovernmental Oceanographic Commission (IOC), UNESCO supported research and international collaboration under the UN Ocean Decade, training over 268,000 people, reaching 34,000 students with ocean literacy programmes, advancing marine spatial planning, and strengthening tsunami early warning systems, with 99 communities achieving Tsunami Ready status. UK experts are closely invovled in IOC. / On indicator 4, UNESCO held a Science Diplomacy Conference in 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

The UK as part of the Executive Board agreed with UNESCO’s assessment that its own indicators are on track, which is why this output is assessed as an A. UK’s experts have been closely involved in the IOC and IHP programmes. There is concern that budget cuts might impact the IOC relatively more than other areas. Its important that IOC’s autonomy is also protected within UNESCO governance.

UNESCO needs to ensure that it continues to focus its scarce resource on these areas and continue to adequately fund the IOC.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first Annual Review for this business case.

There are two recommendations:

- UNESCO continues to fund, and find alternative sources of voluntary contributions, to ensure effective programming continues for this output.
- There is sufficient funding for the IOC to lead international efforts in ocean science, climate resilience and marine biodiversity protection.

Output Title	Build inclusive, just and peaceful societies by promoting freedom of expression, cultural diversity, education for global citizenship and protecting the heritage.
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Indicator 1: Member States' capacities strengthened to identify, protect and manage tangible heritage / Indicator 2: Member States' capacities strengthened for better preparedness, mitigation and response to emergencies affecting culture, including in situations of armed conflict and disaster / Indicator 3: Member States' and communities' capacities strengthened to identify, safeguard and promote living heritage / Indicator 4: Member States have strengthened capacities and raised awareness to enhance norms and policies related to freedom of expression, press freedom, safety of journalists, including women journalists, and the right to access information, online and offline / Indicator 5: Member States and media institutions enabled to strengthen media development and media pluralism, including through the International Programme for the Development of Communication (IPDC)	Decisions and content of Executive Board papers in October 2024 and April 2025 show progress across the indicators.	On Indicator 1: the World Heritage List grew to 1,223 properties, including new additions and removal from the List of World Heritage in Danger. 196 States ratified the 1972 World Heritage Convention. / Regarding indicator 2 UNESCO supported museums, culture in emergencies, and the safeguarding of living heritage by assisting over 50 cultural institutions in crisis, advancing digital documentation of endangered heritage, and integrating intangible heritage into education across more than 100 countries. / For indicator 3, there were 37 new additions to the Representative List of the Intangible Cultural Heritage of Humanity. The UK made progress in launching its own register of living heritage. / On indicator 4 UNESCO strengthened global advocacy for freedom of expression, media pluralism, and journalist safety (training over 400 media professionals in conflict zones). / Regarding indicator 5, UNESCO supported 28 Member States to enhance norms and policies for accessing information, online and offline.

Briefly describe the output’s activities and provide supporting narrative for the score.

The UK as part of the Executive Board agreed with UNESCO’s assessment that its own indicators are on track, which is why this output is assessed as an A.

The UK has provided additional programmatic funding to support UNESCO with its work to protect heritage in crisis-affected countries as well as its work to promote media freedom, through the Media Defence Fund.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first Annual Review for this business case.

One recommendation:
UNESCO continues to fund, and find alternative sources of voluntary contributions, to ensure effective programming continues for this output.

Output Title	Foster a technological environment in the service of humankind through the development and dissemination of knowledge and skills and the development of ethical standards.
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Indicator 1: Member States have strengthened institutional and human capacities to integrate media and information literacy (MIL) in policies and strategies, and to bridge the digital and knowledge divides, through the development of digital skills and competencies, particularly in the small island developing States (SIDS), and among women and girls and different marginalized and vulnerable groups / Indicator 2: Member States’ capacities and policies strengthened to benefit from AI, gene-editing, neuro-technologies, quantum technologies and other frontier technologies, and to address the associated risks, including inequalities and discrimination, in line with international ethical standards, recommendations and frameworks / Indicator 3: Institutional capacities strengthened for harnessing the benefits of artificial intelligence in all areas of UNESCO’s competence, while addressing the ethical challenges and ensuring the use of digital technologies to promote, protect and fulfil human rights and fundamental freedoms	Decisions and content of Executive Board papers in October 2024 and April 2025 show progress across the indicators.	On indicator 1, Global Media and Information Literacy (MIL) Week reached unprecedented levels in 2024, with nearly 300 events across more than 80 countries. The launch of an online MIL course for content creators attracted 10,000 registrants, further amplifying the reach of MIL initiatives. There is significant demand which may outstrip resources. / Regarding indicator 2, UNESCO is currently developing the first global recommendation on the Ethics of Neurotechnology, set for adoption in November 2025 at General Conference. The draft recommendation aims to establish shared values and principles, identify ethical challenges and propose concrete policy actions for ethical development and use. / On indicator 3, UNESCO continued its leadership in AI policy development by supporting countries in creating responsible and effective AI strategies. Through practical tools such as the Readiness Assessment Methodology (RAM) and the Ethical Impact Assessment (EIA), over 60 countries have strengthened their AI frameworks, with notable legislative progress in Chile, Morocco and Senegal.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The UK as part of the Executive Board agreed with UNESCO’s assessment that its own indicators are on track, which is why this output is assessed as an A.

The UK was closely involved in the negotiation of the recommendation on the Ethics of Neurotech this year. As across the spectrum, there is a risk that UNESCO does not have sufficient resources for its level of programming.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no major changes in the past year that would have any implications for the programme or its delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first Annual Review for this business case.

One recommendation:
UNESCO continues to fund, and find alternative sources of voluntary contributions, to ensure effective programming continues for this output.

Output Title	UNESCO continues to reform to improve effectiveness, reduce costs, where possible, and better communicate impact and results to Member States. UNESCO will make use of MOPAN assessments and engage with the UN80 initiative as part of reform efforts and communicate those efforts to Member States.
Output number:		5	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Indicator 1: UNESCO strategically manages its budgetary resources in response to changes in donor funding, ensuring the sustained implementation of effective programmes in service of the outputs. / Indicator 2: UNESCO provides detailed and proactive communication to Member States on the implementation and effectiveness of reform initiatives (including UN80 and UN reform, alignment with other UN agencies in the field, internal cooperation, and initiatives undertaken to close underperforming projects/field offices). / Indicator 3: UNESCO actively engages with and contributes to the Secretary-General's UN80 initiative in close consultation with Member States. / Indicator 4: UNESCO takes forward the recommendations for improvement outlined in the MOPAN assessment.	Decisions and content of Executive Board papers in October 2024 and April 2025 show progress across the indicators.	On indicator 1, publication of the new draft four year strategy and budget documents set out UNESCO’s approach to manage its budget. However, following US announcement of its withdrawal, the budget needs to be recalibrated. Member States have been told that sectors need to find savings of 11%. It is unclear how they will prioritise keeping effective programmes. There was a budgetary overcommitment brought to the Board in October 2024. / On indicator 2, Executive Board papers from April communicate to Member States about some reform efforts. Certain requests from the Executive Board (for example regarding senior travel) have not been communicated to Member States. / There is a regular item regarding UNESCO’s actions to align with the Repositioning of the United Nations Development System. While this document provides valuable information aimed at enhancing coherence, efficiency, and impact in delivering the 2030 Agenda for Sustainable Development, there remains a lack of evidence for a long-term, coherent, strategic approach to reduce costs and ensure value for money. UNESCO is not able to drive down its costs and instead continues to speak about securing additional and more flexible funding. / Regarding indicator 3, UNESCO launched a consultation with a deadline of July 2025. There have been no further communications on UNESCO engagement with UN80. There is a specialised agency cluster which reported to the Secretary-General at the end of July. / On indicator 4, MOPAN has published in 2025 assessment of UNESCO. The management response and launch of the report has been delayed by UNESCO until September 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

The UK, as an Executive Board member, uses its position to push UNESCO to reform and will continue to do so. This output is scored lower than the others given the budgetary overcommitment brought to the Executive Board in October 2024; the relative lack of engagement in the UN80 initiative; and the need for reform given the announcement of US withdrawal. Recent MOPAN findings also show areas for improvement within UNESCO.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first Annual Review for this business case.

Two recommendations:
- UNESCO to engage with the MOPAN findings and to make improvements in line with their areas for improvement. In particular, strengthening its results-based management systems, tracking poor performance, as well as improving its risk management systems and ensuring the field network is fit for purpose.
- UNESCO to closely engage with the UN80 initiatives where relevant.
- UNESCO to carefully consider how to reduce programming to meet new budgetary challenges.
## D: VALUE FOR MONEY

As this programme contributes to UNESCO's regular budget, it is not possible to identify specific programmes and projects funded by the UK assessed contribution. Therefore, Value for money is assessed in collaboration with the UK Delegation for UNESCO, considering key elements such as whether UNESCO continues to be an important delivery partner for UK priorities, whether the organisation continues to reform in line with wider UN reform objectives, and whether we have sufficient influence and credibility at UNESCO to effectively address political risks and geopolitical threats arising across the organisation’s mandate.

UNESCO has previously communicated its reform efforts through the implementation of the Director-General’s Strategic Transformation plan. However, formal reporting on this initiative concluded with the 41st General Conference at the end of 2021. Since then, updates on reform activities have become more fragmented and less comprehensive. While there is a standing agenda item addressing UNESCO’s alignment with the Repositioning of the United Nations Development System, which is a well-structured document aimed at improving coherence, efficiency, and impact in delivering the 2030 Agenda for Sustainable Development, there remains a lack of clear evidence supporting a long-term, strategic approach to reducing costs and ensuring value for money. Instead of demonstrating cost-efficiency, UNESCO continues to emphasise the need for increased and more flexible funding.

Per the most recent MOPAN assessment carried out in 2025, it was deemed that UNESCO is efficient at delivering results based upon evidence from evaluations and programmatic documents. With key indicators of efficiency being assessed as the timely completion of projects, adherence to planned budgets, and effective project management and coordination. It was also found that when challenges do arise, they primarily related to timely funding, staffing and disbursement issues with insufficient resources hindering the delivery of expected results. The MOPAN assessment highlighted UNESCO’s strengths in innovation, agility, and its ability to deliver high-quality policy advice to governments, while also noting progress in several areas. However, it emphasised the need for further improvements in results-based management, performance tracking, risk management, and ensuring the field network is fit for purpose. In its latest 2025 review, MOPAN recommended enhancements to UNESCO’s internal processes. Additionally, in light of the broader UN80 agenda, a tightening global financial environment, and the withdrawal of the US, UNESCO must prioritise reducing programming and accelerating its reform efforts.

UNESCO continues to play a vital role in shaping global norms and practices across a wide range of critical areas. Its unique combination of normative and programmatic functions allows it to influence governments worldwide, supported by its deep expertise in education, culture, communication, freedom of expression, and climate science. UNESCO has reinforced its leadership in global knowledge and policy, actively contributing to the 2030 Agenda and serving as custodian for several SDG targets, particularly SDG 4 on education. The organisation has strengthened interdisciplinary collaboration, enabling a more holistic approach to global challenges. It also consistently integrates priorities such as gender equality, environmental sustainability, and human rights across its initiatives. UNESCO excels in providing high-quality policy advice and capacity building, positioning itself as a key player in supporting countries to achieve sustainable development through integrated and informed policymaking.

E: RISK

The overall risk rating remains at Moderate and there have been no changes to the rating since the original business case was approved. The risk register was last update on 4 July 2025. Over the course of the reporting period, we have seen a number of the risks identified on AMP play out in practice, but the mitigation measures in place are currently sufficient to mitigate any impact on our programme.

For example, on the risk relating to the US choosing to leave UNESCO, the UK Delegation continue to work with the secretariat to plan for the potential consequences and support them where possible. The UK will step up into any important policy debates to shape them in line with UK priorities if there are changes to dynamics at UNESCO following the US departure.

While UNESCO have a clear and robust policy on sexual exploitation, abuse and sexual harassment (SEAH) there is an ongoing risk that their efforts in tackling SEAH are inadequate resulting in potential harm to staff or beneficiaries. The UK should continue to influence UNESCO through our capacity at the Executive Boards and through diplomatic functions such as at Working Groups and Committee Meetings.

Since 2019, UNESCO has implemented additional anti-fraud controls and now has a centralised system for management of suppliers, designed with the purpose to minimise risk of payments being made incorrectly, however, investment in further cyber security software and processes would be beneficial. UNESCO's Internal Oversight Service (IOS) has launched a fraud awareness training and undertake proactive reviews as part of the fraud risk assessment exercise and onsite investigations. IOS also conducted a review of UNESCO's Enterprise Risk Management, concluding that UNESCO "has basic architecture, structured implementation, and some reporting and repeatable management processes relating to risk management. However, improvements are required regarding regular review and reporting of corporate risks" meaning that there still lies a potential risk for the fraudulent misappropriation of UNESCO funds.

There have been no changes to the climate and environment assessment as set out in the original business case.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The business case set out for the UK’s assessed contribution to UNESCO remains the primary means for setting out FCDO’s expectations for funding, payment of which is a mandatory condition of our membership of the organisation.

Based on evidence presented at the Executive Boards and reflected in UNESCO’s Medium-Term strategy for 2022-2029, we have assessed UNESCO’s risks to be considered moderate within FCDO’s risk appetite. This is defined by FCDO risk management guidance as risks that carry a moderate impact on achievement of programme objectives or FCDO reputation, reducing what the programme delivers.

FCDO defines economy as ensuring lowest cost procurement of goods and services within project design and focuses on making sure that the unit costs are benchmarked against market norms. At the programme level, funding is aligned with time-bound work plans. Any delays in spending trigger alerts and prompt management reviews. Financial data, including planned disbursements, is monitored and documented in the annual implementation report (UNESCO’s EX/4 documents), which evaluates progress and budget execution rates.

In the previous fiscal year, UNESCO operated with a significantly higher integrated budget, enabling it to support a wide range of global initiatives. However, the recent announcement of US withdrawal has created a substantial funding gap and as a result, UNESCO will now be compelled to reassess its priorities. This financial constraint may lead to scaled-back operations, delayed projects, and a narrower geographic reach, potentially impacting the organization's ability to fulfil its mission as comprehensively as before.

UNESCO will ultimately need to reduce scope in order to be considered a viable and effective organisation and for the UK to remain a member as part of its assessed contribution.

G: MONITORING, EVIDENCE AND LEARNING

In 2024/25, UNESCO continued to advance its strategic priorities, as reflected in the Strategic Results Report and the 2025 MOPAN assessment. The organisation sustained strong performance in its normative mandate, particularly in education, science, and cultural heritage, while expanding its influence in emerging areas such as AI ethics and ocean governance. Evaluation coverage remained broad, with increased attention to cross-cutting themes including gender equality and sustainable development. However, the MOPAN review identified persistent gaps in performance monitoring and learning systems, notably in the limited number of impact evaluations and inconsistent integration of gender empowerment in evaluation scopes. Furthermore, while management response rates to evaluations improved marginally, concerns were raised by Member States regarding the timeliness and depth of follow-up actions. Despite these challenges, UNESCO’s strategic positioning and global convening power remained key assets, laying a foundation for more robust evaluation practices and accountability mechanisms in the coming year.

This Annual Review was conducted by FCDO officials drawing from documentation submitted to the Executive Board, the MOPAN assessment for UNESCO for 2025 and UNESCO's own Strategic Results Report for 2024, as well as from feedback from colleagues in the UK Permanent Delegation to UNESCO and who work closely with UNESCO.

Date of last narrative financial report	14/08/2025	Date of last audited annual statement	14/08/2025