## Annual Review Template

Title: Technical Assistance to the Health System in Sierra Leone
Programme Value £ (full life): £1,000,000		Review date: May
Programme Code: [AMP ID#]400175	AMP start date:09/05/2024	AMP end date: 01/03/2026

Summary of Programme Performance
Year	2024
Overall Output Score
Risk Rating	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006515.odt
DevTracker Link to results framework:	Not yet available

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

FCDO has provided up to £1m over 2 years (2024 – 2026) to improve the capacity and capability of the health system at national level through Technical Assistance to the Health System in Sierra Leone (TATHS). For this first annual review, we are looking at the only component that has been implemented, which is the health economics TA support to the Office of the Vice President. This is an extension of previous TA support under Saving Lives in Sierra Leone Phase 2, which was much valued by the Vice President of Sierra Leone. The VP takes a keen interest in the health sector, especially health financing, the offer of Free Health Care (FHC), and the overall management, and execution of the budget. The Office of the Vice President (OVP) also leads on nutrition coordination with the Scale Up Nutrition SUN programme residing in the OVP

The current TATHS support has spent £XXX,000 in its first year. It has provided advice on the cost of proposed health financing options, such as a social health insurance scheme (SLeSHI), and informed debate on free health care policy, the direction of travel on this, and its delivery. At a time of significant fiscal challenge and reducing health financing, it is important that policy makers are well informed on the options being proposed, and their costs to ensure a more realistic understanding at senior levels of government. The TA has supported Ministry of Health to navigate the steps for inclusion of health budget lines in the overall GoSL budgeting process, specifically prioritising these for advocacy by the VP. The TA has also provided analysis on health expenditure to the VP, to FCDO, and to Health Development Partners. This has helped ensure funding constraints and delayed budget releases are visible to the VP, who can bring the Ministries of Health (MoH) and Finance (MoF) together to find solutions.

Other areas where the input has supported UK objectives is in providing guidance for design of the IMF programme; helping to fiscally support hospitals, develop realistic handover plans for NGO supported facilities. The TA has advocated for, and supported improved coordination in the health and nutrition sector, including with the private sector. In addition to the direct contributions as outlined above, provision of TA to the OVP is much valued and indirectly contributes to UK influence with GoSL cross sectorial, well beyond its health focus.

This support also provides limited resourcing to other health system support, either through informing other TA, FCDO experts, CMPs or other interventions that enable us to have greater influence on health financing issues. Being based in the OVP allows cross-ministry solutions to health sector issues.

Programme summary:
Once the other components of this programme have started, the programme will support the delivery of quality health services at a national level through strengthening key health systems, including improved supply chain management; better understanding and planning for effective health financing; and overall improved coordination, but other system areas may be added, using as yet unprogrammed funds.
Proposed programme modalities could include financing through the World Bank or provision of specialist technical assistance to influential offices within GoSL and its agencies.
The programme will also include flexibility to respond to health emergencies, if necessary, albeit with very limited resources. As an example of this, the current TA to the OVP has flexed to meet the needs for increasing food insecurity and nutritional poverty in Sierra Leone, by taking on senior roles within the SUN secretariate (as Acting Director), or by responding to emergencies by providing technical briefs and advice to the VP.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

[Summarise – without repeating detail from Section B – progress in the past year and why the programme has scored as it has against the output indicators.

Where a programme is seriously underperforming (scores a C) or failing to improve (scores a consecutive B), improvement measures will need to be put in place. Ministers receive a strategic overview of poorly performing projects, based on data held by Finance Directorate and regional divisions, every quarter as part of regular board reports. Seek support from Commercial Directorate if dealing with a commercial contract) to help you structure a performance improvement plan with your delivery partners.]

Major lessons and recommendations for the year ahead [1/2 page]

Summary of recommendations for the next year

The programme should:

- Find ways to better use and widely share the results of the initiatives supported so far, to further influence the policy initiatives
- Use the remaining support period and the funds to build on the initial successes to achieve higher value for money (given that the programme is due to end next year.
- To conduct a sustainability assessment of these activities of this project and utilise remaining project funds, to maintain support where there is risk that key results will not be sustained. Alternative funding sources e.g MoH should be considered where the project is unable to provide the appropriate level of assistance
- DFID should plan its support to the health commodities supply chain with a holistic view. It should keep in mind the overall cost of the full supply chain and ensure that when it supports one part of the chain that other parts and key dependencies are in place or further support is provided. to an adequate standard

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programmes theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Original Theory of Change (as per TATHS Business Case)

Impact:
Fewer preventable deaths among women, adolescent girls, newborns and children in Sierra Leone.

Outcome:
GoSL Health Systems strengthened, enabling more effective health delivery and improved universal health coverage in Sierra Leone.
Outputs:
To deliver the impact and outcome, the programme will implement interlinked outputs designed to increase equitable access to services. The three proposed outputs are:
      1. Policy and planning reform for delivering UHC, including health security and strengthening health systems Policy and planning reform for delivering UHC and strengthening health systems, including health financing.
      2. Improved access to medicines, supplies and medical equipment through strengthened processes for supply chain management.
      3. Improved partner coordination in the health sector.

Assumptions:
- Fiscal space (GoSL and donor) allows ongoing GoSL political commitment, leadership sound policies and funding for the health system at national and district level.
- MoH and GoSL more broadly willing to uptake support from technical assistance.
- GoSL maintains commitment to adequate remuneration of the health work force and to increasing the staff included on government payroll.
- Government retains and effectively deploys staff with increased capacity.
- Other donor programmes will be implemented as planned.
- Donors willing to participate in coordination for health services support and financing.
- Effective donor coordination/alignment of programme alongside other relevant donor interventions e.g. Global Fund, GAVI, USAID, World Bank.
- Improved quality of health services improves health outcomes and saves lives.
- Support to health system financing plans needed to ensure sustainability.

Consider if the steps to achieving outcome and impact are still valid. Is the ToC logic, supporting evidence and assumptions holding up against implementation experience? Are there any new evidence which challenges the programme design?

Consider flagging any major changes since the programme started, rather than just over the year in question. Significant changes to the outcome or impact level of results frameworks may indicate a material change to the programme design that was approved if these details were set out in the Business Case. In this case, consider whether it would be appropriate to complete a BC addendum, and send the programme for reapproval at delegated authority levels. Otherwise, as set out in PrOF Rule 25, significant changes to the results framework should be approved by the Head of Office.

Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. Explain how you are using engagement with stakeholders and beneficiaries to optimise impact. If the programme was designed to be adaptive, what adaptations have been made? Is there evidence that provides assurance the programme is on track to meeting commitments on gender equality and the Public Sector Equality Duty?

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Review this considering the overall output and outcome assessments. Given where the programme is at, how likely is it that outcomes and impact will be achieved within the time and budget originally planned? Do you have any information from programme stakeholders and beneficiaries to support this? Check the Guide to Beneficiary Engagement for detailed guidance on how to collect and use this kind of feedback.

This is about testing the link between programme outputs and intended outcomes or impact. It is possible that outputs are being delivered but will not lead to the envisaged outcomes or impact as expected. If this looks to be the case, consider the reasons for this and what action might be needed within the programme to put things back on track.

You should refer to the current output and outcome indicators. Are there any unexpected outcomes emerging? Have there been any significant changes in the budget or timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality, or protective characteristics, compared to what was described in the Business Case?

Where an evaluation is planned, set out what progress has been made.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on the above analysis of outcome and output achievement, theory of change and VfM analysis, is there enough evidence that the programme continues to represent good value for money, or should it be restructured, or closed?

You should also consider the contribution that the programme is intended to make to your department’s portfolio (e.g. Business Plan) and if relevant, FCDO (e.g. Single Departmental Plan).

Outcome Title	GoSL Health Systems strengthened, enabling more effective health delivery and improved universal health coverage in Sierra Leone

Indicator(s)	Milestone(s) for this review	Progress
Gov't and partner commitments to the health budget are established, coordinated and shared	Information shared following health budgeting meeting.	Various tools and activities were completed, and some continue. Resource Mobilisation Execution Tracking (RMET) with MOH data presented to HDP and MOH Financing committee. Commitments to list cofinancing agreements by MOH/ MOF ongoing. GoSL has created a gap analysis of USAID ODA commitments. However these not within scope of the TA, though will have analysed for the OVP. The TA has provided budget and other analyses for the OVP, HDP and for FCDO understanding.
Higher percentage of [non-staff] health budget executed	Baseline plus 5%	There has been significant pressure on fiscal space for GoSL in 2024, and despite MOUs with FCDO and other cofinancing agreements MOH has not been able to increase budget execution to non salary elements. This was beyond the capacity of TA or the VP to deliver, but significant effort was demonstrated to advocate for this.
Progress of well resourced locally-led delivery plans developed for nutrition, Free Health Care Initiative (as part of SLESHI) and NMSA funding.	1 FHC Policy established. / 2 Strategy and Priorities established for nutrition.	1 FHC policy recognised and conceptualised as an entity under the UHC Agency Act. Process for developing a benefit package still under development. / A multisectoral national strategy for eradicating malnutrition exits. In addition there is now a development of policy and strategic plan for 'Scaling Up Nutrition (SUN), which the TA has taken leadership on

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Policy and planning reform for delivering UHC including health security and strengthening health systems policy
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
FHC embedded as a policy of UHC/ SLESHI	Development of an FHC policy prioritised by Government	A draft UHC Act has been developed for consideration by interministerial committee. A consultation on the FHC policy undertaken by Health Financing Unit MOH, with stakeholder meetings to develop a policy. Despite SLeSHI sitting under Min of Labour and FHC sitting under the MOH, the VP has advocated for combining SLeSHI and FHC into a new UHC Agency Act.
Strategic direction and mobilisation of resource and effort to progress the national nutrition and food security strategies	Establishment of prioritised activity workplan across Gov't	The TA has taken on an increasing role in the coordination of Nutrition and is now acting Director for Scaling up Nutrition (SUN). Most recently they have led on the strategic commitments in preparation for Nutrition for Growth (N4G)
MoH National Hospitals Strategy Developed (participation and TA)	2 x Strategy meetings attended	Sits on the committee developing the National Hospitals Strategy. WHO has provided TA for this, and a validation meeting held in Feb 2025.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Give an overview of what the output has achieved, and whether it is on track or off track to hit end-of-programme targets. Make sure you highlight any significant challenges, issues or underperformance.

Key Points
The Health Advisor facilitated the forming of the team to draft the Universal Health Coverage (UHC) Agency Act (with representation from the OVP, MoH, Ministry of Labour and Social Security (MoLSS), Attorney General (AG)’s Office, and SLeSHI) and participated in meetings to discuss the technical approach and jointly-draft the paper. This change from SLESHI to UHC ensured that strengthening of the Free Health Care Initiatives was discussed in this forum as it was not a mandate under SLESHI. This decision to establish a UHC agency gave momentum to the meetings on the FHCI which the Health Advisor attended.

The Health Advisor took up two further opportunities to represent the Office of the VP and engage in critical policy discussions, including participating in the MoH’s 2-day Free Health Care (FHC) Policy Development Workshop on the 20-21st November 2024, and in the MoH’s Inter-ministerial Consultation on the Overseas Medical Treatment Policy on the 27th November 2024. Lack of government expenditure on FHC for vulnerable populations and over-expenditure on overseas medical treatment for a limited few has been a serious issue for the past few years; the development of clear policies in these areas presents a huge opportunity to improve equity of spending and access to care.

The Health Advisor continued to engage in the annual budgeting process, having meetings with key stakeholders, including, the consultant hired by FCDO to support the preparation of the health budget, analysed the MoH budget request, and shared key reflections with the VP so that he was able to engage in discussions at a higher level. As a result of the latter, the VP was able to raise the initial budget presentation’s neglect of FHC and emphasis on SLeSHI at cabinet level, in order to press for better alignment of the budget with the latest policy developments (i.e. the UHC Act and the proposed FHC Policy).

In August 2024, the VP and the Minister of State (MoS) in the Office of the VP asked the Health Advisor to take on of the role of Director for the Scaling Up Nutrition (SUN) and Food Systems Coordination Unit in an acting capacity, while the Government recruits for someone to fill the role permanently.

While in the capacity of Acting Director, the Health Advisor continued to provide strategic and start-up support to the team at a time when there is a clear need for stronger multisectoral coordination across the nutrition, food systems, Feed Salone, and climate change spaces, and growing concerns regarding food insecurity and child food poverty. This included engaging with partners and potential donors; attending or chairing key meetings and events to discuss and bring to the VP’s attention key challenges and opportunities within the national push for food systems transformation; and providing the national team with targeted organisational and capacity building support.
The Office of the Vice President has established the SUN & Food Systems Coordination Unit - the unit brings together the SUN coordination work and the food systems coordination work led by the office.
The new unit will work to centre nutrition targets and a whole-of-government approach to food systems.

The Health Advisor has developed concept notes and also joined stakeholder meetings related to the development of a Nutrition Information System. As a result, Capacity 4 Nutrition (C4N) have committed funds for SUN to cover additional human resources and access to an off-the-shelf, customisable digital information system.

On the National hospital strategy development, the Health Advser has joined the MOH’s Hospital strategy Development group in preparation for the work to create a National Strategy.

Output Title	More effective allocation of resources for health through improved use of data, greater oversight of health financing, greater advocacy for health financing and better coordination.
Output number:		2	Output Score:
Impact weighting (%):		30	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Advocacy with VP to support Gov't routine and counterpart funding commitments	3x commitments met
NMSA annual budgets increased through advocacy	"1. VP raises lack of funding for FHC during budget process. / 2. Increased budgets for FHC as a result of advocacy/VP intervention. "
Coordination and sharing of Gov't budgets resulting in stronger advocacy for health financing	"1. Attendance at Health budget meetings incl budget hearing / 2. Analysis and dissemination of budget"

The Health Advisor tracks health disbursements to key areas and analyse trends over time which led to an agreement earlier in the 2024 that the MoH and Ministry of Finance (MoF) would prioritise hospital payments, the Health Advisor paid close attention to this area. She also received information on other areas of concern, including vaccine financing, which she would immediately escalate to the VP.
This work did not only give the VP a better insight and understanding of the budget execution realities but also ensured that the VP took immediate action to get certain critical payments released. This deep understanding of the system-level challenges greatly enhanced the VP’s ability to make sound decisions when it comes to things like SleSHI, co-financing discussions, the energy crisis, public sector reform etc.
Despite a successful meeting on health budget in February 2024, agreed actions, including quick release of priority Q1 and Q2 payments from MoF (to health facilities, NEMS, NMSA, vaccines) have not progressed quickly.
Q1 ceilings for MoH disbursed by MoF but all tertiary facilities were awarded about 45% less than the approved budget amount. PETS forms were submitted by MoH requesting payment of these funds from MoF but two-months later than the agreed date of 16th February 2024, and hospitals were still waiting for payment as of end of May 2024. This process indicates that late payments are not just due to lack of funds on the MoF side, but also to administrative/bureaucratic processes and considerable delays on the MoH side.

The Health Advisor continued to engage in the annual budgeting process. She had meetings with the consultant hired by FCDO to support the preparation of the health budget, analysed the MoH budget request, and shared key reflections with the VP, so that he was able to engage in discussions at a higher level. As a result, the VP was able to raise neglect of FHC, in the initial budget presentations and emphasis on SLeSHI at cabinet level, in order to press for better alignment of the budget with the latest policy developments (i.e. the UHC Act and the proposed FHC Policy). The Health Advisor also attended the final budget presentation in parliament and gave key updates to the VP.
The VP’s sound understanding of these types of operational challenges greatly enhances his ability to make evidence-informed decisions when it comes to co-financing, public-private partnerships (PPPs), and SLeSHI.
The 2025FY represents an almost 11% increase in budget request from 2024FY indicating a bold push
to address critical health priorities, scale up infrastructure projects; all lifesaving interventions while
 moving towards the Abuja declaration target of 15%

Output Title	Improved partner coordination in the nutrition sector
Output number:		3	Output Score:
Impact weighting (%):		30	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Number of opportunities taken to respond to emerging health and nutrition issues	Four responses
National Nutrition Information Management System including key nutrition targets, designed and implemented	NIMS Designed with key nutrition targets
"1. National Food Systems Coordinator recruited and inducted into the OVP team. / 2. Director of Sun recruited and inducted into the OVP team."	Coordinator and Director recruited

Technical and systems support was given to the SUN secretariat, particularly on the establishment of a Nutrition Information Management System which tracks progress towards key nutrition indicators across MDAs; the identification of strategic areas to be prioritised by the SUN Secretariat and Movement

The Health Advisor provided technical assistance to the SUN Secretariat and the Minister of State (who oversees SUN) to help support the team and move things forward at a time when there is a need for stronger multisectoral coordination across the nutrition, food systems, Feed Salone, and climate change spaces.
The Health Advisor developed concept notes, connected with stakeholders, and attended stakeholder meetings related to the development of a Nutrition Information System. As a result, Capacity 4 Nutrition (C4N) have committed funds for SUN to cover additional human resources and access to an off-the-shelf, customisable digital information system…

The Health Advisor proposed the idea of designing and rolling-out a national malnutrition prevention campaign, spearheaded by the SUN Secretariat under the OVP, and supported the team to develop a concept note. The Health Advisor is helping to pitch a ‘proof-of-concept’ approach to partners which will attract enough funds to conduct a Knowledge Attitudes and Practices (KAP) study and design an appropriate, pre-tested, information and behavioural change campaign

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

N/A

This is the first annual review for this programme.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g. costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 5 E’s of FCDO’s value for money framework – economy, efficiency, effectiveness and equity (including gender equality, disability inclusion, LGBT+ and other equality considerations), and overall cost-effectiveness. Referring back to the relevant text in the approved Business Case’s Strategic Case and agreement with the implementing partner(s) may be relevant.

Where an emissions assessment and shadow carbon pricing were required for the original appraisal case, this will need to be periodically reviewed and updated during implementation. Any review or updated estimates of emissions, and any implications these have on value for money once shadow carbon pricing has been applied, should be included here.

Assessment of whether the programme continues to represent value for money
Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down?

Despite the lack of VFM metrics, this TA programme support is providing professional health advice, participating in budget discussions engaging with other health consultancy to better learn from their expertise to support specialised ministries working closely with the office of the VP.

Given that the UK’s longstanding investment in the health system in Sierra Leone coincides with significant reductions in maternal and child mortality, it is fair to assume that the closure of the programme would lead to an increase in mortality statistics. For this reason, we conclude that the programme continues to represent VfM, but will prioritise the development of indicators with partners, ready to assess the final year of delivery and performance.

You should also consider the programme as part of the wider portfolio in your department (e.g. Business Plan) and, if relevant for this document, FCDO as a whole (e.g. Outcome Delivery Plan) or HMG as a whole.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

Few risky pieces to note is this TA is placed in politically sensitive office needing the adviser protected from political influence.
Again, recently the USAID stop work order has incapably render the implementing partner resource liquidated and closing operation in Sierra Leone causing a shift in the management of the TA to a potential existing partner in SL.

We have also experienced a petty fraud recently due to delays in carry out proper controls/checks on partner’s rent billing etc.

We assess the risk at approval as Minor. This programme will fund technical assistance to two ministries and to a small team of supply chain technical specialists through a World Bank Trust Fund. The programme team will focus intense oversight on the work of the programme, the IP staff implementing the programme and the World Bank procedures will be in place to manage the small trust fund. Therefore, the programme team assesses risks to be manageable within the Minor risk rating.

Public Service Delivery & Operations Risk has an appetite of minimal. This Technical Assistance programme will work closely with the relevant Ministries e.g. Ministry of Health, Ministry of Finance and other development partners to ensure policies are developed and implemented. Also, we will build flexibility into the programme, which will allow for adapting to changing environment including respond to shocks

Policy & Programme Delivery: We made use of the available support from PCD at the early stages of procurement of the programme. We will maintain open and ongoing discussions with the partner about the challenges of delivering through FCDO systems and have an open feedback loop.

The Risk appetite for Financial and Fiduciary risk is at Cautious even though this is mainly a technical assistance programme, because of the environment, this is a category to always keep an eye on. Due diligence of implementing partners (IPs) includes a thorough review of financial stability, internal checks and balances, risk management and mitigation measures, and fraud reporting processes. We will ensure regular discussion with IPs on financial performance. IP risk rating forecasts, scrutiny of financial reports and spot checks on invoices.

We seek to avoid significant reputational damage associated with poor delivery, politicisation, mismanagement, misuse of funds, or inadvertently doing harm through our actions. Reputational risk is inextricably linked to all the other risk categories, therefore risks and mitigations in the above category assessments are also relevant here. We will maintain high level of political dialogue with the relevant ministries and departments and timely escalations when blockages are experienced.

The BHC maintains a zero-tolerance approach to inaction on SEAH and other safeguarding incidents. BHC conducts enhanced due diligence (EDD) on the tier 1 partner, ensuring that partner rules and requirements are applied in-country. - Regular review of partner safeguarding policies/processes and regular discussion of the risks in partner’s meetings. Sharing of good practice between BHC implementing partners in quarterly all-partner meetings. With support from the BHC safeguarding champions, work with partners to ensure that policies and procedures are implemented in practice - Staff training on current policy and best practices to ensure we pass-on to IPS.

Review your risk appetite for each of our seven risk categories against residual risk level over the last year, drawing on FCDO’s Risk Appetite Statement. Further guidance on the FCDO’s overall approach to risk management can be found in the Risk Intranet page and Risk Hub .

What have the main trends been in your risk exposure and response over the last year, and what have they been driven by? Where relevant, provide updates on areas requiring particular assurance, for example gender equality, counter-terrorism financing, public sector equality duty, disability, Safeguarding against sexual exploitation and abuse and sexual harassment (SEAH) or child safeguarding. In order to align with the Paris climate Agreement, you must reassess climate and environment risk within your programme and provide a statement, even if risk is judged low. Outline appropriate mitigation action where relevant.

Review the assurances provided in the business case under the Gender Equality Duty and the Public Sector Equality Duty and read your Equalities Impact Assessment (if you completed one). Provide updates against any indicators you have identified to measure impact on equalities.

Consider the following:
- Have any assumptions made about the impacts on equalities in your BC changed? If so how, why and which ones?
- How are you monitoring and mitigating any risks identified?
Review and ensure the main risks identified through partner due diligences, either in the initial assessment or refresh process, are included in the programme risk register. These should be updated to take account of how the programme has responded to them across the year.

Consider the following:
- Review the status of your Due Diligence assessments across your programme use this to inform the overall risk assessment.
- Review the identified risk in the DDA, and the mitigation actions.
- Has the mitigating action progressed and how does it affect our assessment of risk, if at all?
- What have we learned about the partners through the years of implementation?
- How does this affect the initial DDA risk assessment?
- Do any DDA’s need refresh due to timelapse or material changes?
- Has your knowledge of the partner or the progress of recommendations reduced or increased your risk assessment of that partner?
- Is the assessment still a proportionate assurance to the risks of the programme?
Have you been able to deliver comfortably within risk appetite, or have there been areas of pressure? How have you responded, and what further action is required in the year ahead to manage risk within appetite? If you need to amend your risk appetite or your residual risk level rating, explain your rationale and document the changes in AMP. If you are increasing your risk appetite above FCDO’s corporate appetite in any category, discuss this with your head of office/department before finalising.

Some relevant information may not be suitable for publication. You can use the AMP Risk Register, Delivery Plan and Timeline to record information not suitable for publication outside FCDO – these should be updated as part of or following the Annual Review. Remember that throughout implementation, risk registers should be updated as often as required, with monthly review recommended, and quarterly review a minimum standard.]

Update on Partnership Principles (delete this section if n/a) [1/2 page]

[For programmes for where it has been decided (when the programme was approved or at the last AR) to use the PPs for management and monitoring, provide details on:
  1. Any concerns about the four PPs over the past year, including on human rights.
  2. Did you notify the government of any concerns?
    1. If Yes, what was the government response? Explain any remedial actions.
    2. If No, was disbursement suspended during the review period? When? And what were the consequences?

For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.]

Annual Statement of Progress (financial aid programmes only – delete if n/a) [1 page]

Current level of fiduciary risk and direction of travel since last ASP	Insignificant/Minor/Moderate/Major/Severe / Improving/Stable/Worsening
Specific assessment of corruption risk and direction of travel since last ASP	Insignificant/Minor/Moderate/Major/Severe / Improving/Stable/Worsening
Is a full FRA update required?	[Yes: likely to be needed where risk levels have worsened / No: where the situation is stable or improving]

Read the Fiduciary Risk Assessment PrOF Guide to help you answer these questions. If you have sensitivity concerns about publishing this assessment, you should complete this ASP in a separate document to submit to your HoD alongside this Annual Review. You can then delete this section.

What are the key fiduciary risks? Include a brief description of the risks, planned mitigation measures, and progress achieved/remedial actions.
- Is there a credible PFMA reform programme? Is donor support for PFM aligned behind a single government-led action plan?
- Can you cite examples of positive progress to report which could feed into FCDO external publications?

List the sources used in preparing this Annual Statement of Progress, e.g. government/donor reports, meeting minutes, CSO indices.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]
Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]
There is one component under the Technical Assistance to Health Systems-TATHS programme called Technical Assistance to office of the Vice President (TAOVP) and is implemented by International Rescue Committee (IRC) through an Accountable Grant Arrangement (AGA).
The Accountable Grant Arrangement was signed and the agreed budget for the two years (March 2024- March 2026) was £454,928.
Under the Technical Assistance to office of the Vice President Accountable Grant component/project (4000175-401) the IRC partner is providing this Technical Assistance (TA) support to the Vice President (VP) by funding a full-time Health Advisor, based in the VP office since March to date. The Health Advisor briefed the VP on a regular basis and provided data analysis highlights, briefing papers, talking points, and escalates critical issues.
FCDO also have regular meetings with the TA Adviser to update on her support and TORs delivery.

Issues to consider for both the implementing partner(s) and FCDO include quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management e.g. accuracy of forecasting; monitoring of assets. Consider also how FCDO could be a more effective partner to help deliver the programme.

Quality and timeliness of narrative and financial reporting

IRC has been submitting quarterly reports covering the period to March 2024 to date. In total we’ve have received three reports in 2024 all submitted on time. Reporting contains progress made in key areas of implementation, successes and challenges and plans for the next quarter. The process of reviewing, querying and responding to comments and clarification was clear and led to a better understanding of the issues, challenges and successes experienced by the technical assistance adviser.

A main challenge for IRC is managing the forecasting of expenditure or the actual monthly spend and quarterly/monthly forecasts of expenditure have been consistently over-estimated hence forecast always higher that actual invoices that are coming in from IRC. To date, a sum of £143,578 has been disbursed to IRC – these funds have been used to support the TA adviser, Vice president internet cost and IRC overheads etc

If there is a contract, set out (where applicable):

- Delivery against contract KPIs, and Terms and Conditions
- Compliance with the Supply Partner Code, drawing on advice from Commercial Directorate
- Compliance with the new cost and transparency requirements, highlighting any profit variance and challenge and use of Open Book Accounting
- Performance of Partners, including summary of the Strategic Relationship Management scorecard assessment for each delivery partner.
- Compliance with the Gender Equality Duty (for ODA programmes) and an expectation that partners will set out that they will monitor impacts on equalities and how they will give due regard to the Public Sector Equality Duty in their delivery.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and FCDO. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond FCDO). If there is an evaluation linked to this programme provide an update on findings (if not covered elsewhere in the AR).

This is a TA supported programme, and monitoring is not applicable to it delivery. The FCDO team usually meet with the TA Lead and in these meetings, we ask for clarity on issues etc. The adviser has demonstrated professionalism since the commencement of the support activities.

Evidence
Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence.
Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography and other relevant variables.
Where an evaluation is planned set out what progress has been made in line with the Inclusive Data Charter (see PrOF rule 9).

Learning
What learning processes have been used over the past year to capture and share lessons, new evidence and know-how?
What are the key lessons identified over the past year for (i) this programme (ii) wider FCDO and development work?
Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A.
Do you have any learning aims for the programme for the coming year?

Date of last narrative financial report		Date of last audited annual statement