## Annual Review

Title: Technical Assistance to the Health System in Sierra Leone
Programme Value £ (full life): £1,000,000		Review date: 9th May 2025
Programme Code: [AMP ID#]400175	AMP start date:09/05/2024	AMP end date: 01/03/2026

Summary of Programme Performance
Year	2024
Overall Output Score	A
Risk Rating	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006515.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007120.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Through the British High Commission (BHC) the Foreign, Commonwealth and Development Office (FCDO) has allocated up to £1m over 2 years (2024-2026) to improve capacity and capability within the health system in Sierra Leone at national level through the Technical Assistance to Health Systems (TATHS) programme. The programme provides advice, intended to strengthen national systems and therefore improve the quality of health services. Further technical assistance (TA) and systems support was intended to improve supply chain management. We have now decided to limit funding in the second year to the current TA only, due to uncertainty on future funding priorities.

Therefore, for this first annual review, we are assessing a single component: the health economics Technical Assistance (TA) support to the Office of the Vice President. This is an extension of previous TA support under Saving Lives in Sierra Leone Phase 2, which was valued by the Vice President of Sierra Leone (VP). The VP has specific responsibility for key aspects of social delivery, including the health sector. He is focused on health financing, the delivery of Free Health Care (FHC) and the overall management and execution of the health budget. The Office of the Vice President (OVP) also leads on nutrition coordination, hosting the Scaling Up Nutrition (SUN) Secretariat.
Programme summary
The current TATHS support has spent £190,775 in its first year. It has provided advice on the potential and value of health financing options, such as a Sierra Leone social health insurance scheme (SLeSHI), and has informed discussion on the free health care policy, its direction of travel and delivery. It has kept health high on the VP’s radar as a critical element of social spend and has supported increased focus on nutrition as a key determinant of health and development outcomes.

At a time of significant fiscal challenge and reducing health financing, it is important that policy makers in the Ministry of Health (MoH) and the OVP are well informed about policy options proposed, their costs and implications, to ensure a more realistic engagement at senior levels of government. This TA has supported the Ministry of Health to lead in the inclusion of health budget lines in the overall GoSL budget, navigating a complex process and prioritising health budget lines for advocacy with the VP. The TA has also provided analysis on health expenditure to the VP, to BHC, and to Health Development Partners. This has helped ensure funding constraints and delayed budget releases are visible to the VP, who is able to convene Ministry of Health (MoH) and the Ministry of Finance (MoF) to find solutions. The TA is based in the OVP because the VP has specific responsibility for and oversight of health delivery in Sierra Leone and has more influence within Cabinet and with MoF in the provision and execution of budgets than the MoH.

The fiscal constraints within the country mean that the Ministry of Finance is limited in the funding it can release and health faces competition from education, infrastructure and other GoSL priorities. This TA has supported broader UK objectives, for example in providing guidance for design of the IMF programme; helping to ensure the prioritisation of financial support to hospitals, and in developing realistic handover plans for current NGO supported facilities as they transition to government ownership. The TA has advocated for and supported improved coordination in the health and nutrition sectors, including with the private sector. In addition to these direct contributions, provision of TA to the OVP is much valued and indirectly contributes to UK influence with GoSL across sectors, and well beyond its focus on health. This is evidenced in more detailed narrative below.

This support has also provided limited resourcing to other health systems support, either through informing other TA, BHC experts, CMPs or other interventions that enable us to have greater influence on health financing issues. Being based in the OVP has enabled the coordination of cross-ministry solutions to health sector issues such as prioritising the funding of hospitals under the life-saving support agreement.

The programme includes flexibility to respond to health emergencies and to respond to the VP’s requests for specific support despite limited resources. As an example of this, the current TA to the OVP has flexed to meet the needs created by increasing food insecurity and nutritional poverty in Sierra Leone, by taking on the role of Director of the Scaling up Nutrition (SUN) Secretariat and by responding to emergencies (e.g. Kush drug deaths) by providing technical briefing and advice to the VP. Given the importance of nutrition as an underlying cause of morbidity, the programme was able to respond to the VP’s request to lead the Government’s response.

Summary supporting narrative for the overall score in this review
The programme has scored an ‘A – Outputs met expectations’ in its first year. The first two outputs on support to policy and planning and on health financing policy have seen good progress in supporting a Universal Healthcare Policy (UHC) to include FHC (a key BHC policy priority) and there has been some progress in pressing for co-financing payments to several donor-supported healthcare programmes. Progress on the third output around improved coordination in the health and nutrition sectors narrowly missed scoring an A because the nutrition information management system hadn’t yet been launched and recruitment into the OVP is behind schedule. We expect to see further progress on this output early in the second year of the programme.

The programme has made a good start and should continue to support health financing and policy objectives to support Government to maintain health and nutrition services in a reducing donor funding landscape, where domestic prioritisation of scarce resource and execution of budgets to key activities will be increasingly important.

Summary of major lessons and recommendations for the next year
The programme should:

1. Develop a Develop a communications system to share the results of initiatives developed to further influence and mobilise support for health and nutrition policy.
2. Strengthen our mutually agreed workplan to better monitor and track implementation and confirm joint understanding of tasks and deliverables ahead of time, and as developments take place.
3. Given the tight Government fiscal space, the TA should work with stakeholders, including BHC, to prioritise the use of scarce resources to the health sector. Given reductions in global ODA, it is vital to assess and set out options for the prioritisation of funding to NMSA as part of the wider execution of health funds. Consideration should be given to adding the operational funds to NMSA to the lifesaving budget lines priority document, used by MoF.
4. The experience of the budgeting process this year has clarified that an increase in budgets is within the influence of the TA (and the VP) but not within their control. The Programme Team should revisit Output Indicator 2.2 and revise accordingly to reflect this.
5. The TA should focus adequate time on building capacity within the OVP. This is the final year of the project and adequate capacity must remain once the TA has left post. New capacity building goals should be written into the workplan, and the TA and the programme team should encourage the swift appointment of a substantive Director of SUN.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The impact of fewer preventable deaths among women, adolescent girls, newborns and children in Sierra Leone and the outcome of strengthened GoSL Health Systems, enabling more effective health delivery and improved universal health coverage in Sierra Leone, remain unchanged within the Theory of Change (ToC).
The Gender policy marker of ‘significant’ remains appropriate for this programme, given the intended impact and focused support to delivery of Free Health Care. The FHC initiative ends user fees for pregnant women, lactating mothers, and children under five, aiming to improve maternal, neonatal, and child health by reducing the financial burden of healthcare for these vulnerable groups, recognizing that financial barriers were a major obstacle to accessing services. To meet the criteria for the significant gender marker, the programme should more explicitly bring out the gender positive elements of this work in documentation and future reviews.
The original ToC in the business case envisaged a larger programme of TA and systems/data management support to the health supply chain. This additional TA remains on hold as we wait for further clarity on international donor funding to health. Currently this is affecting one of three inputs and three of seven supply chain-related outputs.

We will focus the established TA support on lobbying for increased, prioritised and regularised budget execution to health – to medicines supply in particular – and planning for/recognition of the need to scale up domestic financing as international support to the health sector declines this and next financial year. We will continue to work closely with NMSA where possible to improve supply chain and data management. In parallel, we have signed an MOU with MoH, committing them to press for funding to NMSA to support this. The logic in the ToC remains valid.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The contribution of the TA in progressing policy and action on health financing and nutrition is demonstrated in Section C: Detailed Output Scoring. More challenging is the sustainable building of capacity within the OVP to continue this work when the project ends. The programme will focus more on sustainability and legacy in this, its final year.

Overall, Sierra Leone has seen progress against the expected impact, though attribution to the role of TA in this is difficult to determine. The most recent mortality estimates (IGME 2023) have seen under-five mortality reduce to 94/1000 live births, and maternal mortality is also estimated to have fallen from 443/100,000 to 354/100,000 live births (WHD 2025). The estimated reductions in these impact indicators are a significant achievement, supported by other UK and international programmes.

Outcome Title	GoSL Health Systems strengthened, enabling more effective health delivery and improved universal health coverage in Sierra Leone

Indicator(s)	Milestone(s) for this review	Progress
Gov't and partner commitments to the health budget are established, coordinated and shared	Information shared following health budgeting meeting.	Various tools and activities were completed. Provided information as part of the Resource Mobilisation Expenditure Tracking (RMET) with MoH data presented to HDP and MoH Financing committee. Work to publish co-financing agreements by MoH/ MoF is ongoing. The Government has now completed a gap analysis of USAID pause in ODA commitments which the TA has analysed.. The TA has provided budget and other analyses for the OVP, HDP and for BHC understanding.
Higher percentage of [non-staff] health budget executed	Baseline plus 5%	There was significant pressure on fiscal space for GoSL in 2024, and despite MOUs with BHC and other cofinancing agreements, MoH has not been able to increase budget execution to non-salary elements. It is beyond the control of the TA and the VP to enforce execution of agreements but the VP has a strong voice in prioritising payments and significant effort was demonstrated.
Progress of well-resourced locally led delivery plans developed for nutrition, Free Health Care Initiative (as part of SLESHI) and NMSA funding.	1 FHC Policy established. / 2 Strategy and Priorities established for nutrition.	1. FHC policy recognised and conceptualised as an entity under the UHC Agency Act. Process for developing a benefit package still under development. / 2. A multisectoral national strategy for eradicating malnutrition exits. In addition there is now a development of a policy and strategic plan for 'Scaling Up Nutrition’ (SUN), which the TA has taken leadership on.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
There has been progress against the expected impact, though direct attribution of the role of TA is difficult to determine. The most recent mortality estimates (IGME 2023) have seen under-5 mortality reduce to 94/1000 live births, and maternal mortality is also estimated to have continued to fall to 354/100,000 (WHD 2025). UK funding to this TA programme and the larger Saving Lives 2 and 3 programmes have contributed significantly to this reduction.

The role of the FHC policy in reducing ‘out of pocket’ expenses for Sierra Leoneans is well reported, and formalising this into a defined policy remains a priority. Bringing this into government domestic resourcing remains challenging, and the provision of good data to inform advocacy at the highest levels has been critical, particularly given the likely reductions in support by external donors. Recognition of the tight fiscal constraints by government and the choices for future financing for the most essential health care for mothers and children will involve difficult and potentially sensitive decisions. The TA support to the OVP has helped inform this process at inter-ministerial and cabinet level. Development partner have shared concern about the feasibility of SLeSHI - and insurance-based solution. The development of an alternative UHC Agency approach incorporating FHC has the potential to address issues raised.

Although the full execution of government spend on Free Health Care commodities is rarely achieved, there has been visibility on the need for this at the highest level of government. Support and insight from the TA helped inform the content of the MOU between BHC and Government that may be a tool in continued efforts to seek greater domestic funding and execution for FHC. It is important that the programme continues given its significance role in advocacy for execution of domestic funds to health systems and lifesaving interventions.

The current TA has been requested by the VP to take the role of acting Director of SUN, which BHC was consulted on and agreed to. In this role the TA has been able to progress multisectoral coordination and advocacy for nutrition. Given recent deterioration in food security and nutrition (84% food insecure and 5th worst severe child malnutrition globally), this positioning of TA support has been timely, and has the potential to avert and mitigate the impact of further shocks, through planning, policy and strategy, which have advanced. The TA has represented government at global nutrition meetings in Rwanda, and in preparation of the N4G commitments (for March 2025 Paris meeting). The addition of the Director of SUN role supports us to meet nutrition aims under our Saving Lives 3 programme.

## C. DETAILED OUTPUT SCORING

Output Title	Policy and planning reform for delivering UHC including health security and strengthening health systems policy
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	N/A – First AR

Indicators	Milestones for this review	Progress
FHC embedded as a policy of UHC/ SLESHI	Development of an FHC policy prioritised by Government	A draft UHC Act has been developed for consideration by interministerial committee. A consultation on the FHC policy undertaken by Health Financing Unit MOH, with stakeholder meetings to develop a policy. Despite SLeSHI sitting under Min of Labour and FHC sitting under the MOH, the VP has advocated for combining SLeSHI and FHC into a new UHC Agency Act. / B Outputs moderately did not meet expectations
Strategic direction and mobilisation of resource and effort to progress the national nutrition and food security strategies	Establishment of prioritised activity workplan across Gov't	The TA has taken on an increasing role in the coordination of nutrition and is now acting Director for Scaling Up Nutrition (SUN). Most recently the TA has led the development of strategic commitments in preparation for Nutrition for Growth (N4G) Summit, which now guide the country’s nutrition strategy. / A+ Outputs moderately exceeded expectations
MoH National Hospitals Strategy Developed (participation and TA)	2 x Strategy meetings attended	Sits on the committee developing the National Hospitals Strategy WHO has provided TA for this, and a validation meeting held in Feb 2025 (Strategy completed). / A Outputs met expectations.

Briefly describe the output’s activities and provide supporting narrative for the score.

Key Points
The TA facilitated the forming of the team to draft the Universal Health Coverage (UHC) Agency Act (with representation from the OVP, MoH, Ministry of Labour and Social Security (MoLSS), Attorney General (AG)’s Office, and SLeSHI) and participated in meetings to discuss the technical approach and to draft the paper. This is a significant success as the change from SLeSHI to UHC ensured inclusion of and focus on strengthening the Free Health Care Initiative, a significant area of UK investment and priority initiative with the potential to further improve maternal and child mortality statistics. BHC is not technically convinced about the affordability of SLeSHI and whether it can provide for the most vulnerable. The TA’s role has been vital in preserving and integrating FHCI into future UHC plans.

The TA took up two further opportunities to represent the Office of the VP and engage in critical policy discussions, including participating in the MoH’s 2-day Free Health Care (FHC) Policy Development Workshop on the 20-21st November 2024, and in the MoH’s Inter-ministerial Consultation on the Overseas Medical Treatment Policy on the 27th November 2024. Lack of government expenditure on FHC for vulnerable populations and over-expenditure on overseas medical treatment for a limited few has been a serious issue for the past few years; the development of clear policies in these areas presents a huge opportunity to improve equity of spending and access to care.

The TA continued to engage in the annual budgeting process, having meetings with key stakeholders to support the preparation of the health budget, analysed the MoH budget request, and shared key reflections with the VP so that he was able to engage in discussions at a higher level. As a result of the latter, the VP was able to raise the initial budget presentation’s neglect of FHC and emphasis on SLeSHI at cabinet level, which enabled him to press for better alignment with the UHC Act and the proposed FHC Policy).

The TA helped establish the Health Private Sector Partners (HPSP) group, seeking greater diversification of finance to the health sector. This group offered constructive questioning of hospital financing and management systems and went on to provide financial support for the opening of a new (but delayed) children’s hospital. The TA supported the elections for the HPSP Executive Committee and coordinated the first Quarterly HPSP meeting.

While in the capacity of Acting Director for Scaling Up Nutrition (SUN), the TA continued to provide strategic and start-up support to the team at a time when there is a clear need for stronger multisectoral coordination across the nutrition, food systems, Feed Salone, and climate change workstreams. This included engaging with partners and potential donors, chairing key meetings and events to discuss and bring to the VP’s attention key challenges and opportunities within the national push for food systems transformation; and providing the national team with targeted organisational and capacity building support. We recognise that this position is temporary – once the role is filled by a permanent member of staff, the advisor will more back to advising the team. We support timely progress to filling this role permanently, as part of the TA’s support to national systems capacity building. Nonetheless, time spent filling this critical gap has enhanced the TA’s understanding and the system connections between health and nutrition, benefitting also our wider influencing position and objectives under Saving Lives.

On the National hospital strategy development, the Health Adviser has joined the MOH’s Hospital strategy Development group in preparation for the work to create a National Strategy. This was validated in 2025. There was also the development of a prioritised life-saving list of budget lines that would inform Ministry of Finance on priorities for budget execution. With this list the VP was able to advocate for the timely execution of critical budget lines, albeit with variable impact, given the current fiscal space and lack of transparency around the budget process and the political economy of budgeting.

As directed by the VP, the TA coordinated stakeholders involved in the electronic medical record (EMR) Pilot, including OVP, MoH Directorate of Policy, Planning and Information (DPPI), Smart Systems, International Rescue Committee (IRC), Directorate of Science, Technology and Innovation (DSTI). This coordination was essential to progress the Pilot and to provide a realistic assessment of the project’s sustainability. In the pilot over 7,000 new patients were registered on the system, and the process of digitization has identified inefficiencies in the hospital related to human resources, physician’s varying caseloads, and laboratory referrals to private providers. The hospital leadership can utilise this information to make-evidence-based improvements and reforms. Decisions on maintaining and rolling out EMRs will be informed from this pilot.

Going forwards, the TA and OVP are in a strong position of influence to mobilise support for policy change.

Lessons learned this year and recommendations for the year ahead
This is the first annual review for this programme. The following actions are recommended.

1. Develop a communications system to share the results of initiatives developed to further influence and mobilise support for health and nutrition policy.
2. Strengthen our mutually agreed workplan to better monitor and track implementation and confirm joint understanding of tasks and deliverables ahead of time, and as developments take place.

Output Title	More effective allocation of resources for health through improved use of data, greater oversight of health financing, greater advocacy for health financing and better coordination.
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	NA- First AR

Indicators	Milestones for this review	Progress
Advocacy with VP to support Gov't routine and counterpart funding commitments	3x commitments met	Through coordination with NGO run hospitals and other agencies with co-financing agreements, the VP has been informed when these have not been executed. Support to at least 3 NGO-run hospitals has released partial funds and the VP was able to release fuel payments to doctors, averting strike action. A partial cofinancing payment was made to GAVI and OVP lobbying continued for commitments required, including FP2030. / A – outputs met expectations
NMSA annual budgets increased through advocacy	1. VP raises lack of funding for FHC during budget process. / 2. Increased budgets for FHC as a result of advocacy/VP intervention.	Given the fiscal space for government this has been challenging. / 1. The Budget Process for 2025 benefited from strong, informed advocacy by the OVP, strengthening the voice for MoH. Initial budget for FHC was considerably lower than expected and VP was able to advocate for an increase in the allocated budget (delivered in the next period). / 2. The budget for NMSA in 2025 is NLe 64,355,000 and lower than in 2024 (90,890,000), though only a small percentage was executed. However, the budget this year was initially lower so VP intervention contributed to an increase. An MOU for execution of agreed budgets to NMSA has been signed between BHC and the Ministry of Health. / A – Outputs met expectations.
Coordination and sharing of Gov't budgets resulting in stronger advocacy for health financing	1. Attendance at Health budget meetings including budget hearing / 2. Analysis and dissemination of budget"	1. Achieved. / 2. Detailed budget analyses shared for use by OVP, BHC and others. / A – Outputs met expectations

The TA tracked financial disbursements to key areas and analysed trends over time which led to an agreement earlier in 2024 that the MoH and Ministry of Finance (MoF) would prioritise hospital payments, using a tool developed by the TA – the ‘lifesaving budget lines’ document. The adviser also received information on other areas of concern and relayed this to the OVP, including GAVI vaccine and FP2030 and other conditional cofinancing agreements. However, due to fiscal challenges, some of these were only partially fulfilled. Consideration should be given to the addition of NMSA operational funds to the lifesaving budget lines.

Five NGO-run hospitals now have agreements in place for some government financing and staffing. Following consultation, the TA drafted Host Country Agreement Guidelines, outlining the specific support available for Non-Governmental Organisations (NGOs) running health facilities. Given historical non-payment, these were escalated to the VP who was able to advocate for payment. This work gave the VP a better insight and understanding of the budget execution realities, ensuring that the VP was informed to take action to get critical payments released, subject to broader considerations, fiscal realities and political will. This deepened understanding of the system-level challenges has enhanced the VP’s ability to make informed decisions about funding requirements such as FHC and SLeSHI, co-financing discussions, the energy payment challenges for hospitals, public sector reform etc.

One example of this was the delayed payment of fuel allowances to doctors. These payments had passed through all public-financial management (PFM) approvals stages but were not being prioritised for final sign-off at the Bank of Sierra Leone level, and the Sierra Leone Medical and Dental Council (SLMDC) planned to strike if allowances were not paid. After the TA briefed the VP on the impact of further delays, the VP directed the Bank Governor to make these payments immediately and the risk of a threatened doctors’ strike - and major health sector disruption - was averted.

Despite a successful meeting on health budgets early in 2024, agreed actions, including quick release of priority Q1 and Q2 payments to councils and health facilities, the MoF did not manage to release funds, and by the end of the 2024 year, some hospitals had only received first quarter disbursements. Along with the BHC, the TA will advocate for funding to be released to support NMSA in getting medicines to hospitals and health facilities.

The TA continued to engage in the annual budgeting process. Meetings were held with consultants hired by BHC to support the preparation of the health budget and provided background contextual information. They analysed the MoH budget request, and shared key reflections with the VP, so that he was able to engage in discussions at a higher level. As a result, the VP was able to raise the underfunding of FHC in the initial budget presented by MoH, and to be informed on the costs for SLeSHI at cabinet level which allowed for better alignment of the budget to MoH priorities. It also informed on policy in development, and the move towards a UHC Act, merging the proposed FHC Policy with SLeSHI. The TA attended the final budget presentation in parliament and gave key updates to the VP.

The VP’s increased understanding of these operational challenges significantly enhances his ability to make evidence-based decisions about co-financing, public-private partnerships (PPPs), and social protection health schemes such as FHC and SLeSHI.

Lessons learned this year and recommendations for the year ahead
This is the first annual review for this programme. The following action is recommended.

3. Given the tight Government fiscal space, the TA should work with stakeholders, including BHC, to prioritise the use of scarce resources to the health sector. Given reductions in global ODA, it is vital to assess and set out options for the prioritisation of funding to NMSA as part of the wider execution of health funds. Consideration should be given to adding the operational funds to NMSA to the lifesaving budget lines priority document, used by MoF

4. The experience of the budgeting process this year has clarified that an increase in budgets is within the influence of the TA (and the VP) but not within their control. The Programme Team should revisit Output Indicator 2.2 and revise accordingly to reflect this.

Output Title	Improved partner coordination in the health and nutrition sectors
Output number:		3	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	N/A – First AR

Indicators	Milestones for this review	Progress
Number of opportunities taken to respond to emerging health and nutrition issues	Four responses	Six responses. Potential doctors’ strike averted, non-payment to co-financing agreements, execution of funds to MoH and hospitals, Kush response, Caustic Soda burns to children, national malnutrition prevention campaign / A+ – Outputs met expectations.
National Nutrition Information Management System including key nutrition targets, designed and implemented	NIMS Designed with key nutrition targets	NIMS concept note developed, targets developed, and C4N have committed to support implementation. Not yet at implementation but progress is good considering TA picked this role up temporarily in Aug 2024. / B – Outputs moderately did not meet expectations
1. National Food Systems Coordinator recruited and inducted into the OVP team. / 2. Director of Sun recruited and inducted into the OVP team.	Coordinator and Director recruited	The TA took on the role of Acting Director for SUN and was able to influence the coordination and direction for nutrition. A food systems coordinator has now been recruited, and additional staff funded above this. A permanent Director of SUN has not yet been recruited – this is essential to sustain progress when the project ends. B – Outputs moderately did not meet expectations

At various points in the review period, the TA notified the OVP of emerging issues or was requested to support when emergencies were declared by Government. This included responses to Kush, a narcotic used by youth with negative social impacts. In Sierra Leone there is a very high rate of caustic soda burns incurred by children who accidentally touch or consume the chemical intended for soap production. The TA arranged for the VP to visit a hospital with a ward exclusively for children suffering caustic soda burns. Following this, the TA supported the Facilities Liaison Office to coordinate the design of a multisectoral intervention on Caustic Soda Prevention.

The TA coordinated desk research on social protection to inform the OVP and National Commission for Social Action (NaCSA) and supporting the planning for the Social Protection Interministerial Meeting, held in 2024. This presented an opportunity to discuss the lack of a robust system for identifying and targeting the most vulnerable with social protection mechanisms (an estimated 26% of the population are living in extreme poverty, some estimates state that as little as 0.1% of the population have access to SP).

Technical and systems support was given to the SUN secretariat, particularly on the establishment of a Nutrition Information Management System which tracks progress towards key nutrition indicators across Government Departments, and the identification of strategic areas to be prioritised by the SUN Secretariat and Movement. The TA developed concept notes, connected stakeholders and joined stakeholder meetings related to the development of this Nutrition Information System. As a result, Capacity 4 Nutrition (C4N) has committed funds for SUN to cover additional human resources and access to an off-the-shelf, customisable digital information system.

The OVP established the SUN & Food Systems Coordination Unit which brings together the SUN coordination work and the food systems coordination work led by the office. The new unit will work to centre nutrition targets and bring about a whole-of-government approach to food systems. The TA provided technical assistance to the SUN Secretariat and the Minister of State (who oversees SUN) to help support the team and to increase multisectoral coordination. The TA also supported the development of government commitments to be made at the Nutrition for Growth (N4G) meeting in 2025. Taking such a prominent role in Nutrition has created significant opportunity to influence in this area and the current weighting for this Output could be increased in the next year of the programme, to reflect its significance and value-add for the BHC and Saving Lives programme objectives.

Lessons learned this year and recommendations for the year ahead
5. The TA should focus adequate time on building capacity within the OVP. This is the final year of the project and adequate capacity must remain once the TA has left post. New capacity building goals should be written into the workplan, and the TA and the programme team should encourage the swift appointment of a substantive Director of SUN.
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
As this is a technical assistance programme, the key cost drivers for the programme continue to be advisory input and oversight from the Implementing Partner (IP), IRC. The TA is delivering to their terms of reference and the IP has delivered reports on time and to a good standard. Both TA and IP are readily available to discuss performance and key issues as they arise.

VfM performance compared to the original VfM proposition in the business case
The original business case envisaged a larger programme with multiple strands of TA to support Government in building capacity and delivering results. A decision was taken to focus the programme on health financing and nutrition outcomes. The key intervention for NMSA and the management of medicines was planned to be the rollout of a medical supplies management system. The sizeable costs required the commitment of multiple international donors and given the uncertainties in domestic and donor commitments, a decision was taken to delay investing UK funds pending more clarity of the wider funding landscape, The supply chain remains important but our focus has changed to pressing first for domestic execution of budgets, rather than data management and infrastructural improvements which would be overly reliant on international funding. The programme team will review the logical framework to ensure that it continues to measure results in line with plans and shifting political and fiscal realities.

Assessment of whether the programme continues to represent value for money
The programme continues to provide value for money as it is supporting the government to develop their health policies such as the consideration of Free Health Care into SLeSHI plans and to press for meeting domestic commitments to health programmes which by extension are UK and international donor development policy priorities. The TA has also assumed responsibility for leading the government’s response to and management of nutrition and food insecurity – malnutrition being a key underlying problem in tackling morbidity in Sierra Leone. The delivery of the programme through an accountable grant provided optimum value for money in economy and cost-effectiveness terms, with lower input costs, negating the need for mobilisation costs and having an immediate impact in delivering outputs.

The decision to delay support to the rollout of the medical supplies management system has not reduced the VfM in the programme as funds for this activity have been reduced accordingly. It is important now that the TA leads on influencing Government financing to provide a functioning health service to its population, particularly given uncertainties in international donor support going forwards.

E: RISK

Overview of risk management
The programme risk was assessed as Minor at business case approval and has remained so during the period under review. The programme team continues work with the implementing partner to manage risks across a range of risk categories.

Four out of the five categories have minimal risk appetites, except for Financial and Fiduciary risk which is at Cautious, given the challenging context and environment in which we work. The due diligence assessment completed for IRC included a thorough review of financial stability, internal checks and balances, risk management and mitigation measures, and fraud reporting processes.

This TA programme works closely with the Ministries of Health and Finance and other development partners to ensure policies are developed and implemented. The programme’s flexibility allowed adaption to increasing food insecurity and opportunities to influence in this area, helping Government to respond to a deteriorating food insecurity risk. Work to advocate for health financing continues to support BHC’s objectives in supporting Sierra Leone’s most vulnerable including pregnant adolescents and children under-five, helping to mitigate the contextual risk of reducing fiscal space for health.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The programme’s sole component is currently the TA to the Office of the Vice President (TAOVP) which is implemented by International Rescue Committee (IRC) through an Accountable Grant Arrangement (AGA). This was signed prior to work starting and the latest forecast indicates that the programme is slightly behind schedule in spending its two-year £454,928 budget which means savings have been made compared to the original budget. The programme team is comfortable with the current position as activities continue to be delivered, essentially delivering the same outputs for slightly less than anticipated. BHC have worked closely with the IRC finance team during the period under review, to improve financial forecasting and controls.

IRC have been very responsive to requests for further information and clarification whenever necessary. Reports are also discussed with BHC regularly and delivery is largely on track.

Quality and timeliness of narrative and financial reporting
The quality and timeliness of narrative reporting from IRC has been strong. IRC has submitted quarterly reports in line with the agreed schedule in the AGA. All three reports in 2024 were submitted on time. Reporting contains progress made in key areas of implementation, successes and challenges and plans for the next quarter. The process of reviewing, querying and responding to comments and clarification was clear and led to a better understanding of the issues, challenges and successes experienced by TA.

One challenge for IRC has been the forecasting of expenditure against actual monthly spend as quarterly/monthly forecasts of expenditure have tended to be slightly optimistic though the programme team has accounted for this in reporting forecasts. Payments are made quarterly, in arrears, in line with detailed expenditure reporting.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation and Evidence
This is a TA programme and currently we have one TA in the OVP so does not involve field monitoring. That said, we meet regularly with the TA and a range of interested and engaged stakeholders. We actively gather feedback and ask questions about progress and impact in these meetings. We can monitor the rate of execution of budgets to key areas of the health system, particularly in districts, and share information on execution to the TA. In meetings with the TA, we regularly seek clarity on issues/evidence that has materialised while we are visiting districts and health facilities. The adviser has demonstrated expertise, commitment and professionalism since the commencement of the support activities.

Learning
The key lesson learnt over this year is the extent of fiscal constraint on the Government of Sierra Leone and therefore the potential and limitations of TA focused on financing, regardless of the position of the TA within government. The execution of budgets is a huge challenge where ministers struggle to get funding released.]. We will use this final year to work with the TA to prioritise payments to those health activities which reach the most vulnerable such as the hospitals budget and to lobby for increased execution of funds to NMSA to distribute medicines to where they are most needed in hospitals and Community Health Centres. We will work with the TA, our Gov’t and donor partners and BHC colleagues to increase influencing and lobbying for more government ownership of finances, sharpened by the knowledge of our reducing commitments (as planned under SL3) and cemented by global ODA trends.

Date of last narrative financial report	Dec 2024	Date of last audited annual statement	Not yet due