## Annual Review

Title: Humanitarian Assistance, Recovery and Protection (HARP) Programme
Programme Value £ (full life): £500m [FY 24/25: £60m]		Review date: / 16/11/2025
Programme Code: 400176	AMP start date: 16/10/2024	AMP end date: 30/09/2029

Summary of Programme Performance
Year	Y1
Overall Output Score	A
Risk Rating

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006891.odt
DevTracker Link to results framework:	Uploaded – waiting for devtracker link

Contents
A Summary and Overview
B Theory of Change and Progress towards Outcomes
C Detailed Output Scoring
Output 1	Protection
Output 2	Emergency Response
Output 3	Early Recovery
Output 4	Enabling Environment
Output 5	Moldova response

D Value for Money
E Risk
F Programme Management: Delivery, Commercial and Financial performance

G Monitoring, evidence and learning

A. SUMMARY AND OVERVIEW

Description of programme

1. Our collective security is intrinsically linked to the outcome of the conflict in Ukraine. In addition to military support to win the war, the UK (with allies) will need to bolster Ukraine’s resilience to endure ongoing Russian attacks and flashpoints and manage increasing pressures on vulnerable communities and essential services. We judge that humanitarian need will endure, and in some scenarios increase, over the coming years.
2. This programme aims to meet Ukraine and Moldova’s immediate humanitarian assistance and protection needs and increase resilience through basic livelihoods support. In doing so, activities help prevent a deterioration in household coping capacities, while also saving lives and reducing harm. The interventions mitigate the longer-term risks to recovery (civilian protection, prolonged displacement, and lack of services and infrastructure to respond to shocks). This bolstering of Ukraine’s resilience directly contributes to the UK Foreign Secretary’s priorities for Euro Atlantic security. The programme consists of activities across four pillars – set out below. These activities are designed to complement one another and will be informed by cross-cutting principles: inclusion, safety, promotion of localisation and evidence/learning.

Pillars as outlined in the Business Case
3. This review assesses programme performance between October 2024 and June 2025. Total financial spend in this period was just over £69.7m. Programme delivery commenced in parallel with the final period of the Ukraine Humanitarian Response Programme (programme code 301497 - which has been reviewed separately). As such, the partners and activities evaluated here do not represent the full breadth of UK humanitarian assistance during this period.

4. This period covers FCDO’s winterisation response in FY 24/25 and protection/emergency response activities in the first quarter of FY 25/26 (pillars 1, 2 and 4). During this time the FCDO also began the mobilisation phase of two new delivery partners to deliver Protection and Early Recovery activities respectively. These will be assessed in future reviews once delivery begins. HARP Y1 spent its full allocation. A simplified overview of spend by partner is set out in the table below:
[note] FCDO’s winterisation response covered the period between October 2024 and March 2025 where funding was allocated towards activities (winter cash, NFI’s, WASH) to meet acute needs during the winter period.

Partner	HARP 24/25 actual spend	HARP 25/26 actual spend Q1 (GBP)
British Red Cross (including URCS and ACAPS)	0	819,475
HAVEN	0	3,484,603
XXXXXXX	XXXXXXX	XXXXXXX
OCHA UHF	33,400,000	0
UNHCR	11,360,738	0
Deployments	0	64,623
UNICEF Ukraine	5,000,000	0
Mercy Corps	5,139,658	2,704,259
UNICEF Moldova VAWC	871,340	0
WFP Moldova	1,725,000	0
UNFPA Moldova VAWC	1,149,240	500,000
UNFPA Moldova	0	1,250,000
Programme funded roles	67,217	0
TOTAL	60,921,953	8,822,960

Summary supporting narrative for the overall score in this review

5. The review was conducted by the programme team drawing on evidence from ongoing partner engagement, partner reporting, FCDO monitoring visits where these were possible, and third-party monitoring. Security restrictions have prevented the programme team from directly interviewing beneficiaries in Ukraine as part of this review, but this has been addressed by the third-party monitoring which was designed with these restrictions in mind.

6. The overall score awarded for this review period is A. This reflects that implementation is on track, with the majority of outputs meeting or exceeding expectations. Critically for a context which continues to be characterised by uncertainty, the programme has proven to meet emergency response and protection needs across Ukraine and respond effectively and quickly to heighted risks over the winter period. The FCDO set up two new Ukraine partnerships (UNHCR and UNICEF), increased support to OCHA’s winter reserve allocation and expanded cash assistance through Mercy Corps. The period has also seen strong examples of strengthened coordination between humanitarian actors and government systems (such as between UNICEF, Vodokanals and district heating utilities on infrastructure repair, and the signing of an MoU cementing the role of the Ukrainian Red Cross Society (URCS) with the State Emergency Services of Ukraine (SESU) in responding to emergencies). This demonstrates early efforts under this Business Case to promote localisation and a sustainable humanitarian exit strategy through investing in Ukrainian organisations to absorb future shocks.

Major lessons and recommendations for the year ahead

#	Recommendation	Owner	Deadline
1	Protection: onboarding and partner capacity building that enables a quick and effective set-up of the new Ukrainian-led consortium will be critical to managing risks and maximising opportunities under this Pillar in the second half of the FY.	PRO	October 2025
2	Emergency Response (cash/winter): to ensure beneficiaries receive assistance in time to mitigate the impacts of winter, winter cash distributions should take place in September and October. The timeliness of UNHCR winter cash should be measured effectively in their Post Distribution Monitoring surveys.	PRO	October 2025
3	Emergency Response (cash): drive efficiency and sustainability in the cash response by 1) influencing donors to fund MPCA over sectoral cash and in-kind support, 2) strengthening synergies between HARP and SPIRIT to strengthen the ability of the government social protection system to respond to shocks and, 3) funding parallel MPCA and winter cash through a consolidated number of actors and only when the government social protection system is unable to reach affected populations in a timely, adequate or inclusive manner. The FCDO should continue to use its role as co-chair of the Task Force on Social Protection and Humanitarian Cash Linkages to ensure the HNRP 2026 cash packages complement rather than duplicate social protection programmes.	Cash Lead	March 2026
4	Localisation: The PRO should develop a localisation scorecard which monitors qualitative and quantitative data across all local partners in the delivery chain. This should be developed as part of a wider MEL framework for HARP with data and results assessed as part of annual reviews.	HA cross-cutting Pillar Lead, PRO, and MEL officer	End of Q3
5	Coordination: the global humanitarian reset resulted in an in-country process changing how coordination was done and how the HNRP will be prioritised. It remains very internationally centric and the FCDO should do more to highlight local operational partnership coordination examples (such as HAVEN) and elevate Ukrainian partner voices who can help ensure decisions on resourcing reflect local needs and priorities (e.g. through Area-Based Coordination).	Lead Advisor	End of FY
6	Cross-cutting: The FCDO should invest more resource to ensure organisations are able to operate as safely as possible and should encourage all partners to adopt the “Duty of Care” package for local humanitarian responders in Ukraine in future budgets.	HA cross-cutting pillar Lead	End of FY
7	In Moldova, accelerating the shift towards the humanitarian - development nexus transition should be a key priority. This includes deepening systems strengthening work and advocating for the phased integration of Ukrainian refugees with Temporary Protection or other legal status into the Government of Moldova’s national systems and service provision. Simultaneously, we should reduce short-term emergency contributions, unless triggered by a major displacement or crisis, while investing in more robust crisis preparedness and contingency, with options to pivot and/or scale up emergency response interventions if required.	Moldova Project Lead	End of FY
8	Reflect on and test the assumptions in the evidence review to assess partnership decisions for FY 26/27XXXXXXXXXX. This must be done in alignment with the team vision, portfolio objectives, a streamlined response to cash, and a focus on localisation.	PRO + Lead Advisor	End of Q3
9	FCDO to facilitate a safeguarding learning network among direct and indirect partners to share practical approaches, challenges, and innovations related to PSEA. This could be done through periodic virtual meetings or a shared online platform, enabling partners to exchange experiences and strengthen safeguarding practices without significant resource investment.	Safeguarding Lead (BE Kyiv Humanitarian and Resilience team)	End of FY

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Ukraine ToC as outlined in the Business Case

7. The programme supports vulnerable populations affected by the war in Ukraine, ensuring their rights are protected and helping them transition from humanitarian aid. It strengthens Ukrainian and Moldovan institutions to respond inclusively to needs. The programme is structured across four outcomes (“pillars”):

Outcome 1: Protection - Improved safety and access to survivor-centred services. Strengthened legal frameworks and awareness of international humanitarian law.

Outcome 2: Emergency Response - Timely, relevant, and scalable humanitarian assistance that adapts to emerging needs.

Outcome 3: Early Recovery - Support for socio-economic recovery and resilient institutions aiding vulnerable groups.

Outcome 4: Locally Led Response - A safer, more inclusive, and evidence-based response led by local actors, shaped by affected communities.

The programme also enhances Moldova’s capacity to support Ukrainian refugees and vulnerable Moldovans affected by the war, designed around the following outcomes:

Outcome 1: Protection - Expanded access to child protection and GBV services for refugee and host communities.

Outcome 2: Basic Needs - Improved access to health, education, social cohesion, and emergency support (cash, food, NFIs).

Outcome 3: Protection Systems - Strengthened local and national systems to meet current needs and prepare for future shocks.

8. The Business Case was developed with the flexibility to adapt to the unpredictability of the war and associated changes in humanitarian/development needs. We have slightly adapted the HARP logframe structure since the Business Case, though output milestones for Y1 remained the same. In Ukraine, Outcome 1 (Protection) remains unchanged. Outcome 2 (Emergency Response) now emphasizes a flexible, needs-driven approach that can scale and adapt to shocks. Outcome 3 (Early Recovery) will be further developed to align with opportunities for scaling and the FCDO’s resilience programming. Outcome 4, previously focused on the enabling environment, now covers cross-cutting programme delivery - covering localisation, data use, staff safety, inclusion, accountability, and responsiveness. It also aims to strengthen processes that ensure affected populations influence decisions and support inclusive programming for marginalised groups, while addressing gaps in analysis and research.

9. Our pillar approach aims to retain flexibility to scale across thematic areas over the next five years. Funding to each pillar and outcome could be scaled up or scaled back as needs change. In the case of a ceasefire, the emergency response and protection pillars would still be required to reach newly accessible areas.

10. The Moldova outcomes on protection and provision of basic needs have been split between outcomes 1 and 2, outcome 3 has become the contributions to systems strengthening, a more agile response and preparedness to respond to future shock. These outputs include strengthening the Ministry of Labour and Social Protection (MLSP) capacity to deliver the RESTART reform process and the Governments social protection systems to respond to the needs of Ukrainian refugee children and families, as well as vulnerable Moldovans.

Do we have anything on where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

11. Delays in funding confirmation, reduced team capacity and the parallel delivery of UHRP meant mobilisation of planned partnerships under some pillars was delayed. Whilst outcome indicators have been recently agreed, a full evaluation of progress against all outcomes could not be measured within this Annual Review. However, strong output delivery so far and confidence in the theory of change indicate that HARP is on track to contribute to its intended outcomes. In the year ahead, the Protection and Early Recovery pillars will be fully mobilised and will involve a greater focus on Ukrainian-led models. The FCDO will continue to ensure a streamlined approach to cash, localisation and coordination in decision making related to which partners can most effectively progress the intended outcomes/impact under each pillar. Decision making on allocations and partnerships for FY 26/27 in a timely manner are needed to ensure partner proposals are approved, contracting can begin and annual baseline targets are set and monitored.

12. In the course of approving HARP it was agreed the programme will undergo a mid-term evaluation or review after the second year of implementation programme to inform the ongoing effectiveness of the programme and the final impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

13. The programme should continue based on the achievements to date, intended impact and alignment with the wider HstaR portfolio objectives. It began implementation during a volatile year of reduced humanitarian donor funding along with an increased level of Russian escalation, particularly of drone warfare. The core objectives remain vital to UK interests. Going forward, reduced funding will force humanitarian actors to prioritise lifesaving and harm-reduction interventions over longer-term resilience-focused interventions. The FCDO should use its dual mandate as a humanitarian and development donor to support coordination between humanitarian actors, government and development donors, including international financial institutions (IFIs), to develop sustainable solutions for those facing long-term displacement, economic hardship or with protracted needs. This will help prevent people backsliding into humanitarian need. Within the humanitarian sphere, there must be a deliberate effort to make the cash-based response more sustainable and better aligned with national social protection systems. Rationalisation of the response will also be necessary - a reduction in the number of operational actors is inevitable and the prioritization of local delivery partners and smaller delivery chains is crucial.

## C. DETAILED OUTPUT SCORING

Output Title	Protection of civilians
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Score
Output 1.1.1 # communities in priority areas report increased and safer access to services (HAVEN)	11	16	A+
Output 1.1.2 # of civilians (evacuees, IDPs etc) supported through comprehensive protection response in emergencies (evacuation, referral, case management, legal support (HAVEN)	N/A (target for FY 25/26: 5,203)	N/A	Activity intended to start until Q2
% of civilians in conflict-affected communities experiencing improved protection as a result SDAs action(s) (CIVIC/HAVEN)	0 (target for FY 25/26: 80%)	Results collected annually at end of FY	-
Output 1.2.3 # of people supported by Home Based Care services (URCS)	750*	652	A (target on track as expected)
Output 1.3.3 % of calls to the veterans hotline that are resolved through information shared directly or referred to a more appropriate service (URCS)	100%*	100%	A
Output 1.4.2 % military and military-adjacent groups, as well as frontline civilians, demonstrating improved attitudes towards IHL. (HAVEN)	30%	31%	A
Output 1.1.4 # of trained community, CSO and national actors demonstrating improved IHL capacity (URCS)	800*	138	A (target on track as expected)

*URCS only provide annual targets – Q1 progress will be judged by a qualitative assessment based on expected progress towards the annual target.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output description

14. The Protection of Civilians pillar aims to enhance the safety, dignity, and rights of conflict-affected populations in Ukraine by improving access to services, strengthening adherence to International Humanitarian Law (IHL), and building local protection capacity. This output was particularly urgent given the deteriorating protection environment in late 2024, marked by intensified hostilities, increased attacks on civilian infrastructure, and growing risks to humanitarian personnel. Civilians in front-line and newly contested areas faced heightened threats from shelling, drone strikes, and landmines, while displacement and trauma continued to strain community resilience. In this context, the output was highly relevant, addressing both immediate protection needs and longer-term capacity gaps.

15. Between April and June 2025, the output demonstrated strong early progress. Nonviolent Peaceforce (NP), under the HAVEN consortium, exceeded its milestone by supporting 16 communities - surpassing the target of 11- with protective presence and safe accommodation initiatives. The Ukrainian Red Cross Society (URCS) delivered in-home care to 652 vulnerable individuals and achieved a 100% resolution rate on its veterans’ hotline, reflecting exceptional responsiveness and coordination. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. While some components, such as CIVIC’s community engagement results and provision of protection services under the planned Protection consortium, are still in early stages, the output is broadly on track to meet end-of-programme targets. No significant underperformance has been observed to date, though timely onboarding of the new Protection consortium and continued funding will be critical to sustaining momentum and expanding reach through a range of services we are supporting in the second half of the year.

Review of indicators

URCS
16. Ukrainian Red Cross Society activity under this review falls between April-June 2025 before much of their wider activity had mobilised.
1.3.2 Between this period, the URCS’s Home Based Care programme delivered dignified, in-home support to 652 individuals across Kyiv oblast. The programme directly provided compassionate care and support to the most vulnerable, including elderly people, those with complex health conditions, and persons with disabilities – in turn easing the burden on overstretched public services whilst strengthening community resilience and promoting social inclusion. End of year targets are on track to be met.

1.3.3. URCS veterans’ hotline demonstrated exceptional effectiveness, with 100% of incoming calls successfully resolved, either through direct information provided by hotline staff or by referring callers to the appropriate departments within the Ministry of Veterans Affairs or other relevant institutions. This high resolution rate not only reflects the hotline’s strong coordination and responsiveness but also indicates a well-functioning referral system and a deep understanding of veterans’ needs. The performance during this period is already on track to exceed the programme’s end-of-project targets, highlighting its growing impact in ensuring that veterans receive timely, accurate, and comprehensive support.

1.4.4 As the recognised national society in Ukraine, URCS plays a central role in promoting and supporting adherence to International Humanitarian Law (IHL). 138 community members, civil society organisations, and national actors demonstrated improved capacity in applying IHL principles as a result of URCS-led training and awareness-raising events.

HAVEN
17. HAVEN activity under this review falls between April-June 2025

1.1.1: NP provided direct protective assistance to frontline communities between June and April. Support included providing protective presence at aid distributions, the rapid relocation of child PPE to Donetsk to support mandatory evacuations, and the re-launch of the Safe Accommodation programme in Kherson. These efforts meant NP over-achieved their target of 11 communities reporting safer access to services: in focus group discussions, 16 communities reported that they had experienced improved and more secure access to essential services through NP’s programming.

1.1.2: Output 1.1.2 measures civilians provided with comprehensive protection support by Nonviolent Peaceforce’s subgrantees. In April-June 2025, NP was undergoing to selection process for subgrantees, so no results are yet available. NP will provide subgrantees with comprehensive training and capacity strengthening in protection work, as well as important operational safety support such as PPE and first aid kits. Through this sub-granting process NP hope to strengthen local capacity to respond to community protection needs. Results will be reflected in the next annual review.

18. Under the HAVEN consortium CIVIC will work with conflict-affected communities and security and defence actors to improve their cooperation and strengthen civilian protection. During April-June 2025, CIVIC have engaged with communities across Chernihiv and Kharkiv, conducting Protection Needs Assessments to assess gaps to be addressed during the remainder of the financial year. Results of the assessments included community members identifying key skills they required to enhance their own safety and security, such as first aid training, information on evacuations, training on action during drone attacks and mine safety. The target and result of the indicator is zero as CIVIC will collect data on the results of their community engagement in March 2026 at the end of the current financial year. This will be reflected in the next annual review.

19. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Third Party Monitoring assessment – HAVEN

20. HAVEN is seen to be generally performing well and continuing to add value in providing and strengthening humanitarian assistance and civilian response structures. There are clear examples of relevant, inclusive and, in some cases, unique support being provided through HAVEN and it is adding significant value particularly in terms of the vital capacity building and coordination facilitation support it provides at a local level which empowers key actors and supports sustainability. There are also areas for improvement such as: ensuring a more structured needs assessment and inclusion analysis, which meaningfully involves end beneficiaries; further addressing gaps in knowledge on safeguarding, SEAH and humanitarian standards (including AAP and aid diversion) and the cultural barriers to non-reporting; and maintaining and, where feasible, scaling up staff well-being and anti-burn-out initiatives and access to MHPSS. There are opportunities to strengthen coordination and collaboration across HAVEN partners over coming years.

XXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
Describe any changes to this output during the past year, and any planned changes as a result of this review.

None

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

25. This is the first AR for this programme and the short delivery period of activities in this review mean that specific recommendations to partners are not yet finalised. During this period, significant efforts were undertaken to finalise the types of partnerships and activities required under each Pillar. In May 2025 the Humanitarian team undertook a comprehensive Evidence Review to decide the strategic direction of the humanitarian portfolio and to inform programme and budget decision making for the remainder of the financial year.

26. The Evidence Review concluded that Ukraine’s humanitarian crisis is fundamentally a protection crisis, deeply rooted in armed conflict and marked by violations of international human rights and humanitarian law. Protection needs remain extensive and urgent whereby millions face threats of forced displacement & IHL violations particularly in the frontline. The key recommendations under this pillar were for the FCDO to prioritise protection by supporting service delivery partners to complement GoU social services and specialist agencies. This can be achieved by: 1) concluding the selection of a specialist organisation to deliver case management, GBV, and legal aid with strong advocacy on access barriers; 2) continuing support to frontline responders and high-risk communities via the HAVEN consortium; XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
27. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Recommendation:
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
To meet the growing protection needs, it is recommended that protection services are implemented at scale and locally led. Timely onboarding of the new Protection consortium and continued funding will be critical to sustaining momentum and expanding reach in the second half of the year.

Owner: Lead Advisor and PRO. Deadline: End of Q3

Output Title	Provision of Emergency Response
Output number:		2	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Score
2.1.1 # of individuals/households receiving (1) multi-purpose cash assistance cash (2) winter cash (3) other sectoral cash. Break down by reach by partner by cash type and overall (Mercy Corps, UHF, UNHCR)	59,828	63,724	A+
2.1.2 % of recipients reporting satisfaction with the cash assistance received. Break down by partner (Mercy Corps and UNHCR)	90%	97%	A+
2.2.1 # of people reached with multi sectoral emergency response disaggregated by sex, disability, age, geography and ethnic minorities (Mercy Corps, URCS, UHF, UNHCR, UNICEF)	635,401	762,496	A
2.2.2 # of activations of Mercy Corps LIVES Rapid Response Mechanism	N/A (based on number of attacks)	39	A
2.2.3 # of people accessing a sufficient quantity and quality of water for drinking and domestic needs (UNICEF)	400,000	1,008,732	A+
2.2.4 # of people reached with UHF funding, disaggregated by sector**	(Annual Year 2024) 1.38m	1.48m	A
2.3.1 # of regions where the Emergency Response Team is involved in planned exercises of State Emergency Services of Ukraine units and other services involved in emergency response (URCS)	20	8***	A
2.3.2 % of UHF funding allocated to local partners	31% (2023)	58% (2024)	A+

*Mercy Corps and URCS results covered Q1 FY25/26
**figure for all donor funding – not attributed to the FCDO
***URCS only provide annual targets – Q1 progress will be judged by a qualitative assessment based on expected progress towards the annual target.

Output description

28. Amid escalating Russian drone attacks and bitterly cold winter months, this output aimed to deliver lifesaving emergency assistance to war-affected communities in Ukraine.

29. Russian drone strikes intensified during the reporting period, driving up the need for emergency aid. From July to November 2024, civilian casualties and infrastructure damage rose sharply, coinciding with frontline shifts and increased use of commercial drones. This trend continued into early 2025, with long-range drones contributing to record casualty figures in June, the highest in three years. Since May 2025, nearly a third of civilian casualties occurred in areas like Kyiv, compared to 15% in May 2024, highlighting a broader geographical spread of risk.

30. The increased use of long-range drones enabled Russia to systematically target Ukraine’s energy infrastructure. In 2024, this caused unprecedented damage to generation, transmission, and distribution systems. Essential services such as water, heating, sanitation, public health, and education were severely disrupted. Nationwide attacks in November 2024 undermined earlier repair efforts and confidence in the ability to meet winter energy demand declined. Local authorities worked to secure alternative backup power sources, although significant gaps remained. Due to the severity of the shortfall, there were significant risks of the government needing to introduce rolling blackouts. This potentially could have left millions without electricity during the coldest months.

31. In autumn 2024, the FCDO carried out a winter risk assessment to guide funding decisions and strengthen efforts to mitigate identified risks. This analysis considered risks communicated by local authorities and humanitarian actors. The findings were presented to BE Kyiv’s Country Board. From this analysis, three priority risks were identified for the winter response:

1. Supporting households with cash for utilities and energy
2. Strengthening protection services for vulnerable displaced people, especially older individuals and those with disabilities
3. Ensuring continued access to water, sanitation, energy, and heating in case of further attacks on critical infrastructure
32. Following the assessment, the FCDO committed to the following actions:
- Set up a new partnership with UNHCR to support vulnerable populations with energy and shelter needs
- Set up a new partnership with UNICEF to provide emergency WASH support along with decentralised water, sanitation, and heating solutions – including supporting government to repair and restore heating and water – together with strengthening contingency planning in light of the evolving conflict leading to increase and more widespread attacks on essential WASH and energy services.
- Supported the Ukraine Humanitarian Fund to assist local and international actors working on winter energy needs, cash assistance, evacuation, and protection
- Expanded cash assistance with Mercy Corps to deliver cash support to vulnerable families during winter

33. Review of indicators

2.1.1 During the reporting period, 63,724 individuals received cash assistance. This is broken down by partner and cash type (multi-purpose cash assistance (MPCA) and cash for winter) in the table below. This is in addition to the approximately 15,000 people reached with MPCA during the reporting period under UHRP funding. Going forward, the FCDO should increase the proportion of MPCA in its programming to reflect beneficiary preferences and as cost-effective method for reaching more people at scale. Consolidating MPCA and winter cash across a reduced number of actors would also drive greater cost efficiencies, allowing the FCDO to reach more people.

	Mercy Corps	UNHCR	UHF
MPCA	5,578*	7,500	4,142**
Winter cash	16,165	30,339
Total	21,743	37,839	4,142
Overall total	63,724

*results cover 1st April 2025 to 30th June 2025
** FCDO provided 19% of UHF’s budget. This figure 19% of UHF’s total reach for 2024

2.1.2 FCDO funding under HARP accounted for 12% of the total number of recipients of cash for winter for 2024/25 in Ukraine (15% including cash for winter funded under UHRP). However, only 53% of those included in the planned reach for winter cash under the 2024/25 Inter-Agency Winterisation Plan received winter cash due to funding shortages. Similarly, funding for MPCA rapidly decreased in 2025, meaning that as of 30th June 2025, only 45% of those initial targeted had received MPCA.

2.1.3 Recipients were targeted in accordance with the Cash Working Group targeting criteria for MPCA and the shelter cluster targeting criteria for Winter Cash. This combined geographical targeting to provide rapid MPCA for those residing in or recently displaced from areas of active conflict and socio-economic vulnerability targeting to provide Emergency MPCA to those facing economic hardship away from active hostilities or in long term displacement. Whilst rapid MPCA relies on the accuracy of government beneficiary lists, local downstream partners conducted door-to-door registration to ensure some of the most vulnerable and hard to reach households were included. In recognition of the fact that the criteria for Emergency MPCA does not take into account the compounding effects of intersectional vulnerabilities, the Cash Working Group targeting framework was updated in July 2025 to include a cumulative vulnerability scorecard. For winter cash, both UNHCR and Mercy Corps coordinated with local authorities and employed a needs-based targeting approach prioritising rural households unable to afford heating materials who had had not previously received support from other organisations or government entities.

** FCDO provided 19% of UHF’s budget. This figure 19% of UHF’s total reach for 2024

2.1.2 On average 97% of recipients reported satisfaction with the cash assistance received. During the reporting period, Mercy Corps reported that 97% and 98% of recipients reported satisfaction with MPCA and winter cash assistance respectively, overachieving their target by 8%. UNHCR’s Ukraine winter cash post-distribution monitoring report for 2024-25 reported that 96% of households were satisfied or very satisfied with the assistance and 83% reported an overall improvement in living conditions

2.2.1 762,496 people were reached with multi sectoral emergency response through several key partnerships as detailed in the table below.

Sector	Mercy** Corps	URCS**	UNHCR	UNICEF	UHF***
Protection	2,716	1854*	44,409		119,700
Shelter & NFIs	3,225				40,850
WASH	2,413			39,346	94,430
Food assistance	23				2,926
Livelihood
MHPSS	3,180
Education					9,728
Health					9,595
Cross-cutting - heating				388,101
Total	11,557	1,854	44,409	427,447	277,229

*Cannot be disaggregated
** Results from 1st April 2025 – 30th June 2025
*** FCDO provided 19% of UHF’s budget. This figure 19% of UHF’s total reach for 2024

2.2.2 Mercy Corps’ LIVES Rapid Response Mechanism (RRM) was activated 39 times between 1st April 2025 – 30th June 2025. The RRM enabled Mercy Corps to conduct a rapid assessment of needs following the aftermath of attacks and provide emergency assistance through two local partners.

2.2.3 Through contributing to UNICEF’s 2024/25 WASH programme, 1,008,732 people accessed a sufficient quantity and quality of water for drinking and domestic needs. This significant overachievement of the target was largely due to the implementation of several projects in densely populated urban areas such as Kryvyi Rih and Dnipro. This 4-month programme was established in light of the revised winter response plan highlighting the critical WASH needs across the response.
2.2.4 In 2024, the UK had the second highest contribution to the UHF ($43.7m) among donors. This represented 19% of the total donor contributions ($232m). UHF ran three allocations in 2024 and funded 58 partners. OCHA’s Winter Response Reserve Allocation provided nearly half of its funding to local organisations directly including small CSOs who could access hard to reach areas. 60% of the targeted population were women and girls, and disability inclusion, benefiting 4,400 people with disabilities, including 800 children, as well as protection mainstreaming and accountability in all partners’ programming. The UHF will continue to adapt its tools and processes to increase efficiency and ensure that the most severe needs of populations are met in a timely fashion. Current pilots to decentralise allocation decision making to local actors and communities are underway and lessons learned will be used to improve approaches in 2025/26.
2.3.1 In May 2025, URCS and State Emergency Services of Ukraine (SESU) signed an addendum to the memorandum that outlined the following commitments:
- Establishing a clear procedure for volunteer engagement and coordination during emergencies.
- Developing a briefing programme, including occupational safety.
- Training volunteers in first aid and explosive ordnance recognition.
- Providing volunteers with necessary equipment and protective gear.
- Enhancing cooperation with volunteer organisations, among other measures.
Across 8 regions, URCS’ Emergency Response Team were involved in planned exercises of SESU and other services involved in emergency response. During the reporting period URCS and SESU continued to respond to shocks in coordination with each other. In June, admin the sharp escalation of shelling, URCS received a request for further support from SESU.

2.3.2 UHF’s total funding to NNGOs in 2024 was $94.7m (58% of all funding allocated). Whilst UHF does not set targets for funding to NNGOs it aims to increase funding to NNGOs year on year. So far in 2025 UHF has allocated 66% of funds to NNGOs. The UHF has also been granted permission by HQ to expand its pilot for simplified capacity assessment for national actors to an additional 45 local CSOs. UHF hope this simplified tool can be adopted by other funds.

Assessment of performance
Emergency Response
34. Through this output, FCDO partners delivered a comprehensive, multi-sectoral response that effectively reached the most vulnerable populations in a highly complex and volatile operational environment. Collaboration with local organisations enhanced the relevance and timeliness of aid delivery, leveraging their deep understanding of community needs and their access to hard-to-reach communities. Partners consistently maintained support and demonstrated strong operational capacity, scaling up emergency interventions when needed. They responded with agility to surging needs during winter and in the aftermath of aerial attacks.
35. The programme demonstrated strong adaptability during the review period, leveraging a combination of robust data sources and flexible response mechanisms to address evolving needs across Ukraine. Mercy Corps’ Rapid Response Mechanism enabled the timely distribution of emergency aid, both cash and in-kind, in response to sudden shocks and emerging needs. Continued provision of un- and softly- earmarked funding to UN organisations including OCHA/UHF, XXXXXX and UNICEF ensured the programme retained the ability to reallocate funds to meet new and emerging needs. In February 2025 the programme allocated another £1.3m as a top up to UNHCR mostly to cover MPCA and shelter/house repairs.
Third part monitoring assessment – Mercy Corps:
36. Monitoring of the LIVES 3.0 programme demonstrated Mercy Corps’ strong commitment to relevance, inclusiveness, and accountability. While Mercy Corps adapts well to complex contexts, challenges persist due to geographic targeting limits, shifting frontlines, and unmet needs—especially for evacuees, and families of injured breadwinners. Seasonal and accessibility issues further strained aid delivery. Mercy Corps’ accountability mechanisms, including its independent feedback system (CARM), support responsiveness but faced communication and capacity challenges. Operational hurdles like staff burnout, bureaucratic delays, and legal barriers also affected delivery. Recommendations to the FCDO include extending funding timelines, investing in partner staff wellbeing, and adjusting donor deadlines to allow for more participatory input in design.
Cash
37. Overall, FCDO partners reached 46,504 people with winter-specific cash support and 83,755 people with in-kind assistance. Two-thirds of UNHCR winter cash recipients who responded to the third-party monitoring CATI survey and 68% of Mercy Corps winter cash recipients reported that the amount received was sufficient to support their household in covering basic needs related to winter, with 88% reporting using the assistance to purchase solid fuel, and 12% reporting use on other essential expenses such as utilities, food, and medication. 95% of Mercy Corps winter cash recipients received the cash at the time they needed it most.
38. The overall proportion of in-kind and sectoral cash in the humanitarian response continued to increase during the reporting period. This is despite global evidence and feedback from affected populations in Ukraine confirming that MPCA is the most effective modality for enabling people to meet diverse needs with dignity, flexibility, and efficiency. The FCDO therefore prioritised MPCA and winter cash as a modality, reaching 17,220 and 46,504 people respectively, through partnerships with Mercy Corps, UNHCR and UHF.
39. Throughout the reporting period, the FCDO explored the opportunities and challenges for localisation of the cash response, including delivery via national government systems and national NGOs. This included co-chairing the PereHID Initiative, a joint government of Ukraine, donor, and NGO supported initiative to support the transition of caseloads from humanitarian cash assistance to nationally-led shock-responsive social protection. This initiative was funded under UHRP and has been evaluated under the UHRP PCR and ARs.
40. FCDO also recognised the inherent tension between prioritising both localisation and MPCA (with MPCA traditionally dominated by international actors) and commissioned a study under the STAAR facility (a centrally managed programme partially funded under UHRP) to understand the barriers and opportunities for greater national NGO leadership in Ukraine. FCDO invested significant capacity in ensuring the study was locally-led and drew on global best practice, such as the Passing the Buck studies. Key recommendations from the study include increasing the role of national actors in cash coordination, ensuring national actors shape programme design as well as delivery and allowing 15% flexibility in targeting criteria to allow national actors to meet needs they encounter on the ground.
[note] The Share Trust, Passing the Buck: The Economics of Localizing Aid in Ukraine, 2024. The Share Trust, Passing the Buck: The Economics of Localizing International Assistance, 2022.
41. This was complemented by programmatic efforts to strengthen the capacity of local organisations to deliver cash assistance as well as in kind, via the Mercy Corp partnership. Local organisations delivered cash to 21,743 people, which ensured the assistance was relevant and responsive to community needs, enabled rapid delivery following sudden shocks, and supported sustainability by investing in systems that will outlast international support.
42. In line with evidence review recommendations from the PereHID Initiative, FCDO partners have been leveraging elements of the social protection system to support greater alignment, including using government registries for targeting. Whilst this is promising practice, the need to cleanse local authority data also impacted on the timeliness of winter cash delivery. This was particularly the case for URCS, who were funded under UHRP for winter cash delivery, whose beneficiaries received disbursements between November – January. Ground Truth Solutions cash user journey reports highlight that this time period is too late to mitigate the impacts of the cold season and that fuel prices are highest at this time. To ensure beneficiaries receive assistance in time to mitigate the impacts of winter, future winter cash distributions should aim to take place in September and October. The timeliness of UNHCR winter cash should be measured effectively in their Post Distribution Monitoring surveys.
Third party monitoring assessment - UNHCR
43. UNHCR’s shelter and cash assistance programmes in Ukraine were evaluated as being well-targeted and inclusive, focusing on vulnerable groups like older women, people with disabilities, and those with chronic illnesses. The agency has shown strong adaptability and responsiveness to changing needs, through outreach to marginalized groups such as Roma, stateless persons, in cash and shelter programming needs improvement. Protection efforts are supported by multi-disciplinary teams and referral systems, but usage of data and additional training could be enhanced to increase effectiveness. UNHCR maintains accountability through monitoring and feedback mechanisms, though data disaggregation and dissemination of CFMs (Complaint and Feedback Mechanisms) could be strengthened. Coordination with local authorities is effective, and localisation practices are strong. Shelter support has significantly contributed to stability and recovery, though efficiency could improve with earlier winterisation funding and expanded housing efforts. Key recommendations for improving humanitarian programming in Ukraine include earlier disbursement of winterisation funding by the FCDO to enhance seasonal preparedness, continued support for seconded UNHCR experts aiding access to adequate accommodation and care services for older people in displacement, and better alignment between shelter and economic development initiatives. UNHCR is advised to continue to strengthen protection mainstreaming through mandatory training, enhance the use of monitoring data—especially Post-Distribution Monitoring (PDM)—and continue to support GBV risk mitigation and accessibility in collective sites. Collecting and applying disaggregated data (SADDD) and innovating context-specific solutions like modular housing are also key to increasing programme effectiveness and inclusivity.
WASH
44. Ukraine’s water, sanitation, and heating systems have long required modernisation, with significant rehabilitation needs already evident prior to the full-scale invasion. Since 2022, ongoing hostilities have further impacted WASH and energy infrastructure, placing communities near the frontline at heightened risk of disrupted access to essential services such as clean water and heating.
45. During the reporting period, UNICEF utilised its strong partnerships with local authorities and heating utilities, as well as in coordination with the WASH Cluster and its District Heating Working Group. They identified high priority investments to ensure the continued availability of heating and water for residential populations and social institutions. These efforts ensured 388,101 people have benefited from restored or maintained heating services, while 1,008,732 individuals have gained access to sufficient quantities of safe water for drinking and domestic use. WASH interventions are uniquely inclusive. Water, sewerage, and heating networks typically serve entire towns, ensuring broad coverage across all demographic groups. While there are exceptions, particularly during times of displacement or for those living in temporary shelters, coverage remains extensive. For instance, without district heating, elderly residents in high-rise buildings face severe hardship during winter. For families living in more remote, frontline areas, 39,346 people benefitted from the delivery of hygiene supplies, compensating for constrained market access and difficult living conditions in these areas, where heating systems do not reach and water systems are frequently disrupted.
Third Party Monitoring assessment - UNICEF
46. UNICEF’s “Ukraine Winter Response for Vulnerable Families with Children” project (Nov 2024–Mar 2025) successfully addressed urgent heating and WASH needs in conflict-affected regions, benefiting nearly 1.5 million people. Implemented through local partnerships and aligned with humanitarian goals, the project demonstrated strong relevance, inclusiveness, and efficiency. It adapted to diverse local contexts, supported displaced populations, and integrated protection standards, though challenges remained in partner capacity, data collection, and awareness of reporting mechanisms. UNICEF’s localisation approach empowered local utilities and partners to lead implementation. Recommendations include earlier and longer funding cycles, a dual-track humanitarian-development strategy, improved monitoring practices, and stronger visibility of feedback systems and donor risk protocols.
Recommendations

Streamlining of the cash response: the FCDO should continue to work collaboratively with other donors, including convening donors to implement the Common Donor Approach to ensure that fewer cash organisations operate at scale and that donors fund MPCA over sectoral cash.

The FCDO should adopt a blended approach combining parallel MPCA through door-to-door registration with cash assistance aligned to the social protection system, enabling last-mile delivery to isolated communities while ensuring cost-effective scale. Continued collaboration with agile, locally embedded actors and stronger links to protection case management will help reach those outside the system and support government efforts to remove access barriers.

Owner: Cash Lead. Deadline: End of FY
The FCDO should invest more resource to ensure organisations are able to operate as safely as possible and should encourage all partners to adopt the “Duty of Care” package for local humanitarian responders in Ukraine in future budgets.

Owner: HA Cross-cutting pillar lead. Deadline: End of FY

Coordination and localisation – the global humanitarian reset resulted in in-country processes changing how coordination was done and how the HNRP will be prioritised. It remains very internationally centric and the FCDO should continue to highlight local operational partnership examples (such as HAVEN) and elevate Ukrainian partner voices who can help inform decisions on resourcing (e.g. through Area-Based Coordination).

Owner: Lead HA. Deadline: End of Q3
- Shelter and CCM: As per the evidence review, it is recommended that the FCDO includes shelter in its portfolio through support to cross-sector partners: specifically, through UNHCR (protection, CCCM, cash, shelter), XXXXXXXXXXXXXXXXXXX, and the UHF (48% of 2024 funding was on shelter). It is recommended that the FCDO prioritise support to Collective Sites by continuing to allocate resources to UNHCR – a key area of focus should be prioritisation of disability friendly infrastructure given high proportion of people with disabilities (PwD) and huge gaps in this area.
- In addition, as per the evidence review, health is a priority need for the population of concern in Ukraine. However, as health is one of the clusters with greater levels of funding compared to others, the FCDO should, if resources allow, support activities in this sector as part of multi-sector projects. This would mean working with XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXURCS (mobile health teams and home-based care), and through the UN OCHA Ukraine Humanitarian Fund, which is directed by the health cluster who can monitor quality and adherence to strategies and standards.

  Owner: Lead HA. Deadline: End of Q3.

Output Title	Recovery and Resilience
Output number:		3	Output Score:	N/A
Impact weighting (%):		0%	Weighting revised since last AR?	N/A

Partner mobilisation phase
47. During this review period work was mobilised but not year delivered under the recovery and resilience building output. Delivery and indicators will be assessed in future annual reviews. Mobilisation under this output during the first year of HARP centred around a call for proposals for the joint humanitarian-development livelihoods and economic resilience project.

48. A competitive, open call for proposals ran in November-December of 2024. The call was open to all non-profit organisations, although consortium bids were encouraged and private organisations were welcome to apply as part of a non-profit led consortium. Eight applications were received, and the Building Livelihoods and Opportunities for Optimised Markets (BLOOM) proposal, submitted by a consortium led by Mercy Corps with members Right to Protection, International Rescue Committee and SwissContact/Springfield was selected as the successful bid. This application was chosen due to its strong response to the published statement of requirements for the call, and clear capacity and expertise across consortium members to address a project combining livelihoods, private finance and protection. Additionally, the project proposal had a clear value for money approach and a comprehensive MEL plan – both important given the pilot-approach of the project. The first year of delivery will focus on humanitarian grants and research into barriers to access to private finance. It is expected that following this research and design of interventions to address these barriers, the economic resilience activities funded by TIGER will come live in the 2026/27 financial year.

Evidence
49. Despite the fact that livelihoods is not identified as one of the top four priorities in the Evidence Review, it is identified as a major need in the HNRP. Un- or under-employment affects a huge number of people across Ukraine (58% of households, according to the MSNA). Without a sustainable income, people are reliant on humanitarian assistance or social protection. Widespread employment-generation is a long-term challenge, largely dependent on stability. However, cost-effective options for helping poorer households to achieve economic independence do exist. If done well, these can form a platform for wider regeneration when the situation stabilises. Our evidence review recommended that the FCDO proceed with the planned mobilisation proposals for these reasons. Our delivery will test whether results can be delivered at scale in the Ukraine context and opportunity costs will be kept under review.

Output Title	Locally led, safer, more informed, inclusive and evidence driven response
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

*Covers 2nd May 2025 to 30th June 2025
Indicator(s)	Milestone(s) for this review	Progress	Score
4.1.1 HARP programme: % of HARP programme funding supporting Ukrainian civil society response (break down £ % disbursed to partners directly.	N/A	Scorecard being developed	-
4.1.2 # of NGOs, local authorities, and other stakeholders engaged in RCC coordination mechanisms (HAVEN)	180	182	A
4.1.4 Duty of Care: % or # of Local actors report that they feel they have the tools and equipment to operate safely (HAVEN)	N/A	Results not available until Q2	-
4.2.1 # of analytical products delivered which support strategic discussions in international coordination mechanisms (e.g. Access working group, HCT). (ACAPS)*	2	2**	A
4.2.2 # of IMPACT/ REACH citations in key humanitarian planning documents (such as HRP/HNO) (IMPACT)	N/A	In progress	-

**The FCDO accounted for 60% of the program's overall budget

Briefly describe the output’s activities and provide supporting narrative for the score.

HAVEN
50. Between April and June 2025, RCC delivered coordination of support to communities across Kharkivska, Donetska, Zaporizka, and Dnipropetrovska oblasts, with 182 (compared to a target of 180 in quarter 1 of financial year 25/26) NGOs, local authorities and stakeholders engaged in their coordination mechanisms. RCC worked to process nearly 600 requests for both information and aid during the quarter, working with the 82 stakeholders to coordinate over 3,400 humanitarian missions across the four oblasts. RCC mobilised partners to deliver life-saving assistance including food, hygiene items, non-food items, and medical supplies.

IMPACT
51. IMPACT continue with their data collection and analysis work to support the enabling environment of the Humanitarian response. Their Humanitarian Situation Monitoring assessments remain the most reliable source for tracking humanitarian needs in frontline areas. We rely on these documents to support our understanding of changing trends, and they are frequently referenced by stakeholders. IMPACT published their annual Cold Spot Analysis in June which is a core analytical document referenced by multiple humanitarian organisation for humanitarian planning purposes and provides the foundational analysis behind the geographic prioritisation of the Winter Response Plan – it identifies raions most at risk over winter. In June 2025, they commenced the process for this years Multi-Sector Needs Analysis - the primary data set used to support the analysis of people in need and severity of need for the Humanitarian Needs and Response Plan process (due autumn 2025). Further updates will be provided in the next annual review.

ACAPS
52. Funding to ACAPS in this period covers a two month period (May and June 2025) during which ACAPS produced two analytical reports. They remain on track to meet their end of year targets. The first covers humanitarian access for people with disabilities and examines the barriers different groups face in accessing assistance based on an identified information gap within the response. This has been presented across several coordination fora. The second report was the latest edition of ACAPS humanitarian access overview, which is issued quarterly. This analysis typically draws on a range of sources and is done in consultation with the Access Working Group therefore feeding into broader discussions on access within the response. Several local organisations reported using this analysis to cross check their own operational planning. ACAPS also continued to update and maintain their four core data sets, that monitor key humanitarian trends – which contribute directly to analysis reports and continue to act as a useful tool to monitor changes over time. With FCDO instruction ACAPS discontinued their severity index as this was assessed as no longer meeting the needs of the response (available data sources was not sufficiently granular). In response to FCDO feedback ACAPS continue to prioritise dissemination of their work in order to better support their audience apply analysis to action.

Localisation
53. The Fifth Humanitarian Senior Officials Meeting (SOM) on Ukraine took place in Brussels on January 28, 2025, bringing together over 100 representatives from the Ukrainian government, EU institutions, international organizations, and NGOs. There was a strong emphasis on localisation, with calls to increase direct funding to local NGOs, promote equitable partnerships, and implement Duty of Care (DoC) measures for frontline staff (e.g., insurance, psychosocial support, PPE). Following the SOM, Mercy Corps continued to implement the DoC standards promoted by the Humanitarian NGO Platform in Ukraine and LIVES partners have now, with FCDO approval, integrated costs for items such as insurance, individual first-aid kit training, psychological support for staff, and secure data storage into their project budgets.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

54. There are a limited number of indicators tracked during this review period and activity that has been evaluated has been successful.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Over the coming year, Output 4 has been re-designed to capture a range of cross-cutting areas of importance to the programme. Outcome indicators in the HARP logframe related to products/reports (from ACAPS and IMPACT) will now measure how these are used by stakeholders, recognising that tracking this is often based on anecdotal / qualitative type statements from users of analysis. Output indicators will measure our progress on localisation, safety of programme partners, strength of local coordination mechanisms, evidence of action to strengthen AAP, and the inclusion of marginalised groups within programme activity.

Owner: HA cross-cutting Pillar Lead, PRO, and MEL officer. Deadline: End of Q3

As a result of wanting to strengthen localisation meaningful data needs to be collected across partners. It is recommended that the FCDO develop a localisation scorecard which monitors feedback and data across all FCDO funded local partners in the delivery chain. The aim of this is to measure how many partners we are directly funding and how we can assist to strengthen efforts on areas such as duty of care, GESI, safeguarding and other areas outlined in the Partnership Principles developed by the FCDO Ukraine.

Owner: HA cross-cutting Pillar Lead, PRO, and MEL officer. Deadline: End of Q3

The increased use of drones has significantly altered the humanitarian operating environment. Short-range drones now reach up to 30 kilometres from the frontline. This affects areas previously considered safe for aid delivery and evacuation. Humanitarian organisations are increasingly forced to suspend or halt operations. This is particularly evident in Donetsk and Kherson. Multiple reports document drone targeting of aid facilities and vehicles. Local organisations, which are most active near the frontline, are especially affected. The FCDO should encourage all partners to adopt the “Duty of Care” package for local humanitarian responders in Ukraine in future budgets. This package was developed by Swiss Agency for Development and Cooperation, the Humanitarian NGO Platform in Ukraine, and the Alliance of Ukrainian Civil Society organisations. At the time of writing, the FCDO is engaging with humanitarian partners on new drone monitoring and analysis tools.
[note] Humanitarian NGO Platform in Ukraine. (2025, February 4). Duty of care package for local humanitarian responders in Ukraine. NGO Platform Ukraine. https://ngoplatformua.org/en/publications/duty-of-care-package-for-local-humanitarian-responders-in-ukraine/

Owner: HA cross-cutting Pillar Lead. Deadline: End of FY

Output Title	Moldova – Moldovan institutions (Government and civil society) are shock-responsive and better able to meet the essential protection and assistance needs of Ukrainian refugees and vulnerable Moldovan communities affected by the full-scale Russian invasion of Ukraine.
Output number:		5	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Score
Number of people receiving assistance unconditionally or conditionally (complementary with UNICEF, FAO, WHO) - WFP	34,245 / *Estimate of FCDO attributable target is 8,904, based on WFP reporting of FCDO attributable % of results achieved	67,693 / *FCDO accounted for 26% of the program's overall budget, benefiting 17,600 beneficiaries (10,513 households).	A
Percentage of beneficiaries reporting they were provided with accessible information about WFP programmes, including PSEA – WFP	80%	89%	A
Number of vulnerable children on the Left Bank who received NFI kits to ensure their protection in the face of the energy crisis – UNICEF	2,000	2,000	A
Number of GBV service delivery points supported by UNFPA	6	6	A
Number of young beneficiaries covered with youth-friendly health services, including SRH care	800 (24/25) / 3,000 (25/26)	783 (24/25) / 577 (25/26 Q1)	A (Project on track to meet target in 25/26)
Number of young people covered with youth friendly health information and education activities	1,500 (24/25) / 6,000 (25/26)	2,400 (24/25) / 1,917 (25/26 Q1)	A
Number of persons benefitted from active ageing programmes at local level – UNFPA	1,000 (24/25) / 200 (25/26)	1,702 (24/25) / 180 (25/26 Q1)	A+
Number of GBV prevention curricula targeting boys developed - VAWC	1	1	A
Number of Ukrainian and Moldovan girls and women reached by UNICEF virtual safe space	10,000	10,013	A
Number of individuals reached with GBV prevention initiatives and multisectoral GBV response services - UNFPA	20,000+7,340=27,340 (FY 25/26)	5,654+3,846=9,500 (reached FY 25/26 Q1)	A

Briefly describe the output’s activities and provide supporting narrative for the score.

55. During this review period, interventions in Moldova have been delivered in line with the overall HARP programme strategy, delivering a response tailored to the refugee hosting context. The programme has recognised and responded to the needs of Ukrainian refugees in Moldova alongside those of vulnerable Moldovans, who are facing entrenched poverty and recurrent shocks linked to the war in neighbouring Ukraine. A needs-based targeting approach has ensured tailored provision to the elderly, people with disabilities, women and children experiencing and at risk of violence, and children living in Transnistrian region. Priority winter needs have been accounted for. Interventions have been delivered in partnership with the Government of Moldova, with the Ministry of Labour and Social Protection (MLSP) a primary partner for all the UK’s UN humanitarian agency partners.

Give an overview of what the output has achieved, and whether it is on track or off track to hit end-of-programme targets.

WFP

56. WFP worked under the leadership of the MLSP to deliver Cash to Vulnerable Moldovans (CVM) to elderly pensioners and households of children with disabilities. This activity responded to the impacts of compounding economic shocks through the winter period resulting from the conflict in Ukraine. MLSP leadership ensured alignment with the government’s social protection benchmarks, with the provision of CVM sitting within the MLSP’s RESTART reform (ongoing MLSP reform of the national social protection system). It is judged that this intervention successfully reached a highly vulnerable group of Moldovan beneficiaries at the most financially difficult period of the year. The programme also helped instigate policy changes to reclassify the targeted group of pensioners, enabling them to access the minimum pension rate from May 2025. Learnings from this intervention have also supported in building the MLSP’s capacity for delivery of shock-responsive emergency cash transfers.

57. Delivery through MLSP systems however did present challenges, particularly in beneficiary communication. WFP communication to a majority of the caseload (including on Complaint and Feedback Mechanisms) was limited to MLSP public outreach. Strengthened accountability efforts from WFP would have improved confidence in the process monitoring and impacts of the cash provision. Reliance on MLSP lists also posed a risk that marginalised groups such as Roma communities, who face higher rates of exclusion from national social protection assistance in Moldova, may not have benefitted from WFP support.

UNICEF-UNFPA VAWC

58. The joint UNICEF-UNFPA ‘Breaking the Cycle’ project was initiated in this review period, facilitating a collaborative approach between the two agencies to end violence against girls, boys, and women across refugee and host communities. Whilst the research pieces remain in the early stages due to additional time needed to reflect the complexity of ambition (continuing under FY 25/26 funding), the Boys on the Move pilot garnered constructive learnings to adapt the methodology to the context of Moldova. Community based interventions are judged to have been effective at engaging a broad range of participants in activities around Technology Facilitated GBV (TFGBV), including through flash mobs, trainings and workshops. The project builds on UNICEF and UNFPA’s bilateral relationships with the MLSP to reach the social workforce with appropriate training sessions. A more detailed assessment of this intervention will be feasible in the next reporting period.

UNICEF Transnistria

59. UNICEF mobilised to distribute winter NFI kits to vulnerable children in response to the winter energy crisis in Transnistrian region. An FCDO monitoring visit confirmed the severity of vulnerabilities of the targeted children and the inadequacy of existing social service provision. The UK’s support through winter kits was deemed to be appropriate and necessary, but the intervention highlighted the operational complexities in distributing to this region. Data on vulnerable children was scarce, and as a result collation for targeting was time-consuming. In addition, not all goods were available for procurement on the left bank, necessitating UNICEF and the partner to navigate split procurement, transportation, and customs processes. As a result, the distribution of some kits was late. The activity did however provide a valuable entry point to reaching the most vulnerable children on the left bank and highlighted the criticality of additional support in the likely case of another winter energy crisis.

UNFPA

60. UNFPA delivered interventions designed to reach those individuals most likely to be excluded from standardised support, through expanding mobile services, delivering shelter-based care, and adopting trauma informed outreach. Provision of accessibility-adapted vehicles for outreach and transportation for GBV survivors and individuals at risk, for example, demonstrates commitment to last mile support for the most vulnerable. UNFPA has been responsive to emerging trends in needs, recognising escalating cross-border GBV risks and taking immediate actions to establish a new Crisis Centre. Monitoring visits have validated the quality of shelter rehabilitations. The attendance of President Maia Sandu at the opening ceremony demonstrated the strength of the Government of Moldova partnership and buy-in for UNFPA’s efforts.

61. Safe Spaces continued to provide a valued service for women and girls, with Focus Group Discussions (FGD) confirming users’ experiences in accessing reliable information, emotional support, social connections, and a safe environment. UNFPA took on board FCDO advice, garnering additional input from FGD participants on safeguarding. These discussions verified users’ experiences of positive Safe Space staff conduct and confirmed participant confidence in available reporting mechanisms. FCDO monitoring visits to Safe Spaces found warm, supportive environments delivering the requisite services and fostering a valuable sense of community support for vulnerable refugee women.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

62. In January 2025, following global developments in the provision of humanitarian funding, UNFPA made an urgent request to reallocate budget within the UK-funded intervention. The FCDO approved a reallocation of funding to ensure coverage of static and mobile safe space services (including cash assistance for GBV case management) and GBV service provision (including service centres providing lifesaving GBV services, GBV shelters, and at home GBV prevention and response to people with limited mobility). Funding to lower priority technical assistance and health system strengthening interventions was reduced. This was approved in line with the FCDO’s commitment to maintaining life-saving humanitarian assistance to the most vulnerable – namely those facing, or at risk of facing, GBV.

63. In February 2025, as the energy crisis in Transnistrian region worsened, the FCDO approved a funding top-up to UNICEF for the provision of winter NFI kits to vulnerable children on the left bank. This was identified as a critical intervention targeting Ukrainian refugee children and children in care who had vastly insufficient access to heating and hot water over the coldest months. The kits provided warm clothes, slippers, hot water bottles, flasks, and other essential supplies to the targeted groups.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

64. Across the response in Moldova, efforts have continued towards the integration of refugees with Temporary Protection or other legal status into the Government of Moldova’s national systems and service provisions. UK funding has successfully supported the provision of humanitarian assistance integrated into pre-existing national systems, with the active participation and leadership of the Ministry of Labour and Social Protection (MLSP). The Magnolia GBV Shelter for example, has been rehabilitated by UNFPA with UK support, and now sits under the responsibility of the MLSP in delivering GBV Shelter provision to Ukrainian refugee and Moldovan victims of violence. This approach both ensures the sustainability of the intervention through embedding it within the national system, whilst actively facilitating the coverage of Ukrainian refugees within this.

65. Strong collaboration with the MLSP has been further demonstrated in the successful delivery of winter cash top ups to vulnerable Moldovans. Alongside meeting basic needs, the legislative changes leveraged have improved quality of assistance in meeting basic needs. This is bolstered by the efforts to improve the shock-responsiveness of the national social protection system, covered in UK funded 24/25 UHRP and in 25/26 HARP interventions.

66. The humanitarian-development nexus transition should remain a priority area for the UK in Moldova, utilising established roadmaps to progress on the integration of refugees with Temporary Protection or other legal status into the Government of Moldova’s national systems. The UK focus on Social Protection should remain, providing support to strengthening the quality and accessibility of provision for Ukrainian refugees and vulnerable Moldovans, reinforcing national systems to better support refugee inclusion efforts. Shock-responsiveness remains an important area of focus.

67. Humanitarian crisis preparedness and contingency planning should be continued. UK monitoring of the impacts of the energy crisis in Transnistrian region in early 2025, alongside close engagement with the Government of Moldova, UN, and humanitarian stakeholders, enabled a small-scale intervention to meet the needs of the most vulnerable children in the region, both refugees and Moldovans. A monitoring visit in June 2025 provided further insights into the operational space for humanitarian assistance and the challenges experienced in delivering NFIs, as well as the criticality of need. Continued monitoring and efforts for preparedness and humanitarian access, will be necessary in advance of winter 25/26.

## D: VALUE FOR MONEY (1 page)
VfM performance compared to the original VfM proposition in the business case

Performance against VfM commitments made in the business case
68. The business case set out a number of VfM commitments. There has been clear progress against many of these. In some, progress, metrics or evidence to enable measurement is lacking.

ECONOMY
69. Through identifying implementing partners through competitive procurement for two of HARP’s major projects, BLOOM and SHARP (both procured during the review period but mobilised shortly afterwards), and following best practice for our commercial processes, costs have been driven down (for the delivery of the same services/outcomes). By concentrating cash delivery through a smaller number of partners, and rationalising partnerships across the programme compared with the predecessor programme, we have benefitted from economies of scale and reduced transaction costs. Through increasing the number of local partners who are committed to procuring locally, we have helped to drive down procurement costs while stimulating local markets and ensuring quality through the ability to examine products before purchase. Programme management maintained a high level of scrutiny of budget lines and requests for changes within and between these, and regular engagement with partners ensured a strong understanding of activities. However, this will be enhanced in future by a more robust approach to monitoring and evaluation, and the new VERITAS project.

EFFICIENCY
70. Performance against output indicators is strong (see Section C) showing that the programme is on track to deliver what was agreed, and demonstrating good Efficiency. This assessment would be much more robust if the logframe had been finalised within the period of the review. The programme has sought to earmark funding to projects where this has been possible, allowing for much greater transparency and more detail about results. This has also allowed the programme team to steer projects and support efficient reallocation of funding to course-correct as the context has required. A greater effort on accountability to affected populations (AAP) will be taken in the next review period to increase beneficiary, to improve services and delivery and further strengthen efficiency. The decision for multi-year allocations will increase certainty over partner budgets, to support more efficient planning and drive down costs in future years as start-up costs are reduced and staff recruitment and retention become less burdensome. Finally, as an efficient delivery modality, the team has continued to push up the proportion of support provided as MPCA, wherever local markets are functioning.

EFFECTIVENESS
71. Monitoring and measuring outcomes continues to be a challenge with most partners focussing on output monitoring. A robust Logframe has been adopted, but was finalised after the review period, reducing the robustness for this review. However, following the business case, the programme team’s evidence review allowed for a thorough consideration of the evidence behind the targeting of funds and design of interventions, with a view to maximising effectiveness. Effectiveness has also been supported through investment in technical assistance, and local and international advocacy and engagement on localisation, cash, social protection, humanitarian access and other pertinent issues, to provide an enabling environment for our interventions; support the strengthening of GoU systems; and capacity build amongst local partners. Finally, continued support to context-appropriate local coordination mechanisms is increasing effectiveness for beneficiaries.

COST-EFFECTIVENESS
72. HARP’s thematic pillar-based approach to delivery of outcomes is supporting greater inter-project coherence and focussing partners on the strategic objectives of the programme as a whole. Increasing cross-partner engagement (e.g. through partner days) in future will help maintain this strategic focus. The programme team’s active consideration of the ongoing value of individual activities will help maintain cost-effectiveness of UK funds. As noted above, active policy engagement and advocacy can significantly increase VfM by promoting approaches and modalities with stronger context-specific evidence of cost-effectiveness and positively influencing the humanitarian system in Ukraine and Moldova. The setting-up of the SHARP consortium – also procured during this period – demonstrates a commitment to role modelling the changes we want to see across the system. The BLOOM project – procured during the review period – is seeking to utilise cost-effective options for helping poorer households to achieve economic independence; the next annual review should explore whether BLOOM has succeeded in doing this at scale.

EQUITY
73. In line with humanitarian principles, HARP is underpinned by a commitment to reach the most vulnerable war-affected Ukrainians. To identify the most vulnerable households, partners rely on analysis including REACH’s multi-sectoral needs assessment (funded via the HAVEN consortium), partner-level analysis including Mercy Corps’ internal analysis unit and local downstream partner’s understanding of local communities. The FCDO has also agreed Gender Equality and Social Inclusion (GESI) Partnership Principles with partners which include commitments to collecting and analysing gender, age and sex disaggregated data, training staff on GESI and ensuring activities are informed by gender equality and social inclusion analyses. HARP’s results tracker now provides significantly greater data disaggregation to ensure the programme team have the data they need to track and assess gender and disability inclusion, amongst other inclusion indicators. Working with NGO partners to provide GEDSI and inclusion training and capacity building, including for their downstream partners, and focussing on vulnerability-based targeting across partnerships, has helped to embed inclusion-focussed delivery. Maintaining a commitment to inclusion involves a trade-off with both cost and speed. Inclusion is one of four cross-cutting priorities within the business case; to more accurately evidence the VfM of an approach that has such opportunity costs, the VfM Statement (once developed) should consider clearly incorporating Equity as a key driver of programme VfM.

CROSS-CUTTING
74. Through adopting a “local-first” model, we are following emerging evidence on the benefits of local delivery. Understanding of exactly how this pertains to VfM is still emerging: the Passing the Buck study (2024) found localisation to offer significant cost efficiencies through greater direct funding of local Ukrainian organisations. good cost-efficiency. Meanwhile, the FCDO funded study under the PereHID initiative to assess the VfM of delivering cash assistance through humanitarian organisations and government systems in Ukraine concluded that Government social protection is more cost-effective than humanitarian cash, but that humanitarian cash is more efficient and more equitable. This guided the decision to continue funding MPCA to meet urgent needs equitably under HARP, whilst using levers like SPIRIT to support the government system to become more shock-responsive. Combining these findings on humanitarian cash and localising of responses, humanitarian cash delivered through local partners may offer both the cost-efficiency of local delivery and the efficiency and equity gains of humanitarian cash. The programme is currently supporting some humanitarian cash delivered in this way. A localisation scorecard, to be adopted within the next review period, would help in ensuring more robust monitoring of performance in localisation of the programme’s activities.
[note] The Share Trust, Passing the Buck: The Economics of Localizing Aid in Ukraine, 2024. The Share Trust, Passing the Buck: The Economics of Localizing International Assistance, 2022.
[note] Through the predecessor programme, the Ukraine Humanitarian Response Programme.

75. Under the predecessor programme, funding allocations for winter activities have been made separately to main agreements with partners. In future, the programme team should incorporate winter activities for winter 2025/26 into partner proposals covering the full financial year. This will enable partner winter interventions to be driven less by efficiency considerations against limited timelines for procurement and delivery, and more by considerations of effectiveness and equity.

Assessment of whether programme continues to represent Value for Money

76. There have been some key constraints in measuring VfM over the review period:
- The Business Case did not set out a VfM statement, and at the time of review, a VfM statement has not yet been adopted (this should be remedied ahead of the next Annual Review). This limits the scope of this review in assessing VfM, especially as concerns Effectiveness of the interventions, as there is no agreed definition of what defines VfM for this programme.
- The proposed VfM indicators (from the business case) have not been systematically considered and adopted during programme mobilisation. It will be possible for the programme team to develop VfM indicators from the data being collected from partner reporting and results tracking – ahead of the next review period, the team should consider which VfM indicators to adopt and monitor, to align with the VfM Statement.
- The programme logframe was finalised in September 2025 – which was after the period of this review. This presents a challenge to the effective assessment of Efficiency, which will be primarily assessed through the review of output indicators.

77. Despite these constraints, HARP is demonstrating good VfM across all outputs, through the achievement of output indicators; by focussing on delivery modalities that offer strong VfM (MPCA); by expanding and advocating for localisation and by enhancing support to the most vulnerable and hard-to-reach.

E: RISK

Overview of risk management

78. The risk rating for the programme is severe. This reflects the fact that operating in Ukraine continues to entail a high level of risk for all actors, especially those seeking to deliver humanitarian assistance to the most vulnerable people in need – typically those in frontline areas. The risk appetite for the programme, shown in the table below, is higher than the departmental and British Embassy Kyiv risk appetites across all categories. This is typical of a humanitarian programme given delivery was focused in war-affected areas and given the higher risk nature of humanitarian operations.

79. The FCDO and British Embassy Kyiv have decided to support the programme understanding the risks entailed, agreeing the programme risk appetite aligns with the realities on the ground and the level of risk required to deliver an innovative and effective humanitarian response in this context.

Risk Category	FCDO risk appetite	BE Kyiv risk appetite	Programme risk appetite
Financial and fiduciary	Receptive	Cautious	Receptive
Reputation	Receptive	Cautious	Receptive
Safeguarding	Cautious	Cautious	Receptive
Strategy & context	Cautious	Eager	Eager
Policy and programme delivery	Cautious	Eager	Eager
Public service delivery & operations	Cautious	Cautious	Receptive
People	Cautious	Receptive	Receptive

80. At the end of this review period (June 2025), 9 risks had severe gross risk ratings (pre-mitigation).

Ukraine:
1. Black Swan Events: Sudden crises may overwhelm response capacity, leaving critical needs unmet and damaging trust in humanitarian actors. Mitigation focused around holding contingency funding to respond to spikes in need and close engagement with the FCDO’s Humanitarian Crisis Response Department. BE Kyiv engaged in a live crisis exercise to better prepare for such events.

2. XXXXXXXXXXXXXXXXXXXXXXXXXX: XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

3. Coordination Challenges: Poor coordination risks duplication, exclusion, and reduced effectiveness. Area-Based Coordination is slow (pilots in Kherson and Sumy). Nexus coordination has stalled; some sectoral progress (e.g., cash) remains fragmented. Mitigation included close engagement with the new RC/HC and Head of OCHA.

4. International Humanitarian Law (IHL): Violations by armed actors and aid groups reduce access and increase risks to civilians and aid operations. Mitigation included programme activity continues to fund IHL humanitarian principles compliance and awareness training among both armed and civil society audiences.

5. FCDO Staffing: High turnover and consultant reliance risk burnout and disrupt continuity in the BEK Humanitarian team. This is no longer a severe risk at the time of writing as new staff resources continue to be onboarded.

6. Budget Uncertainty: Partial HMT approval and unclear future budgets limit multi-year funding and innovation; compounded by global donor cuts. This is no longer a severe risk at the time of writing as the team received confirmation of the FY allocation and a proposed multi-year allocation.
Moldova:

7. XXXXXXXXXXXXX: XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

8. Refugee Surge: Escalation or black swan events may trigger mass displacement into Moldova, overwhelming response systems and raising EU/UK political pressure. Increased refugee influx, preparedness was maintained through regular coordination with UNHCR and WFP for contingency planning, alongside efforts to support the development of shock-responsive national social protection systems (through WFP), though progress remains gradual.

9. Safeguarding Risks: SEAH incidents by partner staff— in Ukraine and Moldova—could harm vulnerable groups and damage programme integrity.

81. During the reporting period there was severe risk of partner’s staff perpetrating acts of SEAH causing harm to beneficiaries or other staff members and undermining do no harm principles. However, during the reporting period there were no cases of PSEA reported. To mitigate the risk of PSEA cases being unreported, a specific workshop was held with central safeguarding teams on one partner, HAVEN, to assess organisational policies and procedures plus specific safeguarding risks associated with their activities. Over the next financial year, findings of the workshop will be discussed with HAVEN and implemented. Due to security constraints, FCDO was unable to visit partner’s sites and therefore unable to assess the PSEA procedures in place. To mitigate this, specific questions on PSEA were included in TPM questionnaires for Ecorys to explore with partners. Findings of these reports identified not all PSEA trainings were implemented for all local partners and that some staff lacked knowledge around PSEA and key policies. Recommendations have been shared with partners and the FCDO will work to resolve the identified issues. To better understand the barriers to reporting PSEA at the community level, the FCDO engaged with various organisations. Ground Truths Solution contributed to this effort by publishing and disseminating a paper that identified key obstacles, including distrust in reporting mechanisms, fear of repercussions, and other unidentified factors that may discourage individuals from coming forward.

82. In Moldova, the FCDO team introduced a Safeguarding Engagement Tracker and held deep-dive meetings with partners, including with UNFPA and UNICEF, to strengthen oversight and follow-up mechanisms. No SEAH cases were reported for Moldova programming during the programme cycle. Safeguarding remains a priority area for continued engagement.

83. Separate risk registers were held for Ukraine and Moldova, which were reviewed and updated quarterly by the programme team. All residual risks have remained in appetite during the review period with no escalations.

84. During this review period, unexpected changes in the donor funding landscape led to re-prioritisation efforts across humanitarian agencies. In January 2025 President Trump issued an executive order freezing all U.S. foreign aid for 90 days and by March 2025 USAID funding in Ukraine reduced dramatically. USAID previously contributed ~30% of Ukraine’s humanitarian funding. Cuts affected key sectors like multipurpose cash assistance (MPCA), health, shelter, and WASH, with U.S. contributions making up 40% or more in some areas.

85. In response to mitigating risks and impacts from this, our programmes allowed partners to be flexible and re-allocate funding where required to protect urgent activities (eg: UNFPA Moldova). This sudden change of the donor funding landscape on top of the UK government decision to reduce ODA from 0.5% to 0.3% of GNI led the team to initiate the Evidence Review to re-prioritise future programme decisions. In April 2025, OCHA released an addendum to the HNRP, adjusting priorities to focus on severity of needs. The reprioritisation aligns with the Emergency Relief Coordinator’s call for a “Humanitarian Reset,” aiming to focus limited resources on the most acute needs, particularly in eastern, southern, and northern oblasts.

Recommendation

FCDO to facilitate a safeguarding learning network among direct and indirect partners to share practical approaches, challenges, and innovations related to PSEA. This could be done through periodic virtual meetings or a shared online platform, enabling partners to exchange experiences and strengthen safeguarding practices without significant resource investment.

Owner: Safeguarding Lead (BE Kyiv Humanitarian and Resilience team). Deadline: End of FY.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery

86. Funding Arrangements: The programme was delivered through a mix of mechanisms, depending on context, capacity, and value for money. For this programme, funding was provided to UN multilaterals through donor contributions, local NGOs through Accountable Grant Agreements (AGAs) and the Ukrainian government through a Memorandum of Understanding (MoU).

87. Delivery chain mapping: NGOs set out their DCMs showing their localisation work and number of downstream partners, including the amount of funding distributed. This has given the programme team a clearer picture of accountability and due diligence, reducing the risk of inadequate financial controls and lack of reporting mechanisms. This is tracked through partner reporting and third-party monitoring.

88. Reporting frequency: During this period, partners provided quarterly or biannually narrative and financial reporting in a timely manner and to a high quality. Differences in partner reporting timeframes have impacted other reporting tools such as the results tracker and reporting on achievements and the FCDO will seek to better align these in the coming year. Informal partner engagement with programme managers and subsequent sharing of readouts have helped to cover gaps.

89. Partner Engagement: Generally, programme managers engage with partners regularly. However, there is the need to re-organise ‘local partner days’ which have stopped due to resourcing challenges. The partner days would aim to strengthen partner collaboration and relationships, improve performance and promote shared learning. Plans are proposed in the forthcoming MEL plan to better plan the frequency, content and ownership of these. This has not stopped the FCDO directly engaging with local partners during quarterly meetings and, for example, a local partner day organised by Mercy Corps in Lviv and attended by the FCDO.

Commercial Performance

90. Although most partners were delivering as part of the UHRP programme, all project partners were required to submit new project proposals and budgets, undergoing VfM scrutiny by the programme team. All partners provided budgets and activity plans, and overall partners’ financial management was strong across the programme. Partners who received additional funds were judged to have the capacity to scale up quickly and effectively. A total of 8 partners were delivering activities under signed agreements between October 2024- March 2025. Three partnerships were extended into 25/26 financial year alongside the start of the commercial process for a livelihoods-nexus and protection consortium.

91. For staffing deployments and advisers, requests were made to Palladium to provide a total of five short-term consultants over the reporting period to cover various technical expertise requirements in the absence of successful internal recruitment.

92. Audit: No programme or partner audits commissioned by the FCDO took place during the reporting period.

93. Aid Diversion and asset checks. Partner due diligence documents are up to date and many will be refreshed in Y2 of the programme. Partner asset checks were completed under UHRP and many assets are shortly due to be transferred to HARP so that partners can continue to use FCDO funded assets. These will be regularly checked as part of the MEL plan.

Financial Performance

94. The Business Case approved funding of £500m, notionally split across financial years as follows:

FY 24/25	FY 25/26	FY 26/27	FY 27/28	FY 28/29	FY 29/30
XXXX	XXXX	XXXX	XXXX	XXXX	XXXX

95. The budget allocation finally approved for spending in 24/25 was £58m. In the last quarter of 2024, a decision was taken to uplift the 24/25 budget by a total of £3.05m consisting of potential underspend and unallocated funds reserved for contingencies to ensure a full spend as possible, bringing the final budget allocation to £61.05m.

96. The final spend for the year was £60.93m i.e. 99.8% of final budget allocation.

97. FY 25/26 began with a budget allocation of £100m and Q1 spend is £8.8m. Total spend over this review period is £69.7m.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

Internal monitoring

98. Internally, performance is monitored through logframes and regular documented progress meetings between the FCDO programme team, Humanitarian Adviser and the partner. As we build on an individual partner approach and towards a thematic/pillar approach (as outlined in Section X) our future reviews of partner performance will increasingly consider how well they are contributing towards the outcomes and impact indicators under their respective pillar, and review the strength of HARP’s theory of change.

99. Within this first year of HARP, a new Results Tracker has been developed. This tracker will capture key results across humanitarian sectors, mostly disaggregated by age, sex, and disability. It includes some key indicators of strategic relevance to the programme team such as the % and amount of cash transfers within the programme and the % of direct funding to Ukrainian partners.

100. The programme also received high-level visits such as that of Prime Minister Keir Starmer. During his visit to Kyiv in January 2024, he saw first-hand the work of Ukrainian Red Cross Society at Kyiv hospital’s burns unit and met with wounded civilians receiving treatment. The FCDO’s 2PUS Nick Dyer visited Kyiv in April 2025 and toured a collective site for displaced people from Luhanska Oblast, which was equipped by the national NGO Right to Protection with financial support from the Ukraine Humanitarian Fund (UHF).

101. In Moldova, the programme team conducted a series of site visits and safeguarding deep dives to assess the quality and impact of partner interventions. These included visits to UNFPA-supported Safe Spaces and crisis centres, Refugee Accommodation Centres, and social institutions in Transnistrian region. UNICEF’s safeguarding deep dive highlighted effective collaboration with the Ministry of Labour and Social Protection (MLSP), including the absorption of newly trained child protection specialists into the state system and the development of national safeguarding standards. UNFPA-supported Safe Spaces and crisis centres—such as those in Palanca and the forthcoming facility in Stefan Voda—provided inclusive, survivor-centred services for refugee and host community women and girls, with strong local ownership and multi-sectoral coordination. The Family Justice Centre in Chisinau stood out for its comprehensive, co-located services and successful government–NGO collaboration.

102. The site visit to Transnistrian region demonstrated UK funded winter kits provided critical support to vulnerable children, but distribution was delayed due to procurement challenges, customs procedures, and limited data on beneficiaries. Monitoring efforts were constrained by weak feedback systems and limited institutional capacity. Maintaining linkages with civil society provides an important means through which to monitor changes.

103. Across all sites, partners demonstrated responsiveness to beneficiary feedback, commitment to safeguarding standards, and efforts to strengthen sustainability through local ownership and capacity building.

Third Party Monitoring (TPM) in Ukraine

104. The programme team draws on a central contract implemented by Ecorys for TPM. During the annual review reporting period four partners were monitored. Field work visited project sites in the East and South of Ukraine and included the monitoring of tier one partners i.e. those directly funded by the FCDO. Ecorys sub-contracted field-monitors from the Kyiv International Institute of Sociology to visit 44 project sites of five FCDO partners. Partners monitored included Mercy Corps, UNICEF, UNHCR, and Non-Violent Peaceforce (HAVEN).

105. During the next programme year, the model will change and TPM will be provided via a dedicated supplier for the BEK ODA portfolio under the VERITAS programme. HARP will benefit from a supplier more specialised to the Ukraine context, and the ability to build out a rolling 12-month workplan. Findings are summarised under the appropriate Output assessment sections.
[note] DevTracker Programme GB-GOV-1-400393

Evaluation

106. To inform the ongoing effectiveness of the programme and the final impact, HARP will undergo a mid-term evaluation or review after the second year of implementation. An end-term evaluation may also be commissioned subject to need.

Evidence

107. In May 2025 the Humanitarian team undertook a comprehensive Evidence Review to decide the strategic direction of the humanitarian portfolio and to inform programme and budget decision making for the remainder of the financial year.

108. This process led the FCDO to prioritise the following sectors, approaches and partners for 2025-26:

Protection: Ukraine’s humanitarian crisis is fundamentally a protection crisis, with vulnerable groups facing displacement, trauma, and rights violations. The FCDO should prioritize protection by supporting specialist partners for GBV services, case management, legal aid, and advocacy. This included continuing the frontline-oriented HAVEN consortium, launching a call for proposals for a protection-focused consortium which is in the final stages of agreement (exciting updates on this coming soon), complementing the SPIRIT programme and strengthening state service delivery with UNHCR.

Cash to meet multi-sector basic needs: The continuation of Multi-Purpose Cash Assistance (MPCA) is essential to meet immediate needs, especially where government systems lack funding/speed/reach, while work continues to adapt the social protection system (SPIRIT). A blended delivery model—combining community outreach with alignment to government social protection systems—offers both reach and efficiency. Strengthening links to long-term social protection and livelihoods support will reduce dependency on humanitarian aid over time.

WASH: Water, sanitation, and heating interventions offer both emergency relief and long-term recovery potential. Given the centralized nature of Ukraine’s infrastructure, targeted support—particularly through UNICEF—can yield high-impact results in public health and institutional resilience, working through Government/municipal institutions. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Livelihoods: Economic vulnerability is widespread, with over half of households affected by underemployment. While large-scale employment generation is a long-term goal, immediate support for livelihoods—such as the Mercy Corps programme—can provide a bridge to recovery and resilience. Fundamental to the HARP business case, this provides immediate support and links to economic recovery (implemented in partnership with the Tiger business case).

Displacement and collective shelters: Displacement remains a persistent challenge and collective sites support Ukraine’s most vulnerable displaced people, in often sub-optimal conditions. Continued support to Collective Sites through UNHCR and local actors is recommended, with a focus on disability-inclusive infrastructure and services.

109. The BE Kyiv Humanitarian Team presented this work and its conclusions to colleagues across the embassy and EECAD and the related challenge sessions helped us hone our priorities and identify realistic programme focuses for 2025/2026.

110. As part of our evidence-based approach to programme decision-making, we also drew on two key studies:

“Passing the Buck: The Economics of Localizing Aid in Ukraine” (Refugees International, July 2024), which highlighted the significant cost efficiencies that could be achieved through greater direct funding of local Ukrainian organisations.

“Understanding the Role of Ukrainian Civil Society in the Provision of Humanitarian Cash Assistance” (Ground Truth Solutions and Open Space Works Ukraine, March 2025), which underscored the critical role of Ukrainian civil society in delivering cash assistance and called for a shift in power dynamics—specifically, to shift decision-making power to local actors in programme design and targeting, and fund local CSOs directly, rather than engaging them solely as subcontractors.

111. These findings informed our commitment to strengthening locally led responses and ensuring more equitable and efficient humanitarian assistance in Ukraine.

Learning for the year ahead

112. The HARP programme team have secured specialist short-term technical expertise to support the development of a Monitoring, Evaluation and Learning Plan that enables accountability and decision making at different levels. The plan considers the needs of individual projects and partners, the HARP programme as a whole, and the wider Humanitarian response in Ukraine.

113. The plan aims to bring together MEL activities and products mentioned in this Annual Review (such as the Results Tracker, the localisation scorecard, third party monitoring and the planned mid-term evaluation or review). The plan will propose the design of products and processes that aim to ensure MEL is embedded into project and programme decision making cycles. The key recommendation for BEK is to allocate sufficient staff resource to consistently implement these plans and for the HARP PRO and MEL team to finalise the MEL plan in Q3.

114. The MEL Plan will make broad suggestions on the objectives and purpose of the agreed mid-term evaluation / review. Recommendation: The HARP PRO and BEK Evaluation Adviser should propose to the SRO by March 2026 the objectives and delivery approach for the mid-term evaluation / review (for example to use the FCDO’s GEMFA framework or otherwise).