Business Case Summary Sheet

Country Plan Summary: / This programme will be the main delivery mechanism for Goal 1 of the BE Kyiv Country Plan “Emergency Response: The UK's collective input, influencing, and advocacy on humanitarian responses and emergency repairs maximise the impact of UK support in reducing human suffering, particularly for the most vulnerable.” It will also contribute to the overall country goal, namely “Use our influence to support Ukraine’s institutions to deliver the humanitarian, recovery … needs of the country; … and ensure that all measures to protect Ukrainians are inclusive”. / This programme will also deliver Goal 5 of the BE Chisinau Country Plan “To support Moldova’s response to the protracted refugee caseloads and spikes in humanitarian need: the development of national social protection mechanisms, providing essential assistance and protection to vulnerable refugees and affected Moldovan communities; facilitating contingency planning and preparedness …; and strengthening national and local capacities to respond.”
Title: Ukraine and Moldova Humanitarian Assistance, Recovery and Protection programme
Programme summary / The programme will support the most vulnerable in Ukraine, and Ukrainian refugees in Moldova, with a range of emergency response, protection and early recovery activities, supporting the overall resilience of communities to in the face of Russian aggression. These activities will meet emergency and basic needs, while supporting gradual transitions from humanitarian support where possible. The programme’s systems strengthening and enabling environment work, coupled with its enhanced focus on localisation, will contribute to the development and maintenance of strong humanitarian and government systems, that are more inclusive, sustainable and shock responsive. As such, the programme will address a range of severe needs whilst preparing, where possible, for Ukraine and Moldova to transition away from humanitarian assistance.
What is the rationale for UK Aid spending? / The 2024 Labour Manifesto sets out that the UK’s military, financial, diplomatic and political support for Ukraine will remain steadfast. / This business case proposes a multi-year programme of humanitarian support to Ukraine and Moldova. This approach acknowledges Ukraine faces a protracted humanitarian crisis, where the most vulnerable in Ukraine, victims of Russia’s aggression, will require significant and sustained support. In Moldova, one of the poorest countries in Europe, Ukrainian refugees will also need continued assistance, complemented with proportionate support to host communities to manage risks around social cohesion. Our approach will complement, and provide a foundation for, planned and ongoing HMG stabilisation, and recovery and reconstruction interventions. / A multi-year humanitarian programme will maintain the UK’s position as a key donor and ally to Ukraine, allowing us to influence the spending of other donors. With extensive humanitarian expertise, an excellent relationship with the Government of Ukraine, and the ability to programme across the humanitarian-recovery spectrum, the UK is ideally placed to remain an innovative, thought-leading humanitarian donor to Ukraine. / The programme will be a key element of delivering on public commitments to humanitarian as set out in the Agreement on Security Co-operation between the UK and Ukraine[1], signed by former Prime Minister Rishi Sunak and President Volodymyr Zelensky in January 2024.
[1] Full text available: UK-Ukraine_Agreement_on_Security_Co-operation.pdf (publishing.service.gov.uk)

Programme Value: XXXXXXXXXXXXXXXXXXX		Country/ Region or Sector: Ukraine and Moldova[2]
Department/Country Office confirmation of review processes		Director EECAD, HMA Kyiv and HMA Chisinau endorsed
Contact name		XXXXXXXXXXXXXXXXXXXXXX
Threshold for final approval of Business Case: HMT
Date of Approval of Concept Note:	10/05/2024	Name and role of Approver: Minister Ghani, Minister of State for Europe
Date of Approval of Business Case:	06/08/2024	Name and role of Approver: Minister Doughty, Minister of State for Europe / Minister Dodds, Minister of State for International Development (Foreign Secretary delegated approval)
Programme Code: 400176	AMP Start Date: 16/10/2024	AMP End Date: 30/09/2029
Overall programme risk rating:	Severe
[2] This programme will retain flexibility to fund activities in the wider region surrounding Ukraine to respond to spikes in need, in relation to Russia’s ongoing invasion of Ukraine.

Contents

Strategic Case

Russia’s illegal invasion of Ukraine has precipitated the largest military conflict, refugee and energy crisis in Europe since the end of the Second World War. In addition to the enormous human cost of this aggression, Russia’s action poses a significant challenge to our collective security, the norms of reasonable behaviour, and the fundamental principles of the UN Charter and international law, as well as seeing the weaponisation of food and energy supplies with direct impacts on the British people.

European collective security is now intrinsically linked to the outcome of conflict in Ukraine. This means supporting Ukraine to reassert its sovereignty, to defend itself, to secure a just and sustainable peace, while supporting its economic stability, recovery, and reconstruction. Over the short and medium it also means shoring up Ukraine’s resilience in the face of Russian aggression. The case for UK humanitarian interventions, in both Ukraine and Moldova, set out in this document sits within, and contributes to, this overarching strategy.

## Context
Historically, Ukraine has faced significant development challenges. After independence from the Soviet Union in 1991 Ukraine transitioned to a market economy. These years were characterised by corruption and insufficient structural reform which impeded economic growth and social development, exacerbating regional disparities. Ukraine’s economy lagged behind that of its neighbour Poland. Just 20 per cent larger that Ukraine’s in 1990 it was more than three times bigger by 2012[3].
[3] Poland and Ukraine: A tale of two tale of two economies by Simon Tilford (cer.org.uk)

Russian aggression, commencing in 2014, precipitated a humanitarian caseload and tried to challenge Ukraine’s independence and prosperity. The Euromaidan popular protests demanding greater alignment and integration with the EU, led to a collapse of Ukraine’s pro-Russian government. In response Russia illegally annexed Crimea and forcibly took control of parts of Donetsk and Luhansk. The Minsk agreements[4] established a, frequently violated, ceasefire and the conflict remained largely static for the next eight years – neither escalating nor making progress toward a political resolution. In addition to exacerbating pre-existing structural inequalities and regional disparities, a nascent humanitarian caseload emerged in both the east and among internally displaced peoples – typically comprising of 4 million in need of humanitarian assistance. A small-scale international humanitarian response was established.
[4] The agreement commonly referred to as ‘Minsk II’ agreed a package of measures to stop the war in Donbas and was formulated by the then leaders of Ukraine, Russia, France and Germany.

Russia invades Ukraine, triggering a humanitarian crisis in Europe of a scale not seen since the Second World War. Recognising separatist regions in Donetsk and Luhansk as independent, Russia launched a full-scale invasion across Ukraine on 24 February 2022. Russian forces advanced quickly across much of the East, South and North. Millions were forced to flee their homes amid the widespread destruction of social infrastructure across Ukraine. Within a month of the invasion more than 15 million people were assessed by the UN to need humanitarian assistance, with over five million people having fled to neighbouring countries and over seven million displaced in Ukraine. A significant number of civilians were trapped in Russian occupied areas or in encircled cities being besieged. Ports were effectively blockaded. Across the country, hospitals, clinics, schools and other education facilities were being destroyed or damaged and supply chains into the country were severely disrupted. Scaling up the UN-led international response, from effectively a standing start, to respond to needs in Ukraine and the surrounding region was a huge undertaking which took about four months[5].
[5] Prior to invasion the humanitarian response in Ukraine was one of the smallest in the world.

Ukrainian counteroffensives regain territory, but Russia holds ground and begins targeting energy infrastructure. Gaining momentum in September 2022, Ukraine’s counter-offensive reclaimed 54% of the land previously captured since the beginning of the war[6]. Russia was pushed out of the northeast and southern parts of the country but held territory in the south and east of Ukraine. In response, Russia illegally annexed Donetsk, Luhansk, Kherson and Zaporizhzhia regions, further entrenching denial of humanitarian access to the territories it controls. Humanitarian needs, while stabilising to some degree in some parts of Ukraine over this period, remained severe across the frontline and in the areas controlled by Russia. As winter approached, Russia targeted Ukraine’s energy infrastructure launching waves of missile and drone strikes, seriously affecting energy distribution across Ukraine and neighbouring countries. With support from its allies, Ukraine was able to restore much of its power over the following months.
[6] Analysis based on data from the Institute of War.

Ukraine’s human, social and economic losses are immense, setting back 15 years of development gains. In 2022, Ukrainian GDP fell by nearly 30% and the World Bank estimates that the national poverty rate increased from 5.5% to 24.2%, equating to an additional seven million people[7]. Employment remains below pre-war levels and most have seen a drop in income. In parallel Ukraine’s infrastructure has suffered considerable damage – including transport, energy, healthcare[8], communications and water with reconstruction costs now estimated at $486bn USD[9]. The scale of this destruction not only affects a significant proportion of the population but also impedes economic growth. Realistically, recovery and reconstruction will take years and progress will not be linear. Provision of essential services by GoU is still disrupted and heavily reliant on external financing.
[7] The World Bank, The World Bank in Ukraine, 15 December 2023.
[8] As of 30 November 2023, WHO has recorded 1,415 attacks on health care facilities in Ukraine.
[9] Ukraine Third Rapid Damage and Needs Assessment (RDNA3) February 2022 – December 2023 Ukraine - Third Rapid Damage and Needs Assessment (RDNA3) February 2022 – December 2023 (worldbank.org)

Nascent economic recovery but widening inequality and challenges to resilience continue. Throughout 2023, there have been indications of economic recovery, including a slight fall in inflation rates, however, multiple humanitarian data sources indicate widening inequality. The cost of living remains high, access to employment scarce, and coping capacities exhausted[10]. While social protection mechanisms are adapting, inflation has reduced coverage of payments on household needs, and needs far outstrip the level of support available. Vulnerable groups are at growing risk of falling through the gaps, while in parallel their levels of resilience are declining as the crisis protracts, adding to the risk of further backsliding on poverty and endangering future prospects for their recovery.
[10] International Organisation for Migration, General Population Survey, Rounds 12 – 14, December 2023.

As of April 2024, Russia is regaining territory and its attacks on Ukraine’s energy infrastructure have significantly intensified. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Airstrikes on urban centres, such as Sumy, Odesa, and Kharkiv are intensifying. Kharkiv is suffering almost daily bombardment with the city now regularly suffering power outages and disruption to water and heating supply. On 22 March, Russia conducted the largest single attack on Ukraine’s energy infrastructure, launching a total 151 missiles. At the time of writing, attacks have continued and Ukraine has lost over 30% of its electricity generation capacity. Ukraine is warning of, and preparing for, a Russian summer offensive. If realised, this risks a further sharpening of humanitarian needs in frontline areas and increases the potential for further displacement.

## Humanitarian needs in Ukraine

Severe and widespread humanitarian needs in Ukraine remain. Over 25% of the country’s pre-war population is displaced – including nearly 6 million refugees[11] and 3.7 million people displaced internally[12]. As of January 2024, the UN estimates 14.9 million people need multi-sectoral humanitarian assistance inside Ukraine (around 40% of the total population). Of these the UN-led response plans to target 8.5 million people with an appeal for $3.11 billion USD. From a sudden onset emergency, humanitarian needs in Ukraine are now protracted.
[11] UNHCR, Operational Data Portal, 22 December 2023.
[12] 52% of all IDPs are concentrated in five oblasts, Dnipro, Kharkiv, Kyiv City, Kyiv and Odesa. IOM, General Population Survey – Round 14, September 2023.

Across the country, millions are struggling to meet their most basic needs and severity of need is worsening. Causes included protracted displacement, declining economic resilience, limited employment prospects and an unaffordable cost of living. Affected populations have suffered damage to homes, some have been obliged to live in collective centres[13], and have endured disruption to services including healthcare. Cold weather increases challenges, exacerbating serious illnesses and presenting particular risks for older people and those with disabilities. In response to fiscal constraints, the government has already significantly reduced the coverage of their IDP allowance programme and is moving towards a means-tested approach for other programmes.
[13] Some 120,000 displaced persons are estimated to live in collective centres. Conditions there are often reported as inadequate, with around half reporting that they need repair works, more than half not equipped with disability friendly infrastructure, and 40% lacking a back-up power. source Reach, CCCM Cluster, Ukraine Collective Site Monitoring Round 10, October 2023

Protection risks are heightened for vulnerable and marginalised groups with intersecting needs, compounded by the crisis. Marginalised and vulnerable groups (people with disabilities, older people, LGBT+, Roma, female head of households) face additional barriers to accessing services and assistance, and many types of assistance fail to target their specific needs. Twenty-five per cent of Ukraine’s pre-war population was over 60 and the humanitarian caseload in Ukraine is the ‘oldest’ in the world. Older people and those with disabilities are the least likely to evacuate from their homes and communities. Over three million children have been affected by damage of schools, and provision of child protection and services remains insufficient with widespread shortages of specialist staff.

Along the frontline and in the northern oblasts that border Russia, protection risks drive severe humanitarian needs, which are worsening. Needs are most severe along both sides of the 900km frontline, where whole towns and villages have been destroyed, shelling occurs daily, and there is minimal access to basic goods. In some cities over 90% of buildings have been damaged or destroyed[14] with people facing complex housing, land and property issues. In some war affected areas 1.4 million people are without running water[15]. Those remaining in frontline areas are disproportionately older people and people with disabilities whose needs and vulnerabilities have been severely compounded by the crisis, due to barriers accessing essential and humanitarian services, erosion of support networks and the mental health and psychosocial impacts of exclusion and isolation. In these areas health and livelihoods rank as the two highest areas of need[16].
[14] # Guardian, Russia-Ukraine war: Russia has damaged or destroyed almost every building in Avdiivka, 18 December 2023.
[15] UNICEF, 1.4 million people without running water across war-affected eastern Ukraine, April 2022 https://www.unicef.org/press-releases/14-million-people-withoutrunning-water-across-war-affected-eastern-ukraine
[16] Reach, Multi-sector Needs Assessment, September 2023.

Challenges are compounded by the high degree of landmine contamination. The Government of Ukraine (GoU) estimates that 174,000km2 (or nearly 29%) of Ukraine’s territory needs to be surveyed for contamination by landmines or unexploded ordnance.[17] This poses evident risks to the ten million civilians living in affected areas (particularly rural populations, rescue workers, deminers and humanitarian workers), as well as limiting access to land, homes, roads and infrastructure.[18] Beyond the immediate protection risks, it will also challenge recovery and reconstruction.
[17] ACAPS, Humanitarian implications of mine contamination, January 2024. To note that while demining is not a primary focus of the proposed future humanitarian programme captured in this business case, HMG does support demining through other programmes, most notably through the Global Mine Action Programme. As of end December 47,052 square metres of land has already been cleared under the current contract (commencing September 2023) with the HALO Trust. Demining activities in this programme – primarily on education and demarcation – will be complementary to this.
[18] Ibid.

In Russian controlled territory protection concerns are widespread[19]. Several million people live in occupied territory, some of whom have been impacted by armed conflict for almost a decade. Concerns include, but are not limited to: extensive human rights abuses, including sexual violence; issues concerning documentation and legal rights; forced transfer and deportation[20]; forced conscription; and extensive surveillance. We judge that humanitarian need across these geographies is likely to vary, with some areas still experiencing heavy military operations and severe disruption but other areas having more regular access to markets and services – albeit tied to an agenda of Russification and obliging acceptance of Russian citizenship and passports. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX[21]. There are reports that Russia has moved significant numbers of its own citizens into these areas.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX.

## Humanitarian needs in the Region

Significant numbers of Ukrainian refugees remain displaced, with six million abroad. This includes 956,000 refugees in Poland, 373,000 in Czech Republic, 113,000 in Slovakia, 112,000 in Moldova, and 86,000 in Romania.[22] Most refugees have come from highly-conflict affected areas, such as Kharkiv, Donetsk, Zaporizhzhia and Mykolaiv.
[22] UNHCR Ukraine Refugee Situation Dashboard, Accessed 09/01/2023, Situation Ukraine Refugee Situation (unhcr.org)

Host national governments across Europe responded with great generosity to the sudden large-scale influx of refugees, offering protection under the EU’s Temporary Protection Directive. This offers immediate and collective protection to displaced persons for a maximum period of three years. The directive is set to expire March 2025 and host governments will need to prepare for a tailored regime which may further reduce assistance to refugees.

The Ukraine Regional Refugee Plan appeals for $1.1 billion USD and plans to support refugees in 11 countries[23]. Refugee numbers have remained relatively static over recent months, with border crossing data suggesting current movements are primarily pendular in nature, with Ukrainians returning to the country (and leaving again) on a short-term basis. Since the start of the invasion 4.6 million are estimated to have returned home, 20 per cent of whom have returned from abroad. Evidence suggests a decrease in intentions among refugees to return[24] with safety and security being the greatest factor in decision-making. The UN assesses that some return movement will continue, but the rate of return is unlikely to increase substantially.
[23] To note European countries hosting Ukrainian refugees are not ODA-eligible – barring the first twelve months of in-donor refugee costs which can be scored. Past this point donors can fund ODA-eligible international in non-eligible countries according to an agreed coefficient if it contributes to systems strengthening. Moldova is a notable exception as an ODA eligible country in its own right. Historically UK programming did support humanitarian needs across the region in the first year of displacement, but this was refined down to Moldova in 2023 in line with DAC rules on ODA spending.
[24] IOM, Displacement Tracking Matrix – Ukraine Returns Report, October 2023.

## Humanitarian needs in Moldova

Moldova has been severely affected by the Russian invasion of Ukraine and faces a much higher risk of destabilisation and conflict-related crisis than other refugee-hosting countries. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Moldova is one of the poorest countries in Europe, with an absolute poverty rate of 31.1% in 2022. The country’s social services and infrastructure were already weak prior to February 2022. The influx of refugees post invasion (800,000 refugees and third-country nationals have entered Moldova, most often in transit) increased strains in Moldova. Absolute poverty rates rose over 6% from 2021 to 2022[25]. Price spikes were seen for energy, fuel, food, and rented accommodation. This increased vulnerability for many poor Moldovan households, left some unable to meet their essential needs and further entrenched poverty, By December 2022, inflation had hit 30.2% and the GDP had contracted by 5.9%.
[25] Statistica Moldova, 2023 Analiza_saracie_copii_2022.pdf (gov.md)

Moldova now hosts c. 120,000 Ukrainian refugees. 81% of refugees in Moldova are women and children and 70% of refugee households are single female-headed households. 19% of refugees have one or more specific need that may heighten their vulnerability, including people with disabilities, who constitute 6% of the total refugee population.[26] These groups face particular barriers to socio-economic integration and access to the labour force including discrimination, limited availability of childcare services, language barriers, and low school enrolment rates.[27] The majority of refugees (62%) in Moldova have expressed a desire to return to Ukraine one day, but this is over the longer term and many express concerns about security in their places of origin.
[26] UNHCR, Regional Refugee Response Plan, January 2024
[27] Ibid.

The Government of Moldova however relies heavily on international assistance to meet the needs of the refugee population. Within the 2024 Regional Refugee Response Plan $303.1m of the appeal is for Moldova, with a target population of 90,000 refugees and 55,000 vulnerable Moldovans. Moldova is the only country in the RRP to include both Ukrainian refugees and vulnerable host communities as target groups, given the unique vulnerabilities of the host population and weak capacity of the country[28].
[28] The 2023 Regional Refugee Response Plan (RRP) had a financial request of $427m for Moldova, which was around 50% funded by the end of 2023.

## Ukraine Humanitarian trajectory and trends

Scenarios

This business case recognises it is impossible at this stage to predict the outcome of the war in Ukraine or the humanitarian outlook over the next five years. There is a direct correlation between Russian aggression and warfare and humanitarian need in Ukraine. As such, we judge that in the absence of a cessation of hostilities and a just and sustainable peace, humanitarian need will persist in Ukraine.

As such, this programme will need to plan against a range of scenarios, where there will be some commonalities, but also the potential for significant differences in the scale and severity of need, and within some scenarios very specific risks. In parallel, events like the destruction of the Nova Kakhovka Dam illustrate the potential for ‘black swans’ in this context and the limits of our collective ability to intuit all risks. To keep UK humanitarian support relevant and targeted, agility in programming will be key.

While the overall outcome of the war cannot be predicted, our scenario analysis presents five key different, but plausible futures over the coming three to five years, set out below. The scenarios consider key differences in the conflict, governance, and economic environments and the extent to which these changing circumstances could impact living conditions and shape humanitarian consequences. To note, these are not intended to be exhaustive but provide a frame of reference and indicate how a UK intervention will need to flex in scale and shape (up or down) to remain effective in our overarching strategy.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

1. Commonalities between all scenarios include:
  1. Humanitarian access to territory under Russian control remains blocked. Human rights abuses persist and occupation authorities enforce Russification agenda.
  2. Severe humanitarian needs remain irrespective of conflict intensity. XXXXXXXXXXXXXXXXXXXXXXXXXXXX
  3. Some groups disproportionality affected by unemployment. Action needed to create jobs and broaden access to employment.
  4. Recovery uneven in all scenarios. Growth focused in Kyiv and the West, exacerbating regional disparities. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
  5. Population movement remains dynamic, with new and repeated internal displacement, and cross border movement. Dnipro, Kharkiv, Odesa and Kyiv continue to host the highest number of IDPs, while also receiving the highest numbers of returns. Both Ukrainian and Russian efforts to take more territory will result in displacement and evacuations
  6. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

The key differences between the scenarios are the extent to which different factors drive need (e.g., economic decline, missile strikes, shifts in territorial control) and degrees of access afforded. Importantly, in the event of Ukraine retaking significant territory, the re-establishment of law and order will be of paramount concern. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Trend: Reducing international funding for humanitarian response

The humanitarian appeal in Ukraine in 2022 was extraordinarily well funded at 87%. In 2023 the percentage of funding against funds requested was 68.8%. While a reduction of funding, this is comparatively good given almost all humanitarian appeals are underfunded. However, in real terms funding for humanitarian dropped by just over $1 billion USD from year one to year two.

Arguably with needs more acute at the outset of the invasion, triggering as it did a level of displacement not seen globally for decades and requiring a massive scaling up of humanitarian operations, it follows logically that funding needs would reduce. Reduced funding following a significant spike in need is a well-established trend across multiple humanitarian contexts. This speaks to an overarching global problem where humanitarian needs far outpace available resources, a problem which is becoming more acute over time.

1. We judge that overall funding for humanitarian in Ukraine will follow this pattern and continue to reduce over time. In best case scenarios this will reflect a hand-off to recovery and reconstruction activities. But experience in multiple contexts shows humanitarian funding can, and often does, reduce without a correlating reduction in need. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
2. In context of diminishing international humanitarian funding, there will be consequential reductions in the operation of international humanitarian actors over time. This underlines both the importance of the localisation of the humanitarian response and strengthening delivery of essential services through GoU as part of the longer-term sustainable approach.

Trend: Poverty is increasing, a humanitarian ‘crisis within a crisis’ is possible

In parallel with the scale of challenge on recovery there are emerging signs of households struggling to meet their basic needs which does not correlate directly to Russian military attacks. The strain on the economy at the community and household level illustrates the potential for a ‘crisis within a crisis’. Poverty is increasing, with an additional seven million people falling into poverty in 2023. Unemployment, already reaching an all-time high in 2021, fell to 15.5% below the pre-war level equating to roughly 2.4m jobs [29]. Of those still earning, around half report a reduced income and half of all households report not having enough money to meet their most basic needs, including medicine, food, accommodation, and utilities – this is particularly pronounced amongst IDPs[30]. Certain groups are disproportionately impacted by unemployment and increasing poverty[31].
[29] World Bank, December 2023.
[30] As the Government of Ukraine is reducing IDP payments out of fiscal necessity, there is evidence that some are moving back to unsafe areas.
[31] Persons with disabilities, IDPs, female single headed households, Roma communities and displacement is a key factor in ability to manage financial shocks IOM, General Population Survey – Round 14, September 2023.

People are increasingly resorting to negative coping strategies, including reliance on savings, accruing additional debt or selling assets. Surveys indicate 40% of all households are relying on such strategies to manage gaps in income and 20% of households’ report increasing their debt since the start of the invasion – this rises to 30% in conflict-affected areas of the East and South[32]. Around half the IDP population continue to report that they have exhausted their savings.[33] Many households are at risk of reliance on collective centres, as 20% of female-headed households and 13% of male-headed households report being unable to afford rent and utilities.[34]
[32] Reach, Multi-Sector Needs Assessment, September 2023.
[33] IOM, General Population Survey – Round 14, September 2023.
[34] CARE, Rapid Gender Analysis, October 2023

This is compounded by the enormous disruption to agriculture infrastructure and markets and disruption to food supply chains, in turn threatening the food security of already vulnerable populations. As stands, approximately one in three families in Ukraine – 11 million people – are food insecure[35]. Ukraine’s agriculture sector is also an important source of livelihoods for the roughly 13 million Ukrainians living in rural areas, many of whom are involved in small-scale agricultural production[36].
[35] WFP, War in Ukraine: How a humanitarian tragedy fed a global hunger crisis | World Food Programme (wfp.org)
[36] 32% of agricultural production in Ukraine is directly created by households Ukraine: Impact of the war on agriculture and rural livelihoods in Ukraine (fao.org)

Without action Ukraine faces increasing risks of multidimensional poverty and a decline in human development[37] indicators, as people are obliged to spend less on healthcare, reduce food consumption and are experiencing disruptions to education. Ukraine has adapted social safety net programmes to a wartime context, but people are still at risk of slipping into poverty[38]. Supporting people into work will be needed to help reduce burdens on the state and counter the risks that increasing poverty presents.
[37] The global Multidimensional Poverty Index measures overlapping deprivations across 10 indicators in three equally weighted dimensions. The Human Development Index aggregates indicators of life-expectancy, education levels and GDP per capita into a HDI score. Ukraine’s latest HDI score from 2021 had fallen by almost 2% since 2019 - Inequality-adjusted Human Development Index | Human Development Reports (undp.org)
[38] Largely the result of inflation eroding the value of social protection payments, rising and intersecting needs, inadequate targeting methodologies, and barriers to accessing assistance. As Ukraine faces a significant budget deficit and seeks to reform its social assistance towards a means-tested model, there are likely to be further barriers and delays in accessing assistance.

Trend: The rising challenge of an uneven recovery

Rebuilding Ukraine’s economy is vital to its future success and requires swift recovery and reconstruction effort wherever possible. While there has been some GDP growth in the past year, this is not, on its own, an indicator of sustainable economic recovery. It is also precarious and dependent on international donor support. Equally the cost of the damage countrywide is massive, now estimated by the World Bank to cost $486 billion and will take at least a decade to remedy[39].
[39] It should also be recognised that this assessment of damage is at a point in time and cannot be judged to be final. Russian aggression continues.

By its nature, recovery effort, particularly in its early stages, must be opportunistic and begin where it can. But UK policy recognises that progress will not be linear or even. Some regions of Ukraine have suffered very significant infrastructure damage and landmine contamination and are still under frequent attack.XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

There is a role for humanitarian actors, who can act fast and reach into more difficult areas, to both promote early recovery and protect the space for more broad-based recovery when this is possible, helping to prevent the erosion of human capital. Humanitarian support also bolsters Ukraine’s resilience by helping it support its most vulnerable people, against a backdrop of Russian aggression which seeks to undermine social cohesion and exploits economic vulnerabilities.

Trend: A growing population of people with complex needs related to gender and disabilities

Gender-based violence (GBV) is rising. UNFPA estimates that 3.6 million people need GBV and response services in Ukraine. Women and girls are a heightened risk of humanitarian trafficking and sexual exploitation – not only at border crossing points and in transit, but in collective, and bomb, shelters[40]. In parallel the widespread mobilisation of men has reinforced gender narratives with implications for male mental health and women’s role in the domestic sphere[41]. An invisible group of men lack access to humanitarian support and essential services such as healthcare, access to employment and unemployment benefit as fear of conscription leads them to avoid formal registration.[42] This is particularly the case for male IDPs and members of the LGBT+ community.[43]
[40] IOM, Human trafficking in times of conflict: the case of Ukraine, November 2023
[41] CARE, Rapid Gender Analysis, October 2023. Men and adolescent boys are also less likely than women and girls to seek support services due to a higher level of stigma towards men’s mental health.
[42] Ibid.
[43] Ibid.

As the war continues, Ukraine faces enormous mental health challenges, with WHO estimating that 25% of the population will suffer from some form of mental health challenge. In parallel the number of people with disabilities is expected to increase significantly over the next five years. Soldiers and civilians will continue to acquire disabilities because of conflict, those with existing disabilities and chronic health conditions will struggle to access medical and social services, and demographic shifts will see an increasingly ageing population. People with disabilities are also least likely to be externally displaced. Family separation and depleted social services, coupled with the 2023 government decree simplifying procedures for placing people in institutions, is likely to lead to an increase in the number of people with disabilities in institutions. Only 16% of people with disabilities were employed prior to the invasion and, as livelihood opportunities in Ukraine decrease, people with disabilities are likely to face greater exclusion from the labour market and increased reliance on social protection and social services.

Many of these needs could be met through GoU-led service provision but this relies on reform, sustained support to systems strengthening, increases in quality and coverage of services and predictable financing. Even in the best-case scenarios for these efforts, there will be disruption to services in geographies under frequent attack and gaps in provision as people become newly vulnerable. A degree of humanitarian action will continue to be needed to bridge these gaps in the short to medium term.

Trend: A effective humanitarian response, but one that needs to change to meet future challenges

The scaled-up humanitarian response in Ukraine is still relatively young and not at the maturity of comparable responses at scale, i.e. Afghanistan and Syria. Levels of delivery, risk and financing having changed significantly in the last two years. We judge this will continue for at least the next two to three years.

While effective, the humanitarian response in Ukraine has needed to continuously shift gears; from rapid scale-up in 2022 and emergency response in newly retaken areas, to contingency planning for counter-offensives and responses to the Nova Kakhovka Dam, and preparation for cycles of winter and attacks on critical national infrastructure[44]. Given the unpredictability inherent in this context, it will need to maintain this agility, but also become more efficient and effective to manage the challenge of reducing budgets and to take advantage of the unique opportunities that Ukraine offers, particularly in relation to localisation.
[44] The UN-led 2023 Humanitarian Response Plan assisted 10.5 million of whom 3.8 million were IDPs, 1.8 million (mainly internal) returnees and 4.8 million non-displaced, with most of the latter group living in frontline oblasts. Multisectoral life-saving assistance was provided to 8.9 million people and access to basic services covered 6.5 million.

Improving humanitarian coordination in Ukraine will be key to ensuring quality and effectiveness over the coming period. Currently over 500 humanitarian actors work in Ukraine, more than 60% of which are Ukrainian national NGOs. This presents a challenge to both streamline humanitarian assistance for cost efficiency and ease of accessing assistance (particularly cash interventions[45]) but also to support and strengthen the ongoing Ukrainian-led response, both civil society and though the Government of Ukraine. This will be critical to the longer-term sustainability of the response and reach and effectiveness of aid in Ukraine. Robust data and analysis, including of needs in Russian held areas (insofar as this is possible) will be a strategic enabler.
[45] The UK has spearheaded the establishment of the Perekhid Initiative, an analysis function embedded in the Ministry of Social Policy to provide recommendations to the government and humanitarian actors. The next phase of the initiative will be to implement recommendations to enhance the coverage and sufficiency of shock responsive government programmes and enable the humanitarian response to focus on populations in humanitarian need who are not covered by the government systems. The UK has also commissioned a study on the role of Ukrainian actors in the provision of cash to ensure the response doesn’t take a default internationalist approach to cash.

The cluster system has taken time to gear up and remains a barrier for many local organisations who struggle to engage with the humanitarian architecture. Ukraine is a decentralised country with significant responsibility for government support and services sitting at Oblast or Hromada level. Area-based models for coordination would better serve localisation and decentralisation agendas. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXMore effort is also needed to realise the ‘centrality of protection’[46], to improve trust in reporting mechanisms and to improve access to humanitarian assistance among marginalised groups (and those living in rural areas and close to the frontline) and better tracking of progress.
[46] The centrality of protection refers to efforts by the HCT and humanitarian partners to: (1) strengthen evidence-based advocacy on the most critical protection risks; (2) promote accountability for obligations under international humanitarian law and international human rights law with the parties to the conflict and other duty bearers; and (3) ensure that all collective actions assisting war-affected people, including Internally Displaced People, seek to reduce and mitigate risks and address immediate and longer-term protection needs.

The emergency response in frontline areas is carried out at enormous risk to staff and volunteers, with responders facing regular shelling and no meaningful respect of the protection of humanitarian staff and locations by Russian forces. The operational environment and humanitarian situation in these areas will remain difficult. The delivery of humanitarian assistance in remote areas and close to the line of contact is undertaken almost exclusively by national NGOs, Civil Society Organisations and volunteer groups, who work in close coordination with local authorities and UN Agencies. Despite the conflict, civil society remains committed, effective and a significant part of emergency response capacity, but they need support[47]. Equally more consideration is needed, from the UN and donors, on risk-sharing with organisations operating in the most dangerous areas.
[47] In recognition of the importance of these organisations to delivering in the hardest to reach areas an unprecedented third of UHF funding allocated (US$119 million) has gone to local and national partners. UHF Ukraine Crisis 2023_Simplified Assessment Note_16Jan2023.pdf

Trend: An impressive civil society response, but one still developing humanitarian technical expertise
With increasingly kinetic frontlines and renewed strikes across the country, community and volunteer groups have become an essential part of the humanitarian response. Delivery of humanitarian assistance in Ukraine is often seen as ‘part of the war effort’. Many actors doing the ‘last mile’ delivery have pivoted from their previous expertise (for example in gender, democracy, media) to lifesaving activities or founded CSOs following the full-scale invasion in 2022. These groups work in the riskiest locations, close to frontlines, where INGOs and UN agencies largely do not operate. They are taking the risks to reach populations most in need.

Responsible sharing of risks with these organisations is critical to sustaining the ability of humanitarian actors to reach communities in need. This means: provision of security equipment and expertise; ensuring they have dependable longer-term funding to enable them to retain experienced staff; and supporting reasonable conditions for their staff and volunteers to reduce the burn out occurring in the response.

Recognising the level of risk, responsibility and scrutiny that comes with delivering humanitarian assistance, these actors need support to adhere to, and navigate, humanitarian principles and standards. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. Investment is also needed to support the improvement of financial controls and policies and practice on aid diversion and safeguarding, alongside support on needs assessments, targeting and specialist technical areas. Modalities like OCHA’s Ukraine Humanitarian Fund go some way to fulfilling this function, but the short-term nature of grants through this mechanism is an impediment to supporting organisational capacity over time and continuity of service-provision.

More generally, there is growing evidence on the cost effectiveness of localisation, one study[48] suggests delivery through 'local intermediaries could deliver programming that is 32% more cost efficient than international intermediaries, by stripping out inflated international overheads and salary costs’. Granularity of data for Ukraine on the cost-benefits of localisation is not yet available, as would be expected at this early juncture, but it logically follows that more direct funding to the organisations delivering assistance will reduce costs.
[48] https://thesharetrust.org/resources/2022/11/14/passing-the-buck-the-economics-of-localizing-international-assistance

The potential to do better on, and the unique opportunities to advance, localisation – a key ‘Grand Bargain’ reform[49] - in Ukraine is recognised by donors, the UN, iNGOs and thinktanks. In the UK, the Independent Commission for Aid Impact, in its recently published rapid review into the UK’s non-military aid in Ukraine[50], recommended that more aid is channelled through Ukraine’s civil society organisations to ensure sustainability of the humanitarian response. It also highlighted the lack of progress on the 2016 Grand Bargain localisation commitment, to increase funding to local actors to a target of 25%, has not been achieved by some margin. This suggests a sustained change of behaviour, by the UN, iNGOs and donors, and strategy is needed.
[49] The Grand Bargain (Official website) | IASC (interagencystandingcommittee.org)
[50] UK aid to Ukraine - ICAI (independent.gov.uk)

Trend: Best for the beneficiary? A cash response on the brink of change with reducing use of ‘gold standard’ multi-purpose cash to meet needs

Ukraine has a mature social protection system which was able to quickly scale to meet the needs of those displaced, and some of those exposed to war-related shocks. But this is not without limitations, most notably: reach in locations close to frontlines; the timeliness of assistance for people in urgent need; and the adequacy of coverage. Social protection in Ukraine was not designed to meet humanitarian needs and high inflation has eroded the value of this assistance.

As such, there has been a significant expansion in humanitarian cash assistance, both sectoral and multi-purpose cash assistance (MPCA). As of 2024 there are estimated to be over 110 cash actors in Ukraine, with around 50 managing end to end processes with many actors running registration processes.

Given the growth of humanitarian cash-based assistance (both MPCA and sectoral) following the full-scale invasion the UK, with other donors and in partnership with the UN and iNGOs, has launched the Perekhid Initiative. This aims to improve the design and delivery of humanitarian assistance through multi-purpose cash assistance (MPCA) and sectoral support, to better complement, and to prepare for transition to, Ukraine’s existing social protection systems. As of April 2024, Perekhid is being re-structured to shift from analysis into implementation of the recommendations. The initiative will develop guidance and policy to support humanitarian actors delivering humanitarian assistance through cash to implement a more social protection-informed humanitarian cash approach, aiming to improve both cost effectiveness and equity in assistance for populations.

There is robust evidence from other contexts that multipurpose cash assistance is best for the beneficiary, both in terms of sectoral outcomes, cost-effectiveness and dignity[51]. But, as set out by the Centre for Global Development, the increasing use of unconditional cash assistance poses significant challenges to the industry’s business model, as it transcends sectors and mandates. Increasing delivery through MPCA has required sustained donor intervention in responses in Lebanon and Turkey against considerable resistance[52].
[51] Numerous studies available on MPCA in Lebanon, available here: CAMEALEON
[52] The New Humanitarian | Unconventional cash project challenges aid status quo in Lebanon

The cash landscape in Ukraine is complex. Lack of agreement on technical approaches to targeting mean that humanitarian actors use a range of approaches, and individual sector modalities[53] (e.g. cash for food, vouchers for WASH) are being deployed in locations where needs are multi-faceted and where markets are functional. This is resulting in a reduction in the use of MPCA. In the first quarter of 2024, 19% of assistance was provided as cash (MPCA and sectoral) vs 32% in 2023 and 42% in and the proliferation of sector-based approaches, compounded by the fact that a large proportion of sector-based assistance is still delivered in-kind. For the many households in humanitarian need who have multi-faceted needs[54], this means they will need to access more than one type of assistance from different organisations, reducing the efficiency and accessibility of the response.
[53] External Review of the Humanitarian Cash Programme 2022–2023, Prepared by Key Aid Consulting for the Humanitarian Coordinator, December 2023
[54] 2023 MSNA Bulletin: Ukraine (November 2023) [EN/UK] - Ukraine | ReliefWeb

This, alongside the lack of agreement on intra-sectoral (reducing overlap of same-sector assistance) and inter-sectoral deduplication (reducing overlap of multi-purpose cash with sectoral assistance covering the same needs) risks even greater opportunity for unintended overlap. It also risks inefficient or wasted assistance, alongside a lack of clarity or ease of accessing assistance for people who are going through a shock.

## Moldova humanitarian trajectory and trends

1. Moldova has warmly welcomed refugees, but this support has been predicated on international support to bear the costs, of which an important element has been support to vulnerable Moldovan households both in recognition of the pressures of hosting, a rise in local vulnerabilities resulting from a spike in costs of living following the invasion, and to mitigate social tensions. Beyond the expansion of humanitarian assistance to meet the needs of vulnerable Moldovan households, efforts have been made to strengthen national social protection, education and health systems, while facilitating the socio-economic inclusion of refugees. Moldovan government capacity is stretched and will continue to be over the next five years. They will need continued international support to manage immediate burdens, but also help to strengthen systems to move away from humanitarian support while allowing refugees to access to the rights associated with their Temporary Protection status.XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXThere is a high risk that without support that Moldova will become poorer and consequently more fragile. Ensuring humanitarian assistance is delivered based on identified needs and vulnerabilities, for both refugees and Moldovans, is one way to mitigate risks of rising tensions linked to perceived discrepancies in provision of international assistance. XXXXX
2. Like Ukraine, we anticipate a reduction in international funding for humanitarian assistance in Moldova due to global strain on humanitarian financing. As such, reform of Moldova’s social protection system remains an important endeavour in achieving a more sustainable solution. This is underway, but Moldova remains some way from achieving its ambitious goals. Government social assistance is available but minimal, with only 3.4% of the population accessing the main social benefit. In the interim, humanitarian assistance for Ukrainian refugees is needed to cover critical gaps and limit use of negative coping strategies, with proportionate support to vulnerable Moldovan households where possible.

Conclusions

Drawing on the analysis in the previous sections the programme team have developed the following problem statements.

UKRAINE PROBLEM STATEMENT
In Ukraine, humanitarian needs will persist for the coming years, both because of continuing Russian attack, but also in relation to a growing population of people with complex needs and economic vulnerabilities compounded by a uneven economic recovery. Support for livelihoods will become increasingly important. Some needs will be in very hard to access locations (i.e. temporarily occupied territories or frontline areas). In parallel overall humanitarian funding will reduce and it will be imperative to spend it more efficiently and effectively and capacity must be maintained to meet continued needs and those related to spikes or shocks. The humanitarian business model needs to be challenged to work differently, primarily by prioritising Ukrainian leadership, complementing and supporting a highly capable government and civil society and ensure an efficient and quality response, that is based on strong evidence, to reach and protect those in severe need (and/or where Ukraine itself has stretched capacity). The International Community and UK should also plan for the sustainable exit of the international community at the appropriate point, ensuring Ukrainian civil society are able to handle shocks in the future, while maintaining sufficient international specialist neutral humanitarian capability.

MOLDOVA PROBLEM STATEMENT
The conflict in Ukraine has put huge pressure on Moldova’s already struggling national and civil society social protection, health, and education systems. The refugee population remains highly vulnerable and returns at scale to their place of origin are unlikely in the short to medium term. Moldovan institutions are not shock-responsive and are unable to meet the essential protection and assistance needs of Ukrainian refugees and vulnerable Moldovan communities hosting them. As a result, the basic needs of Ukrainian refugees, third country nationals, and vulnerable Moldovan hosting communities are only being met through the support of international humanitarian assistance. 'The Government of Moldova’s Social Protection system reform is ongoing, but remains extremely reliant on international technical and financial assistance. Sustainable exit of the international humanitarian community will rely on a shock-responsive social protection system, with effective support to refugees where needed, managed by the Government of Moldova and Moldovan civil society. Contingency planning for a spike in emergency need is jointly managed by the Government of Moldova and UNHCR, but this too remains fully reliant on international humanitarian assistance.

Ultimately the long-term solution to meeting needs is the cessation of Russian aggression, a just and sustainable peace, and broad-based inclusive development. Humanitarian action has a role as a bridge to these solutions, particularly in geographies where recovery will be most challenged, but cannot replace them. What timely and targeted humanitarian action can do is blunt the impact of crisis, smooth spikes in need and preserve the space for development.

If the international community does not provide humanitarian aid, it has the potential to drive and entrench a cycle of poverty in parts of the country – the domino effects of which could last for generations. Humanitarian aid offsets the immediate effects of a crisis to reduce this greater risk. While we cannot perceive every risk entailed by the absence of humanitarian aid where it is needed, typically, unmet needs increase the drivers for uncontrolled migration and drive conflict over resources. In addition, the displacement of working age populations will impact Ukraine’s economy, with one estimate that the non-return of the current refugee population could cost $113 billion in GDP[55].XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
[55] What will incentivise Ukrainian refugees to return home? Insights from an economist’s prediction. | Centre for Economic Strategy (ces.org.ua)

## The case for UK support to humanitarian action in Ukraine and Moldova

Europe’s collective security, which includes the UK, is now intrinsically linked to the outcome of conflict in Ukraine. Since invasion UK policy has been to help Ukraine to reassert its sovereignty, to defend itself, to secure a just and sustainable peace, while supporting its economic stability, recovery, and reconstruction. Humanitarian support is also part of the Agreement on Security Co-operation between the UK and Ukraine[56], which was signed by former Prime Minister Rishi Sunak and President Volodymyr Zelensky January 2024.
[56] Full text available: UK-Ukraine_Agreement_on_Security_Co-operation.pdf (publishing.service.gov.uk)

The agreement affirms that, as Ukraine begins early recovery and reconstruction, they will ensure the continuation of well-coordinated life-saving humanitarian aid where it is needed. This includes working together to ensure prioritised targeted humanitarian response which delivers to those most in need, including in hard-to-reach areas. The agreement also states participants will progressively shift the response to a nationally-led one with an emphasis on Ukrainian service provision and puts more leadership, capacity and funding in the hands of Ukrainian organisations to drive operational delivery of humanitarian services. Finally, participants confirmed they will continue to play an active role to support refugees from Ukraine.

The ICAI review on UK aid to Ukraine[57] commended the UK’s response to Russia’s invasion, noting that “humanitarian support has been rapid and flexible, effectively targeting vulnerable groups and working well alongside national social protection systems”, and recommending that FCDO should “intensify its support for localisation of the coordination and delivery of the humanitarian response”. The report specifically noted the lack of adaptation of the international humanitarian system and the need to adapt coordination mechanisms. In the following section this business case will set out how HARP will double down on efforts started under its predecessor programme on these areas.
[57] UK aid to Ukraine - ICAI (independent.gov.uk), April 2024

This business case proposes a UK funded multi-year humanitarian programme to provide lifesaving assistance to the most vulnerable people in Ukraine and Moldova. This will:

PRIORITISE humanitarian assistance to the most vulnerable people in the areas of most severe needs, mostly in the east and south of Ukraine, and for the most vulnerable refugees and host community members in Moldova.

PROTECT civilians and other non-combatants, particularly those who may face barriers to accessing assistance, with a focus on reducing exposure to risks, alleviating the effects of violence (including gender-based violence) and other forms of harm and promoting awareness and respect for International Humanitarian Law.

PREVENT the deterioration of households into humanitarian need by working closely with early recovery and economic resilience programmes and through encouraging national and community-level preparedness efforts to mitigate impact of shocks, including through shock-responsive social protection systems.

Cross cutting priorities are protection, inclusion, support to IHL, localisation as well as evidence and lessons learning. This will be complemented by targeted support to strategic enablers in the overarching humanitarian response, including data and analysis, an internal risk facility (IRF) with the ability to deploy technical expertise, operational and security support, and volunteer support.

The programme will build on areas of expertise and learning from its predecessor, the Ukraine Humanitarian Programme[58]. To capitalise on UK USP, we will focus in areas where UK thought leadership and innovation can encourage others to programme in a similar way. For example, in Ukraine, FCDO has been influential in donor coordination, among the first movers in advancing localisation, as well as directing practical support to local coordination mechanisms and volunteers. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX. We will also capitalise on our ability to work more definitively across the humanitarian and development nexus.
[58] An overview of the lessons is attached Annex A with commentary on how these lessons have informed programme design.

For Moldova, this approach is centred on a response which brings together the delivery of immediate humanitarian assistance to meet basic protection needs, whilst simultaneously providing extensive technical expertise for systems strengthening and improved, shock-responsive social protection systems at the local and national level, thereby facilitating sustainable support to benefit both refugees and vulnerable Moldovan households.

Although the programme will primarily focus on Ukraine and Moldova, given the continued volatility of the situation in Ukraine, the UK will maintain monitoring, emergency preparedness planning and the potential for IRF funding to respond to a new spike in humanitarian need in Moldova as well as within the region (most likely Romania and Poland), if the scale of displacement and associated humanitarian need necessitates this. Equally, recognising that it is impossible to predict with certainty the future, programme design will have a strong focus on ensuring agility, allowing the team the option to flex between areas of focus, depending on what the context demands.

## Coherence with broader UK programming in, and policy toward, Ukraine

While the moral case for humanitarian action in Ukraine and Moldova is self-evident, such effort also supports wider UK strategic objectives and policy for the region. UK policy has been to help Ukraine to reassert its sovereignty, to defend itself, to secure a just and sustainable peace, while supporting its economic stability, recovery, and reconstruction. The 2024 Labour Manifesto sets out that the UK’s military, financial, diplomatic and political support for Ukraine will remain steadfast.

The case for UK supported humanitarian interventions, in both Ukraine and Moldova, sits within, and contributes to, this policy and has informed the Ukraine and Moldova Country Plans. A humanitarian programme will also deliver on the UK’s commitment to ‘ensure the continuation of well-coordinated life-saving humanitarian aid where it is needed’ as set out in the Agreement on Security Co-operation between the UK and Ukraine, signed by the Prime Minister and President Zelensky January 2024.

This programme will sit alongside, and complement, a broad range of programming interventions in Ukraine and Moldova, including traditional ODA programming, and CSSF/Good Governance Fund efforts. Programme development has been undertaken in close collaboration with teams working on economic recovery and reconstruction, social recovery, World Bank Loan Guarantees, stabilisation, and governance programming. Efforts have been made not only to align proposed programming but also to further nexus ways of working. Of note in Ukraine is:

  1. This programme will take a vulnerability-focused approach to the pathway to enable people to transition from humanitarian support into jobs and livelihoods where appropriate. This will be complemented by a market systems approach in intended economic recovery programming. Supporting livelihoods though humanitarian interventions will not only capitalise on the speed the humanitarian system can bring to bear, but also enable us to work in more difficult parts of Ukraine. We will also develop links between humanitarian emergency infrastructure repairs and systemic/structural improvements or replacement of infrastructure.

  1. Building on the UK-sponsored Perekhid Initiative[59], the programme will work with delivery partners to ensure humanitarian cash programming is designed in line with recommendations for strengthened linkages with social protection and potential transition to a reformed social protection system. The programme will have a strong inclusion focus and will seek to lay the foundations for an equitable social recovery.
    [59] The Perekhid Initiative is a UK-initiated multi-stakeholder project to provide embedded technical assistance to the Government of Ukraine on the transition between humanitarian assistance and government support and services.

  1. The programme will take a community and regional perspective, supporting local coordination, the strengthening of Ukrainian humanitarian civil society, and supporting the strengthening of government systems (particularly the Ministry of Health). We will work closely with teams who are also supporting regional authorities, to benefit from their analysis and expertise on local governance structures.

Compliance with legislation and PrOF

Legislation: The intended programme will be fully compliant with the International Development Act. It will contribute to poverty reduction in Ukraine and Moldova. We judge that terrorist financing is not a significant risk in Ukraine or Moldova, but partners will be subject to routine clauses in agreements to safeguard funds against terrorist financing.

Equality and inclusion: In line with commitments in the Public Sector Equality Duty, FCDO Humanitarian Framework and other associated documents[60], the programme will adopt a twin-track approach to promoting gender equality and social inclusion in humanitarian action in Ukraine and Moldova. This will include working with partners to develop their capacity and operationalise the Inter-Agency Standing Committee commitments and guidelines on GBV, Disability, Aging and Children Protection, mainstreaming them throughout across their activities. We will also work with, and through, our partners to directly support diverse and intersecting needs of vulnerable populations, advocating for participation in planning of relevant CSOs.
[60] Including, but not limited to the: FCDO Disability Inclusion Strategy, FCDO Women and Girls Strategy, our commitments as signatories to the Charter on Inclusion of Persons with Disabilities in Humanitarian Action, UNSCR 2475, Women, Peace and Security Resolutions, and Article 11 of the UN Convention on the Rights of Persons with Disabilities.

Climate: The intended programme will not support resilience to, or recovery from, climate-related shocks. We do not anticipate this programme being ICF eligible but will keep this under review. Where possible we will encourage climate-sensitive elements i.e. provision of renewable energy-based items instead of fossil fuel equivalents[61]. Ukraine and Moldova do not face significant climate risks, but the nature of warfare in the former is leading to high levels of land contamination (unexploded ordnance and chemicals) and the potential for further flooding if dams are targeted.
[61] As a humanitarian programme HARP will be exempt from FCDO programming restrictions around using ODA to support fossil fuels.

Specific climate risks that the programme team will need to consider are: the high levels of carbon emission through importing humanitarian supplies into Ukraine and Moldova; and the provision/maintenance of energy systems reliant on fossil fuels which then perpetuates reliance. Possible mitigations are to locally procure supplies or deliver support through cash, and provide green fuel emergency measures, such as solar panels and generators, where possible.

Partnership principles: This programme will not provide direct financial support to the Governments of Moldova or Ukraine. Limited technical assistance will likely be provided, but can draw on, and be guided by, country-level partnership assessments.

Safeguarding: In line with FCDO’s safeguarding policy we will actively seek to mitigate risks of sexual exploitation and abuse of the most vulnerable. Any partner selected for funding will be subject to due diligence, including a robust assessment of safeguarding measures, with regular reminders of FCDO expectations. Regular monitoring, through third-party, field visits, and ongoing partner engagement will ensure active risk management.

Appraisal Case
## Theory of Change
In response to the Problem Statement set out in the Strategic Case, the proposed Humanitarian Assistance, Recovery and Protection (HARP) programme will address Ukraine and Moldova’s immediate humanitarian assistance and protection needs and increase their resilience through basic livelihoods support, thereby preventing a deterioration in household coping capacities. HARP will support the most vulnerable across Ukraine, as well as Ukrainian refugees in Moldova. To mitigate social tensions, and in broad support of a positive host environment for Ukrainian refugees, the programme will also deliver activities that support those hosting refugees in Moldova and vulnerable Moldovans[62]. The programme will also support civil society and Governments in both countries through systems strengthening to respond to emergency needs resulting from the Russian invasion of Ukraine, and to enhance resilience to future shocks.
[62] Primarily through complementing government services and supporting social protection reform efforts that will also benefit refugees.

In design, the programme team considered the differing contexts across Ukraine and Moldova and identified aligned objectives. Building on the objectives outlined above, HARP aims to address specific problems, via targeted interventions under four pillars: Protection, Emergency Response, Early Recovery and Systems Strengthening, and Enabling Environment. These interventions aim to drive an overarching impact across both countries as set out below:

Overall Programme Impact statement

Alleviate the suffering of the most vulnerable people affected by the war in Ukraine and Moldova and ensure their rights are protected, whilst supporting them to transition from humanitarian support where possible. Support inclusive, effective, efficient and shock-responsive systems and ensure Ukrainian and Moldovan institutions are supported and strengthened to inclusively respond to needs.

Underpinning the overall programme impact are two country specific theories of change. These are presented in detail at Annexes B and C. These can be summarized as follows:

Ukraine Theory of Change:: "IF exposure of vulnerable civilians and non-combatants to protection risks are reduced AND lives are saved through emergency response AND resilience through a sustained civil society response is promoted AND household and community level recovery is supported (particularly within vulnerable populations in the east and south) AND the local and international humanitarian response is more informed, principled, inclusive and safe, THEN the suffering of vulnerable populations will be alleviated, their rights will be protected and their dignity upheld. A contribution will also be made to early recovery as people will be enabled to rebuild their lives, access essential services and pursue sustainable livelihoods.

Moldova Theory of Change: IF the basic and protection needs of Ukrainian refugees and vulnerable Moldovans are met by the international humanitarian system in the early phases of the programme AND social inclusion of refugees is supported AND the humanitarian system is prepared to respond to shocks and mobilise emergency operations ALONGSIDE strengthening local & national Moldovan systems and capacities for social protection throughout the lifespan of the programme THEN Moldovan institutions would be better able to meet the essential protection and assistance needs of Ukrainian refugees, and by extension Moldovan communities, and would be shock-responsive for future events.

Changes needed to deliver more efficient and effective UK-supported humanitarian interventions in Ukraine and Moldova

The needs of the most vulnerable in both Ukraine and Moldova are better met through a more localised, efficient and targeted response, which supports household and community resilience. To best deliver intended impact, and build on HARP’s predecessor programme, the following shifts will be advanced in this programme.

Complementing government systems and supporting government leadership: As the humanitarian response continues to mature in both Ukraine and Moldova it must rationalise, scaling back where local authorities or national government are able to deliver while maintaining support where there are critical gaps. This programme will continue support to strained services including protection, emergency healthcare, and psychosocial support services. This will be complemented by support for systems strengthening and reform, particularly in Moldova, to ensure benefit to Ukrainian refugees and the vulnerable communities hosting them.

Streamlining the cash response: In parallel the programme will work to streamline the delivery of humanitarian assistance through cash in Ukraine, in collaboration with other donors, considering the recommendations of the Perekhid Initiative to support the continuing transition of the humanitarian caseload being supported through cash to delivery with and through more adequate social protection systems and programmes[63]. Our assessment is that we need to collectively and deliberately work on influencing the response to see the desired efficiencies and rationalisation, through both funding to the right partners and collective engagement and advocacy efforts. To do this we have secured the support of a Humanitarian Cash Expert who is conducting a short mission to Ukraine and will make recommendations on how we can use our programming and influencing to ensure that internationally established good practice and policies (including UK policies and commitments on the use of humanitarian cash assistance) are being adhered to, and to harmonise and rationalise the response. The UK also re-established a donor working group on cash and are exploring collective funding options to support a mechanism to reduce the number of actors and improve the quality of MPCA delivery. Similar initiatives in Lebanon[64] and Turkey have taken an investment of time and effort but have enhanced cost effectiveness and better respond to affected population preferences and feedback.
[63] This will need to be balanced with our objectives to advance localisation. Actors able to deliver humanitarian cash at scale are most likely to be the UN or Red Cross Movement. The programme team recognises the need for a blended cash response in order not to cut across localisation efforts. The forthcoming FCDO-funded study on the role of Ukrainian Civil Society in the provision of cash assistance will also provide a further evidence base for good practice and understanding barriers.
[64] The cash debate in Lebanon | Humanitarian Practice Network (odihpn.org)

Reaching those most in need though localisation: Civil society and volunteer groups have shouldered a major portion of the humanitarian response close to the frontlines in Ukraine, but these organisations face the greatest risks, barriers in accessing resources, and their voices are under-represented in the governance and decision-making of the response. Furthermore, the ICAI report on UK aid to Ukraine[65] recommended that “FCDO should intensify its support for localisation of the coordination and delivery of the humanitarian response in Ukraine”, noting that “FCDO continues to direct insufficient funding through Ukrainian non-governmental organisations”.
[65] UK aid to Ukraine - ICAI (independent.gov.uk), April 2024

HARP’s approach to localisation is comprehensive and cross-cutting and will be guided by the “HARP: Approach to localisation” set out in Annex D, which combines programming and influencing under overarching aims which will be reviewed throughout the programme. We will set out to:

  1. Ensure the most vulnerable and at-risk populations in Ukraine can access quality humanitarian assistance
  2. Promote adherence to humanitarian principles, standards and policies
  3. Reduce risks of diversion of assistance, safeguarding and targeting errors
  4. Support the strengthening of government and civil society response capability to transition the humanitarian caseload and support the sustainable exit of international humanitarian actors

We will track and measure progress against these aims using tools such as the Ukraine humanitarian partnership principles[66], which we are rolling out in HARP’s predecessor programme, the Localisation Baseline for Ukraine[67] to assess shifts in the participation of civil society, and will advocate for a Humanitarian Country Team Localisation Strategy and monitoring framework to track changes to the UN-led system.
[66] The Ukraine humanitarian partnership principles have been developed by British Embassy Kyiv Humanitarian Team in collaboration with Ukrainian partners and considering FCDO’s CHASE Humanitarian Funding Guidelines
[67] ICVA, A Humanitarian Localisation Baseline for Ukraine, September 2023

We will also continue our collaboration with FCDO’s Humanitarian Department who are developing a global localisation policy to identify where research, evidence or learning can be generated from Ukraine to contribute to the global evidence base on localisation, including on value for money and cost-effectiveness.

Improving coordination: Good coordination underpins quality delivery and reduces duplication. National coordination models imposed as ‘one size fits all’ risk creating parallel systems – particularly in Ukraine. Locally-led initiatives need more investment. Previously piloted support to localised models of area-based coordination will be expanded under HARP.

Supporting vulnerable households towards self-reliance: In Ukraine, recognising that humanitarian needs are being driven by lack of access to livelihood opportunities (which in turn exacerbates protection needs) HARP will expand from lifesaving activities to those contributing to household resilience i.e. livelihoods. While having a strong humanitarian dimension, this will help contribute to early recovery, including among critical groups, such as small and subsistence farmers, veterans, women, older people and people with disability.

HARP will continue efforts to protect those most at risk, recognising the highest concentrations of extreme needs in Ukraine are on the frontline and areas bordering Russia and the inherent vulnerability of refugees in Moldova. This appreciates that under all scenarios, protection needs are growing and requires a specialist response in parallel with efforts to reduce barriers to services (such as stigma and a lack of civil documentation). Similarly, the demographics of refugee households in Moldova, the vast majority of which are women and include unaccompanied children[68], necessitate ongoing protection support. This support includes access to social assistance and transfers, specialist child protection services, GBV interventions, and social cohesion activities. Underpinning HARP are three cross-cutting principles. We will continue to invest in, learn from, and apply these principles to our partnerships and advocacy in Ukraine and Moldova:
[68] In 2023, there were 1,067 unaccompanied and separated children registered in Moldova. More than 80% of refugees in Moldova are women and children and 70% of refugee households are single female-headed households. Almost 20% of refugees have one or more specific need that may heighten their vulnerability, including to sexual and gender based violence, including people with disabilities, who constitute 6% of the total refugee population.

Protection will be central to everything we do, ensuring an inclusive response which reaches those most in need. This means promoting protection and respect for International Law to uphold safety of civilians and humanitarian staff and adherence to the Joint Operating Principles to build humanitarian access to all affected populations[69]. All partners will follow protection principles, promoting meaningful rights-based access, safety and dignity to maximise the protective impact of programming. We will encourage GESI mainstreaming and tailoring of support to specific intersecting needs of the most vulnerable, removing barriers to access and inclusion, and promoting the meaningful participation of vulnerable populations in all stages of the humanitarian response.
[69] The Joint Operating Principles, promoted by the Access Working Group and overseen by the Humanitarian Country Team, set out a number of commitments humanitarian actors should follow in order to operate according to the humanitarian principles and to maintain acceptance and access in the long term. The aim is for the humanitarian community to address common challenges and operational dilemmas as consistently as possible.

We will support an enhanced focus on localisation throughout our programme, taking a broad interpretation of the concept to include a focus on representative community-level programming (for coordination, strengthening resilience) while supporting local authorities and national government structures where possible[70]. Recognising that civil society will be here long-term, we will support their development and empower them to take on leadership roles, building their capacity to respond to future shocks. Our support to localisation will also contribute to our commitment to inclusion, accountability to affected populations and reaching the most vulnerable. We will use the Ukraine Baseline on Localisation study as a tool to measure the success of the response in this[71]. In Moldova, the UK will support localisation through interventions with partners who are able to focus on community-level programming and participation, as well as those facilitating system-strengthening at the local (civil-society) and national (governmental) levels.
[70] The programme team recognises that our ambition for localisation must be contextualised within a strong understanding of the civil society ecosystem in Ukraine and cognisant of the distortionary impact UK funding could have. There will be careful coordination with other donors so help national organisations manage the challenges which come with growth.
[71] ICVA, A Humanitarian Localisation Baseline for Ukraine, September 2023

Capture evidence to bridge theory and practice and influence the response writ large. UK funding of research and analysis has been influential[72]. We will pursue the development of evidence through our programme partnerships, linking where possible to UK global policy priorities and increasingly by working with Ukrainian leaders and research institutes to ensure meaningful collaboration and ground truthing. Moldova also provides an opportunity for capturing evidence on best practice, particularly in understanding how refugee groups can be integrated into national social protection systems.
[72] Examples include the UK funded work on the environmental impacts of the war and implications of International Humanitarian Law, the latter through our partnership with the Ukrainian Red Cross Society.

HARP’s four pillar approach

HARP will consist of activities across four pillars: Protection, Emergency Response, Early Recovery and Systems Strengthening, and Enabling Environment. These activities are designed to complement each other, and through the three cross-cutting principles set out above, will support a set of overarching objectives to save lives and reduce harm. The four pillars and primary activities are set out on the diagram overleaf, followed by an articulation of how the problem statements are addressed by the planned interventions.

Figure 2: The four programme pillars with key interventions and the link to the impact statement

Figure 3: Problem statements, interventions and impact (below)

Pillar 1: Protection

Ukraine: facilitate evacuations, prevention & response to gender-based violence and child protection concerns, psychosocial support, legal assistance, promotion of respect for International Humanitarian Law and land mine risk education.

Moldova: prevention and response to gender-based violence and child protection concerns, education programming (digital learning centres), refugee accommodation

Alleviate the suffering of the most vulnerable people affected by the war in Ukraine and Moldova and ensure their rights are protected, whilst supporting them to transition from humanitarian support where possible. Support inclusive, effective, efficient, and shock-responsive systems and ensure Ukrainian and Moldovan institutions are supported and strengthened to inclusively respond to needs.
Pillar 2: Emergency Response

Ukraine: establish rapid response mechanisms for frontline emergencies, contributions to UN pooled funds in priority areas, multi-purpose case assistance (where markets function)

Moldova: cash assistance, hot food, safe spaces, emergency psychological support

Pillar 3: Early Recovery and Systems Strengthening

Ukraine: link with BE Kyiv social and economic recovery programmes via complementary activities in east and south that reduce the requirement of humanitarian and government assistance by encouraging people into work, thereby supporting local economic growth.

Moldova: technical assistance to ministry of social protection, directly and through supporting technical assistance through UN agencies in the areas of child-protection & services, education, cash assurance, social food services, establishment of the National System for Prevention of GBV and Domestic Violence.

Pillar 4: Enabling Environment
Ukraine: contingency planning and preparedness funding for information, evidence and analysis to specialist organisations, working with the assessment and analysis working groups & age and disability working group. Strengthening security for volunteer groups (e.g. provision of personal protection equipment, insurance).

Moldova: contingency planning and preparedness for emergency response.

Ukraine & Moldova: stand-by partnerships

Overall Programme Impact
Problem Statements
 Main Interventions
Humanitarian needs most acute in frontline areas, where there is increased risk of shelling and extensive landmine contamination.
Civilians across Ukraine are likely to remain exposed to the threat from military attacks as well as other protection risks, including widespread impacts on mental health.
Conflict in Ukraine puts huge pressure on Moldova’s struggling national and civil society social protection and education provisions.

Emergency needs likely to remain for the duration of the war in Ukraine and after (priority needs within vulnerable populations).
While GoU and civil society have high-capabilities humanitarian response needs to complement where capacity is stretched.
In Moldova, humanitarian needs persist for the most vulnerable refugees and Moldovans, as the government social protection system remains unable yet to cover all essential services and transfers.

Information-sharing space not yet well-coordinated
Critical and dangerous humanitarian work carried out by volunteer groups and local CSOs who lack protection and access to information in Ukraine.

In Moldova, contingency planning for a spike in emergency need (i.e. new spike in displacement of Ukrainians) remains essential

Ukraine Household-level economic resilience likely to deteriorate in all scenarios (particularly among vulnerable groups and those remaining in regions affected by attacks/fighting)
Uneven recovery processes undermine poverty reduction and social cohesion gains in Ukraine.

GoM’s social protection system reform is ongoing,but remains extremely reliant on international technical and financial assistance.

## Approach options

Under this theory of change, three options were considered for the UK’s humanitarian approach in Ukraine and Moldova.

Option	Pros	Cons
Do nothing: Withdraw UK funding from humanitarian in Ukraine and Moldova, look to other donors to pick up slack.	Allows finite ODA to be reallocated to other Ukraine, or global, priorities.	Would contradict UK commitment to broad-based support to Ukraine. / XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX / Signalling effect to other donors, suggesting that they can reduce their contributions and/or frustrations on UK not sharing burdens. / Given we know overall humanitarian funding to Ukraine will drop significantly, in a context where needs are already deepening, we would increase the drivers for displacement and conflict over resources and instability in Ukraine. / A loss of reputation and significant reduction of influence in the overall humanitarian response, compounded by a loss of in-house expertise working on Ukraine XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
Limit support to immediate humanitarian response only: This would see a reduced focus with priority given to emergency response, primarily in the east and south of Ukraine across frontlines, with some support for refugees in Moldova.	Fulfils UK commitments to broad-based support to Ukraine. / Maintains some influence on the overall humanitarian response albeit reduced. / Would likely mean reduced ODA requirement, allowing for resources to be switched to deliver against other UK priorities.	Likely to mean proportionately more money through UN actors. / Geographies in need may shift significantly. / No UK contribution to an early recovery through humanitarian interventions, particularly in areas where resilience is very challenged. / Limited ability to invest in longer term solutions i.e. systems strengthening. Contributes to siloed approaches.
A humanitarian, recovery and systems strengthening programme.	Fulfils UK commitments to broad-based support to Ukraine and maintains UK leadership in humanitarian space. / Maximises opportunities to advance localisation and to work across the humanitarian development nexus (a UK USP) / Offers opportunity to make contribution to wider UK strategic commitments on early recovery, helping to mitigate risks posed by uneven recovery in Ukraine and a blended approach which help reduces the drivers for displacement. / Most agile option which can flex to multiple scenarios and risks, including significant displacement into Moldova. / Invests in longer-term solutions through systems strengthening. / Opportunity to advance UK thought-leadership and develop proof of concept on innovations which can then be applied globally.	Complexity of programming effort will require a larger team to deliver (as opposed to channelling funds primarily through the UN). / Opportunity cost of spending on humanitarian interventions in Ukraine and Moldova, versus a development intervention or indeed another context.

Table 1: Options for the overarching focus of the HARP programme

Doing nothing was discounted, not least because of the UK’s commitment to humanitarian as set out in the Agreement on Security Co-operation between the UK and Ukraine but also because it benefits Russia’s strategic goal of the complete eradication of Ukrainian statehood. The option to limit focus to immediate needs and essential humanitarian support in current areas of severe need was also rejected in the scoping phase. This was primarily because it would place limits on what the programme is able to do in geographies that quickly shift from humanitarian need into early recovery and ignores key resilience work that aims at preventing a further deterioration of conditions amongst vulnerable populations.

The third option is recommended. This option would give us the ability to respond to the context as it evolves over the duration of the programme, leaning more into humanitarian response if there is an uptick in military activities and/or territorial changes, or other significant events resulting in increased humanitarian need. It would similarly be able to shift into more resilience and early recovery support in the eventuality of a frozen conflict or moves towards peace negotiations. It also invests in longer-term more sustainable approaches through systems strengthening.

As a donor the UK is also well placed to operate across humanitarian and recovery work, with a Development Director that covers programming across the humanitarian/nexus/recovery portfolio allowing for programme linkages between each stage and no financial rules limiting us to spend certain budgets on humanitarian or development activities. These characteristics, alongside the fact that our humanitarian, recovery and development functions are collocated with our diplomatic and political efforts mean the UK can better harness the full range of diplomatic, humanitarian and development levers to work towards our objectives in Ukraine.

The scoping process for this option incorporated close collaboration with other embassy teams, this helped defined the humanitarian space and appropriate contribution to early recovery – to maximise complementarity with broader UK aid spend in Ukraine. This programme will provide an opportunity to ensure linkages to the work of other actors and embassy programming on jobs, livelihoods, government support and social recovery[73].
[73] For example, through strengthening pathways for households in the east and south to move from receiving humanitarian assistance into jobs, supported by wider economic recovery work. This reduces reliance on humanitarian and government support and has benefits for local and national economic development.

The above options have been appraised in more detail according to scoring criteria as per the table below, with a score of 0-5 applied across all criteria. Criteria include the ability to deliver the theory of change, deliver relevant UK strategic priorities on Ukraine, build on learning and deliver effectively and flexibly.

Scoring criteria	Option 1 - Do nothing	Option 2 - Humanitarian assistance and protection only	Option 3 - Humanitarian assistance, protection, recovery and systems strengthening
Ability to deliver across all four outcomes	0 – no delivery	4 – would deliver three of four targeted outcomes but limited ability to contribute to early recovery and systems strengthening	5 – a broader programme can effectively contribute to all intended outcomes for Ukraine and Moldova in the theory of change
Ability to deliver cross-cutting objectives	0 – no delivery	4 – limited ability to deliver on supporting localisation in the recovery sector and to support inclusive government systems strengthening efforts. Lost opportunity to contribute to learning on what works to support recovery in the East and South.	5 – a humanitarian, recovery and systems strengthening programme can effectively deliver all cross-cutting objectives across the intended outcomes in Ukraine and Moldova.
Ability to deliver on FCDO commitments and ambition on Ukraine	2 – FCDO’s commitments to Ukraine would be delivered via budget support, recovery and other programmes, as well as through diplomatic and military means. However, UK support to the most vulnerable people of Ukraine would be significantly curtailed as this is the largest FCDO intervention focussing on the most vulnerable Ukrainians.	3 – a humanitarian-only programme would still provide a crucial element of UK support to Ukraine, as part of our wider continuum of support, but would not support people as they transition away from humanitarian support in more frontline areas, thereby not supporting the comprehensive delivery of the UK’s recovery ambition. In Moldova, a humanitarian only programme would meet immediate needs of refugees and vulnerable Moldovans but would fail to provide strengthening of systems to ensure future shock-responsiveness.	4 – whilst remaining just one part of a wider range of UK support to Ukraine, a humanitarian, recovery and systems strengthening programme will provide more comprehensive support to Ukraine than a pure humanitarian programme and more effectively contributes to existing UK commitments and priorities around supporting Ukraine’s recovery[74]. In Moldova, this approach will also provide more comprehensive support, including meeting immediate needs and supporting longer-term shock-responsiveness of the country, whilst more effectively supporting the transition from humanitarian to recovery when and where appropriate.
Effectively channels learning from the first phase of humanitarian programming	1 – some learning may be able to be followed up through influencing, advocacy or centralised humanitarian relationships held by the FCDO	3 – the humanitarian aspects of the programme would draw on existing learning, but experience to date highlights the importance of complementing this with a recovery transition pathway and systems strengthening support.	5 – a programme of this scope will allow FCDO to channel all existing learning on humanitarian, systems strengthening and early recovery work into this new programme.
Ease of delivery	5 – no delivery, only close down of previous programme required	3 – a humanitarian-only programme would remain a complex, high-profile and high-risk programme, but would involve fewer outcomes and potentially fewer delivery partners.	2 – including early recovery and systems strengthening work will increase the complexity of this programme and likely the number of partners to manage. Delivering early recovery activities in the East and South of Ukraine will continue to be challenging as long as the war continues.
Flexibility	0 – no ability to flex to needs	3 – A humanitarian-only programme could be flexible to meet humanitarian needs (in terms of changing geographies or sectors) but would not be able to respond to an improved context and support people on the transition to recovery	5 – this is the only option that will allow the programme to flexibly shift between pure humanitarian and recovery and systems strengthening activities depending on how the contexts in Ukraine and Moldova evolve, allowing the programme to best respond to the context. This is critical given the ongoing volatility of the context in Ukraine.
Total scoring	8 – not recommended	20 – not recommended	26 - recommended
[74] UK boosts Ukraine’s recovery at major London summit - GOV.UK (www.gov.uk)

Table 2: Appraisal of programme scope
## Delivery Options Appraisal

The following delivery options were appraised against (1) ability to deliver HARP’s intended outcomes, (2) ability to deliver cross-cutting objectives and (3) key operational considerations, such as risk and value for money.

Delivery Option 1: Partnerships with the UN and Red Cross: this option would channel most UK humanitarian funding through a set of UN and Red Cross partnerships, assessing those who are positioned to support complementarity to the Governments of Ukraine’s and Moldova’s response and our overall aims.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

This option could deliver on our system strengthening aims and would go some way to supporting our inclusion objective. As a counterpoint, our ability to pursue localisation aims would be limited. It would also limit partner choice and curtail activities in some key areas under our protection, early recovery and enabling environment pillars. This option presents a lighter management burden than bespoke project design with partners, but the trade-off is less specificity in programming. This is because we would be buying into larger pre-existing UN/Red Cross programmes that deliver beyond the scope of UK funding. Studies on the economics of localising assistance point to savings of around 32% by programming directly with local actors rather than through international structures[75], though assessments of the impact on quality of programming is an underexplored area, for which Ukraine provides opportunities to contribute to this understanding. Programming through the UN does have the advantage of significant scale and the associated economies these afford.
[75] Analysis estimates that programming directly with local intermediaries could cost 32% less than international actors Passing the Buck: The Economics of Localizing International Assistance — The Share Trust; November 2022

Honing in on localisation aims within this option, the programme team considered the merits of an expanded investment in the UHF. This would offer benefits of a lower administration investment from FCDO and the fund has admirably increased the funding it channels to local actors. However, the programme team judged that the grant-based nature of funding through the UHF would limit what could be achieved in terms of broader capacity building. OCHA’s year to year budget uncertainty[76] and global demand for capable and experienced fund management staff exceeding what was available - due to the pure number of humanitarian crises in 2024 – were also considered risks to mitigate.
[76] OCHA receives only 1% of its funding through the UN’s Regular Budget and raises the remainder through extra budgetary contributions, it is therefore often underfunded for its operations.

Option 1 was rejected as it would limit our influence on key priority areas; particularly supporting the development of a tailored humanitarian coordination system and strong Ukrainian humanitarian civil society. Delivering solely through the UN often entails more limited oversight and control over how UK funding is delivered, depending on the agency selected for delivery. To support the delivery of tailored projects and objectives, NGO partnerships can be a more effective tool.

Delivery Option 2: A localised partnership approach, working exclusively with Ukrainian and Moldovan organisations.

This would be a novel approach for humanitarian donorship in Ukraine and Moldova, and indeed globally, sending a strong message on UK commitment to supporting localisation. It would require more day-to-day management, many partners will struggle to absorb additional funds quickly, and few operate at scale, restricting our ability to flex and surge our response in case of spikes in need. The overarching response would continue to be UN dominant and we would struggle under this model to influence it directly.

This option would be a strong message on the UK’s commitment to localisation and would make the most of our relative advantage vs. other donors to fund Ukrainian and Moldovan organisations directly. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXNational and international organisations will also continue to learn a lot from each other.

In Moldova, whilst national and local organisations have gained capacity and experience in humanitarian programming over the past two years, there are very few organisations able to deliver to a high quality at scale.

We also have limited direct experience of partnership with Ukrainian and Moldovan organisations to date so this option would require extensive market scoping and engagement, and multiple competitive processes, as well as multiple new due diligence assessments. It will also require a larger programme team to manage it.

Option 2 was considered, but rejected as the humanitarian response needs both the scale and experience of international actors alongside Ukrainian and Moldovan civil society.

Delivery Option 3: Deliver through the Government of Ukraine and Government of Moldova. This option would work with ministries and government delivery channels to support their capacity to meet humanitarian needs.

Options could include financing for shock responsive social protection, support to bolster State Emergency Services capacity, strengthening regional social policy offices to enable processing of government support claims and supporting oblast and hromada coordination centres.

Ukraine will need to continue to prioritise the defence of the country and does not have the capacity to meet all humanitarian needs inclusively and effectively. They have requested, and are relying on, the assistance of international organisations to meet humanitarian needs. Whilst development actors (including FCDO) plan to support the government to reform the social protection system to better meet the changed needs of the population, these are long term aims and reductions in international budget support and limited government capacity make increases in amount and coverage of social payments very unlikely in the immediate term. A recent UNICEF assessment stated that only 7.4% of social services are being covered in Ukraine. The Government of Moldova similarly does not have sufficient capacity to deliver all the activities envisaged under this programme. The complexity of some protection issues calls for principled engagement by independent specialist protection actors. Above we have also included a more detailed analysis of the constraints posed by the GoU’s social protection system.

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Option 3 was rejected as it wouldn’t sufficiently deliver on the programme objectives to assist the most vulnerable wherever they are. However, this programme will work closely with government systems to minimise the risk that the international system erodes state capacity and creates parallel structures.

Delivery Option 4 (recommended): A portfolio of UN, Red Cross and NGO partners (both national and international).

This option allows for a full range of potential delivery partners, giving us the maximum choice across all pillars, allowing HARP to provide both emergency humanitarian response activities and support a pivot to early recovery – both in a specific geography if a localised context shift requires, and across the programme if the context changes significantly. The programme will ensure a balance between UN agencies, Red Cross and NGOs, recognising the importance of the UN as the holder of the rules-based system and its continuing significance as a convener. By continuing to fund the UN, the UK will be able to influence the wider response and the funds channelled through it.

This option will deliver localisation through community-level interventions, systems strengthening support to institutions in Ukraine and Moldova, including the Ukrainian Red Cross and Moldovan Red Cross, and pooled funding enabling both national and international organisations to address evolving priorities.

This option will allow us to deliver on our localisation commitments, enabling Ukrainian and Moldovan actors to deliver community level interventions and strengthen systems at national and local levels, without losing the benefits of experience, scale, adherence to principles and specific mandates that international actors can bring to bear.

Option 4 is the recommended option. It enables us to prioritise and protect the most vulnerable by harnessing both the scale and experience of international organisations and the knowledge and the capacity of Ukrainian and Moldovan civil society, alongside working with a range of actors who can deliver across humanitarian response, early recovery, and systems strengthening pillars.

We have discounted the option of delivering purely through the private sector due to the humanitarian nature of this programme. As a donor committed to delivering in line with humanitarian principles[77] we must have confidence in our partners to deliver in this way. This is only guaranteed by delivering through humanitarian organisations, such as UN agencies, the Red Cross and relevant NGOs. While private sector partners can be used in “fund manager” type roles in humanitarian programmes, to manage a portfolio of NGO interventions, this would give FCDO less direct control and influence over these partnerships. Many partners would not be open to such management arrangements. Delivering solely through the private sector would also limit the programme’s ability to harness existing expertise in international and national organisations – it is unclear to what extent the private sector is involved in delivering the humanitarian response in Ukraine and Moldova beyond supply chain involvement. It is also unlikely that private sector suppliers would be able to deliver as economically as established humanitarian actors[78].
[77] UK humanitarian framework - GOV.UK (www.gov.uk) para 5
[78] Commercial arrangements will be considered for monitoring, evaluation, learning and research (MELR). Contractual arrangements are often relied upon to ensure effective management and control of deliverables, however, there are also many NGOs capable of delivering effective MELR work. Where appropriate, the programme will access the central HEROS contract and/or other centralised humanitarian capabilities. HEROS is currently due to run until October 2025 and the current supplier is Palladium. It is assumed this programme will continue to access services via HEROS and/or its successor in due course.

Over the following pages we have scored the delivery options.

Table: Delivery Options Appraisal Scoring (Score 0 low to 5 high)
	Delivery option 1: UN and Red Cross	Delivery Option 2: Local partners	Delivery Option 3: XXXXXXXXXXX	Delivery Option 4 (recommended): UN, RC, iNGO and NNGO
Ability to meet intended outcomes
Protection	3 – This option would preclude several strong protection iNGOs from bidding for work under this programme, weakening our potential market.	1 – given the complexity of protection issues in Ukraine, and the importance of adhering to international standards, principles and best practice when delivering protection activities, inputs and guidance from international organisations would be important to ensure quality.	XXXXXXXXXXXXXX	4 – This option allows the programme to harness the full range of international protection expertise on offer and competitively procure a protection partner who can deliver a full range of protection activities.
Emergency response	4 – UN agencies are generally well placed to meet the full range of emergency needs at scale, with their wide-ranging mandates in both Ukraine and Moldova.	3 – local organisations are at the frontline of the response in Ukraine. However, there are few national organisations that have the capacity and experience to deliver on a large scale.	XXXXXXXXXXXXX	5 – By harnessing UN, Red Cross and NGO partnerships, this programme will be able to select partners with specialist skills or mandates in specific sectors and scale partnerships up or down over the lifetime of the programme to effectively respond to need.
Early recovery and system strengthening	4 – some UN agencies are well placed to deliver livelihoods work to support early recovery and to support systems strengthening.	3 – we are not aware of local organisations that are well placed to deliver systems strengthening technical assistance. Systems strengthening work often benefits from learning from other countries, systems, and contexts.	XXXXXXXXXXXXX	4 – Broadening our delivery options on this may help the programme achieve greater value for money and will give greater options for implementation.
Enabling environment	2 – experience suggests that the UN should not be relied on as the sole delivery mechanism for the programme’s target areas including coordination, data and analysis, support to frontline organisations etc.	2 – some aspects of the enabling environment would be best delivered through national partners, i.e. localised coordination approaches. However, few Ukrainian organisations are providing safety and security advice and resources to other humanitarian actors at a national level.	XXXXXXXXXXXXX	5 – delivering across a range of enabling priorities as envisaged will require the programme to harness the niche skillsets and mandates of multiple specific partners, particularly international NGOs. These partners are already known to FCDO and fulfil specific and unique roles.
Ability to deliver cross-cutting priorities
Localisation	1 - this approach would not allow us to directly fund any local organisations and would make it difficult to support more grassroots volunteer initiatives. Supporting local organisations via UN agencies limits the extent to which local organisations can lead the strategic direction of the response.	5 – this option would robustly deliver on the funding aspects of the localisation agenda. Increased funding and advocacy support from the UK would also support national organisations to have a more significant role in decision-making and coordination structures in the humanitarian system.	XXXXXXXXXXXX	3 – this option will allow the programme to fund a number of national organisations and initiatives both directly and indirectly, while also supporting GOU and GOM leadership at national and local levels.
Inclusion	3– the UN-led response has struggled to effectively include and meet the specific needs of the most vulnerable, marginalised groups.	3 – this option presents a risk of siloing specific groups and overlooking the intersectional needs of the most vulnerable populations. This option may also limit ability to include and target the most vulnerable at scale.	XXXXXXXXXXXXX	4 – by combining the ability of UN agencies to reach people at scale and dedicate specific resource to inclusion, with the unique knowledge and expertise held by local organisations, we will most effectively achieve FCDO and International commitments on inclusion in humanitarian response.
Key operational considerations
Operational resilience	4 – across the UN system there is a good degree of resilience to various scenarios given the range of sectors covered, the volume of staff and the scale of operations.	2 – in general Ukrainian and Moldovan organisations will be smaller and have less access to funding than international organisations. This limits delivery at scale and staff recruitment and retention.	XXXXXXXXXXXXXX	5 – by funding a range of organisations with different skillsets and operational strengths, this option gives the maximum possible level of operational resilience to respond to the context.
Management requirements	4 – UN organisations XXXXXgenerally require less FCDO staff time than NGOs or private sector partners.	1 – these organisations will likely not have been managed by FCDO previously so would require closer management to ensure our requirements and expectations are met. All new organisations would require a new due diligence assessment.	XXXXXXXXXXXXXXX	3 – depending on the mix of partnerships, this option is likely to require relatively high levels of FCDO management. However, under this option the team can balance management through funding different types of partnerships with varying management burdens.
Value for money and cost-effectiveness	2 – Delivering through the UN system is generally considered to be more expensive than delivering through NGOs or through local organisations. However, the UN can effectively achieve economies of scale through large operations and there is more evidence for the quality and cost-effectiveness of UN approaches globally.	4 – national organisations are likely to have lower staff, operational and management fees, but many will not be able to deliver at scale. The quality and cost-effectiveness of the interventions would also need to be assessed.	XXXXXXXXXXXXXXXX	3 – costs will vary significantly by partner in this option, however, the overall value for money of the programme will be balanced by selecting a range of partners. This option will allow the programme to balance economies of scale, against smaller organisations with lower costs localised access to hard-to-reach beneficiaries. A range of delivery modalities will also offer ultimate flexibility and therefore a better chance of the programme continuing to meet the most pressing needs.
Risk	4 – for key UN agencies, risk processes and approaches are assessed and monitored by the UK at an institutional level. UN risk appetites have not proven to be as high as national NGOs in Ukraine.	2 – national partners are likely to be new partners for FCDO and therefore this presents a delivery and compliance risk. Risk management processes for smaller or newer organisations may be less mature. National partners in Ukraine anecdotally have a higher risk appetite to operate in frontline locations.	XXXXXXXXXXXXXXXXX	4 – under this option, risk will be well balanced across the portfolio, as the programme works with organisations with varying risk appetites and varying risk levels associated with their operations.
TOTAL SCORES	31 – not recommended	26 – not recommended	21 – not recommended	40 – recommended

Table 3: Delivery Options Appraisal Scoring

## Delivery approach under the recommended option

Following the approach and delivery option selection, and in line with the Theory of Change, the programme team have agreed in principle the following delivery partners or mechanisms against each partner. This builds on learning from HARP’s predecessor programme, experience working with and funding some partners and FCDO’s knowledge of the humanitarian sector and key actors in both Ukraine and Moldova. Our intention is both to streamline the number of partners for a more sustainable approach and advance the key objectives of the programme.

Pillar 1: Protection - to protect and support civilians at risk in Ukraine and Moldova; evacuations, case management, GBV prevention and response, Child Protection services and MHPSS.

In Ukraine, the protection pillar will be delivered through:
XXXXXX: XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Protection consortium (identified through a call for proposals): This will be led by an international organisation with strong global experience in specialist protection work in armed conflict situations. The lead NGO will work with international and Ukrainian organisations to identify and mitigate protection risks (including at community level) a) to help prevent and respond to gender-based violence and child protection concerns, b) to offer legal assistance and psychosocial support and c) potentially to enhance awareness of the risks posed by landmines and unexploded ordnance. As well as service delivery, the consortium will engage in advocacy, protection and access analysis and potentially technical support to GoU, Ukrainian lawmakers and other actors to improve the legal, institutional and policy environment. We will explore whether this consortium can also incorporate work to mainstream disability inclusion approaches, following on from similar projects HARP’s predecessor.

HAVEN consortium: See pillar 4; enabling environment.

In Moldova, the primary delivery mechanisms for this pillar will be:

UNICEF: UNICEF Moldova will support protection programming, with a focus on child protection and disability support and technical assistance to further child protection service reform delivered by the Government of Moldova. This reflects UNICEF’s unique expertise in these areas in Moldova. We judge they are the only provider who can provide these activities and advance social protection systems strengthening.

UNFPA: UNFPA to continue their work preventing and responding to Gender Based Violence, supporting Safe Spaces for refugees, youth, elderly, and other marginalised groups, and on inclusion activities for the elderly including social cohesion activities for refugees and vulnerable Moldovans. Our previous work with UNFPA has illustrated their extensive experience in GBV in Moldova and the leadership they can bring to bear in regard to systems strengthening more broadly[79].
[79] UNFPA are part of the National Programme for Preventing and Combating Violence Against Women and Girls and Domestic Violence 2023-2027 in Moldova.

Pillar 2: Provision of Emergency Response - the provision of lifesaving emergency assistance to save lives and alleviate suffering while promoting resilience and restoring dignity for individuals and communities affected by the war. Including in-kind, humanitarian cash, emergency repairs and basic services.

In Ukraine our emergency response programming will be delivered by:

Ukrainian Red Cross Society: We have selected UCRS given their long history in Ukraine, that they will be present for the long-term, and in recognition of their status as an auxiliary to the Government of Ukraine. Through our funding URCS’s highly capable emergency response mechanism will be maintained, with a wider focus on branch development for community resilience, support and reintegration of veterans, support to people with disabilities and health support[80]. This will be a continuation of a partnership URCS (through British Red Cross) from HARP’s predecessor programme. To further advance our commitments to localisation we will look to transition the partnership to a direct FCDO-URCS arrangement.
[80] XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

OCHA Ukraine Humanitarian Fund (UHF): The UHF allows donors to pool contributions into single, unearmarked fund which then disburses to a wide range of partners. It is a tool that not only supports a swift response to spikes in need and tackles underfunding it also helps to realign incentives in the response – by forcing field-level trade-offs and priority setting – across agencies and sectors based on a comprehensive view of needs, priorities, and gaps. By contributing to this fund, we are able to encourage further localisation, leveraging the contribution of other donors, through our membership of the fund’s Advisory Board.

Complementary emergency response activities: In recognition of the need to streamline and refine the provision of emergency humanitarian assistance, this project will deliver lifesaving assistance in whichever way is most efficient – assistance by local actors who can provide where others can’t, or multi-purpose cash where markets are functioning and needs are multi-faceted.

The value-add of this approach is that our funding, alongside our influencing, will enable the UK to (1) support the development of Ukrainian humanitarian civil society to ensure the response is principled, efficient and delivered within humanitarian standards, where we assess additional wraparound support is needed to do this, and (2) use our influence with other donors to restructure the delivery of multi-purpose cash and particularly to address inefficiencies in the current system. We recognise the latter cannot be achieved immediately, and will likely take years as it did in contexts such as Lebanon, but it is critical to a more efficient and effective overall response and will deliver considerable benefits.

To develop our approach we have secured a short-term consultancy on humanitarian cash to: assess the underlying issues in cash provision, with a focus on what is best for the beneficiary and most efficient and effective; and provide recommendations on how donors can use our programming to ensure adherence to internationally agreed good practice and policies in Ukraine, and to rationalise the response.

Based on the recommendations of this work, and those of the Perekhid Initiative, we will continue to pursue a harmonised approach with humanitarian donors and identify an trusted cash partner to deliver humanitarian assistance to basic needs through MPCA. Alongside this we will assess existing granting mechanisms supporting Ukrainian-led humanitarian response and identify a mechanism which is able to bolster the development needs we have identified towards our localisation aims set out in Annex D. We will prioritise organisations who can support a comprehensive response to basic needs, based on preferences and circumstances, and are able to deploy response modalities appropriately.

This will build on three years of experience through the current programme and learning in supporting Ukrainian civil society and collaboration with grant mechanisms including UHF. We will use our MELR facility to develop a stronger evidence base on ‘what works’ in Ukraine, with a focus on value for money and cost effectiveness in this context. This does not currently exist at the level we see in much longer established responses and requires investment.

In Moldova, provision of emergency response programming will be carried out through:

  1. World Food Programme: WFP will deliver cash-based assistance to vulnerable populations, such as refugee-hosting households, and hot food in Refugee Accommodation Centres. In parallel, it will provide technical assistance to the Ministry for Labour and Social Policy. This will be focussed on improving vulnerability profiling, optimising data access, and better beneficiary targeting and inclusion. WFP have been directly selected as a existing partner which has been assessed to perform strongly in the desired areas[81] and their ability to scale up rapidly in the event of a spike in displacement. If the context in Moldova remains stable, we envisage being able to phase out our support to WFP partway through this programme and transition to a funding relationship with the Moldovan Red Cross.
    [81] FCDO’s support to WFP scored an A+ in FCDO’s latest annual review based, in part, on programming in Moldova. https://iati.fcdo.gov.uk/iati_documents/D0004112.odt

Pillar 3: Early Recovery and System Strengthening - supporting the transition of households from humanitarian assistance into self-reliance through jobs and livelihoods in conflict affected geographies. Supporting community level resilience and government system strengthening.

In Ukraine, early recovery and system strengthening will be delivered through:

  1. Livelihoods partner here are a number of well-known organisations delivering livelihoods[82] programmes. Through market engagement we will assess the best route to identifying a partner who can deliver against our objectives. The FCDO resillience-focused livelihoods programme will seek to support: access to dignified livelihoods; support for the protection and restoration of Micro/small and medium enterprises; as well as agricultural support for small/backyard farmers from vulnerable demographics. We will explore sharing livelihood partners with the planned Economic Recovery and Resilience programme to allow for complementarity to further nexus ways of working and look to other livelihoods consortiums funded by donors.
    [82] Including but not limited to: IOM’s community based resilience work and links to data services, FAO’s agricultural and support to rural livelihoods approach, and DRC’s protection-led livelihood programme.

  1. Ukrainian Red Cross Society: Rationale for selection under pillar 2. We anticipate our intended support to UCRS will contribute to community-level resilience.

In Moldova, early recovery and system strengthening will be delivered by:

  1. UNICEF: As per pillar 1. HARP will also work through UNICEF to embed technical social protection expertise within the MLSP. This TA will provide technical guidance for the implementation of the RESTART reform. UNICEF will also deliver community participation and engagement activities linked to RESTART to ensure this reform is truly inclusive of all levels of Moldovan society. The value add of this work lies in bringing in civil society organisations and local NGOs to lead design and implementation of the activities, supporting not only systems strengthening but localisation in Moldova. As a global leader in social protection, with access to a range of experts and learning from other contexts, as well as extensive experience working with GoM on social protection in Moldova, UNICEF is uniquely placed to provide this support[83].
    [83] These activities are subject to scoping with UNICEF and other delivery mechanisms may be explored in due course if scoping indicates this route is not viable.

  1. IFRC/Moldovan Red Cross: FCDO will both support IFRC to both build capacity of the Moldovan Red Cross and channel funds to the latter’s activities. The Moldovan Red Cross will provide service delivery and social assistance support to vulnerable Moldovans and refugees through structured volunteer networks. As an auxiliary to government, the Moldovan Red Cross has a unique role and will be a more sustainable option for supporting vulnerability in Moldova over the longer-term. This will be a new partnership under HARP. If the context remains stable in Moldova we would plan to phase out our support to WFP and start supporting IFRC/Moldovan Red Cross partway through the programme.

  1. WFP: See pillar 2

  1. UNFPA: See pillar 1

Pillar 4: Supporting an Enabling Environment - ensuring quality information, analysis, services and research underpins decision making to ensure a quality response for people in need. Strengthening and adapting humanitarian coordination for a more localised response.

In Ukraine we will support an enabling environment through:

  1. HAVEN consortium (led by Non-Violent Peaceforce): This consortium was established under HARP’s predecessor programme in spring 2023. It supports frontline volunteer groups to deliver assistance and facilitate evacuation of civilians more safely, promote International Humanitarian Law and norms, and facilitate an effective humanitarian response in Ukraine through enhanced local coordination and data collection and analysis. In addition to the assistance delivered, an explicit aim is to narrow the gaps between international and local service providers as well as conflict affected communities. The programme team judge that it is a strong fit with objectives under this pillar[84]. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
    [84] At the time of writing, it should be noted that HAVEN is yet to go through a review process. As such, while the programme team anticipates continuing support to this consortium, this will be subject to upcoming programme reviews. Pending the first review process, the consortium may be continued under the HARP with the same or a reconfigured set of specialised partners, or the project may be put out for a call for proposals.

  1. Operational coordination: Operational coordination ensures day-to-day activities are agreed and shared among those on the ground within a given geographic area. Often informal, it can be carried out through messaging services such as WhatsApp. This prevents duplication of efforts and helps highlight gaps. While OCHA considers its role in area-based coordination, we will build on our operational coordination successes locally[85].. Assessments indicate that operational coordination has improved, but ensuring this local level information and knowledge, built through operational coordination networks, is fed into the Government and UN planning, and ultimately decision making and funding needs further work. Joint coordination and analysis led by local government will also be essential as early recovery actors step up engagement. By learning from our existing programming, we will strengthen ongoing operational coordination partnerships and identify opportunities that support the creation of an effective area-based coordination model. We will explore opportunities to engage throughout our partnerships.
    [85] HAVEN has provided sustained operational and technical support to Kharkiv and Zaporiska Regional Coordination Centres and is expanding localised coordination in Mykolaivska and Khersonska through the Legal Development Network. Work is also ongoing on local recovery plans.

  1. Analysis and assessment: HARP will also identify opportunities to provide support to analysis and assessment organisations to ensure quality data quality and analysis which will underpin the overall targeting and prioritisation in the response. This could include, but is not limited to, support to Reach and ACAPS.[86] This would be delivered within the other projects mentioned above.
    [86] REACH is a leading assessment actor in the provision of multi-sectoral needs assessments. ACAPS is an independent analysis organisation providing secondary data analysis, on specific thematic areas, and humanitarian scenario analysis.

In Moldova, enabling environment activities will be delivered through:

  1. UNICEF; see pillar 1

  1. IFRC and Moldovan Red Cross; see pillar 3

Programme monitoring, evaluation, learning and research capacity and contingency

These elements will be shared across the Ukraine and Moldova contexts.

  1. MELR mechanism: with support from a commercial advisor, the HARP team will run a competitive process to identify an NGO or commercial provider(s) of monitoring, evaluation, learning and research activities. This work will include third-party monitoring. The procurement or call for proposals may be fully open, may draw on an existing relevant FCDO framework contract (depending on commercial advice) or be awarded via a restricted call for proposals. Some elements of this work may also be separated and functions shared with other programmes.

  1. Humanitarian technical expertise: In agreement with FCDO’s Humanitarian Response Group, HARP will draw upon the FCDO’s central humanitarian contract (currently HEROS) to procure humanitarian technical assistance. The programme will also make use of the Standby Partnership mechanism, whereby FCDO can pay for experts to be seconded into UN agencies on a short-term basis. This would be funded from the programme’s IRF budget line.

  1. Internal Risk Facility (IRF): Incorporating an IRF, similar to a contingency budget[87], will increase the agility of the programme, making it more shock responsive and able to respond to spikes in need or ‘black swans’. We expect to use the IRF to surge support via our existing partners. This is more efficient than in-kind support and allows FCDO to harness economies of scale with a lower management burden. If the context in Ukraine or the region necessitates the direct provision of in-kind support from the UK, the HARP programme would draw on procurement and logistics capabilities owned by Humanitarian Response Group, subject to their agreement.
    [87] IRFs can be unfunded. If there is not a direct budget allocation at the embassy level, it can be resourced through wider FCDO budgets.

The shape of the programme outlined above is illustrated in the diagram below:

Figure 4: HARP pillars with indicative interventions and partners

Measuring success in localisation

There is a nascent evidence base for the need to support civil society actors in Ukraine[88], and emerging tools to measure and track progress on localisation. This includes the forthcoming first annual Update on the Localisation Baseline and the development of a Localisation Strategy by the National Network of Ukrainian NGOs, known as ‘the Alliance’. We will also advocate for a localisation strategy to be adopted by the Humanitarian Country Team with a measurement framework.
[88] Assessment of the basic level of localization of humanitarian response in Ukraine, "Ways to support and strengthen local humanitarian activities in Ukraine", "Perceptions of localization in humanitarian response"

HARP will build on the work of its predecessor programme in designing and implementing the Ukraine humanitarian partnership principles which set out recommended indicators on partnerships, such as the passing on of overhead costs, safeguarding and GESI. These principles are currently being sensitised with partners and will be incorporated into HARP’s MEL approach to track quality of partnerships and systematic inclusion of the specific needs of affected populations.

We will further develop this approach as part of the development of HARP’s monitoring plan through (1) ensuring evidence of prospective partner ability to support these objectives in proposals, (2) setting KPIs in programme management processes where appropriate, including using the Ukraine humanitarian partnership principles, and (3) considering options for process reviews such as evaluations, alongside using research and evidence to contribute to the response effectiveness and global evidence base. Third Party Monitoring will be used to review in near real-time that delivery is as expected and will be used to course correct as needed.

Exit strategy

In line with the problem statements and theory of change articulated above, the programme's exit strategy will hinge on the localisation of the humanitarian response and the increased capacity of national Governments to respond to needs in Ukraine and Moldova - including their ability to raise revenue/sustainably finance social protection and services. This will enable the eventual exit of the international humanitarian community. HARP's localisation, recovery and systems strengthening approaches will contribute to developing the enabling environment for this outcome. This exit strategy will also be dependent on both improvements or stabilisation in both countries, leading to a reduction in scale and severity of needs, as well as continued support from development actors and international financial institutions.
## Delivering Value for Money (VFM)
This section sets out how we intend to monitor and improve VFM over time. The programme team have examined the five aspects of VFM: Economy, Efficiency, Effectiveness, Equity and Cost-Effectiveness. Our previous programme assessed and monitored VFM using the appropriate emphasis in a humanitarian emergency - quality and speed being first and foremost. These considerations remain relevant, but we will update our approach given Ukraine is now considered a protracted crisis, creating indicators to track VFM where possible. Given the fact the full-scale humanitarian response is also still relatively new in Ukraine, and the evidence base underdeveloped, HARP will also focus on building an understanding of and evidence base around humanitarian VfM in the Ukraine context.

The context remains complex and volatile and in response the programme will need to retain the ability to respond to changing needs. A key modality for this will be HARP’s IRF at (see paras 189-196). Where the programme changes it may affect some VFM indicators. For example, if the programme flexes to prioritise speed of delivery in an emergency, this could incur higher overhead costs by spending through agencies best placed to respond quickly and at scale, at the cost of economy. Any major changes will be reflected in the logframe.

Cost-effectiveness and best buys

Some of the interventions and principles that HARP will support are acknowledged as being, or having high potential to be, “best buys” [89]. For example, the core case for the cost-effectiveness of localisation is widely accepted. Previous studies on localisation have also emphasised the importance of working with effective informal local actors to build on their ongoing work, as HARP’s predecessor has done by supporting volunteer collectives via HAVEN. Oxfam have also identified the importance of conflict sensitivity assessments for understanding the likely effectiveness of local partners, stating that good knowledge of the local context and good access, might come with the risk that local actors may be bias, party to the conflict or more easily co-opted due to the pressures they face. Our approach to conflict sensitivity under HARP will address this (see the management case also).
[89] DFID Humanitarian ‘Best Buys’ Analysis [January 2019 Revision] - EED Library (Open) - 2019-01 Best buys in humanitarian contexts.pdf - All Documents (sharepoint.com)

There is also a high level of evidence for the cost-effectiveness of cash-based programming, particularly unrestricted multi-purpose cash assistance. Evidence indicates that cash transfers not only improve outcomes for the beneficiary but can also contribute to economic recovery and prosperity by supporting local trade and jobs. In Ethiopia, one dollar distributed generated up to $1.84 for the local economy[90]. Technological advances, such as digital payments prevalent in Ukraine, drive the cost efficiency of cash programming, as does delivering at scale once programmes are set up. HARP’s work to support digital cash delivery at scale through an accepted cash partner of choice responds to the evidence around cash as a “best buy" intervention. In addition, the modality for much of the livelihoods interventions will be cash, further supporting markets and responding to the evidence around best buys. Additionally, the Centre on International Cooperation[91] concluded that joint humanitarian and development programmes improve opportunities for displaced persons and host communities.
[90] Cabot Venton, C., S. Bailey and S. Pongracz, 2015, Value for money of cash transfers in emergencies, Final Report, UK Department for International Development.
[91] Center on International Cooperation, Displacement: A Framework for Development, drawing on collaboration between OCHA, UNDP, UNHCR, UNICEF, WFP, and the World Bank

We also recognise that some of the interventions HARP seeks to support have a relatively undeveloped evidence base on cost-effectiveness, for example strengthening protection through IHL training and localisation. Through its partners’ MEL systems and the programme’s MELR work, we will seek to build an evidence base around the VfM of these interventions in Ukraine and contribute to wider global evidence on the VfM of the types of interventions funded through HARP.

Equity

As a humanitarian programme we aim to reach those most in need. The most vulnerable are also the hardest (and most expensive) to reach, particularly in the areas where access is challenged. Predictability of funding and support to deliver efforts in these locations will help drive the efficiency of these more risky and potentially more expensive activities.

Supported by a full time humanitarian GESI adviser, we will continue to work with partners to ensure humanitarian assistance delivers on principles of impartiality and neutrality, supporting the most vulnerable people without discrimination in Ukraine and Moldova. We will look to remove institutional, structural and attitudinal barriers preventing equity of access to humanitarian assistance, tailoring support to the specific needs of marginalised groups, with a focus on women, children, older people and people with disabilities. Equally we recognise needs are intersectional and diverse. We will promote geographical equity by supporting an area-based approach and focusing on those in front line areas in Ukraine. In the Moldova context we will consider the balance of equity across both host and refugee communities, whilst considering all the aforementioned demographics.

Under HARP, we will continue to develop this approach to ensure support is as accessible as possible, and that support is tailored towards specific needs. The programme will adopt a twin-track approach to gender and social inclusion, by both funding assistance tailored to specific vulnerable demographics alongside mainstreaming meaningful inclusion principles across all partnerships and stages of the programme cycle.

Effectiveness narrative

The programme’s overarching aim is to: “Alleviate the suffering of the most vulnerable people affected by the war in Ukraine and Moldova and ensure their rights are protected, whilst supporting them to transition from humanitarian support where possible. Support inclusive, effective, efficient and shock-responsive systems and ensure Ukrainian and Moldovan institutions are supported and strengthened to inclusively respond to needs.” Overarching logframe indicators will be developed to keep a focus on outputs that are likely to have the best chance of saving lives and delivering humanitarian protection outcomes.

In Ukraine and Moldova, we are working in support of civilians with functioning governments at central and local levels, and an active civil society. In this context effectiveness not only applies to the immediate effectiveness of aid delivered, but also the sustainability of the response over the longer term. Achieving both means delivering a local response that a) works to strengthen and complement government systems, b) strengthens local NGO/CSO capacity, c) leaves the country better able to respond to shocks in future. VFM is most likely to be achieved by delivering our activities with, through and in support of government and local NGOs. However, the need to also achieve broader flexibility, speed, and often scale, and carefully manage fiduciary risks associated will oblige us to also deliver through international organisations.

This programme will continue to support better coordination of the local and international effort to drive effectiveness of the overall response, not limited to FCDO funded interventions. Ensuring coordination takes place at both operational and strategic decision-making level maximises efficiency of the overall response by encouraging synergies, avoiding duplication and ensuring interventions are grounded in reality.

In Moldova we will work with humanitarian systems to support refugee integration and social cohesion, to reduce the potential destabilising effects of a high per capita refugee population. Efforts on this will be monitored via close collaboration with political colleagues in BE Chisinau, monitoring of qualitative data and analysis from partners, and through outcome monitoring against our activities in Moldova. In support of effectiveness, cash and local procurement will also be used where possible to ensure humanitarian responses benefit the local economy[92]. Where possible we will also look for interventions where we can exploit synergies with other HMG programming to increase programme effectiveness, for example in early recovery interventions.
[92] In this context local procurement is assessed to generally present better value for money as import costs can be avoided and there is the added benefit of injecting capital into the local economy.

Monitoring approach

As the programme transitions to better monitor the five Es, we will focus on gathering data against a refined selection of the indicative VFM indicators (table below) at partner level at proposal stage and through regular project reporting. To do this, we will draw largely on partners’ internal MEL and project management systems and will ensure sufficient staffing and budget is allocated to support this. We will then, where possible, aggregate to monitor indicators at programme level. Benchmarking of quantitative indicators will likely be internal (within the programme), although the HARP programme team will consider using comparable data sets from other humanitarian responses, where available. The programme will also collect qualitative and anecdotal VFM analysis.

For Ukraine we anticipate security restrictions which limit FCDO staff travelling outside of Kyiv will limit direct monitoring in the short-term and possible longer. We will continue to engage third-party monitoring for Ukraine), to provide an objective and thorough assessment across all the five Es, ensuring findings generate learning and are fed back into the programme. We will also consider how to use monitoring to develop case studies to support assessments against qualitative indicators, and how to build VfM into planned programme evaluations. Outcome monitoring will take place across the lifecycle of the programme, drawing largely on partner reporting.

Draft Value for money (VFM) Indicators

The following indicators will be developed and refined during programme mobilisation and implementation.

How we will ensure this?	Partner-level Examples	Draft Indicators
Economy: Are we buying inputs of the appropriate quality at the right price?
Where appropriate, we will assess partners based on cost through competitive commercial processes and calls for proposals. We will engage with FCDO commercial team to implement best practice in our commercial processes and drive down costs (for the same service) where possible. / We will assess the robustness of partner procurement processes through our Due Diligence Assessments, to ensure all partners are running open, transparent and competitive procurement processes to award contracts with competitive costs. / We will encourage partners to procure locally where possible, to drive down costs, and to help stimulate local markets. / We will (where appropriate), fund partners who benefit from economies of scale.	Engagement with partners to encourage local procurement where high proportions of budgets are spent on commodities. / Set cost-related or value for money criteria for selecting partners for consortium projects. / Engagement with commercial teams on procurement for any contracts. Deliver call for proposals in line with guidance. / Continue to fund partners where VfM benefits can be driven through economies of scale/reach, especially for commodity-dependent or wide-reaching activities.	Cost per input (for commodities); / % of local staff employed[93]; / % of goods procured locally.
Efficiency: How well are we (or our partners) converting inputs into outputs?
We will provide partners with longer term certainty over budgets to aid efficient planning and reduce start-up costs and staff turnover associated with shorter term interventions. / We will earmark funding (where appropriate) to improve transparency and better monitor and steer programme funding to drive desired outputs. / We will push for cash to be considered as the preferred modality wherever markets function.	Greater emphasis on cash assistance though selected partnerships where markets are working. / Encouraging partners to implement robust accountability to affected populations approaches to gather feedback on interventions and use this to drive improvements. / We will agree fair and reasonable overhead rates with partners.	Cost per beneficiary per type of intervention; / Cash transfers - ratio of transfer value to delivery cost; / Data and feedback from beneficiaries on the utility of the aid received.
Effectiveness: How well are the outputs of an intervention having the intended effect?
We will use targeted funding to support systemic interventions to support coordination in Ukraine, and systems strengthening in Ukraine and Moldova. / We will conduct advocacy and engagement on localisation with partners and the wider system and consider ways to drive localisation throughout the programme’s lifetime e.g implementation of localisation principles (under development). / We will engage with government, especially social protection ministries. / We will learn from localisation studies, such as the Mercy Corps localisation/vfm study, to inform programme adaptations. / We will support partners to improve the appropriateness of aid provided for the context/need and support the modification of projects through their life cycle as new needs arise/evidence changes. / We will support partner interventions through our advisory capacity and MELR contract, working closely with partners to tailor and adjust interventions to best meet the needs.	Increasing financial support, capacity building and cascading of operational costs to local actors, directly and indirectly (both through pooled und mechanisms and through first tier partnerships). / Systems strengthening technical assistance to government. / Pilot and develop contextually-appropriate local coordination mechanisms in Ukraine. / Encourage all partners to adhere to our localisation principles or to increase compliance with these throughout delivery. / Ensure learning from within partner systems and HARP’s MELR approach is harnessed to drive improvements. Refresh project plans regularly and support new or modified interventions where required due to a change in context.	% of beneficiaries reporting satisfaction with interventions delivered; / % of beneficiaries reporting satisfaction with the speed of the intervention they received; / % of beneficiaries reached through local organisations or government systems; / % of funds channelled to local organisations; / % of funds spent on capacity support to government or local organisations. / Increase in number of organisations using UK-supported local coordination mechanisms;
Equity: How fairly are the benefits distributed, in particular amongst marginalised groups?
We will engage with and interrogate needs assessments, to fully understand which groups are most vulnerable, facing the most challenges in accessing services, and the best way to support them. / We will place emphasis on accurate vulnerability-based targeting across partnerships and use advisory capacity to support partners to target the most vulnerable. / We will ensure support is tailored to the needs of these identified groups, and accessible to all. / We use engagement and advocacy, as well as robust management techniques, to encourage partners to prioritise inclusion, i.e. ensuring partners build this into all stages of the programme cycle, adhere to and report against inclusion principles (under development).	In addition to inclusion-focussed partnerships in the programme, we will mainstream inclusion throughout our programme, making it a core consideration in project proposal review and assessment processes, as well as assessing inclusion activities and progress regularly through management and reporting. / Encourage partners to dedicate staffing resource to focus on inclusion and share best practice between partners.	% of funding that is gender/disability inclusive across the programme or supporting targeted inclusion activities; / No. of partners tracking = beneficiary data disaggregated by age, sex and disability; / Case studies and qualitative data on how interventions have supported the most vulnerable groups; / Partner performance against pre-defined inclusion principles.
Cost- Effectiveness: How will the intervention have the biggest possible impact on humanitarian outcomes with the resources available?
We will ensure that all partners and project proposals are approved in line with our overall strategic objectives for the programme, and represent a credible contribution to our theory of change. / We will consider the opportunity cost of not funding partners/interventions, and adjust the funding allocations to the context to maximise the cost effectiveness of FCDO funds. / With our technical expertise and in-country presence we will engage in policy and advocacy in parallel to our programmatic interventions, to promote messages of importance to the FCDO, including localisation, access, coordination etc. to maximise the reach and impact of our funding, and influence the humanitarian systems in Ukraine and Moldova to further advance our objectives. / Where appropriate the programme will provide catalytic funding to innovative interventions and support “proof of concept” to drive the changes we want to see across the humanitarian system.	We will select partnerships on the basis of our ToC, scenarios analysis and available evidence sources to ensure our resources are deployed in the most cost-effective way to have the most impact. / Where appropriate, we will consider seed-funding, pilots and funding of a catalytic nature (including through leveraging other donor funding and the provision of technical assistance) to create impact beyond our direct funding. / We will invest in evidence and analysis to benefit the wider international community and response and support other actors to make informed evidence-based decisions. / Continuity in our position as a large donor which will support us to maintain roles on the UHF Advisory Board and as chair of the donor group in Ukraine to maintain influence around our key objectives. / If appropriate, invest in preparedness to mitigate higher costs associated with a response, i.e. prepositioning emergency supplies. / Identifying and prioritising the most vulnerable groups and geographies, to prevent further decline in standard of living.	Qualitative assessments of effectiveness completed by partners or third parties; / Poverty rates in Ukraine and Moldova (disaggregated by refugees and host population); / Food security rates; / % of the population resorting to negative coping strategies; / Track results related to technical assistance; / Evidence of UK-funded pilots or innovations being replicated; / Evidence of UK-funded evidence and analysis being used; / Case studies demonstrating examples of where preparedness or early interventions mitigated risk impacts.
[93] This is based on the assumption that staff employed locally receive a lower salary than international staff.

Table 4: HARP framework for the 5Es

Commercial Case
The Appraisal Case sets out four programme pillars and outlines the case for these to be delivered by a mixed portfolio of international and national partners. As per FCDO practice, the programme will be delivered using the following instruments: MoUs for the UN and Red Cross, Accountable Grants for NGOs and commercial contracts for the private sector. The table below outlines how this will be delivered, drawing on FCDO guidance and experience delivering humanitarian programming in Ukraine and Moldova to date. As noted, we will retain a certain level of flexibility and funding may be shifted between partners over the course of the programme, to best meet the needs of the context.

## Funding Instruments – detailed summary
Pillar	Partner/ mechanism	Funding instrument	Rationale	XXXXX
Ukraine
XXXXXX	XXXXX	XXXX	XXXXXXXXXX	XXX
Protection	Ukraine Protection Consortium	Accountable Grant	The implementing partner will be determined by an open call for proposals, but we expect this consortium to be led by an international NGO.	XXX
Protection and enabling environment	HAVEN or successor consortium	Accountable Grant	HAVEN is led by an iNGO, an Accountable Grant is standard practice for iNGO projects. If the project is reprocured we would run a call for proposals to identify a successor NGO to lead the project.	XXX
Emergency response and early recovery/ systems strengthening	Ukrainian Red Cross Society (URCS) (and British Red Cross)	MoU	Funding to URCS will be channelled via an MoU with an international Red Cross entity, namely British Red Cross, or an MoU may be signed directly with URCS.	XXX
Emergency response	Ukraine Humanitarian Fund	MoU	Funding to the Ukraine Humanitarian Fund will be channelled via an MoU with OCHA as per standard practice.	XXX
Emergency Response	Complementary emergency response activities	MoU or Accountable Grant	Depending on the partner selected we will sign an MoU, if a UN partner, or an Accountable Grant, if an NGO partner.	XXX
Early recovery and systems strengthening	Livelihoods project	MoU or Accountable Grant	We will identify a partner to lead a project focussed on livelihoods, jobs and community resilience in the East and South of Ukraine.	XXX

Moldova
All pillars	UNICEF	MoU	We will sign an MoU with UNICEF, as per standard practice for UN agencies.	XXX
Protection and early recovery/ systems strengthening	UNFPA	MoU	We will sign an MoU with UNFPA, as per standard practice for UN agencies.	XXX
Emergency response and early recovery/ systems strengthening	WFP	MoU	We will sign an MoU with WFP, as per standard practice for UN agencies.	XXX
Early recovery/ systems strengthening, enabling environment	Moldovan Red Cross Society (MRCS) and the International Federation of the Red Cross and Red Crescent Societies (IFRC)	MoU	As per standard FCDO practice for funding to national Red Cross societies, funding to MRCS will be channelled via an MoU with an international Red Cross entity, namely IFRC.	XXX
Both Ukraine and Moldova
Enabling environment	Monitoring, evaluation, learning and research services	Contract or accountable grant	Based on market engagement, FCDO will either conduct a commercial procurement or a call for proposals to identify (a) supplier/partner(s) to deliver these services. A procurement could be implemented under an existing FCDO framework for suppliers or be fully open and a partner could also be shared with other programmes.	XXX
Enabling environment	Internal Risk Facility (IRF) – existing partners under the programme or central humanitarian capabilities contract or UNHCR	MoUs, accountable grants or contracts	Depending on available budgets, funding under the IRF can be accessed each year by existing partners under the programme, or to draw on central FCDO humanitarian capabilities contracts, and by UNHCR[94]. If partners are allocated funding under the IRF, their existing agreement with FCDO will be amended as appropriate. Subject to the agreement of FCDO’s Humanitarian Response Group, needs for procurementa and logistics support, or technical expertise will be met through the central humanitarian capabilities contract.[95] Under this contract, the supplier can deploy experts into FCDO teams or can organise Standby Partnerships[96]. / For more information on programme IRF plans please refer to the management case.	XXX
XXXXXXXX
[94] UNHCR has been a partner in the predecessor programme to manage large scale displacement in the region. In similar circumstances we anticipate the programme would be revived.
[95] Current contract is HEROS and the current supplier, Palladium.
[96] Standby partnerships embed technical experts into the UN to fill short-term gaps. Experts for standby partnerships are identified from rosters managed by three iNGOs (all hold accountable grants with FCDO).

Table 5: funding instruments – detailed summary

## Expected Procurement Timeline
For indirect procurement, where partners have been identified and funding earmarked for specific activities, these partners will send a proposal for work to be funded. The programme team will ensure this aligns with FCDO and the programme objectives, and agree management arrangements, prior to signing funding agreements. Proposals will not be sought for partners where FCDO will provide unearmarked contributions to an appeal or pooled fund.

For indirect procurement, where partners are not yet identified above, procurement will be undertaken through a competitive two-stage call for proposals process. Following market engagement, applicants will be asked to submit a concept note. Successful applicants at concept note stage will then be invited to submit full proposals. Where market engagement indicates a limited pool of potential partners, the programme team may choose to run a restricted call for proposals. In this scenario, a limited number of applicants will be selected through market research and invited to apply.

For direct procurement, a terms of reference will be developed (staff resourcing allowing) in parallel to the business case approval – with the aim that procurement can commence as soon as the business case is approved. The programme team will engage with commercial experts to identify the best route to implementation – whether via an existing FCDO contract, procurement via an existing FCDO framework contract, or a new procurement.

All funding commitments will include regular opportunities to refine activities and incorporate learning. The table below provides an estimate of timelines for procurement under this programme.

HARP procurement processes	2024
Activity	May	Jun	Jul	Aug	Sept	Oct	Nov	Dec
Business case approved
Process for pre-identified partners
Proposals commissioned
Proposals clarified, management arrangements agreed
Funding agreements signed
Delivery
Process for call for proposals
Draft ToRs developed
Market engagement
Concept note stage
Full proposal stage
Project documents finalised, management arrangements agreed
Funding agreements signed
Delivery
Process for commercial procurement
Draft ToRs developed
Procurement plan agreed with commercial advisor
Market engagement
ITT launched
Bids submitted and evaluated
Post tender clarification
Contract signed
Mobilisation

Table 6: HARP procurement processes

## Partner Management
UN, Red Cross and NGO partnerships

For pre-identified partners invited to submit proposals, FCDO will clearly convey to each partner: our expectations; why they have been selected for funding; and how we expect them to align with FCDO and programme objectives. FCDO will work with partners to refine proposals as required, ensuring they are aligned with our plans and strategy.

For partners selected via call for proposals, FCDO will set out strategic objectives and expectations for funding via a terms of reference. The terms of reference will also clearly outline how the competitive process will be run and concept note and proposals assessed. Assessment criteria will cover technical, management, and cost/value for money aspects of proposals.

For UN, Red Cross and NGO partners where funding is supporting specific activities or projects, FCDO will agree clear activities and results targets with partners. Partners will then be empowered to deliver against these activities and targets, escalating any significant proposed changes or issues to FCDO for discussion and agreement on how to proceed. Performance will be reviewed against targets, through regular reporting and quarterly formal update meetings. Scrutiny of progress and financial reporting will also be used to inform payments.

Where FCDO funding is being provided to support a pooled fund or an appeal (XXXXXand UHF), FCDO will also conduct regular formal update meetings with partners, reviewing progress against standard reporting provided.

Partners will be expected to self-assess progress against annual performance targets each year. This will be complemented by an internal review by FCDO staff. These reviews will feed into the programme’s annual review each year. Partner-specific or relevant annual review recommendations will be conveyed to partners. FCDO staff and partners will agree how these should be implemented. FCDO will also work with partners to understand how activities and plans for the next year of the programme will incorporate learning from delivery to date and the latest contextual developments.

Partners will also be expected to strive to meet programme standards on inclusion, localisation and conflict sensitivity (under development). Progress and compliance against these standards will be monitored via reporting. Most partners will likely deliver through downstream local partners. To ensure we are meeting our commitments to localisation, FCDO will also regularly meet with a range of local downstream partners to enable us to directly engage them on FCDO strategy, key operational issues and to ensure our direct partners are effectively implementing our localisation standards.

HARP staff will liaise regularly with staff in FCDO’s humanitarian department responsible for maintaining institutional relationships with UN and RC partners. This will ensure experiences from Ukraine and Moldova feed into institutional conversations and keep the programme team abreast of best-practice.

Technical expertise and central humanitarian capabilities

Funding arrangements to facilitate technical expertise and central humanitarian capabilities will continue to be managed centrally by the FCDO’s Humanitarian Response Group, who are responsible for managing the performance of the current supplier (Palladium). The HARP programme team will agree clear roles for any experts and budgets with the team at Palladium, and monitor and scrutinise spend against agreed budgets.

Commercial partners

For contracted partners, FCDO will agree a set of key performance indicators (KPIs) and will be closely involved in decision-making at the contract progresses. Performance will be monitored against KPIs on at least a quarterly basis, utilising an appropriate mix of written progress reporting and formal update meetings. Payment will be made on the basis of timely and quality delivery of an agreed set of outputs. Team resources (both programme and advisory) will be identified to support sufficient contract management with appropriate levels of training and required skillsets to support these functions.

All partners

All partnerships under this programme, excluding central contracts as outlined above, will be managed by the HARP programme team, with support from a commercial advisor for technical advice on contract management and other cross-cutting advisors, i.e. a MEL advisor and a conflict advisor. The management case makes provision for a proportionate level of management, technical and programme management capacity in the HARP team.

It is expected that most, if not all, partners will conduct downstream procurement under this programme. The HARP Programme Team will ensure there are up to date due diligence assessments of all implementing partners, which include a review of partner procurement policies and practices. All lead partners will comply with the FCDO requirement to conduct due diligence assessments on downstream partners to check that robust procurement policies are in place and adhered to throughout the delivery chain.

All MoUs and accountable grants will include standard termination clauses that allow FCDO to terminate agreements early should there be performance or compliance concerns or should the context or FCDO’s strategy evolve in such a way as to necessitate this. Break points will be built into contracts at key points, such as post inception and at programme mid-point.

A mid-term programme evaluation will provide important evidence for a review of programme shape and strategy. This may see some partnerships or activities, those no longer deemed most appropriate to the strategy and context, discontinued.

Continued FCDO funding for the programme and for individual partnerships within the programme will be contingent upon i) continued relevance to the context of Ukraine and/or Moldova, and ii) satisfactory programme performance – both technical performance and value for money. Value for money will be assessed regularly throughout the programme cycle.
Value for money of proposed partnerships

The proposed option will harness the expertise of a range of pre-identified partners with unique mandates or skillsets, whilst driving value for money through competition wherever appropriate. The programme also strikes a balance between harnessing economies of scale through working with several large partners and supporting smaller-scale, sustainable, cost-effective local partnerships. The programme’s overall value for money approach is outlined at paras 122-135.

All partner budgets will be scrutinised by the HARP programme team with a view to ensuring best value for money and driving down costs where possible. When procuring NGO or commercial partners, value for money and budgets will form key parts of the proposal or bid scoring approach. Knowledge of existing partners and costs in Ukraine and Moldova will be applied to drive VFM in budgets. Detailed cost information will be assessed and benchmarked against known market rates to help ensure economy in programme contracts.

Key cost drivers under the programme are likely to include: cash or in-kind humanitarian support; staffing; management; and security costs. We will work with partners to support the procurement of the appropriate quality of inputs and staffing at the right price across the programme, ensuring that we encourage robust security approaches at all levels of the delivery chain in Ukraine. Where partners have institutional relationships with FCDO, the programme will implement standard management fee rates. For NGO and commercial partners, we will negotiate or competitively test fair, but cost-reasonable, overhead rates.

Commercial risks

Key commercial delivery risks in Ukraine are linked to the volatile context. Some actors struggle to operate in this environment, especially closer to frontline areas XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXor charge high insurance premiums to do so. To mitigate this, we have selected partners with a track record of delivery in the most conflict-affected parts of Ukraine. We will also assess ability and willingness of potential partners to operate in these areas when running procurements for HARP. It will be particularly critical that our third-party monitoring provider is able to access conflict-affected populations in areas FCDO staff cannot travel to.

Staffing and capacity is another significant risk across both Ukraine and Moldova. With the rapid growth of the humanitarian sector in both countries, the labour market has struggled to keep up. There are high levels of competition for qualified national staff. Both countries are suffering brain drain as millions of Ukrainians have fled since the war, and many Moldovans leave the country looking for opportunities in other EU countries. As above, we will work both with organisations that have track records of delivery, whilst assessing management and staffing plans in procurements. Our localisation standards for partners will also seek to mitigate the phenomenon of international organisations poaching national staff from local organisations in Ukraine.

Independent verification of project progress and quality has also been challenging to date, with HARP’s predecessor programme relying on partner self-reporting and some third-party monitoring delivered through a wider MEL contract, shared with other FCDO programming. To mitigate this, HARP will look to implement a bespoke MELR facility with a significant element of third-party monitoring planned for Ukraine and a proportionate budget allocated.

Early Market Engagement

FCDO staff routinely engage with a range of humanitarian organisations in Ukraine and Moldova, as well as holding regular consultations with a group of international NGOs in the UK. This existing knowledge of the market has been harnessed during programme design. Market engagement events will be carried out prior to all procurements and call for proposals under HARP, and publicised broadly via existing FCDO relationships, humanitarian networks (i.e. relevant UN clusters) and FCDO public platforms (i.e. FCDO supplier portal, BE Kyiv facebook page) to ensure maximum engagement and reach.

## D. Financial Case

Ninety per cent of the funding of this business case falls beyond the current spending review (SR) period and is therefore unconfirmed. We anticipate up to £50m being funded under the current SR (FY 24/25). As this business case goes beyond the SR period, appropriate termination or break clauses will be included in all partner agreements. Funding will sit on the EECAD baseline.

The proposed budget of XXXXXXXXXXover five years (but spanning six financial years), is recommended based on existing spend patterns in Ukraine and Moldova[97], which have developed as per the table below since February 2022.
[97] Figures for FY 21/22 and FY 22/23 also include funding to activities across the wider region.

FY 21/22	FY 22/23	FY 23/24	FY 24/25
XXXXXXXXX	XXXXXXXX	XXXXXXXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX / XXXXXXXXXXXXXXXXXX

Table 7: Ukraine Humanitarian Response Programme spend by financial year since February 2022

The proposed budget for this programme averages XXXXer year and continues the gradual trajectory of declining UK humanitarian funding. This assumes continuing efficiencies and rationalisation of the overarching response. At the time of writing, this feels appropriate to the context, given the lack of significant military movement in either direction in frontline areas and the fact that the humanitarian response is now more established. However, this trajectory will need to be kept under constant review due to the volatile context. Allocations through the programme will ultimately be determined by FCDO’s Development Director, allowing for a balanced portfolio of UK funded humanitarian and development investments.

Based on donor funding data and experience to date, we judge that an average of XXXXX per financial year is the minimum credible investment to allow the UK to deliver its strategic objectives and maintain its role and reputation as a leading and influential humanitarian donor. Our contributions to date have allowed the UK to establish ourselves as a “middle of the pack” donor. We have been able to access fora (much of which is ‘pay to play’), thereby influencing the thinking of other donors and their spending, as well as the overarching response. In Moldova, our targeted and consistent funding has positioned us as a key player in social protection reform, enabled us to build strong relationships with key UN agencies, as well as the Ministry of Labour and Social Protection.

We anticipate some large donors to decrease their funding to Ukraine significantly in the near future. As such stable UK funding will become more critical to the overall response and increase the UK’s leadership position amongst other donors. A strong and stable commitment to humanitarian efforts in Ukraine is also commensurate to the continuing prioritisation of Ukraine at a departmental level.

The proposed budget will enable a core multi-year programme, as well as providing an IRF allocation that can be triggered to response to spikes in need or unpredictable changes in context. IRF allocations will be governed by the process outlined in para 194. The table below outlines indicative annual spend under this programme, although during implementation funding could shift between years based on needs and budget availability. As multiple partners will be delivering activities across multiple pillars, spend is disaggregated by Ukraine, Moldova, MELR and IRF.

Programme element	FY 24/25	FY 25/26	FY 26/27	FY 27/28	FY 28/29	FY 29/30	TOTAL
Ukraine	XXX	XXX	XXX	XXX	XXX	XXX	XXX
Moldova	XXX	XXX	XXX	XXX	XXX	XXX	XXX
MELR	XXX	XXX	XXX	XXXX	XXX	XXX	XXX
IRF	XXX	XXX	XXX	XXX	XXX	XXX	XXX
TOTAL	XXX	XXX	XXX	XXX	XXX	XXX	XXX

Table 8: HARP indicative budget

Budget centre

We expect the programme to be 100% RDEL. There are currently no opportunities to utilise CDEL. If the opportunity arises finance business partners and strategic finance will be consulted. Opportunities to contribute towards ICF targets will be explored.

Funds disbursal, reporting and controls on expenditure

Funding will be disbursed in accordance with the funding mechanism in question. All funding disbursement patterns are in line with FCDO experience, PrOF guidance and best practice when working with different partners.

Accountable grants: funding will be disbursed quarterly upon submission and review of proposal, budgets, quarterly narrative and financial reports and forecasts by partners. We will pay in arrears by default, with the option to approve payment in advance on a case-by-case basis depending on need. We will always ensure partners are not paid in advance of need.

MoUs: for MoUs with UN and Red Cross partners, funding will be disbursed in accordance with central agreements and, where appropriate, earmarked to specific activities. Funding may be disbursed up to six-monthly in advance for some UN and Red Cross partners, as per standard practice across FCDO. For unearmarked contributions to appeals (XXXXX the Ukraine Humanitarian Fund), payments will be made in advance based on need. Reporting will be agreed in line with central FCDO agreements with these organisations – where possible we will push for quarterly narrative, financial and results reporting. The HARP programme team will conduct quarterly performance meetings with all partners to discuss progress, challenges and risks (including financial risks).

IRF: IRF funding will be allocated upon review and approval of applications and budgets by the programme team and approval from the programme SRO and Development Director or the appropriate senior official or Minister depending on the source of funding. Funding will be disbursed according to the nature of the partnership.

Contracts: we will seek to set up a payment by results schedule, paying based on milestones/outputs achieved.

For any payments made under the humanitarian capabilities contract (currently HEROS) for technical expertise or procurement and logistics capability, payment will be made in arrears upon receipt of invoices for services rendered or items procured.

Partners will be required to provide annual independent assurances to FCDO that funds have been used for the intended purpose through audits or audited financial statements. No funding will be in advance of need. Where applicable, partners will be required to maintain an updated register of all FCDO funded assets and provide updated registers annually. Where possible, spot checks will be conducted by the programme team or through TPM. Asset disposal will be done in accordance with the FCDO Programme Operating Framework while maximising value for money.

Ensuring accurate forecasting

The programme team will work closely with partners throughout delivery to track spend through robust relationship management and regular reporting on spend and forecasts. Due to the delivery context, the team will adopt a flexible approach to managing the programme, encouraging partners to respond to contextual changes as appropriate and to make sensible, context- and evidence-based adjustments to projects.

The HARP team will work with partners, applying their knowledge of project activities and context to ensure forecasts are as accurate and realistic as possible – encouraging partners for forecast accordingly. We will aim for variances of less than 10% in project reporting as standard. Partners will report the reasons for high variances.

Internally, we will aim for less than 5% variance for monthly forecasts and 1% variance for annual forecasts and budgets. The programme team will work to profile and forecast 90% annual budgets to spend toward ODA.

Assessment of financial risk and fraud

Ukraine remains a high-risk operating environment due to the ongoing war. XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

In both Ukraine and Moldova, the rapid scale-up of a large-scale humanitarian response presents financial risks. New organisations, or those who have grown rapidly, may struggle to embed proper compliance processes or train staff effectively. Risks such as physical misappropriation of aid (theft) and collusion are also present in these contexts. We recognise that these risks cannot be eliminated entirely but we expect that partners: strive to detect aid diversion when it occurs; investigate specific incidents; identify control weaknesses and lessons learned; and implement improvements to existing controls.

Throughout the HARP programme the team will track the risk of aid diversion and mitigate this through:

- Regular aid diversion and counter fraud training for the HARP programme team, tailored to the Ukraine and Moldova contexts
- Assessing partners’ track record of successful delivery as part of partner selection processes
- Carrying out due diligence on all partners to assess their ability to mitigate and respond to aid diversion risks and incidents. Due diligence will also assess how our partners manage aid diversion risk with their downstream partners
- Clearly communicating the importance of reporting incidents of aid diversion to all partners and reporting any incidents or suspicions of aid diversion as soon as they occur
- Regularly raising aid diversion with partners and explaining our zero-tolerance approach. Ensuring partners are aware of their obligations under the Bribery Act and counter-terrorist financing legislation
- Tracking this risk in project-level risk registers, as well as the HARP programme risk register
- Robust scrutiny of financial reporting and receipt of external audit statements
- Third-party monitoring
- Regularly escalating details of any cases to the programme SRO
- Where cases occur, working with partners to understand what happened and how risks can be better mitigated in future

As per FCDO rules, all partners will be subject to due diligence, which aims to assess any risks in the partners current control environment and identify recommendations to mitigate these risks. Where partners are subject to central assurance assessments, these will be used to inform country-level due diligence assessments. Recommendations from due diligence assessments will be communicated to the partner and tracked throughout the programme (or until completion). Where country-specific due diligence already exists under the previous humanitarian programme, the HARP programme team will do a light-touch assessment to check this due diligence is still considered adequate before new agreements start under HARP. A full refresh of due diligence assessments will be carried out every three years.

Management Case
## Governance and management arrangements
The British Embassy Kyiv Humanitarian team will manage the HARP programme, with support from staff embedded in British Embassy Chisinau. The team will retain oversight of and accountability for programme delivery. The team is envisaged to be structured initially as follows:

Role	Grade	Rationale
Humanitarian Team Leader	1 x G6	SRO responsible for the programme meeting its objectives, providing strategic leadership and decision-making
Senior Programme Lead	1 x G7	PRO responsible for day-to-day management and decision-making
Humanitarian Advisers	3 x G7	Ensure programming remains technical robust and evidence-based. Related advocacy and influencing with donors and the wider response. This can be scaled up if agreed by Humanitarian Response Group through HSOT.
Social Development Adviser	1 x G7	Ensure programme is inclusive, with appropriate linkages to social protection systems development.
Analysis and Assessment Lead	1 x G7	Responsible for humanitarian information management and analysis
Humanitarian Affairs Officer	1 x HEO	A split CBS role between programme and advisory functions to support the delivery of the programme
Senior Programme Manager	1 x SEO	Responsible for portfolio coordination, comms, compliance and programme excellence.
Programme Managers	(up to) 4 x HEOs	Lead on day-to-day programme, financial and risk management and oversight of specific projects within the programme.
Team Support and Programme Officer	1 x EO	Support with team management, financial management and oversight of specific projects.

Table 8: Proposed team structure for the FCDO HARP team

In addition to this the team will be supported by a Commercial Advisor, MEL Advisor and Conflict Advisor, who are shared with other teams. This programme will also form part of the major programmes portfolio, which will give the HARP team access to additional support from FCDO’s Centre for Delivery Department.

Experience has demonstrated that this scale of team and mix of roles and expertise best ensures robust management of this high-profile, high-risk, programme. Technical and programme management expertise is particularly essential to ensure effective management of partner activities and performance. The programme will be managed in full compliance with the PrOF rules. A lack of adequate programme or advisory resource over the longer term will necessitate a reduction of ambition.

As the programme commences, the HARP team will have to navigate various competitive processes and proposal development processes to mobilise the portfolio. The team will mitigate the management burden of this by phasing the start dates of different components, where this can be done without adverse impacts, and completing some work in parallel to the business case being signed off, where this is possible. This programme will also overlap with the existing Ukraine humanitarian programme for its first six months, which will allow mobilisation for HARP and closure for the predecessor programme to be staggered. This will allow the team to start or transition some elements under HARP immediately, whilst other partners continue receiving funding under the previous programme and transition later.

Regular peaks in programme management will occur during quarterly, six-monthly and annual reporting cycles. The team will conduct an annual review of the programme each year, drawing on information from partner reporting, regular partner engagement, third-party monitoring and any field visits. Where necessary, the team may surge advisory support through the Humanitarian or Social Development cadres, or through programme networks. Where additional staff time is required, but not available internally, the programme may draw upon consultant Humanitarian Advisors or Humanitarian Affairs Officers through central contracts.

We expect that most partners will have some pre-existing staff in place to manage activities funded under HARP but will need to conduct some level of recruitment to deliver activities. The team will work with partners to define realistic project timelines and milestones. There will not be a programme-wide inception phase for the programme, but individual inception or mobilisation phases may be agreed with specific partners. We anticipate that commercial partners will require a 3-month inception phase to hire staff, finalise workplans and budgets and key documentation. For non-commercial partners, the team will work with them to develop and finalise proposals, budgets, results frameworks and risk registers, prior to signing agreements. Continuation of funding will be dependent on continued performance (technical, compliance and financial).

During the design of this programme the HARP team have developed theories of change for programming in Ukraine and Moldova, as well as an overarching impact statement. The programme will be managed via two logframes aligned to these theories of change. The draft logframes will be finalised based on partner proposals and updated regularly. This programme will remain responsive to the volatile operating environment, we will therefore adjust results targets as required if plans change for valid contextual reasons. Partner-level results will be aggregated into these logframes to track progress against output and outcome indicators. Results will feed into programme annual reviews and, eventually, the Project Completion Review.

The HARP team will conduct quarterly performance review meetings to discuss topics such as, progress and challenges, results, key risks, financial issues (spend, forecasting and risk), learning and changes to programming, and technical areas. During these meetings project delays, issues or risks will be tackled and changes or mitigations discussed as required. At annual review, the team will scrutinise partner results reporting against logframe targets and discuss overall performance with partners. Annual reviews will be based on reporting and results, meetings with partners and their downstream partners, consultations with other key humanitarian actors, Third Party Monitoring and, where possible, field visits.

HARP will need to respond as required to the volatile context throughout its lifetime. The programme team will set out clear parameters for when partners need to revert to FCDO for approval of project or budget changes, whilst allowing some flexibility within the agreed parameters of each project. Day-to-day changes to projects will be approved at PRO level, with the SRO sighted as appropriate, and more significant or high-risk decisions being taken at SRO level.

Where appropriate, decisions or risks will be escalated through the British Embassy Kyiv governance structure, in consultation with British Embassy Chisinau if needed. Examples of significant decisions could include termination of partner agreements, inception of new partnerships to meet programme objectives, cost extensions to partners, movement of budget between financial years and movement of budget between partner projects. Day-to-day decisions could involve significant movement between budget lines within projects (>10%) and amendments to project activities.

## Internal Risk Facility (IRF)
In line with FCDO PrOF guidance this programme will include provision for an IRF mechanism. As per agreements between the FCDO and HMT, 10% of the programme budget has been allocated to this - £50m equally distributed across five years. Use of the IRF budget will be subject to available resources being allocated to HARP.

This builds upon the successful inclusion of contingency funding in HARP’s predecessor programme. In this programme, contingency funding was used to respond to the destruction of the Nova Kakhovka dam in June 2022, providing emergency flood response items to the Government of Ukraine and funding an environmental impact assessment of the resulting damage, whilst existing planned funding to programme partners was also redirected towards the dam response.

Assuming funding is available, the IRF can also complement any rapid response mechanisms delivered by our partners or embedded into partner projects.

The scope of the IRF mechanism is as follows:

  1. The IRF budget can be used where significant and unforeseen needs have arisen, that cannot be met through existing programming or to tackle underfunding in critical areas of the response. Examples of this could include, i) a rapid unexpected forward movement of the Ukrainian armed forces opens up new areas requiring immediate assistance, basic services and emergency infrastructure repairs, ii) rapid, significant and unexpected infrastructure damage in Ukraine leaves a significant population in need of basic assistance, iii) rapid and significant influxes of refugees move into Moldova or other countries in the region. Our internal data and analysis, and that of our partners and the wider humanitarian system, will be harnessed to support a recommendation to use the IRF. Where possible, we will work with partners to understand how existing FCDO funding can be reprogrammed to respond to new needs.

  1. The IRF budget can be allocated to any existing partner under the programme. It can also be allocated to activities covered by the central humanitarian capabilities contract (such as technical expertise, and procurement and transport of in-kind assistance) or to UNHCR. We have retained the ability to fund these additional mechanisms in case in-kind support is considered most appropriate, technical expertise is required (either internally or within the UN system) or in case of a regional spike in need[98]. We will ensure up-to-date due diligence assessments are maintained for all partners eligible to receive IRF funding. The HARP team may also consider mobilising new partnerships or reviving partnerships from its predecessor programme in extremis.
    [98] UNHCR holds the mandate for regional coordination and for support to refugees.

  1. The IRF budget can be used to fund any activities that fall within the scope of the HARP theory of change and geographical remit of the programme (Ukraine, Moldova or countries neighbouring Ukraine[99]).
    [99] In country donor refugee costs to newly displaced refugees in non-ODA eligible countries neighbouring Ukraine would count as ODA eligible for the first year.

We judge that an IRF represents VFM by allowing partners to respond more swiftly to spikes in need or emergencies by reducing administration burdens. IRF mechanisms are a key method for achieving the ‘speed’ aspect of the humanitarian VFM triangle, as outlined in the Emergency Funding PrOF guide[100], while also supporting programme flexibility, essential to achieving ‘effectiveness’ under the 5Es. By providing swift additional funding when required via an IRF, HARP will support partners to:
[100] PrOF Guide_Humanitarian emergency funding.docx (sharepoint.com)

  1. Procure new inputs as quickly as possible at the right quality and price (economy);
  2. Deliver inputs to beneficiaries as promptly and efficiently as possible (efficiency);
  3. Promptly reallocate staff or recruit new staff to respond to new needs (effectiveness);
  4. Avoid staff time being spent on administrative activities associated with applying for new funding and support them to spend more time designing and delivering the most effective, efficient, and equitable response possible (efficiency and equity).

The IRF will be managed by the HARP programme team. The IRF will not be proactively briefed out to partners unless there is agreed funding year on year. The IRF will be utilised in the event that technical advisers confirm a spike in need, supported by data and evidence, which warrants an additional intervention. Moving forward with an IRF allocation relies on funding being available. If IRF use is recommended, and a source of funding is secured, the team will issue proportionate guidance to partners and ask for proposals. The proposal template will include sections on anticipated results, risk, and inclusion. IRF allocations and related proposals will be subject to the following review, approval and governance structures:

  1. Review by the relevant technical advisor and programme manager to confirm if they endorse the proposal
  2. Senior Programme Manager to confirm affordability within the HARP budget or appropriate senior official if funded from the crisis reserve or a wider reorganisation of portfolio spend (which could be BE Kyiv/BE Chisinau, EECAD or DG Cone)
  3. SRO and Development Director to approve IRF funding proposal
  4. Budget identified and transferred to partner component and payment made when required, forecasting updated
  5. Programme logframe and risk register updated as required
  6. At the next available opportunity, BE Kyiv, and where appropriate BE Chisinau, programme boards to be notified of the IRF allocation

Partners will be expected to manage any IRF funding allocations as per usual management arrangements outlined above. All IRF allocation decisions will be recorded in writing and saved for audit purposes.

Where partners are paid in advance for IRF activities from HARP programme budgets, any underspend may be reimbursed to the programme or reallocated to other activities, subject to agreement by the HARP programme team. If IRF funding is allocated from a central FCDO budget, i.e. the crisis reserve, any underspend would be returned to the reserve or as directed by FCDO’s central Humanitarian Teams. If the IRF budget is available but not fully utilised, the HARP team will work with partners to reallocate this across the programme in the most effective manner at the end of the financial year.

## Programme flexibility
As noted above, in recognition of the continuing volatility in the context, this programme has been designed to be flexible. A key part of this is the IRF component as noted above, but flexibility will be embedded across the programme.

The importance of flexibility was also acknowledged in the recent ICAI review of HARP’s predecessor programme, which recommended “the design of future FCDO programmes should encompass programming options for different scenarios and the ability to adapt quickly when circumstances change”[101]. We recognise that the situation in Ukraine retains the potential for volatility and it is far from static. In 2023 it was widely anticipated that Ukraine would have further successes in military counter offensives, this did not come to pass. In the winter of the same year it was widely anticipated that Russia would target energy infrastructure at scale. This did not happen, albeit these attacks are now taking place until Spring 2024. The programme will need to be able to flex to multiple scenarios in a way that a static refugee response, or where climate risks drive humanitarian need in a more predictable way, do not have to.
[101] UK aid to Ukraine - ICAI (independent.gov.uk)

Our approach to flexibility under HARP builds on the predecessor programme, where flexibility has been assured through maintaining and releasing contingency funding, reallocating funding across the programme and having access to central humanitarian capabilities for expertise and in-kind responses. Within this there is opportunity to refine focus (phasing partnerships in and out) to respond to the reality of internal resourcing if needed.

Beyond the IRF, HARP will ensure flexibility in the following ways:

  1. Within partnerships: The HARP team will work closely with partners to monitor project progress and identify opportunities for flexibility, where the context requires. We will encourage partners to proactively notify the team when they feel changes are necessary, then work with the HARP team to propose proportionate project changes which are appropriate to the changing context and needs. We will also apply best practice in budget flexibility, allowing partners a certain degree of flexibility to shift spend between budget lines within their existing budget cap, but requiring more significant changes to be submitted to the FCDO HARP team for approval.

  1. Across the HARP programme: Across both partnerships and pillars, HARP will be able to scale activities and sectors up or down as appropriate to the context. The start of each financial year will offer an important review point to test that the spread of annual budget allocations remains appropriate and regular programme assurance discussions with the SRO can provide a further opportunity to test whether our budget is still proportioned appropriately and whether there are opportunities to reallocate budget across the programme.

Evidence, analysis and information will be critical to supporting HARP’s flexibility. Decision-making will draw on multiple sources of information and evidence such as:

  1. Reporting from and meetings with partners.
  2. Contextual information gathered by the data and analysis lead.
  3. Specific pieces of research or analysis completed by project partners or by the MELR partner(s), i.e. the mid-term evaluation will allow us to test programme performance at the halfway mark and products from partners, like displacement tracking data, will help us to understand the spread of needs.
  4. Findings from third-party monitoring (this will inform a comprehensive view on partner performance).
  5. Information gathered through external engagement with donors and the wider humanitarian system, and through internal engagement with defence, political and economic colleagues.

Programme governance structures will also be designed to support flexibility, with decisions being taken at various governance levels to ensure proportionality.

  1. Minor changes within projects will be approved at PM level, with PRO cover as deemed appropriate. Minor changes are those that do not change the fundamental objectives or nature of the project and can be delivered within the existing agreed budget ceiling.
  2. More significant changes or budget reallocations between partners would be discussed among the HARP team to agree the team’s recommended approach, drawing on technical and programme expertise, and then sent for SRO approval.
  3. Significant and fundamental shifts across the programme, i.e. a significant scale down in one pillar and scale up in another pillar, would be discussed under post governance structures, including with the Development Director who is empowered to move investments between programmes to deliver FCDO strategy. Where appropriate the HARP team would also discuss these changes with complementary programmes in the Embassy.
## Monitoring, evaluation, learning and research
Monitoring, evaluation, learning and research (MELR) capability for this programme will be identified through a competitive process. The MELR approach for this programme will focus on the following areas:

  1. Third-party monitoring (TPM) covering areas of Ukraine that FCDO staff cannot regularly travel to. TPM will monitor for quality and quantity of activities conducted, assess the knowledge of staff on the ground in key technical and compliance areas, and aim to conduct spot-checks in key compliance areas, i.e. asset spot-checks.

  1. Evaluation: to inform the ongoing effectiveness of the programme and the final impact, HARP will undergo a mid-term evaluation or review after the second year of implementation. The results of the mid-term evaluation/review will be used to inform the scale and shape of the second half of the programme and may result in significant changes to the Moldova portfolio where needs may stabilise or reduce over time. Any material changes following this evaluation would be implemented in the latter half of the programme and be formalised through a business case amendment. An end-term evaluation may also be commissioned subject to need.

  1. Learning: drawing on third-party monitoring and information from partners, the MELR provider will be asked to propose a learning approach that encourages learning between partners, thematic learning across the programme and learning from the wider humanitarian response. We will explore how to regularise collection of learning for sharing with HQ colleagues (in the case of policy collaboration, for example on localisation) and for wider dissemination to influence global humanitarian approaches.

  1. Research: given the recent scale-up of the Ukraine humanitarian response, part of the theory of change for this programme is that continued analysis will support a stronger enabling environment, which in turn supports more effective humanitarian systems. The research component of our MELR activities will allow the HARP programme to be driving the latest thinking and innovation in the response, maintaining FCDO’s role as a thought leader. Areas of focus could include localisation, inclusion, cash approaches and linkages to social protection. Where possible, the programme will aim to engage Ukrainian and Moldovan experts and institutions for this work, and/or set up advisory structures for Ukrainian and Moldovan input.

Management arrangements for the MELR facility will emphasise the requirement for the MELR work to be responsive to the context – activities will need to be defined over the lifetime of the programme and specific pieces of work may need to be commissioned on an ad hoc or unplanned basis. Forward planning will need to be balanced with flexibility. The supplier/partner(s) will be required to update workplans every quarter and to produce quarterly narrative and financial reports.[102]
[102] If a commercial supplier is used KPIs will be agreed and used to monitor and drive performance and payments will be performance and output based.

In line with HARP’s cross-cutting priority on localisation, the HARP team will explore how best to work with and through local actors through the MELR component. Early market engagement will be conducted with this in mind, and we will encourage international bidders/applicants to consider working with Ukrainian organisations.

The HARP team will also work closely with project partners to understand what evidence, analysis, learning and research work can be done by them and ensure any work commissioned through HARP’s MELR approach is complementary to this.

Indicative outputs and results

The country-specific theories of change for both Ukraine and Moldova are at Annex B and C. Indicative outputs are included in both diagrams.

Unlike many other humanitarian responses around the world, the at-scale response in Ukraine is still relatively new, as is the FCDO’s large-scale humanitarian intervention. This poses challenges in terms of both the volume of data and evidence, and a track record of results which can be used to develop future results modelling. The lack of stability of the response, which experienced an extreme surge in 2022 and is only entering its third year at the time of writing, means that those results that have been achieved to date cannot yet be utilised as a reliable dataset to model potential future results. Over the course of the HARP programme, the team will work with partners to agree results targets and ensure regular results monitoring, as well as ensuring partners have sufficient capability and budgets to support robust results collection.

## Conflict sensitivity
Conflict sensitivity and “Do No Harm” processes were developed by aid practitioners in the contexts of civil war, where the principal concerns of aid actors were to avoid fuelling violent conflict and to support opportunities for de-escalation, dialogue and peace. Some adaptation may be needed for inter-state wars of aggression, as is the case in Ukraine. However, conflict sensitivity should remain rooted in analysis and understanding the interaction between aid interventions and the broader context, identifying ways to minimise harmful outcomes and promote positive outcomes.

In preparation for the HARP programme, we will undertake discussions with other British Embassy Kyiv teams, HARP delivery partners and other donors to share analysis of conflict sensitivity risks. Building on this dialogue, we will also develop a checklist of key assumptions and questions to identify potential conflict triggers that might be caused by humanitarian aid provision. This will be shared with partners to encourage them to take these assumptions and questions into consideration at each stage of planning and delivery. We will also encourage partners to maintain capacity to have a ‘minimum standard’ of conflict analysis built into their programmes.

To demonstrate proper assessment of conflict sensitivity we will ask partners to:

  1. Understand the context, both national and the regional and local dynamics and stakeholders,
  2. Understand the potential impacts of their engagement/interventions on the context;
  3. Act upon this understanding in order to avoid negative impacts and maximise positive impacts;
  4. Regularly update their knowledge in these areas and maintain a rolling analysis of these risks and appropriate mitigations.
Following a baseline assessment against HARP’s conflict sensitivity checklist, we will ask partners to include updates against their conflict sensitivity assessment as part of their regular reporting. We will consider whether to include ongoing context/conflict analysis in our MELR mechanism and how the learning element of this mechanism can contribute to the programme’s conflict sensitivity aims.
## Risk management
The overall risk rating for the programme is severe. This risk rating reflects the volatility of the context in Ukraine, the ongoing security risks of operating in Ukraine, the high value of the proposed programme and the nature of the activities to be conducted (input-/cash-heavy in high-risk areas). HARP’s predecessor programme is also rated as severe risk and its risk appetite was agreed with the current SRO, at Deputy Director level.

The volatile operating environment in Ukraine necessitates continuous risk monitoring. The HARP will undertake the following risk management measures under the programme:

  1. Agree programme risk appetites per category with the SRO and Development Director Kyiv. These risk appetites are likely to exceed departmental risk appetite levels and, if they do, they will be escalated as required.
  2. Commission risk registers at the partner level wherever possible and appropriate as part of proposals, and ask partners to update these regularly.
  3. Drawing on partner proposal risk registers, the HARP team will develop a programme risk register, which will be updated regularly drawing on partner-level risk updates.
  4. Risk ownership will be shared across the HARP team, ensuring everyone takes an active role in the programme’s risk management processes.
  5. Risks outside of risk appetites will be escalated through programme governance chains as per the relevant PrOF guidance.

The main risks under HARP are expected to relate to:

  1. The intensification of the war in Ukraine impeding humanitarian operations
  2. The deprioritisation of humanitarian support by the international community and/or GoU, leading to increased unaddressed need.
  3. Black swan events creating significant spikes in humanitarian need that overwhelm response capacity
  4. Continued lack of access to Russian controlled territory leading to an increase in needs in those areas and potential for longer-term social inequalities and tensions with the rest of UkraineRegaining access to these territories could increase humanitarian caseloads to the extent that response capacity is overwhelmed. The inclusion of Russian nationals in humanitarian caseloads, or Ukrainians with Russian passports, could create tensions and challenges to core humanitarian principles (such as neutrality) which will create a very complex operating environment.

Aid diversion and safeguarding risks are also both high given the context. We will maintain and build on risk management approaches and mitigations from HARP’s predecessor programme to manage these, such as using third-party monitoring to check for compliance and issues, and we will deliver robust messaging to partners on these issues. Both aid diversion and safeguarding risks will be tracked at portfolio level throughout the programme.

Based on learning from HARP’s predecessor programme, we expect the risk appetites for HARP to be high to enable delivery and for residual risks to remain high. The risk management processes above are designed to manage this context effectively and will be complemented by robust partner management, ongoing context monitoring, third-party monitoring and field visits in Ukraine and Moldova, when possible, within security restrictions.

A draft risk matrix indicating the most significant anticipated risks for the HARP programme is below. This risk matrix draws on experience to date delivering HARP’s predecessor programme.

Description	Gross likelihood	Gross impact	Mitigation
Strategy and context
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX	XXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX	XXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX	XXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX	XXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX	XXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
Financial and fiduciary
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX	XXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
Safeguarding
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX	XXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
People
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX	XXX	XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

Annex A: Key lessons from Ukraine Humanitarian Programme Annual Review

The table below sets out the key findings from the Ukraine Humanitarian Programme Annual Review 2023 and offers commentary on how the future programme, proposed within this business case, will build on the learning from the previous FCDO interventions.

Finding	Action in future programme design
The programme was a good example of how FCDO’s in-house technical capability positions us well to shape the response and establish ourselves as a lead actor. However, our inability to travel outside of Kyiv, particularly to operations in the South and East of Ukraine, present challenges to programme monitoring and management of fiduciary risks	Maintain FCDO in-house technical advisory capability, bolstering this where necessary through specialist consultancies and through standby partnerships. Include provision for third-party monitoring alongside core programming, to allow for effective on the ground monitoring.
The iterative nature of humanitarian programme design in an emergency, particularly in a new context, has seen the UK represented in all sectors with a large number of delivery partners with a high programme management burden. FCDO will need to mature programming efforts, by focusing in on key sectors and interventions which will best deliver on over-arching strategies.	Programme design draws on learning from programming since 2022. Using this learning, humanitarian advisors are recommending a refined scope under this business case, on key areas of intervention where we have established expertise and experience, or where we have a unique added value as a donor.
The humanitarian business model, while effective, can easily default to supply side vs demand-led approaches. Greater effort should be made in future years of programming to understand, and design interventions against, the beneficiary experience.	We will continue to encourage partners to prioritise feedback mechanisms and design programming with beneficiaries input, encouraging them to include reflections on feedback in regular reporting. Through our Monitoring, Evaluation, Learning and Research partnership we will conduct third-party monitoring, which will gather feedback from beneficiaries, as well as wider learning work that will look at this.
Interventions in Ukraine illustrate that unrestricted cash assistance remains the preference of beneficiaries where markets operate. However, this response has led to a multiplicity of cash actors and a consequently complex environment for cash coordination. Donors will need to make choices, particularly in regard to localisation and the transition of humanitarian cash to nationally-led social protection systems.	In future humanitarian programming we will support a limited number of cash actors of choice, based on experience to date and consultation with other donors, with due deference to improving beneficiary experience and advancing localisation of the response.
Humanitarian response in Ukraine highlights the tension between ambition and delivery on localisation. Most funding continues to be channelled through traditional international partnerships, however going further in localisation is key to making the response more effective and preparing for the exit of international actors - when that is possible.	The future programme will prioritise localisation and balance this priority against the desire to continue delivery at scale, while working closely with HQ colleagues on the development of FCDO policies and procedures.
Challenges around access are likely to endure and gains through the programme will likely be marginal in isolation. Strategic progress and lasting solutions will rely on political efforts and development diplomacy.	The programme will operate in collaboration with ongoing humanitarian advocacy and diplomacy efforts. Maintaining our role as a significant humanitarian donor to Ukraine gives legitimacy to the UK’s advocacy and enhances our and enhances our access to humanitarian fora, key donors, and IASC principals.

Annex B: Ukraine Theory of Change

Problem Statement: humanitarian needs will persist for the coming years and humanitarian funding will reduce. Capacity must be maintained to meet continued needs and those related to spikes or shocks. Some of those needs will be in very hard to access locations (i.e. temporary occupied territory). The humanitarian business model needs to be challenged to work differently and should prioritise Ukrainian leadership, complement and support a highly capable government and civil society and ensure an efficient, quality response based on strong evidence to reach and protect those in severe need (and/or where Ukraine itself has stretched capacity). The UK should also plan for the sustainable exit of the international community at the appropriate point, ensuring Ukrainian civil society are able to handle shocks in the future. The Theory of Change is below:

Interpretating the Theory of Change: Each pillar is represented with a separate colour, with its own outcome statement(s) and potential outputs to be pursued. The causal pathways within each pillar are drawn using arrows of the same colour and can each be interpreted as directly contributing to the pillar’s outcome. Sometimes, outputs are expected to work together across pillars to jointly drive an outcome from another pillar. For example, the output “armed actors trained in IHL and political leadership awareness of protection recommendations improve” AND the output “evidence, information gathering and analysis inform a targeted and principled response” could work together to drive the outcomes in pillar 4 for an enabling environment. In some cases, outputs from within a particular pillar, are contributing to both the outcome within its pillar and also another pillar. For example, the output under the enabling environment pillar “local government/civil society/volunteer co-ordination networks supported” is not only expected to drive the enabling environment outcomes but is also expected to contribute to the protection outcomes. The black dashed line linking outcome 2 and 3 represents the programmes intention to focus on emergency response (alongside protection and enabling environment programming), while gradually pivoting to early recovery and systems strengthening programming. This will be highly dependent on the context and the assumptions underpinning the theory of change.

Assumptions underpinning the theory of change: The overarching assumption is that the war continues, but doesn’t escalate to a level where operations are not possible in the target areas for the programme within Ukraine, and that the overall level of HMG support to Ukraine is sustained. The scenario analysis presented in the strategic case also expects that protracted humanitarian needs (including protection risks) will continue in all scenarios, including if there is cessation of hostilities. Specific contextual and programming assumptions are presented in the tables below.

Output to Outcome

Contextual Assumptions	Strength of Evidence
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXXX
The economic situation will not deteriorate to the extent that inflation makes cash programming and other humanitarian interventions unaffordable or ineffective. The economic situation remains conducive for livelihoods programming	Medium
Programming Assumptions
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX
Those who have experienced protection issues have the knowledge to and feel comfortable and empowered to seek support	Weak
Data, information and analysis is effectively utilised by humanitarian actors to refine the response	Medium
Humanitarian basic services will be sufficient to meet basic needs	Medium
The humanitarian system/our partners have sufficient resources to devote to preparedness efforts and to respond to new or increased needs when they arise.	Strong
Ukrainian civil society will remain engaged, dynamic and effective, and be well placed to provide humanitarian assistance and respond to shocks	Strong
The programme will be able to effectively support contextually-appropriate improvements to coordination structures. Local actors have the capacity to coordinate the humanitarian response (at the local level). Local coordination structures are the most appropriate coordination modality for the humanitarian system moving forward	Medium
The Government of Ukraine is receptive to systems strengthening efforts	Medium
For agricultural livelihoods, sufficient land will be uncontaminated and accessible; other actors will conduct demarcation and demining activities to facilitate this	Weak

Outcome to Impact

Contextual Assumptions	Strength of Evidence
The UK will continue to influence international donors and the Government of Ukraine	Medium
The Government of Ukraine and UN relationship remains constructive	Medium
Humanitarian actors retain the capability to flex and respond to most scenarios	Strong
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX
Population movement remains dynamic, but mass movements are unlikely XXXXXXXXXXXXXXXXXXX	Medium
Programming Assumptions
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX
GoU have stretched capacity, and lack the resources to support the whole population effectively whilst the war is ongoing, hence complementary humanitarian support for the most vulnerable is needed	Strong
XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX	XXX
Data and analysis is adequately used to support identification of most vulnerable within the programme	Medium

Annex C Moldova Theory of Change

Problem Statement: The full-scale Russian invasion of Ukraine has put pressure on Moldova’s already struggling national and civil society social protection, health, and education systems. The basic needs of Ukrainian refugees, third country nationals, and vulnerable Moldovans are only being met through the support of international humanitarian assistance. GoMs social protection system reform is ongoing but is reliant on international technical and financial assistance. Contingency planning for a spike in emergency need is jointly managed by GoM and UNHCR, but this is reliant on international humanitarian assistance. To help address these problems, the theory of change is as follows:

Impact (5yrs+) Moldovan institutions (Government and Civil Society) are shock-responsive and better able to meet the essential protection and assistance needs of Ukrainian refugees and vulnerable Moldovan communities affected by the full-scale Russian invasion of Ukraine.
Outcome 2: Local and national systems and capacities for social protection (government and civil society) are strengthened and able to meet the needs of Ukrainian refugees and Moldovans.
Outcome 1: Unmet basic needs and protection needs amongst Ukrainian refugees and vulnerable Moldovans is reduced and social inclusion of refugees is supported.
Outcome 3: The humanitarian system is well prepared to respond to future shocks and has effectively mobilised emergency operations as required.
Potential Outputs:
Vulnerable Moldovans and Ukrainian Refugees receive:
- protection services
- cash assistance
- digital learning centres

Potential Output: Contingency and preparedness planning for emergency responses in place

Potential Outputs
- Technical assistance to national and local social protection systems for reform and implementation.
- Technical assistance to national programmes for combatting Gender-Based Violence for delivery and roll-out.
- Community engagement and participation in social protection systems is facilitated.

Outcomes (3-5 yrs.)
Outcomes (2-5 yrs.)
Key Programming Assumptions underpinning the Moldova Theory of Change:

The overarching programme assumption is that essential protection and basic needs assistance are scaled down over the duration of the programme, as GoM (e.g. after the first 2-3 years) and civil society capacity improves (this refers to the interventions and outputs under outcomes 1 and 2 presented with dotted red lines)

Highest costs for protection and basic needs support (e.g. investment in facilities/centres and wide-scale cash assistance) will be needed in the early phases of the programme, and will decrease over time (e.g. to running/maintenance costs and more tightly targeted cash assistance) (this refers to the interventions and outputs under outcomes 1 and 2 presented with dotted red lines)

IRF planning is sufficient to manage response to new refugee influxes, and contextual changes wouldn't require a full pivot of the direction of the programme to a repeat of the full-scale emergency response efforts (This relates to interventions and outputs under outcome 3)

Emergency response efforts in case of a significant spike in need would continue to require extensive international assistance (and could not be covered in the short-medium term by shock-responsive GoM systems); (This relates to interventions and outputs under outcome 3)

Overarching Contextual Assumptions for the Moldova Theory of Change:

GoM will not have the capacity, within the duration of the programme, to cover all the essential protection and basic needs of the target population.

The political situation remains relatively stable and is not significantly destabilised XXXX
Significant changes are not seen in terms of acceptance of refugee communities within the lifespan of the programme.

The UN will maintain a presence and operations in Moldova throughout the programme, which are able to support GoM and fill critical gaps in service provision.
Annex D: HARP: Approach to localisation