## KPMEL LOGFRAME
ORGANISATION NAME | Itad Limited
PROJECT NAME | Kenya Portfolio Monitoring Evaluation and Learning Facility
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target
BHC Nairobi activities are impactful, influential, evidence-based and value for money to serve UK and Kenyan citizens and taxpayers | Evidence that BHC’s portfolio is achieving identified outcomes for the UK and Kenya | Planned | N/A | Postive contribution (3+) score for CBP, SP, and/or Portfolio Strategy Reviews | Postive contribution (3+) score for CBP, SP, and/or Portfolio Strategy Reviews | Postive contribution (3+) score for CBP, SP, and/or Portfolio Strategy Reviews | Postive contribution (3+) score for CBP, SP, and/or Portfolio Strategy Reviews
Achieved
Source
Rubric-based BHC self-assessment scoring (1-4): 1 = Limited or no contribution pathway evident to CBP, SP and Portfolio Strtaegy reviews. 2 = Significant contribution identified but weak evidence base 3 = Significant contribution identified and strong evidence base 4 = Highly significant contribution identified and strong evidence base
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target | Assumptions
Objectivity and accountability in BHC Kenya programme results and use of resources, including consideration of risk | Evidence of improvements in programme data quality systems as a result of PMEL support | Planned | TBC | At least 40 percent of assessed programme MEL system components ranked green in diagnostic tool | At least 50 percent of assessed programme MEL system components ranked green in diagnostic tool | At least 60 percent of assessed programme MEL system components ranked green in diagnostic tool | At least 70 percent of assessed programme MEL system components ranked green in diagnostic tool | • Implementing partners provide accurate, timely data • FCDO teams and senior leadership have the capacity, incentives and willingness to use evidence • Sufficient resources and an enabling organisational environment support transparent monitoring • Staff turnover does not undermine continuity in compliance processes or the uptake of evidence
Achieved
Source
Annual RAG ranked MEL systems diagnostic tool by BHC unit/programme, Annual light touch qualitative feedback (2-3 questions) from PT PoCs on changes in delivery, data quality, and the nature and number of MEL recommendations addressed
| Outcome Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target
| Evidence that programmes are delivering value-for-money through demonstrated efficiencies in resource allocation and utilisation | Planned | TBC | Annual VfM self-assessment completed for all active programmes, with initial efficiency gaps and priority improvement actions identified and documented. | At least 50 percent of assessed programme VfM components ranked green in self-assessment tool | At least 60 percent of assessed programme VfM components ranked green in self-assessment tool | At least 70 percent of assessed programme VfM components ranked green in self-assessment tool
Achieved
Source
KPMEL Value-for-Money monitoring self-assessment tool conducted annually
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target | Assumptions
Strategic decision-making is grounded in evidence, maximising impact, adaptive management, and influence | Evidence of increased demand and use of PMEL products to guide decisions, current and future actions within BHC (disaggregated by pillars, programmes) | Planned | N/A | Early examples of PMEL-generated evidence informing decisions, such as programme design, adjustments or improved risk/VfM discussions, are documented in at least 2-3 cases | Regular use of PMEL insights in strategic planning, programme adaptation and influencing efforts, and clear evidence of improved VfM analysis and risk management, with at least 4-6 documented cases | Routine integration of PMEL evidence across pillars and senior decision-making, with 6-8 concrete examples of adaptation, diplomacy or strategy shaped by PMEL work | PMEL evidence is systematically used to inform strategic decisions, adaptive management, diplomatic influence, and VfM, evidenced by consistent uptake across pillars and at least 10 examples | • Teams and leadership consistently demand and use evidence to guide strategy, adaptation and influence. • Programme and contextual data are sufficiently reliable and accessible to inform decisions. • Partners and teams are willing to share learning and act on findings to enable adaptive management. • The political and operational environment allows evidence-informed adjustments to programmes and diplomacy.
Achieved
Source
Country Business Plan, Pillar Leads, BHC Strategies, Programme Team feedback, programme board minutes, Outcome Change Stories/Case Studies
| Outcome Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target
| Proportion of DQA, evaluation, and/or research recommendations adopted in the Management Response & Recommendations Action Plan | Planned | N/A | At least 50 percent of consolidated recommendations adequately address in recommendations action plan | At least 60 percent of consolidated recommendations adequately address in recommendations action plan | At least 70 percent of consolidated recommendations adequately address in recommendations action plan | At least 80 percent of consolidated recommendations adequately address in recommendations action plan
Achieved
Source
Programme Management Response and Recommendations Action Plan
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target | Assumption
Programme monitoring data is more relevant, valid, and reliable | Number & percentage of BHC programmes receiving PMEL support for QA of MEL & VfM frameworks, DQAs, and capacity development (disaggregated by support type) | Planned | N/A | All programmes received some type of KMPEL support annually | All programmes received some type of KMPEL support annually | All programmes received some type of KMPEL support annually | All programmes received some type of KMPEL support annually | • Implementing partners collect and share accurate, timely monitoring data and permit proportionate verification. • Programme teams and partners have sufficient capacity and incentives to improve monitoring practices and act on PMEL guidance. • PMEL can safely and feasibly access sites or use TPM to validate data quality where needed. • The operating environment enables transparent reporting, without disincentives to disclose errors or data gaps.
Achieved
Source
RAG ranked KPMEL diagnostic tool
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target
30% | Number and proportion of KPMEL identified compliance and/or data quality issues resolved (disaggregated by thematic) due to improved monitoring support | Planned | TBD | At least 40 percent of identified issues adequately resolved | At least 50 percent of identified issues adequately resolved | At least 60 percent of identified issues adequately resolved | At least 70 percent of identified issues adequately resolved
Achieved
|  | Source | [5 empty] | RISK RATING
KPMEL DQA register, Monitoring and Compliance Log, Learning and Adaptation Tracker
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target | Assumptions
independent, evaluation and contextual evidence, on programme and across the portfolio | Number of programme, thematic, and/or portfolio evaluations completed by PMEL | Planned | N/A | 2 to 4 | 2 to 4 | 2 to 4 | 6 to 10 | • Programme teams and implementing partners cooperate with evaluation requests and provide timely access to data, documents, and stakeholders. • High-quality, evaluable data is available or can be generated to support credible assessments. • PMEL has access to the necessary expertise and resources to design and deliver rigorous, independent evaluations. • The organisational environment supports transparency and honest reflection, enabling candid participation in evaluative processes.
Achieved
Source
Evaluation and assessment reports
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target
30% | Number and percentage of eligible PMEL products achieving a 'Good' or above rating by EQUALS or BHC team | Planned | N/A | 100% | 100% | 100% | 100%
Achieved
|  | Source | [5 empty] | RISK RATING
PMEL workplan and progress reports, EQUALS QA results, BHC feedback
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target | Assumption
Generation of evidence and learning around cumulative effects, diplomacy, and influence at the strategic and portfolio level, including non-programme areas | Number and utility of activities supporting development of theories of change and/or articulating goals, objectives, MEL strategies for non-programme areas (e.g. diplomacy, influence, policy, operational models etc.). | Planned | N/A | At least 2 structured support activities delivered, with initial draft ToCs or strategic articulation notes produced for priority non-programme areas and positive qualitative feedback from participating teams. | 4–5 activities completed, with documented ToCs or MEL/strategy articulation products in use by multiple teams and evidence of early application in planning or decision-making processes. | 6–7 activities completed, with routine integration of ToCs or articulated MEL/strategy frameworks into at least three non-programme functions, and user feedback indicating clear practical utility. | 8+ high-quality support activities delivered, resulting in institutionalised use of ToCs and/or articulated goals and MEL strategies across key non-programme areas, with demonstrable evidence that these frameworks inform planning, reporting, and strategic decision-making. | • Senior leaders and pillar teams are willing to engage with PMEL and provide access to strategic processes, data, and stakeholders. • Non-programme and diplomacy teams have the capacity and incentives to articulate theories of change and participate in strategic evidence work. • Sufficient, credible information is accessible across pillars and workstreams, including in non-ODA areas. • The organisational environment enables open sharing of insights and reflection, supporting cross-mission learning and strategic uptake.
Achieved
Source
WS2 Progress Reports, BHC stakeholder feedback
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target
| Evidence of learning products contributing towards strategic goals (CBP, SP, Portfolio Strategies) and/or objectives within them. | Planned | N/A | At least two documented references of learning products in key strategies and plans, supported by positive user feedback | At least two documented references of learning products in key strategies and plans, supported by positive user feedback | At least two documented references of learning products in key strategies and plans, supported by positive user feedback | At least two documented references of learning products in key strategies and plans, supported by positive user feedback
Achieved
Source
Learning and Adaptation Tracker, BHC Stakeholder Feedback
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target
30% | Number of non-programme and/or cross-thematic assessments delivered by PMEL to high standard of quality and utility | Planned | N/A | 1 to 2 | 1 to 2 | 1 to 2 | 3 to 6
Achieved
|  | Source | [5 empty] | RISK RATING
PMEL workplan and progress reports, assessment reports, QA results, BHC feedback
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target | Assumptions
All BHC staff have better ability to access and use evidence on politics, contexts and results, including data and analysis, information, formal and informal knowledge. | Number of priority issues to advance the CBP/SP delivery, identified by and relevant to work of RAs, disaggregated by team/sector/geographic area | Planned | TBC | 3-5 per person per quarter | 3-5 per person per quarter | 3-5 per person per quarter | 3-5 per person per quarter | • Staff have adequate time, incentives, and capacity to engage with new tools, guidance, and evidence products. • Data and knowledge platforms function reliably and are easy to access, with minimal technical or security barriers. • Teams are willing to share information openly across pillars and workstreams. • Training, support, and troubleshooting are available to help staff confidently use data and evidence in their work.
Achieved
Source
BHC Priority Issues Tracker
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Cumulative Target
| Number of data dashboards demanded by teams and produced by KIO | Planned | TBD by BHC | TBD by BHC | TBD by BHC | TBD by BHC | TBD by BHC
Achieved
Source
KIO Reports
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target
10% | Evidence of successful implementation of uptake and influence plans | Planned | TBC | A high degree of implementation of uptake and influence plans across the BHC | A high degree of implementation of uptake and influence plans across the BHC | A high degree of implementation of uptake and influence plans across the BHC | A high degree of implementation of uptake and influence plans across the BHC
Achieved
|  | Source | [5 empty] | RISK RATING
BHC feedback on use of uptake and influence plans
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## RECORD OF CHANGES
Date | Version number | Level of Change (OUTPUT/OUTCOME/IMPACT) | Reason for Change | Approved by (PROGRAMME/STRATEGY/REGIONAL SRO)