Annual Review

Summary of Programme Performance
Year	2024-25	2025-26	2026-27
Overall Output Score	A	A
Risk Rating	Minor	Minor

Programme title: Portfolio evaluation of RED economic development research programmes
Programme Value £ (full life):	£600k plus VAT	Review Date: May 2026
Programme AMP Code: 400187	Programme Start Date: 06/06/2024	Programme End Date: 31/01/2027

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006883.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006884.xlsx

SUMMARY AND OVERVIEW

Programme description: / The UK has a strong comparative advantage in economic development research, being the only bilateral donor with significant ODA funding in this area. Economic growth is a major focus for the UK Government. / The portfolio evaluation will investigate three key aspects of Research and Analysis Directorate’s economic development research programmes: / Coherence and research gaps, within programmes and across the portfolio as a whole. / Value for money / Outcomes and impacts in terms of policy and practice change and influencing the knowledge frontier.
Intended policy objective(s) of projects within this programme. / The results of the evaluation will inform the Economic Growth Research Team’s (EGRT) decision-making about future programming, related to: research themes, questions and methods; commissioning processes; capacity strengthening; programme collaboration; and metrics for measuring outcomes and impacts. The results will also provide learning for partners and other researchers on addressing gender issues and disability, involving researchers from lower-income countries (LICs), and improving and measuring uptake. Furthermore, the evaluation will provide evidence on the outcomes from the portfolio and the extent to which it offers value for money.
Overall Programme Score / During the second year, the programme scores an A.
Summary supporting narrative for the overall programme score in this review. / There were two main deliverables, producing 1) the first evaluations and 2) associated learning products. The original contract stated that five of the seven evaluations would be delivered by the time of this annual review. In practice, there were delays in the transition from inception to implementation due to delays in getting the inception report reviewed by EQUALS and agreeing the final version. This led to a contract amendment that pushed delivery of three of the evaluations to year 3 of the evaluation, leaving only two evaluations (DEGRP and EDI) to be delivered within the year under review. The supplier has delivered these evaluations and the associated learning products to a satisfactory standard. / The Evaluation Management Team within FCDO decided to get the first two evaluation reports quality-assured by EQUALS, which caused a further delay to the timeframes. Furthermore, in May 2026, a decision was made by the FCDO to drop the CERPA evaluation, due to budget pressure. It also became clear that a re-ordering of the evaluations needed to be made in line with partner availability. The timeline for delivery of the portfolio evaluation and synthesis report has been pushed back by 2 months, but OPM is confident that the end date of the contract will not need to be changed. At the time of writing this review, a contract amendment is in progress. / A hybrid payment mechanism is used with output-based milestone payments and expenses paid quarterly based on actuals. This is working well. At the beginning of the contract the supplier did not claim VAT but has subsequently determined that this is required. The need to back-date VAT for payments that have already been made is causing issues on both sides with regards to the invoicing and payment software used. This has been time-consuming for the FCDO programme manager but a way forward has now been identified. / Positive EQUALS ratings and satisfactory response to EQUALS and Evaluation Management Team comments on the first two programme evaluation reports mean that this evaluation remains low-risk.
Major lessons and recommendations for the year ahead / There are no recommendations this year. The contract is running smoothly, the evaluator OPM (Oxford Policy Management) has been proactive and responsive and the evaluation outputs are on track in relation to mutually-agreed changes throughout the year under review.

PROGRAMME STRATEGY OR THEORY OF CHANGE

The objectives, which are unchanged since the business case was approved, are to:
1. consider the overall portfolio of research in relation to coherence, research gaps and inclusion.
2. assess value for money of EGRT programming
3. identify outcomes and impacts in terms of policy and practice change and influencing the knowledge frontier.

The evaluation will enable EGRT to improve the quality, scope and relevance of future research programmes so that the findings can better support decision-making on economic growth. This includes thematic focus and inclusion. It will also provide accountability to the UK taxpayer by independently generating evidence on the extent to which the programme investments have led to research outputs that are taken up in decision-making, leading to impact and value for money. The primary user of the evaluation findings is EGRT but the findings will also be of interest to other FCDO research teams, other economic growth research funders and researchers working on development economics.

Oxford Policy Management (OPM) won the tender to carry out the evaluation. To date their work has been of high quality, confirmed by positive EQUALS feedback on the first two evaluations which were completed during the reporting year.

The business case included the delivery of 7 programme evaluations. Over the course of the reporting year the Evaluation Management Team decided that, due to funding pressures, the standalone capacity-building programme (Capacity for Economic Research and Policy making in Africa, CERPA) should be dropped from the evaluation, leaving 6 research-generating programmes to be evaluated and synthesised. The evaluation question that relates to capacity-building (“Is the approach to ensuring the participation, capacity-building and recognition of Southern researchers and their institutions adequate and appropriate?) was retained, since most of the other programme partners deliver capacity-building activities among research teams.

Given good performance from OPM and all evaluation questions retained albeit with a slightly reduced scope, the above objectives are on track to be achieved.

DETAILED OUTPUT OR PERFORMANCE AREA SCORING

During the second year of the project there is one log frame output:
Performance area:	Robust independent evaluation of the economic development research portfolio
Number:		2	Score:	A
Weighting (%):		100	Weighting revised since last AR?	N/A

Briefly summarise the projects that have been delivered and provide supporting narrative for the score.

The log frame output indicators that are relevant to the reporting year are:

Presentation of preliminary findings
The Evaluation Management Team decided that presentations of the individual programme evaluations to FCDO staff would not be as useful as presentations of the final portfolio-level and synthesis evaluations. A seminar would therefore be planned once all evaluation outputs have been delivered. However, there is no indicator related to delivering the programme evaluations so this indicator should be renamed “Delivery of programme evaluations and portfolio level evaluation”. Two evaluations of closed programmes (Development and Economic Growth Research Programme (DEGRP) and Economic Development and Institutions (EDI)) were completed as planned. As these were the first two evaluations, the drafts were sent to EQUALS for feedback. The DEGRP report was given a “good” rating and the EDI report an “excellent” rating. Evaluation management team comments on the reviews were satisfactorily addressed by the evaluation team.

According to the log frame established at the beginning of the inception phase, three further evaluations were due to be completed by June 2026. One of these (CERPA) has been dropped from the evaluation and the other two (International Growth Centre (IGC) and Gender, Growth and Labour Markets in Low-Income Countries (G2LM)) have been postponed by mutual agreement, given that getting the inception report and first two evaluation reports quality-assured by EQUALS took longer than anticipated. Performance against this indicator is therefore considered to have met expectation (A score).

Focused learning/knowledge products for individual programmes
Products were produced for the DEGRP and EDI programmes, containing key learning points and recommendations. These were reviewed by the Evaluation Management Team and comments addressed by OPM. Performance against this indicator met expectation (A score).

All outputs will be published once the final synthesis report has been completed. In the meantime, the PRO shared the two knowledge products with other FCDO research teams so that the learning could benefit other FCDO research programmes.

Programme-level recommendations for the year ahead, and progress on recommendations from previous AR (if completed).
Log frame indicator “Presentation of preliminary findings” should be renamed to “Delivery of programme evaluations and portfolio level evaluation”.