## Annual Review

Title: Twiyubakire – Effective and Accountable Governance for Development
Programme Value £ (full life): £35,000,000		Review date: November 2025
Programme Code: 400197	AMP start date: 21/11/2024	AMP end date: 31/03/2030

Summary of Programme Performance
Year	2025
Overall Output Score	B
Risk Rating	Moderate

DevTracker Link to Business Case:	Twi-Business Case
DevTracker Link to results framework:	To be published shortly.

## A: SUMMARY AND OVERVIEW

Description of programme

Twiyubakire (the Kinyarwanda word for “Let us build together”) is the UK’s flagship governance programme in Rwanda. It aims to strengthen local government systems and build local government capacity, supporting Rwanda’s vision for decentralisation, whilst also working with both government and non-state actors to increase accountability. The goal is to contribute to both more efficient, effective, and accountable policy responses, as well as better local service delivery, which will in turn lead to more accelerated and inclusive socio-economic development at the district level.

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

This has been a challenging year for Twiyubakire, with two major contextual changes significantly undermining progress:
1. In February 2025, in response to the situation in Eastern DRC, the UK took measures against Rwanda, including pausing “direct bilateral financial aid to the Government of Rwanda (GoR), excluding support to the poorest and most vulnerable”. This means that the planned non-budget financial support to the Ministry of Economic Planning and Finance (MINECOFFIN) and the Ministry of Local Government (MINALOC) were paused, and no disbursements have been made to the GoR under this programme
2. Additionally, the announced reduction of Official Development Assistance (ODA) from 0.5% to 0.3% of UK’s Gross National Income (GNI) has led to both immediate delays in implementation (the cancellation of one procurement process and significant delay to the other), as well as the decision to close Twiyubakire early, which means the overall objectives must be significantly scaled down. It also means that non-budget financial support will not be resumed.

Overall, the programme has, therefore, scored a B, which reflects the significant delays to establishing the programme’s various components, as well as the need to redesign the programme in light of the ODA reductions and wider context.

Major lessons and recommendations for the year ahead

- The top priority should be providing strategic clarity for the whole programme (e.g. confirming when all components will close), which will allow the programme team to focus on delivering the maximum impact within those parameters. The logframe should be finalised by December 2025.
- Key areas of support which require continuation beyond the truncated lifetime of Twiyubakire (e.g. programme funded roles) should be aligned with the new business case for UK support in Rwanda that is being developed.
- Given the significant reduction in budget and planned early closure of this programme, a new approach to governance should be developed. This should explore how to:
  - Use governance tools and approaches to help deliver sectoral objectives (e.g. in education);
  - Leverage peer-to-peer partnerships, Centrally Managed Programmes (CMPs), and Centres of Expertise (CoEs) to ensure continuity in the gains made in the governance sector;
  - Explore how to use diplomatic and political levers to meet governance objectives (e.g. convening civil society); and
  - Test innovate models that use small amounts of funding to achieve catalytic change.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Figure 1. Theory of change

Impact: Accelerated and more inclusive socio-economic development at the district level.
Outcome: More efficient, effective and accountable policy responses and service delivery at local level

Output 1: Local Government policies and systems strengthened.

Output 2: Human resource and institutional capacity in decentralised entities strengthened.

Output 3: Capacities of CSOs, citizens and non-state actors strengthened to meaningfully participate in Governance and accountability processes.

Interventions

1. TA to MINALOC on data analysis systems, operationalising the PM order on sectoral decentralisation, and strengthening planning and M&E systems.
2. TA to MINECOFIN to develop an intra-governmental OSR collection framework, review Tax Procedures Law, strengthen M&E for NST2, and improve internal audit.
3. Programme Funded Advisor to support cross-ministry implementation.

Interventions

1. TA to MINALOC on operationalising service delivery at the cell level and building the strategic communications capacity of officials in decentralised entities.
2. TA to MINECOFIN to support integrating an AIM tool into the SDMS, as well as the LAIS and LGT systems.
3. Programme Funded Advisor to support cross-ministry implementation.

Interventions

1. Strengthen the institutional capacity of small and medium size CSOs to effectively engage in local governance, transparency and accountability processes.
2.Strengthen CSO’s research and evidence capabilities for advocacy on policy issues affecting local governance and socio-economic development.
3. Build capacity to meaningfully engage in budget cycle and accountability processes.

Interventions:

1.Research conducted on identified policy issues to inform effective delivery of programme outcomes (evidence)
2. Ongoing Monitoring, Evaluation, and Learning to support programme impact.

Output 4: Policy making and implementation in GoR institutions and advocacy among non-state actors is strengthened.

Despite the significant changes to the programme this year, the original theory of change broadly holds true. It still includes activities that aim to deliver across all four outputs, though notably less under output 4. Note the interventions have been updated to better reflect the agreed workplans. However, it is important to note that with a budget reduction of more than 90%, and the implementation period decreasing from five to one to two years, the scale of delivery against the outputs will be greatly reduced. It also significantly reduces both the likely scale and probability of impact at outcome and impact level.

Whilst most of the underlying assumptions remain true (for example that the GoR remains committed to decentralisation), an important assumption that has changed is the presence of financial aid, which provided the GoR with resources to enact change. Therefore, an important new assumption is that the government will have the resources, from other sources, to implement the changes recommended or developed through the technical assistance or civil society components.

A one-year mobilisation logframe was used for this first review, as there would have been little to nothing to monitor or report against for the outputs described in Figure 1. It is important to note that this logframe was also only agreed shortly before this review was completed, due to competing demands across the team, but reflects the initial ambitions (e.g. includes the financial aid components). However, it is now a priority to develop the full logframe, using the above outputs; this is being developed with partners and will be finalised by December 2025.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Whilst it is too early to judge the likelihood of this programme achieving outcome/impact level change, two components have been successfully mobilised, and delivery has started. However, the significant expected reduction in budget means that the ambitions for change also need to be scaled back. This will be reflected in the new logframe.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Twiyubakire is the flagship governance programme and responds to the country business plan (2025/2026) priority of improving Rwanda’s public service delivery and institutional performance. However, in light of the ODA reduction, this programme is expected to close early but it is important that it continue for the next 6 – 18 months to avoid a cliff-edge exit from the sector.

## C: DETAILED OUTPUT SCORING

Output Title	New financial aid arrangements established with the Government of Rwanda
Output number:		1	Output Score:	C
Impact weighting (%):		50%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Partnership, under Twiyubakire, established with MINECOFIN	New MOU signed with MINECOFIN by the end of March 2025, with first disbursement by May 2025 / Workplan agreed and shared with the PFM sector working group	Substantially did not meet expectations: The MOU was signed in January 2025, but no disbursement was made. / Substantially did not meet expectations: Discussions about the workplan had just started when the decision to pause financial aid was made.
1.2 Partnership, under Twiyubakire, established with MINALOC	New MOU signed with MINALOC by the end of March 2025, with first disbursement by May 2025 / Workplan agreed and shared with the Governance and Decentralisation Steering Committee	Substantially did not meet expectations: The MOU was signed in January 2025, but no disbursement was made. / Partially met expectations: The workplan was agreed with MINALOC and shared with the Governance and Decentralisation Steering Committee, but it was not agreed given the pause in financial aid.

Briefly describe the output’s activities and provide supporting narrative for the score.

This pillar was designed to strengthen local government systems and build local government capacity through non-budget support financial aid to MINECOFFIN and MINALOC. This financial aid would support the GoR to strengthen policies, systems, and both individual and institutional capacities in decentralised entities, delivering against both outputs 1 (local government policies and systems strengthened) and 2 (human resource and institutional capacity in decentralised entities strengthened).

Mobilisation of the component was initially progressing smoothly, with new MoUs signed between the UK and the GoR in January 2025 to support the implementation of both the Public Financial Management and the Governance and Decentralisation Sector Strategic Plans. However, given the decision to pause financial aid in February 2025, no disbursements were made and progress on the respective work plans was stopped. Given the reduction in ODA, the planned activities under this component will not restart.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Given this first year was focused on mobilisation, a separate Year 1 logframe was used to assess progress. Due to pressures across the office, this was not formally agreed till shortly before the annual review but reflects the initial ambitions. A new logframe for the remaining years will be finalised, using the outputs outlined in the business case, by the end of November 2025.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The reduction in UK ODA means that bilateral aid to Rwanda will significantly reduce, which may affect the Government of Rwanda’s (GoR) performance in public financial management (PFM), governance, and decentralisation, given our longstanding support to these sectors. As the British High Commission Kigali (BHCK) shapes future support to Rwanda, it is important to come up with innovative ways to support these areas and avoid losing the gains made in recent years. This could include leveraging centrally managed programmes (CMPs) or allocating a small budget to catalyse reforms in the governance sector, given its key role in accelerating service delivery to citizens. Peer to peer partnerships with other government departments (e.g. HMRC and ONS) have been particularly valued, and BHCK should explore how to maintain them, including committing ODA if necessary.

Output Title	Technical Assistance Facility established
Output number:		2	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Commercial supplier identified and onboarded	Terms of reference developed, and competition launched by January 2025 / Contract signed by June 2025	Met expectations: Terms of reference were developed, and the competition for a new 5-year TA facility was launched in January 2025. / Met expectations: Due to the reduction in ODA, the procurement process was cancelled. To mitigate the risk of a cliff edge exit, a costed extension to the DAI contract (the commercial supplier of the technical assistance component of the predecessor programme, SPARC) was issued. The extension was approved in June 2025.
2.2 2025/26 workplan started	Workplan and activities for 2025/26 agreed between supplier, government ministries, and FCDO / All embedded advisers have been recruited and all workstreams started	Met expectations: The workplan for FY 2025/26 has been agreed between DAI, MINALOC, and MINECOFIN. / Met expectation: All technical advisers have been recruited and the implementation of all workstreams started.

Briefly describe the output’s activities and provide supporting narrative for the score.

The technical assistance facility was designed to run for 5-years and provide issue-based and embedded technical advice to both MINALOC and MINECOFIN, as well as support on emerging issues aimed at strengthening citizen participation in development processes and accountability.

As mentioned above, timely progress was initially made on developing the terms of reference and launching the competition for a new commercial supplier for the envisioned 5-year facility. However, the ODA reduction was announced during the final stages of the competition, and the decision was made to cancel the competition and proceed with a costed extension of an existing technical facility (the Rwandan Technical Assistance Facility, RTAF, led by DAI) under the predecessor programme (SPARC) to avoid a cliff-edge exit. This extension was signed in June 2025, started in July, and is expected to close in March 2026.

DAI has quickly identified interventions based on the government’s priorities as laid out in the PFM and Governance and Decentralisation sector strategic plans. They have recruited all the technical advisers that will deliver the interventions and all workstreams have now started. These include:
- MINALOC:
  - Establishing a clear, evidence-based model for operationalising service delivery at the lowest level of Rwanda’s administrative system (cell).
  - Building and blending MINALOC’s data analysis systems and functions with its business processes to improve operational efficiencies, particularly in planning, monitoring and evaluation (M&E), data flow, and decision-making.
  - Operationalising the PM Order on sectoral decentralisation as a mechanism to fast-track implementation of the decentralisation roadmap and piloting decentralisation of a selected set of services in health, agriculture, and environment.
  - Strengthening planning and M&E systems and functions to enable timely and accurate planning, reporting, and decision-making.
  - Building capacity of Provincial Governors, Mayors, District Executive Secretaries, and Public Relation Officers on strategic communication to enhance quality of service delivery, transparency, and public trust.
- MINECOFIN:
  - Developing a detailed and practical intra-governmental coordination framework to enable effective own source revenue collection.
  - Preparing comms materials on the own source revenue mobilisation (OSRM) strategy, targeting different stakeholders to enhance visibility, accessibility, and the practical application of OSRM.
  - Supporting the legal team to review and elaborate the Tax Procedures Law for decentralised taxes.
  - Integrating an asset and inventory management (AIM) tool into the school data management system (SDMS).
  - Strengthening M&E of the 2nd National Strategy for Transformation (NST2) by integrating M&E systems with the Integrated Financial Management Information System (IFMIS) and ensuring the interoperability of all M&E systems.
  - Integrating the Land Administration Information System (LAIS), Local Government Tax System (LGT), and other related systems to improve information sharing and increase local government revenue mobilisation capacities.
  - Reviewing and updating the Audit and Risk Committee and Internal Audit tools used in Public Sector Entities to ensure alignment with the revised Global Internal Audit Standards issued in January 2024.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Given this first year was focused on mobilisation, a separate Year 1 logframe was used to assess progress. Due to pressures across the office, this was not formally agreed till shortly before the annual review but reflects the initial ambitions. A new logframe for the remaining years will be finalised, using the outputs outlined in the business case, by December 2025. However, as the DAI contract will end in March 2026, rather than the initially envisioned 2030, the overall ambition of the programme has to be scaled down, which will be reflected in the logframe.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As discussed under output 1, in light of the early closure of both the financial aid and technical assistance to the GoR, BHCK should explore innovative ways to preserve the gains in governance and catalyse further progress.

Output 3 Title	New civil society grant manager launched
Output number:		3	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Grant manager identified and onboarded	Call for proposals developed and competition launched by January 2025. / Accountable grant signed by April 2025. / Detailed work plan, including capacity strengthening activities, agreed by August 2025.	Met expectations: The call for proposals was launched in January 2025. Through a rigorous, open, transparent and competitive process, Trócaire was selected to be the Grant Manager. / Partially met expectations: This milestone was achieved in July 2025, due to delays caused by the ODA reduction announcement. / Partially met expectations: A detailed workplan, including capacity strengthening activities, was shared by the Grant Manager in November 2025 and is under review.
3.2 CSOs working in priority areas identified and onboarded	Competition launched to identify CSOs working on decentralisation, private sector advocacy, and sensitive issues (e.g. human rights, social cohesion, and media freedom) by August 2025. / Sub-grant agreements signed with all selected CSOs by November 2025. / All sub-grantees begun implementation by November 2025.	Partially met expectations: Given delays, it was not possible to run a full open competition, but a closed call for expressions of interest (EoIs) was launched in July. / Met expectations: Trócaire signed sub-grant agreements with five CSOs by the end of October 2025. / Met expectations: All sub-grantees began implementation in late-October to early-November 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

The initial vision was to onboard a 5-year civil society grant manger that would strengthen the capacities of civil society organisations (CSOs) and citizens to meaningfully participate in governance and accountability processes. The grant manager was meant to deliver long-term capacity building and institutional strengthening whilst supporting subgrantees to deliver across three thematic windows: governance systems strengthening; strengthening policy advocacy in thematic areas (e.g. climate change, gender, and economic growth); and citizen-led issues (e.g. inclusion, media freedom, and civic space).

As with output 2, initial progress was smooth, with a call for proposals launching in January. However, the announcement of the global ODA reduction led to the competition being paused and the scope (both time and budget) being reduced. Ultimately, the initial five years duration has been reduced to 20 months, and the budget from £7 million to a maximum of £2.2 million. Trócaire was the successful bidder but had to adapt their proposal to these new parameters. Most importantly, this has led to significantly truncating the inception period, including the scoping of priorities, engaging with the market, and onboarding of downstream partners. Trócaire ran a mini closed competition, with a rigorous selection process, that led to two CSOs being selected under a combined window 1 and 2 (governance systems and policy advocacy), and three CSOs under window 3 (citizen-led issues). The selected projects are:
- Conseil de Concertation des Organisations d'Appui aux Initiatives de Base (CCOAIB): Strengthening Local Voice and Accountability in Rwanda’s Agricultural Governance (Twiyubakire-Engage)
- Rwanda Education for All Coalition (REFAC): Twiyubakire Imiyoborere y’Uburezi - Strengthening Local Education Governance and CSO Participation for Enhanced Service Delivery.
- Iriba Center for Multimedia Heritage: Strengthening Social Cohesion and Citizenship through the transmission of knowledge and experience.
- Commission Episcopale Justice et Paix Rwanda (CEJP): Contribute towards strengthened social cohesion in Post-Genocide Communities in Rwanda
- Syndicat des Travailleurs aux services des Droits Humains (STRADH): Towards socio-economic reintegration of Victims of the Worst Forms of Child Labour in Rwanda
Whilst the inception period will officially end in December 2025, this truncation may account for the lack of bids from either private sector actors or CSOs in private sector advocacy, despite the desire to engage them.

Following the selection process, co-creation workshops were convened with the selected CSOs to elaborate agile, adaptive projects with clear theories of change, logical frameworks, and budgets. Agreements have been signed with all five downstream partners for a period of 5 months running from November 2025 to March 2026. A decision will be made in December 2025 on whether to extend these activities to March 2027. Trócaire has also delivered a detailed work plan, which is currently being reviewed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Given this first year was focused on mobilisation, a separate Year 1 logframe was used to assess progress. Due to pressures across the office, this was not formally agreed till shortly before the annual review but reflects the initial ambitions. A new logframe for the remaining years will be finalised, using the outputs outlined in the business case, by December 2025. However, as the Grant Manager will end in March 2027 at the latest, rather than the initially envisioned 2030, the overall ambition of the programme has to be scaled down, which will be reflected in the logframe.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The most important recommendation is to ensure that the lessons from the predecessor programme (SPARC) are implemented, including:
- Engage, when appropriate, government stakeholders early in advocacy interventions.
- Encourage regular feedback mechanisms between citizens, CSOs, and government institutions.
- All initiatives must be informed by rigorous PEA; this was introduced at selection but must be continued throughout the lifetime of the programme and inform timely adaptations.
- Align the work on decentralisation by CSOs with that being supported by the RTAF, drawing out complementarities.
- Given the reduction in ODA funding, explore how to harness the UK’s technical expertise and convening power to support CSO advocacy and accountability interventions without direct funding.
Additionally, given the reduced timeframe, the sub-grantees must stay focused on specific policy outcomes that can be achieved within a short time. Through a co-creation model, each implementing partner has focused on a specific policy outcome instead of advocating for a variety of related issues. Other priorities for the coming year should be:
- Exploring innovative ways to continue to engage civil society, including through diplomatic convening;
- Completing the CSO capacity strengthening activities identified through the due diligence assessments in order to maximise he project’s legacy of improved capability; and
- Ensuring detailed and actionable documentation of learning on what work works to improve civil society participation in accountability processes to inform future work (including that funded by others).

## D: VALUE FOR MONEY

Key Cost Drivers and Performance
Given the nature of the Twiyubakire programme, by far the largest cost driver is personnel/expertise costs; this includes technical advisers embedded in the ministries, advocacy and thematic experts within the CSOs, and the programme-funded adviser. Given that both pillars are being delivered by management facilities, there are also significant costs associated with programme management, oversight, coordination, and MEL activities. There are also costs associated with meeting venues and procuring small amounts of equipment, but these are significantly smaller. Management costs have been a higher portion of expenditure this year given the need to mobilise, but overall costs have been in line with what was expected during business case design.

VfM Performance Compared to the Original Proposition in the business case
Following the UK’s ODA reduction from 0.5% to 0.3% of GNI, and the financial aid pause, Twiyubakire’s budget is expected to be reduced from £35 million over five years to approximately £3.2 million over two years (£2.2M for CSOs, and £1M for technical assistance). This decision will be confirmed by January 2026. In line with this significant budget cut, the ambitions of the programme are also being reduced, whilst ensuring the programme continues to deliver strong value for money.

Given the early stage of the programme, we cannot assess efficiency, effectiveness, or therefore cost-effectiveness yet. We expect to be able to make an initial assessment in the next annual review. Early performance against economy and equity is summarized below.

Economy
- The extension of the commercial contract with DAI continues to leverage the previously agreed terms to keep costs low, including that they cap consultant rates, keep overheads (like office rent) low, and principally engage national experts to enhance contextual relevance and lower costs.
- Trócaire was selected as the Civil Society Grant Manager through a competitive process that assessed their proposed costs against the market. Further negotiation was conducted on their budget to minimise unnecessary costs.
- Due diligence assessments on both DAI and Trócaire show that they have robust procurement processes and policies in place that favour lowest-price bids.
Equity
The CSO sub-grants are all focused on especially vulnerable populations as either the primary target or mainstreaming their inclusion; for example, CCOAIB is considering how to support subsistence farmers (who are some of the poorest and most food insecure in Rwandan society) and STRADH will be working on child labour.

Assessment of Whether the Programme Continues to Represent Value for Money
The above analysis suggests that whilst the programme is still in its early stages, it is so far delivering against economy and equity principles. However, the real challenge will be whether, given the significant reduction in scope (including the loss of financial aid component, severe reduction in budget, and, perhaps most importantly, the loss of time), it will still be able to deliver change at the outcome level. This will be monitored closely.

E: RISK

Overview of Risk Management

The overall risk rating at approval was ‘major’, and it remains so. This has been a challenging year for the Twiyubakire programme with large strategy and context risks (some that had been included in the risk register and others not) coming to fruition. The main issues that arose were the conflict in eDRC, which led to the UK imposing measures against Rwanda, and the global reduction in UK ODA. These have caused not only severe delays to implementation but will lead to early closure. The programme had been designed flexibly and with multiple delivery modalities, which has allowed the programme to shift (e.g. closing financial aid and prioritising technical assistance) to the new context but this has significantly impacted performance and what this programme will ultimately be able to deliver. Additionally, the change in UK-Rwandan relations and compressed implementation timeframe have increased the delivery risks across the technical assistance and civil society components. However, we have put mitigations in place, including more regular check ins with partners and building strong technical level relationships.

All risks are currently within appetite but being monitored closely.
- Strategy & Context Risks: Major - within appetite. Due to the issues that arose earlier in the year, the programme has significantly shifted how it delivers and is now less exposed to the ongoing risks. However, there remain important risks around the eDRC peace process faltering, changes in key government officials leading to loss of buy in, and the CSOs failing to get traction for their reforms with the government.
- Policy & Programme Delivery Risks: Moderate - within appetite. These are principally focused around getting the necessary engagement from government ministries and poorly targeting or coordinating workstreams. These are being mitigated through strong stakeholder engagement, co-creation of terms of reference, and regular check-ins with implementing partners.
- Safeguarding Risk: Moderate - within appetite. All TA experts received induction training on ethics and safeguarding, and contracts include safeguarding clauses. Trócaire has identified safeguarding gaps in CSOs and is addressing them through capacity strengthening; this is critical given some of the CSOs will be working with very vulnerable populations.
- Financial & Fiduciary Risk: Moderate - within appetite. The main concerns are the misappropriation of funds and risk of underspend. There have been no issues reported in these first months of implementation and the due diligence assessments for both Tier 1 partners showed they have robust financial controls. Trócaire has been, understandably, slow to start spending but this does raise the risk of a significant underspend; this is being monitored closely with the partner.
- Reputational Risk: Moderate - within appetite. There are several reputational risks around our work with the GoR, given the measures, as well as the perceptions of how we are working with the government and civil society on accountability. These are being managed through careful communication and ensuring that we identify suitable areas of overlapping interests.
- People Risk: Moderate – within appetite. The most important risk was the challenge of recruiting qualified TA experts and CSO staff. The main recruitments have been completed now but there remains a risk in keeping those staff and them having sufficient availability to complete the work.

As the conflict in eDRC escalated, the context/reputational risks did end up outside of appetite; however, the programme has otherwise operated within its risk appetite. Areas of pressure (e.g. CSO capacity gaps, compressed timelines) have been managed through adaptive planning, increased support, and close coordination with partners. No changes to the risk appetites are proposed at this stage.

Equality and Inclusion

The programme remains aligned with Gender Equality and Public Sector Equality Duties. Trócaire’s CSO selection and engagement models prioritise inclusion of women, youth, and marginalised groups and will collect disaggregated data whenever possible.

Due Diligence Assessments

FCDO conducted a new due diligence assessment (DDA) of Trócaire, as part of their onboarding, which overall found the organisation both globally and in Rwanda to have strong systems in place. It did identify a few key risks and FCDO’s Programme Manager has worked closely with Trócaire to ensure suitable measures are being taken to address and mitigate these:
- Inconsistent documentation of project-level risk registers.
- Only partial rollout of data protection policies to downstream partners.
- Trainings not always being contextualised to local needs or languages.
- No explicit foreign exchange risk mitigation strategy.
- Limited detail on VfM cost drivers and output-specific data.
- Community feedback and complaints not consistently being documented.
- Safeguarding trainings are not always tracked or contextualised.
Trócaire also conducted DDAs for the downstream CSOs. These identified some key risks, including:
- Weak financial management systems.
- Incomplete safeguarding policies.
- Limited proposal writing and strategic planning capacity.
It is a specific goal of the programme to build civil society capacity, including in these more administrative/compliance areas, so not only are short-term mitigations in place but Trócaire is developing capacity strengthening plans with each of the partners.

Update on Partnership Principles

In February 2025, in response to the situation in Eastern DRC, the UK took measures against Rwanda, including pausing “direct bilateral financial aid to the Government of Rwanda (GoR), excluding support to the poorest and most vulnerable”. This, in combination with the reduction in global ODA, means there have been, and will be, no disbursements of financial aid under this programme. Going forward, the Partnership Principles will continue to guide UK support to Rwanda.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Given this year was focused on mobilisation, section C discusses progress in establishing the main components of the programme. However, in summary, the programme was designed to be delivered through the following four mechanisms:
1. Non-budget support financial aid to MINALOC and MINECOFIN – this was paused and, due to the global reduction in ODA, has now been closed without any disbursements.
2. A commercial contract to deliver a technical assistance facility – due to the global pause in ODA, the competition for a new 5-year delivery partner was cancelled and a 9-month costed-extension was issued to the previous Rwanda Technical Assistance Facility (RTAF), delivered by DAI under the predecessor programme (SPARC).
3. An accountable grant to deliver the civil society grant management – a competition was successfully completed, but the contract is for 20 months, rather than 5-years.
4. A grade 7 programme-funded adviser to support coherence – an adviser was recruited through a competitive process in January 2025.
Technical Assistance Facility

DAI has demonstrated strong performance in the mobilisation and delivery of the Rwanda Technical Assistance Facility (RTAF) under Twiyubakire. Since the contract extension was signed in June 2025, DAI have successfully scoped and launched 12 technical assistance interventions in collaboration with MINALOC, MINECOFIN, and other government institutions. These interventions are aligned with national priorities and build on previous SPARC programme achievements.

DAI’s financial management has been robust:
- The total budget for the 9-month extension period is £1M. During the first three months of implementation, they have spent 36% of this, primarily on TA fees and initial activities.
- Forecasting has been accurate.
- Procurement and recruitment processes have been transparent and compliant with FCDO standards.
- DAI has achieved savings of over £52,000 through internal scoping and negotiation with TA experts, demonstrating strong cost control and commercial discipline.
- DAI has complied with the Supply Partner Code, and all TA experts have signed contracts with ethics and safeguarding clauses. Open Book Accounting principles have been followed, and no profit variance issues have been reported.
CSO Grant Manager

After significant delays to the competition, the agreement with Trócaire was signed in mid-July 2025. During a truncated inception period, they have so far completed the:
- Selection and onboarding of five CSOs following a rigorous due diligence and capacity assessment process;
- Recruitment of key staff (Team Leader, Finance Manager, Advocacy Advisor, Capacity Strengthening Advisor); and
- Procurement of equipment through competitive bidding.

The budget for FY 2025/26 is £1.2M, but they have only spent 4% of that so far, which means there is a risk of under, or rushed, spending given the limited time to implement what is an ambitious component. This does raise concerns about their forecasting, but activities are expected to accelerate in the next quarter, which will give a more accurate picture. Disbursements are made in arrears, and financial controls are in place. Some key programme documents, such as the asset register, are still being established.

The inception period ends in December 2025, and a decision will be made then on continuing until March 2027 (or stopping in March 2026).

Programme-funded adviser (PFA)

The PFA has worked closely with both the grant manager and DAI to quickly identify priorities and specific projects, as well as to ensure coherence between the components. They have helped steer the programme and have been critical to making quick adaptations and maintaining working level relationships with the GoR. They have also worked internally to support other High Commission teams with governance issues; for instance, they are working with the education team on decentralisation.

FCDO Management

Changes in FCDO policy have been the main cause of delays to the programme; going forward, it should be a priority to provide strategic clarity for the remainder of implementation. Given these uncertainties, BHCK should continue the regular (at least monthly) check-ins with both Tier 1 partners. Additionally, the programme team is working closely with both partners to ensure financial management requirements are accurate and timely. Partners provide FCDO with quarterly invoices, financial, and narrative reports. As a safeguard, the programme team scrutinise progress reports in conjunction with annual workplans, budgets, and milestone schedules and discuss progress with partners prior to disbursement of funds or payment of invoices. As partners are now in implementation, monitoring visits will be conducted for all programme components.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
As activities only began in July 2025, the focus of both implementing partners has been on mobilisation, onboarding, and foundational activities. The FCDO programme team monitored the progress of competitions and recruitments, and activities are now getting underway this month. Partners’ logframes and theories of change have been designed to be aligned with the overall programme documents and are feeding into the finalisation of the outer year programme-level logframe. Monitoring information will be received quarterly from both partners.

The RTAF was evaluated through an independent impact evaluation earlier this year (2025), as part of the predecessor programme’s (SPARC’s) Programme Completion Review (PCR). Recommendations from that evaluation have informed their remaining programming as far as possible (given the short timeframe).

The Civil Society Grant Manager is developing an adaptive monitoring, evaluation, and learning approach that will be implemented throughout the project. They are currently collecting baseline data across the sub-grantees.

Evidence

This programme is informed by its predecessor, whose PCR was finalised in September 2025. No further evidence has been generated under Twiyubakire, but both components are testing new approaches, capturing learning, and the civil society component will be generating evidence on specific advocacy issues. Monitoring data will be disaggregated by age, sex, disability, and geography, in line with the Leave No One Behind agenda.

Learning

Adaptive learning has been embedded across both components, but given the early stage of the programme there has been little learning in the first months of implementation, though RTAF has highlighted the importance of flexible TA design and collaborative recruitment to securing buy-in, and the Civil Society Grant Manager has already identified the need to support smaller CSOs on their proposal writing skills.

Date of last narrative financial report	October 2025: DAI Quarterly Report / November 2025: Trócaire Quarterly Report	Date of last audited annual statement	N/A