Accountable Grant Arrangement

Between

The Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”)
and
Trócaire (“the Partner”)
together called “the Participants”

FCDO Project Name: Twiyubakire - FCDO Civil Society Grant Manager
FCDO Project Number: 400197 - 404

  1. In any correspondence with FCDO with regard to this Arrangement, reference must be made to the Project Name and Project Number shown above.

Provision of grant
  1. The FCDO has agreed to pay the Partner a Grant for the delivery of the Project on the understanding that the Partner uses the Grant in accordance with, and continues to fulfil the provisions of, this Accountable Grant Arrangement, its annexes (including Annex 1: Project Definitions) and the corresponding Proposal (Inclusive Accountability: A Pathway to Strengthened Governance, see Annex 8), logframe (see Annex 9), and Project Budget (see Annex 10). Together these documents form “the Arrangement” and set out the purpose for which the Grant will be used and the provisions that apply to the Partner.

  1. The Project to which this Arrangement relates will start on 16th July 2025 and end on 31st March 2027 (“Project End Date”) unless terminated earlier. FCDO will make available an amount not exceeding £2,200,000.00 (two million two hundred thousand pounds sterling). The amount is expected to be allocated across the following years.

FCDO Financial Year (by quarter)	Quarterly Allocation (£GBP)
16 July – 30 September 2025:	£357,723.50
1 October – 31 December 2025:	£441,108.10
1 January – 31 March 2026:	£401,168.40
1 April – 30 June 2026:	£298,800.00
1 July – 30 September 2026:	£262,600.00
1 October – 31 December 2026:	£312,700.00
1 January – 31 March 2027:	£125,900.00

  1. The funding amount is subject to revision and is dependent on the fulfilment of the provisions of this Arrangement, any revisions to budgets, actual expenditure and need and the continuing availability of resources to FCDO.

Status and compliance with the law
  1. The Partner is registered as a not for profit organisation and has the capacity to comply with the provisions set out in this Arrangement. If not previously provided, the Partner must provide evidence of its status to FCDO. The Partner must notify FCDO immediately if its status changes in any way.

  1. The Partner and any person, organisation, company or other third-party representative engaged as part of this project (“Downstream Partners”) will at all times comply with all applicable legislation, regulations and rules both in the countries they are registered and operating in. All Partners will comply with their reporting obligations to relevant national and international bodies such as the Charity Commission for England and Wales.

Prevailing language and amendments
  1. In the event of translation, the English text of this document will prevail.

  1. Any amendments to this Arrangement will be set out in writing and approved through FCDO’s standard amendment letter or, where appropriate, a revised Arrangement.

Special provisions
  1. The Partner accepts the following specific provision relating to this Arrangement:
Review Point 1: This Arrangement shall be subject to a formal review at the end of the Inception Phase [March 2026]. Following such review, the FCDO may, at its sole discretion, taking into account available funding and the Partners performance, choose to: (a) continue; (b) amend; or (c) terminate the Arrangement in line with the obligations set out in Clause 8, Amendments, and Clauses 90 – 94, Termination & Closure.

Eligible expenditure
  1. The funding amount is to be used solely for costs included as part of the budget agreed with FCDO for the delivery of the outputs and outcomes set out in the logframe (see Annex 9) included as part of this Arrangement.

  1. FCDO funding will not be used to meet the costs of any other expenditure. In particular the Grant cannot be used to pay any of the ineligible items set out in FCDO’s Eligible Cost Guidance for Accountable Grants as amended from time to time, unless they are expressly agreed in advance and in writing by FCDO and included in the Project Budget. In case of any doubt on the eligibility of any item of expenditure, the Partner will consult FCDO prior to incurring or committing to incur the cost.

  1. Additionally, FCDO funds will not be used, unless explicitly approved by FCDO in writing in advance, to meet the cost of any refundable duties, taxes or similar charges applied by local Governments or by any local public authority.

Non-project attributable costs (NPAC)
  1. The Partner will adhere to FCDO’s Eligible Cost Guidance for Accountable Grants.

  1. The Non-project Attributable Costs (NPAC) to be paid by FCDO for this project are as calculated in the agreed budget.

  1. The maximum amount of NPAC payable under this arrangement will be calculated based on the final total of FCDO funds spent under this arrangement.

  1. Any change to the budget, including NPAC, must be explicitly approved by FCDO in writing in advance. The Partner will inform FCDO of any significant changes to organisational overheads that may affect the NPAC.

  1. The Partner will repay any surplus NPAC following a final reconciliation against total spend at the end of this project.

Digital Spend
  1. The Partner will ensure that all Digital Spend related to this Arrangement is carried out in a manner consistent with the Digital Service Standard, the Technology Code of Practice and the Principles for Digital Development.

  1. The Partner and its Downstream Partner(s) (of any spend £100,000 and above) will notify the FCDO programme team of any proposed digital spend prior to carrying out any digital activities. FCDO will then engage with the respective Partner or Downstream Partner to complete the 'Get approval to spend' online form on their behalf. The FCDO programme team will receive feedback and approvals from FCDO’s Portfolio Assurance Team, which will be shared with the respective Partner or Downstream Partner(s).

Disbursement and financial reporting
  1. The funding amount approved is as per the Sterling (GBP) value, as at the date of signature of this Arrangement. FCDO’s preferred currency for disbursements is in GBP. Where it is more efficient to pay in foreign currency, FCDO may do so, however, the funding amount will still be that approved in GBP as at the date of signature of this Arrangement. Budgets must be submitted in GBP with the stated exchange rate specified (including the date and the source of rate used).

  1. The Partner is responsible for monitoring and managing any exchange rate fluctuations across the life of the project. Where significant exchange rate gains or losses are being accumulated the Participants will jointly decide how these are managed.

  1. Where costs are incurred in foreign currency the Partner will use the monthly average exchange rate stated in OANDA (www.oanda.com) for the month in which the purchase was made or services acquired by the Partner. Use of any other exchange rate should be approved in writing in advance.

  1. In line with UK Government financial regulations, FCDO will not pay in advance of operational or commercial need and justification will be required for any FCDO payment prior to partner disbursement. Where a Pre-Payment is approved and the Partner is holding FCDO funds, prior to disbursement, funds should be held in a minimum risk interest bearing account. Any interest accruing from these investments will be re-invested within the project.

  1. When requesting payment, the Partner will complete Annex 2: Partner Payment Request Form. Along with the request the Partner should provide detailed project financial reports that set out in both cash and resource terms actual expenditure to date against the approved project budget and quarterly forecast expenditure for FCDO’s financial year (1 April-31 March). Where payment in advance has been agreed, a copy of the Partner’s justification and FCDO’s agreement should be included with each payment request. In multi-donor arrangements, these reports should clearly segregate the FCDO proportion of funding.

  1. Payment will be made to the bank account details provided. The Partner will ensure that these details are shared with the key contact in the FCDO Programme Team and provide updates as needed if bank details change. The Partner should confirm the details for this Arrangement within the Payment Request Form for each payment.

  1. All outstanding claims must be submitted no later than six months after the Project End Date.

  1. The Partner will reimburse FCDO any overpayment or erroneous payment made by FCDO within 30 days of receiving a sales invoice.

  1. FCDO may, from time to time, request project financial reports for the calendar year in line with Official Development Assistance reporting requirements.

  1. FCDO funds must be separately accounted for by the Partner and therefore readily identifiable at all times unless explicitly approved otherwise and in writing by FCDO.

Performance reporting
  1. The Partner will provide FCDO with quarterly progress reports on the execution of this Arrangement that describe performance against indicators contained in the logframe (see Annex 9) and, where possible, the associated receipt and utilisation of the resources used to deliver these. Continuation of this Arrangement after year one will be dependent upon satisfactory progress and Value for Money, as defined in Annex 1: Project Definitions, being achieved each previous year.

  1. The Partner will at least once annually as part of the regular reporting outlined above, provide a proportionate and meaningful summary of:
- how they have given due regard to the need to: a) prevent discrimination, harassment and victimisation; b) advance equality of opportunity between persons who share and do not share protected characteristics; and c) foster good relations between those persons (in particular the protected characteristics of disability, race, sex, age, religion or belief, gender reassignment or sexual orientation).
- specific needs of girls, women, boys and men, and the extent to which women and girls have been included in design, implementation and monitoring of the Project. This will include an assessment of:
  - how the Grant supports the reduction of gender inequality;
  - progress against any gender-related commitments made in the Proposal; and,
  - potential unintended negative consequences, such as gender-based violence.

  1. The Partner will at least once annually as part of the regular reporting outlined above in line with the UK Government’s commitment to align all UK ODA to the Paris Agreement and the Kunming Montreal Global Biodiversity Framework, provide a summary of how climate and environment risks and opportunities have been proportionately considered throughout design, implementation and monitoring of the project. This will include an assessment of:
- the impact of the Project on current and future climate and environment risk (including any opportunities);
- the vulnerability of the Project itself to current and future climate and environment risk;
- a summary of any mitigating actions put in place (including how environmental safeguarding concerns have been considered) where relevant.
In addition, programmes that address climate change mitigation and / or adaptation must report on all relevant International Climate Finance (ICF) Key Performance Indicators (KPIs), disaggregated to the appropriate level following FCDO’s Inclusive Data Charter.

  1. The Partner will immediately notify FCDO of any delay, obstruction or event which interferes with or threatens to interfere with this Arrangement. This includes any delay, obstruction or event which damages or is capable of damaging the reputation or integrity of FCDO or that of the Project.

  1. The Partner will seek to ensure that beneficiary feedback is integrated in project design, mobilisation, delivery, monitoring, evaluation and annual review processes and takes account of the voices of both women and men. The Partner should work with, through and represent the diversity of communities in order to respond to their needs more effectively and strengthen accountability.

Due diligence
  1. In utilising the resources, the Partner will exercise the same care in the discharge of its functions under this Arrangement as it exercises with respect to the administration and management of its own resources and affairs. The Partner will co-operate fully with any due diligence assessment by FCDO or its agents, of the Partner’s own internal controls and system prior to or during the implementation of this Arrangement and take appropriate action on any recommendations arising. Due diligence assessments may be conducted every 3 years or earlier if there is a significant change to the Partner’s procedures and controls or operating environment. A range of tools may be used to conduct the assessment and continuation of this Arrangement will be dependent on FCDO being satisfied that the Partner has sufficient capacity and capability to deliver the project and manage FCDO funds.

  1. The Partner will undertake suitable due diligence and take the necessary steps prior to transferring FCDO funds and at regular intervals throughout the implementation to assess the internal controls and systems of any Downstream Partners. These assessments will be shared with FCDO, upon request and should determine, relative to project risk:
- the reliability, integrity and efficiency of the Downstream Partners’ controls, systems and processes including compliance with applicable legislation, regulations, rules, policies and procedures;
- whether the Downstream Partner can successfully deliver the relevant outputs based on its processes, past experience and whether they have the sufficient staff capacity and capability available;
- the Downstream Partner’s ability to correctly manage and account for aid monies and assets as well as its financial health; and
- where appropriate, whether the Downstream Partner has sufficient capacity and capability to properly monitor and control its implementing partners.

  1. The Partner is accountable for ensuring Downstream Partner assessments are completed, however it may choose to pass all or part of its responsibility for conducting these assessments down the delivery chain. Where it does so, the Partner will ensure that the Downstream Partner conducting the assessment has sufficient capacity and capability to conduct these assessments in a manner consistent with the Partner’s obligations under this Arrangement.

Delivery chain risk mapping
  1. The Partner will maintain and provide to FCDO an up to date and accurate record of Downstream Partners in receipt of FCDO resources. This forms the basis of the delivery chain risk map which should demonstrate how funds flow from the initial source to end beneficiaries, and the risks and potential risks along the chain.

  1. The delivery chain risk map should be updated regularly by the Partner and when there are material changes to the project risk assessment and/or to delivery partners in the chain. As a minimum the Partner will provide FCDO with an updated delivery risk map at the following intervals:
- within 60 days of the commencement of this Arrangement;
- annually, as part of the annual review Process; and
- at the end of the project, as part of the project completion review process

Audit and assurance
  1. The Partner will within six months of the end of their financial year provide FCDO with independent assurance that FCDO funds have been used for the intended purposes. This includes for all financial years in which they receive and/or spend FCDO funds under this Arrangement even where the end of the financial year is beyond the life of this Arrangement. The Partner will provide annual accounts audited by an independent and appropriately qualified auditor where FCDO project funding is clearly segregated from other funds.

  1. The Partner will ensure that all goods and services financed either fully or in part from FCDO funds will continue to be used for the purpose set out within this Arrangement. In the event of such goods or services being used for other purposes, the Partner must notify FCDO immediately and in writing and FCDO may seek to recover from the Partner the value of the goods and services concerned.

  1. The Partner will retain all records associated with this Arrangement for a period of not less than 5 years after the end of this Arrangement.

Information and data protection obligations
  1. The Partner acknowledges that FCDO is subject to the requirements of the Freedom of Information Act 2000, the Environmental Information Regulations 2004, the UK General Data Protection Regulation (UKGDPR), the Data Protection Act 2018 (DPA), subordinate legislation and guidance and codes of practice issued by the Information Commissioner and relevant Government Departments.

  1. The Partner will assist and co-operate with FCDO to enable FCDO to comply with its information disclosure and data protection obligations.

  1. The Partner is the controller of any data created or processed and will perform its obligations under this Arrangement in such a way as to protect the personal information of individuals.

  1. The Partner will comply at all times with its obligations under the UKGDPR and DPA.

Transparency
  1. The Partner will publish to the International Aid Transparency Initiative (IATI) standard on all its FCDO funding within six months of the start of this Arrangement. FCDO expects the Partner to publish to the IATI standard on all its non-FCDO funding and for Downstream Partners to publish to the IATI standard on their funding. The intention of this commitment is to allow traceability throughout the delivery chain. For further advice please go to FCDO IATI Guidelines - GOV.UK (www.gov.uk).

  1. The Partner gives consent for this Arrangement (and any subsequent amendments) and associated funding information to be published on FCDO’s website.

Open Access
  1. The Partner will make all in scope research outputs from the ‘Twiyubakire – FCDO Civil Society Grant Manager’ programme available to the public in accordance with the FCDO Open Access Policy as may be updated from time to time.

Responsibility
  1. The Partner is solely accountable for compliance with the provisions of this Arrangement including where the Partner engages any Downstream Partner(s). The Partner will reflect the provisions of this Arrangement as necessary in any arrangement(s) with any Downstream Partner(s) to ensure both the Partner and Downstream Partner(s) are compliant with the provisions of this Arrangement.

  1. FCDO will not be responsible for the activities of the Partner or any Downstream Partner(s) in connection to this Arrangement, nor will FCDO be responsible for any costs incurred by the Partner or its Downstream Partner(s) in terminating their engagement or the engagement of any other person, company or organisation.

  1. The Partner will be accountable for the appropriate use of FCDO funds, management of risk and delivery of project outputs and outcomes, including any adverse effects of aid expenditure that have an undesired or unexpected result upon recipients including any adverse gender related impacts.

  1. FCDO may at any time during, and up to five years after the termination of this Arrangement, conduct or arrange for additional investigations, audits, on-the-spot checks and inspections to be carried out, or ascertain additional information where FCDO considers it necessary. These may be carried out by FCDO or any of its duly authorised representatives or agents. Access will be granted, as required, to all sites and relevant records. The Partner will ensure that necessary information and access rights are explicitly included within all funding arrangements with its Downstream Partner(s).

Risk management
  1. The Partner will establish an effective project risk management process that takes account of the Project context and as a minimum includes:
- Maintaining an up-to-date risk register that enables individual risks to be clearly identified, with explicitly allocated ownership, and includes an assessment of the likelihood and impact of the risks materialising and details of how the risks will be managed. The Partner will share the risk register with FCDO upon request;
- A regular dialogue in line with agreed reporting requirements on risk with FCDO, Downstream Partners and other relevant Project stakeholders;
- The escalation to FCDO, as soon as possible, of any new or change to existing risk or issue that has the potential to materially impact on the delivery of the Project, the use of the Grant or the reputation or integrity of FCDO.

  1. The Partner will manage all risks in relation to this project unless otherwise approved as part of the risk register and in writing with FCDO. Where the Partner transfers risk to any Downstream Partner, the Partner will remain accountable to FCDO for the effective management of that risk.

Cyber security
  1. Cyber security is the protection of systems, networks and data to prevent cybercrime. The Partner is responsible for managing cyber security risk under its own policies and procedures.

Procurement
  1. The Partner will ensure that any procurement using FCDO funds adheres to international best practice and applicable regulations, is transparent, fair and open and is designed to achieve value for money.

  1. Records of all procurement activity including but not restricted to, costs, volumes, suppliers, value for money, savings and efficiencies must be kept by the Partner and made available to FCDO, upon request. FCDO reserves the right to assess the procurement capacity and capability of the Partner at any time.

Exclusivity Arrangements
  1. The Partner will not include in any arrangement related to this project with any Downstream Partner(s) any provisions which limit Downstream Partner(s) from working directly with FCDO or any other organisation, except as required under paragraph 82 of this Arrangement.

Assets and inventory
  1. The Partner will establish and maintain an inventory of all Project Assets, as defined in Annex 1: Project Definitions.

  1. The Partner will ensure that a physical check of all assets takes place on at least an annual basis and submit to FCDO an up-to-date inventory using the template provided in Annex 3: Inventory, providing confirmation of the checks, alongside the annual accounts. Where possible the Partner should undertake these checks directly.

  1. The Partner will be accountable for the appropriate use and control of inventory items, in line with this Arrangement.

  1. The Partner will manage the risk of assets being lost, stolen, damaged or destroyed under its own policies and procedures. FCDO expects the Partner to cover the cost of repairing or replacing lost, stolen, damaged or destroyed assets and should make a risk-based decision on how best to do this. If the Partner decides to take out project specific commercial insurance to cover lost, stolen, damaged or destroyed assets, FCDO funds cannot be used to fund the premiums unless, by exception, explicitly approved in writing in advance.

  1. FCDO will retain ultimate ownership of all assets, specifically project assets, financial assets and information assets, until ownership transfer or asset disposal is otherwise approved in writing by FCDO normally at the end of this Arrangement. The Partner should propose an appropriate disposal schedule to FCDO in writing no later than 14 days before the Project End Date.

Health, safety and security
  1. The Partner is responsible for all security arrangements in relation to this Arrangement including the health, safety and security of any person employed or otherwise engaged as part of this Arrangement, including those employed or engaged by any Downstream Partners.

  1. FCDO funds cannot be used to fund any project specific insurance premiums intended to cover medical expenses, injury or disablement, and death unless, by exception, explicitly approved by FCDO in writing in advance.

Environment
  1. The Partner is committed to high environmental standards, recognising that their activities may change the way people use and rely on the environment, or may affect or be affected by environmental conditions. The Partner will ensure that they have taken sufficient steps to protect the local environment and community they work in, and to identify environmental risks that are imminent, significant or could cause harm or reputational damage to FCDO.

Communication and branding
  1. The Participants will collaborate and proactively look for ways to build support for development and raise awareness of FCDO’s funding. The Partner will explicitly acknowledge FCDO’s funding, in written and verbal communications about activities related to the funding, to the public or third parties, including in announcements, and through use, where appropriate, of FCDO's “UK International Development – Partnership, Progress, Prosperity” logo (‘UK Dev logo') in accordance with FCDO Branding Guidance for ODA funded programmes, unless otherwise approved in advance by FCDO, and in all cases subject to security and safety considerations of the Partner.

  1. The Partner will provide a visibility statement using the template provided in Annex 4: UK International Development and UK Aid Visibility Statement of how and when they will acknowledge funding from FCDO and where they will use the UK Dev logo, which should be approved by FCDO prior to the Partner releasing any public communications. The Partner will include reference to this in its progress reports and annual reviews.

  1. The Partner may use the UK Dev logo in conjunction with other donor logos, and where the number of donors to a project is such as to make co-branding impractical, acknowledgement of funding from FCDO should be equal to that of other co-donors making contributions of equivalent amounts to the project.

Intellectual property
  1. Intellectual property in all material (including, but not limited to, reports, data and designs, whether or not electronically stored) produced by the Partner or its personnel, members or representatives in the course of this Arrangement (“the Material”) will be the property of the Partner.

  1. In signing this Arrangement, the Partner hereby grants to FCDO a worldwide, non-exclusive irrevocable and royalty-free licence to use all the Material, where “use” shall mean, without limitation, the reproduction, publication and sub-licence of all the Material and the intellectual property therein, including the reproduction and sale of the Material and products incorporating the same, for use by any person or for sale or other dealing anywhere in the world.

  1. FCDO shall inform the Partner before it seeks to sub-license or reproduce and sell any Material and the intellectual property therein, for use by any person or other dealing anywhere in the world in relation to the license agreed in paragraph 76.

  1. Ownership of Third-Party software or other intellectual property necessary to deliver the activities funded by this Arrangement remains with the relevant Third-Party. The Partner must ensure they have obtained relevant agreement from the third-party before any additions or variations are made to the standard ‘off-the-shelf’ versions of any Third-Party software or other intellectual property. The Partner will be responsible for obtaining and maintaining any appropriate licences to use the Third-Party software.

Conflict of interest
  1. Neither the Partner nor any individual employed or contracted by the Partner shall engage in any personal, business or professional activity which conflicts or could conflict with any of their obligations in relation to this Arrangement. The Partner will inform FCDO as soon as possible if there is a conflict of interest which interferes or threatens to interfere with this Arrangement, whether financed in full or in part by FCDO. The Partner will share the conflict of interest register relating to this Arrangement on request.

Aid Diversion
  1. Aid Diversion is any event, including fraud, corruption, bribery, theft, terrorist financing, money laundering and other misuse of funds that prevents funds being directed to the aid outcomes or recipients intended.

  1. The Participants will immediately and without undue delay inform each other of any event which interferes or threatens to interfere with this Arrangement, whether financed in full or in part by FCDO, including credible suspicions of, or actual Aid Diversion. The Partner should assess credibility based on the source of the allegation, the content, and the level of detail or evidence provided.

  1. The Partner should immediately contact FCDO’s Counter Fraud Section at reportingconcerns@fcdo.gov.uk or +44 (0)1355 843747 if they have any cause to suspect a case of fraud or misuse of funds. All information will be treated with the utmost confidentiality. Information can also be reported directly to the FCDO programme team managing where appropriate; this will be immediately passed on to FCDO’s Investigations Department. The Partner should also ensure Downstream Partners are aware of how to contact FCDO’s Investigations Department.

  1. The Participants have a zero-tolerance approach towards inaction or mishandling of Aid Diversion. Both Participants will fully co-operate with investigations into such events, whether led by FCDO or the Partner.

  1. Notwithstanding any provisions in this Arrangement or other contractual requirements, FCDO may recover from the Partner all or part of the funds paid under this Arrangement in the event of actual or suspected Aid Diversion.

  1. It is the policy of the FCDO to prevent and suppress the financing of terrorist acts and to refrain from providing support to those organisations and individuals involved in them. In accordance with this policy, the FCDO expects the Partner to take all reasonable steps to ensure that activities funded by the Grant comply with relevant United Nations Security Council resolutions, including S/RES/1267 (1999) and S/RES/1373 (2001), and related resolutions S/RES/2462 (2019) and S/RES/2664 (2022).

  1. The FCDO expects the Partner to take a risk-based approach and consider its likely exposure to UK sanctions and terrorism legislation and to take all reasonable steps to mitigate the associated risks, including in relation to making funds available to designated persons or entities, or proscribed groups, including those on the following lists as updated from time to time:
Consolidated List of Financial Sanctions Targets in the UK[1] - HMT Treasury
Proscribed Terrorist Organisations in the UK[2] - UK Home Office

      The Partner shall not be in breach of this paragraph if it conducts activities under this Arrangement which are covered by an exception contained in UK law or by a general licence issued by the UK Government.

  1. The need to respect relevant UK terrorism legislation and sanctions regulations should not impede the timely delivery of humanitarian assistance or other activities that support basic human needs in accordance with humanitarian principles, international humanitarian law and human rights law, and S/RES/2462 and S/RES/2664. The Partner is therefore not expected to screen end-beneficiaries. The Partner and any Downstream Partners are also not precluded from liaising with designated persons or members of designated entities and proscribed groups to implement the activities funded by this Arrangement.

Safeguarding for the prevention of sexual exploitation, abuse and sexual harassment
  1. The Participants have a zero tolerance for inaction approach to tackling sexual exploitation, abuse and sexual harassment (“SEAH”) and agree the terms set out in Annex 5. This means the Partner, and its implementing partners, will take all reasonable and adequate steps to prevent SEAH of any person linked to the delivery of this Arrangement by both its employees and any implementing partner and respond appropriately when reports of SEAH arise. The Partner will apply the IASC Six Core Principles relating to Sexual Exploitation and Abuse and will adhere to the IASC Minimum Operating Standards on PSEA and/or the Core Humanitarian Standard on Quality and Accountability.

  1. When the Partner becomes aware of suspicions or complaints of SEAH, the Partner will take swift and appropriate action to stop harm occurring, investigate and report to relevant authorities (for criminal matters) when safe to do so and after considering the wishes of the survivor. The Partner will also promptly contact FCDO at reportingconcerns@fcdo.gov.uk to report any allegation credible enough to warrant an investigation of SEAH related to this Arrangement. The Partner will promptly report to FCDO any allegation credible enough to warrant an investigation of SEAH that are not directly related to this Arrangement but would be of significant impact to the partnership with FCDO. It is understood and accepted that the Partner’s arrangement to report on SEAH is subject to not compromising the safety, security, privacy and due process rights of any concerned person.

Termination and closure
  1. To allow for final payments, this Arrangement will terminate six months after the Project End Date unless terminated earlier in accordance with the provisions in this Arrangement.

  1. If FCDO is concerned that the provisions of this Arrangement have not been fulfilled by the Partner, or if any activities occur which will significantly impair the implementation or development value of the project, FCDO will discuss its concerns with the Partner in an attempt to resolve any issues. Following such negotiation, this Arrangement may be amended, suspended or terminated in accordance with the relevant provisions in this Arrangement.

  1. This Arrangement can be terminated at any time by three months’ written notice by either Participant. All unspent funds other than those irrevocably committed in good faith before receipt of a written notice of termination, in line with this Arrangement and approved between the Participants as being required to finalise activities, will be returned to FCDO within 30 days of the date of receipt of a written notice of termination. At any time when returning funds, the Partner must quote the relevant Sales Invoice reference number.

  1. Notwithstanding any provisions in this Arrangement or other contractual requirements, FCDO may suspend or terminate this Arrangement with immediate effect, in preference to the standard notice period, and at its discretion may recover all or part of the funds paid under this Arrangement if any of the following occur:

The Partner directly or through its Downstream Partners either repeatedly fails to comply with, or is in material breach of, any of the provisions of this Arrangement or any other FCDO arrangement or contract whether currently or previously in place;

The Partner, or any Downstream Partner, at any time during this Arrangement becomes insolvent or goes into liquidation, administration or other similar process, is dissolved or enters into any arrangements with its creditors;

The Partner or any Downstream Partner, without the prior consent of FCDO in writing, assigns or transfers, or purports to assign or transfer, or causes to be assigned or transferred, any interest in this Arrangement or any part, share or interest therein;

There is a change in identity or character of the Partner (such assessment to be made at FCDO’s sole discretion) or that of any Downstream Partner including, but not limited to, through the take-over, merger, change of ownership or control.

An event occurs which materially affects, or has the potential to materially affect, the performance of the Partner’s obligations as part of this Arrangement;

In the event of actual or suspected Aid Diversion;

In the event of actual or suspected sexual exploitation, abuse or harassment;

An event occurs which damages, or is capable of damaging, the reputation or integrity of FCDO or that of the project to which this Arrangement relates.

  1. The Partner will return any surplus NPAC and unspent funds remaining at the end of this Arrangement within 14 days of receiving a Sales Invoice from FCDO, unless otherwise agreed by FCDO in writing. At any time when returning funds, the Partner must quote the relevant Sales Invoice reference number.

Signature
  1. This Arrangement places on record the understanding of the Participants and comes into operation on the date of signature below.

Signed on behalf of FCDO
Name:
Position:	Political Counsellor and Head of the Political and Governance Team, British High Commission Kigali
Address/Contact Details:	British High Commission Kigali, / KG 7 Avenue / Kigali / Rwanda
Date:	15th July 2025

Signed on behalf of the Partner:
Name:
Position:	Head of Portfolio – Climate & Gender
Address/Contact Details:
Date:	15th July 2025

### ANNEX 1: PROJECT DEFINITIONS

AID DIVERSION	Any event, including fraud, corruption, bribery, theft, terrorist financing, money laundering and other misuse of funds that prevents funds being directed to the aid outcomes or recipients intended.
ANNEX(ES)	The Annexes attached as part of this Arrangement, including the Proposal, Results Framework and Project Budget
ANNUAL ALLOCATION	The maximum amount of the Grant that has been allocated to be paid/spent in each Financial Year
ANNUAL REPORT	A report submitted annually that describes performance against the output and outcome indicators in the Results Framework and the utilisation of the Grant to deliver, covering the previous 12 months
ARRANGEMENT END DATE	Six months after the Project End Date
BENEFICIARIES	The people, communities, populations and constituents that the Project intends to benefit as defined in the Proposal and Results Framework.
BENEFICIARY ENGAGEMENT	The two-way process of involving beneficiaries in the design, delivery, monitoring, review and evaluation of the Project.
CONFIDENTIAL INFORMATION	Confidential information means any information (however conveyed, recorded or preserved) disclosed by a party or its personnel to another party (and/or that party’s personnel) whether before or after the date of this arrangement, including but not limited to: / Any information that ought reasonably to be considered to be confidential (whether or not it is so marked) relating to: / the business, affairs, customers, clients, suppliers or plans of the disclosing party; and / the operations, processes, product information, know-how, designs, trade secrets or software of the disclosing party; and / Any information developed by the parties in the course of delivering the project / The FCDO’s Personal Data; / Any information derived from any of the above. / Confidential information shall not include information which: / Was public knowledge at the time of disclosure (otherwise than by breach of the confidentiality section of these conditions); / Was in the possession of the receiving party, without restriction as to its disclosure, before receiving it from the disclosing party; / Is received from a third party (who lawfully acquired it) without restriction as to its disclosure; or / Is independently developed without access to the confidential information.
DELIVERY CHAIN	The chain of all partners involved in the delivery of the outputs and outcomes of the Project from the Partner, through Downstream Partners, to the Beneficiaries.
DELIVERY CHAIN RISK MAP	A visual depiction of the Project’s delivery chain that should to the extent possible include: / The name of all downstream delivery partners and their functions. / Funding flows (e.g. amount, type) to each delivery partner. · / Risks involved in programme delivery, mitigating measures and associated controls.
DIGITAL SPEND	Any external-facing service provided through the internet to citizens, businesses, civil society or non-government organisations, including any spend on web-based or mobile information services, websites, knowledge or open data portals, transactional services such as cash transfers, web applications and mobile phone apps.
DOWNSTREAM PARTNER / IMPLEMENTING PARTNER	Any person, organisation or entity within the Partner’s delivery chain that receives an allocation of the Grant either directly or indirectly to deliver the outputs and outcomes of the Project.
DUPLICATE FUNDING	Using the Grant to pay for costs which have been or will be paid from another Third Party source.
ELIGIBLE EXPENDITURE	Any cost or item of expenditure which has been agreed as part of the Project Budget
FCDO	The Foreign Commonwealth and Development Office, including any third party representative or agent it duly authorises to act on its behalf
FINANCIAL YEAR	The standard UK Government Financial Year, 1 April to 31 March
GRANT	The funding amount FCDO will pay to the Partner to deliver the Project
GRANT COMPLETION REPORT	A final report submitted at the end of the grant that describes performance against the output and outcome indicators in the Results Framework and the utilisation of the Grant to deliver, covering the full grant duration
INFORMATION AND DATA PROTECTION LEGISLATION	Any applicable law relating to the processing of Personal Data and privacy including the General Data Protection Regulation (GDPR); the Data Protection Act 2018; the Environmental Information Regulations 2004; the Freedom of Information Act 2000; relevant subordinate legislation, guidance and codes of practice issued by the Information Commissioner and relevant government departments.
INTELLECTUAL PROPERTY	All material produced by the Partner or its representatives in relation to the Project in the course of this Arrangement (including, but not limited to, reports, data and designs, whether or not electronically stored)
NON-PROJECT ATTRIBUTABLE COSTS (NPAC)	Costs incurred by an organisation in order to support the projects that it runs that are not feasibly allocable to a single project.
PARTICIPANTS	Both the FCDO and the Partner together
PARTNER	The direct Grant recipient named in the Accountable Grant Arrangement
PERSONAL DATA	has the meaning given to it in the Information and Data Protection Legislation as amended from time to time
PRE-PAYMENT	A payment made by FCDO in advance of the Partner incurring expenditure but where operational or commercial need for the payment has been justified and agreed
PROJECT	The set of activities, outputs and outcomes to which the Grant relates as named in the Accountable Grant Arrangement and described in the corresponding Proposal, Results Framework and Project Budget.
PROJECT ASSET	Equipment or supplies purchased in part of or fully by the Grant which have a useful life of more than one year from purchase. This applies to: / an individual asset with a purchase price or development cost in excess of £500 or equivalent in local currency; or / lower value items that are mobile and considered attractive (e.g. Mobile phones, cameras, laptops, tablets, satellite phones, vehicles, food, pharmaceutical products, relief packs, etc.) With a combined purchase price or development cost in excess of £500 or equivalent in local currency.
PROJECT BUDGET	The most recent Budget for the Project which has been agreed in writing with FCDO
PROJECT END DATE	The date on which the Grant ends either as noted in the Accountable Grant Arrangement or an earlier date as noted in formal termination communication in accordance with the Termination section of this Arrangement. This indicates the latest point at which the Partner may incur costs that can be paid from the Grant.
PROJECT NUMBER	The FCDO reference number for the Project to be delivered
PROJECT START DATE	The date on which the Grant begins. This cannot be earlier than the date the Arrangement comes into operation (i.e. is signed by both Participants) and indicates the earliest point at which the Partner may incur, or commit to incur, costs that can be paid from the Grant.
PROJECT TITLE	The FCDO name for the Project to be delivered
PROPOSAL	The document written and submitted by the Partner setting out the Project
RESULTS FRAMEWORK	The logframe or other results framework that contains the expected outputs, outcomes and impact along with measurable indicators and milestones to assess progress against a defined baseline.
THE/THIS ARRANGEMENT	The provisions within this document, its Annexes including the corresponding Proposal, Results Framework and Project Budget, and any subsequent amendments
THIRD PARTY	Any person, organisation or entity other than the Partner or FCDO
UK GOVERNMENT	The Government of the United Kingdom of Great Britain and Northern Ireland
UNSPENT FUNDS	Any part of the Grant paid to the Partner that remains unspent and uncommitted at the end of the Grant Period
VALUE FOR MONEY	Making the best possible use of our resources to maximise our impact. This means driving cost efficiency, throughout the life of the programme by budgeting and pricing realistically and appropriately to reflect delivery requirements and levels of risk over the life of the programme. It also entails managing uncertainty and change by regularly monitoring and updating programme plans and budgets, and building appropriate contingency levels therein, to protect value in the often-challenging environments that both parties work in.

### ANNEX 2: PARTNER PAYMENT REQUEST FORM

*If the bank details are not completed in full this will delay payment. *
To:
When submitting this payment request the Partner must include the following supporting documentation: / Detailed project financial reports that set out in both cash and resource terms actual expenditure to date against the approved project budget and quarterly forecast expenditure for FCDOs financial year (1 April-31 March). / Reports must be in Sterling (GBP). Foreign currency reports should be converted using the relevant exchange rate in OANDA (www.oanda.com). / In multi-donor arrangements, reports should clearly segregate the FCDO proportion of funding. / For payments in advance, a copy of the Partner’s justification and FCDOs agreement.

Project Details and Summary of Funding Period
Partner organisation name
Title of Grant / Project name
Project Location
FCDO Project Code / Purchase Order No.
Date of Claim
Period of detailed Statement of Expenditure / (Date finance report covers actual expenditure)	{dd/mm/yyyy}	to	{dd/mm/yyyy}
Period of detailed Forecast of Expenditure / (Date detailed forecast covers)	{dd/mm/yyyy}	to	{dd/mm/yyyy}

Partner Bank Details
Bank Name:
Bank Postal Address:
Bank Account Country:
Name of Account:
Bank Account Number:
Sort Code:
Currency of Bank Account:
IBAN number: / [required for bank accounts within Europe]
SWIFT number:
ABA or BIC Number: / [BIC required for bank accounts within Europe]
Intermediary bank details:
Bank Email Address:

Payment Request Details
For Payments in Arrears
Unspent balance of FCDO funds for the finance period ending {dd/mm/yyyy}
Partner Expenditure for the finance period ending {dd/mm/yyyy}
Payment being requested for previous finance period (actuals) / ((b)-(a))
OR
For Payments in Advance
Unspent balance of FCDO funds for the finance period ending {dd/mm/yyyy}
Forecast of Expenditure for next finance period ending {dd/mm/yyyy}
Payment requested for next finance period / ((d)-(c))

Expenditure Forecasts
Partner Forecast Expenditure to 31 December {20XX}
Partner Forecast Expenditure to 31 March {20XX}

Certification
I certify that this claim is correct and that the sum requested is properly due on the basis of the information provided, project outputs and outcomes and on the work carried out or future work plans. I confirm that receipt of this payment will not result in double funding of the work carried out or future activities. I have the authority to sign this on behalf of Trócaire.

Signature:
Date:
Name:
Job title:
Address & Contact Details:

### ANNEX 3: INVENTORY

Project Name: Twiyubakire – FCDO Civil Society Grant Manager
FCDO Project Number: 400197	FCDO Component Code: 404

FCDO considers any equipment and/or supplies purchased in part of fully from FCDO funds as project assets if they have a useful life of more than one year; and either (1) the purchase price or development cost of the asset is in excess of £500 or equivalent in local currency; or (2) is a group of lower value items (e.g. pharmaceutical products, food, relief packs, etc.) where the combined value is in excess of £500 or equivalent in local currency; or (3) can be considered an attractive item regardless of cost (e.g. mobile phones, cameras, laptops, tablets, satellite phones, vehicles, etc.).

Item no.	Serial no.	Date of purchase / (dd/mm/yy)	Description / (Make and Model)	Purchase value / (£)	Location	Responsible person	Anticipated years of life	Disposal date (dd/mm/yy)	Reason for disposal (if applicable)

On behalf of Trócaire, I certify that this inventory is up to date and correct following a physical check on all project assets. The physical check commenced on {XX Month 20XX} and was completed on {XX Month 20XX}. I have the authority to sign this on behalf of Trócaire.
Signature:
Name:
Job Title:
Date:

### ANNEX 4: UK INTERNATIONAL DEVELOPMENT AND AID VISIBILITY STATEMENT

As part of this Arrangement with FCDO, the Partner is required to acknowledge funding from the UK government on ODA funded programmes, in written materials and verbal statements and through use of the UK International Development (UK Dev) or UK Aid logo on programme assets. Please refer to the UK Dev branding guidance for further information on how to acknowledge ODA funding from the UK government. Please note that from 27 April 2023, the UK Aid logo will be used mainly for humanitarian and rapid onset disaster responses. If the Partner is not clear on which logo to use, they should check with the FCDO programme manager.

The Partner may be asked to provide, as part of the agreed reporting requirements, evidence of the branding in use, including photographs of the logo in the field and examples of communications materials. Branding Guidance and details of how to access the UK Dev or UK Aid logo files can be found here: Official Development Assistance (ODA) funded programmes: branding guidance - GOV.UK (www.gov.uk).

By completing and signing this statement the Partner agrees to fulfil these requirements.

Partner Name	Trócaire
Project Title and brief description of what it will deliver:	Twiyubakire - FCDO Civil Society Grant Manager
Please list the assets that will be delivered by the programme that will carry the UK International Development or UK Aid logo or acknowledgement of UK International Development funding
List all assets including physical items and supplies, and other non-physical items that will be delivered as part of the programme e.g. annual reports, research reports, press releases, websites, other communication or event materials (refer to Sections 5 & 6 of the branding guidance for more information on where UK International Development branding should / should not appear)
Please list the assets that will be delivered by the programme that will not carry the UK International Development or UK aid logo and/or acknowledgement of funding and explain clearly why these items will not carry UK International Development or UK Aid branding
All exceptions require approval by the Head of Department of the team in whose portfolio the programme sits and a record of this approval, e.g. an email, should be kept along with the programme documentation (refer to Section 6 of the UK Dev branding guidance for more information on branding exceptions)

Declaration
I understand that no UK International Development funds may be used to procure any promotional communications goods or activities that do not have a direct impact on the successful delivery of this programme or serve to increase the transparency of funding.

By signing this statement, the Partner agrees to fulfil the commitments stated above.

TROCAIRE Representative: / Name: Conor Molloy / Job title: Head of Portfolio – Climate & Gender / Signature: / Date:	Agreed by FCDO programme manager: / Name: / Job title: / Signature: / Date:

### ANNEX 5 – JOINT DONOR LANGUAGE ON SEAH

1. The Participants have a zero tolerance for inaction approach to tackling sexual exploitation, abuse and harassment (“SEAH”).[1] This means the Partner, and its implementing partners, will take all reasonable and adequate steps to prevent SEAH of any person linked to the delivery of this Arrangement by both its employees and any implementing partner and respond appropriately when reports of SEAH arise. The Partner must apply the IASC Six Core Principles Relating to Sexual Exploitation and Abuse and the following principles and practices when implementing this programme and provide evidence to demonstrate this where required: / Adherence to the IASC-Minimum Operation Standards and/or SEA elements of the Core Humanitarian Standard on Quality and Accountability; / A survivor-centred approach[2] to SEAH issues; / Strong leadership and signalling on tackling SEAH; / Make all reasonable and adequate efforts to address gender inequality and other power imbalances; / Robust reporting to enhance accountability and transparency; / Ensure that SEAH standards from this arrangement are reflected in funding templates with implementing partners, [for UN entities: by means such as, but not limited to, adherence to the United Nations Protocol on Allegations of Sexual Exploitation and Abuse Involving Implementing Partners.]
2. The Partner will adhere to the following reporting requirements: / The Partner will promptly contact through written notice to reportingconcerns@fcdo.gov.uk to report any allegation credible enough to warrant an investigation of SEAH related to this Arrangement. / The Partner should also promptly report to reportingconcerns@fcdo.gov.uk any allegation credible enough to warrant an investigation of SEAH that are not directly related to this Arrangement but would be of significant impact to the partnership. / [For UN entities] The Partner will report all allegation credible enough to warrant an investigation of sexual exploitation and abuse and, where relevant, the action taken, with regard to its governance and operations, regardless of the relation to this Arrangement, to the Secretary-General’s public reporting mechanism on SEA.
3. The report, as referred to in paragraph 2.a and 2.b, will indicate: [agreement/arrangement number], nature of the alleged misconduct, date of alleged misconduct, date of first report to Partner, location [as/if specified by [donor]], involvement of implementing partner, state of affairs concerning the investigation and the action that will be taken by the Partner, and whether the case is referred to law enforcement. The organisation will provide updates on the status of the case. The notice will be given in writing and delivered to the point of contact mentioned in paragraph 2.a and 2.b.
4. It is understood and accepted that the Partner’s arrangement to report on SEAH is subject to not compromising the safety, security, privacy and due process rights of any concerned persons.
5. When the Partner becomes aware of suspicions or complaints of SEAH, the Partner will take swift and appropriate action to stop harm occurring, investigate and report to relevant authorities (for criminal matters) when safe to do so and after considering the wishes of the survivor.
6. The donor or any of its duly authorised representatives may at all times carry out reviews, evaluations or other control measures to verify the Partner’s zero tolerance for SEAH. The Partner shall fully cooperate with the donor or any of its duly authorized representatives or agents to carry out such control measures.
[1] See UNGA Resolution A/RES/73/148 for the definition of sexual harassment and UNSG Bulletin ST/SGB/2003/13 for the definition of sexual exploitation and abuse. Both definitions are included in the DAC Recommendation on Ending Sexual Exploitation, Abuse, and Harassment in Development Co-operation and Humanitarian Assistance: Key Pillars of Prevention and Response.
[2] A survivor-centred approach is one for which the survivor’s dignity, experiences, considerations, needs, and resiliencies are placed at the centre of the process, from the initial program design to investigating and responding to potential incidents. Consistent with the UN Protocol on Allegations of SEA Involving Implementing Partners, the survivor should be informed, participate in the decision-making process, and provide consent on the possible use and disclosure of their information. Those interacting with the survivor and/or handling information regarding the allegation must maintain confidentiality, ensure safety of the survivor, and apply survivor-centred principles which are safety, confidentiality, respect, and non-discrimination. When the survivor is a child, the approach must consider the best interests of the child and engage with the family/caregivers as appropriate. Staff and partners should comply with host country and local child welfare and protection legislation and international standards, whichever gives greater protection.

### ANNEX 6: NOTIFICATION OF RETURN OF FUNDS TO FCDO

To:

Project Details
Partner Name
FCDO Project Name
Purchase Order / Project Code
Payment Date
Payment Amount to FCDO

Payment Method
For UK Payments under £10,000 we recommend the use of BACS. For UK Payments in excess of £10,000 we recommend the use of CHAPS. Cheques should be made payable to ‘Foreign, Commonwealth & Development Office’ and sent to the FCDO Programme Manager.
Bank Details
For payments in GBP pounds sterling (£):
Account Name:	FCDO Multi Vote
FCDO Bank:	National Westminster Bank
Bank Address:	Government Banking, CST, PO Box 2027, Parkland, De Havilland Way, Horwich, Bolton, BL6 4YU
FCDO Sort code:	60-70-80
FCDO Account number:	10012362
IBAN:	GB56NWBK60708010012362
SWIFT/BIC:	NWBKGB2L

For payments in Euros (€):
Account Name:	FCDO – Milton Keynes
FCDO Bank:	Standard Chartered Bank
Bank Address:	1 Aldermanbury Square, London, EC2V 7SB
FCDO Sort code:	60-91-04
FCDO Account number:	01725957396
IBAN:	GB85SCBL60910417259573
SWIFT/BIC:	SCBLGB2L

For payments in US dollars ($):
Account Name:	FCDO – Milton Keynes USD A/C
FCDO Bank:	Standard Chartered Bank
Bank Address:	1 Aldermanbury Square, London, EC2V 7SB
FCDO Sort code:	60-91-04
FCDO Account number:	01271410850
IBAN:	GB39SCBL60910412714108
SWIFT/BIC:	SCBLGB2L

Partner Contact Details
Name:
Position:
Address:
E-mail:

### ANNEX 7: NOTIFICATION OF PAYMENT BY FCDO

To:	Trócaire, Rwanda Country Office
CC:	FCDO Rwanda Country Office

Partner Name
FCDO Project Name
Purchase order / Project Code
Payment Date
Payment Amount

Payment has been made to the bank account as provided on the Payment Request Form, confirmed below:

Bank Name:
Bank Postal Address:
Name of Account:
Bank Account Number:
Sort Code:
Currency of Bank Account:
IBAN number: / {required for bank accounts within Europe}
SWIFT number:
ABA or BIC Number: / {BIC required for bank accounts within Europe}
Intermediary bank details

FCDO Contact Details
Name:
Position:
Address:
E-mail:

### ANNEX 8: Proposal
Summary

Organisation Primary Contact
Title of the Project
Submitted By
Need to Be Addressed:
Rwanda has made significant progress in governance and socio-economic development since 1994, but challenges persist in translating related policies into practice at the local level. Implementation inconsistencies in governance systems, centralisation of service delivery functions, and capacity limitations within local government undermine effective citizen engagement and accountability. Mechanisms for citizen participation, while institutionalised, often lack inclusivity, with marginalised groups such as youth and persons with disabilities frequently excluded. Civil Society Organisations (CSOs) play a critical role in advancing governance and accountability but face challenges in evidence-based advocacy due to resource constraints, technical capacity limitations, and dependency on external funding. Across key sectors—governance systems strengthening, agriculture, education and economic growth—there are opportunities for CSOs to influence local planning, budgeting, and policy implementation while fostering transparency, inclusion, and citizen-led dialogue. Further, critical areas such as civic space, social cohesion, and media development present unique opportunities for CSOs to engage in citizen-led advocacy, advancing rights, promoting legal reforms, and ensuring a vibrant and inclusive civil society landscape. Addressing these challenges is essential to ensure efficient, effective, and accountable policy responses and service delivery at local level.
Impact, Outcome, and Top-Line Results Expected:
Adjusted Impact: Improved responsiveness and accountability in local service delivery through strengthened civil society-led engagement and learning. The impact shifts from broad systemic change to a more immediate, observable improvement in responsiveness and accountability, aligned with what can reasonably be achieved in a pilot phase with limited funding. Adapted Outcome: CSOs and citizens better equipped and positioned to participate in local governance, influence accountability mechanisms, and generate actionable learning for future scale-up. The revised outcome focuses on foundational capacity strengthening and positioning, a more realistic expectation for a pilot-focused, short-duration programme. Adjusted Outputs: (1) CSOs engage in rapid evidence generation, and policy analysis to pilot innovative advocacy approaches within defined themes and geographies. (2) Selected 2-3 medium size CSOs demonstrate agile, adaptive institutional practices to engage effectively in local governance and citizen-led processes, deliver pilot activities and contribute to iterative learning. and (3) Pilot-tested CSO and citizen engagement models influence short-term local planning and accountability processes, producing actionable learning for scale. Together, these outputs will enable CSOs to pilot evidence-based advocacy approaches and foster participatory governance practices, generating actionable learning that can inform future efforts to strengthen local accountability and service delivery.
Project Start/End Date:	15th July 2025 to 31st March 2027 with a possibility for extension.
Total Funding Requested from FCDO:	Year 1 (July 2025-March 2026): £1,200,000 / Year 2 (April 2026-March 2027): £1,000,000

Strategic and Technical Approach

2.1. Problem Analysis and Context: Rwanda has achieved notable governance and economic advancements since 1994, including increased tax revenue, reduced corruption, and enhanced public financial management. These reforms, supported by strong institutional frameworks, have fuelled the country's aspiration to achieve middle-income status under its Vision 2050. Decentralisation and citizen participation are central pillars of this vision, aimed at bringing services closer to citizens and fostering inclusive development. However, systemic challenges continue to impede progress, particularly at the local governance level.
Despite Rwanda's commitment to decentralisation, implementation inconsistencies hinder its full potential. Many service delivery functions, such as education personnel hiring, remain centralised, limiting districts’ ability to address local needs effectively. This mismatch between policy and practice underscores an entrenched centralisation bias that slows the decentralisation agenda. Local governance systems face capacity constraints, including limited resources and skills, particularly in technical areas like procurement and planning, undermining service delivery and participatory development.
Citizen participation mechanisms, such as Umuganda (monthly community participation) and Inteko z’abaturage (Assemblies of the Citizen) meetings, have been institutionalised but often lack genuine inclusivity and effectiveness. The pressures of national planning priorities, combined with limited district budgets, lead to rushed engagement processes. Marginalised groups, including youth, persons with disabilities, and older persons, are disproportionately excluded due to structural and practical barriers, such as inconvenient meeting times and limited accessibility.
Civil society organisations (CSOs) play a vital role in service delivery but face significant challenges in their advocacy function. Many CSOs lack the technical capacity, resources, and evidence-based advocacy skills required to influence policy effectively. Moreover, the existing civic engagement infrastructure is primarily state-led, leaving few independent, citizen-driven platforms for oversight and dialogue. In 2023, only 24.5% of citizens reported involvement in CSO interventions over the past three years, highlighting the limited reach and engagement of CSOs in fostering meaningful participation in governance and development processes​.[3]
[3] See Rwanda Governance Board. Rwanda Civil Society Barometer 2023.
The Government of Rwanda (GoR) cites civil society as a key partner in promoting accountability, strengthening citizen engagement, ensuring that development goals align with community needs, and delivering more inclusive and sustainable outcomes.[4] A recent assessment highlighted that while 93.3% of surveyed CSOs believe the regulatory framework supports partnerships with the government, gaps remain between policy and practice. Many CSOs emphasise the need for collaborative frameworks to enhance efficiency and ensure meaningful participation across all stages of policymaking and implementation.[5]
[4] See Republic of Rwanda. National Strategy for Transformation (NST2): 2024-2029.
[5] See Rwanda Civil Society Platform. Assessment on the Level of Partnership Between Civil Society and Government in the Implementation of Rwanda’s Development Agenda. 2021.
Notably, CSOs play a significant role in fostering citizen engagement and accountability. Their interventions include capacity strengthening, policy advocacy for marginalised groups, and raising awareness of laws and policies. However, their reliance on external donor funding—accounting for 92.6% of CSO financing—raises sustainability concerns. This dependency underscores the importance of diversifying funding sources, including through increased government partnership, income generating activities, and support through national budget allocations.[6] The private sector can also play a role in potentially funding civil society through environmental, social, and governance (ESG) practices.
[6] Ibid.
While CSOs contribute to advocacy and policy research, citizen perceptions indicate room for improvement in facilitating public participation and addressing citizens’ concerns effectively. This gap further underscores the need for targeted capacity strengthening to enhance the role of CSOs in these critical areas​.[7]
[7] See Rwanda Governance Board. Rwanda Civil Society Barometer 2023.
The Rwanda-UK Development Partnership represents a strategic alignment between UK and Rwandan priorities, leveraging long-term, accountable partnerships to address governance and capacity challenges. The partnership’s flagship Twiyubakire programme exemplifies this collaboration, targeting decentralised governance and capacity strengthening for CSOs. Building on the successes of prior UK-funded programmes in public financial management (PFM) and accountability, Twiyubakire takes a multi-sector approach to strengthen governance systems, including planning, monitoring and evaluation, and PFM at the district level. In turn, this contributes to the GoR’s Vision 2050 goals while also reinforcing the UK’s commitment to fostering open societies and human rights.
Through Twiyubakire, the UK aims to empower CSOs to engage in evidence-based advocacy, focusing particularly on marginalised groups. This bottom-up accountability complements Rwanda’s existing governance structures by enabling citizen-driven oversight and promoting dialogue on local needs. By fostering an inclusive civic space, Twiyubakire helps bridge the gap between policy commitments and practical implementation, ensuring more equitable and responsive governance.
By addressing these interconnected challenges, interventions can strengthen decentralised governance, enhance citizen participation, and equip CSOs to drive meaningful change. By empowering CSOs through capacity strengthening, supporting their organisational development journeys and sustainability, and enhancing their evidence generation and advocacy capabilities, the programme not only advances Rwanda’s development trajectory but also aligns with UK priorities in governance, economic growth, climate action, and gender equity.

2.2. Proposed Approach: As illustrated in the annexed Theory of Change, the programme will use a hybrid implementation model structured around three thematic windows:
Windows 1 & 2: Sectoral Governance (Medium CSOs)
- Select 2–3 medium-sized CSOs through a closed competition.
- Focus on agriculture and/or education and governance in economic spaces
- Strengthen evidence-based advocacy, institutional agility, and citizen engagement.
Window 3: Citizen-Led Issues (Small CSOs)
- Provide small grants (£20–50k) to 2–4 CSOs working on issues like social cohesion, civil rights, UPR monitoring, or media development.
- Prioritise capacity strengthening, coaching, and flexible tools for adaptation.
Cross-Cutting:
- Integrate Trócaire’s Citizen Monitoring and Advocacy (CMA) approach as an adaptive learning and engagement model.
- Focus on rapid testing of tools, agile learning cycles, and short feedback loops.
- Emphasize inclusion, particularly of women and marginalised voices.
To achieve the intended outcome and impact, the programme will deliver against three key outputs, with a structured set of activities under each:

Output 1: CSOs engage in rapid evidence generation, and policy analysis to pilot innovative advocacy approaches within defined themes and geographies. This output will be delivered primarily through selected CSOs under Windows 1 & 2, engaging in policy influencing and accountability in sectors such as agriculture, education, and economic governance.
Key pilot activities:
Identify and support CSOs to engage with District-level Joint Action Development Forums (JADFs), sector working groups, and policy platforms.
Facilitate citizen-led research, scorecard exercises, and participatory planning spaces to ensure citizens are meaningfully contributing to decision-making at the local level.
Test localised CMA tools for feedback collection and advocacy, tailoring them to selected pilot districts and thematic areas.
Facilitate targeted learning cycles with selected CSOs and their networks, focused on rapid evidence generation aligned with pilot themes and geographies. Emphasis will be on time-bound, actionable evidence collection that supports agile advocacy.
Deliver thematic workshops to co-create or refine short-term advocacy strategies with 2–3 selected medium-sized CSOs (and potentially their networks). Workshops will incorporate innovative communication approaches such as data storytelling, digital media, SMS, and radio to reach diverse audiences and support quick turnaround cycles.
Support the development of rapid CSO-led evidence/knowledge outputs, such as policy briefs, issue snapshots, or short case studies. These will focus on priority local governance or socio-economic issues and be designed in accessible formats such as infographics or social media cards, aligned with the innovation hub’s thematic focus.
Coordinate dissemination and socialisation activities tailored to short pilot cycles. These will include virtual briefings, interactive dashboards, social media campaigns, and local stakeholder dialogues to ensure timely uptake of learning by communities, duty bearers, and peers.
Provide adaptive technical support and peer mentorship throughout the pilot phase. This will help enhance CSOs’ responsiveness, quality of outputs, and ability to iterate based on feedback and learning. Mentorship will also support documentation of what works across themes and geographies.

Output 2: Selected 2-3 medium size CSOs demonstrate agile, adaptive institutional practices to engage effectively in local governance and citizen-led processes, deliver pilot activities and contribute to iterative learning.  With this adjusted output, the programme will maintain its aim of strengthening selected CSOs’ internal governance and operational capacities, fostering transparency, accountability, and sustainable engagement in local governance processes. The focus will be on in-depth institutional capacity building tailored to each CSO’s needs, with the ultimate goal of leaving them in a stronger position to secure future funding and adapt effectively in shifting civic environments.
The pilot phase will prioritise targeted coaching on adaptive management, innovation design, and learning integration. The programme will also introduce light-touch governance tools such as simplified SOPs, digital reporting systems, and rapid grant compliance practices to reduce bureaucratic burden and foster a culture of experimentation. Trócaire’s Citizen Monitoring and Advocacy (CMA) approach will be tested across varied micro-contexts to capture insights on what works where.
Key pilot activities:
Facilitate learning for CSOs on Trócaire’s CMA approach, positioning it as an adaptive, context-responsive model for engagement. Emphasis will be placed on using CMA to test and reflect on civic engagement practices across different pilot contexts.
Deliver institutional capacity strengthening support to CSOs in areas such as governance, leadership, financial management, and resource mobilisation. This foundational support will enhance organisational agility and improve prospects for sustainability. Light-touch SOPs, digital resource tracking tools, and simplified reporting templates will be encouraged.
Facilitate partner-led institutional capacity assessments and progress reviews. These exercises will support adaptive learning and encourage CSOs to reflect and adjust regularly. Assessments may follow a 3-month review cycle during the pilot phase.
Support CSOs to develop and update their institutional capacity strengthening action plans. These plans will be designed as living documents, evolving alongside pilot activities and learning outcomes.
Provide ongoing technical support and mentorship tailored to each CSO’s capacity needs. Mentorship will include coaching on adaptive management, innovation design, rolling reviews, and learning documentation.
Deliver trainings on compliance, safeguarding (including PSEA), data protection, and related standards. Trainings will be modular, scenario-based, or digital to reduce burden and increase accessibility, especially for smaller CSOs.
Manage a flexible capacity strengthening fund to address emerging organisational needs, access technical expertise, or facilitate peer exchange. This fund will be linked directly to pilot implementation, enabling mid-cycle adaptation or innovation where necessary.
Output 3: Pilot-tested CSO and citizen-led engagement models promote inclusive local governance by advancing social cohesion, civic participation, and media freedoms, while generating actionable learning for broader adoption With this adjusted output, the programme will support 2–4 2–4 small or emerging CSOs to design and run small-scale, participatory pilot engagements aligned to the decentralisation agenda in one to two specific sectors (e.g., agriculture, education) and selected governance issues in the private sector/growth space (e.g., tax policy, compliance). These engagements will use mechanisms such as thematic forums, mini CSO-private sector consultations, and multi-stakeholder roundtables.
To enhance responsiveness and inclusion, we will incorporate feedback tools to ensure community voices shape local planning and service accountability. All pilots will be guided by short learning and feedback cycles (3 months), enabling iterative adaptation and deeper analysis of what works in facilitating citizen–government engagement.
Key pilot activities:
Facilitate capacity-strengthening for selected CSOs/ grassroots actors on local planning, budgeting, decentralised policy processes, rights-based advocacy, and citizen engagement. This includes CMA training tailored to the needs of 2–4 small or emerging CSOs leading pilot implementation.
Design and support participatory processes for aggregating citizen voice, including inclusive public consultations, thematic dialogues (e.g., on civic space or social cohesion), and citizen perception surveys. These processes will test context-relevant models for local governance influence.
Establish and adapt inclusive citizen feedback mechanisms such as community scorecards, citizen report cards, and digital tools. These will enable real-time, disaggregated feedback from diverse community members and support adaptive local decision-making.
Support the co-creation of community-informed policy briefs and submissions by selected CSOs, reflecting citizen-generated evidence, pilot outcomes, and rights-based concerns (e.g., UPR recommendations, civic freedoms, media rights). Outputs will emerge from iterative 3-month learning cycles.
Facilitate direct and inclusive citizen engagement spaces, such as town hall meetings, participatory budgeting forums, and multi-stakeholder roundtables. These platforms will test facilitation models that promote equitable participation of youth, women, persons with disabilities, and other underrepresented groups.
Enable CSOs to provide regular and transparent feedback to communities, closing the loop between community input, policy engagement, and action. This activity will reinforce local accountability and strengthen trust in participatory governance processes.
Support engagement between CSOs and local governance structures, including JADFs, sector coordination platforms, or community development committees. This will foster institutional anchoring and enhance the sustainability of tested citizen engagement models.
Strengthen the capacity of local authorities and key stakeholders on inclusive governance, constructive CSO collaboration, and the value of citizen participation, particularly from marginalised and vulnerable groups. This will create enabling conditions for effective CSO–government partnership.
Provide continuous technical support and mentorship to selected CSOs, focusing on quality delivery of pilot activities, inclusive facilitation, use of citizen-generated data, and documentation of learning to inform scale-up and replication.
The proposed approach strategically links inputs, outputs, and outcomes to the overarching programme impact. Strengthened CSOs will serve as effective intermediaries between communities and local governments, ensuring governance processes reflect community priorities; produce and disseminate driving evidence-based policy advocacy and fostering more efficient local decision-making; and enhance transparency, accountability, and participatory governance through sustained community engagement and feedback mechanisms.
By addressing governance and accountability gaps, Trócaire’s approach will directly contribute to the Twiyubakire programme’s vision and long-term impact of more accountable, inclusive, and citizen-responsive governance in Rwanda.
CSO Selection and Roles
The Twiyubakire Programme will adopt a strategic, phased approach to CSO selection that aligns with the programme’s dual objectives of piloting scalable governance models and supporting citizen-led advocacy on emerging issues. CSOs will be selected under two distinct windows with tailored processes and criteria, in line with the final Terms of Reference and FCDO’s guidance.
Windows 1 and 2: Medium-to-large CSOs for Sectoral Governance and Private Sector Engagement
The programme will work with 2–3 medium-sized to large CSOs, selected through a closed and competitive process, to implement pilot models on decentralisation in 1–2 priority sectors (with a focus on agriculture and a light-touch groundwork on education) and governance issues in the private sector/growth space (e.g., taxation, compliance).
CSO Selection Process
The selection will be overseen by a CSO Selection Committee, comprised of:
- Trócaire Country Director (or designate) – Chair
- Localisation and Partnerships Manager
- Programme Manager
- Twiyubakire Team Leader
All committee members will declare and manage conflicts of interest.
The process includes:
Mapping and Direct Invitation: Trócaire will map potential CSOs, focusing on those with thematic expertise in agriculture, education, and private sector governance. A shortlist of eligible CSOs will be invited to apply through a targeted call.
Application Submission: Invited CSOs will submit applications that include programme concept, budget, logical framework, and institutional capacity profiles.
Evaluation and Due Diligence: Proposals will be scored against a rigorous scorecard. Criteria will include:
  1. Budget range (typically between 200–600 million RWF)
  1. Experience in governance, decentralisation, or private sector advocacy
  1. Operational capacity and staff expertise
  1. Capacity to produce evidence-based advocacy
  1. Focus on inclusion of women, youth, and marginalised groups
Final Selection and Contracting: Top-scoring CSOs will undergo due diligence based on Trócaire’s Minimum Requirements Tool. Final recommendations will be submitted to the FCDO Twiyubakire Programme team for validation.
Roles and Responsibilities
Selected CSOs will:
- Pilot engagement models under defined sectoral or private sector themes
- Lead citizen engagement activities and short-term advocacy campaigns
- Generate rapid evidence and policy outputs
- Implement inclusive feedback loops
- Participate in adaptive learning cycles and institutional strengthening
- Engage in quarterly reviews and contribute to program-wide reflection

Window 3: Small CSOs for Emerging Citizen-led Issues
Window 3 supports 2–4 small or emerging CSOs with targeted sub-grants (up to £50,000) to respond to sensitive, citizen-led issues such as but not limited to:

The focus of this window will include, but is not limited to, the following emerging governance themes:
- Social cohesion and inclusion: initiatives that strengthen community harmony, conflict resolution, peaceful coexistence, and local-level trust-building.
- Civic space/civil and political rights: community-led monitoring of Rwanda’s progress in implementing recommendations from the Universal Periodic Review (UPR); supporting citizens and civil society to engage with the National Commission for Human Rights.
- Media development: supporting safe, responsible citizen journalism, independent media voices, or community engagement on media rights and freedoms.
Selected projects under this Window shall emphasize participatory approaches that elevate citizen voice, particularly those of marginalized or underrepresented groups, including youth, women, people with disabilities, and vulnerable communities.

Selection Process for Window 3
The selection of CSOs for Window 3 will follow a tailored and flexible approach that responds to emerging citizen-led issues above. Unlike Windows 1 and 2, CSOs under this window will not receive institutional capacity strengthening support but will instead benefit from smaller, targeted sub-grants.
A separate Steering Committee will be established to oversee the selection of the small 2-4 CSOs, ensuring alignment with the unique objectives of this window. This committee will be chaired by the Senior Responsible Officer (SRO) for Twiyubakire and will include members from the FCDO Programme Team, Trócaire’s Twiyubakire Team Lead, and other relevant team members of Trocaire Rwanda. All committee members will declare and manage conflicts of interest.
The Steering Committee will oversee the process. Trócaire will coordinate logistics and facilitate the mapping process. The approach includes:
Ongoing Mapping and Direct Outreach: Based on stakeholder consultations, Trócaire will identify potential CSOs with grassroots advocacy capacity.
Simplified Application Process: Targeted CSOs will submit a short proposal, budget, and logical framework focused on their advocacy priorities.
Evaluation and Decision-Making: The Steering Committee will assess proposals using a tailored scorecard. Due diligence will be flexible to accommodate smaller, less formalised organisations.
Rolling Selection Cycles: Window 3 will remain open to additional applications at least twice yearly to adapt to emerging needs and civic space dynamics.
Roles and Responsibilities
Selected CSOs under Window 3 will:
- Address timely and politically relevant issues with community resonance
- Generate rapid evidence and policy outputs
- Engage in rapid-response advocacy and media campaigns
- Receive technical support and capacity-building, particularly in advocacy and digital communications

Cross-Cutting Principles
- Impartiality & Transparency: All processes will uphold rigorous documentation, fairness, and transparency.
- Learning and Adaptation: Each CSO will participate in the programme’s real-time learning cycles, contributing evidence and reflection for scaling.

2.3. Advocacy Issue Identification:
Trócaire proposes a strategic and participatory approach to identifying advocacy issues across the three windows of the Twiyubakire programme. This approach is grounded in community voice, government priorities, and programmatic alignment. It combines citizen-led identification, policy relevance, and collaborative vetting to ensure that supported advocacy efforts are credible, impactful, and responsive to Rwanda’s evolving governance context.
Windows 1 and 2: Collaborative Prioritisation for Sectoral Governance & Economic Growth
For Windows 1 and 2, Trócaire will convene a national participatory prioritisation workshop early in the programme. This event will bring together: Representatives from CSO networks, Grassroots and community representatives (e.g., through Umuganda and Inteko z’Abaturage), local government actors, national stakeholders, including MINALOC, MINECOFIN, RGB, and sector working groups. The workshop will serve to:
Validate Twiyubakire’s problem analysis and refine focus areas using government frameworks such as the Governance and Decentralisation Sector Strategy (2024–2029), the PFM Strategy, and the Economic Recovery Strategy.
Identify feasible and timely governance priorities, such as:
  1. Effectiveness of participatory budgeting and planning processes
  1. Implementation of fiscal decentralisation policy
  1. Transparency in Imihigo performance reporting
Highlight thematic advocacy opportunities in agriculture, education and private sector growth, based on national strategies.
Trócaire will then work with the 2–3 selected CSOs to co-develop short-cycle advocacy strategies rooted in these themes. Each strategy will include:
- Tangible advocacy goals with defined outputs/outcomes
- Clear communication and media outreach plans
- Alignment with national systems (e.g., Imihigo, JADF, public consultations)
- Embedded learning and adaptation mechanisms
Technical support and mentorship will be provided throughout to ensure strategic clarity, government engagement, and real-time responsiveness.
Window 3: Citizen-Led Advocacy in Emerging Spaces
For Window 3, Trócaire will apply a targeted and agile approach to identifying advocacy priorities in social cohesion, civic and governance spaces. Selection will focus on issues , including but not limited to:
- I
- Social cohesion and inclusion: community harmony, conflict resolution, peaceful coexistence, and local-level trust-building, etc.
- Civic space/civil and political rights: community-led monitoring of Rwanda’s progress in implementing the UPR recommendations; citizens and civil society engagement with the National Commission for Human Rights.
- Media development: safe, responsible citizen journalism, independent media voices, or community engagement on media rights and freedoms.
In parallel, Trócaire will maintain ongoing dialogue with CSO to:
- Surface new and emerging civic space challenges
- Identify advocacy gaps
- Ensure balanced geographic and thematic coverage
Trócaire will work closely with selected CSOs, FCDO, and the Window 3 Steering Committee to finalise issue selection. Where necessary, and in consultation with FCDO, Trócaire will facilitate dedicated reflection spaces for CSOs to explore risks, political sensitivities, and mitigation strategies. This ensures flexibility while safeguarding programme integrity and government relationships.
2.4. Flexibility and Adaptability: Given the significantly reduced funding and condensed timeframe, the programme will adopt a streamlined yet flexible and adaptive approach to ensure interventions remain responsive to emerging priorities and contextual shifts. During the inception and early implementation phases, interventions under Windows 1 and 2 will be focused and prioritised based on consultations with CSOs, key stakeholders, and relevant government actors in the agriculture sector, with a soft touch on education sector. Rather than comprehensive strategies, selected CSOs will be supported to develop targeted, time-bound advocacy plans aligned with immediate opportunities and evidence gaps in the decentralisation agenda in the 2 sectors. These plans will be reviewed and adjusted at key implementation milestones, based on rapid learning and feedback loops, and in consultation with FCDO, GoR, and CSO networks.
For Window 3, flexibility will be maintained through a light-touch adaptive approach, enabling timely support to critical and time-sensitive citizen-led advocacy needs, particularly in the areas of social cohesion, civic space/civil and political rights, including media development. Trócaire will continue to monitor trends, identify priority shifts, and provide agile support and strategic guidance to selected 2-4 partners, while ensuring alignment with FCDO priorities and value for money principles.
In the context of reduced funding and a shorter implementation period, Trócaire, in consultation with FCDO, will adopt a targeted and pragmatic approach to capacity strengthening under Windows 1 and 2, grounded in its Partner Capacity Assessment and Support (PCAS) Framework. Emphasis will remain on partner-led processes, with a focus on prioritising critical institutional capacity gaps that directly influence CSOs’ ability to engage in effective, time-bound advocacy and their ability to enhance the institutional systems and achieve the organisational resilience.
Where institutional capacity strengthening plans do not yet exist, selected CSOs will be supported to develop streamlined action plans focused on high-impact areas, ensuring continued ownership and alignment with their strategic priorities. Given budget constraints, the approach will prioritise cost-effective and scalable activities, such as peer-to-peer exchanges, joint learning forums, and remote technical support.
Rather than multiple funding streams, the programme will integrate a consolidated and strategically managed capacity strengthening fund, overseen by Trócaire in close collaboration with CSOs. This fund will be used to support high-priority, non-duplicative activities that align with immediate programme outputs and deliver measurable value. Decisions on fund allocation will be jointly made, ensuring relevance, equity, and accountability within the limited resource envelope.

2.5: Contingency Arrangements: Trócaire recognises the importance of preparing for potential changes in the political environment and has incorporated contingency arrangements to ensure programme continuity and relevance. Ongoing risk monitoring and scenario planning will be central, with the Trócaire Twiyubakire Team regularly assessing the political landscape, consulting with FCDO and the TAF component of the overall programme, and maintaining open communication with GoR, CSOs, and CSO networks. If significant shifts in the political environment occur, such as changes in government priorities or restrictive regulations, Trócaire will adapt its strategies and activities accordingly in close consultation with its partner CSOs. This may include revising advocacy priorities, adjusting implementation timelines, or redirecting resources.
The programme will adopt adaptive management practices, including regular reviews of advocacy strategies and ongoing dialogue with stakeholders. CSOs will be supported to pivot their efforts in alignment with new realities, while retaining a core focus on accountability and citizen engagement. Further, Trócaire’s PCAS Framework will ensure CSOs have the institutional resilience to navigate and respond effectively to political changes. In the event of heightened risks or restrictions, Trócaire will prioritise the safety of staff and partners, while ensuring compliance with legal and regulatory requirements to safeguard programme integrity.
Under Windows 1 and 2, Trócaire will enter into time-bound partnership agreements with selected CSOs for the duration of the self-contained inception/pilot phase of the programme. These agreements will include indicative budget allocations to support essential operational and programmatic needs, with flexibility to review and adjust allocations at key intervals based on performance, emerging priorities, and evolving context. There will be a decision point at the end of Dec 2025/Early Jan 2026, with nearly 3 months to either ensure maximum impact & closure or plan for the second year. In case of the later, there will be addendum downstream agreements.
Given the compressed timeline, partnership management will emphasise early clarity, strong coordination, and rapid mobilisation. In cases where a CSO is no longer able to contribute meaningfully to programme objectives—due to political shifts or internal challenges—Trócaire will implement a responsible exit strategy, including light-touch capacity support to safeguard past investments and mitigate disruption.
Due to the limited duration and funding, onboarding of new CSOs will be highly selective and based on clearly defined strategic needs, particularly in Window 3, where the programme may respond to urgent advocacy opportunities in social cohesion, civil and political rights, including media development.

2.6. Innovative Elements: The Twiyubakire programme integrates multiple innovative elements designed to enhance adaptability, sustainability, and long-term impact. It leverages Trócaire’s CMA approach to ensure effective, contextualised, and locally led advocacy with tangible measurements for success. The programme envisions providing ongoing support and mentorship, including through Trócaire's advocacy expertise as well as Rwanda-based mentors with governance expertise. The programme’s design incorporates adaptive programming as a core feature, enabling flexibility to respond to evolving priorities over the programme’s lifecycle. By embedding Monitoring, Evaluation, and Learning, the programme will continuously generate timely data and learning to inform decision-making. Ongoing stakeholder engagement with government, civil society, and communities ensures alignment with the most pressing issues and emerging opportunities, while also strengthening evidence-based advocacy.
The adaptive approach under Window 3 allows for the identification and support of 2-4 CSOs on a continuous basis, ensuring that new and emerging advocacy priorities, particularly in social cohesion, civic space/civil and political rights and media development, can be addressed promptly. Trócaire’s capacity strengthening approach leverages mechanisms that promote partners’ autonomy and ownership of their own capacity strengthening journeys, such as core funding, NPAC, and flexible capacity strengthening budget lines. Trócaire’s PCAS Framework prioritises a partner-led approach, recognising existing capacity strengthening plans where these exist (in close coordination with CSOs and other international partners), while also enabling CSOs to develop new plans if these do not yet exist or are outdated. This framework includes innovative strategies for long-term organisational sustainability, such as resource mobilisation support beyond traditional funding proposals, including exploring business branches to generate unrestricted income, as well as grant management training so CSOs can competently manage FCDO and other donor funds. The project also incorporates local-to-local capacity sharing through peer learning exchanges, mentorship opportunities with established civil society experts, and collaborations with universities. These linkages enhance evidence generation and advocacy while fostering resilience and sustainability.
The programme opens its scope to non-traditional CSOs or NSAs, such appropriate private sector actors or CSO trade groups with economic growth interests or expertise, thus fostering innovative advocacy for unlocking regulatory and economic barriers. Tailored approaches across thematic windows also ensure that strategies are differentiated, allowing prioritisation of specific governance and advocacy needs such as economic growth/taxation.
The Trócaire Twiyubakire Team’s institutional connections with Trócaire’s Rwanda-based Localisation and Partnership Unit and Kenya-based Global Hub on Partnership & Localisation create opportunities for strategic evidence collection, sector-wide learning, and knowledge sharing. These linkages also facilitate the design and implementation of effective community and CSO feedback mechanisms, leveraging existing best-practice mechanisms, such as Trócaire’s global partnership surveys.

2.7. Sequencing of Programme Implementation: The civil society output of the Twiyubakire programme will be implemented over a 21-months period (July 2025 to March 2027) with a close to 9-months self-contained inception phase. The first 3 months of this phasewill lay the groundwork for the programme, engaging closely with FCDO and the other programme components, particularly the TAF, to ensure coherence. Further, in the first 3 months of this period, Trócaire will finalise a detailed workplan that outlines timelines, staffing, and budget allocations. Critical design documents will be prepared, including governance and financial management arrangements, a log-frame with progress indicators, a value-for-money framework, and a monitoring and learning plan. The CSO selection process under Windows 1, 2 and 3 will be done in the first two months of this phase; partnership agreements for the self-contained inception phase will be signed with selected CSOs and/or NSAs and implementation will immediately start, spanning over the remaining months (approx. 6-7 months), with strong focus on delivering the programme’s outcomes and outputs. Risk assessment and management strategies will be developed, alongside a delivery chain risk map to identify and mitigate potential challenges. An exit strategy will be drafted to address potential closure or termination scenarios. This phase will conclude with the submission of an Inception Report to FCDO for approval, consolidating deliverables and confirming readiness to closure or transition to the second year. A decision point at the end of Dec 2025/early Jan 2026, with nearly 3 months to either ensure maximum impact and closure or plan for the second year.

2.8. Alignment with FCDO Requirements: Trócaire is committed to full compliance with FCDO requirements and has robust policies, systems, and practices in place. As an agency registered in both the UK and Ireland, Trócaire adheres to the EU and UK General Data Protection Regulation (GDPR) and the Data Protection Act 2018 across all its offices and programmes. All staff adhere to Trócaire’s Data Protection Policy and strict data protection measures, including management of personal data and ensuring secure data storage and transfer. Regular training is conducted for all staff to uphold GDPR principles in all programme activities.
Trócaire has a comprehensive Global Safeguarding Policy that aligns with FCDO’s zero-tolerance approach to tackling sexual exploitation, abuse, and harassment (SEAH). This policy applies to all staff, partners, consultants, and volunteers, and it serves to protect programme participants and communities as well as personnel. Safeguarding is embedded in Trócaire’s due diligence assessments of CSOs, ensuring downstream partners have and enforce robust safeguarding policies. Trócaire has clear reporting mechanisms for safeguarding concerns and fraud, including escalation to FCDO through designated channels as required.
Trócaire has a global Counter modern slavery, trafficking in persons and child labour statement and commits to adhering to the UK Government’s Modern Slavery Statement and the International Labour Organisation’s standards. Trócaire ensures that no practices in its operations or those of its partners contribute to modern slavery or child labour. All staff and partners are trained to identify and report concerns of exploitative practices.
Trócaire prioritises gender and disability inclusion across all programmes, aligning with the OECD’s Development Assistance Committee (DAC) gender equality markers and mainstreaming these considerations across programmes. People with disabilities and marginalised groups are systematically consulted and engaged to ensure their voices and needs are represented and addressed.
Trócaire aligns its programmes with the Paris Agreement and Rwanda’s climate adaptation commitments. Through strengthened governance systems and grants, Trócaire will aim to deliver International Climate Finance outcomes and integrate climate considerations into policy decisions. Synergies with FCDO’s broader climate programming will be explored during the mobilisation phase.
Trócaire is committed to the International Aid Transparency Initiative (IATI) standards. Trócaire ensures open data reporting, accurate financial documentation, and publishing in a reusable format.
Trócaire will continuously update its comprehensive delivery chain map, outlining the flow of FCDO funds and sharing this with FCDO as required. Trócaire operates under a zero-tolerance policy for fraud and corruption, in line with Trócaire’s Global Code of Conduct and its Fraud, Theft, Corruption, and Bribery Policy. Trócaire’s risk matrix (see annex) includes measures to monitor and mitigate these risks throughout the programme’s delivery chain. Trócaire ensures robust internal controls, conducts audits, and provide training to staff and partners. Trócaire will report suspected cases of fraud to FCDO. Trócaire will also develop and maintain a detailed Asset Management Plan and Asset Register during the Inception Phase. This will include plans for the use, maintenance, and disposal of assets, in compliance with FCDO requirements. As a Cyber Essentials Plus certified agency, Trócaire will comply with FCDO’s Digital Service Standard for any digital-related expenditure. Any plans for web-based or mobile services will be approved by FCDO in advance, ensuring alignment with their guidance on digital spend.
Trócaire will adhere to FCDO’s branding guidance, ensuring appropriate and consistent use of UK Aid branding by all downstream partners. Any exceptions will be documented and approved in writing by FCDO. External communications will reflect the programme’s UK-funded nature in line with FCDO’s visibility statement.

3. Track Record and Expertise
3.1. Organisational Experience: Trócaire brings over five decades of organisational expertise in partnership management, fund management, and institutional strengthening, with active partnerships with more than 200 local organisations worldwide. In Rwanda, Trócaire has operated for over 30 years, establishing itself as a leader in institutional strengthening, social accountability, advocacy, and grant management. Trócaire utilises proven methodologies and tools that enable the delivery of high-quality programmes, achieving tangible and sustainable impacts.
As a Core Humanitarian Standards (CHS) certified organisation, Trócaire meets all FCDO’s selection criteria. It is recognised for its excellence in organisational development, programme quality, and grant management. It has a robust track record of implementing complex and multi-stakeholder programmes, including managing sub-grants for local CSOs and delivering tailored capacity strengthening initiatives. Trócaire’s CMA approach exemplifies this commitment, equipping CSOs and citizens to claim and realise their rights through evidence-based advocacy and accountability mechanisms. Globally, Trócaire manages Ireland's Civil Society Partnership (ICSP), which supports 157 local organisations across 17 countries with an annual budget of £23M. Trócaire also serves as the grant manager for FCDO programmes in diverse contexts, including Somalia (£4.8M for health services), Zimbabwe (£2.2M for climate-sensitive food security and women’s empowerment and £10M for human rights), and South Sudan (£2.3M for climate-sensitive food security and women’s empowerment).
Trócaire Rwanda meets the criteria of handling over £1 million annually, having worked with over 40 local CSOs to build advocacy capacity and drive governance reform in collaboration with line ministries. Trócaire’s work, which has integrated its CMA approaches, includes advocating for joint land titles to enhance women’s access to credit (2019); supporting civil society contributions to Rwanda’s National Land Use Policy from a gender perspective (2020); and strengthening citizen participation in district development planning across four provinces (2021-2023). These achievements were possible through funding from donors such as Irish Aid (£1.47M annually), USAID (£755k), and the European Union (£828k), which facilitated the empowerment of CSOs and small-scale farmers to advocate for inclusive governance and influence agricultural and environmental policy. Additionally, Trócaire, in collaboration with the Scottish Catholic International Aid Fund (SCIAF) and 5 local CSO partners, currently implements a £8M programme funded by the Scottish Government to address climate change impacts in Rwanda.
Trócaire Rwanda hosts a Localisation and Partnership Unit that focuses on capacity strengthening, mentorship, and accompaniment for CSO partners. This unit works in synergy with Trócaire’s Global Hub on Partnership and Localisation, based in Nairobi, which advances programming and thought leadership on locally led approaches, informed by CSO and community feedback. Trócaire’s data-driven monitoring and evaluation systems ensure programme effectiveness, and its robust financial management frameworks align fully with FCDO compliance requirements.

3.2. Team Expertise: The Trócaire Twiyubakire Team, a dedicated unit that engages closely with Trócaire Rwanda’s Programme Team and Localisation and Partnership Unit, will ensure the effective programme delivery. The team includes:
- Team Leader (TL): The TL is responsible for the overall leadership and management of the programme, including the selection of CSO partners under Windows 1, 2, and 3. The TL provides oversight for all project deliverables, indicators, and stakeholder relationships, including with FCDO and CSO partners. The TL is also responsible for measuring and tracking programme indicators, ensuring robust monitoring, evaluation, and learning processes. This role requires at least 10 years of relevant experience, ideally including prior team leadership experience, and a master’s degree.
- Finance Manager (FM): Leading the financial management of the grant, the FM oversees due diligence processes and provides capacity strengthening support to CSOs in financial management systems and compliance, including through hands-on accompaniment and mentorship. With at least 5 years of experience, including managerial expertise, and a professional accounting certification, the FM ensures the financial integrity of the programme.
- Capacity Strengthening Advisor (CSA): Leading institutional strengthening efforts, this advisor guides CSOs through capacity assessments using Trócaire’s PCAS framework and supports CSOs to develop CSO-led capacity strengthening action plans. The CSA oversees delivery of collective and individualised capacity strengthening activities. A master’s degree and at least 5 years of experience in capacity strengthening are required.
- Advocacy Advisor (AA): The AA provides technical assistance to CSOs, ensuring the development and implementation of effective advocacy strategies aligned with government priorities and best practice methodologies, including CMA. The AA regularly engages with CSOs, their networks, and the GoR. This role requires at least 5 years of experience and a master’s degree.

3.3. Capacity Strengthening & Issue Based Sub-Granting: Over the past 30 years, all Trócaire programming in Rwanda has been implemented through issue-based sub-granting to local CSOs, making this an area of significant expertise. Trócaire Rwanda is recognised for its strong partnership model with civil society, fostering long-term, trust-based collaborations that emphasise shared ownership and accountability. Further, Trócaire integrates institutional capacity strengthening across all grants, ensuring CSOs are equipped with the technical, financial, and institutional skills to deliver impactful, sustainable outcomes and to ensure robust governance systems. Trócaire mainstreams capacity strengthening across thematic areas such as gender, climate adaptation, and civic space—its core areas of expertise—while also collaborating with CSO partners working on economic growth, inclusion, and media. Across projects, Trócaire encourages partners to allocate at least 5% of their budgets to capacity strengthening, in addition to covering CSOs’ overhead/indirect costs.

3.4. Lessons Learned: Trócaire has generated learning that enhances its work with CSOs and stands to benefit the Twiyubakire Programme. Learning includes how to conduct effective, efficient, and timely partner onboarding and due diligence assessments, particularly with new partners. Based on previous experience, Trócaire has also learned of the importance of supporting CSO partners to develop coherent advocacy strategies with measurable targets, in line with the Trócaire’s CMA approach. This ensures advocacy efforts are impactful, measurable, and relevant.
Recent research conducted by Trócaire on capacity strengthening efforts with local partners in Honduras[8], Kenya, and Uganda—particularly those in transition or phase-out scenarios—underscores the value of early and intentional investment in CSOs’ institutional capacity. Findings highlight the need to prioritise critical roles in resource mobilisation within CSOs to enhance their sustainability and to approach capacity strengthening in flexible and tailored ways. These insights have directly informed the design of the Twiyubakire Programme, with a focus on long-term resilience and sustainability of the selected CSOs.
[8] See Trócaire. From Donor Phase-Out to Local Resilience: Mitigating the Impact of the SDC’s Exit on Local Organisations in Honduras through Tailored Capacity Strengthening. 2024.
Trócaire also conducts regular partnership surveys across its global programmes, with a survey completed in 2022 and the latest one ongoing in 2025. In Rwanda, the results emphasised the added value that CSOs attribute to Trócaire’s ability to foster locally led advocacy, provide tailored capacity strengthening, and enhance institutional resilience. These findings reinforce the importance of Trócaire’s collaborative and adaptive approach, which places partners and communities at the centre of its programming while equipping them with the tools to lead and sustain their own development trajectories.

Programme Management/Coordination
4.1. Management and Performance: The programme’s management structure and systems have been designed to ensure effective programme delivery, robust technical oversight, and rigorous quality assurance. The TL will lead a dedicated unit (the Trócaire Twiyubakire Team) for the civil society component and serve as the primary manager, providing strategic and operational leadership and oversight. Reporting directly to Trócaire’s Country Director (CD) in Rwanda and the Twiyubakire Programme Board, and with dotted line management to Trócaire's Programme Manager (PM) and Localisation and Partnership Manager (LPM), the TL will also serve as the primary liaison with FCDO for all project-related matters.
Key technical and financial roles—CSA, AA and FM—will report to the TL, ensuring a cohesive and coordinated approach to project implementation. All programme roles will be based in Kigali, ensuring proximity to key stakeholders and operational efficiency. Ensuring continuity, Trócaire’s PM and LPM will provide technical support to the TL and act as deputies in the TL’s absence. These managers provide oversight of Trócaire’s grant management and compliance while ensuring CSOs are supported in these areas.
Drawing on Trócaire’s experience of fostering equitable collaboration with civil society actors, the following accountability mechanisms will be implemented:
- Trócaire Twiyubakire Programme Steering Committee (TTPSC): This committee will ensure the management of Trócaire’s International Division maintains oversight of the programme, given the scale of funding and nature of the contract. The TTPSC’s objective is to monitor and oversee organisational risks related to the Twiyubakire Programme and contract, ensuring strategic guidance, organisational oversight, and divisional accountability. Membership will include Trócaire’s Director International Operations (Chair), Director of Global Programmes, Head of Finance, Head of Global Partnerships and Funding Unit, Global Director – Partnership & Localisation, Head of Portfolio (Climate Change & Gender), and Country Director (Trócaire Rwanda). The TTPSC will meet bi-annually or as required to address specific accountability or contractual issues.
- Programme Governance Steering Committee (PGSC): Comprised of Trócaire Rwanda’s Senior Management Team (SMT) and the Executive Directors of each CSO selected for the project, this committee will meet bi-annually to review progress, with the TL providing programme updates and the FM delivering financial updates. CSOs will share highlights and challenges, fostering a collaborative environment to address key issues collectively. Accountability between Trócaire and its partners will be a cornerstone of this structure. The committee will develop agreed Terms of Reference (ToR) and act as a primary space for direct engagement, ensuring transparency and inclusivity in decision-making. To ensure accountability to communities engaged in the project, individuals and/or community leaders participating in the programme can also be invited to participate in PGSC meetings on an agreed basis.
- Partnership Agreements: Following onboarding of partners, Trócaire Rwanda’s Localisation and Partnership Unit will support the TL to co-develop partnership agreements with selected CSOs within the first year of the programme. Going beyond project grant agreements, these partnership agreements will be tailored for each partner and will outline agreed partnership principles and vision for multi-year partnerships, thus fostering equitable decision-making and inclusivity.
- Partnership Reviews: Trócaire will employ mechanisms such as regular health checks and feedback surveys to ensure strong partnerships, in line with its Partnership Policy. Rwanda’s Localisation and Partnership Unit will support the development of feedback mechanisms to evaluate partnerships twice yearly to promote mutual accountability. Findings will be compiled into short reports, with the Rwanda Localisation and Partnership Unit conducting internal meeting with the Trócaire Twiyubakire Team to share findings and recommendations. Trócaire will also conduct follow-up meetings with CSOs to discuss findings in a constructive, transparent, and solutions-orientated manner.
- Annual Stakeholder Meeting: A yearly gathering involving the full Trócaire Twiyubakire Team, CSO staff associated with the project, and FCDO representatives will provide a platform for reviewing progress, addressing challenges, and sharing key updates. This shared space will promote collective problem-solving and relationship-building among stakeholders.

Trócaire will implement a multi-tiered system for technical oversight and quality assurance that includes the following:
- Quarterly Grant Management Meetings: A quarterly grant management meeting will be held with Trócaire Rwanda’s Country Management Team, the Trócaire Twiyubakire team, and Trócaire’s Business Development and Grants Manager. The meeting will review programme progress, assess expenditure (Budget vs. Actual), address challenges, and ensure the timely, efficient, and effective flow of funds to CSOs. Decisions and actions from the meeting, will be reported to internal TTPSC and, where relevant, to the PGSC.
- Weekly Team Meetings: The Trócaire Twiyubakire Team will hold regular weekly meetings with a standing agenda to track the implementation of the programme work plan, review progress, identify challenges, and follow up on agreed actions.
- Performance Management: Formal performance reviews will be conducted biannually for all staff and their line managers, using Trócaire’s established performance management processes. These reviews will be supplemented by monthly informal one-on-one conversations between managers and staff.
- Monthly Reporting to Regional Leadership: The CD will provide monthly updates to Trócaire’s Head of Portfolio, based in Nairobi, for regional oversight.
The programme organogram illustrating the programme’s management structure, reporting lines, and accountability mechanisms is attached as an annex and provides a visual representation of the programme’s operational and management framework. Included is a visual representation of the flow of funds, or Programme Delivery Chain, illustrating the relationships between Trócaire, CSO partners, and the Twiyubakire Programme Board.

4.2. Collaboration/Coordination: To operationalise collaboration and coordination with all Twiyubakire programme delivery partners, Trócaire will leverage various collaboration mechanisms designed to foster co-ownership, adaptability, and inclusivity. The Programme Governance Steering Committee (PGSC) will serve as a central forum for high-level collaboration, bringing together Trócaire’s SMT and the Executive Directors of all selected CSOs under the programme. Trócaire’s AA will lead an Advocacy Community of Practice among all participating CSOs to foster knowledge sharing, learning, and coordination of advocacy efforts. These efforts will feed into Trócaire’s global CMA Working Group, which includes 8 country programmes and headquarters. Trócaire’s AA will also collaborate regularly with Trócaire’s global Governance and Civil Society Advisor, who supports CMA. Meanwhile, Trócaire’s CSA will facilitate a Capacity Learning Circle, which includes spaces for capacity sharing and mutual learning.
In addition, Annual Stakeholder Meetings will bring together all Twiyubakire stakeholders, including FCDO, Trócaire staff, and CSO representatives, to collectively review progress and align strategies. Trócaire will ensure regular attendance at FCDO-convened meetings, including those with the Twiyubakire SRO; Senior Governance Advisor and Twiyubakire Technical Lead; and Twiyubakire Programme Board. Where feasible and in agreement with FCDO, Trócaire will encourage the participation of CSOs in meetings, offering opportunities to spotlight their contributions and enable direct engagement with FCDO.
Recognizing that Output 3 forms part of the broader multi-component Twiyubakire Programme, which includes direct financial aid to line ministries and technical assistance to GoR stakeholders, Trócaire will prioritise planned coordination across components to ensure synergies, complementarities, and coherence. These mechanisms will be developed and agreed with FCDO during the inception phase, with the Team Leader or an appropriate representative ensuring active participation in relevant coordination efforts.
The proposed collaboration mechanisms face key risks that require proactive mitigation measures. One potential challenge is the risk of hierarchical, top-down decision-making. This will be addressed by co-creating the PGSC’s ToR, ensuring equitable participation and shared ownership among all stakeholders and involvement of community members. Additionally, the staggered onboarding of CSOs across Windows 1, 2, and 3 could lead to initial gaps in representation. To address this, the ToR will undergo an annual review, enabling newly onboarded CSOs to influence changes over time.
Another risk is the limited availability of stakeholders, which may hinder participation in meetings. To mitigate this, meetings will be scheduled at regular but manageable and agreed intervals, with advanced planning to optimise attendance while avoiding undue burden on participants. The various structures are designed to accommodate different staffing levels within the CSOs, ensuring responsibilities are distributed across staff rather than overburdening individual staff members.
Finally, the issue of non-biased feedback poses a potential challenge. To ensure confidentiality, CSO surveys will be compiled and analysed by Trócaire Rwanda’s Localisation and Partnership Unit, with support and oversight from Trócaire’s Global Hub on Partnership & Localisation. Findings will focus on actionable insights rather than attributing feedback to individuals, fostering a collaborative, respectful approach to addressing challenges.
To coordinate with other accountability programmes in Rwanda, Trócaire and CSOs will conduct ongoing mapping of existing accountability programmes and mechanisms in collaboration with FCDO. This will include assigning Trócaire and CSO staff to relevant forums, with contextual updates incorporated into the programme’s governance structures. To avoid duplication, Trócaire will work closely with FCDO to identify areas of overlap and refine the collaboration approach to address gaps and capitalise on synergies. Discussions with FCDO will clarify the scope of CSO engagement and ensure Twiyubakire’s interventions complement, rather than duplicate, existing initiatives. The mapping exercise will also highlight priority areas and opportunities for collaboration, ensuring resources are efficiently allocated and aligned with Rwanda’s accountability objectives.

4.3. Risk Management: Regarding its risk appetite statement, Trócaire’s risk appetite for the Twiyubakire Programme is confidently high, underscoring the organisation’s commitment to engage with diverse CSOs, including ones Trócaire has not partnered with previously, to achieve high-quality outcomes. Trócaire understands that achieving meaningful results in governance, accountability, and advocacy requires a willingness to accept certain risks, particularly when engaging with emerging CSOs, engaging in multi-annual partnerships, or navigating complex political and operational contexts. Trócaire mitigates these risks through its established approaches, including partner accompaniment, mentorship, capacity strengthening, and open, transparent communication. When challenges arise, Trócaire addresses them with accountability and adaptability, ensuring that risks are managed in alignment with organisational values and programme goals. Further, Trócaire employs a three lines of defence model for strategic risk management and internal control: (1) day-to-day management of operations and internal controls, (2) risk management and compliance oversight functions, and (3) an independent Internal Audit Unit reporting to the Audit & Risk Committee, providing assurance and consultancy across Ireland, UK, and overseas operations.
The risk management process for this programme is designed to systematically identify, assess, mitigate, and review risks at all levels:
Identification: Risks will be identified through multiple channels, including: regular discussions in Quarterly Grant Management meetings; updates from external entities such as the United Nations Department of Safety and Security in Rwanda; consultations with CSOs during PGSC meetings, the Advocacy Community of Practice, the Capacity Learning Circle, and ongoing project activities; consultations with FCDO staff and during Twiyubakire Programme Board meetings; and ongoing security monitoring and project feedback loops.
Assessment: Identified risks will be classified and scored based on their probability and impact, following Trócaire’s established risk assessment framework and in line with FCDO’s measurement grid. Only risks deemed major or severe will be included in the matrix as a matter of prioritisation.
Mitigation: The TTPSC will play a lead role in risk mitigation and management. A comprehensive set of mitigation measures has been established and are included in the annexed risk matrix. Mitigation measures include:
- Government-Related Risks: Strengthen relationships with GoR officials, demonstrate alignment with national priorities, and leverage evidence-based advocacy to foster collaboration.
- Financial and Compliance Risks: Conduct due diligence and financial management capacity strengthening; implement accountability mechanisms.
- Safeguarding Risks: Adhere to Trócaire’s safeguarding policies and support CSOs to implement or establish their own policies; conduct training for CSOs; and ensure CSOs establish confidential reporting and response mechanisms.
- Health and Security Risks: Conduct risk assessments, provide security protocols, and develop contingency plans where necessary.
Review and Monitoring: The risk matrix will be reviewed bi-annually by the TTPSC and PGSC. Risks no longer deemed relevant or that score as moderate or minor will be removed. New risks will be added as they emerge.
Regarding escalation and ownership of risks, the TL holds primary responsibility for ensuring risk management is performed, working in close collaboration with the CD. Specific risks are owned by relevant project roles, with the TL owning government-related risks, as well as capacity and programme quality risks; the FM owning financial or compliance risks; and the CD owning health or security risks, safeguarding risks, and donor-related risks. Risks requiring urgent escalation will be communicated directly by Trócaire to FCDO, CSO Directors, and relevant stakeholders. Otherwise, risks will be updated at PGSC meetings. The updated risk register will be shared by Trócaire with FCDO and all CSO partners quarterly.
Risk management has been fully integrated into the programme’s design, costs, time allocation, and results. The TL and FM, as primary risk holders, are included in the budget, and Trócaire’s headquarters-based International Accountant will provide ongoing support and oversight. The project contributes to the CD's oversight responsibilities. Training activities for CSOs in safeguarding, financial management, and compliance are covered within the capacity strengthening budget. The AA and CSA will conduct ongoing risk monitoring through partner engagements and capacity assessments, ensuring risks are addressed proactively.
To ensure coordination with FCDO on risk management, Trócaire will align its risk management approach with FCDO’s guidelines, ensuring regular updates to the risk register (see annex). This register will reflect any changes in the probability, impact, and severity of risks and will be shared quarterly with FCDO.

4.4. Due Diligence: Trócaire has developed a clear and accountable delivery chain for the Twiyubakire programme, which is detailed in the annexed diagram. The delivery structure ensures a seamless flow of funds and reporting lines that align with the programme’s governance and operational frameworks. For Windows 1 and 2, funds will flow from FCDO to Trócaire, which will then allocate grants to 2 to 4 CSOs selected through a transparent and rigorous process detailed in Section 2 of this proposal. For Window 3, funding will flow from FCDO to Trócaire and then to selected CSOs/NSAs through an adaptive approach that ensures responsiveness to evolving programme needs while maintaining robust oversight and accountability.
Trócaire is a registered charity in Ireland and the UK with offices in Northern Ireland a head office in Ireland. Trócaire fully complies with all relevant UK legislation, including regulations on gender equality, counterterrorism, data protection, sanctions, and anti-bribery. The organisation operates under a comprehensive policy framework that includes, inter alia, a Global Code of Conduct, which prohibits discrimination based on gender, sexual orientation, culture, ethnicity, race, age, religion, disability, marital status, family status, or membership of any minority or marginalised identity group; a Safeguarding Policy; a Fraud, Theft, Corruption, and Bribery Policy; an Aid Diversion Policy Statement; a Conflict of Interest and Gift Policy; a Whistleblowing (Protected Disclosures) Policy; a Counter-Terrorism and Anti-Money Laundering Policy; a Data Privacy Policy; and a Counter Modern Slavery, Trafficking in Persons & Child Labour Statement.
As a data controller, Trócaire and its staff comply with the data protection principles set out in the relevant UK, Irish, and EU legislation. In addition, Trócaire Rwanda is a certified data controller in Rwanda and has successfully obtained a data protection certificate in compliance with national laws, further ensuring that all programme activities respect privacy and data security regulations. Trócaire has a dedicated Data Protection & Information Security (DPIS) Team, supported by a Data Protection Officer based at its headquarters, a DPIS Security Steering Group reporting to the Audit & Risk Committee, and a global network of 50 data champions who coordinate and implement DPIS initiatives across teams.
With over 50 years of operational experience globally and over 30 years in Rwanda, Trócaire has developed a strong reputation for grant management, civil society strengthening, and advocacy. Trócaire has demonstrated its capacity to deliver the programme through extensive experience in managing large-scale, complex, multi-donor and multi-stakeholder programming (including annual donor funding of €66 million in financial year 2023-24 from donors such as European Union, Irish Aid, the Swedish International Development Cooperation Agency, UN agencies, and USAID). Specifically, the organisation currently manages substantial FCDO-funded programmes in Somalia, Zimbabwe, and South Sudan. In Rwanda, Trócaire has experience delivering funding from USAID, the European Union, the Scottish Government, and Jersey Overseas Aid, among other donors. Further, Trócaire Rwanda has a proven track record of strengthening over 40 CSOs through flagship initiatives, contributing to governance reform and enhancing advocacy capacity in alignment with national priorities. Trócaire Rwanda also benefits from collaborative relationships with FCDO, GoR, MINALOC, and MINECOFIN, which will support with alignment with broader accountability and governance goals.
Trócaire has established systems to monitor and manage the financial and operational performance of downstream partners, ensuring high-quality delivery and accountability. This involves regular site visits, mentorship, and capacity strengthening, with clear recommendations and follow-ups to address any issues identified. Partners are supported through results-based management training and regular progress tracking to ensure alignment with programme objectives. In cases of poor performance, Trócaire follows a structured escalation process, including formal meetings between Trócaire and CSOs’ senior management. Trócaire also issues warning letters and engages with partners’ boards as required, providing opportunities for resolution before considering partnership termination.
The multi-year nature of FCDO funding allows Trócaire to extend similar multi-year funding arrangements to CSOs, fostering stability and continuity in programme delivery. This approach ensures that CSOs can plan effectively and maintain momentum in achieving programme outcomes.
In relation to financial management and fraud prevention, Trócaire maintains a zero-tolerance policy for fraud, corruption, and aid diversion, guided by its Fraud, Theft, Corruption, and Bribery Policy, complemented by an Aid Diversion Policy Statement. The policy is reinforced by the organisation’s Global Code of Conduct, which outlines expectations for all employees and stakeholders. There are clear procedures for reporting and investigating incidents. Any cases of fraud or aid diversion are promptly escalated to donors, including FCDO, with detailed remediation plans implemented.
In the past financial year, Trócaire has proactively monitored its operations to mitigate risks and ensure compliance. At the start of March 2023, Trócaire had two investigations in progress. During the 2023/24 financial year, a further five cases were received that required preliminary or more detailed investigation. Five of seven cases were closed during the year with two cases open at the year end. The value of loss to fraud/theft in 2023/24 following completed investigations was €57,173.
Regarding countering violent extremism and terrorism, Trócaire is committed to this in all its programming. The organisation conducts thorough due diligence assessments for all partners to ensure alignment with this commitment. Trócaire’s zero-tolerance approach is embedded in its operational practices and partner engagement strategies. Additionally, Trócaire’s procurement department conducts regular checks of partners and suppliers against terrorist watchlists to ensure compliance and safeguard programme integrity.
Trócaire undergoes regular external audits to ensure financial, operational integrity, and executive oversight. Any findings, including management letters and remedial actions, are addressed promptly. Recent audit reports for Trócaire headquarters and Rwanda are annexed to this proposal.

4.5. Other Funding: Trócaire Rwanda does not currently receive other funding from FCDO beyond the proposed Twiyubakire programme. This ensures that all resources allocated under the programme are uniquely dedicated to achieving its goals and objectives without duplication. However, Trócaire’s work in Rwanda is supported by additional funding streams from other donors, which complement and enhance the Twiyubakire programme. Trócaire Rwanda receives funding from the Scottish Government for a Climate Resilience Programme to address climate change impacts in Rwanda, working with five CSOs. This £8M programme runs from 2023 to 2026 and focuses on empowering communities—particularly marginalised groups such as women, youth, and persons with disabilities—to develop and implement climate adaptation and recovery plans. Trócaire Rwanda also receives an annual allocation of £1.47M through Ireland’s Civil Society Partnership (ICSP) from 2023 to 2027. This funding supports over 15 local and national CSOs in Rwanda, including the establishment of a civil society climate advocacy network. This network engages government and private sector stakeholders to influence environmental policy, directly aligning with the Twiyubakire programme’s focus on climate change as a thematic priority. To avoid duplicating efforts. Trócaire Rwanda ensures that clear coordination and communication channels are established across all programmes.
The cessation or reduction of complementary and current funding streams could pose risks that impact Trócaire’s work in Rwanda, including the ability to sustain or expand climate advocacy networks and grassroots adaptation initiatives that directly contribute to Twiyubakire outcomes. However, to mitigate this, Trócaire has a team of staff working in headquarters and country offices that focus on securing funding from institutional donors. Successful grant management of projects and positive engagement with donors has resulted in a steady growth of institutional funding. This proactive approach to securing funding will provide a buffer against the abrupt cessation of any single funding source. While funding from the Scottish Government and ICSP is confirmed for their respective timelines, Trócaire remains engaged in ongoing dialogue with other potential donors to further diversify its funding base and mitigate risks to programme implementation. Regular updates on funding opportunities and risks will be shared with FCDO to ensure transparency and alignment with Twiyubakire’s objectives.

5. Monitoring, Evaluation, Accountability and Learning (MEAL)

5.1. MEAL Structure:
Trócaire’s MEAL approach in the Twiyubakire programme supports inclusive, evidence-based learning and downward accountability within a condensed implementation timeline. Grounded in Trócaire’s global MEAL Policy and aligned with OECD-DAC, CHS, and International CSO Effectiveness standards, the approach prioritises practical, partner-led systems that generate real-time insights for adaptation and accountability.
Under the 9-month pilot phase, MEAL is designed to be light-touch yet strategic, emphasising co-creation, rapid learning, and citizen feedback. A strong emphasis will be placed on supporting CSOs to document results, reflect on lessons, and identify scalable models to inform the second phase.
Key features include:
- Rapid co-development of indicators and MEAL plans with CSOs during the inception phase.
- Light baseline data collection shortly after CSO onboarding to establish benchmarks for pilot tracking.
- Quarterly reflection sessions with Trócaire and partners to assess progress and enable fast pivots.
- Use of Trócaire’s digital tools (e.g., CommCare) where feasible, while maintaining flexibility for partner-preferred tools.
- Integration of FCHM (Feedback and Complaints Handling Mechanism) and safe reporting channels from the outset.
- Partner mentoring and coaching by Trócaire’s in-house Monitoring, Inclusion, Learning Advisor (MILA), who replaces the previously proposed MELO role.
The MEAL function will be led by the Trócaire Rwanda MILA with technical support from the global Programme Impact and Learning (PIL) Team. This team will ensure MEAL tools are adapted to the pilot’s duration and scope, with a strong focus on inclusion, accountability, and locally relevant evidence.
5.2. Project Monitoring Strategy and Timelines (Pilot Phase)
Monitoring will be anchored in the programme’s logical framework and guided by a streamlined MEAL plan co-developed with selected CSOs. Key elements include:
- Baseline Snapshot (Month 2): A light but participatory baseline will be conducted to validate indicators and capture pre-intervention status across key outputs and outcomes.
- Quarterly Joint Monitoring Visits (Months 3, 6, 8): Trócaire technical teams will visit each CSO at least once per quarter. Monitoring will focus on results, learning, and compliance. Senior-level visits will be organised where possible.
- Monthly Partner Check-Ins: Informal progress updates and mentorship sessions will be conducted monthly by the MILA and programme team.
- Monitoring Tools: A simplified partner results-tracking template will be developed and shared. Partners will be supported to collect sex-, age-, and disability-disaggregated data aligned to key indicators.
- Documentation of evidence (e.g., photos, success stories, meeting records, community feedback, FCHM data) will be part of ongoing monitoring to assess progress.
All monitoring activities will be documented, and partners will receive written feedback with clear, time-bound follow-up actions.
5.3. Project Evaluation Plan
Given the short duration of the pilot, a single, streamlined learning review will be conducted at the end of the 9-month phase instead of a formal mid-term or final evaluation. This will be structured as follows:
End-of-Pilot Learning Review (Month 9):
- Led by Trócaire’s Rwanda MILA and Programme team, with support from the global PIL Team.
- Will synthesise monitoring data, CSO reflections, and community feedback.
- Will include:
  - A rapid outcome harvesting exercise to identify early signs of change.
  - A short series of key informant interviews with CSO staff, local government actors, and community members.
  - An internal synthesis report documenting lessons learned, gaps, and promising models for scaling.
- Findings will be shared with FCDO during a joint End-of-Pilot Learning Session, including discussion of recommendations for Phase 2.
Anticipated Second Phase (12 Months):
- If the programme is extended, MEAL activities will be scaled up accordingly, including:
  - A short inception and onboarding phase for continuity.
  - Quarterly reflection meetings and two joint learning forums (mid-point and end of phase).
  - Continued joint monitoring and documentation of community outcomes.
  - An end-of-phase evaluation, led by an external consultant or the Trócaire global MEAL team (depending on scale and budget), will assess progress and generate learning for long-term planning.
Note: All evaluation and learning activities will remain flexible and proportionate, aligned to the available budget and agreed-upon scope with FCDO.

5.4. Value for Money (VfM) Framework: Trócaire will ensure that the Twiyubakire Programme delivers high VfM by balancing Economy, Efficiency, Effectiveness, and Equity throughout its implementation. This framework (see annex) includes metrics and indicators aligned with FCDO standards. It will be reported on quarterly and annually unless otherwise agreed. Refined during the Inception Phase, it will be reviewed by the TTPSC and PGSC and will be updated annually to reflect programme progress and evolving priorities, in consultation with FCDO.

1. Economy: The programme will ensure that inputs are procured at the best value without compromising quality.
1.1. The inputs that the civil society component of the Twiyubakire programme will pay for include but are not limited to: salaries, purchase of goods, consultancies, travel, hotels. Trócaire uses competitive bidding (min. 3 quotations) for goods above €500 and for services and works above €1,000, aimed at maximising VfM. Open tender is €20,000 upwards for goods/supplies and from €40,000 upwards for services/works. Trócaire will ensure CSOs have robust procurement mechanisms that meet Trócaire and FCDO requirements.
Measurement: Financial statements and verified audit statements will be submitted to FCDO annually by Trócaire; Trócaire and CSO work plans and budgets; financial documentation reviews of CSOs conducted by Trócaire.
- 1.2. Staff costs. Measurements: Staff salaries will be benchmarked to ensure alignment with market rates (e.g. annual Birches reviews).
- 1.3. Ratio of overhead costs to overall programme costs. Measurements: FCDO’s estimate, based on other programmes in Rwanda is between 9-12%.
- 1.4. Savings through management process efficiency. Measurements: Analysis of expenditure trends of significant operating items, e.g. consultancy fees, travel.

2. Efficiency: The programme will ensure optimal conversion of inputs into outputs while minimising waste.
- 2.1. The average cost per programme participant reached. Measurement: Total annual programme expenditure divided by number of programme participants.
- 2.2. The average cost per trainee for capacity strengthening activities undertaken by Trócaire and CSOs.
- 2.3. The average cost per evidence generation or advocacy paper to support policy development or CSO engagement.
Measurement: Indicators 2.2 and 2.3 to be measured against average costs in similar Trócaire-led programmes and FCDO programmes.
2.4. Number of CSOs selected and onboarded within agreed timelines.
Measurement: Documented through CSO Selection Committee decisions, signed grant agreements, and supporting financial records.

3. Effectiveness: The programme will achieve the desired outcomes through the efficient delivery of outputs.
- 3.1. Number and percentage of CSO-led advocacy initiatives leading to policy changes or measurable improvements in governance.
- 3.2. Number of government decisions taken on changing, stopping or improving implementation of policies based on citizen participation mechanisms.
- 3.3. % increase in citizen satisfaction with local government service delivery.
Measurements for the above include the annual Rwanda Governance Scorecard (citizen participation indicator); the Citizen Report Card scores on citizen participation; Twiyubakire Civil Society Component tracking mechanism.

4. Equity: The programme will ensure that that programme benefits are distributed equitably and reach those most in need.
- 4.1. Strong inclusion of marginalised groups in programme activities. Measurement: Numbers of GEDSI individuals directly involved in programme activities, disaggregated.
- 4.2. Diversity of selected CSOs led by or focused on the rights of members of marginalised groups (e.g. WCOs and OPDs). Measurement: Number and percentage of selected CSOs led by or focused on the rights of members of marginalised groups; amount and percentage of programme resources allocated to CSOs led by or focused on the rights of marginalised groups.

5.5. Learning and Improvement: Trócaire ensures that insights from reviews, evaluations, and partner feedback directly inform programme adjustments, thus promoting flexibility, agility, and responsiveness. Quarterly and annual reflection meetings with Trócaire, CSOs, and FCDO provide structured opportunities to assess progress and address challenges collaboratively. Partner surveys will serve as a basis for proactive discussions between Trócaire and CSO partners, enabling adjustments in ways of working to promote stronger collaboration and enhance effectiveness. The mid-term review, conducted collaboratively with CSOs, will generate actionable recommendations to refine the programme’s direction. Similarly, the final evaluation will prioritise the perspectives of CSOs and programme participants to assess impact and inform future initiatives.

6. Commercial
6.1. Budget Summary: Trócaire maximises cost efficiency in all interventions. For this opportunity, 60% of funds are allocated to CSOs through Funding Windows 1, 2, and 3. Trócaire has streamlined support from country office and headquarters teams, ensuring cost-effectiveness without compromising quality by aligning budgets closely with activity needs. Additionally, cost-effective principles and economies of scale have been applied, with office running costs kept under 2.5% of the budget. Trócaire’s NPAC calculations follow FCDO guidance, with costs derived primarily from published consolidated financial statements (latest for the year ending 29 Feb 2024). Using the FCDO template, Trócaire has populated costs from accounts and internal expenditure reports to determine the NPAC percentage. The movement in 2024 compared to the previous year reflects increased institutional funding and shifts in eligible indirect costs relative to direct costs. The NPAC rate presented in the grant proposal is the 3-year average of 12%, which will also be applied to CSOs.

6.2. Financial Monitoring and Reporting: Trócaire employs a robust financial management system, Agresso, to ensure effective expenditure control and accurate forecasting. This system will be used to oversee and manage all Twiyubakire Programme financial operations. Agresso is integrated with Salesforce, Trócaire’s internal business development and grant management platform, ensuring that grant figures are accurately reconciled across both systems, facilitating effective financial oversight and reporting. In line with Trócaire’s financial policies and best practices—including rigorous budgeting, real-time tracking, and periodic variance analysis—all Twiyubakire financial operations and expenditures will undergo multi-level approvals, internal audits, and independent external audits to uphold financial integrity. For downstream partners, the Twiyubakire Programme will leverage Trócaire’s established financial monitoring system, which includes monthly and quarterly reviews of CSO transactions, verification of monthly financial reports, and quarterly voucher reviews. In accordance with government requirements, all partners must conduct an annual organisational audit, which will be submitted to the Revenue Authorities at the end of each financial year.
To ensure realistic forecasting, Trócaire will employ a structured approach that includes historical trend analysis, scenario planning, and adaptive budgeting, engaging downstream partners throughout the process. Regular financial reviews, conducted collaboratively by Twiyubakire Programme teams and CSO partners, will allow for data-driven adjustments to financial projections. Trócaire will also provide ongoing mentoring and accompaniment to CSOs to support their financial management, grant management, compliance, and capacity strengthening.

6.3. Indicative Payment Plan: Trócaire requests quarterly payment in advance given the fund disbursement nature of the programme as per below:

Quarter	Year 1 (£)	Year 2 (£)
Q1	N/A	£ 298,800.00
Q2	£357,723.50	£262,600.00
Q3	£441,108.10	£312,700.00
Q4	£401,168.40	£125,900.00
Total	£1,200,000.00	£1,000,000.00

Total: £2,200,000

6.4. Accounting: Trócaire confirms adherence to financial requirements, including forecasts, reporting, and audit schedules. Trócaire also confirms it manages finances on a resource (accruals) accounting basis.

6.5. Compliance with FCDO funding requirements: Trócaire confirms it adheres to the following points if it receives FCDO funding:
- Trócaire will not undertake activities until an Accountable Grant Agreement (AGA) has been signed off by both FCDO and Trócaire. Before signing the AGA, FCDO will ask for a quarterly forecast of the Trócaire’s year one budget (9 months pilot phase). Trócaire’s projections shall be realistic. Forecasts must be updated every quarter, and more regularly if needed. Trócaire will inform FCDO of any changes that have a significant impact on the forecast as soon as possible.
- The AGA will set out the budget for the programme by UK financial year. Trócaire shall not exceed the budgetary allocation per financial year without prior approval in writing from FCDO. Unspent funds will not be automatically rolled forwards between UK financial years.
- If Trócaire needs to roll funds forward, it must submit a request in writing to FCDO, to be considered on a case-by-case basis. FCDO’s decision on this request will be based on the accuracy of financial forecasts for preceding quarters, and performance against targets in the log frame, alongside any mitigating circumstances.
- The agreement will set out the schedule for quarterly report submission dates, and the submission of annual audited statements. These shall be adhered to; and any requests for changes to these dates shall be submitted in writing for approval.
- All FCDO payments will be made in arrears unless there is a strong justification for making them in advance. Payments in advance will only be continued if forecasting is robust and realistic with little underspending against previous allocations.

Revised Annexes: Annex A: Theory of Change; Annex B: Logical Framework; Annex C: Budget; Annex D: Organogram and Programme Delivery Chain; Annex E: Risk Register and Annex G: JDs of Key Personnel.