Business Case
Summary Sheet

Portfolio/ Business/Country Plan Summary:

Title: / Strengthening Systems for Science and Technology in Africa and Asia (SS4ST)
Programme summary (100 words maximum): / The Strengthening Systems for Science and Technology (SS4ST) programme will transform fragmented Science and Technology (S&T) ecosystems across Africa by investing in locally led research, capacity building, and evidence-based policymaking. Delivered through trusted local partners, country-level programming will generate context-specific knowledge, strengthen capability at individual, institutional, and government levels, and scale innovative solutions to pressing development challenges. Building on a decade of proven impact, the programme aligns with UK diplomatic and development priorities, deepening bilateral relationships in FCDO priority countries. The programme prioritises long-term results over short-term activities. By addressing systemic gaps and leveraging £200m in co-investment, SS4ST will position the UK as a partner of choice in science-driven development - fostering inclusive growth, reducing aid dependency, and laying the foundations for longer term shared prosperity.
What is the rationale for UK Aid spending? / The UK’s comparative advantage lies in its world class science and technology ecosystem, global diplomatic reach, and deep development expertise. SS4ST capitalises on these strengths to advance one of UK Aid’s highest priorities: driving inclusive, sustainable growth through systems level transformation. The programme strengthens national science, technology and innovation systems in Africa and Southeast Asia - enabling countries to generate locally relevant solutions to shared global challenges including climate resilience, health security, and economic productivity. By supporting equitable, locally led research partnerships, SS4ST moves beyond traditional aid delivery toward durable capability building that endures well beyond programme lifetimes. / UK Aid funding plays a catalytic role. SS4ST will generate new value by engaging a broader spectrum of stakeholders, mobilising approximately £200 million in co-investment from governments, multilaterals, philanthropy and the private sector. Using UK credibility to convene actors and unlock scale, this approach delivers exceptional value for money while embedding global standards, shaping policy, and opening pathways for UK researchers and businesses to collaborate responsibly in emerging markets. / At its core, SS4ST reflects a modern UK development model: partnership driven, financially innovative, and system centred - repositioning the UK as a global leader in delivering resilient, inclusive development outcomes by 2030.
Programme Value: / Up to £34M ODA / (£28M CDEL £6M RDEL)		Country/ Region or Sector: / International Science & Tech Directorate (ISTD), Global Science Department (GSD)
Department/Country Office confirmation of review processes		Confirmed.
Contact name		Alison MacEwen
Threshold for final approval of Business Case: Director
Date of Approval of Concept Note:	22/10/2025	Name and role of Approver: / Baroness Chapman, Minister for Development
Date of Approval of Business Case:	15/12/2026	Name and role of Approver / Ros Eales, Director International Science & Technology
Programme Code: 400199	AMP Start Date: / 01/04/26	AMP End Date: / 31/03/31
Overall programme risk rating:	Moderate

Strategic Case

Aligned with FCDO’s modern development agenda Strengthening Systems for Science and Technology in Africa and Asia (SS4ST) aims to transform Science & Technology (S&T) ecosystems through strategic investment in locally led research and stronger institutional and government capacity. The programme will enable evidence-based policymaking, build resilient national and regional S&T systems, and catalyse co-investment for sustainable, inclusive growth. Co-designed with governments, stakeholders and development partners across Africa and Southeast Asia, and leveraging UK expertise and global partnerships, SS4ST tackles pressing challenges and – positions the UK as a trusted partner in shaping equitable, science-driven development.

Context
# Addressing fragmented S&T systems - Why it matters
An effective S&T ecosystem connects universities, research institutions, startups, government, investors, and the private sector. Strategic investment in institutions, infrastructure, funding mechanisms, and talent pipelines drives innovation, resilience and sustainable growth. In today’s fast-changing technological landscape, an integrated approach is vital for producing quality research, fostering innovation and maintaining long-term economic competitiveness.

Strong S&T systems are vital for economic, security, and development goals. In the UK, science and technology underpin the Modern Industrial Strategy, driving productivity and growth. A recent Royal Society report highlights the significant direct and indirect contribution S&T to the economy.[1]
[1] Royal Society, 2024. Science-2040-economic-value-of-science.pdf.

Globally robust research systems correlate with higher GDP, competitiveness, and human development.[2] Yet, many S&T ecosystems in the Global South remain fragmented, underfunded, with most countries in Africa and ASEAN countries far below R&D targets. The African Union committed to allocating 1% of GDP to ST&I in the 1980 Lagos Plan of Action and reaffirmed this commitment in 2014. Yet only seven African countries report on their R&D expenditure, and most Asian countries remain at or below 0.2%.[3]
[2] Jonathan Adams, Martin Szomszor, 2022. A converging global research system. Quantitative Science Studies 3 (3): 715–731. Available: https://doi.org/10.1162/qss_a_00208; UNESCO Science Report: the race against time for smarter development; executive summary. UNESCO Digital Library
[3] UN Economic Commission for Africa. Realizing the R&D expenditure target of “1% of GDP”? NTIS Policy Brief; Asia Power Index 2024: R&D spending (% of GDP) data - Lowy Institute Asia Power Index.

As the UK redefines its development strategy, we have a unique opportunity to leverage diplomatic influence, technical expertise and targeted funding to strengthen local S&T systems, mobilise domestic resources and foster shared prosperity through innovation.

Rationale for a multi-layered approach

Strengthening S&T systems requires a holistic, multi-layered approach addressing interconnected drivers of change. As shown in Figure 1, the programme works across three reinforcing levels - Individual, Institutional, and Environmental – critical for building resilient S&T ecosystems.

- Individual Level: People are the foundation of research systems. Empowering researchers with advanced skills, knowledge, and the capacity to innovate is critical to success. By equipping scientists and practitioners with the competencies and confidence they need, we enable them to produce world-class research and develop innovate solutions to the most pressing global challenges.
- Institutional Level: Individuals succeed when supported by strong institutions. Strengthening governance, processes, and resources enables research organisations to deliver cutting-edge outputs, meet global standards, and respond to emerging priorities.
- Environmental Level. The outer layer represents the enabling environment - policies, regulations, norms, markets and government systems - that shapes institutional and individual success. A strong environment makes systemic improvements sustainable, scalable, and attractive to investment.
These layers reinforce each other - progress in one accelerates the others. Addressing all three moves beyond fragmented interventions to create transformational impact, turning research systems into engines of innovation and development.

The proposed intervention

This programme reflects a modern development approach. Through equitable, locally driven partnerships SS4ST strengthens S&T systems in the Global South – building research capacity, fostering innovation, and enabling governments and private sectors to lead development and attract investment. It tackles development challenges, drives sustainable growth, reduces aid dependency, and delivers long-term returns while reinforcing UK leadership in S&T.

Our Global Science department (GSD) brings long-standing partnerships and deep contextual knowledge of partner priorities. Building on this foundation, the programme - co-designed with country and regional stakeholders - takes a systemic approach, engaging individuals, institutions, and the wider ecosystem, including government, to deliver an integrated offer across all dimensions of the S&T ecosystem.
At the impact level, the programme will build inclusive, locally led, and responsible S&T ecosystems to tackle development challenges, improve quality of life across Africa, Southeast Asia, and promote shared global prosperity.
At outcome level the programme will:

1. Build vibrant, nationally-led S&T ecosystems that scale innovative research to tackle local and global challenges;
2. Strengthen national leadership on ethical and effective use of science and emerging technologies; and
3. Enhance UK contribution to and benefit from partner countries S&T advances.

Building on a decade of evidence, the new programme focuses on three components:

  1. Science Granting Councils Initiative (SGCI): Expanding support for 20 African science councils to commission local research, strengthen collaboration, improve research delivery and policy uptake, with co-investment from Wellcome, Canada, Norway, Sweden and African governments.
  2. Wellcome/FCDO partnership: Extending an impactful Africa programme to Southeast Asia, supporting research consortia to tackle development challenges and enhance institutional excellence, with regional government co-investment. Led by local delivery partners – Science for Africa Foundation and the Southeast Asia Ministers of Education Organisation.
  3. Responsive country-level S&T programming: Co-designed with partner governments and institutions to address bilateral priorities, using UK expertise to drive policy reform and innovation.
Programme’s outputs are detailed in the Theory of Change in the Appraisal Case.

This programme supports key UK strategies across Africa and Southeast Asia, focussing on FCDO priority countries, and aligns with the UK’s broader goal of securing strategic advantage in emerging technologies such as AI.

Why FCDO should intervene

Maximising impact in a 0.3% world. With global ODA reductions, we must deliver the greatest Value for Money (VfM) and impact by working together with partners to ensure coordination and coherence. The UK’s strong research base and innovation capabilities position us to build equitable partnerships that help Global South countries meet development priorities, attract investment, and reduce aid dependency. Delivered by FCDO teams across Africa, South and Southeast Asia, the programme supports HMG Country Business Plans and bilateral priorities under strategic Government to Government partnerships.

Building on a decade of FCDO-supported investment and partnerships that have already leveraged £150 million from global leaders like Wellcome and IDRC Canada, this next phase represents an evolution of that success. In a reduced ODA context, it retains proven, high-impact elements from existing partnerships and programmes while introducing next-generation approaches to deliver systemic outcomes. This phase will mobilise new partners and secure match funding from African and ASEAN member states - strengthening local ownership, ensuring sustainability, and reducing aid dependency to enable a responsible FCDO exit.

Advancing UK bilateral relationships through S&T. Science and technology are powerful enablers of economic growth, evidence-based policymaking, and research commercialisation. By adopting a systems approach, the UK can strengthen bilateral ties through improved decision-making, risk anticipation, and resilience building.[4] Enhancing S&T ecosystems in Africa and Asia advances FCDO priorities—mutual prosperity, diplomatic influence, and global stability, while projecting UK soft power through knowledge exchange and S&T leadership. Rapid technological shifts and post-COVID recovery create opportunities to leverage R&D for shared benefit. For example, ASEAN’s R&D investment has surged fivefold, from USD 10.6 billion in 2002 to USD 54.9 billion in 2023.[5] Through multi-country consortia, co-developed solutions, and emerging technologies such as AI and big data, the UK will accelerate innovation and deliver transformative impact in partnership with key regions cementing its role as a partner of choice in global science diplomacy.
[4] Harvard Business Review, 2025: Why You Need Systems Thinking Now; Creating A Vision and Setting Course for the S&T Ecosystem of 2050; 2025 Lancet One Health Commission
[5] Global Innovation Index 2024: ASEAN continuing to cement itself as a global Innovation Hub.

Alignment with FCDO R&D priorities. Aligned with FCDO’s new ODA R&D approach, this programme advances S&T for Development through equitable partnerships with the Global South, supporting priorities in Africa, Indo-Pacific, and beyond. It will expand knowledge, improve research competitiveness, and strengthen FCDO’s thematic research, while laying foundations for future markets that benefit UK growth. A key lever for the proposed Tech Centre of Expertise, the programme builds core S&T capabilities, streamlines the UK offer globally, and enables access to UK research in priority countries - reinforcing UK leadership in systems strengthening and international development.

Alignment with x-HMG ODA R&D programming. FCDO leads on UK ODA R&D coordination, and this programme will shape the UK’s approach to systems strengthening. We will drive cross-government coordination, working closely with the Department for Science, Innovation and Technology (DSIT) and UK Research and Innovation (UKRI) to align their programming, reflecting the Minister of Science - Patrick Vallance’s priority on S&T systems strengthening.

Equitable partnership. Delivery will follow a responsive, partner-led approach, co-creating equitable science collaborations. The programme fulfils SDG 17 commitments by strengthening north-south and south-south S&T partnerships, and supports Growth Mission for sustainable, inclusive growth.

Responding to local ambition and strategic priorities for S&T. In Africa, the UK’s new approach emphasises genuine partnership, mutual respect, and co-creation, shaped by consultations with African governments and organisations. It shifts the UK’s role from donor to investor, aligning with African priorities in trade, climate, science, technology and innovation, while leveraging UK expertise and people-to-people links. The goal: sustainable growth, strengthened institutions, and high-impact partnerships reinforcing UK global leadership in science and technology. This programme directly advances African Union (AU) Agenda 2063 and Science, Technology and Innovation Strategy for Africa (STISA) 2034, accelerating Africa’s transition to an innovation-led, economy by strengthening research infrastructure, fostering collaboration, promoting equity and catalysing entrepreneurship. It also supports key regional frameworks, including the Regional Economic Communities (RECs), the African Union’s High-Level Panel on Emerging Technologies (APET), the African Observatory for Science, Technology, and Innovation (AOSTI), the Policy and Regulatory Initiative for Digital Africa (PRIDA), and the African Continental Free Trade Area (AfCFTA).

In Southeast Asia, the programme supports the ASEAN Plan of Action on Science, Technology and Innovation (APASTI), ASEAN-UK Plan of Action, and ASEAN Innovation Roadmap. GSD’s strategic engagement through the ASEAN Committee on Science, Technology and Innovation (COSTI) has strengthened the UK’s Dialogue Partnership with ASEAN.[6] The second COSTI Policy Dialogue facilitated by GSD in October 2025 marked a milestone with ASEAN formally endorsing key S&T initiatives - AI for Sustainable Development (AISDA) and ASEAN-UK Research-to-Market Opportunities for Regional Advancement (AURORA) - signalling joint ownership by ASEAN and long-term commitment to UK collaboration.
[6] In SE Asia, the UK became an ASEAN Dialogue Partner in 2021 and agreed an ASEAN-UK Plan of Action (PoA) in 2022, which sets out priority areas for ASEAN-UK cooperation over the next five years, and provides the framework for cooperation across a substantial set of global and regional issues including on S&T.
Addressing shared global challenges. Issues like climate change, pandemics, and food security demand global solutions informed by local contexts.[7] Strengthening S&T systems in developing countries ensures global research agendas reflect their needs and enables meaningful contributions to shared problems (UNCTAD 2024).[8] Rapid advances in AI, green tech, and Industry 4.0 risk widening the gap between developed and developing nations - without inclusive access, the Global South faces growing inequality and reduces capacity to tackle global challenges.
[7] World Economic Forum, 2025. How university partnerships could ignite innovation in the Global South.
[8] UNCTAD, 2024. Global cooperation in science, technology and innovation for development.

Beyond the above, the programme delivers secondary UK benefits:

- Expanding markets. Supports UK Trade Strategy and Modern Industrial Strategy by creating market-enabling environments, unlocking opportunities for UK’s SMEs, technology exports and services. As emerging economies grow, demand for UK expertise in AI, biotech, and clean energy will rise. Strengthening S&T ecosystems and shaping global standards positions the UK as a preferred partner to deliver mutual prosperity.
- Geopolitical influence. In an era rising geopolitical tensions and technological competition, S&T diplomacy strengthens alliances, shapes global standards and builds resilient, values-aligned partners – reducing aid dependency and reinforcing UK leadership.[9]
  [9] The UK's International Technology Strategy - GOV.UK

Why this programme, now?

The UK is globally recognised for science and technology leadership, with world-class universities, multi-disciplinary expertise and strong research systems. We bring valuable lessons on S&T systems strengthening. GSD delivers high-quality partnerships with UK, African and Southeast Asian institutions, leveraging overseas teams, the FCDO/DSIT Science & Technology Network, and deep regional knowledge.
The UK is a trusted partner, with a proven record of locally led, sustainable solutions through programmes like the Science Granting Council Initiative (SGCI), Strengthening Research Institutions in Africa (SRIA), and Africa Technology and Innovation Programme (ATIP) - each consistently rated ‘A+’ or ‘As’ in reviews.[10] With over a decade of programming, there is strong evidence of impact to build on through this initiative.
[10] All programmes have consistently scored an ‘A+ and As’ in Programme Annual Reviews and an ‘A’ in their Programme Completion Reviews.
Driving locally led, strategic S&T partnerships to secure long-term impact. The window of opportunity to shape S&T ecosystems in Africa and Asia is narrowing as countries rapidly scale their own investments. Acting now ensures the UK remains a trusted partner and leverages its diplomatic and development expertise for maximum impact. Through country-level S&T programming, we deliver tangible returns: In Ghana, UK engagement secured a government commitment of 0.5% of GNI for R&D and an additional $5 million for the Ghana National Research Fund (GNRF). This year, we are operationalising GNRF - sharing UKRI expertise on governance, capacity building, and digital systems. Continued technical assistance will enable GNRF’s first research call in 2026, unlocking locally led innovation and reducing long-term aid dependency. In India, strategic partnerships - such as an Agri-innovation initiative with the Department of Biotechnology and South Africa, and institutional collaborations linking entrepreneurial ecosystems across India and East Africa - have already unlocked matched funding from Indian partners. These partnerships position UK as an equal and committed partner in advancing South-South cooperation, co-creating scalable solutions, and mobilising shared resources to accelerate inclusive growth across regions.
The return on investment is clear: every pound invested now multiplies through partner commitments, matched funding, and systemic reforms that deliver sustainable impact. Delaying risks losing influence, missing co-investment opportunities, and ceding ground to competitors in shaping global norms and innovation ecosystems.
The UK’s ability to convene global partners and align diverse funding streams is a strategic advantage. In Africa and Southeast Asia, we have trusted relationships with leading development partners - Wellcome, IDRC, SIDA, NORAD, BMGF, Mastercard - and regional bodies like ASEAN. This programme will amplify these partnerships through co-investment and joint delivery, targeting proven collaborations to maximise impact. For example, Developing Research Excellence and Mentorship in Southeast Asia (SEA-DREAM), co-developed with Wellcome, adapts the successful Developing Excellence in Leadership, Training, and Science in Africa (DELTAS) model to Southeast Asia, with Southeast Asia Ministers of Education Organisation (SEAMEO), as a delivery partner and policy platform. Secured commitments include £50 million from Wellcome, £1.5 million from Thailand’s Science and Research Council, and additional funding from Indonesia, Malaysia, and the Philippines. ASEAN’s strong interest in partnering with the UK signals long term commitment to science, innovation and technology. Over the past decade FCDO has leveraged £25 million from partners through SGCI and recently secured £10 million from Wellcome for the next phase. National governments increasingly value Science Granting Councils, mobilising funding and support. South Africa’s National Research Foundation (NRF-SA) has led this progress, providing financial and technical leadership, strengthening regional capacity through partnerships with German, Dutch, and Japanese agencies.
The UK has supported the development of the Good Financial Grant Practice (GFGP) and Good Research Management Practice (GRMP) standards with Science for Africa (SFA) Foundation and the African Organisation for Standardisation (ARSO), boosting African institutions’ credibility and global funding potential. Through SS4S&T, we will promote adoption of these standards in SGCI phase III and SEA-DREAM, aligning assurance mechanisms across UK and global partners.

How will the programme deliver transformative change?

This programme builds on FCDO’s proven impact across Africa and Asia, leveraging regional and bilateral partnerships to address shared priorities, catalyse co-investment, and ensure a sustainable UK exit. Our approach is anchored in the following approach:

Addressing systemic gaps. Since 2015, SGCI - designed by FCDO and partners - has transformed Africa’s research ecosystem by strengthening national science funding agencies, developing policy frameworks, digitising grant management, and creating new funding bodies in countries like Botswana, Sierra Leone, and Ghana. Recognised by the African Union Development Agency – New Partnership for Africa’s Development (AUDA-NEPAD) and the African Union Commission as pivotal to implementing STISA-2034 and Africa’s innovation agenda, SGCI demonstrates that strategic investment in science systems delivers long-term, systemic change.
1. Focussing on regional coordination and impact: SEA-DREAM will strengthen UK–ASEAN cooperation on health and climate research, foster equitable partnerships, and enhance science leadership. With £50 million from Wellcome and additional regional funding, the programme will deliver over £60 million in research support. ASEAN’s strong engagement with the programme highlights its potential to shape science and technology across the region in Southeast Asia. Early FCDO support to SEAMEO has already improved research grants management and quality assurance frameworks.
2. Leveraging strategic relationships and co-investment to amplify impact: The programme capitalises on trusted networks built through SGCI, DELTAS, ATIP, and ASEAN engagement, embedding UK leadership in S&T diplomacy. DELTAS attracted 10x additional Wellcome funding and 3x from other funders, demonstrating FCDO’s catalytic role. Wellcome’s £50m commitment to SEA-DREAM reflects this confidence. Initiatives like Sankore (Ghana), AISDA (ASEAN), and Kenya’s Innovation Roadmap have delivered policy reforms and strengthened S&T ecosystems. We will expand these partnerships to create jobs, attract co-investment opportunities and ensure sustainable investment.
3. Driving inclusion and equity. Building inclusive science systems is not just a goal - it is a deliberate strategy for sustainable development. This programme embeds equity as a core design principle, explicitly prioritising gender equity and broader inclusion at every stage. For example, DELTAS has implemented targeted measures to close gender gaps, resulting in nearly 50% of fellows being women and 41% of first-authored publications led by women. Similarly, initiatives such as the Research and Innovation Systems for Africa (RISA) Fund under ATIP and Research and Innovation for Development in ASEAN (RIDA) in Asia have introduced dedicated funding streams and mentorship for female innovators, enabling them to launch startups, access markets, and create pathways for entrepreneurship and economic empowerment. By intentionally directing resources to women, early-career researchers, and institutions in less-resourced regions, we ensure that inclusion and equity are not by-products but drivers of systemic change, fostering diverse leadership and innovation ecosystems across Africa and Asia.
4. Driving cross-regional learning. A targeted influencing strategy will ensure programme delivery is aligned with diplomatic priorities in FCDO priority countries, amplifying both impact and visibility of UK interventions. Cross-regional learning across Africa and Asia will serve as a mechanism to test, adapt, and refine interventions, supported by structured review cycles (e.g., bi-annual) to recalibrate activities - adding, adjusting, or discontinuing as evidence dictates.
5. Building foundations for long-term impact. Beyond outputs, the programme will create infrastructure for future trade, innovation, and policy reform, opening opportunities for UK businesses and researchers. Initiatives like AISDA, RIDA, and Sankore show how locally grounded research drives policy change and innovation while strengthening S&T systems. ATIP’s success – such as Kenya’s research commercialisation guidebook and Nigeria’s Innovation Action Plans - has attracted co-investment and integrated innovation in government planning. Launching investment vehicles like Ci-Gaba Fund of funds and the Nigeria’s Wholesale Impact Investment Fund (WIIF) has leveraged domestic capital for S&T. Also, FCDO’s leadership in forums like International Research for Development Funders Forum (IRDFF) ensures sharing of best practice and partner engagement.
Measuring impact. The programme aims to deliver systemic change - stronger institutions, coherent policies, and future markets benefiting development and UK interests. We will embed systemic change measurement from inception hence monitoring, learning and results tracking will be central. SS4ST will prioritise high-impact interventions based on evidence and theory, while generating new insights on what works during the implementation.

Assurance of compliance with UK Law
Gender Equality and Public Sector Equality Duty: This programme will comply with UK Gender Equality Act and Public Sector Equality Duty by ensuring equitable S&T systems that provide access opportunities, resources and design-making for all genders and backgrounds. During inception, stakeholder consultations and in-country analyses will identify barriers and inform interventions that address gender and other exclusions, such as age, disability and socio-economic status.
The programme will generate evidence on what works for S&T system strengthening, including how gender and other intersecting factors - such as age, disability, ethnicity, and socio-economic status - affect access to, participation in, and outcomes around S&T solutions. This will guide targeted approaches to ensure equitable benefits. SS4ST will ensure equality of opportunity throughout all levels of its delivery and will actively avoid negative impacts related to age, disability, gender reassignment, pregnancy and maternity, race, religion or belief, sex, and sexual orientation, in line with the Gender Equality Act and the Public Sector Equality Duty. We will include women, youth, and other marginalised groups in processes that strengthen accountability in government, ensuring their voices are heard and needs addressed.
The new phase of SGCI will build on previous success in mainstreaming gender equality by further supporting Science Granting Councils to integrate gender and inclusion across all aspects of their grant-making and research processes. Building on initiatives such as Kenya’s award-winning Gender, Equity and Inclusion (GEI) framework and Ghana’s ‘3Fs’ (funding, functionality, and fairness) approach, the programme will expand best practice, strengthen institutional policies, and promote women’s leadership in science, technology, and innovation across Africa.

Counter terrorist financing: The risks of terrorist financing in this programme are low and acceptable. A thorough risk management framework will be applied to all partner staff recruitment and downstream partner selection. In addition, GSD will ensure all implementing partners are aware of UK Counter Terrorism legislation; due diligence and audit of all downstream partners; and inclusion in all down-stream partner agreements and contracts, and details of their obligations of all relevant terrorism legislation (and a recorded audit trail). Reporting of any suspicions to the Counter Fraud and Whistleblowing Unit and National Crime Agency will be prioritised.

Climate and environment: At least 25% of the portfolio will contribute to International Climate Fund (ICF) commitments. SS4ST commits to be rooted in “Do No Harm” approach to nature in order to ensure compliance with the Green Finance Strategy criteria of the Paris alignment. The programme will not invest in fossil fuel-based energy generation or other activities that may undermine efforts to reducing carbon emissions.

Partnership principles: Implementing partners will work in partnership with line ministries, departments and agencies. It is expected that technical support will be offered through some of the supported interventions. As part of FCDO’s ambition to deliver aid directly in-country, direct payments to National Research Funds within national governments will be explored. This will provide a pilot with a view to FCDO’s thematic R&D funding and other UK R&D being disbursed in this way in future. We will follow HMG Partnership Principles and guidance on working with Government.

Disability: The programme will contribute to implementation of the FCDO Disability Inclusion Strategy. This includes ensuring persons with disability are not excluded from programmes, and that proactive measures are taken by GSD and partners to maximise inclusion.

Safeguarding: The programme will adhere to HMG’s safeguarding policies, referenced under Contract Condition 50 in FCDO’s standard terms and conditions for suppliers and within the Code of Conduct Annex. During the mobilisation phase, GSD will conduct enhanced Due Diligence assessments of all proposed implementing partners. First tier implementing partners will work closely with FCDO to ensure that any downstream implementing partners are compliant with the safeguarding rules. Application and monitoring of these policies will be regularly reviewed and tested throughout the programme lifecycle.

## B. Appraisal Case

The Strategic Case establishes that FCDO has a proven track record of delivering high-impact interventions across Africa and Asia, demonstrating that equitable S&T partnerships and strong governance frameworks build resilient systems, attract investment, and drive innovation. Yet, a critical gap remains: without a systems-oriented programme that integrates research generation, science leadership, and institutional strengthening, early gains risk stagnation. To achieve the SDGs and unlock the full potential of Global South S&T ecosystems, we must act now. This strategic investment offers a unique opportunity to consolidate progress, scale success, and continue to position the UK as a global leader in shaping connected, sustainable S&T systems.

Delivery options appraisal

The approach to the appraisal case is structured as follows:

This section considers the following three (3) delivery options:
1. A counterfactual option of ‘doing nothing’
2. Continuing with a business as usual (BAU) approach of multiple, separate programmes focussing on different levels on systems strengthening that are individually designed, developed, and governed/ managed by different GSD teams
3. A single substantial ‘platform’ programme by integrating components across Africa and Asia implementing activities relating to systems strengthening – recommended approach.

These are elaborated briefly below:

Option 1: Do nothing – the counterfactual
In this case FCDO would complete current programmes but launch no new initiatives to strengthen S&T systems in the Global South. Existing programmes would end after April 2026, delivering short-term benefits; but risking long-term sustainability as trust-based networks erode UK influence declines. S&T, policy and capacity strengthening in Africa and Southeast Asia would have also lose valuable input from African stakeholders, reducing cross-regional learning and impact.

While technically feasible, a ‘do nothing approach’ is not considered further given the combination of:
1. High demand for UK engagement from partners in Africa, India and Southeast Asia
2. Decadal partnership and impact
3. Significant match funding already leveraged
4. UK Science Minister’s support for S&T systems strengthening for ODA R&D
5. Current UK leadership and expertise in S&T systems strengthening globally
6. Unlikelihood of other funders replacing UK leadership in this area

Option 2: Deliver on strategic goals through existing programming (BaU)
This BaU approach would entail extending or developing a new set of parallel programmes focussed on different levels of systems strengthening to replace current ones ending in March 2026. These would need to be individually designed, developed and managed. This involves increased staff resources and administration, potential duplication of functions across the projects and reduces ability to drive synergies in research and uptake across the programme, effectively acting as stand-alone entities unconnected to each other with separate monitoring and evaluation (M&E), annual reviews and financial management. Separate business cases would need to be developed for each. Fragmented delivery would constrain systemic impact, fail to meet partner demand for a holistic approach, reduce UK visibility and miss opportunities for cross-learning to inform FCDO approach and S&T policy. This would not respond to demands from LMIC partners to design a programme that covers systems strengthening from a more holistic and multi-modal perspective.
Option 3: Design a single programme encompassing all components [Recommended]

This option would consolidate most of the existing FCDO S&T system strengthening portfolio and new initiatives into one overarching programme, enabling a multi-layered approach to system change. A sharper focus on HMG priorities in a 0.3 world will exclude innovation systems strengthening and direct funding to test and scale individual innovations which will be addressed in a limited capacity by thematic R&D programming across government. A ‘framework’ programme, with a single management approach and governance, Theory of Change, Logframe, and risk framework will improve agility enable greater impact at scale and build up a potentially more sustainable host or home for the research in the long term. The programme will allow flexibility to adapt to emerging issues, support localisation, and increase impact of research initiatives via economies of scale. A common set of portfolio-wide supporting functions (MEL knowledge management, communications, etc.) will facilitate learning across the portfolio. This is the preferred option.

Assessment of feasible delivery options

Table 1 below summarises the criteria used to assess the delivery options including:

1. Deliver on FCDO’s vision to position the UK as a modern development actor, build new partnerships, and drive UK growth through supporting sustainable, inclusive markets
2. Deliver rapidly, ensuring funding is disbursed quickly and efficiently and impacts are achieved over a short to medium-term time horizon
3. Focus on FCDO priority geographies, leveraging local institutions
4. Deliverable within GSD staffing levels with minimal risk
5. Offer flexibility to adapt and respond to opportunities
6. Ensure strong VfM
7. Align with UK Government policy objectives on development, and S&T (as set out in our new approach to development, the S&T Framework, and the Industrial Strategy and Trade Strategy)
8. Potential for cross-programme learning.

Table 1:
1 = poor fit against the criteria – not recommended
Raw score: 1-5
Weighted score (1-5) (Raw score x Weight)
Weight: 0-1

2= partial fit to criteria
3= moderately good / acceptable fit against the criteria
4= good fit to criteria
5 = strong fit to criteria

Criteria	Weight	Option 1: / Do nothing	Option 2: Multiple programmes	Option 3: / Single programme
Delivering on all addressable aspects outlined in FCDO’s vision	0.20	0.20	0.60	1.00
Delivering efficiently through channels that have a strong track record, and impacts are achieved over a short to medium-term time horizon	0.15	0.30	0.45	0.75
Delivering in FCDO priority geographies, leveraging local institutions and capacity	0.15	0.30	0.60	0.75
Can be delivered effectively and with minimal risks within GSD’s current staffing levels	0.15	0.30	0.60	0.75
Approach affords flexibility and adaptability in programming and decision making and ability to quickly respond to opportunities	0.10	0.20	0.30	0.40
Delivering effective Value for Money	0.10	0.20	0.40	0.40
Alignment with FCDO policy objectives on Development and S&T	0.10	0.20	0.30	0.50
Potential for cross-programme learning	0.05	0.10	0.15	0.20
Total	1.00	1.80	3.40	4.75

Proposed delivery option: Table 1 above summarises a Multi-Criteria Analysis (MCA) of appraised options using criteria derived from the programme’s objectives. Each criterion is weighted (0–1) to reflect its relative importance, with higher weights assigned to factors such as strategic fit, impact potential, and leveraging opportunities, compared to operational considerations like flexibility and risk. Options are scored on a scale of 1–5 against each criterion, and weighted scores are calculated by multiplying raw scores by their respective weights.

Options 2 and 3 outperform Option 1 (the counterfactual) across all criteria. For strategic fit (Criteria 1 and 2), Option 3 scores significantly higher than Option 2, reflecting its stronger alignment with FCDO’s vision and strategy, particularly in development and S&T. On value for money (Criterion 7), Option 3 again leads, due to its ability to pool economies of scale across programme strands and enhance overall coherence. For impact potential, leveraging, and risk mitigation (Criteria 3–5), Option 3 maintains an advantage over Option 2, offering greater likelihood of delivering short- and medium-term results, mobilising additional resources, and strengthening local institutional capacity. Both Options 2 and 3 score equally on flexibility and adaptability, though both outperform Option 1. MEL (Criterion 8) is strongest under Option 3, as integrating all three strands creates greater opportunities for cross-programme learning and continuous improvement.

Recommendation: Based on the MCA, Option 3 is the preferred delivery model, offering the highest strategic alignment, value for money, and potential for impact at scale. Hence, funding a single programme that brings together all implementing activities relating to systems strengthening is the recommended option.[11]
[11] The associated risk mitigation of the selected option is provided in the management case.
Evidence increasingly demonstrates that portfolios of interventions deliver greater flexibility, efficiency, and impact compared to standalone efforts. SS4ST builds on a suite of mature predecessor initiatives in S&T systems strengthening that have previously operated in isolation. By adopting an ecosystem approach, the programme aligns with FCDO’s new development strategy and responds to growing interest from external partners - enabling transformative impacts across geographies at scale.

This programme is designed to elevate collaboration to the next level - facilitating learning and adoption at a portfolio level across Africa and Southeast Asia. It will generate new value by engaging a broader spectrum of stakeholders, including from the private sector. The scale of SS4ST also creates opportunities for risk diversification and accelerates innovation, delivering efficiency and effectiveness gains that smaller, fragmented initiatives cannot achieve.

Programme description
The programme will work to create the desired impact – Inclusive, locally led, and responsible science and technology ecosystems to tackle development challenges, enhance quality of life across Africa, Southeast Asia, and beyond, and drive shared global prosperity – through three main components:

Table 2: High-level summary of SS4ST delivery model and funding

Component	Implementing Partners	Potential Co-funders
Component 1: / Science Granting Councils Initiative / FCDO indicative budget £4m	IDRC (£5m)	Wellcome (£9.7m) / Norad (£9m) / SIDA (£2.2m) plus contributions from Govt departments
Component 2: / Strategic Partnership with Wellcome / FCDO indicative budget £8m	Africa: Wellcome + SFA / SE Asia: Wellcome + SEAMEO	Wellcome indicative budget £169m plus contributions from Govt departments
Component 3: / Responsive, country-level S&T programming / FCDO indicative budget £5.3m per Hub	Local suppliers, competitively procured	Partner governments, regional multilaterals like ASEAN, private sector

Component 1: Science Granting Council System Strengthening
This component will be delivered through the pan-African Science Granting Councils Initiative (SGCI) – delivered in partnership with IDRC (Canada), SIDA (Sweden), NORAD (Norway) and Wellcome. The research is delivered through the Science Granting Councils (SGCs) in 18 countries across Africa responding directly to local needs. FCDO has previously provided £2 million for 81 research projects delivered through SGCs, strengthening research delivery and increasing collaboration across national and linguistic borders. The investment delivers research outputs to strengthen evidence-based policy making and build wider institutional capability e.g. improved crisis response as demonstrated through the COVID-19 pandemic, or advancing gender equality through implementing formal gender and equality frameworks such as Ghana’s “3Fs” model and Kenya’s National Research Fund’s award-winning strategy on Gender and Inclusion. To date, SGCI has supported the development of 18 SGCs - national science funding councils - and developed enduring UK-Africa partnerships, increasing African led S&T investment and equitable UK research partnerships across Africa. FCDO’s investment is expected to be matched by approx. £5M from partner government domestic financing, and £26M from other donors.
In its next phase, SGCI will shift from capacity building to positioning Councils’ as regional and global leaders in S&T systems, exemplified by Côte d’Ivoire co-chairing the Global Research Council. A key innovation is the SGCI Alliance - a Councils-led structure - that reflects the evolution of the initiative and the increasing maturity of Africa’s Councils and S&T systems. Through the Alliance, SGCI-3 will establish new mechanisms that enable the Councils to significantly influence the direction and deliverables of the initiative alongside increased engagement with policymakers, development partners, private sector, civil society, regional and global S&T fora and organisations. Consolidating progress made over the last decade, this phase will shift from a primary focus on capacity-building to even greater focus on research collaboration, promoting African-led leadership in S&T, and contributing to sustained investment and stronger S&T systems across Africa.

## Component 2: Strategic partnership with Wellcome
This component will be delivered through a strategic partnership with the Wellcome to support pan-regional S&T consortia across Africa and Southeast Asia that deliver high-quality outputs, strengthening science leadership and institutional capability and excellence, supporting the professionalisation of S&T management in priority areas in health and climate.

This strand is based on the existing DELTAS programme, which has strengthened S&T systems across Africa, unlocked funding, and advanced African science leadership through UK partnerships. Delivered via Science for Africa (SFA) Foundation, and research consortia, DELTAS’ achievements include discovering an Omicron variant in Botswana, launching Kenya’s first PCR testing facility and the world’s first MSc in Antimicrobial Resistance launched in Mali by DELTAS researchers. Lessons show development accelerates when S&T systems are locally led and globally connected. The hub-and-spoke model, now inspiring replication in Southeast Asia, demonstrates how coordinated investments sustain capacity and enable cross-border innovation. SFA led a high-level session at the UNGA science summit 2025, drawing on the DELTAS model of co-leadership, equitable collaboration, and long-term investment in Africa’s science systems which are helping to position Africa’s science ecosystem as a driver of global resilience. DELTAS has leveraged 10x Wellcome funding and 3x from other donors, positioning Africa as a global science leader.

Under DELTAS phase 3, FCDO will partner with Wellcome to advance priorities including climate and health, and expand GFGP and GRMP standards, with potential roll out to SGCs. Key innovations include: a maturity framework, with tiered support for consortia at emerging, developing, and mature levels; sustainability and co-financing through matching-fund mechanisms with African governments and institutional co-funding requirements; equity and inclusion through consideration of gender, language, geography, and career stage, and science–policy integration through enhanced mechanisms for policy fellowships, science diplomacy, and community engagement. These measures will ensure sustainability, reduce aid dependency and maximise inclusion.

SEA-DREAM will build on Africa’s regional experience to deliver transformative impact in Southeast Asia. It will fund regional consortia through open competition to generate globally excellent, outcome-focused research addressing national, regional and global health and climate priorities. Its systemic approach will strengthen research excellence and equitable ecosystems – nurturing leaders, breaking barriers to collaboration, and translating research into real-world solutions and policies. Bespoke leadership pathways for researchers from Low- and Middle-Income Countries (LMIC), combined with mentorship and stakeholder engagement, will ensure evidence and innovations drive progress on SDGs. Within four years, SEADREAM will: (i) establish research consortia generating new evidence on health/climate; (ii) establish multi-country collaboration, including lower-resourced nations, building equitable ecosystems; (iii) improve communication with national, regional, and global stakeholders to disseminate research; (iv) expand research career opportunities across Southeast Asia; and (v) translate research into policy and practice.
## Component 3. Responsive, country-level S&T programming

This component delivers country-led, demand-driven S&T programming that is agile and tailored to local contexts. Through two streams: (a) basic research for new knowledge and evidence, and (b) applied research for actionable policy insights – it tackles barriers to nationally owned S&T ecosystems. By aligning outputs with real-time policy needs, it strengthens technical and institutional capacity, accelerates uptake, and positions the UK as a trusted partner in building resilient, future-ready S&T systems.

This component draws on collaboration between GSD teams across Africa and Asia, partner governments, and lessons from past UK and regional programmes. Examples include RIDA, the first R&D initiative to secure ASEAN accreditation, that strengthened the regional research ecosystem in Southeast Asia by bringing in the private sector, and AISDA, highlighted by ASEAN as “a pioneering AI project under the ASEAN AI framework”. In Africa, our work with Kenya’s National Innovation Agency (KeNIA) supported the development of Kenya’s 10-Year Innovation Masterplan, including a new national R&D policy integrated into their STI framework, alongside transferring the UKs approach to innovation clusters and creating UK / Kenya clusters on biosciences and green tech with Oxford University and Imperial College London. In Ghana we supported the drafting of the Legislative Instrument to bring the National Research Fund Act into full effect alongside providing support to draft and implement governance mechanisms and operational procedures.

This component is designed as a ‘menu’ of different possible activities that can be selected, tailored and adapted to the specific needs identified within HMG Country Business Plans, S&T G2G bilateral agreements, and strategic partnerships. A strong emphasis of this component is on using GSD’s regional networks and expertise to ensure we are listening to and consulting with key stakeholders, taking time to understand the specific contexts in which we operate, and ensuring solutions are co-created in partnership with host country institutions – whether government, academia, civil society organisations, or private sector – promoting greater collaboration, addressing fragmentation and catalysing change.

This component will form part of the UK’s proposed Technology Centre for Expertise, providing local insights and connections that complement UK capabilities - delivering high-impact, sustainable outcomes for both the UK and our partners.

Proposed interventions under this component will focus on two strategic pillars - ‘Building’ and ‘Leveraging’ - the essential building blocks of systemic change. Through ‘Building,’ we will strengthen locally owned S&T systems, creating the foundations for sustainable innovation. Through ‘Leveraging,’ we will unlock the UK’s full suite of assets - world-class expertise, advisory capabilities, programmes, and global networks - to accelerate impact. Together, these interventions will deepen UK–partner country partnerships, drive inclusive growth, and position science and technology as a catalyst for long-term prosperity.

The activities outlined below will be tailored to each country’s unique context and S&T ecosystem, following a rigorous, collaborative assessment and aligned with existing UK commitments. These activities span a broad spectrum, including:

1. Knowledge generation and evidence building: Map S&T landscapes, develop open-access data platforms and repositories, pilot innovative data tools, generate insights and foresight to inform policy, practice and programming. Key outputs: Landscape maps highlighting gaps and opportunities, digital collaboration platforms, open data repositories, bespoke data tools, and evidence reports
2. Government-to-Government bilateral partnerships and strategic engagement: Advancing S&T policy, implementing joint frameworks aligned with UK and national priorities, and fostering regional collaboration for diplomatic benefit. Key outputs: Policy frameworks, policy dialogues, agreements on regulatory standards, collaboration platforms, and joint research for policy development
3. Technical assistance and capacity building: Establish S&T thematic clusters (e.g. global health, climate, AI, digital economy), deliver training and mentoring, facilitate peer learning embedding UK expertise. Outputs such as: Training modules, mentoring toolkits, and peer learning portals
4. Partnership and network building: Create equitable UK-partner collaborations through S&T networks, forums, thematic groups, and knowledge-sharing platforms. Key outputs: bilateral S&T agreements, networking platforms, and partnerships with emerging market economies such as India leveraging its innovation and entrepreneurship strengths for joint initiatives in third countries, including in Africa[12]
  [12] By leveraging the UK's advanced research capabilities and India's cost-effective innovation and implementation experience, the partnership can deliver scalable solutions to Africa's development challenges. This collaboration will enhance the UK's global influence, open new markets for British businesses, and support sustainable growth in Africa, aligning with UK priorities on prosperity, climate, and health. Investing in this partnership positions the UK as a leader in inclusive, future-focused international development, while fostering stronger diplomatic and trade ties with two of the world’s fastest-growing regions.
5. Harnessing UK expertise and market actors: Coordinate access to UK technical assistance, research, finance, and co-financed projects. Key outputs: Joint research infrastructure, policy advisory platforms, co-created intellectual property, and market access toolkits
6. Monitoring, Evaluation & Learning (MEL): Develop shared robust MEL systems to generate insights and facilitate regional learning and exchange. Key outputs: MEL toolkits, knowledge exchange platforms, and impact reports
Leveraging the UK’s scientific strengths, technical expertise, global networks, and convening power, these initiatives will: (a) strengthen strategic government-to-government partnerships, (b) build local research capacity, including in government systems, and (c) foster knowledge exchange across regions.

Collectively, they will drive uptake of research, evidence-based policy influence, pan-regional learning, and amplify UK investment and influence. Critically, this work will equip countries to anticipate and manage technological disruptions, ensuring resilience and inclusive growth.

This pillar enables GSD teams to respond swiftly and flexibly to requests from in-country partners - including partner governments and research institutions - beyond regular programming cycles. It ensures agility in advancing UK diplomatic objectives and strengthening influence in FCDO priority countries. The activities and partnerships will be firmly anchored in national and regional priorities, such as the national STI policies of Ghana, Nigeria, and the ASEAN Plan of Action on STI (APASTI), as well as agreements/MoUs between UK and national governments and regional entities, such as the UK-South Africa Science MoU, UK–Ghana Science, Tech & Innovation Strategy, UK-Kenya Strategic Partnership, UK-India Research and Innovation Partnership MoU, and the ASEAN-UK Plan of Action. Building on proven successes, such as the partnership with KeNIA, this approach strengthens trust, accelerates impact, and positions the UK as a responsive, strategic partner in shaping innovation ecosystems.

Proposed implementation option

For Component 1, IDRC has been identified and is proposed as the key partner on SGCI. IDRC invests in knowledge, innovation, and solutions to improve the lives of people in the developing world. Created by the Canadian Parliament, IDRC funds high-quality research across the Global South, fosters collaboration across national borders, and encourages the application of knowledge to further development goals. IDRC is a public corporation reporting to the Canadian Parliament through the Minister of International Development and their financial systems are audited annually by the Auditor General of Canada. On delivery and management of research, specifically:
- IDRC has the expertise on research management and governance research, talent and skills and data, and has a strong foundation and regional networks across both Africa and South and Southeast Asia. A 2022 due diligence report by FCDO on IDRC found that current net risks were all minor across the main pillars.[13] FCDO has substantial experience working with IDRC which has a track record dating back to at least 2009-10, with payments totalling over £117 million.
  [13] DDA-0922-IDRC-Global Science Department-301049.docx
- IDRC financial management systems and procedures are assessed as very strong and as a Crown Corporation of the Government of Canada, IDRC’s financial stability is rated as excellent.
- IDRC has substantial experience in managing downstream delivery partners, significantly underpinned by both technical and administrative regionally based staff able to engage directly with implementation partners.
For Component 2, FCDO has a long and successful track record of joint research with Wellcome through two modalities a) co-funded programmes where Wellcome also acts as the research Fund Manager, and b) co-funded programmes where a third-party acts as fund manager/implementing partner. FCDO and Wellcome are currently in the process of finalising a new FCDO-Wellcome Collaborative Strategic Partnership. This process has shown substantial equivalence between FCDO and Wellcome systems, norms and procedures, so that there is not a requirement to undertake separate due diligence at individual project level. It has also confirmed that Wellcome has strong and tested governance and financial management controls.

For Component 3, we will work directly with partners across the Global South, with a focus on Africa, India (through regional/global partnerships) and Southeast Asia. A single supplier model would limit the ability to leverage existing regional networks essential for effective localisation; therefore, regional suppliers will lead implementation. Most activities will be delivered through non-commercial implementing partners, selected via competitive calls for proposals using proven, globally recognised processes that ensure value for money and adherence to best practice.

This approach provides FCDO with greater programmatic control over individual activities under the component and ensures an optimal combination of technical expertise and regional knowledge required for projects that require decentralised delivery. It also positions FCDO to take a more prominent leadership role in shaping research and innovation ecosystems globally.

Theory of Change

SS4ST is designed to deliver impact through a coordinated portfolio of programmes and projects under a unified strategic framework. Recognising the complexity and diversity of its components, the programme employs four distinct Theories of Change (ToC), each tailored to a specific component. These individual ToCs converge within an overarching structure (see Fig 2), providing a clear strategic vision while enabling flexibility to assess outcomes through multiple perspectives. Detailed ToCs are included in the Annex:

- SGCI Phase 3 specific ToC (Annex 1)
- DELTAS Africa specific ToC (Annex 2)
- SEA-DREAM specific ToC (Annex 3)
- Responsive, country-level S&T programming ToC (Annex 4)

This integrated approach ensures coherence across interventions, maximises synergies, and strengthens the pathway to achieving transformative S&T outcomes at scale. While each component follows its own set of activities, outputs, and impact pathways, they are strategically aligned and mutually reinforcing - collectively driving progress toward shared high-level outcomes:
1. Vibrant, sustainable, and nationally-led S&T ecosystems that foster the growth and scaling of transformative research and development[14]
  [14] For each component, indicators will be established, and achievement of milestones monitored and reported against during Annual Reviews
2. Strong national ownership and leadership in S&T, with countries prioritising the ethical and effective use of research and emerging technologies
3. Enhanced UK contribution to, and benefit from, national S&T advances in partner countries, driving growth and shared prosperity

By reducing barriers to S&T commercialisation, the programme will boost social and economic impact, safeguard national interests, and attract sustainable investment. Strengthened local capacity and ownership will enable partner countries to drive their own S&T agendas, positioning them as leaders in innovation and development.

The programme prioritises long-term results over short-term activities, contributing to:

Impact: Inclusive, locally led, and responsible S&T ecosystems that tackle development challenges, enhance quality of life across Africa, Southeast Asia, and beyond, and drive shared global prosperity.

A summary diagram of the programme-level Theory of Change is presented in Fig 2 (next page):

Inclusive, locally led, and responsible science and technology ecosystems to tackle development challenges, enhance quality of life across Africa, Southeast Asia, and beyond, and drive shared global prosperity
IMPACT
Strong institutions produce and support uptake of high-quality, relevant and impactful research
Collaborative cross-sectoral partnerships successfully scale locally and nationally developed S&T products and services
Favourable policies, evidence-informed strategies and practices support improved investment and commercialisation capacity
OUTPUTS
FUNDING
Multi-year funding from FCDO + co-investment from partners

INPUTS
HUMAN CAPITAL
FCDO Advisers + programme managers
PARTNERSHIPS
Collaboration with partners, engagement with govts., regional
fora
SGCI
DELTAS
SEA-DREAM
Country-led demand responsive programming
COMPONENTS
Strong national ownership and leadership in science and technology, with countries prioritising the ethical and effective use of research and emerging technologies
Vibrant, sustainable, and nationally-led science and technology ecosystems that foster the growth and scaling of transformative research and development
OUTCOMES
Enhanced UK contribution to, and benefit from, national S&T advances in partner countries, driving growth and shared prosperity

Key Assumptions
- FCDO and key partners (Wellcome, IDRC) agree overall approach and delivery plan, aimed at influencing both S&T systems and development impact
- FCDO continues to prioritise working increasingly with local actors through equitable partnership
- FCDO commitment to move from service delivery to system support, helping countries build their own S&T and education systems so they can thrive without aid, is maintained
- FCDO continues to prioritise health, climate & nature, and mutual prosperity as thematic priorities where we can drive real change
- Policy and legislative environment facilitate strong research ecosystems across Africa and Southeast Asia
- Research agencies and governments commit to collaborate regionally/globally and prioritise S&T aligned with national/regional priorities
- Stronger research systems lead to enhanced access to local, regional and global research
- Researchers across Africa and Southeast Asia generate proposals with high potential to drive sustainable development
- Value of research for development is uncontested

At the impact level, the programme aligns with ambitions set by partner governments and regional bodies such as the African Union (AU) and ASEAN, as articulated in their Science, Technology, and Innovation strategies. These strategies aim to harness S&T to drive sustainable development, economic transformation, and regional integration, supporting inclusive growth, resilience, and transition to a digital, innovative, and sustainable future.

The MEL component of the programme will strengthen frameworks and metrics to capture impact-level change, drawing on best practices and ongoing regional learning (including OECD, AU, and ASEAN) to measure the strength of S&T systems in the Global South.

Through a combination of the three components, the programme will help catalyse:
- At least 300 new R&D partnerships funded leading to new evidence produced on priority sectors
- At least 50 bilateral and multilateral S&T initiatives e.g. policy dialogues, supported across Africa, India and SE Asia
- At least 2000 early career researchers supported
- Improved research call and grant management systems, including peer review, MEL systems etc.
- At least 50 improved S&T frameworks e.g. GESI, research excellence, open access, intellectual property management, etc.
- Improved capacity to provide training and mentorship support to potential grantees
- Increased co-funding calls funded through national funding and partnerships.
- Increased research and innovation projects with a % led by women, youth and persons with disability
Leading to:
- At least 1000 new peer-reviewed publications
- At least 50 research-based innovations commercialised or adopted at scale
- At least 50 Global South researchers who establish themselves as thought-leaders, recognized in global science or policy fora, national or international awards, or publishing in top-tier journals
- At least 100 documented cases of influencing national or international ST&I policies
- At least 50 institutions across Africa and Southeast Asia with strengthened research, science, and tech management operations.
- At least 30% of supported researchers, innovators, or institutions demonstrate significant progress in advancing Gender Equality and Social Inclusion (GESI) through their work or organisational practices.

The programme is structured around a four-month inception phase followed by an implementation phase. The inception phase will further define governance structures, processes, procedures, staffing, ways of working and research themes.  Managing the programme in such a way provides a mechanism to test the effectiveness of inputs and delivery of outputs, as well as assumptions, thus enabling refinement over time.

Value for Money

Research in general is assessed as being a cost-effective intervention because it creates global public goods that can influence and leverage considerable levels of investment by other parts of HMG more broadly as well as development partners and the private sector. Haskel et al estimate total public Research and Development spending yields a social rate of return of around 20%.[15]
[15] Haskel et al, 2014. Economic Significance of the UK Science Base https://www.rsc.org/globalassets/04-campaigning-outreach/policy/research-innovation/economic-significance-uk-science-base-2014.pdf

This programme delivers strong Value for Money (VfM) by investing in strategic, locally led sustainable S&T ecosystems in partner countries. The programme brings together three mutually reinforcing components into one coherent programme that will share administrative resources and costs, ensuring these are targeted towards mutually beneficial outcomes and long-term systemic change.

Partnering with Wellcome and IDRC brings good VfM (ensuring economy) to UK ODA. Our strategic partnerships across Africa and Southeast Asia will leverage significant match funding of approximately £200 million over a 4-year period from philanthropies, development partners, partner governments, and private capital sources.

A key objective of the SS4ST programme is to ensure research is more problem and user-focused, better tailored to demand and more likely to result in improved uptake by users at local, national and international levels. GSD will work across with government partners, focusing on the weakest links in order to deliver mutual reinforcement between different initiatives and therefore improved impact and VfM. This aims to lead to higher use (efficiency) as well as greater and more effective user uptake (effectiveness).

SS4ST will adopt a portfolio approach, which has several advantages:
1. Enhanced Coordination and Learning: This approach prioritizes collaboration and lesson-sharing across initiatives, enabling rapid adoption of proven strategies throughout the portfolio.
2. Integration of Legacy and Best Practice: By building on the achievements of previous systems-strengthening programs, SS4ST will incorporate successful practices and leverage promising results to identify priorities for scale-up
3. Leveraging Networks and Expertise: It creates opportunities to draw on diverse teams, institutions, and partners, fostering innovation and strengthening the overall impact.
4. Balanced Risk Management: A portfolio approach allows for a mix of initiatives, including high-risk, high-return projects, while maintaining overall stability.
5. Value Chain Engagement: It ensures coherent and coordinated action across the entire value chain, improving the translation of research into tangible impact.
6. Economies of Scale: Consolidating core programme management and administrative functions reduces costs and improves operational efficiency.
7. Integrated Monitoring, Evaluation, and Learning: A unified approach to M&E enhances lesson-learning and accelerates uptake of successful interventions.

Monitoring and Evaluation

Within SS4ST, a range of VfM measures will be applied to assess the interventions and monitor progress through reporting and annual reviews. We will measure success by research outputs and policy influence, innovations adopted and scaled in LMICs, capacity built in partner institutions, the strength and longevity of partnerships, the UK’s global leadership and soft power, and funding leveraged into research partnerships. The following initial measures are proposed, using the ‘Five Es’ Assessment with some more applicable for certain delivery routes than others.

Economy: Achieving the desired outputs at the lowest possible cost without compromising quality.

- Two main delivery channels managed by tried and tested like-minded partners have been pre-identified, Wellcome and IDRC. Both have established governance and administrative procedures, and the arrangements will be formalised through separate MoUs. Partnerships with established local entities such as the SEAMEO, SFA, regional multilateral bodies such as ASEAN, and bilateral governments will reduce risks of duplication and maximise effective resource allocation
- The programme leverages both co-investment and UK expertise from a diverse range of partners (in the UK and in partner countries) including government, private entities, industry and beyond, ensuring cost-effective use of resources
- Competitive selection of delivery partners for the country-level component will ensure efficiency and cost-effectiveness, with supplier bids explicitly including clear VfM criteria
- The FCDO team will provide in-house monitoring and evaluation expertise through a dedicated programme funded post

Efficiency: The efficiency of the programme is how well it uses the inputs to create outputs that are relevant and cost effective, ensuring resources are used optimally.

- The programme-level ToC aligns the four component-level ToCs showing how these will deliver on shared outcomes and impact, aligning project activities and outputs for mutual reinforcement and streamlining
- Adaptive and responsive country-led interventions will ensure that resources are directed to locally relevant priorities, minimising overheads and wasteful expenditure
- Strategic partnerships with like-minded stakeholders will enable resource pooling, minimise duplication, and create opportunities to catalyse co-financing and follow-on investments - fostering co-ownership and long-term sustainability
- Rigorous MEL frameworks and deployment of internal expertise from GSD teams will enable ongoing assessment of cost and VfM and adjustment of programming to course correct and mitigate risks, improving operational efficiency
- Monitoring measures will include regular assessment of unit and delivery costs, quality of skills and research capacity, strength of collaborative partnerships, and the value of learning generated and effectiveness of Technical Assistance and networking activities.

Output targets in the Logframe will be calibrated against other programmes to ensure that the consortia are delivering good VfM in terms of outputs per pound spent (recognising that costs per output vary significantly depending on the nature of the output).

Effectiveness: This considers whether the outputs have produced effective outcomes. This will be monitored in the medium term via the Outcomes in the Log frame and ToC.

- The programme is designed to deliver long-term, sustainable outcomes that will outlast the duration of delivery of the activities. These include vibrant, nationally led S&T ecosystems, strong national ownership, and enhanced UK S&T partnerships with Africa and Asia. Additionally, the programme will be guided by local stakeholders and partner governments and regional institutions such as the AU and ASEAN in their Science, Technology and Innovation strategies
- Through its focus on reducing barriers to research commercialisation the programme will maximise the social and economic impact of research investments in Africa and Asia
- By working at systems level, strengthening local capacity for and ownership of S&T, SS4ST will enable partner countries to drive their own S&T agendas, ensuring lasting change
- Monitoring measures will include, leveraging of co-financing from development partners, partner country governments, private sector and other sources of capital, attraction of funding and staff to research institutions, and influence on policy and enabling environments.

Equity: This considers whether the effective outcomes are distributed evenly across various subpopulations including marginalised groups and LMIC researchers. A key contributor to ensuring equity is SS4ST having beneficial outcomes and impact for LMIC partners, women and marginalised groups. These will be factored into the Logframe targets.  Engagement of women and LMIC researchers in delivering the research itself is another important aspect of equity. Countries across the African continent and Southeast Asia are at different levels of economic development. Involvement of lower resource countries in originating and delivering research leads to enhanced consideration of their needs and requirements within the outputs, as well as providing evidence that the programme is engaging these groups in delivery.

- The programme will include a specific focus on ‘inclusive S&T’ ensuring that the initiatives we support actively involve underrepresented groups (particularly women, youth, persons with disabilities and rural communities) in the development and application of new scientific knowledge and solutions, both as researchers, as well as beneficiary groups, ensuring that advancements benefit all groups in line with FCDO’s commitment to the SDGs and leaving no one behind.
- All activities within this programme will be based on active stakeholder engagement, and co-creation with local governments and other stakeholders to ensure that benefits of S&T reach marginalised and underserved populations. Programmes for equitable access and support for developing countries help future-proof national interests and foster shared prosperity.
- Monitoring measures will include disaggregation of beneficiaries by gender, income, and geography and disability where possible, inclusion of marginalised groups in engagements, and equitable access to new technologies and business models.

Finalisation of Logframe indicators will be made during the inception phase, but potential indicators on equity might include:

- % of published products with >40% of female co-authors
- % of published products with >40% of authors from LMICs
- % of published products with female lead authors
- % of published products with LMIC lead authors

Summary Value for Money Statement

The SS4ST programme represents a highly cost-effective investment, leveraging £34 million from FCDO alongside substantial co-funding commitments of approximately £200 million including significant pledges from development partners, partner governments and private sector actors. This collaborative approach creates significant opportunities to crowd in further resources, anchored around a shared vision for strengthening science and technology systems across Africa and Southeast Asia.

By operating as a joint programme, SS4ST achieves economies of scale, maximises social and economic returns, and accelerates research commercialisation. It strengthens foundational systems, enabling partner governments to lead their own S&T agendas, reduce aid dependency, and future-proof S&T ecosystems. Through policy alignment and locally owned interventions, the programme secures UK investments while unlocking additional funding and in-kind contributions, ensuring benefits that extend well beyond its lifetime.

A robust monitoring and evaluation framework will track progress against clear VfM indicators, guaranteeing transparency, accountability, and sustainable impact. This approach delivers high-impact, long-term value for money for partner countries as well as the UK.

## C. Commercial Case

This section sets out the commercial strategy for the programme. It details the rationale for the chosen delivery routes, funding instruments, partner selection, VfM approach, risk management, and performance management arrangements. The commercial approach is designed to ensure that the programme delivers high-quality, impactful results, maximises VfM, and supports long-term sustainability through strategic partnerships and robust oversight.

Commercial approach

The SS4ST programme will be delivered through a combination of Memoranda of Understanding (MoUs), Accountable Grants, and, where appropriate, contracts. The delivery model is structured around the three core components:
1. Pan-African Science Granting Councils Initiative (SGCI): Delivered in partnership with IDRC (Canada), NORAD (Norway), Wellcome and SIDA (Sweden) via a Delegated Co-operation Arrangement (DCA) with IDRC as the lead implementing partner.
2. Science Leadership and Institutional Excellence: Delivered through a strategic partnership with Wellcome, leveraging their established delivery mechanisms and networks, formalised via an MoU with Wellcome.
3. Responsive, country-level S&T programming: Delivered following early market engagement and call for proposals to ensure transparency, innovation, and VfM and select Accountable Grants and MoUs with local and regional non-profit partners, or contracts where appropriate.

This approach builds on FCDO’s experience of strategic partnerships with like-minded, technically capable organisations that deliver greater impact, sustainability, and leverage than traditional commercial procurement alone. It also demonstrates the UK’s modern approach to development: collaborating with African and Asian partners to jointly design and implement meaningful projects that address needs identified by local stakeholders, drawing on local expertise to ensure initiatives are contextually relevant and strengthen UK strategic partnerships. By fostering collaboration and leveraging partner resources, this model maximises VfM by reducing duplication, enabling resource pooling, and ensuring that investments are targeted toward high-impact, locally driven solutions.

Rationale

Components 1 & 2
Effective management of high-quality, technically rigorous system strengthening initiatives – aligned with UK Government priorities as described in the Strategic Case – will require targeted expertise in system strengthening and context-specific development research. In the last ten years, FCDO has partnered closely with like-minded partners, IDRC and Wellcome. We share common goals, values, and a collaborative and equitable approach, working together to address shared priorities in Africa and Asia. These partners have demonstrated technical excellence, robust governance, and a track record of leveraging significant co-funding. MoUs enable joint strategic direction, knowledge sharing, and alignment of objectives, while reducing management overheads and enabling rapid mobilisation.

Component 1: IDRC as a strategic partner for the Science Granting Councils Initiative (SGCI)
IDRC is globally recognised for research system strengthening across Africa, with decades of experience supporting knowledge, innovation, and development solutions. IDRC’s engagement has supported science and technology management and the delivery of high-quality, context-specific research across the continent. It has a proven track record in managing complex, multi-country programmes, leading the delivery of the SGCI since 2015 in partnership with FCDO, South Africa’s National Research Foundation, and others. IDRC delivers SGCI through its regional teams in East Africa (Kenya) and West Africa (Senegal), enabling it to deliver contextually relevant work and support. IDRC’s financial statements are audited annually by an independent auditor and included in SGCI Annual Review processes. A high-level summary of these audits is available. Additionally, projects delivered by downstream partners regularly undergo financial audits before payments are released.
SGCI 3 will adopt a streamlined governance model built around a consolidated funding pool managed by IDRC. The Core Funders Group (development partners/donors) will all contribute to a central pooled fund and ensure alignment with SGCI’s overall objectives. IDRC will provide strategic oversight of the initiative including financial accountability. Working with the new SCGI Alliance and the Councils Coordination Group, the Core Funders group will establish new mechanisms that enable African SGCs to increasingly lead programme delivery and design and directly implement projects. SGCs will co-fund and manage research and innovation projects that align with their respective development priorities. Co-investment has been a core requirement since the inception of SGCI, and the SGCs have fulfilled this to varying extents, reflecting their individual financial capacities.
A Programme Management Team (PMT) based at IDRC will lead the coordination and operational delivery of SGCI 3. This includes managing grants, ensuring quality assurance, and supporting implementation through SGCs and Technical Support Agencies (TSAs). TSAs are all African-based and provide flexible on-demand technical assistance and implementation support to SGCs.

Component 2: Wellcome as a strategic partner for Science Leadership and Institutional Excellence (DELTAS Africa and SEA-DREAM)
Wellcome is a globally respected charitable foundation renowned for its extensive expertise in research, capacity building, and strategic partnerships, with a particular focus on Africa. As a key strategic partner to FCDO, Wellcome played a central role in establishing the DELTAS Africa programme in 2015, leading joint funding efforts to empower delivery partners and ensure effective programme implementation. Over this period, FCDO has leveraged this enduring partnership to influence Wellcome funding into additional areas of FCDO priorities such as climate change and social sciences (new research agendas for DELTAS II).
Wellcome’s deep engagement in Africa is evidenced by its enduring partnerships and its important role supporting SFA, which now manages DELTAS Africa II. Notably, DELTAS consortia have achieved milestones such as the discovery of the Omicron variant in Botswana and the establishment of Kenya’s first PCR testing facility during the COVID-19 pandemic. Through its work, Wellcome has facilitated the training and mentorship of thousands of African researchers, significantly strengthening research infrastructure across the continent. Wellcome’s approach emphasises strategic alignment with local stakeholders, leveraging established networks and delivery mechanisms to ensure initiatives are contextually relevant and sustainable, and its commitment to partnership, knowledge sharing, and capacity building has made a transformative contribution to the advancement of science and research leadership in Africa. Wellcome has the technical capacity and expertise to expand the DELTAS Africa model to Southeast Asia through SEA-DREAM working with the Southeast Asian Ministers of Education Organisation (SEAMEO), alongside FCDO’s physical presence in the region through our regional teams in High Commissions and Embassies.
Wellcome will manage the regional downstream delivery partners, SFA and SEAMEO, undertaking due diligence assessments, independent reviews, audits, etc. The findings of these assessments and audits are shared with FCDO and discussed in the DELTAS and SEA-DREAM partners group, with actions including mitigation measures, agreed jointly. At the start of each year, SFA and SEAMEO will provide a comprehensive budget that outlines how they intend to spend Wellcome and FCDO funding. This will be rigorously reviewed by FCDO with recommendations where necessary. Any changes are managed in line with agreements between FCDO and Wellcome.
Since its establishment in 2021, SFA maintains a robust, multi-layered assurance framework that combines outsourced internal audit and independent external audit to provide continuous oversight of governance, operations, grants management, programming, financial management, and risk environment. Annual external audits conducted by Ernst & Young provides independent assurance on financial statements and internal controls, with the FY2024 Management Letter highlighting targeted opportunities for improvement in travel management controls, procurement compliance, and IT policy update all of which have documented management responses and implementation timelines monitored by the Board Finance, Audit & Risk Committee. Alongside the internal audits, these assurance processes demonstrate a strong culture of accountability, risk awareness, and continuous improvement across SFA, reinforced by active participation of departmental risk champions and quarterly updates to risk registers, confirming that risk management is embedded across the organisation rather than centralised in a single function. When implemented SEA-DREAM with Wellcome and SEAMEO, FCDO will ensure a similar set of assurance processes will be implemented.

## Component 3: Responsive, country-level S&T programming
This component will work directly with partners across the Global South, with a focus on Africa and Southeast Asia, and be delivered predominantly through non-commercial implementing partners, selected via a competitive call for proposals and following market engagement.

This component will be delivered through a limited set of delivery mechanisms overseen by GSD in East (Nairobi), West (Accra) and Southern Africa (Pretoria) and in Southeast Asia (Delhi). Building on FCDO experience on regional demand-responsive S&T support through Sankore (Ghana) and RIDA (ASEAN), preference will be given to Accountable Grants to local non-commercial delivery partners that can demonstrate context-specific S&T technical expertise, in-depth country knowledge including understanding of local institutions and existing relationships with local government partners and S&T ecosystem stakeholders, and physical presence in-country. MoUs and contracts will be used if appropriate. Partners will be selected based on the technical capacity to deliver our UK-Africa-SE Asia priorities and objectives as set out in our G2G partnerships and identified with in-country partners. Preference will be given to local delivery partners to support building local capacity, ensure interventions are contextually relevant, and promote sustainability beyond the programme’s lifecycle. Through an early market engagement process, we will identify both the capability within local ecosystems to respond to priorities, and the appropriate contracting instrument. The call for proposals will ensure we select partners based on key criteria including value for money, technical capabilities and experience, contextual knowledge and ability to deliver high quality/impactful outputs. Delivery mechanisms will be chosen to ensure value for money through fit-for-purpose approaches aligned with local realities.

Procurement of downstream partners
Component 1: IDRC’s procurement capability is underpinned by robust governance structures, clear separation of duties, independent oversight, and strong controls. Its systems ensure rigorous selection and management of funding recipients, with transparent processes for proposal assessment and ongoing due diligence. IDRC has substantial experience in managing downstream delivery partners, significantly underpinned by both technical and administrative regionally based staff able to engage directly with implementation partners. Under SGCI-3, IDRC will enter into funding agreements with SGCs and TSAs to deliver research. Institutional risk assessments and financial audits are conducted before issuing contracts to grantees. Nairobi and Dakar based IDRC Programme Officers will conduct targeted missions to participating Councils to assist with project start-up, monitor progress, and address any challenges. In addition to established technical and financial reporting mechanisms, IDRC grant administration staff will also conduct physical visits, spot-checks, and periodic institutional due-diligence assessments to ensure compliance and effective oversight.

Component 2: Wellcome has comprehensive policies on procurement, data protection and risk management. Its approach to downstream delivery involves rigorous selection of funding recipients, expert assessment of proposals, and ongoing support from specialists in finance, legal, grants management, and science. Joint governance structures with partners ensure robust controls and transparent procurement processes. A delivery chain risk assessment is produced by downstream partners, SFA and SEAMEO once grantees are established. For the next round of DELTAS grants, SFA will release a competitive call for research proposals, building on the previous rounds, and balancing equity with excellence in the design of the call. In DELTAS II, SFA greatly increased the participation of a wide range of universities and institutions across the continent from different countries including Congo, Niger, Sierra Leon, Liberia, Guinea Bissau, Morocco, and Mozambique. SFA conduct due diligence assessments of the consortia through virtual and in-person visits to the grantees in line with SFA’s Grant Assurance Guidelines. Due diligence reports are then shared with FCDO and Wellcome for review.

Component 3: This will be managed directly by GSD teams in East (Nairobi), West (Accra/Lagos) and Southern (Pretoria) Africa, and for Southeast Asia (Delhi) and will therefore align with FCDO procurement rules and processes to ensure value for money and adherence to best practice. All proposals will be rigorously assessed and benchmarked against comparable FCDO-funded programmes, in line with the PrOF.

Performance management
Performance management is anchored in strategic collaboration with delivery partners, leveraging flexibility, agility, and enduring relationships to ensure effective oversight and impact. By partnering with likeminded entities such as IDRC and Wellcome, the programme benefits from leveraging partner expertise and resources, while minimising administrative burden. Joint governance structures with IDRC, Wellcome, and other delivery partners, with clear separation of duties and robust controls, are critical for managing complex, high-value initiatives. SGCI programme performance will be monitored through a clear set of key indicators focused on timely delivery of milestones, budget accuracy, impact i.e. improving research collaboration and evidence uptake and influence, and quality of delivery i.e. adherence to quality standards based on IDRC’s RQ+ standards to safeguard research quality and relevance. Programme managers and responsible officers in relevant FCDO regions will oversee delivery by closely monitoring partners in-country, providing technical advice, delivery support, coordination, and conducting monitoring, evaluation, and learning activities. Regular quarterly updates, annual reviews, and adaptive management practices ensure that relationships are effectively managed throughout the project lifecycle, enhancing trust, credibility, and assurance of delivery capability among stakeholders. Wellcome’s performance is managed in line with MoU requirements. While the MoU does not specify quantitative KPIs, it sets out clear qualitative performance indicators related to financial management, compliance, safeguarding, communications, risk management, transparency, and governance. Over the past decade, these requirements have been met and have ensured successful delivery.

Risk management
Key commercial risks include lack of coordination across components, slow spend, and poor exit strategy. Mitigation measures include strong cross-programme management with dedicated resource to ensuring component complementarity, minimising duplication and identifying efficiency savings. The commercial approach prioritises sustainability by building local capacity, securing co-investment, and supporting responsible FCDO exit strategies. Exit plans will be developed with all major partners, ensuring transfer of assets, knowledge, learning and impact through the lifetime of this next phase of investment.

Key cost drivers
Key cost drivers for the programme are:
- Research funding disbursed by IDRC or Wellcome to researchers for research and innovation projects
- Labour costs, particularly linked to technical support, data collection, training and capacity building, communication and outreach
- Travel and subsistence, and cost of meetings
- Other system development costs, including equipment
- Overheads
- Admin and running costs associated with managing research activities

The programme will manage and monitor cost drivers through a combination of strategic funding arrangements, regular reviews, and phased implementation. Significant expenditures, such as sub-grants and consortium delivery costs, will require FCDO approval and sign-off, ensuring robust oversight. Regular reviews and adaptive management will enable early identification of inefficiencies, while phased delivery allows for learning and adjustment at each stage. Leveraging in-house expertise and engaging local stakeholders in co-design and delivery will help ensure interventions are relevant, sustainable, and cost-effective.

Programme oversight will be maintained by dedicated Programme Responsible Officers, a Senior Programme Manager, senior leadership, and an independent Advisory Board, all supported by robust governance structures including audits and compliance checks. Value for Money (VfM) will be monitored across the five E’s—Economy, Efficiency, Effectiveness, Equity, and Cost-effectiveness—using agreed KPIs and the log frame to track and report on cost drivers and outcomes. This approach will facilitate communication, share best practices, and uphold financial management standards across all components.

Working with delivery partners, FCDO will promote open competitions by IDRC, Wellcome and downstream partners to drive economy and VFM for project investments. Where a supplier will be contracted directly by IDRC, Wellcome and our regional teams, FCDO will draw on expertise within Commercial and Procurement Group on unit cost benchmarks, particularly in relation to daily fee rates, which is likely to be the most significant cost driver. For all other agreements FCDO will carefully scrutinise the overhead charge, including for issues such as cascading overheads for downstream partners.

Value for money
Integrating FCDO S&T system strengthening investments into a unified programme helps minimise duplication and ensures resources are allocated efficiently. VfM is achieved through significant co-financing and match-funding across all component projects, alongside the ongoing promotion of sustainability and inclusion throughout the programme. IDRC has played a pivotal role in leveraging significant additional funding from partners into SGCI and encouraging greater domestic investment in R&D by African governments. Through DELTAS Africa, Wellcome has enabled transformative impact by leveraging significant co-funding and catalysing further investment from partner governments and other donors. For every £1 invested in DELTAS Africa by Wellcome and FCDO, up to £3 has been leveraged from other partners and governments, multiplying the reach and sustainability of research leadership and institutional strengthening efforts. This quantity of funding leveraged is anticipated for both DELTAS III and SEA-DREAM. Competitive tendering for Component 3 drives efficiency and cost-effectiveness, with clear value for money criteria. Monitoring and evaluation frameworks, supported by in-house expertise, will ensure ongoing assessment of costs and VfM throughout the lifetime of the programme.
## D. Financial Case

The proposed cost of the programme is £34 million ODA over four years, with £28 million CDEL R&D for research outputs and £6 million as RDEL for convening expertise and technical assistance. Future ODA settlements are yet to be announced; the budget forecast is based on ISTD’s indicative future year allocations and subject to SR2 R&D portfolio allocations.

Following the reduction of ODA from 0.5% to 0.3% of GNI, the programme design has undergone substantial revision to ensure a targeted approach, prioritising the most impactful and effective interventions and maximising alignment and match-funding from like- minded development partners, philanthropic organisations, local partners, and governments. The programme prioritises sustainability, using UK investments to attract co-financing for long-term support of local S&T systems and development-focused institutions. Co-funding has been secured from Wellcome (£169 million) and IDRC (£6.6 million), with further contributions expected from Norad, Sida, partner governments, and the private sector. The programme aims to leverage over £200 million in additional funding over four years.

The initial projected budget by year and CDEL / RDEL is shown in Table 3 below.
Table 3: Total programme budget allocation per year

Year	Total ODA (£m)	CDEL (£m)	RDEL (£m)
1	8.5	7.0	1.5
2	8.5	7.0	1.5
3	8.5	7.0	1.5
4	8.5	7.0	1.5
Total (£m)	34	28	6

Table 4 below shows the proportional allocations per component. This is informed by decades of experience within GSD and independent reviews of SGCI and DELTAS programmes. The disbursement schedule is based on timely partner mobilisation and procurement. No major delays are expected with co-funding contributions or implementation by our lead suppliers e.g. IDRC, Wellcome.

Table 4: Budget allocation by component (£m)

		26/27		27/28		28/29		29/30
Component	Sub-component	CDEL	RDEL	CDEL	RDEL	CDEL	RDEL	CDEL	RDEL	Total
SGCI		1.0		1.0		1.0		1.0		4.0
Wellcome Partnership	DELTAS	1.0		1.0		1.0		1.0		4.0
	SEA DREAM	1.0		1.0		1.0		1.0		4.0
Bilateral, responsive funding	West Africa	0.88	0.38	0.88	0.38	0.88	0.38	0.88	0.38	5.0
	East Africa	0.88	0.38	0.88	0.38	0.88	0.38	0.88	0.38	5.0
	Southern Africa	0.88	0.38	0.88	0.38	0.88	0.38	0.88	0.38	5.0
	Southeast Asia	0.88	0.38	0.88	0.38	0.88	0.38	0.88	0.38	5.0
PFPs – up to 5 roles		0.47		0.47		0.47		0.47		1.9
Total		7.0	1.5	7.0	1.5	7.0	1.5	7.0	1.5	34

Disbursement and expenditure control
Robust due diligence will be conducted on all delivery partners prior to programme inception and maintained throughout the programme lifecycle, in line with FCDO’s Due Diligence Framework and PrOF guidance. Funds will be disbursed to implementing partners in line with PrOF rules and the terms of various funding instruments (MoUs, Accountable Grants, and contracts), with arrangements denominated in GBP. Delivery partners will bear the risk of exchange rate fluctuations as per FCDO policy.

Financial payments will be made based on performance against the results framework; evidenced and supported by required documentation, such as receipts and financial statements, to ensure a full audit trail. Financial reporting and expenditure monitoring will align with specific delivery mechanisms and contractual requirements, with partners submitting accurate forecasts and detailed expenditure reports, reviewed by the GSD programme team for continual process improvement.

Funds will be disbursed in tranches, aligned with delivery milestones, partner capacity, and procurement timelines and never in advance of need. Disbursement mechanisms include MoUs for Components 1 and 2 (IDRC, Wellcome), and Accountable Grants, MoUs, or contracts for Component 3 with local or regional partners. All partners must submit quarterly and annual financial reports, reconciled against budgets and delivery plans. FCDO oversight is maintained by the Senior Responsible Owner (SRO), Programme Responsible Officers (PROs), and finance managers.

Financial management and assurance
Aid diversion is considered low due to robust partner systems and FCDO oversight. The programme will ensure that financial and fraud risks remain within appetite (cautious), through rigorous monitoring. A delivery chain risk map will be created for the programme, encompassing all delivery partners. All partners will be required to implement rigorous downstream partner monitoring procedures. A zero-tolerance approach will be taken to fraud and corruption. Spot checks will be conducted on partners, and financial and systems audits will be considered.

The programme will maintain oversight through periodic financial reviews, reconciliations, assessments of financial management systems, governance structures, safeguarding policies, and anti-fraud measures; enabling timely monitoring of expenditure, early identification of financial risks, and assurance that value for money is achieved throughout the programme.

All programme assets, including intellectual property (IP), equipment, and data platforms, will be managed in accordance with FCDO asset management policies. Delivery partners must maintain accurate asset registers and ensure assets are safeguarded, used efficiently, and transferred appropriately at programme closure.

For Component 1, to manage fiduciary risks, IDRC implements:
- Financial and administrative controls based on institutional risk assessments.
- Periodic reviews of risk ratings, with higher risks necessitating stringent reporting.
- Monitoring recipient accountability through technical and financial reports.
IDRC’s Financial Control Framework includes:
- Recipient financial reports detailing project spending and cash status.
- Sampling of documentation for grant expenses, like spot-checking.
- Rigorous compliance reviews when needed.
For Component 2, Wellcome closely monitors SFA’s financial management. Wellcome’s finance team scrutinises requests for funding from SFA and internal audit functions at SFA, looking at adherence to grant conditions, financial control, risk assessment, application of policies and programmatic management. SFA continues using the Good Financial Grants Practice (GFGP) initiative, to review grantees’ compliance with internationally accepted standards for financial management.
For Component 3, FCDO’s regional S&T teams will implement robust financial management and assurance processes to ensure that funds are used for their intended purposes and fiduciary risks are effectively managed by delivery partners. Local partners will undergo due diligence and risk assessments before agreements are made.

Affordability and Value for Money
The programme is fully funded within FCDO’s ODA allocation. Management and administrative costs for Components 1 (IDRC) and 2 (Wellcome + SFA and SEAMEO) are deemed proportionate when benchmarked against similar FCDO programmes as per previous DFID/FCDO investments, these are 10-15% of the total component costs. Component 3 delivery partners will be chosen through competition to ensure value for money, with careful review of overheads and cascading costs. Key cost drivers such as personnel, travel, and equipment will be benchmarked and monitored throughout the programme lifecycle through regular programme reviews and quarterly meetings. The programme utilises substantial co-funding from Wellcome, IDRC, and other sources, while progressively increasing match-funding obligations for partner governments and institutions. This approach fosters sustainability and decreases reliance on aid.
## E. Management Case

# Governance and Management Arrangements
FCDO Governance Structure
The SS4S&T programme is centrally funded and delivered through a decentralised mechanism drawing on GSDs science and technology regional teams in priority geographies in Africa and Asia. The programme delivers directly against priority Country Business Plans, our shared bilateral priorities set out in strategic G2G partnerships, and regional strategies including the new Africa Approach and ASEAN Plan of Action.

FCDO roles and responsibilities will be as follows:
- Senior Responsible Owner (SRO): The GSD Deputy Head will provide strategic oversight, leadership, and accountability for programme objectives. SRO is the nominated contact for engagement with IDRC and Wellcome.
- Programme Responsible Officer (PRO): Will support the SRO to ensure portfolio coherence, and overseeing operational delivery across all component projects.
- Regional Technical Advisers and Project Managers: Will oversee funding and delivery in respective regions working closely with SRO and PRO to ensure alignment with strategic vision of the programme. One programme-funded post in each priority country/region (total max 4).
- MEL Adviser: A programme-funded post will support cross-programme learning, results tracking and internal engagement with on outcomes and impacts.

Programme Governance Arrangements
The programme brings together multiple investments and strategic partnerships in a single, agile platform programme in line with the approach taken in other areas of FCDO’s Research & Evidence Directorate. Investments under the programme share a common high-level vision and significant potential for synergistic lesson-sharing and knowledge exchange. As described in the Appraisal Case, the delivery model enables FCDO to rely on expert co-funders and delivery partners for much of the commissioning and management activity associated with the programme, while also remaining flexible to respond to emerging G2G priorities.

- Programme working group (internal): monthly meetings chaired by the SRO, to cohere and coordinate activities across components. The group will be formed of SRO, PRO, relevant regional technical advisers and project managers (including regional PFPs) and MEL lead.
- Component oversight: each programme component will be overseen by a dedicated lead responsible for delivery, risk management, and regular reporting, with progress reviewed through structured, monthly partner meetings to ensure alignment, accountability, and adaptive management.
- Cross-component delivery partners: biannual meetings chaired by the SRO with all delivery partners (Wellcome, SFA, SEAMEO, IDRC, and local delivery partners), focusing on strategic review of programme against milestones as identified in the Logframe and alignment with FCDO policy objectives.

# Risk Management
Overall Risk Rating
The risk level associated with this programme has been assessed as moderate, aligning with FCDO’s risk appetite as ‘receptive’ for strategy, policy and programme delivery, while ensuring a ‘cautious’ approach to risks on people, safeguarding, financial and reputational including a zero-tolerance approach to fraud and safeguarding. While science and research are inherently uncertain, partnering with reputable and experienced co-funders and delivery partners helps to deliver strong results while mitigate potential risks through robust oversight, leveraging proven expertise, and promoting adaptive management throughout the programme lifecycle.

Risk Management Process
Risks will be monitored and managed through regular communications with partners as well as progress updates and reviews. Partners will be engaged early on risk, through the due diligence process and the development of project level risk matrices, where appropriate. Risk management expectations will then be formalised through the MoU/funding arrangement wording. Partners will share all technical and financial reports with FCDO and provide regular updates on the progress of the programme in line funding arrangements (through monthly project and biannual programme meetings with FCDO). The Annual Review process will act as a check-in point for the programme risk matrix to be reviewed and updated where necessary. Risks will also be considered and updated throughout the year in response to any changes to internal and external factors. Should an identified risk move outside FCDO’s established risk appetite for the programme, the programme team will take immediate action to address the risk, including escalating through Department and Directorate processes.

Table 5: Risk register
Category	Risk	Mitigation	Likelihood	Residual Risk
Strategy and Context	Political economy in focus countries is not conductive to successful SS4ST interventions.	Political economy in priority countries will be assessed during quarterly and annual reviews with FCDO teams and partners to anticipate changes, plan scenarios, and adjust activities and resources as needed.	Possible	Moderate
Policy and Programme Delivery	Fragmented policy environments and under-resourced institutions may limit impact.	Invest in targeted bilateral S&T initiatives co-created with partner governments to address locally identified needs, including policy alignment and institutional reforms through Component 3. MEL Adviser to develop dissemination plan for cross-country policy dialogue to share best practice and coordinate interventions, ensuring coherence and reducing fragmentation.	Possible	Moderate
	Partnerships fail to deliver programme objectives or unlock co-investment.	Single programme SRO, PRO and MEL Adviser oversight to ensure coherence across delivery partners in different locations. Regular (quarterly and annual) strategic reviews with all partners, using the programme’s governance structure, will monitor progress and address misalignment early.	Possible	Minor
	Complex causal pathways and long timescales required for system-level change make monitoring and attribution of impact difficult.	The dedicated MEL Adviser as a Programme-Funded Post will develop a robust, multi-level MEL system with clear, disaggregated indicators for each component, including qualitative and quantitative metrics.	Possible	Moderate
Operational	Large, multi-country programmes require complex governance and may strain FCDO resources.	Delivery partners and FCDO regional teams have a strong track record of collaborating on regional and bilateral projects, applying lessons learned from previous work. Partnering with the two main co-funders for Components 1 and 2 will keep FCDO's transaction costs manageable, as described in the Appraisal Case. Deployment of Programme-Funded Posts will support the management and oversight of the programme. FCDO will continue to identify options for increasingly streamlined delivery models in the programme (e.g. joint calls across locations).	Possible	Minor
Safeguarding	Safeguarding or social inclusion issues are not sufficiently integrated.	FCDO’s due diligence assessment process will review measures by delivery partners to safeguard for the prevention of sexual exploitation, abuse or harassment. Gender and social inclusion considerations will be integrated into all project activities and monitored through annual reviews and periodic spot-checks.	Possible	Moderate
Financial and fiduciary	Corruption in delivery chain may result in funds not being used for the intended purposes.	The standard terms and conditions of FCDO’s funding arrangements include specific requirements to protect against fraud and corruption. Financial and fiduciary risk will be assessed during due diligence processes and revisited in project monitoring meetings and as part of the annual review process. Funds will be disbursed in tranches tied to verified milestones and deliverables, never in advance of need. Delivery chain risk maps will be maintained and periodic risk assessments conducted, escalating issues promptly to FCDO leadership.	Unlikely	Minor
	Limitations or adaptations within the FCDO finance system requires continual workarounds that reduce staff capacity and compromise delivery quality.	System improvements are in progress. Maintaining sufficient programme management staff is vital for proper oversight. FCDO Finance will provide regular updates and guidance. Payment processing will be prioritised to avoid delays.	Likely	Moderate
Reputational	Grantees fail to acknowledge FCDO co-funding.	FCDO will work with the principal co-funders / delivery partners to ensure grantees are required to acknowledge FCDO co-funding in research outputs and public communications.	Possible	Minor

# Monitoring and Review
The programme’s monitoring and review framework is designed to ensure robust oversight, learning, and adaptive management throughout implementation. A significant proportion of grant management and day-to-day oversight will be delegated to expert global funding partners. These partners are directly responsible for tracking investment results and ensuring that each project develops and reports against a detailed results framework. This approach guarantees alignment with the overarching programme Logframe, which is co-designed by the programme team and partners and grounded in the Theory of Change. The Logframe integrates key indicators from each investment, providing a clear line of sight to the programme’s strategic objectives.

To facilitate cross-programme learning and effective results monitoring, the programme will deploy dedicated, programme-funded positions. Under the coordination of the MEL Adviser, these roles will drive coherence and consistency in monitoring, learning, and reporting requirements across all components. The MEL Adviser will convene regular internal challenge meetings to review progress, assess performance against Logframe outputs, and escalate risks or issues as needed. Insights from these meetings will directly inform Annual Reviews, supporting timely decision-making and continuous improvement.

Given the programme’s flexible and adaptive approach, indicators and targets will be refined iteratively in response to emerging evidence and contextual changes. Adaptation decisions will be informed by robust data collection and analysis within each programme component, led by the MEL Adviser in close collaboration with the SRO and PRO.

A strong commitment to learning is embedded throughout the programme. Regular consultations with partners and dedicated learning initiatives will ensure that lessons are captured and shared. The MEL Adviser will work collaboratively with delivery partners and regional teams to package and disseminate programme outputs, informing evidence-based science and technology policy and investments in Africa and Asia. Learning will be shared through programme websites, engagement with the International Research Development Funders Forum (IDRFF), and other relevant forums, ensuring that insights contribute to both internal improvement and broader sectoral knowledge and system strengthening.

Annex 1

Theory of Change: SGCI Phase 3

Annex 2
Theory of Change: DELTAS Africa

Annex 3
Theory of Change: SEA-DREAM

Annex 4
Theory of Change: Responsive, country-level S&T programming