## Annual Review Template

Title: Development of Mahagi One Stop Border Post and customs process and procedures in DRC - TMEA Strategy 3
Programme Value £ (full life): 5,000,000		Review date: 07/08/2025
Programme Code: 400200	AMP start date: 07/05/2024	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2024/2025
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006850.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006851.odt

A. SUMMARY AND OVERVIEW

Description of programme This programme forms part of a wider Foreign Commonwealth and Development Office (FCDO) programme – TradeMark East Africa – Strategy 2 (Regional). This is the first year that the programme had a dedicated bilateral element led from the British Embassy Kinshasa (BEK). The Democratic Republic of Congo (DRC), bordered by nine countries and endowed with vast natural resources, holds significant potential for regional trade and economic diversification. While the mining sector continues to dominate the economy, non-mineral trade is important for inclusive growth and poverty reduction. The DRC government also has an ambitious programme for the development of One Stop Border Posts (OSBPs) and the government’s asked for technical and financial support. To support DRC’s integration into regional trade and promote sustainable economic development, TradeMark Africa (TMA) partnered with the BEK to implement targeted interventions in the customs sector.

The primary objective of the project is to enhance infrastructure and operational efficiency at the Mahagi One Stop Border Post (Mahagi OSBP), with the goal of reducing border dwell time to under six (6) hours. The project also aims to promote the inclusion of small-scale cross-border traders, particularly women and youth, within the OSBP ecosystem.
The development of Mahagi OSBP and customs process and procedures project is an initiative aimed at transforming the Mahagi border post into a fully operational OSBP to facilitate smoother, faster, and more secure cross-border trade with interventions grouped in three key pillars namely:
- digital solutions for border efficiency;
- improved OSBP infrastructure capacity; and
gender mainstreaming.
Ultimately, this border should act as a model for DRC’s OSBP programme.

In addition to the activity at Mahagi Border post, as part of broader activities to support DRC’s trading system through development the programme worked with the DRC to develop its Regional Electronic Cargo Tracking System (RECTS) and modernised its customs management system.

The project is expected to:
- Reduce transport time and costs along the Northern Corridor (a multi-modal corridor linking Burundi, DRC, Rwanda, South Sudan and Uganda to the Mombasa sea Port in Kenya);
- Increase capacity and efficiency at the Mahagi OSBP; and
- Improve overall border performance by decreasing crossing time and associated expenses.

These outcomes are long-term and will not be fully measurable until 2027.

Summary supporting narrative for the overall score in this review
The project has scored an ‘A’ as it has broadly met its agreed milestones, narrowly missing some due to the political context.

In January 2025, the M23 occupation of key towns (including Goma and Bukavu) in eastern DRC necessitated the pausing or adjustment of some limited activities. The British Embassy worked closely with TMA to ensure that these changes were handled sensitively and in accordance with legal and ethical guidelines. As a result:
- Electronic seals (security feature - see output 4) were delivered to alternative locations within DRC
- Activities were adjusted to account for the changed security situation in Goma and Bukavu.

Major lessons and recommendations for the year ahead

Lesson 1: Strengthen Risk Management and Contingency Planning
The programme experienced several delays. Putting in place a systematic approach is important given competing priorities. Future projects should incorporate more comprehensive risk assessments and develop contingency plans to address potential disruptions, ensuring project continuity and adaptability in volatile environments.

Lesson 2: Enhance Stakeholder Coordination and Communication
Effective collaboration between DRC and Uganda was crucial for the OSBP's success. Establishing clear communication channels and joint operational frameworks early in the project can facilitate smoother cross-border cooperation and shared ownership of project outcomes.

Lesson 3: Prioritise Gender Inclusion in Project Design
Recognising that women constitute a significant portion of cross-border traders, the project implemented gender-focused training and awareness campaigns. TMA should continue to integrate gender considerations from the outset ensures that infrastructure and policies are inclusive, addressing the specific needs and challenges faced by women traders.

Lesson 4: Ensure Sustainable Infrastructure and Resource Allocation
The installation of hybrid power systems and ICT equipment highlighted the importance of sustainable resource planning. Future projects should prioritise environmentally friendly solutions and ensure that infrastructure investments are resilient, cost-effective, and aligned with long-term operational needs.

Lesson 5: Implement Continuous Monitoring and Evaluation Mechanisms
Ongoing assessment of project activities allowed for timely adjustments and informed decision-making. Establishing robust monitoring and evaluation frameworks enables the identification of best practices and areas for improvement, enhancing the effectiveness and impact of development interventions.

Lesson 6: TMA need to strengthen accuracy of forecasts and timelines that consider the country context
TMA’s financial forecasts were consistently inaccurate throughout the year, resulting in a disproportionate amount of delivery occurring in the final quarter. . Looking ahead, it is essential that TMA incorporates lessons learned and takes greater account of the DRC operating context when preparing financial forecasts. Improved accuracy and timeliness will be critical to ensuring smoother delivery and more effective oversight in the 2025/26 cycle.

Recommendation 1: BEK to engage further on Bilateral agreement
The BEK team should further develop engagement with political stakeholders on both the DRC and Uganda side to support delivery.

Recommendation 2: TMA to engage with DRC to support alternative financing approaches to develop its border infrastructure
Given the demonstrated economic potential of border infrastructure, TMA should work with the Government of DRC to develop sustainable financing plans to take forward its border development initiatives and ensuring it has the right expertise to take forward interventions. Building on the success of this programme, the DRC could leverage existing work and outcomes as a model for future investments.

Recommendation 3: Ensure clear and visible theory of change
The programme took place as part of the regional business case and governed by the existing Memorandum of Understanding (MoU). However, given the specificity of the work in the DRC, the programme would benefit from a dedicated theory of change. This should be developed as a priority for the 2025/26 planning cycle to ensure strategic clarity and alignment with national and regional objectives.

Recommendations 4: Quarterly strategic conversations
During the 2024/25 period, engagement between the BEK and TMA teams primarily focused on delivery-related matters, ensuring alignment with agreed outcomes and outputs. However, this emphasis on operational issues left limited space for broader strategic dialogue. For 2025/26, it is recommended that the teams incorporate more strategic discussions into their quarterly review processes to enhance programme responsiveness and longer-term impact.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

TMA’s Strategy 3 in the Democratic Republic of Congo (DRC) builds on earlier achievements and focuses on enhancing trade within and beyond the East African Community (EAC). Key initiatives include:

- Design and preparation for infrastructure development at One-Stop Border Posts (OSBPs), particularly at Mahagi (DRC–Uganda border);
- Deployment of the Regional Electronic Cargo Tracking System (RECTS) along the Northern Corridor for goods destined for eastern DRC; and
- Modernisation of the Customs Management System through the implementation of ASYCUDA World.

A central priority remains the DRC’s full integration into RECTS, reinforcing the programme’s emphasis on digitalisation and efficient trade monitoring. Strategy 3 also introduces a stronger focus on green and inclusive trade, embedding climate resilience and sustainability into trade facilitation efforts. While maintaining continuity in infrastructure development, the strategy expands to include sustainability, inclusivity, and innovative financing models.

The security situation in the eastern and southern provinces in the DRC has significantly increased the complexity and unpredictability of programme implementation. In response, the central Theory of Change (ToC) has undergone a rapid review to incorporate evolving regional political and security dynamics. Given the strategic importance of cross-border collaboration, government relations between the DRC and Uganda play a key role in the programme’s ability to achieve its intended outcomes.

Ongoing conflict in Goma and Bukavu not only meant the programme stopped operating in that area. The seizure of strategic towns by M23 and the security situation in Ituri Province created further challenges with programme implementation,

TMA DRC has had to reassess risk factors related to internal and regional security and political developments. The relocation of field staff from Goma (where some TMA operations were based) for security reasons has further complicated coordination with stakeholders, though operations in Mahagi have continued.

Despite these unprecedented challenges, the TMA DRC programme has demonstrated resilience, supported by:
- strong internal team cohesion,
- donor flexibility, such as FCDO’s integration of ERRA components into its funding,
- donor solidarity, with the Netherlands expressing willingness to fund selected Economic Recovery and Resilience Activity (ERRA) outputs which will help support the longer-term ambitions of the programme, and
- stakeholder collaboration, marked by constructive communication and joint problem-solving.

These factors enabled TMA DRC to record positive results particularly in promoting cross-border trade—where women represent the majority of small-scale traders.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The TMA DRC programme established clear goals, and its outputs are well-aligned with these objectives. However, while TMA can ensure the delivery of outputs and outcomes, measuring the broader impact remains a challenge. For instance, while OSBPs can significantly enhance long term logistics facilitation, the scale they are able to do this depends on many factors including trade connectivity within the country. Further investment in DRC roads will enable OSBPs to add significantly more value to the DRC economy.

During the review, DRC officials acknowledged the significant progress made by the TMA programme—progress that, five years ago, would have seemed unimaginable. Despite the existential challenges posed by the current security situation, TMA could consider relocating certain programme activities to areas still under central government control. For example, cross-border interventions in Goma and Bukavu could be continued in Kalemi.

An unexpected but positive outcome was the strengthening of relationships between DRC and Ugandan officials. One DRC official even mentioned learning English—a step he said would never have been necessary or possible without the OSBP initiative.

The delay in signing a bilateral agreement between the DRC and Uganda—largely due to the prevailing political climate—has resulted in Output 2 not being achieved and hindered progress on Output 4. To ensure delivery of Output 2, there should be a more concerted effort using both implementer but also making use of broader policy engagement. Planning is already underway for FY25/26. Strategic meetings, as flagged as a recommendation should ensure a more coordinated approach.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The TMA DRC programme should continue and receive increased support. In a challenging context the programme has largely delivered on its objectives and is working with a government who has an ambitious plan to transform trade across its borders. Trade facilitations links in with wider DRC infrastructure developments including the Lobito Corridor, Banana Port and a growing agriculture sector.

Interviews with donor representatives highlighted two strategic dimensions that could position TMA DRC as a leading model within TMA as a whole:

Coordinated Donor Engagement: TMA DRC’s role in fostering coordinated programming among donors is important to the development of integrated approaches suited to the environment of the DRC.

Innovative Partnership Models: Donors emphasised the need to shift perceptions of partnership, advocating for greater involvement of citizens from donor countries. They suggested that investors from both the DRC and donor nations could benefit from greater collaboration with citizens within programme frameworks—particularly in value chains where expertise and experience can be transferred to local counterparts.

## C. DETAILED OUTPUT SCORING

Output Title	Designs for the processes of: Mahagi OSBP road, bridge maintenance, cross border market and Mahagi border post officials’ accommodation completed
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Progress towards the finalisation of the Designs for the Mahagi OSBP road	Final designs and tender documents in preparation for Procurement for Civil Works (100% completion).	A+ - moderately exceeded. Funding secured for development of the road.
Progress towards the finalisation of the designs for the bridge maintenance	Final designs and tender documents in preparation for Procurement for Civil Works (100% completion)	A+ - moderately exceeded. Funding secured for development of the road.
Progress towards the finalisation of the designs for the Mahagi cross border market	Final designs and tender documents in preparation for Procurement for Civil Works (100% completion)	A - Achieved milestone.
Progress towards the finalisation of the designs for the Mahagi border officials’ accommodation	Final designs and tender documents in preparation for Procurement for Civil Works (100% completion)	A - Achieved milestone.

Briefly describe the output’s activities and provide supporting narrative for the score.

TMA engaged a consultant to support the design and preparation of key infrastructure works at the Mahagi border. The procurement document was advertised to a restricted pre-selected and verified list, due to the time constraints. The assignment includes technical studies, designs, procurement support, and obtaining necessary environmental and statutory approvals. The scope of services for the Consultant included reviewing existing studies, preparing detailed designs and the preparation of tender documents, conducting an Environmental and Social Impact Assessment, and assisting with the preparation of the tender documents and bidding process. Contract supervision is part of the overall scope but not funded by FCDO.

To ensure the sustainability of infrastructure-related components, BEK engaged with TMA to secure alternative donor support. For the 2025/26 financial year, the European Union will fund the construction of the access road and maintenance of the bridge. Initially, BEK had planned to finance the cross-border market; however this is no longer feasible. BEK will continue to work with TMA to explore alternative funding options for both the market and the border officials’ accommodation albeit TMA agreed these would be prioritised from core funding should such donor funding not be available.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This was the first year that BEK directly worked with TMA as part of the wider FCDO programme, and consequently, the first year working with a jointly developed logframe. The infrastructure-related output included in the 2024/25 logframe will not be carried forward into 2025/26, as the associated activities have been completed. Additionally, due to unforeseen delays, there will be no further funding for infrastructure construction in the upcoming year

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The UK and EU provided complementary funding to TMA, with the UK financing the design phase and the EU supporting construction—demonstrating effective alignment of donor resources and delivering strong value for money for UK aid.

Given the changing donor landscape, it is important to continue to pursue further opportunities for joint or complementary funding to maintain delivery momentum and ensure the sustainability of key infrastructure investments.

Output Title	Trade barriers identification, reporting and resolution monitoring mechanisms facilitated, developed Implemented
Output number:		2	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
OSBP procedures operationalised to support operationalisation of IBM at Mahagi OSBP:	OSBP procedures in use at Mahagi OSBP	C – significantly not met: Officials trained and draft OSBP procedures drafted. However, these were not agreed nor operationalised.
Progress towards operationalisation of OSBP National OSBP Steering Committee and subcommittees	At least 4 NOSC meetings held(cumulatively) / At least 6 issues resolved cumulatively	C – significantly not met. National Steering Committee created. However, no meetings and no issues resolved.
Border agencies enforce and comply with agreed OSBP processes	All border agencies enforce and comply with OSBP procedures	C - OSBP procedures drafted but not agreed and not being operationalised. Officials aware of their responsibilities and how to work with an OSBP.

Briefly describe the output’s activities and provide supporting narrative for the score.

To support the operationalisation of the One Stop Border Post (OSBP) at Mahagi, the programme recruited a consultant to develop training materials in line with the East African Community (EAC) OSBP Act of 2016, in collaboration with the EAC Secretariat. Three Integrated Border Management (IBM) training sessions were delivered in partnership with the EAC Secretariat and the Directorate of Customs. These sessions focused on DRC officials and Mahagi border officers and were tailored to the local context. Notably, a DRC co-facilitator from Directorate General of Customs and Excise (DGDA)—trained in earlier cohorts—participated for the first time, contributing to the sustainability of knowledge transfer. The first two sessions, held in Moshi, Tanzania, brought together senior officials from DRC ministries and agencies, alongside counterparts from Kenya, Tanzania, and the EAC, and included field visits to operational OSBPs such as Namanga and Taveta/Holili. The third session, held in Arusha, focused on technical training for DRC and Ugandan border officials stationed at Mahagi-Goli, aiming to strengthen operational capacity, legal understanding, and cross-border collaboration.

Across all sessions, participants discussed key operational challenges, including clearance delays, inter-agency coordination gaps, staff turnover, porous borders, and language barriers. The training sessions were well received and considered highly effective in building practical knowledge of the OSBP model and regional integration. Draft OSBP procedures were developed; however, discussions between the DRC and Ugandan border committees to operationalise them could not take place. In parallel, the programme supported the physical modernisation of the Mahagi border post through the provision of ICT equipment, power infrastructure, and furniture. While a national steering committee has been established, TMA was unable to convene the planned National OSBP Steering Committee (NOSC) meetings with both DRC and Uganda due to contextual constraints.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This was the first year of managing TMA from BEK and therefore the first bilateral logframe. In 2025/2026, it is important that the implementer brings issues of concern to BEK attention and involves BEK more closely in relevant discussions. This will enable BEK to properly support the implementation of the OSBP.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The bilateral agreement between DRC & Uganda which would allow the One Stop Border Post to be fully operationalised has not been signed due to the current political environment. The BEK team should consider how they can engage with relevant political stakeholders in both the DRC and Uganda to enable this.

Output Title	ASYCUDA World System is live and functioning
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Progress towards operationalisation of the ASYCUDA World System	Deployment of ASYCUDA World to its live environment and Go-Live to support live transactions (100% operational).	A - Achieved: ASYCUDA World fully Operational with 20 upgraded modules.

Briefly describe the output’s activities and provide supporting narrative for the score.

ASYCUDA (Automated System for Customs Data) is a comprehensive customs management system developed by UNCTAD to support the modernisation and streamlining of customs operations. In this financial year, 20 ASYCUDA modules were successfully installed, supported by Private Cloud Appliance (PCA) infrastructure to host ASYCUDA World. This means that the Customs operations in the Democratic Republic of Congo will be better equipped to prevent fraud, secure government revenue, and generating accurate, real-time trade statistics.

Training sessions were conducted in Kinshasa and Geneva to build operational capacity. However, integration with external networks—such as Uganda Customs—remains pending due to political arrangements that must be resolved before cross-border system linkage can proceed.

Technically, the output has achieved all the targeted milestones; thus, it is on track. DRC stakeholders (government and its technical agencies such as DGDA and users) are happy with the completion stage. However, for the reasons mentioned above, the ASYCUDA platform is not yet 100% operational (has not been integrated with Uganda) as systems integration for the two countries has not yet been completed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This was the first year of managing TMA from BEK as part of the wider FCDO programme and therefore our first bliateral logframe. In 2025/2026, BEK will continue to engage on ensuring that any contextual constraints preventing the full use of ASYCUDA are effectively managed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The bilateral agreement between DRC and Uganda which would allow the One Stop Border Post to be fully operationalised and allow for ASYCUDA system integration has not been signed at this point. It will be important to consider how all parties can engage with stakeholders on both the DRC and Uganda side to enable this.

Output Title	Progress towards operationalisation of the DRC Electronic Cargo Tracking system (ECTS)
Output number:		4	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
Progress towards operationalisation of the DRC Electronic Cargo Tracking system (ECTS)	ECTS fully tested and ready for deployment	B - Partially achieved : 2,000 Electronic seals were delivered in Mahagi (1000) and Kasindi (1000), e-Seals Setup and Cargo Truck Test to be done by May 2025. / DRC ECT System is being deployed (Geofencing report and user validated, Pre-Production environment commissioned). Integration with ASYCUDA to be done in2025. / Maintenance Centre (to manage E-seals) installation to be completed in 2025

Briefly describe the output’s activities and provide supporting narrative for the score.

Electronic seals (e-seals) are GPS-enabled, tamper-evident devices attached to cargo trucks or containers. Their primary functions include:
- Real-time tracking: They transmit the location of cargo in transit, allowing customs authorities and fleet managers to monitor movement across borders;
- Security monitoring: If a seal is tampered with or removed before reaching its destination, the system triggers an alert—helping prevent theft, smuggling, or diversion;
- Route compliance: The system uses geofencing to ensure trucks follow approved routes. Deviations can be flagged immediately; and
- Faster clearance: Because the cargo is monitored electronically, customs can reduce physical inspections, speeding up border crossings and reducing delays.

TMA DRC successfully delivered 2,000 electronic seals to the Customs Authority (DGDA), with 1,000 units deployed in Mahagi and another 1,000 in Kasindi. The deployment was completed alongside the setup of the e-Seals system and successful testing of cargo tracking functionality. The DRC Electronic Cargo Tracking (ECT) System has been validated through a geofencing report, a user guide, and the commissioning of the pre-production environment. However, the regional electronic cargo tracking (RECT) System on the DRC side experienced delays due to the full integration with the ASYCUDA system and is scheduled for completion in  2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

It will be important to have a more systematic approach to stakeholder engagement to ensure political agreement follows programme developments.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The e-Seals deployed in the DRC are currently labelled for national use and are not fully compliant with East African Community (EAC) standards. This limits their integration with regional systems, particularly with Uganda Customs. Future deployments should prioritise regional standardisation to ensure seamless cross-border tracking and compliance with EAC protocols.

## D: VALUE FOR MONEY

Key cost drivers and performance
Nearly half of the project’s total budget was allocated to digital infrastructure for the DGDA. Major investments included:

- Electronic Cargo Tracking System (ECTS): GPS-enabled devices, software, and monitoring infrastructure;
- ASYCUDA World: A full customs management system requiring licensing, integration, and training;
- Oracle PCA: Enterprise-grade hardware for data centre operations; and
- IBM Equipment & Furnishings: Servers, networking tools, and office infrastructure for the Mahagi OSBP.

Training costs rose significantly due to the need to build capacity among border officials and ensure sustainability. While not fully anticipated, these costs were covered by reallocating funds from underused budget lines. Staff costs remained in line with projections, with recruitment phased from mobilisation through peak implementation.

The full £5 million budget was effectively utilised by March 2025, reflecting strong alignment between planning and execution. Despite some disruptions—such as relocating activities from Goma and Bukavu due to conflict—project performance remained unaffected. The programme also absorbed additional activities following the suspension of USAID funding.

Beyond infrastructure, the project prioritised capacity building and inclusion, delivering:
- Training for border and leadership officials at Mahagi OSBP.
- A gender empowerment programme for small-scale cross-border traders.

These efforts reflect a holistic approach, strengthening institutions while promoting equity and long-term impact.

VfM performance compared to the original VfM proposition in the business case

TMA did not develop specific VFM indicators for the BEK Programme. However, VFM analysis can still be drawn from its delivery, and FCDO has worked with TMA previously on a strategy for their delivery.

Economy
The project was delivered cost-effectively using a £5 million grant. Strategic procurement choices, such as leveraging existing agreements with UNCTAD and Oracle, reduced administrative overhead. Infrastructure design continuity at Mahagi OSBP and alignment with prior ECTS installations ensured technical and financial efficiency. The ECTS system is expected to enhance cargo security, reduce costs, and streamline trade, with long-term savings anticipated as adoption increases.

Efficiency
Despite operating in a challenging environment, the programme adapted efficiently by relocating activities to safer areas and redeploying staff. Key outputs like roads, bridges, and customs systems were delivered on time and on budget. The programme responded flexibly to funding gaps, ensuring continuity and reinforcing value for money. At times, the programme could have strengthened political engagement to support the programme’s outputs more effectively.

Effectiveness
The project largely achieved its objectives despite disruptions. Operational efficiency at Mahagi OSBP improved, reducing border dwell times. Integration of ASYCUDA World and ECTS into customs operations is expected to enhance transparency and revenue collection – however, some key parts of operationalisation are still to take place. Early FCDO investment catalysed additional EU funding, demonstrating strategic value and alignment with regional trade goals.

Equity
The project was equality sensitive. Community engagement events ensured diverse needs of groups were identified and addressed. Gender-sensitive infrastructure and targeted training workshops sought to raise awareness on the barriers that different identity groups face in accessing services. Gender-sensitive infrastructure and targeted training workshops promoted equitable trade participation. Community engagement events and tailored outreach reinforcedequitable participation..

Assessment of whether the Programme continues to represent value for money

The programme has made solid progress, successfully implementing several key interventions over the review period. Early indicators demonstrate that the intended outcomes, as outlined in the Logframe, are on track to be achieved. However, it will be vital to see results from increased stakeholder engagement early within the next period. Considerable efficiency gains will only be realisable through the sign off and ongoing engagement from senior stakeholders within the DRC and Uganda.

E: RISK

The overall risk of the programme is Major. Risks are updated on a quarterly basis. The continued conflict in eastern DRC elevates the overall risk profile. The project is viable and progressing, but contingency planning and adaptive management are essential, especially for field operations in conflict-affected areas. Some examples of risk management are set out below:

Strategy & Context: TMA has remained flexible in relocating activities from high-risk areas and adjusting interventions as needed. Additionally, TMA has an active contingency plan in place that enables remote work for all staff and contractors.

Financial & Fiduciary: In response to need for strengthened financial reporting, the BEK has been closely monitoring TMA’s monthly financial performance to identify any deviations from the workplan that could impact monthly targets. Additionally, regular monthly finance meetings have been held with TMA to review progress against the workplan and address any emerging issues.

Policy & Programme Delivery: TMA has undertaken significant work on internal people and systems reforms, and in parallel has embedded new frameworks and processes aligned with Strategy 3. These measures are helping to mitigate this risk. A continued focus on effective business planning and real-time monitoring of delivery against these will be important.

People: Both FCDO and TMA have adapted plans to ensure aligning staffing capacity with programme funding and ensure appropriate levels of resourcing are in place through work-force planning measures.

Safeguarding: TMA has a Safeguarding Policy in place. Compliance and implementation are assessed and reviewed through internal review processes. FCDO is currently undertaking an update of its Due Diligence Assessment on TMA which will include a review of TMA's approach to safeguarding, relevant policies and reporting of safeguarding allegations. TMA reports any potential incidents to FCDO in line with agreed procedures.

Public Service Delivery and Operations: TMA has built capability during the reporting period. Nevertheless, it should continue building the capacity of its partners, improve procurement and budgeting processes, and invest in climate-proofing infrastructure. Similarly, it should look to strengthening cybersecurity. By proactively addressing these risks, TMA can safeguard the successful delivery of its expected results.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

TMA has maintained a strong presence in eastern DRC for several years and recently expanded its operations by opening an office in Kinshasa. This strategic move has enhanced coordination with key stakeholders and strengthened TMA’s in-country footprint.

Embassy staff maintained regular engagement with TMA, holding biweekly meetings to monitor project progress. These meetings were instrumental in guiding implementation and addressing emerging challenges. The primary point of contact was the TMA Country Representative, with other team members participating as needed. During the reporting period, TMA also addressed initial staffing gaps by recruiting key personnel, including a Project Manager and a Resident Engineer—both critical to effective programme delivery.

In January 2025, Embassy staff conducted a field visit to Mahagi, where they met with a range of stakeholders. Feedback from the visit was overwhelmingly positive. TMA was commended for its strong engagement and effective delivery, particularly in the area of gender mainstreaming. Assessments indicated a marked improvement in stakeholders’ understanding of gender equality and related issues.

TMA’s financial performance should be strengthened going forward. There were consistent discrepancies between forecasted and actual expenditures across most quarters, which placed considerable pressure on the Embassy. Similar concerns were raised by other FCDO posts working with TMA, citing delays in financial reporting and inaccuracies in forecasting. The Embassy has since reiterated the importance of accurate financial forecasting, and improvements are expected in the coming year.

While the quality of reports submitted by TMA was generally satisfactory and included relevant updates on project progress, there were consistent delays in submission beyond agreed timelines. Additionally, the programme logframe was not regularly updated. These lapses in internal reporting placed undue pressure on the BEK programme team and hindered timely oversight. Moving forward, it is essential that TMA adheres strictly to reporting deadlines and maintains up-to-date monitoring tools. Future reports should also provide more comprehensive context, including political developments that may impact delivery.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Prior to the recent period of insecurity, the TMA DRC programme relied heavily on field visits, regular stakeholder engagements (including meetings with DGDA, DGM, and provincial government officials), and direct beneficiary feedback. However, due to escalating security concerns, programme staff have been subject to stricter travel protocols, including prohibitions on visiting certain sites in South Kivu Province—such as Bukavu and Goma—and restrictions on extended stays in specific locations.

In response, the TMA Logistics and Security teams have intensified collaboration with local stakeholders, leading to a more centralised approach to monitoring and evaluation. Additional security check-ins have been introduced, and most field logistics are now coordinated through locally based partners, including the use of UN system flights.

Evidence

Throughout the year, the TMA DRC team was expected to report regularly to the central TMA team, providing evidence of both progress and challenges. While consistent reporting occurred—particularly on FCDO-funded outputs such as the Mahagi OSBP and digital systems—broader evidence-sharing was uneven due to the difficult operating environment. Staff relocations and restricted access to key sites made it challenging to track results or verify claims on the ground.

Despite these limitations, digital tools such as the iSOKO platform (digital marketplace) and documentation from training activities in Mahagi offered credible inputs for assessing progress.

Learning

During the year under review, the TMA DRC team engaged in critical reflection amidst significant uncertainty and disruption. Learning occurred, particularly in areas such as adaptive programming, donor coordination, and the integration of cross-border traders into service delivery. However, this learning was often reactive rather than structured.
The closure of USAID funding and regional insecurity disrupted key activities and limited opportunities for deeper learning. Balancing operational demands with reflective practice proved difficult, especially as staff were relocated. Nevertheless, the programme began to extract valuable lessons on building resilience and operating flexibly across political and security boundaries.

Date of last narrative financial report	26 March 2025	Date of last audited annual statement