## Annual Review

Title: UK Development Engagement Programme
Programme Value £ (full life): 3,000,000		Review date: 30/10/2025
Programme Code: 400208	AMP start date: 30/10/2024	AMP end date: 15/08/2027

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The programme is intended to raise UK public awareness, understanding and support for international development. The design of the original programme was based on a budget of up to £3 million over 3 years (2024 - 2027) to deliver against two pillars: 1) targeted communications in collaboration with key stakeholders; and 2) the production of small-scale research, the piloting of development awareness activity, and monitoring and evaluation to assess the effectiveness of such activities.
Since the business case was approved in May 2024, the context has changed significantly. A new Government and the reduction in UK ODA from 0.5 to 0.3 GNI (see below) has required substantial re-shaping and a significantly reduced programme. The programme now has a targeted focus on addressing UK public perceptions and understanding of international development rather than wider behavioural change. The programme will now be delivered through an FCDO-led communication effort that is complemented by strategic engagement and collaboration with key partners. We will continue to test our approaches for reaching and engaging the UK public, including by commissioning research where needed via the programme, to ensure we monitor, learn and innovate.
This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition. We will be completing a business case addendum to reflect the substantial changes to the programme, including confirmation of the new programme budget.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

The programme has scored an A overall, and for each of the outputs. For output 1 (public engagement with content through communicating the importance of international development) we made significant progress in shifting HMG’s approach to communicating international development, including identifying the target audience, producing content, and beginning to test the effectiveness of messages, messaging and channels. The programme’s size and scope was reduced during the first year which means we have not delivered against the indicator relating to behaviour change.

We have also made progress against output 2 (evidence generated, synthesised, and used to improve understanding of effective development engagement approaches, and events participated in that aim to raise awareness of, and support for international development). Our focus during the first year has been on research, working with independent insight specialists to analyse data that has helped inform our communication approach. While the changes in context during the first year have limited our ability to lead and drive outreach activity, we have built relationships across HMG and with key external organisations to understand what is currently happening in the public engagement space, and to identify future opportunities.

Major lessons and recommendations for the year ahead

Changes in UK ODA and Ministerial portfolios have meant a revised budget, focus and delivery model for the programme. Recommendation: we will complete a business case addendum which will set out changes to the programme, including the new theory of change. We will also update the log frame/results framework. Recommendation: With a smaller programme we will expand our partnerships, including beyond the development sector. This will extend and amplify our reach to new audiences and will allow us to capitalise on opportunities for collaboration that in turn will help deliver our objectives in a low/no-cost way.
Focus during the first year has been on upskilling communication, policy and programme teams within the FCDO on our new approach to communicating international development. Recommendation: Over the next year we will expand training across HMG, to other Government departments.
The strategic communication expert funded by the programme has delivered significant results in shifting HMG’s approach to communicating development to the UK public, and taken steps to bring organisations outside HMG onboard to ensure consistency of message across multiple channels and platforms. The loan agreement for the communication expert is due to expire in November 2026, leaving a gap of 9 months under the programme. Recommendation: consider options for extending the contract or recruiting a replacement.
The communication expert has worked effectively in the International Development Strategic Communication Team to build capacity and understanding regarding UK public support for development across the organisation. The Communication team do not currently have the resources or capacity to continue this work without the expert funded by this programme. Recommendation: consider resources and capacity required over the long-term to ensure continued FCDO focus on public support for development, beyond the lifecycle of the programme.
The programme is informed by research and data produced by partners, including public polling on attitudes towards international development and the most effective engagement approaches. We have worked with partners to shape polling questions and the results have helped test and refine our approaches to reaching and engaging the UK audience. There are however some gaps in data which limit our understanding of the perceptions of certain groups. Recommendation: continue working with partners to identify critical knowledge gaps and how partners can support, including, if needed, by using modest programme funding to commission research.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The initial programme was designed according to a theory of change that would achieve the impact of more supportive attitudes and behaviours towards international development by the UK public and UK institutions. The outcomes were: 1) increased number of, and more effective development engagement approaches, and; 2) improvement in attitudes and behaviours towards international development among the target audience.
New Ministerial direction and a smaller programme will limit the impact and outcomes to public attitudes, rather than behaviour change. The focus of the programme will be increased public support for international development. We will revise the theory of change accordingly.
In the first year we have worked with external communication professionals and insight experts, and worked with the Development Engagement Lab (DEL) on public polling. This has allowed us to better understand UK public attitudes, their main issues of concern, and level of engagement with international development. We have access to disaggregated data according to age, gender, education and social level, which in turn allows us to segment the target audience groups. New research and data has informed the new HMG communication approach to international development by providing insights into the sorts of messaging, messengers and stories that resonate with the UK public, as well as channels to most effectively reach them. While the programme is not intended to further gender equality, we ensure that potential equality impacts based on gender and other protected characteristics are addressed in our communication and engagement activity.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Significant activity has taken place under Pillar 1 of the original programme intervention: improvement in attitudes and behaviours towards international development among the target audience. We have encouraged public engagement with international development content (the output) through a shift in the FCDO’s approach to communicating international development using a story-led approach to demonstrate impact, value for money and mutual benefit. The programme-funded strategic communication expert has been critical to this shift. They have provided training sessions to colleagues to strengthen understanding of UK public perceptions, produced cross-HMG communications guidance, and worked with teams across the FCDO to produce a bank of ready-to-use content. They have also convened external communication professionals and insight specialists to develop a common messaging framework to better reach and engage the UK public. While we have not seen an improvement in attitudes towards international development, support has remained steady and we have not seen a decrease in public support following the ODA cuts in February 2025 (DEL - GB-Dashboard-June-2025-1.pdf).
The outcome of pillar 2 is: increased number of and more effective development engagement approaches. Progress against this outcome has been more limited given the shifts around budget and Ministerial priorities. However, we have used evidence to improve our understanding of effective development engagement approaches (the output) primarily by bringing together communication and policy experts within the development sector, sharing best practice and ideas on messengers and channels that can reach the UK public. Over the next year we plan to expand our engagement with stakeholders outside the development sector that can help us expand our reach, tap into new audiences and amplify our message.
There is a risk that the programme does not achieve the intended impact of increased support for international development. This is in part due to conditions that are out of our control, including public perceptions driven by domestic concerns (e.g. cost of living, migration), negative media coverage, and a wider global narrative of multilateral withdrawal. With a smaller budget, our delivery model depends even more on effective cross-HMG working and partnerships with others. While this creates opportunities for greater coordination in support of our overall objective, there is a risk that competing priorities and lack of buy-in undermine delivery.
As outlined above we will be refocusing the impact of the programme and making changes to the outcomes and wider theory of change which we will set out in a business case addendum.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

We recommend that the programme continues in line with the reduced budget and revised theory of change. It represents good value for money and has strong Ministerial support. The programme-funded strategic communication expert has been instrumental in delivering a step-change in how HMG communicates development. Communication Directorate do not have capacity within baseline FCDO Communication resourcing to deliver this work. Contracting an external communication agency would incur significant additional costs which would not be value for money, nor could be covered by the small budget. A discrete amount of additional funding is available to support in-country projects and programmes in engaging the UK public and to test effective engagement approaches. We will embed learning to help refine how we communicate and build support. The revised delivery model with its dual focus on communications and engagement demonstrates how we’ll continue to work with and through partners at low-cost/no-cost.
The programme supports wider FCDO objectives. Public perceptions are part of our efforts to modernise the UK’s approach to international development, and rebuilding public support will help sustain the international development agenda in the long-term, as set out by the Minister for Development to the International Development Committee in May 2025.

## C. DETAILED OUTPUT SCORING

Output Title	Public engagement with content through communicating the importance of international development.
Output number:		1	Output Score:	A
Impact weighting (%):		80%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
1.1 Measurable positive attitudinal shifts amongst the target audience with regards to international development.	Shifting HMG’s approach to communicating development. / Decision on metric for measuring public support. / Determine priority target audiences. / Produce and test messaging and innovative content across a range of channels via different messengers.	Substantive progress to refine HMG’s communication approach to international development, and to embed the change across HMG via insight sharing, training and practical toolkits. / Ministerial agreement to use metrics, independently tracked via DEL, to measure progress on public support. / Agreed focus on ‘core supporters’ and ‘concerned sceptics’ as target audience. / Substantive progress on increased number of development stories produced and shared across media and digital channels in collaboration with a range of voices, including partner and digital influencers. Messenger testing in progress.
1.2 Measurable positive movement of the percentage of the audience from being behaviourally “marginally engaged” to “transactionally engaged” on the issue of international development, as tracked from the DEL baseline.		As outlined in Section B, we will not directly pursue behavioural change.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme has made good progress towards delivery of this output. The milestones above reflect substantial work to adapt how this programme delivers in a significantly changed operating context, and decisions to narrow the focus of this output.

Indicator 1.1
We’ve made substantive progress towards supporting positive attitudinal change through a shift in the FCDO’s approach to communicating international development focused on impact, value for money and mutual benefits. We have recruited a programme-funded strategic communication expert who has been critical in using insight to develop the new strategic approach, and embedding it across the organisation. This is enabling communication staff, as well as policy and programme teams, to more consistently produce engaging and impactful content that appeals to the UK public. The communication expert has:
- Produced cross-HMG guidance around messages and messengers that evidence shows will best reach and engage the UK public.
- Delivered training to colleagues across communication, policy and programme teams to outline latest insight on public perceptions around aid and international development, including practical guidance on producing and sharing stories focused on impact, progress and mutual benefits.
- Produced monthly newsletters that set out the new communication approach and the impact of resulting outputs, as well as best practice on effective messages and messengers.
- Provided advice and helped shape development communication activity of relevant ODA programmes to support how partners engage on development with the UK public – making sure activity is insight based, strategic and complementary to our wider approach.
- Instituted a series of workshops with external communication professionals and insight experts to test analysis and develop a messaging framework that organisations working across development, and outside of development (for example, philanthropy, business, technology, creative services), can use to make the case to the UK public that development is impactful.
1. A metric for measuring public support for development which is tracked independently, has been agreed with Ministers and embedded in key organisational delivery plans. Alongside a clear timeline for implementation, this will help to galvanise organisational support for the programme’s objectives.
2. Building on research by DEL, we have identified target audiences to reach and engage that will be most impactful in increasing awareness, understanding and ultimately support for international development. These are: (1) ‘core supporters’– already supportive of international development; and, (2) ‘concerned sceptics’– sceptical about aid effectiveness but concerned about poverty and other global issues (conflict, terrorism, migration).
Identifying and targeting these groups supports this output in two ways: (1) we will retain and reinforce the support of ‘core supporters’, who are also likely to act as advocates for international development across their peer networks and local communities; (2) we will aim to build confidence among ‘concerned sceptics’ that aid is effective in order to help shift attitudes from scepticism to support.
We have made progress on working with partners to test new content, messaging, channels and different messengers to expand the reach of our content. We are utilising research and best practice from HMG digital specialists to inform our activity, particularly across social media channels. This includes, for example, including more voices of engaging messengers like medics and other frontline workers as well as collaborating with popular and authentic digital influencers with a track record of interest in relevant issues. For example, to mark the UN’s 80th anniversary and reach new audiences, we partnered with influential voices to produce a video explaining the UN’s role in clear, relatable terms. The video was viewed 300x more than typical development content, demonstrating the effectiveness of strategic partnerships with engaging messengers in amplifying reach and impact. We have also begun identifying stories from across FCDO’s development programmes, and secured budget for this financial year to fund a small number of pilot projects to gather stories demonstrating impact told by people, communities and organisations we are supporting, and will distribute these through a range of traditional media, new media and digital channels.
Indicator 1.2: Given the changing operational context and reduction in budget outlined in Section A, alongside agreement to focus on overall public support, we will not directly pursue changes to behaviour as an outcome of this activity. In practice, we judge this will have limited impact on the focus and scope of the programme given the original theory of change assumes behavioural change may follow a shift in public opinion, which we continue to pursue.

Describe any changes to this output during the past year, and any planned changes as a result of this review

Please see the end of this Section.

Output Title	Evidence generated, synthesised, and used to improve understanding of effective development engagement approaches, and events participated in that aim to raise awareness of, and support for international development.
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of research products produced.	Engagement with audience insight experts including pollsters and academic researchers. / Ensure results of independent polling/research is used for achieving programme objectives. / Ensure FCDO insight tools capture UK public perceptions of international development. / Identify research gaps to better understand how to reach and engage the UK public.	Working closely with leading independent researchers (DEL), including Ministerial briefing on latest audience insights. / Inputting messengers to be tested via online panel survey, coordinated by DEL. / Refined development questions as part of routine FCDO UK public perceptions survey. / Convened insight specialists to agree evidence gaps and developed research proposals.
2.2 Number of engagement outreach events participated in.	Scope options for Ministerial and senior official engagement with existing networks and groups. / Build a network of external organisations that will support public engagement activity.	Advice submitted to Ministers detailing opportunities to participate in engagement events. / Convened a meeting of external insight specialists and organisations in the UK development sector that can support public engagement activity.

Briefly describe the output’s activities and provide supporting narrative for the score.

In the context of a significantly reduced budget, we have pivoted to a low/no-cost approach to research and evidence gathering. We have made some progress against the indicators set out above, including building a strong evidence base for our communication approach that we’ll continue to refine as new polling and research is conducted.

Indicator 2.1:
We have drawn on the research of, and developed close working relationships with, independent organisations with expertise in understanding public attitudes to international development.
We have collaborated to test the assumptions and analysis behind our communication approach, including target audiences, messages and messengers. We have also used their analysis to build the understanding of policy and programme teams in the FCDO, and have drawn on it routinely for Ministerial briefings and to draft communication plans.
As part of this work, the programme team delivered a workshop with external communication professionals and insight specialists focused on UK public perceptions. The group will develop and agree a common messaging framework that organisations across the development sector can use to better make the case to the UK public. Once developed, future workshops will include organisations outside the development sector - including but not limited to philanthropy, business, technology and creative industries – to amplify our messaging and expand our reach.
1. We have begun work with insight specialists to test the effectiveness of different messengers for communicating with the public.
2. We have worked with insight leads in FCDO to refine questions on development when gathering insight around international partner perceptions. This data is currently being analysed.
3. As part of the workshop mentioned above (1), we convened insight specialists to agree gaps in the evidence base that will help us better understand public perceptions and engagement approaches. Where gaps were identified, we are commissioning further research to build the evidence base to help support our objectives.

Indicator 2.2:
We have built a network of teams across the FCDO and worked closely with them to scope opportunities for HMG engagement with the aim of amplifying our reach among the target audiences described under Indicator 1.1. Opportunities included participation in outreach events with a broad range of networks and groups representing the target audiences, and drawing on research described under Indicator 2.1.
We will continue to consider opportunities for participating in outreach events, and maintain close relationships with partners and policy teams to identify effective and timely opportunities. We will refresh plans for more strategic and systematic engagement by Ministers and officials.
We have built a network of organisations working directly on public engagement and continue to scope opportunities to collaborate on outreach events to engage with key audiences.

Describe any changes to these outputs during the past year, and any planned changes as a result of this review.

As set out in previous sections, we will revise the theory of change and programme outputs.
We will formalise changes in a business case addendum and log-frame/results framework.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

We have taken an adaptive approach throughout the year in response to the changing operational context, so some of the lessons learned have been covered in sections above.

We’ve found that close collaboration between the Development Strategic Communication team and the UK Development Engagement programme team has been crucial to coordinating activities across workstreams, including ensuring that effective insights and ways of working are communicated and acted on across both teams.

Building awareness and understanding of the new communication approach across HMG teams not working directly on development will be crucial, enabling them to contribute to delivering consistent and effective public messages demonstrating impact, value for money and mutual benefits of international development work. Similarly, to expand public engagement beyond the development sector and beyond audiences that already show strong support, we’ll need to work more closely and consistently with new partners – including philanthropy, business, technology and creative services.
## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost driver is the cost associated with the strategic communication expert. As outlined in Sections B and C, this role has been critical to shifting the FCDO’s communication approach to international development and to shaping a common narrative that makes the case for development in a way that better reaches and engages the UK public.
There is a small additional budget this Financial Year for the creation of communication content, and for research and evaluation. We are in the process of identifying projects that will support the revised focus of the programme and theory of change.

VfM performance compared to the original VfM proposition in the business case

The cost drivers remain valid, including under the revised focus of the programme, and theory of change.
Assessment against the FCDO’s value for money framework:
- Economy – the programme relies on low-cost/no-cost ways to reach the UK public, including tailoring how the FCDO and other Government departments communicate to the UK public and working through partners to engage new audiences. The in-house programme-funded strategic communication expert is considerably more cost-effective than contracting an external agency and allows us to more effectively build the capability of colleagues and embed the new communications approach across the FCDO/HMG.
- Efficiency – the programme’s focus on partnerships means we are able to draw on research funded and produced by independent insight specialists. We have inputted into the surveys and polling conducted by some of these organisations to ensure that we are able to get data that can help inform our communication and engagement approaches, including who the target audiences should be. We have convened organisations within the development sector to agree the target audience, share best practice on the most effective messages and channels, to pool expertise and ideas, and ensure a coordinated approach across the sector.
- Effectiveness – while there has not been an increase in the UK public’s support for international development over the past year, the announcement of ODA cuts in early 2025 did not lead to a decline in support. Furthermore, the new approach to communicating international development is being implemented as standard practice across the FCDO and HMG, and with some implementing partners. We’ll aim to encourage further collaboration with key suppliers. Working with and through partners, sharing learning and securing buy-in for UK development engagement objectives, amplifies the impact of our work and investment.
- Equity – equality impacts are addressed in our communication and engagement activity. Disaggregated data from our partners helps identify target audiences and ensures we are using the right messengers and channels to reach particular groups.
- Cost-effectiveness – through relatively modest investment the programme provides capacity to innovate and flex to meet our objective of increased UK public support for international development.
There was one account of ‘fruitless payment’ made during the first year of just under £5,000. The costs were intended to cover the flights for an FCDO videographer to accompany the Minister on a visit to South Sudan in order to produce local digital content that would support development awareness. As a result of illness during the first leg of the trip the content was not produced and the costs could not be recovered.

Assessment of whether the programme continues to represent value for money

The programme represents value for money. Based on the above, and as set out in section B, we believe there is sufficient justification for the programme to continue in line with the reduced budget and revised focus.

E: RISK

Overview of risk management

The current programme risk rating is major. This has remained steady over the past year with the main pressure points relating to ODA cuts and changes to the overall budget. We have managed this by ensuring we have a clear sense of Ministerial appetite for the objectives of UK development engagement work going forward, and refocusing the scope, budget and intended impact of the programme accordingly.
Risk matrix
Strategy and context	Strategy and context	Policy and programme delivery	Policy and programme delivery	People	Financial and fiduciary	Reputational	Overall
Major	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Major

We have developed a risk register which we monitor regularly, and update every quarter. The main risk to the programme is linked to strategy and context – that financial or political events result in negative media coverage and political debate about the effectiveness and necessity of international development. As a result, it would become harder for the programme to shift public perceptions.
This risk materialised following the decision to reduce the ODA budget to 0.3% of GNI by 2027. While we did not see a decline in overall public support for ODA, 65% of the UK public supported the Government’s decision to increase defence spending by making cuts to overseas aid (results here). To mitigate, we continue to monitor the latest public insights so that our approach to communications and engagement incorporates both public sentiment and their consumption of news and media.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The only contract under the programme is for the strategic communication expert. They were recruited in November 2024 under a two-year agreement. Recruitment complied with FCDO requirements, and performance is reviewed according to FCDO standards. The strategic communication expert is embedded in the International Development Strategic Communication team but is a core member of the UK Development Engagement programme team which means there is regular dialogue on delivery, performance, risks and monitoring.

G: MONITORING, EVIDENCE AND LEARNING

The programme is informed by audience insight research and public polling that measures the UK public’s perceptions of and attitudes towards international development. This is complemented by tracking key performance indicators of communication activity, such as reach, impressions and sentiment. Audience research and polling is conducted by independent external organisations like DEL. We work closely with them and other insight specialists to share data (from online surveys, behavioural research, focus groups, media tracking etc.) and to test ideas on how to reach and influence the UK public. In September 2025 we hosted a workshop with insight specialists and communication professionals to explore strategies for strengthening public support for international development.
By sharing data and research, and by monitoring shifts in public attitudes according to age, gender, region, education and social level, we have been able to refine our approach. Examples of key lessons include refining and segmenting the target audience and identifying the most effective messages, channels and messengers to reach and engage the target audience.
This Annual Review was completed by the PRO and SRO for the programme. The programme-funded strategic communication expert and the previous SRO who set up the programme also inputted.

Date of last narrative financial report	n/a	Date of last audited annual statement	n/a